## Slide 1: sPHENIX Construction Plan
Russell Feder for the sPHENIX Team
Dec 16th, 2020
sPHENIX PMG

## Slide 2: sPHENIX Construction
sPHENIX has all the key components to start construction in late March 21’ and then make good initial progress
  The Cradle-Base is complete at Streck’s
  Outer HCAL sectors 1-13 will be ready for assembly
  The magnet is also generally ready for initial placement
The team is managing procurements and completing design that are critical for the early phase of sPHENIX construction
  The 1008 Assembly Hall track upgrade is the key predecessor to start construction
  Magnet support hardware and the Large Support Ring structures procurement needs to start ASAP
sPHENIX construction planning and safety review in February
  Complete work planning packages for Cradle-Base and Outer HCAL
  Critical lift strategy
Availability of personnel is one key for success
  Continued COVID risk  full technician staff for construction while still supporting oHCAL, EMCAL and iHCAL factories and on going infrastructure work
  Need dedicated (or at least on-call) rigging and metrology. Hours and timing may be unpredictable.
  Project needs to synchronize working schedules and holidays through the 21’-22’ construction period

## Slide 3: sPHENIX Detectors and Magnet Construction Schedule
Sequential Build Steps | Locate | Start | End | CY 2021 |  |  |  | CY 2022 |  |  | 
RHIC Run FY21 |  | 1/30/21 | 7/15/21 |  |  |  |  |  |  |  | 
Cradle-Base | AH | 2/23/21 | 5/17/21 |  |  |  |  |  |  |  | 
Outer HCAL | AH | 6/2/21 | 11/12/21 |  |  |  |  |  |  |  | 
Secure Magnet in oHCAL | AH | 9/14/21 | 9/29/21 |  |  |  |  |  |  |  | 
Large Support Rings | AH | 9/30/21 | 10/6/21 |  |  |  |  |  |  |  | 
Inner HCAL | AH | 11/22/21 | 12/8/21 |  |  |  |  |  |  |  | 
EMCAL | AH | 12/10/21 | 3/14/22 |  |  |  |  |  |  |  | 
Upper Platform, Pole Tips | AH | 11/15/21 | 3/28/22 |  |  |  |  |  |  |  | 
RHIC Run FY22 |  | 11/15/21 | 4/3/22 |  |  |  |  |  |  |  | 
Open Wall and Move to IR | IR | 4/5/22 | 4/20/22 |  |  |  |  |  |  |  | 
Magnet Connect | IR | 4/5/22 | 6/13/22 |  |  |  |  |  |  |  | 
Magnetic field mapping | IR | 6/14/22 | 7/6/22 |  |  |  |  |  |  |  | 
TPC | IR | 7/11/22 | 7/22/22 |  |  |  |  |  |  |  | 
Beam Pipe | IR | 8/1/22 | 8/9/22 |  |  |  |  |  |  |  | 
INTT | IR | 8/16/22 | 8/18/22 |  |  |  |  |  |  |  | 
MVTX | IR | 8/12/22 | 10/3/22 |  |  |  |  |  |  |  | 
MBD | IR | 8/11/22 | 8/29/22 |  |  |  |  |  |  |  | 
ORR | IR | 10/4/22 | 10/31/22 |  |  |  |  |  |  |  | 

## Slide 4: Opportunities in AH phase to complete some steps in parallel
(1) Cradle-Base
(2) oHCAL 1-13
(3) Magnet Part #1
(4) Large Rings
(5) oHCAL 14-32
(6C) iHCAL insert
(8) Upper Pltfrm #1
(7) EMCAL
Move to IR
Magnet Map
TPC
Platforms, INTT, Beam Pipe Supports
Beam Pipe #1
(17) INTT
(18) MVTX
(19) Beam Pipe survey/supports
(20) MBD
(9) Pole Tip Doors
Magnet Cryo, Power
(11) Move to IR
(13) Magnet Mapping
(14) TPC
(15) INTT Support Structure
(12) Magnet Connect
(10) Shield Wall Shuffle
Ongoing AH, IR and other bldg. 1008 infrastructure upgrades and installations
Ongoing AH, IR and other bldg. 1008 infrastructure upgrades and installations
1008 Assembly Hall Work
1008 IR Hall Work
(6A) iHCAL barrel fab
(6B) iHCAL install structures
Ongoing Sub-System Infrastructure and Commissioning
Upper Platform Rack Installation/setup Ongoing
Base Platform Rack Installation/setup Ongoing
Mid Platform Rack Installation/setup Ongoing
(16) Beam Pipe Install/Vacuum
(21) System Integration
Ongoing Sub-System Infrastructure and Commissioning

## Slide 5: sPHENIX Construction Sequence
(1) Cradle Base | (2) oHCAL Sector 1-13 | (3) Magnet Initial Install | (4) Large Support Rings | (5) oHCAL Sector 14-32 | (6) Inner HCAL
(7) EMCAL | (8) Upper Platform | (10) Open Shield Wall | (11) Move sPHENIX to IR | (12) Magnet Connect | (14) TPC Installation
(15) INTT Supports | (16) Beam Pipe Install | (17) INTT Installation | (18) MVTX Supports and MVTX | (19) Secure Beam pipe | (20) MBD
TPC
Results from an sPHENIX OPERA EM FEA
The base will be built on top of the AH rails
Magnet mount hardware is also attached
The magnet is lowered in to the oHCAL bore
The rings also work to stabilize the magnet
The full oHCAL barrel weighs ~480 tons
The iHCAL barrel slides in from the North
There are 64 EMCAL sectors each installed one at a time with a special tool
Work on sPHENIX will stop for the time needed to remove the shield wall
There is a 5-foot move North in the IR
TPC slides in the EMCAL bore from North
MVTX has a 2mm clearance to the beam pipe
Beam pipe is supported temporarily
+MBD supports
iHCAL Barrel fabrication ,AH
(9) Pole Tips
(13) Magnetic Field Mapping
(21) Full System Integration, ORR