Joseph F Muratore

11-Dec-2014

Revised 8-Apr-2015

Revised 13-Apr-2015

sPHENIX Solenoid Magnet Cold Test Plan Summary

A. Electrical Checkout at Room Temperature

1. Measure lead resistances to ground with meter.

2. Hipot to ground at 520 V of magnet leads.

3. Impulse test at 400 V of separate layers and full coil.

4. DC voltage series resistance measurements at 1 A.

5. 1 A level shift test to check data acquisition system.

6. Connect magnet to power supply.

7. Ramp magnet to 2 A (or more if possible - TBD) at 0.1 A/s and measure magnet total

voltage and inner and outer layer voltages in order to determine the inductances.

8. Checkout of Quench Detector (QD) - validate stop signal

a. Half Coil Difference (Δ)– inner and outer layer voltage difference

difference;

b. Current Derivative (Idot)– total coil voltage and L(dI/dt) difference

9. Vacuum leak check of cryostat.

10. Set slow logger for 1 min intervals - monitor LHe level, temperatures, and strains.

11. Notify cryogenics personnel to start cooldown.

B. Cooldown to 4.5 K

C. Electrical Checkout at 4.5 K

1. Measure lead resistances to ground with meter.

2. Hipot to ground at 520 V of magnet leads.

3. AC voltage tap measurements at 1 A.

4. Impulse test at 400 V of separate layers and full coil.

5. Connect magnet to power supply. Use inductance result of Part A.7 as starting point for

power supply regulation.

6. Set fast data logger at 1 kHz sampling rate (1 ms intervals). Slow data logger at 1 s

intervals. Monitor LHe level, temperatures, strains, and voltages of magnet, coils, SC leads,

and gas-cooled leads. Adjust lead flow if necessary.

7. Ramp to 10 A at 1 A/s. Determine the total, inner, and outer inductances and adjust Idot

QD and Delta QD as necessary to balance for the difference in the inner and outer layer

inductances ; determine the Idot QD voltage threshold. Adjust lead flow if necessary.

8. Ramp to 25 A at 1 A/s. Verify results from C.7. Shut off power supply (manual QD trip) and

analyze voltage tap data signals for proper operation of instrumentation and hardware.

Adjust lead flow if necessary.

9. Repeat C.8 at 50 A. Adjust lead flow if necessary.

D. Ramp Testing

Set Delta QD at 50 mV. Set  Idot QD at pre-determined threshold.

Fast data at 1 KHz. Slow logger at 1 s.  1 A/s ramp rate.

1. Ramp to 100 A at 1A/s. Verify inductances. Monitor leads

and adjust flow if necessary. Shut off power supply. Analyze voltage tap data signals.

2. 5 power cycles from 0 A to 100 A at 1 A/s.

3. 1 hour at 100 A. Monitor leads and coil voltages.

4. If no QD trip occurs, warm up magnet to room temperature.

5. If QD trip occurs, analyze voltage tap signals to determine nature of trigger event.

If signals show no anomalies, repeat ramp test to 100 A.

6. When tests have been completed, set slow logger to 1 min. Monitor LHe level,

temperatures, and strains.

7. Notify cryogenics personnel to start warmup to room temperature.

E. Warmup to Room Temperature

Monitor LHe level, temperatures, and strains. Slow logger at 1 min.