## Risks
| Risk Identification | [7 empty] | Primary Risk (Unmitigated Risk Assessment) | [10 empty] | Risk Handling Plan (Mitigations) |  |  |  | Residual Risk (Post- Mitigation Assessment)
Key | Risk ID Number | RLS activity or next WBS | Lab | System | Sequence | Owner | Risk Title | IF/THEN | Likelihood of Impact (%) | Schedule Impact | Technical Impact | Cost Impact Estimate ($K) | Probability Score (1-4) | Cost Score (1-4) | Schedule Score (1-4) | Technical Score (1-4) | Overall Impact Score | EMV K$ | Overall Impact Score | Risk Handling Plan (Mitigations) | Risk Handling Schedule (Triggers, Milestones, Due Dates) | Risk Handling Method | Cost of Mitigations ($K) (Notes OK) | Residual Risk Likelihood of Impact (%) | Residual Schedule Impact | Residual Technical Impact | Low Cost Impact ($K) | Likely Cost Impact ($K) | High Cost Impact ($K) | Low Schedule Impact (Mos) | Likely Schedule Impact (Mos) | High Schedule Impact (Mos) | Probability Score (1-4) | Cost Score (1-4) | Schedule Score (1-4) | Technical Score (1-4) | Overall Impact Score (Calculated) | Overall Impact Score (Residual) | Management Assessment: Overall Impact (Over-Ride) | Expected Value ($K) | Average Expected Value ($K) | Basis of Impact Estimates How were cost and schedule ranges ( Columns Z through AE) developed? | Matrix Code Likelihood | Matrix Code Severity | Risk Burndown Notes | Risk Manager Quantitative Model Notes | Risk Manager Review Questions | Retired Risk Notes Date, Risks Realized, etc.… | Notes | Realized
1 | Mgmt_001 | 101022 | BNL | Management |  | Ed O'Brien | Departure of Key Personnel | If someone critical to the Project informs of his intention to leave sPHENIX, then a replacement needs to be found. | 10% | Moderate |  | 72 | 2 | 2 | 3 | 0 | 3.3333 |  | High | Closely work with sPHENIX collaboration and BNL management to identify and hire a replacement. | T: Someone critical to the Project informs of his intention to leave sPHENIX Dec 2018 Don Lynch retires Jan 2019 Paul Giannotti retires | Mitigate |  | 10% | Moderate |  | 0 | 0 | 0 | 1 | 3 | 6 | 2 | 1 | 3 | 0 | 2.6667 | Moderate |  | 0 | 0 | Impact estimates were approved on Jan 31 2019 based on most recent project experience with fillig out vacancies. Cost impact is considered zero because of the savings during personnel replacement search. | Unlikely | Moderate
2 | Mgmt_002 | 101022 | BNL | Management |  | Ed O'Brien | Safety incident | If safety incident resulting in serious injury and 'Stop Work' protocol initiated at BNL happens, then schedule delay may occur. | 5% | Low |  | 63 | 2 | 2 | 2 | 0 | 2.6667 |  | Moderate | Carefully plan all work in accordance with BNL SBMS. Include safety reviews and safety review recommendations implementation in sPHENIX resource loaded schedule. | T: Safety incident resulting in serious injury and 'Stop Work' protocol occurs at BNL | Mitigate |  | 2% | Low |  | 0 | 0 | 0 | 0.1 | 0.5 | 1 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 | Schedule delay will not have a cost impact because the project has 14 mo of float. | Unlikely | Low
3 | Mgmt_003 | 101010 | BNL | Management |  | Ed O'Brien | Funding profile stretches | If funds are not available on time then procurements will be delayed, resulting in schedule delays and possibly cost increase. | 50% | Low |  | 500 | 3 | 4 | 2 | 0 | 6 |  | High | Work closely with the funding agency so any funding profile changes can be evaluated as early as possible and sPHENIX Project schedule optimally adjusted to match the new funding profile. Since the Project is internally funded through redirect, the mitigation also comes through good communication within BNL management to ensure success. | T: Funds not available on time | Mitigate |  | 10% | Low |  | 0 | 213 | 213 | 0 | 0 | 0 | 2 | 3 | 2 | 0 | 3.3333 | High |  | 21.3 | 14.2 | Cost Impact was assessed for FY20 and FY21 spend profile (using the preliminary baseline), assuming one (likely) or two (worst) quarter funding delay. Further assumption was that delayed procurements would result in 10% cost increase. | Unlikely | High |  |  |  |  | 20-10%, schedule impat Is 0 because will use contingency
4 | Mgmt_004 | S101022 | BNL | Management |  | Ed O'Brien | University Contributed Labor for sPHENIX | If sPHENIX loses University contributing labor, then there will be a loss of progress on the specific detector to which the university was contributing labor and need to replace this effort either by recruiting another university to the tasks or hiring the needed skill sets. | 4% | Low |  | 3900 | 2 | 4 | 2 | 0 | 4 |  | High | Informing DOE-ONP about scale and duration of efforts planned by all the various universities on sPHENIX. Recruitment of other sPHENIX collaborating institutions if a given University cannot continue. Maintain contact with other NP/HEP groups capable of such work if a paid contract must be placed. Cost and schedule impacts will be reduced as individual work activities are completed. | T: Loss of a University contributing labor to the sPHENIX project | Mitigate |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Jan 31 2019. Nine new risks (one per each participating University) replace this one. CAMs will own the respective University labor related risks. |  | yes
5 | Mgmt_005 | 101022 | BNL | Management |  | Ed O'Brien | Schedule Delay | If Planned Early Completion moves out past Baseline Early Completion milestone, then Project L1 Milestone 'Early Project Completion' is not achieved | 30% | Low |  | 13 | 3 | 1 | 2 | 0 | 3 |  | Moderate | Reserve contingency throughout project for covering schedule delay. | After PD-2 approval monitor cost contingency using the baseline change control and schedule contingency using the RLS in P6. Reassess residual risk parameters monthly and approve any changes by the RMB. |  |  | 0% | Low |  | 0 | 0 | 46 | 0 | 0.5 | 1 | 0 | 1 | 2 | 0 | 0 | Not Residual |  | 0 | 0 | We assume that there is a 10% chance of a month delay beyond 'Early Project Completion' milestone. The probability went down from 30% because of the project's success with prototypes. In case of such a delay we estimate the 'standing army' cost for the BNL contributed labor and supplies is 25, 872 per month. Estimated Resources: Scientist Managing 50% | Not Residual | Not Residual |  |  |  | Retired. All delays are assigned to WBS 1.2-1.7 |  | no
6 | Mgmt_006 | 1.01 | BNL | Management |  | Ed O'Brien | Infrastructure support delayed | If an Infrastructure/Installation Milestone is delayed, then Project activities dependent on Infrastructure milestone are delayed | 5% | Low |  | 0 | 2 | 1 | 2 | 0 | 2 |  | Low | Develop a detailed resource loaded schedule with key milestones for Infrastructure support and closely monitor this schedule for risk triggers. |  |  |  | 0% | Low | [7 empty] | 0 | 0 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Jan 31 2019. sPHENIX MIE does not include installation, so the installation-related risks will be tracked in sPHENIX Support. |  | no
7 | Mgmt_007 | 101022 | BNL | Management |  | Ed O'Brien | Major Vendor Failure | If a major vendor fails to deliver, a different vendor will be needed and that can increase the cost and delay the schedule. | 5% | Low |  | 0 | 2 | 1 | 2 | 0 | 2 |  | Low | Develop a detailed resource loaded schedule with key milestones for Infrastructure support and closely monitor this schedule for risk triggers. |  |  |  | 0% | Moderate |  | 1000 | 1000 | 1000 | 0 | 2 | 3 | 0 | 4 | 3 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Jan 31 2019. sPHENIX MIE does not include installation, so the installation-related risks will be tracked in sPHENIX Support. |  | no
8 | Mgmt_008 | 101022 | BNL | Management |  | Ed O'Brien | COVID-19 delays | If the Project experiences COVID-19 delays, then additioanal labor will be needed and that will increase the cost. | [10 empty] | Not Primary | Work with BNL management and implement all COVID safety protocols. |  |  |  | 50% | Moderate |  | 200 | 300 | 400 | 2 | 4 | 6 | 3 | 4 | 3 | 0 | 7 | High |  | 150 | 150 | Cost was estimated based on TECH3 labor hours and rates. Schedule delays were estimated based on production EMCal and Hcal schedules. | Possible | High | [5 empty] | no
9 | sPH_TPC_001 | 112100 | BNL | TPC |  | Tom Hemmick | Performance failure of v2 prototype | If the v2 prototype fails, then there will need to be a v3 prototype added to the cycle. | 5% |  |  | 150 | 2 | 3 | 0 | 0 | 2 |  | Low | We will add a design cycle of a smaller device than the full sized field cage if the v1 prototype fails. We will proceed on v2 only after success of the small version. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Jan 31 2019. This risk is retired since Field Cage v2 prototype production is in the RLS. |  | no
10 | sPH_TPC_002 | 112100 | BNL | TPC |  | Tom Hemmick | Success of v1 field cage prototype | Cost savings due to skipping the v2 step. No schedule impact since the v2 field cage is not on the critical path. | 50% | Negligible |  | 150 | 3 | 3 | 1 | 0 | 4 |  | High | This is an opportunity so no mitigation is required. |  |  |  | 0% | Negligible |  | -150 | -150 | -150 | -4 | -4 | -4 | 0 | 1 | 1 | 0 | 0 | Not Residual |  | 0 | 0 | Cost and schedule impact are based on the RLS where V2 Field Cage prototype step would be unnecessary in case of V1 success. | Not Residual | Not Residual |  |  |  | Opportunity realized. Retired December 2020. |  | yes
11 | sPH_TPC_003 | 1.02 | BNL | TPC |  | Tom Hemmick | Failure or delay of CERN production | If factories wait upon GEM foil delivery and suffer schedule shifts, then the factory production of modules is critical path and will directly affect schedule. | 10% |  |  | 174 | 2 | 3 | 0 | 0 | 2 |  | Low | We will monitor carefully the success of CERN foil production and will hire a technician who will exclusively work on producing GEM foils for our Project. If delays still occur, we will seek a second vendor. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired based on production status. |  | no
12 | sPH_TPC_004 | 139000 | BNL | TPC |  | Tom Hemmick | SAMPA Chip 80 nsec development | If SAMPA chip modification to include 80 nsec option (by eliminating 320 nsec option) fails to work effectively, then the TPC will have to default to using the 160 nsec option which may effect rate capability, but not affect performance of the TPC using moderate rates. | 33% | Negligible |  | 180 | 3 | 3 | 1 | 0 | 4 |  | High | An additional design cycle shall be added. |  |  |  | 0% | Low |  | 147 | 170 | 215 | 4 | 5 | 7 | 0 | 3 | 2 | 0 | 0 | Not Residual |  | 0 | 0 | Low cost, schedule impact: Very minor error was found for the full SAMPA chip. In this case, the design change can be done in 1-week or so. Mandatory time for design adjustment in negotiation with the chip company is estimated as 1 month, followed by the chip production time of 3-months. $125K for chip production and $22K for 1-month design workforce Activities to be recycled: S139600 (1 month out of this) S140200,S140300,S140400 ($125K out of this) Likely cost, schedule impact: Some minor errors were found for the full SAMPA chip. In this case, the design change may take 1-month. Mandatory time for design adjustment in negotiation with the chip company is estimated as 1 month, followed by the chip production time of 3-months. $125K for chip production and $45K for 2-month design workforce. Activities to be recycled: S138900 (1 month out of this) S139600 (1 month out of this) S140200,S140300,S140400 ($125K out of this) High cost, schedule impact: Major issues were found already at prototype chip which is before the full SAMPA chip. In this case, we should try to find the solution to the issues by prototype test (additional 1-month), implement in the full SAMPA chip design and go for the full SAMPA chip production. If the full SAMPA chip was not successful, we have to go for another thorough design cycle (2-month). Mandatory time for design adjustment in negotiation with the chip company is estimated as 1 month, followed by the chip production time of 3-months. $125K for chip production and $90K for 4-month design workforce. Activities to be recycled: S138600 (1 month out of this) S138900 (2 month out of this) S139600 (1 month out of this) S140200,S140300,S140400 ($125K out of this) | Not Residual | Not Residual |  |  |  | Retired on Apr 27 2020. Based upon results measured over multiple chips, we have declared the chip as having met or surpassed our requirements. |  | no
13 | sPH_TPC_005 | 1.02 | BNL | TPC |  | Tom Hemmick | Currency fluctuation on TPC GEMs contract with CERN | If US to Swiss Franc exchange rate goes up, then cost to produce TPC GEMs at CERN goes up. | 10% |  |  | 174 | 2 | 3 | 0 | 0 | 2 |  | Low | Accept this risk since nothing can be done to mitigate it. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Not Residual | Not Residual |  |  |  | Retired on Jan 31 2019. Currency fluctuations can go both ways and there is no reason to expect that Swiss franc will go up against the US dollar in near future. |  | no
14 | sPH_TPC_006 | 125500 | BNL | TPC |  | Tom Hemmick | Wayne State Students Unavailable (R1 Modules) | If student labor unavailable at Wayne State University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 |  | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of Wayne State students in December 2019 |  |  | 0% |  |  | 0 | 0 | 428 | 3 | 6 | 6 | 0 | 1 | 0 | 0 | 0 | Not Residual |  | 0 | 0 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Not Residual | Not Residual |  |  |  | Retired. Paid TECH labor is in the RLS. |  | no
15 | sPH_TPC_007 | 129500 | BNL | TPC |  | Tom Hemmick | Vanderbilt Students Unavailable (R2 Modules) | If student labor unavailable at Vanderbilt University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 |  | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of Vanderbilt students in December 2019 |  |  | 0% |  |  | 0 | 0 | 428 | 3 | 6 | 6 | 0 | 1 | 0 | 0 | 0 | Not Residual |  | 0 | 0 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Not Residual | Not Residual |  |  |  | Retired May 2021. GEM production is complete. Risk did not realize. |  | no
16 | sPH_TPC_008 | 133700 | BNL | TPC |  | Tom Hemmick | Temple Students Unavailable (R3a Modules) | If student labor unavailable at Temple University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 |  | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of Temple students in December 2019 |  |  | 0% |  |  | 0 | 0 | 428 | 3 | 6 | 6 | 0 | 1 | 0 | 0 | 0 | Not Residual |  | 0 | 0 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Not Residual | Not Residual |  |  |  | Retired May 2021. GEM production is complete. Risk did not realize. |  | no
17 | sPH_TPC_009 | 134000 | BNL | TPC |  | Tom Hemmick | Weizmann Students Unavailable (R3b Modules) | If student labor unavailable at Weizmann University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 |  | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of Weizmann students in December 2019 |  |  | 0% |  |  | 0 | 0 | 428 | 3 | 6 | 6 | 0 | 1 | 0 | 0 | 0 | Not Residual |  | 0 | 0 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Not Residual | Not Residual |  |  |  | Retired May 2021. GEM production is complete. Risk did not realize. |  | no
18 | sPH_TPC_010 | 112900 | BNL | TPC |  | Tom Hemmick | SUNY Stony Brook Staff and/or Students Not Available (TPC) | If detector-scientist, engineering and/or student labor unavailable to prepare prototype and production TPC field cage, TPC mechanics, HV and gas system and to contribute to TPC laser and DAM, and to perform final TPC assembly and testing, then new staff would need to be hired at SUNY Stony Brook, leading to schedule delay, or a technician would have to be hired to replace student labor, leading to cost and schedule delay. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 |  | Moderate | SUNY Stony Brook recruitment of professional and student staff as part of ongoing contract. Maintain contact with other NP/HEP groups with appropriately-skilled detector-scientists. Maintain contact with technicians if one must be hired on short notice to hold schedule in absence of students. Cost and schedule impacts will be reduced as individual work activities are completed. | Get a list of Stony Brook students in December 2019 |  |  | 0% |  |  | 40 | 60 | 80 | 3 | 6 | 8 | 0 | 2 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Realized, PCR017 Nov 2020. | $100K, $20K higher that estimated | yes
19 | sPH_TPC_011 | 133700 | BNL | TPC |  | Tom Hemmick | Delay of GEM production | If student labor unavailable at Weizmann University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible | [8 empty] | Not Primary | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. |  |  |  | 0% |  |  | 0 | 0 | 0 | 2 | 3 | 6 | 0 | 1 | 0 | 0 | 0 | Not Residual |  | 0 | 0 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Not Residual | Not Residual |  |  |  | Retired May 2021. GEM production is complete. Risk did not realize. |  | no
20 | sPH_TPC_012 | 134000 | BNL | TPC |  | Tom Hemmick | Insufficient Laser Power for Diffuse Illumination | If the TPC laser power is not enough for diffuse illumination, then additional lasers will be needed and that means additional cost. | 15% | Negligible | [8 empty] | Not Primary | Keep track of latest design. |  |  |  | 0% |  |  | 140 | 140 | 140 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Realized, PCR017 Nov 2020. | $200K, $60K higher that estimated | yes
| sPH_TPC_013 | [5 empty] | TPC FEE assembly is late | If TPC FEE assembly rate is lower than planned, then TPC FEE assembly could be behind schedule up to 3 mo. | [11 empty] | Check P6 progress schedule monthly |  |  |  | 10% |  |  | 0 | 0 | 0 | 1 | 2 | 3 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 0 | Based on latest experience
| sPH_TPC_014 | [5 empty] | TPC assembly is late | If TPC assembly rate is lower than planned, then TPC assembly could be behind schedule up to 3 mo. | [11 empty] | Check P6 progress schedule monthly |  |  |  | 10% |  |  | 0 | 0 | 0 | 1 | 2 | 3 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 0 | Based on latest experience
| sPH_TPC_015 | [5 empty] | TPC Lasers | If fiberoptic cable has to be 18 m long, then more diffuse lasers will be needed. | [11 empty] | Keep track of latest design. |  |  |  | 50% |  |  | 20 | 40 | 80 | 0 | 1 | 1 | 3 | 2 | 0 | 0 | 2 | Low |  | 20 | 23.3333 | Based on latest experience
| sPH_TPC_016 | [5 empty] | TPC FPGA replacement | If the project needs to change FPGA vendor, the purchase will cost more | [11 empty] | Keep track of FPGA procurement. |  |  |  | 100% |  |  | 100 | 100 | 100 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 2.6667 | Moderate |  | 100 | 100 | Based on latest experience
21 | sPH_EMCal_001 | 1.03 | BNL | EMCal |  | Craig Woody | Tungsten powder cost go up | If there is a failure of the primary supplier of W powder (Tungsten Heavy Powder) to sign a contract and deliver the powder for the final block production at an affordable price, then | 50% |  |  | 332 | 3 | 4 | 0 | 0 | 4 |  | High | We have identified another supplier (Starck) that we feel can deliver powder that can meet our specs at roughly 2/3 the THP price. Preliminary tests of samples of their powder appear to have adequate density. Further tests are being planned to build and test a number blocks (~10) using their powder and measure their performance. |  |  |  | 0% |  |  | 0 | 80 | 160 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. UIUC placed 2 contracts with Starck in April 2018 and Oct 2019, got both delivered. |  | no
22 | sPH_EMCal_002 | 1.03 | BNL | EMCal |  | Craig Woody | Loss of SciFi supplier | If there is a failure of fiber vendor to sign a contract or deliver fiber on time, then that will cause a delay in the schedule and result in higher cost for the fiber | 10% |  |  | 868 | 2 | 4 | 0 | 0 | 2.6667 |  | Moderate | There are only two vendors capable of supplying fibers that will meet our specs, Saint-Gobain and Kuraray. We have built and tested blocks made with fibers from both vendors. If the Saint-Gobain cannot deliver the fiber for the price they quoted and on the time scale we require, we would have to purchase the fiber from Kuraray and pay the higher price. The production of sectors 0-12 will test whether Saint-Gobain can deliver the fiber on time and within budget. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Jan 22 2019 (PO 359217) |  | no
23 | sPH_EMCal_003 | 1.03 | BNL | EMCal |  | Craig Woody | Loss of primary production site for blocks (University of Illinois Urbana Champaign) | If UIUC decides to not fabricate the absorber blocks, then there will be a delay in EMCal schedule and a significant increase in labor resources required to build the blocks at BNL or another collaborating institution, unless the outside institution provides the labor as an in-kind contribution to sPHENIX. | 5% | Negligible |  | 300 | 2 | 4 | 1 | 0 | 3.3333 |  | High | Several Chinese institutions have recently joined sPHENIX which have expressed interest in contributing to the EMCAL project and have the capability to produce the blocks. There will be a meeting in China in April 2018 to discuss this. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 | Best case: move effort to another University, Likely: add new University. Worst: absorb the effort into BNL: 15,333 h to TECH3 PO M (includes escalation) | Not Residual | Not Residual |  |  |  | Retired based on production status. |  | no
24 | sPH_EMCal_004 | 178100 | BNL | EMCal |  | Craig Woody | Delay of EMCal block production at UIUC due to component supplies or technical issues | If EMCal Block production rate is not on schedule, then there will be a delay in EMCal schedule. | 25% | Negligible |  | 50 | 3 | 2 | 1 | 0 | 3 |  | Moderate | Add shifts or additional production when supplies are available or technical issues are resolved. Schedule early purchase & delivery of W powder, fibers, screens, epoxy . Monthly labor rate at UIUC is $7500/sector. |  |  |  | 10% | Low |  | 0 | 0 | 0 | 0.2 | 0.5 | 1 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 | Estimates based on experience with other projects | Unlikely | Low
25 | sPH_EMCal_005 | 196500 | BNL | EMCal |  | Craig Woody | Delay of EMCal module production or sector assembly rate due to component supplies or technical issues | If EMCal module production/assembly rate is not on schedule, then there will be a delay in EMCal schedule. | 40% | Negligible |  | 30 | 3 | 2 | 1 | 0 | 3 |  | Moderate | Add shifts or additional production when supplies are available or technical issues are resolved. Store partially assembled sectors until they can be completed. Use planned sector storage time as float. Rate for hiring a job shopper is ~$30/hour. However, If we cannot find all the primary labor for the module and sector factories from the BNL labor pool, we would need to hire new technicians for roughly one year. This would be result in an additional cost of ~ $100K/technician/year. |  |  |  | 10% | Low |  | 0 | 0 | 0 | 0.2 | 0.5 | 1 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 | Estimates based on experience with other projects | Unlikely | Low
26 | sPH_EMCal_006 | 1.03 | BNL | EMCal |  | Craig Woody | EMCal Preproduction sectors do not meet production specs | If Preproduction EMCal sectors fail testing, then EMCal Sector components need replacements or/and assembly steps need rework. | 30% |  |  | 58 | 3 | 2 | 0 | 0 | 2 |  | Low | It is likely that during the assembly of the first sectors we will need to tune and modify our fixtures and procedures. By pre-assembling, before epoxying parts together we can minimize any irreversible errors. Some re-working and testing will likely be required as part of the production. If additional blocks are needed, they can be added to the end of the block production run. |  |  |  | 0% |  |  | 0 | 0 | 0 | 0.5 | 1 | 4 | 0 | 1 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Mar 22 2019. |  | no
27 | sPH_EMCal_007 | 174700 | BNL | EMCal |  | Craig Woody | Labor and M&S estimates low and more of each is needed to stay on schedule | If EMCal Block production is not on schedule, then there will be a delay in EMCal schedule and increased cost. | 15% | Low |  | 169 | 3 | 3 | 2 | 0 | 5 |  | High | Add an additional UIUC TECH3 to the fiber filling team (205h x $76/h x .75 = $24k) and to the block production team(50h/sector x 51 sectors x $76/h x 0.75 = $145k |  |  |  | 0% | Low |  | 300 | 300 | 300 | 0.25 | 0.5 | 1.5 | 0 | 4 | 2 | 0 | 0 | Not Residual |  | 0 | 0 | Add an additional UIUC TECH3 to the fiber filling team (205h x $76/h x .75 = $24k) and to the block production team(50h/sector x 51 sectors x $76/h x 0.75 = $145k | Not Residual | Not Residual |  |  |  | Realized, PCR017 Nov 2021 | $460K, $160K higher than estimated | yes
28 | sPH_EMCal_008 | 1.03 | BNL | EMCal |  | Craig Woody | Loss of Epoxy supplier | If current vendor stops producing the epoxy we have chosen, or we lose the manufacturer/vendor, or experience delivery delays, then we would have to find an alternative product, either from the same manufacturer or from another manufacturer, resulting in a schedule delay. | 10% |  |  | 6 | 2 | 1 | 0 | 0 | 0.66667 |  | Negligible | An alternative epoxy would need to be tested to be sure that it infuses the tungsten powder and doesn't affect the fiber light output. $6k for 1 week of technician time plus cost of epoxy samples and test materials. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Feb 20 2019. Successful preproduction contract and more than one supplier identified. |  | no
29 | sPH_EMCal_009 | 172800 | BNL | EMCal |  | Craig Woody | UIUC students not available for EMCal Fiber Assemblies | If UIUC students are not available for fiber assemblies, then there will be a delay in EMCal schedule and increased cost. | 0% |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  | Not Primary | Get a list of participating students from collaboration institutions at least 3 months before activity begins. | Get a list of students in late Spring 2019 |  |  | 5% | Negligible |  | 0 | 100 | 0 | 3 | 6 | 6 | 2 | 2 | 1 | 0 | 2 | Low |  | 5 | 1.6667 | Best: move effort to another University Likely: add new University Worst: absorb the effort into BNL. 15,333 h to TECH3 PO M (includes escalation) | Unlikely | Low | Prob. Changed to 5% from 10% May 2021
30 | sPH_EMCal_010 | 178100 | BNL | EMCal |  | Craig Woody | UIUC students not available for EMCal Final Block Fabrication | If UIUC students are not available for block fabrication, then there will be a delay in EMCal schedule and increased cost. | 0% |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  | Not Primary | Get a list of participating students from collaboration institutions at least 3 months before activity begins. | Get a list of students in February 2020 |  |  | 10% | Moderate |  | 0 | 0 | 0 | 3 | 6 | 6 | 2 | 1 | 3 | 0 | 2.6667 | Moderate |  | 0 | 0 | Best: move effort to another University Likely: add new University Worst: absorb the effort into BNL. 135h*52 to TECH3 PO M (includes escalation) | Unlikely | Moderate | Prob. Changed to 10% from 20% May 2021
31 | sPH_EMCal_011 | 196500 | BNL | EMCal |  | Craig Woody | Loss of Students for Sector testing | If UIUC students are not available for sector testing, then there will be a delay in EMCal schedule and increased cost. | 10% | Moderate |  | 6 | 2 | 1 | 3 | 0 | 2.6667 |  | Moderate | Get a list of participating students from collaboration institutions at least 3 months before activity begins. | Get a list of students in late Spring 2020 |  |  | 10% | Moderate |  | 0 | 0 | 200 | 1 | 3 | 6 | 2 | 1 | 3 | 0 | 2.6667 | Moderate |  | 0 | 6.6667 | Estimates based on experience with other projects | Unlikely | Moderate | Prob. Changed to 20% from 40% May 2021
| sPH_EMCal_013 | [5 empty] | EMCal Sector Assembly is late due to shortage of TECH labor | If sector assembly rate is low, we will need more TECH labor | [11 empty] | Monitor sector assembly rate closely. |  |  |  | 30% |  |  | 0 | 100 | 100 | 1 | 2 | 3 | 3 | 2 | 0 | 0 | 2 | Low |  | 30 | 20 | Based on latest experience
32 | sPH_EMCal_012 | 196500 | BNL | EMCal |  | Craig Woody | Tech labor for EMCal Sectors | If UIUC students are not available for sector assembly, then there will be a delay in EMCal schedule and increased cost. | [15 empty] | 0% | Moderate |  | 150 | 300 | 450 | 1 | 3 | 6 | 0 | 4 | 3 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Risk Realized. PCR021
| sPH_EMCal_014 | [5 empty] | TECH Labor at UIUC for EMCal blocks | If rate of machining blocks is low, we will need another machinist at UIUC | [11 empty] | Monitor block machining rate closely. |  |  |  | 50% |  |  | 0 | 200 | 200 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | High |  | 100 | 66.6667 | Based on latest experience
33 | sPH_HCal_001 | 208100 | BNL | HCal |  | John Lajoie | Loss of scintillating tile provider (Uniplast) | If Uniplast is unable to engage in or complete the production contract, then schedule delay in the procurement of the scintillating tiles, along with correspond delays in inner and outer HCAL assembly. | 10% | Moderate |  | 2380 | 2 | 4 | 3 | 0 | 4.6667 |  | High | Explore alternate scintillator vendors (FNAL, Eljen). Detailed risk analysis here: https://docdb.sphenix.bnl.gov/cgi-bin/private/ShowDocument?docid=111 | Mar 12 2019: Residual risk probability reduced from 10% to 7% on the basis of placing a contract at GSU. |  |  | 0% | Moderate |  | 0 | 160 | 160 | 0 | 12 | 12 | 0 | 3 | 3 | 0 | 0 | Not Residual |  | 0 | 0 | Details documented here: https://docdb.sphenix.bnl.gov/cgi-bin/private/ShowDocument?docid=111 | Not Residual | Not Residual |  |  |  | Retired December 2020. |  | no
34 | sPH_HCal_002 | 1.04 | BNL | HCal |  | John Lajoie | Some pre-production scintillating tiles do not meet production specifications. | If testing of pre-production outer HCAL scintillating tiles indicates that some fraction do not meet specifications, then then this may cause a delay in the full production to make up the loss. | 10% |  |  | 26 | 2 | 2 | 0 | 0 | 1.3333 |  | Low | Test scintillating tiles at supplier as part of production, and again upon receipt at BNL. This will catch any problems as quickly as possible so they can be remediated quickly as part of the pre-production. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Apr 3 2019. |  | no
35 | sPH_HCal_003 | 208400 | BNL | HCal |  | John Lajoie | Georgia State U Staff and/or Students Not Available for HCal scin. tiles testing | If student labor is unavailable for HCal scintillating tile or HCal sector assembly and testing, then a technician would need to be hired to replace students. | 0% |  |  | 150 | 0 | 3 | 0 | 0 | 0 |  | Not Primary | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of students in Summer 2019. |  |  | 0% | Low |  | 0 | 0 | 72 | 1 | 2 | 2 | 0 | 1 | 2 | 0 | 0 | Not Residual |  | 0 | 0 | Best: ISU takes over Likely: add new OHCal University Worst: absorb the effort into BNL. 1300 h from Student to TECH3 PO M | Not Residual | Not Residual |  |  |  | Retired December 2020. |  | no
36 | sPH_HCal_004 | 210000 | BNL | HCal |  | John Lajoie | Georgia State U Staff and/or Students Not Available for HCal sector assembly and testing | If student labor is unavailable for HCal scintillating tile or HCal sector assembly and testing, then a technician would need to be hired to replace students. | 15% |  |  | 150 | 3 | 3 | 0 | 0 | 3 |  | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of students in late Spring 2020 |  |  | 0% | Low |  | 0 | 0 | 648 | 0 | 2 | 4 | 0 | 1 | 2 | 0 | 0 | Not Residual |  | 0 | 0 | Best: ISU takes over Likely: add new OHCal University Worst: absorb the effort into BNL. 1300 h from Student to TECH3 PO M | Not Residual | Not Residual |  |  |  | Retired March 2021. Hcal Sector assembly is complete.
| sPH_Hcal_005 | [5 empty] | Delay of Inner HCAL assembly due to technical or component supply issues | If HCal components are not available on time, then the assembly of the inner HCAL barrel and installation into sPHENIX will be delayed. | [11 empty] | Carefully plan delivery and availability of all components. |  |  |  | 25% |  |  | 0 | 0 | 0 | 0.5 | 1 | 2 | 3 | 1 | 0 | 0 | 1 | Negligible |  | 0 | 0 | Schedule impact estimates made assuming delay in sector delivery (last 8) and time to machine and assemble.
37 | sPH_CalEl_001 | S195200 | BNL | CalEl |  | Eric Mannel | Delay in SiPM Delivery | If OPC SiPM order is not placed on schedule or vendor is unable to meet production schedule, then there will be a delay in assembly of HCal and EMCal SiPM daughter boards and a potential delay in HCal and EMCal module assembly. | 15% |  |  | 11 | 3 | 1 | 0 | 0 | 1 |  | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO ) |  | no
38 | sPH_CalEl_001_a | 1.05 | BNL | CalEl |  | Eric Mannel | Delay in SiPM Delivery | If TEC SiPM order is not placed on schedule or vendor is unable to meet production schedule, then there will be a delay in assembly of HCal and EMCal SiPM daughter boards and a potential delay in HCal and EMCal module assembly. | 15% |  |  | 11 | 3 | 1 | 0 | 0 | 1 |  | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 |  | no
39 | sPH_CalEl_002 | 1.05 | BNL | CalEl |  | Eric Mannel | Delay in testing of SiPMs | If SiPM Delivery not placed on schedule, vendor delay, or collab. institution unable to meet production schedule, then there will be a delay in assembly of HCal and EMCal SiPM daughter boards and a potential delay in HCal and EMCal module assembly. | 20% |  |  | 11 | 3 | 1 | 0 | 0 | 1 |  | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 |  | no
40 | sPH_CalEl_003 | 1.05 | BNL | CalEl |  | Eric Mannel | Delay in Assembly of HCal Daughter boards, Preamps, Interface boards, LED Drivers | If Procurement of components for HCal and issuing of orders are late, then this will delay HCal module assembly and testing | 20% |  |  | 25 | 3 | 1 | 0 | 0 | 1 |  | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO ) |  | no
41 | sPH_CalEl_004 | 1.05 | BNL | CalEl |  | Eric Mannel | Delay in assembly of EMCal Daughter boards, Preamps or Interface boards | If Procurement of components for EMCal and issuing of orders are late, then this will delay EMCal module assembly and testing | 20% |  |  | 25 | 3 | 1 | 0 | 0 | 1 |  | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO ) |  | no
42 | sPH_CalEl_005 | 1.05 | BNL | CalEl |  | Eric Mannel | Foreign Procurement of SiPMs | If Change in procurement costs/delivery schedule, then SiPM procurement cost goes up. | 50% |  |  | 43 | 3 | 2 | 0 | 0 | 2 |  | Low |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Jan 31 2019 Risk did not realize. Order with Hamamatsu has been placed, foreign vendor uncertainty no longer applies. |  | no
43 | sPH_CalEl_006 | 1.05 | BNL | CalEl |  | Eric Mannel | Hamamatsu declines to bid/Alternative vendor | If Hamamatsu declines to bid, then we will find a different vendor | 10% |  |  | 100 | 2 | 2 | 0 | 0 | 1.3333 |  | Low |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Jan 31 2019 Risk did not realize. Order with Hamamatsu has been placed. |  | no
44 | sPH_CalEl_007 | 230200 | BNL | CalEl |  | Eric Mannel | U. Michigan Staff and/or Students Unavailable (Cal FEE/SiPM) | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then technicians will be hired | 15% |  |  | 100 | 3 | 2 | 0 | 0 | 2 |  | Low |  |  |  |  | 0% | Low |  | 0 | 0 | 107 | 1 | 2 | 2 | 0 | 1 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired. |  | no
45 | sPH_CalEl_008 | 1.05.02.02 | BNL | CalEl |  | Eric Mannel | EMCal electronics component prices go up | If EMCal electronics component prices go up, then there will be additional costs | [8 empty] | 0 |  | Not Primary |  |  |  |  | 0% | Low |  | 161 | 161 | 161 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired. |  | no
46 | sPH_CalEl_009 | 229300 | BNL | CalEl |  | Eric Mannel | EMCal electronics components procurement is late | If EMCal electronics components are late, then there will be schedule delays up to 6 mo | [8 empty] | 0 |  | Not Primary |  |  |  |  | 0% | Low |  | 0 | 0 | 0 | 1 | 3 | 6 | 0 | 1 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | All components for EMCal and HCal other than external cables have been delivered. The risk has been replaced with sPH_CalEl_015 |  | yes
47 | sPH_CalEl_010 | 240600 | BNL | CalEl |  | Eric Mannel | HCal electronics component prices go up | If Hcal electronics component prices go up, then there will be additional costs | [8 empty] | 0 |  | Not Primary |  |  |  |  | 0% | Low |  | 161 | 161 | 161 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired. |  | no
48 | sPH_CalEl_011 | 252900 | BNL | CalEl |  | Eric Mannel | HCal electronics components procurement is late | If HCal electronics components are late, then there will be schedule delays up to 6 mo | [8 empty] | 0 |  | Not Primary |  |  |  |  | 0% | Low |  | 0 | 0 | 0 | 1 | 3 | 6 | 0 | 1 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | All components for EMCal and HCal other than external cables have been delivered. The risk has been replaced with sPH_CalEl_015 |  | yes
49 | sPH_CalEl_012 | 252700 | BNL | CalEl |  | Eric Mannel | Digitizer component prices go up | If digitizer components cost more, then there will be additional costs | [8 empty] | 0 |  | Not Primary | Accept |  |  |  | 70% | Low |  | 117 | 117 | 117 | 0 | 0 | 0 | 4 | 3 | 2 | 0 | 6.6667 | High |  | 81.9 | 81.9 | Based on the BOE and remaining work | Very Likely | High
50 | sPH_CalEl_013 | 1.05.02.04 | BNL | CalEl |  | Eric Mannel | Digitizer components procurement is late | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then schedule delays up to 6mo are possibel | [8 empty] | 0 |  | Not Primary | Work with participating University to monitor student availability |  |  |  | 10% | Low |  | 0 | 0 | 0 | 1 | 3 | 6 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 | Based on most recent experience | Unlikely | Low
51 | sPH_CalEl_014 | 1.05.02.04 | BNL | CalEl |  | Eric Mannel | EMCal, Hcal signal/power cables cost more | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then | [10 empty] | Not Primary |  |  |  |  | 0% | Low |  | 800 | 800 | 800 | 1 | 3 | 6 | 0 | 4 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Realized, PCR017 Nov 2021 | $800K, exactly the estimate | yes
| sPH_CalEl_015 | [5 empty] | External cables delivery is delayed | If cables are late, then there will be schedule delays up to 6 mo | [11 empty] | Work with BNL procurement, maintain Critical Procurement list for POB |  |  |  | 25% | Low |  | 0 | 0 | 0 | 1 | 3 | 6 | 3 | 1 | 2 | 0 | 3 | High |  | 0 | 0 | Based on most recent experience
52 | sPH_DAQ&Tr_001 | 257000 | BNL | DAQ&Trigger |  | Martin Purschke | DAQ Prototype does not meet specifications | If tests with the various prototype stages reveal problems, then DAQ prototype throughput and performance is below specifications | 10% |  |  | 10 | 2 | 1 | 0 | 0 | 0.66667 |  | Negligible | Acquire more or more expensive PCs |  |  |  | 5% |  |  | 10 | 35 | 74 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1.3333 | Low |  | 1.75 | 1.9833 | Expert estimate | Unlikely | Low
53 | sPH_DAQ&Tr_002 | 1.06 | BNL | DAQ&Trigger |  | Martin Purschke | Global Lvl1 expert not available | If we lose engineering expertise due to employees leaving, then adaptation of PHENIX GL1 runs into obstacles. | 10% |  |  | 0 | 2 | 1 | 0 | 0 | 0.66667 |  | Negligible | Select different card, identify a different BNL engineer |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Jan 31 2019. Risk did not realize. The design is ready. |  | no
54 | sPH_DAQ&Tr_003 | 1.06 | BNL | DAQ&Trigger |  | Martin Purschke | Timing System technology still not finalized | If legacy systems using the obsolete GLink protocol need to be changed, then conversion/adaptation from GLINK problematic, or envisioned replacement board cannot be used | 40% |  |  | 0 | 3 | 1 | 0 | 0 | 1 |  | Negligible | Meet with experts to down select technology; select different card and/or re-engineer fiber interface |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Dec 17 2018. We have already procured the GL1 and GTM units that we believe are the final ones. |  | no
55 | sPH_DAQ&Tr_004 | 1.06 | BNL | DAQ&Trigger |  | Martin Purschke | Local LVL1 implementation runs into obstacles | If simulations reveal the failure of an envisioned algorithm, then performance of LLVL1 algorithms inadequate. Trigger latency too high. | 30% |  |  | 85 | 3 | 2 | 0 | 0 | 2 |  | Low | Prioritize Physics goals to decide which triggers to run or procure more hardware |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Dec 17 2018. Full simulations of all trigger algorithms are now complete. Specific implementations in the firmware and latencies need to be measured. There are two rounds of prototype modules and firmware in the P6 schedule including specifically called out reviews after each stage. Handling any timing and algorithm issues is already accounted for in the official schedule. |  | no
56 | sPH_DAQ&Tr_005 | S258900 | BNL | DAQ&Trigger |  | Martin Purschke | TPC produces higher data rate than we can store | If the TPC or other subsystem cannot meet the envisioned data reduction specifications, then data volume, especially from the TPC, is too high | 30% |  |  | 100 | 3 | 2 | 0 | 0 | 2 |  | Low | Invest in more local storage, change compression algorithms |  |  |  | 30% |  |  | 50 | 100 | 150 | 0 | 1 | 2 | 3 | 2 | 0 | 0 | 2 | Low |  | 30 | 30 | Expert estimate | Possible | Low
57 | sPH_DAQ&Tr_006 | 1.06.02.04 | BNL | DAQ&Trigger |  | Martin Purschke | U Colorado Staff and/or Students unavailable (LL1 Trigger) | If engineering labor unavailable to write and test trigger firmware and/or assemble and test LL1 trigger system, then new professional staff would need to be hired at U. Colorado, leading to schedule delay, or an outside professional would have to be hired by U. Colorado to complete the work on time, leading to cost and schedule impact | 10% |  |  | 100 | 2 | 2 | 0 | 0 | 1.3333 |  | Low | U. Colorado recruitment of engineering and postdoctoral staff as part of ongoing contract. Maintain contact with other NP/HEP groups capable of such work if a paid contract must be placed. Cost and schedule impacts will be reduced as individual work activities are completed. |  |  |  | 0% |  |  | 388 | 388 | 388 | 3 | 3 | 3 | 0 | 4 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Dec 17 2018. Engineering for board design and initial firmware is handled at Nevis Laboratories. For longer term maintenance and algorithm updates in firmware, the U. Colorado group will have postdoctoral research scientists and graduate students for the task. The schedule includes time for transitioning between such scientists and students, and faculty at the U. Colorado will provide necessary continuity. |  | no
| sPH_DAQ&Tr_007 | [5 empty] | DAQ DCM boards are late | If Nevis contract is delayed, then board production will be late | [11 empty] | Work with BNL procurement, maintain Critical Procurement list for POB |  |  |  | 20% |  |  | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 2 | 0 | 0 | 2 | Low | 30 | 0 | 0 | Based on latest experience
58 | MinBias_001 | 272600 | BNL | MinBias |  | Mickey Chiu | Failure of D/S Board Prototype | If the D/S Board does not meet specifications, then we need to redesign to more conservative design | 10% |  |  | 50 | 2 | 2 | 0 | 0 | 1.3333 |  | Low | Work with the vendor, Columbia University |  |  |  | 10% |  |  | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 0 | Based on most recent experience | Unlikely | Negligible
59 | MinBias_002 | 273600 | BNL | MinBias |  | Mickey Chiu | Nevis Labor not available | If Nevis labor is not available, then there will be schedule delays. | 0% |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  | Not Primary | Work with the vendor, Columbia University |  |  |  | 50% |  |  | 35 | 70 | 105 | 1 | 3 | 6 | 3 | 2 | 0 | 0 | 2 | Low |  | 35 | 35 | Based on most recent experience | Possible | Low
60 | sPH_2.X Mgmt_001 | 2.01 | BNL | Management |  | Ed O'Brien | Procurement Delays | If procurements are delayed, then the Project will experience schedule delay and increase cost. | [11 empty] | Weekly meeting with procurement; maintain critical procurement list |  |  |  | 10% | Negligible |  | 0 | 50 | 80 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 2 | Low |  | 5 | 4.3333 | Latest Project experience | Unlikely | Low | New risk as of March 2021 |  |  | Open Risk
61 | sPH_2.X Mgmt_002 | 2.01 | BNL | Management |  | Ed O'Brien | Key Personnel Unavailable | If key personnel are not available on schedule, then the Project will be delayed and cost more. | [11 empty] | Maintain key personnel look-ahead list |  |  |  | 10% | Low |  | 50 | 100 | 130 | 1 | 2 | 3 | 2 | 2 | 2 | 0 | 2.6667 | Moderate |  | 10 | 9.3333 | Latest Project experience | Unlikely | Moderate | New risk as of March 2021 |  |  | Open Risk
62 | sPH_2.X Mgmt_003 | 2.01 | BNL | Management |  | Ed O'Brien | COVID Delays | If labor is not available due to COVID, then the Project will experience delays and cost more. | [11 empty] | Follow BNL COVID protocol |  |  |  | 10% | Low |  | 0 | 50 | 100 | 1 | 2 | 3 | 2 | 2 | 2 | 0 | 2.6667 | Moderate |  | 5 | 5 | Latest Project experience | Unlikely | Moderate | New risk as of March 2021 |  |  | Open Risk
63 | sPH_2.X Mgmt_004 | 2.01 | BNL | Management |  | Ed O'Brien | Raising Commodity Prices | If commodity prices go beyond the EU, then the Project will incur new costs. | [11 empty] | Accept, hold contingency |  |  |  | 10% | Negligible |  | 0 | 65 | 130 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 2 | Low |  | 6.5 | 6.5 | Latest Project experience | Unlikely | Low | New risk as of March 2021 |  |  | Open Risk
64 | sPH_SC_Magnet_001 | 2.02 | BNL | SC Magnet |  | Roberto Than | Delay in sPHENIX support platform construction | If a delay in sPHENIX support platform construction occurs, then the installation of cryogenic components on platform can't start | 15% |  |  | 5 | 3 | 1 | 0 | 0 | 1 |  | Negligible | Monitor platform construction and see if some construction can begin without platform |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Mar 28 2019. Risk did not realize. The support platform is in a different WBS and therefore the schedule will be monitored by a different L2 manager. |  | no
65 | sPH_SC_Magnet_002 | 2.02 | BNL | SC Magnet |  | Roberto Than | Magnet temperature sensors too far to read | If one is unable to read existing magnet temperature sensors in the service building over 400 feet away, then the sensors are not read or monitored by the cryogenic control system | 15% |  |  | 5 | 3 | 1 | 0 | 0 | 1 |  | Negligible | An instrumentation rack will need to be added to the sPHENIX platform to read the sensors. Alternatively, different equipment may be needed with added cost. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual | Jan 17 2019: prob. went from 55% to 10%. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need. |  |  | Retired Mar 28 2019. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need. |  | no
66 | sPH_SC_Magnet_003 | 2.02 | BNL | SC Magnet |  | Roberto Than | Vendor Delay in fabrication (Cryogenic ) | If a delay in sPHENIX support platform construction occurs, then the installation of cryogenic components on platform can't start | 15% |  |  | 5 | 3 | 1 | 0 | 0 | 1 |  | Negligible | Monitor platform construction and see if some construction can begin without platform |  |  |  | 0% | Low |  | 42 | 42 | 42 | 0 | 2 | 6 | 0 | 2 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired Mar 28 2019. Risk did not realize. The support platform is in a different WBS and therefore the schedule will be monitored by a different L2 manager.
67 | sPH_SC_Magnet_004 | 2.02 | BNL | SC Magnet |  | Carl Schultheiss | Parts availability or fabrication (Quench Detector) | If one is unable to read existing magnet temperature sensors in the service building over 400 feet away, then the sensors are not read or monitored by the cryogenic control system | 15% |  |  | 5 | 3 | 1 | 0 | 0 | 1 |  | Negligible | An instrumentation rack will need to be added to the sPHENIX platform to read the sensors. Alternatively, different equipment may be needed with added cost. |  |  |  | 0% | Low |  | 27 | 27 | 27 | 0 | 2 | 6 | 0 | 2 | 2 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual | Jan 17 2019: prob. went from 55% to 10%. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need. |  |  | Retired Mar 28 2019. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need.
68 | sPH_SC_Magnet_005 | 2.05 | BNL | SC Magnet |  | Kin Yip | Magnet Transport Likely case | If a delay in sPHENIX support platform construction occurs, then the installation of cryogenic components on platform can't start | 0% | [9 empty] | Negligible | Plan work according to BNL, CAD safety procedures; hold reviews. |  |  |  | 10% | Low |  | 0 | 100 | 0 | 0 | 6 | 48 | 2 | 2 | 2 | 0 | 2.6667 | Moderate |  | 10 | 3.3333 |  | Unlikely | Moderate
69 | sPH_SC_Magnet_005a | 2.05 | BNL | SC Magnet |  | Kin Yip | Magnet Transport Worst Case | If a delay in sPHENIX support platform construction occurs, then the installation of cryogenic components on platform can't start | 0% | [9 empty] | Negligible | Plan work according to BNL, CAD safety procedures; hold reviews. |  |  |  | 0.1% | Low |  | 0 | 0 | 10000 | 0 | 6 | 48 | 1 | 1 | 2 | 0 | 1 | Negligible |  | 0 | 3.3333 |  | Rare | Negligible
70 | sPH_SC_Magnet_006 | 2.05 | BNL | SC Magnet |  | Kin Yip | Full field test too short | If a delay in sPHENIX support platform construction occurs, then the installation of cryogenic components on platform can't start | 0% | [9 empty] | Negligible | Plan work according to BNL, CAD safety procedures; hold reviews. |  |  |  | 5% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 0 |  | Unlikely | Negligible
71 | sPH_Carriage_Cradle_001 | 311350 | BNL | Carriage and Structural Components |  | J. Mills | Steel Prices rise beyond EU | If raw steel prices rise due to market changes then the budget for this subsystem will need to go up. | 25% | Negligible | [8 empty] | Negligible | Closely monitoring market trends in hopes of anticipating any major changes. May procure components earlier if possible. |  |  |  | 30% |  |  | 126 | 126 | 126 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | High |  | 37.8 | 37.8 | (Pole tips: 110) + (Carriage Cradle+rings: 130) = 240 (tona). Weight X $/pound = $600,000. EU 40% = $240,000 15% of $840,000 = $126,000 | Possible | High
72 | sPH_Carriage_Cradle_002 | 316000 | BNL | Carriage and Structural Components |  | J. Mills | Existing Detector Support Rails Require Replacement | If the support rails are deemed unacceptable then the rails will need full replacement increasing this subsystem cost. | 50% | Low | [8 empty] | Negligible | Will need to replace rails. |  |  |  | 10% |  |  | 250 | 500 | 720 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 2.6667 | Moderate |  | 50 | 49 | Best case: encasing existing rails in concrete. Likely: using available solid plates and machining them. Worst: fully replacing tracks and support beams. | Unlikely | Moderate
73 | sPH_Infrastructure | 2.04 | BNL | Infrastructure |  | R. Pisani/J. Mills | Failure of a major piece of facility equipment | If there is a single component failure then replacement or repair of component will be necessary. | [11 empty] | CAD to inspect existing hi-risk components planned for use in sPHENIX in FY'19/FY'20. Maintenance/repair will be performed prior to start of operations/commissioning. |  |  |  | 10% | Low |  | 7.5 | 20 | 132.5 | 1 | 3 | 6 | 2 | 1 | 2 | 0 | 2 | Low |  | 2 | 5.3333
74 | sPH_Infrastructure_01 | 2.04 | BNL | Infrastructure |  | J. Vasquez | CA-D engineers are not available for timely design efforts | If CA-D engineers are not available for timely design efforts, then there would be cascading delays to production, assembly and installation | 30% | Negligible |  | 0 | 3 | 1 | 1 | 0 | 2 |  | Low | Sign MOU with CAD. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired after MOUs with CAD were signed |  | no
75 | sPH_Infrastructure_02 | 2.04 | BNL | Infrastructure |  | J. Vasquez | Cradle and/or Pole Tips Fabrication delayed | If fabrication is delayed, then Cradle and/or Pole Tips are not available on time to commence assembly and installation | 10% | Negligible |  | 0 | 2 | 1 | 1 | 0 | 1.3333 |  | Low | Use baseline schedule to monitor subsystem progress. Notify PM when installation activity float becomes less than 40 days. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired after a contract was placed |  | no
76 | sPH_Integration_Installation_01 | 2.05 | BNL | Integration Installation |  | R. Feder | Subsystem not ready for installation | If a subsystem on a Critical Path is not delivered on time for scheduled installation, then there will be delays in construction/installation of sPHENIX | 30% | Negligible |  | 0 | 3 | 1 | 1 | 0 | 2 |  | Low | Use baseline schedule to monitor subsystem progress. Notify PM when installation activity float becomes less than 40 days. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired based on Total Float in P6 |  | no
77 | sPH_Integration_Installation_02 | 2.05 | BNL | Integration Installation |  | R. Feder | Labor not available for installation | If Labor is not available for timely installation, then there will be delays in construction/installation of sPHENIX | 10% | Negligible |  | 20 | 2 | 1 | 1 | 0 | 1.3333 |  | Low | Sign MOU with CAD. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual |  |  |  | Retired after the Baseline approval. Labor needs will be tracked via RCT (Resource Comparison Tool). |  | no
78 | sPH_Integration_Installation_03 | 2.05 | BNL | Integration Installation |  | R. Feder | Key equipment failure | [16 empty] | 10% |  |  | 5 | 25 | 150 | 0 | 0.2 | 1 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 2.5 | 6 |  | Unlikely | Negligible
79 | sPH_Integration_Installation_04 | 2.05 | BNL | Integration Installation |  | R. Feder | Safety incident | [16 empty] | 5% |  |  | 5 | 10 | 50 | 0 | 0.2 | 1 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0.5 | 1.0833 |  | Unlikely | Negligible
80 | sPH_Integration_Installation_05 | 2.05 | BNL | Integration Installation |  | R. Feder | Component damage | [16 empty] | 5% |  |  | 5 | 25 | 200 | 0 | 0.2 | 1 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 1.25 | 3.8333 |  | Unlikely | Negligible
81 | sPH_Integration_Installation_06 | 2.05 | BNL | Integration Installation |  | R. Feder | Component rework | [16 empty] | 10% |  |  | 5 | 25 | 200 | 0 | 0.2 | 1 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 2.5 | 7.6667 |  | Unlikely | Negligible
82 | sPH_Integration_Installation_07 | 2.05 | BNL | Integration Installation |  | R. Feder | The rehab and extension of the current sPHENIX beam pipe is unsuccessful | If current beampipe needs modifications, then there will be additional cost and schedule delays. | [15 empty] | 20% | High | Moderate | 25 | 50 | 100 | 1 | 6 | 12 | 3 | 2 | 4 | 3 | 9 | High |  | 10 | 11.6667 | Best case: Put in the spare STAR pipe so we can start sPHENIX on time without MVTX while we get a new beam pipe in parallel (not sure this is worthwhile). Helps with schedule impact and smears cost impact out down the road. Likely: Rehab and extend START pipe so that MVTX can be installed. Allows for full sPHENIX performance but has higher cost and schedule impact up front Worst: Get quotes now for the STAR pipe rehab and rework and/or creation of a brand new beam pipe so that we can hit the ground running if we realize this risk. Will help with schedule impact. | Possible | High
83 | sPH_INTT_001 | 3.01 |  | INTT |  | R. Nouicer | Custom INTT Extension cable | If TAIYO-KOSAKUSHO company is unable to produce a 7 layer extension cable with a length of 1.2 m, then we need to use another cable vendor or switch to another type of cable. | 30% | Low |  | 0 | 3 | 1 | 2 | 0 | 3 |  | Moderate | Re-design and fabricate another type of cable such FPC cable. | [12 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0 |  | Not Residual | Not Residual
84 | sPH_INTT_001 | 3.01 |  | INTT |  | R. Nouicer | Stave carbon fiber composite. | If LBNL is late procuring staves, then INTT stave production at LBNL is delayed. | 10% | Negligible |  | 0 | 2 | 1 | 1 | 0 | 1.3333 |  | Low | Increase communication with LBNL and schedule stave production ahead of time. Work with alternative vendor, Nippon Graphite Fiber co. in Japan | [12 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  | 0 | 0
85 | MVTX_001 | 3.1.5 |  | MVTX |  | M. Liu | Stave Delivery Delay | If Staves not delivered on schedule then assembly delayed | 10% | Low |  | 0 | 2 | 0 | 2 | 0 | 1.3333 | 0 | Low | Participate in stave production to be aware of possible delays. Assembly schedule could be compressed with additional manpower. |  |  |  | 10% | Negligible | [7 empty] | 2 | 0 | 1 | 0 | 0.66667 | Negligible |  | 0 | 0
86 | MVTX_002 | 2.1 |  | MVTX |  | M. Liu | RU Delivery Delay | If RUs not delivered on schedule then commissioning is delayed | 10% | Negligible |  | 0 | 2 | 0 | 1 | 0 | 0.66667 | 0 | Negligible | Large float in schedule before RUs are critical path |  |  |  | 10% | Negligible | [7 empty] | 2 | 0 | 1 | 0 | 0.66667 | Negligible |  | 0 | 0
87 | MVTX_003 | 2.2 |  | MVTX |  | M. Liu | FELIX delivery Delay | If FELIX boards not delivered on schedule then commissioning is delayed | 10% | Negligible |  | 10 | 2 | 1 | 1 | 0 | 1.3333 | 1 | Low | Large float in schedule before FELIX boards are critical path. |  |  |  | 10% | Negligible |  |  | 10 |  |  |  |  | 2 | 1 | 1 | 0 | 1.3333 | Low |  | 1 | 0.33333
88 | MVTX_004 | 2.3 |  | MVTX |  | M. Liu | Samtec Cable R&D | If 10m 30AWG data cables noise levels too high then Move to 28AWG or higher | 0% | Negligible | Low | 10 | 0 | 1 | 1 | 2 | 0 | 0 | Retired | Early R&D, ITS already uses 32 AWG custom cable at 8m. |  |  |  | 0% |  |  |  | 10 |  |  |  |  | 0 | 1 | 0 | 0 | 0 | Not Residual |  | 0 | 0
89 | MVTX_005 | 2.3 |  | MVTX |  | M. Liu | Samtec Cable Delivery | If cables not delivered on schedule then installation is delayed until cables can be connected at inner patch panel | 10% | Negligible |  | 10 | 2 | 1 | 1 | 0 | 1.3333 | 1 | Low | Large float in schedule before cabling of assembled detector is critical path |  |  |  | 10% | Negligible |  |  | 10 |  |  |  |  | 2 | 1 | 1 | 0 | 1.3333 | Low |  | 1 | 0.33333
90 | MVTX_006 | 2.3 |  | MVTX |  | M. Liu | Custom Power Cable Unavailable | If Unable to procure custom ALICE ITS cable from CERN production then Seek outside vendor | 30% | Low |  | 20 | 3 | 1 | 2 | 0 | 3 | 6 | Moderate | Early involvement in ITS cable production to maximize advance notice |  |  |  | 30% | Negligible |  |  | 20 |  |  |  |  | 3 | 1 | 1 | 0 | 2 | Low |  | 6 | 2
91 | MVTX_007 | 2.3 |  | MVTX |  | M. Liu | Power System Radiation | If Non rad-hard power supplies not suitable then get more expensive rad-hard CAEN PS | 15% | Low |  | 20 | 3 | 1 | 2 | 0 | 3 | 3 | Moderate | Purchase additional radiation hard power modules from CAEN. Already procured control unit is needed in this scenario. `Harsh environment' tolerant crate already exists at LANL and can be used. |  |  |  | 15% | Negligible |  |  | 20 |  |  |  |  | 3 | 1 | 1 | 0 | 2 | Low |  | 3 | 1
92 | MVTX_008 | 2 |  | MVTX |  | M. Liu | lower yield in purchased electronics boards | If lower yields in the procurement of RDO boards, power boards, Felix boards, etc. can require procurement of additional boards and extend testing then costs will increase, schedule can be impacted as more boards are ordered and tested | 30% | Low |  | 20 | 3 | 1 | 2 | 0 | 3 | 6 | Moderate | Reserve contingency to cover possible additional boards. early procurement and testing to mitigate schedule impacts. |  |  |  | 30% | Negligible |  |  | 20 |  |  |  |  | 3 | 1 | 1 | 0 | 2 | Low |  | 6 | 2
93 | MVTX_009 | 3.2 |  | MVTX |  | M. Liu | Carbon Structure Cost | If Carbon structure design can't be produced at estimated cost by LBNL then Seek outside vendor | 30% | Low |  | 20 | 3 | 1 | 2 | 0 | 3 | 6 | Moderate | Producing low-cost prototypes from outside vendors to validate other options |  |  |  | 30% | Negligible |  |  | 20 |  |  |  |  | 3 | 1 | 1 | 0 | 2 | Low |  | 6 | 2
94 | MVTX_010 | 3.2.3 |  | MVTX |  | M. Liu | Carbon Structure Delivery Delay | If Carbon structure design can't be delivered on schedule by LBNL due to other obligations then Seek outside vendor | 30% | Low |  | 20 | 3 | 1 | 2 | 0 | 3 | 6 | Moderate | Stay in contact with other vendors. |  |  |  | 30% | Negligible |  |  | 20 |  |  |  |  | 3 | 1 | 1 | 0 | 2 | Low |  | 6 | 2
95 | MVTX_011 | 3.2.2 |  | MVTX |  | M. Liu | Spiderwheel Design | If Cable routing not possible through spiderwheel structures then Develop strut design or finalize original conical structure with greater cost uncertainty | 30% | Low |  | 20 | 3 | 1 | 2 | 0 | 3 | 6 | Moderate | Conical design is essentially complete but would be produced by outside vendors to stay on cost. Strut design would need further development |  |  |  | 30% | Negligible |  |  | 20 |  |  |  |  | 3 | 1 | 1 | 0 | 2 | Low |  | 6 | 2
96 | MVTX_012 | 3.2.2 |  | MVTX |  | M. Liu | Inner Support Material | If Simulations indicate aluminum causes too much background then modify design to use carbon fiber where necessary | 20% | Negligible |  | 0 | 3 | 0 | 1 | 0 | 1 | 0 | Negligible | Most parts of concern are planar and can be produced with CF if necessary. These elements are a small component of total CF cost. |  |  |  | 20% | Negligible | [7 empty] | 3 | 0 | 1 | 0 | 1 | Negligible |  | 0 | 0
97 | MVTX_013 | 3 |  | MVTX |  | M. Liu | Half-Barrel Assembly | If Damage or other delay in assembly process then installation is delayed | 10% | Moderate |  | 20 | 2 | 1 | 3 | 0 | 2.6667 | 2 | Moderate | Personnel trained in ALICE ITS assembly to reduce risk. Practice assembly with dummy or sacrificial parts first. |  |  |  | 10% | Moderate |  |  | 20 |  |  |  |  | 2 | 1 | 3 | 0 | 2.6667 | Moderate |  | 2 | 0.66667
98 | MVTX_014 | 3.3 |  | MVTX |  | M. Liu | Installation | If Damage or other delay in installation process then installation and commissioning is delayed | 10% | Moderate |  | 10 | 2 | 1 | 3 | 0 | 2.6667 | 1 | Moderate | Practice (dry run) installation with dummy or sacrificial parts. Installation scheme designed with non-administrative device safety in mind. Significant number of spare staves can replace any damaged ones. |  |  |  | 10% | Moderate |  |  | 10 |  |  |  |  | 2 | 1 | 3 | 0 | 2.6667 | Moderate |  | 1 | 0.33333
99 | MVTX_015 | 4.4 |  | MVTX |  | M. Liu | Clam shell insertiion redesign | If Beampipe aluminum section cannot be extended or welding cannot be done precisely enough to allow clamshell outside of bore then Installation scheme and design must be modified to clamshell within the TPC bore | 10% | High |  | 40 | 2 | 2 | 4 | 0 | 4 | 4 | High | Developed alternate insertion schemes with OSI. Discuss with C-AD to get advance warning. Seek quotes for new beampipe. |  |  |  | 10% | High |  |  | 40 |  |  |  |  | 2 | 2 | 4 | 0 | 4 | High |  | 4 | 1.3333
100 | MVTX_016 | MVTX |  | MVTX |  | M. Liu | Currency fluctuations | If currency fluctuations add cost to foreign procurements such as CAEN power system then costs will increase | 15% | Negligible |  | 20 | 3 | 1 | 1 | 0 | 2 | 3 | Low | Reserve contingency to cover possible fluctuations |  |  |  | 15% | Negligible |  |  | 20 |  |  |  |  | 3 | 1 | 1 | 0 | 2 | Low |  | 3 | 1
101 | MVTX_017 | 3 |  | MVTX |  | M. Liu | Integration of slow controls, configuration and software/firmware into SPHENIX environment | If The estimated effort to fully modify and integrate the control, configuration and readout environments to work in the SPHENIX environment take more effort and possible hardware than anticipated then possible cost increases if additional hardware is required. Additional effort in the software and firmware adaptation | 30% | Low |  | 10 | 3 | 1 | 2 | 0 | 3 | 3 | Moderate | Early efforts with prototypes of full chain of complete system to test full needed functionality to mitigate schedule concerns. a moderate increase in contingency to cover any additional needed hardware for integrate. |  |  |  | 30% | Negligible |  |  | 10 |  |  |  |  | 3 | 1 | 1 | 0 | 2 | Low |  | 3 | 1
102 | MVTX_018 | 3 |  | MVTX |  | M. Liu | Wirebonds not encapsulated | If wire bonds could be damaged by external contamination or hard object then Broken wire bonds, loss of chips | 10% | Low | Negligible | 20 | 2 | 1 | 2 | 1 | 2.6667 | 2 | Moderate | Use triple bonds, dedicated transportation plates |  |  |  | 10% | Low |  |  | 20 |  |  |  |  | 2 | 1 | 2 | 0 | 2 | Low |  | 2 | 0.66667
103 | MVTX_019 | 3 |  | MVTX |  | M. Liu | End Wheel Redesign | If wire bonds could be damaged by external contamination or hard object then Broken wire bonds, loss of chips | 10% | Low |  | 200 | 2 | 3 | 2 | 0 | 3.3333 | 20 | High | Review current design, reserve contingency. |  |  |  | 10% | Low |  |  | 200 |  |  |  |  | 2 | 3 | 2 | 0 | 3.3333 | High |  | 20 | 6.6667
87 | [17 empty] | 70
88
89
90
91
92
93
131
132
Note on U109: Having a large number of spare staves is also a mitigation for this item -Leo Greiner yes, this is a good point -Ming Liu

## Preview
Risks! | Item - | 83
Col | Field | CA-D engineers are not available for timely design efforts
| Risk Identification | If CA-D engineers are not available for timely design efforts, then there would be cascading delays to production, assembly and installation
B | Risk ID Number | sPH_Infrastructure_01
C | RLS activity or next WBS | 2.04
D | Lab | BNL
E | System | Infrastructure
F | Sequence | 0
G | Owner | J. Vasquez
H | Risk Title | CA-D engineers are not available for timely design efforts
I | IF/THEN | If CA-D engineers are not available for timely design efforts, then there would be cascading delays to production, assembly and installation
| Primary Risk (Unmitigated Risk Assessment) | 0
J | Likelihood of Impact (%) | 0.3
K | Schedule Impact | Negligible
L | Technical Impact | 0
M | Cost Impact Estimate ($K) | 0
N | Probability Score (1-4) | 3
O | Cost Score (1-4) | 1
P | Schedule Score (1-4) | 1
Q | Technical Score (1-4) | 0
R | Overall Impact Score | 2
S | Overall Impact Score | 0
T | Risk Handling Plan (Mitigations) | Low
U | Risk Handling Schedule (Triggers, Milestones, Due Dates) | Sign MOU with CAD.
V | Risk Handling Method | 0
W | Cost of Mitigations ($K) (Notes OK) | 0
| Residual Risk (Post- Mitigation Assessment) | 0
X | Residual Risk Likelihood of Impact (%) | 0
Y | Residual Schedule Impact | 0
Z | Residual Technical Impact | 0
AA | Low Cost Impact ($K) | 0
AB | Likely Cost Impact ($K) | 0
AC | High Cost Impact ($K) | 0
AD | Low Schedule Impact (Mos) | 0
AE | Likely Schedule Impact (Mos) | 0
AF | High Schedule Impact (Mos) | 0
AG | Probability Score (1-4) | 0
AH | Cost Score (1-4) | 0
AI | Schedule Score (1-4) | 0
AJ | Technical Score (1-4) | 0
AK | Overall Impact Score (Calculated) | 0
AL | Overall Impact Score (Residual) | 0
AM | Management Assessment: Overall Impact (Over-Ride) | Not Residual
AN | Expected Value ($K) | 0
AO | Average Expected Value ($K) | 0
AP | Basis of Impact Estimates How were cost and schedule ranges ( Columns Z through AE) developed? | 0
AQ | Matrix Code Likelihood | 0
AR | Matrix Code Severity | Not Residual
AS | Risk Burndown Notes | Not Residual
AT | Risk Manager Quantitative Model Notes | 0
AU | Risk Manager Review Questions | 0
AV | Retired Risk Notes Date, Risks Realized, etc… | 0
AW | Notes | Retired after MOUs with CAD were signed

## CB_DATA_ (hidden)
#NAME?

## SelectionCriteria
Value | Score | Value | Score | Cost Threshold ($K) | Modifier | Score
High | 4 | Very Likely (>50%) | 4 | High | > | 225
Moderate | 3 | Possible (≤50%) | 3 | Moderate | <= | 225
Low | 2 | Unlikely (≤10%) | 2 | Low | <= | 100
Negligible | 1 | Rare (≤1%) | 1 | Negligible | <= | 25
Handling Methods | What does it mean? (Info Only)
Mitigate | Active Planning to Reduce Odds/Impact
Avoid | Project Plan is changed; Risk CAN'T occur, and is retired or deleted.
Accept | If risk happens, Impact will happen, No plan to reduce.
Transfer | 3rd Party bears impact of risk - WARNING: MOU or similar document in place!
Burndown Start Year (YY) | 19
NOTE: This Column alters Cost Score Thresholds.
NOTE: Altering values on this page may change or break scoring on the "Risks" Tab. Please do not alter without reviewing underlying formulas and conditional formatting!
The VALUE Column and Score are for REFERENCE ONLY, and are not used as selection criteria in the spreadsheet - Instead actual % values are directly entered into Likelihood columns, and are used in formula calculations.

## Retired Risks
Retired Risks
Risk ID Number | Project L3 or L4 WBS | Lab | System | Sequence | Owner | Risk Title | IF/THEN | Likelihood of Impact (%) | Schedule Impact | Technical Impact | Cost Impact Estimate ($K) | Probability Score (1-4) | Cost Score (1-4) | Schedule Score (1-4) | Technical Score (1-4) | Overall Impact Score | Overall Impact Score | Risk Handling Plan (Mitigations) | Risk Handling Schedule (Triggers, Milestones, Due Dates) | Risk Handling Method | Cost of Mitigations ($K) (Notes OK) | Residual Risk Likelihood of Impact (%) | Residual Schedule Impact | Residual Technical Impact | Low Cost Impact ($K) | Likely Cost Impact ($K) | High Cost Impact ($K) | Low Schedule Impact (Mos) | Likely Schedule Impact (Mos) | High Schedule Impact (Mos) | Probability Score (1-4) | Cost Score (1-4) | Schedule Score (1-4) | Technical Score (1-4) | Overall Impact Score (Calculated) | Overall Impact Score (Residual) | Management Assessment: Overall Impact | Expected Value ($K) | Average Expected Value ($K) | Basis of Impact Estimates How were cost and schedule ranges ( Columns Z through AE) developed? | Risk Burndown Notes | Risk Manager Quantitative Model Notes | Risk Manager Review Questions | Retired Risk Notes Date, Risks Realized, etc… | Notes
Mgmt_001 |  |  |  |  | Ed O'Brien | Departure of Key Personnel | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
Mgmt_002 |  |  |  |  | Ed O'Brien | Safety incident | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
Mgmt_003 |  |  |  |  | Ed O'Brien | Funding profile stretches | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
Mgmt_004 |  |  |  |  | Ed O'Brien | University Contributed Labor for sPHENIX | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019. Nine new risks (one per each participating University) replace this one. CAMs will own the respective University labor related risks.
Mgmt_005 |  |  |  |  | Ed O'Brien | Schedule Delay | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired. All delays are assigned to WBS 1.2-1.7
Mgmt_006 |  |  |  |  | Ed O'Brien | Infrastructure support delayed | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019. sPHENIX MIE does not include installation, so the installation-related risks will be tracked in sPHENIX Support.
sPH_TPC_001 |  |  |  |  | Tom Hemmick | Performance failure of v2 prototype | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019. This risk is retired since Field Cage v2 prototype production is in the RLS.
sPH_TPC_002 |  |  |  |  | Tom Hemmick | Success of v1 field cage prototype | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Opportunity realized. Retired December 2020.
sPH_TPC_003 |  |  |  |  | Tom Hemmick | Failure or delay of CERN production | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired based on production status.
sPH_TPC_004 |  |  |  |  | Tom Hemmick | SAMPA Chip 80 nsec development | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Apr 27 2020. Based upon results measured over multiple chips, we have declared the chip as having met or surpassed our requirements.
sPH_TPC_005 |  |  |  |  | Tom Hemmick | Currency fluctuation on TPC GEMs contract with CERN | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019. Currency fluctuations can go both ways and there is no reason to expect that Swiss franc will go up against the US dollar in near future.
sPH_TPC_006 |  |  |  |  | Tom Hemmick | Wayne State Students Unavailable (R1 Modules) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired. Paid TECH labor is in the RLS.
sPH_TPC_007 |  |  |  |  | Tom Hemmick | Vanderbilt Students Unavailable (R2 Modules) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired May 2021. GEM production is complete. Risk did not realize.
sPH_TPC_008 |  |  |  |  | Tom Hemmick | Temple Students Unavailable (R3a Modules) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired May 2021. GEM production is complete. Risk did not realize.
sPH_TPC_009 |  |  |  |  | Tom Hemmick | Weizmann Students Unavailable (R3b Modules) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired May 2021. GEM production is complete. Risk did not realize.
sPH_TPC_010 |  |  |  |  | Tom Hemmick | SUNY Stony Brook Staff and/or Students Not Available (TPC) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Realized, PCR017 Nov 2020.
sPH_EMCal_001 |  |  |  |  | Craig Woody | Tungsten powder cost go up | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. UIUC placed 2 contracts with Starck in April 2018 and Oct 2019, got both delivered.
sPH_EMCal_002 |  |  |  |  | Craig Woody | Loss of SciFi supplier | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Jan 22 2019 (PO 359217)
sPH_EMCal_003 |  |  |  |  | Craig Woody | Loss of primary production site for blocks (University of Illinois Urbana Champaign) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired based on production status.
sPH_EMCal_004 |  |  |  |  | Craig Woody | Delay of EMCal block production at UIUC due to component supplies or technical issues | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_005 |  |  |  |  | Craig Woody | Delay of EMCal module production or sector assembly rate due to component supplies or technical issues | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_006 |  |  |  |  | Craig Woody | EMCal Preproduction sectors do not meet production specs | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Mar 22 2019.
sPH_EMCal_007 |  |  |  |  | Craig Woody | Labor and M&S estimates low and more of each is needed to stay on schedule | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Realized, PCR017 Nov 2021
sPH_EMCal_008 |  |  |  |  | Craig Woody | Loss of Epoxy supplier | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Feb 20 2019. Successful preproduction contract and more than one supplier identified.
sPH_EMCal_009 |  |  |  |  | Craig Woody | UIUC students not available for EMCal Fiber Assemblies | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_010 |  |  |  |  | Craig Woody | UIUC students not available for EMCal Final Block Fabrication | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_011 |  |  |  |  | Craig Woody | Loss of Students for Sector testing | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_HCal_001 |  |  |  |  | John Lajoie | Loss of scintillating tile provider (Uniplast) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired December 2020.
sPH_HCal_002 |  |  |  |  | John Lajoie | Some pre-production scintillating tiles do not meet production specifications. | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Apr 3 2019.
sPH_HCal_003 |  |  |  |  | John Lajoie | Georgia State U Staff and/or Students Not Available for HCal scin. tiles testing | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired December 2020.
sPH_HCal_004 |  |  |  |  | John Lajoie | Georgia State U Staff and/or Students Not Available for HCal sector assembly and testing | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired March 2021. Hcal Sector assembly is complete.
sPH_CalEl_001 |  |  |  |  | Eric Mannel | Delay in SiPM Delivery | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO )
sPH_CalEl_001_a |  |  |  |  | Eric Mannel | Delay in SiPM Delivery | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018
sPH_CalEl_002 |  |  |  |  | Eric Mannel | Delay in testing of SiPMs | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018
sPH_CalEl_003 |  |  |  |  | Eric Mannel | Delay in Assembly of HCal Daughter boards, Preamps, Interface boards, LED Drivers | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO )
sPH_CalEl_004 |  |  |  |  | Eric Mannel | Delay in assembly of EMCal Daughter boards, Preamps or Interface boards | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO )
sPH_CalEl_005 |  |  |  |  | Eric Mannel | Foreign Procurement of SiPMs | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019 Risk did not realize. Order with Hamamatsu has been placed, foreign vendor uncertainty no longer applies.
sPH_CalEl_006 |  |  |  |  | Eric Mannel | Hamamatsu declines to bid/Alternative vendor | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019 Risk did not realize. Order with Hamamatsu has been placed.
sPH_CalEl_007 |  |  |  |  | Eric Mannel | U. Michigan Staff and/or Students Unavailable (Cal FEE/SiPM) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired.
sPH_DAQ&Tr_001 |  |  |  |  | Martin Purschke | DAQ Prototype does not meet specifications | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_DAQ&Tr_002 |  |  |  |  | Martin Purschke | Global Lvl1 expert not available | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019. Risk did not realize. The design is ready.
sPH_DAQ&Tr_003 |  |  |  |  | Martin Purschke | Timing System technology still not finalized | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Dec 17 2018. We have already procured the GL1 and GTM units that we believe are the final ones.
sPH_DAQ&Tr_004 |  |  |  |  | Martin Purschke | Local LVL1 implementation runs into obstacles | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Dec 17 2018. Full simulations of all trigger algorithms are now complete. Specific implementations in the firmware and latencies need to be measured. There are two rounds of prototype modules and firmware in the P6 schedule including specifically called out reviews after each stage. Handling any timing and algorithm issues is already accounted for in the official schedule.
sPH_DAQ&Tr_005 |  |  |  |  | Martin Purschke | TPC produces higher data rate than we can store | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_DAQ&Tr_006 |  |  |  |  | Martin Purschke | U Colorado Staff and/or Students unavailable (LL1 Trigger) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Dec 17 2018. Engineering for board design and initial firmware is handled at Nevis Laboratories. For longer term maintenance and algorithm updates in firmware, the U. Colorado group will have postdoctoral research scientists and graduate students for the task. The schedule includes time for transitioning between such scientists and students, and faculty at the U. Colorado will provide necessary continuity.
MinBias_001 |  |  |  |  | Mickey Chiu | Failure of D/S Board Prototype | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
MinBias_002 |  |  |  |  | Mickey Chiu | Nevis Labor not available | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_SC_Magnet_001 |  |  |  |  | Roberto Than | Delay in sPHENIX support platform construction | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Mar 28 2019. Risk did not realize. The support platform is in a different WBS and therefore the schedule will be monitored by a different L2 manager.
sPH_SC_Magnet_002 |  |  |  |  | Roberto Than | Magnet temperature sensors too far to read | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Mar 28 2019. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need.
sPH_Infrastructure_01 |  |  |  |  | J. Vasquez | CA-D engineers are not available for timely design efforts | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired after MOUs with CAD were signed
sPH_Infrastructure_02 |  |  |  |  | J. Vasquez | Cradle and/or Pole Tips Fabrication delayed | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired after a contract was placed
sPH_Integration_Installation_01 |  |  |  |  | R. Feder | Subsystem not ready for installation | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired based on Total Float in P6
sPH_Integration_Installation_02 |  |  |  |  | R. Feder | Labor not available for installation | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired after the Baseline approval. Labor needs will be tracked via RCT (Resource Comparison Tool).
MVTX_001 |  |  |  |  | M. Liu | Stave Delivery Delay | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
MVTX_002 |  |  |  |  | M. Liu | RU Delivery Delay | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
MVTX_003 |  |  |  |  | M. Liu | FELIX delivery Delay | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
MVTX_004 |  |  |  |  | M. Liu | Samtec Cable R&D | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
`

## RiskPresentation
Choose Row: | 12 |  | 20 | 55.86 | 19.29 | 15.29 | 17.14
|  | 18 | Risk ID | Title | System | Owner | Residual Impact
|  |  | 10 | Tom Hemmick | BNL |  | 0
|  | 18 | Risk Statement (If/Then): |  |  | Likelihood: | 0%
|  | 18 | Success of v1 field cage prototype |  |  | Cost Impact: | Negligible
|  | 18 |  |  |  | Schedule Impact:
|  | 18 |  |  |  | Technical Impact: | 0
|  | 18 | Risk Handling (Mitigations): |  |  | Cost Impacts ($K) |  | Schedule Impact (Months)
|  | 18 |  |  |  | Expected Value: | Not Residual
|  | 18 |  |  |  | Average EV: | 0
|  | 18 |  |  |  | Low Cost: | Negligible | Low: | -150
|  | 18 |  |  |  | Likely Cost: | 0 | Likely: | -150
|  | 18 |  |  |  | High Cost: | -150 | High: | -4
Basis of Impact Estimates (Cost & Sched.):
0
|  | 18 | Risk Handling Schedule ( Triggers, Milesones, Due Dates):
High
NOTE: In cell B1 above, enter the ROW from the "Risks" Tab to display a page for the selected risk.
Use caution altering any data other than cell B1 above, as it may break the summary.
If you add or remove columns from the "Risks" tab, you will need to manually update the corresponding formulas on THIS page.

## BASIC Counts
Impact | Pre-Mitigation | Post-Mitigation
High | 9 | 5
Moderate | 12 | 4
Low | 14 | 11
Negligible | 9 | 4
Retired | 0 | 21
Residual Total |  | 24
|  |  | Severity of Impact ---------------------- Probability | Negligible | Low | Moderate | High
|  |  | Very Likely | 0 | 0 | 0 | 1
|  |  | Possible | 0 | 2 | 0 | 2
|  |  | Unlikely | 2 | 8 | 7 | 1
|  |  | Rare | 1 | 0 | 0 | 0
|  |  | Expected Value Total: | 701.25
|  |  | Averate Expected Value Total: | 655.3833
NOTE: If columns are altered on the RISKS tab, this page may stop working.

## Risks never proposed
Name | Description | Cost Impact, Direct $
Inner HCal Support Rings | Reduce technical and schedule risk for the inner HCal support rings by adding all needed design features for these rings. This is addressed by revising the design features for these rings to their detailed manufacturing drawings. | 110000