## Report
CLASSIFICATION (When Filled In)
|  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | Dollars | OMB No. 0704-0188
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
Brookhaven Science Associates |  |  |  | sPHENIX |  |  |  |  | sPH MIE Current as of data date
b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | 2021-01-01
Brookhaven National Laboratory | [16 empty] | b. TO (YYYYMMDD)
|  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
[10 empty] | NO | X | YES | 2008-09-15 |  |  |  | 2021-01-31
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
|  | AT COMPLETION |  | BASE
|  | (1) |  | (2) |  | (3) |  | O'Brien, Edward | [5 empty] | Project Director
a. BEST CASE |  | 0 | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
b. WORST CASE |  | 0
c. MOST LIKELY |  | 0 |  | 0 |  | 0
8. PERFORMANCE DATA
CA (3) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
|  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
|  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
1.01A Project Management |  | 13540.0731 | 13540.0731 | 20399.35 | 0 | -6859.2769 | 1819854.5299 | 1819854.5299 | 1682267.1 |  | 0 |  | 137587.4299 | 0 | 0 | 0 | 1951678.531 | 1814091.1011 | 137587.4299 | 1 | 1.0818
1.02A TPC |  | 1001180.5316 | 166053.4405 | 266595.97 | -835127.0911 | -100542.5295 | 4092286.1341 | 2707382.1591 | 2495255.32 |  | -1384903.975 |  | 212126.8391 | 0 | 0 | 0 | 5026775.4896 | 4667067.8564 | 359707.6332 | 0.66158 | 1.085
1.03A EMCal |  | 435773.4743 | 212598.008 | 264700.03 | -223175.4663 | -52102.022 | 4963737.2519 | 4497278.223 | 4776234.21 |  | -466459.0289 |  | -278955.987 | 0 | 0 | 0 | 6070008.4675 | 6376233.0844 | -306224.6169 | 0.90603 | 0.94159
1.04A HCal |  | 0 | 13771.6426 | 20978.15 | 13771.6426 | -7206.5074 | 2813551.1098 | 2537256.9544 | 2586996.14 |  | -276294.1554 |  | -49739.1856 | 0 | 0 | 0 | 4143415.8223 | 4199221.5179 | -55805.6956 | 0.9018 | 0.98077
1.05A Calorimeter Electronics |  | 406014.771 | 35236.6257 | 40063.04 | -370778.1453 | -4826.4143 | 4987888.9005 | 3033830.2953 | 2860414.06 |  | -1954058.6052 |  | 173416.2353 | 0 | 0 | 0 | 6290621.0515 | 6118311.9485 | 172309.103 | 0.60824 | 1.0606
1.06A DAQ & Trigger |  | 74423.0777 | 0 | 4445.82 | -74423.0777 | -4445.82 | 492607.1533 | 525778.2454 | 576818.22 |  | 33171.0921 |  | -51039.9746 | 0 | 0 | 0 | 1245090.3958 | 1300715.6651 | -55625.2693 | 1.0673 | 0.91151
1.07A MinBias Trigger Detector |  | 0 | 0 | 163.87 | 0 | -163.87 | 99147.5508 | 99147.5508 | 79089.99 |  | 0 |  | 20057.5608 | 0 | 0 | 0 | 170169.8235 | 151532.7081 | 18637.1154 | 1 | 1.2536
b. COST OF MONEY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. GENERAL AND ADMINISTRATIVE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. UNDISTRIBUTED BUDGET | [16 empty] | 0 | 0 | 0
e. SUBTOTAL |  | 1930931.9277 | 441199.7899 | 617346.23 | -1489732.1378 | -176146.4401 | 19269072.6303 | 15220527.9579 | 15057075.04 |  | -4048544.6724 |  | 163452.9179 | 0 | 0 | 0 | 24897759.5812 | 24627173.8815 | 270585.6997 | 0.78989 | 1.0109
f. Contingency | [16 empty] | 2102240
g. TOTAL |  | 1930931.9277 | 441199.7899 | 617346.23 | -1489732.1378 | -176146.4401 | 19269072.6303 | 15220527.9579 | 15057075.04 |  | -4048544.6724 |  | 163452.9179 | 0 | 0 | 0 | 26999999.5812
9. RECONCILIATION TO CONTRACT BUDGET BASELINE
a. VARIANCE ADJUSTMENT | [10 empty] | 0 |  | 0
b. TOTAL CONTRACT VARIANCE | [10 empty] | -4048544.6724 |  | 163452.9179 |  |  |  | 0 | 0 | 0
CLASSIFICATION (When Filled In)
[13 empty] | 9570098.8415 |  |  |  | ETC
[13 empty] | 9677231.6233 |  |  |  | BCWR
[13 empty] | 21.97% |  |  |  | % Contingency on ETC
[13 empty] | 21.72% |  |  |  | % Contingency on Remaining Work
[13 empty] | 77.39% |  |  |  | % Planned
[13 empty] | 61.13% |  |  |  | % Complete
[13 empty] | 60.48% |  |  |  | % Spent
Report Options
Criteria: CA (3)
Calendar: 18 Previous, Todate, At Completion
Cost Sets: Scheduled, Performed, Actuals, Estimate at complete, , , Over target baseline
Filter:

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report} | f. Contingency | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | BCWR
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on Remaining Work
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Planned
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Complete
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Spent
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2020-12-31 | PREVIOUS | 10488
2021-01-31 | TODATE | 152
2025-09-30 | ATCOMPLETE | 9344

## Data
CA (3) | Cost Set | Date | Value | Currency
1.01A | Budget | 2020-12-31 | 1806314.4568 | TRUE
1.01A | Budget | 2021-01-31 | 13540.0731 | TRUE
1.01A | Budget | 2025-09-30 | 131824.0011 | TRUE
1.01A | Progress | 2020-12-31 | 1806314.4568 | TRUE
1.01A | Progress | 2021-01-31 | 13540.0731 | TRUE
1.01A | Actuals | 2020-12-31 | 1661867.75 | TRUE
1.01A | Actuals | 2021-01-31 | 20399.35 | TRUE
1.01A | EAC | 2020-12-31 | 1661867.75 | TRUE
1.01A | EAC | 2021-01-31 | 20399.35 | TRUE
1.01A | EAC | 2025-09-30 | 131824.0011 | TRUE
1.02A | Budget | 2020-12-31 | 3091105.6025 | TRUE
1.02A | Budget | 2021-01-31 | 1001180.5316 | TRUE
1.02A | Budget | 2025-09-30 | 934489.3555 | TRUE
1.02A | Progress | 2020-12-31 | 2541328.7186 | TRUE
1.02A | Progress | 2021-01-31 | 166053.4405 | TRUE
1.02A | Actuals | 2020-12-31 | 2228659.35 | TRUE
1.02A | Actuals | 2021-01-31 | 266595.97 | TRUE
1.02A | EAC | 2020-12-31 | 2228659.35 | TRUE
1.02A | EAC | 2021-01-31 | 266595.97 | TRUE
1.02A | EAC | 2025-09-30 | 2171812.5364 | TRUE
1.03A | Budget | 2020-12-31 | 4527963.7776 | TRUE
1.03A | Budget | 2021-01-31 | 435773.4743 | TRUE
1.03A | Budget | 2025-09-30 | 1106271.2156 | TRUE
1.03A | Progress | 2020-12-31 | 4284680.215 | TRUE
1.03A | Progress | 2021-01-31 | 212598.008 | TRUE
1.03A | Actuals | 2020-12-31 | 4511534.18 | TRUE
1.03A | Actuals | 2021-01-31 | 264700.03 | TRUE
1.03A | EAC | 2020-12-31 | 4511534.18 | TRUE
1.03A | EAC | 2021-01-31 | 264700.03 | TRUE
1.03A | EAC | 2025-09-30 | 1599998.8744 | TRUE
1.04A | Budget | 2020-12-31 | 2813551.1098 | TRUE
1.04A | Budget | 2025-09-30 | 1329864.7125 | TRUE
1.04A | Progress | 2020-12-31 | 2523485.3118 | TRUE
1.04A | Progress | 2021-01-31 | 13771.6426 | TRUE
1.04A | Actuals | 2020-12-31 | 2566017.99 | TRUE
1.04A | Actuals | 2021-01-31 | 20978.15 | TRUE
1.04A | EAC | 2020-12-31 | 2566017.99 | TRUE
1.04A | EAC | 2021-01-31 | 20978.15 | TRUE
1.04A | EAC | 2025-09-30 | 1612225.3779 | TRUE
1.05A | Budget | 2020-12-31 | 4581874.1295 | TRUE
1.05A | Budget | 2021-01-31 | 406014.771 | TRUE
1.05A | Budget | 2025-09-30 | 1302732.151 | TRUE
1.05A | Progress | 2020-12-31 | 2998593.6696 | TRUE
1.05A | Progress | 2021-01-31 | 35236.6257 | TRUE
1.05A | Actuals | 2020-12-31 | 2820351.02 | TRUE
1.05A | Actuals | 2021-01-31 | 40063.04 | TRUE
1.05A | EAC | 2020-12-31 | 2820351.02 | TRUE
1.05A | EAC | 2021-01-31 | 40063.04 | TRUE
1.05A | EAC | 2025-09-30 | 3257897.8885 | TRUE
1.06A | Budget | 2020-12-31 | 418184.0756 | TRUE
1.06A | Budget | 2021-01-31 | 74423.0777 | TRUE
1.06A | Budget | 2025-09-30 | 752483.2425 | TRUE
1.06A | Progress | 2020-12-31 | 525778.2454 | TRUE
1.06A | Actuals | 2020-12-31 | 572372.4 | TRUE
1.06A | Actuals | 2021-01-31 | 4445.82 | TRUE
1.06A | EAC | 2020-12-31 | 572372.4 | TRUE
1.06A | EAC | 2021-01-31 | 4445.82 | TRUE
1.06A | EAC | 2025-09-30 | 723897.4451 | TRUE
1.07A | Budget | 2020-12-31 | 99147.5508 | TRUE
1.07A | Budget | 2025-09-30 | 71022.2727 | TRUE
1.07A | Progress | 2020-12-31 | 99147.5508 | TRUE
1.07A | Actuals | 2020-12-31 | 78926.12 | TRUE
1.07A | Actuals | 2021-01-31 | 163.87 | TRUE
1.07A | EAC | 2020-12-31 | 78926.12 | TRUE
1.07A | EAC | 2021-01-31 | 163.87 | TRUE
1.07A | EAC | 2025-09-30 | 72442.7181 | TRUE