## Report
CLASSIFICATION (When Filled In)
|  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | Dollars | OMB No. 0704-0188
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
Brookhaven Science Associates |  |  |  | sPHENIX |  |  |  |  | sPH MIE Current as of data date
b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | 2021-05-01
Brookhaven National Laboratory | [16 empty] | b. TO (YYYYMMDD)
|  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
[10 empty] | NO | X | YES | 2008-09-15 |  |  |  | 2021-05-31
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
|  | AT COMPLETION |  | BASE
|  | (1) |  | (2) |  | (3) |  | O'Brien, Edward | [5 empty] | Project Director
a. BEST CASE |  | 0 | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
b. WORST CASE |  | 0
c. MOST LIKELY |  | 0 |  | 0 |  | 0
8. PERFORMANCE DATA
CA (3) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
|  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
|  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
1.01A Project Management |  | 14252.7085 | 14252.7085 | 2031.01 | 0 | 12221.6985 | 1879715.9059 | 1879715.9059 | 1731909.26 |  | 0 |  | 147806.6459 | 0 | 0 | 0 | 1951678.5311 | 1803871.8852 | 147806.6459 | 1 | 1.0853
1.02A TPC |  | 64108.9186 | 127173.3818 | 214001.08 | 63064.4632 | -86827.6982 | 4762915.5837 | 3585188.3287 | 3286623.83 |  | -1177727.255 |  | 298564.4987 | 0 | 0 | 0 | 5026775.4895 | 4720538.1589 | 306237.3306 | 0.75273 | 1.0908
1.03A EMCal |  | 113615.6317 | 161468.294 | 121200.35 | 47852.6623 | 40267.944 | 5580535.8361 | 5262934.7841 | 5543988.97 |  | -317601.052 |  | -281054.1859 | 0 | 0 | 0 | 6070008.4674 | 6353539.1542 | -283530.6868 | 0.94309 | 0.9493
1.04A HCal |  | 12972.6738 | 141885.9587 | 3237.9 | 128913.2849 | 138648.0587 | 2855608.0561 | 3039759.4481 | 3163223.93 |  | 184151.392 |  | -123464.4819 | 0 | 0 | 0 | 4099592.292 | 4223056.7739 | -123464.4819 | 1.0645 | 0.96097
1.05A Calorimeter Electronics |  | 141602.0211 | 468934.6056 | 338878.42 | 327332.5845 | 130056.1856 | 6053313.618 | 4280810.6682 | 3879106.21 |  | -1772502.9498 |  | 401704.4582 | 0 | 0 | 0 | 6290621.0515 | 5910215.7284 | 380405.3231 | 0.70718 | 1.1036
1.06A DAQ & Trigger |  | 155675.6219 | 0 | 5129.18 | -155675.6219 | -5129.18 | 1109290.332 | 525778.2454 | 599107.33 |  | -583512.0866 |  | -73329.0846 | 0 | 0 | 0 | 1245090.3958 | 1323004.7751 | -77914.3793 | 0.47398 | 0.8776
1.07A MinBias Trigger Detector |  | 0 | 0 | 1384.78 | 0 | -1384.78 | 170169.8235 | 99147.5508 | 87968.57 |  | -71022.2727 |  | 11178.9808 | 0 | 0 | 0 | 170169.8235 | 160411.2881 | 9758.5354 | 0.58264 | 1.1271
b. COST OF MONEY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. GENERAL AND ADMINISTRATIVE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. UNDISTRIBUTED BUDGET | [16 empty] | 0 | 0 | 0
e. SUBTOTAL |  | 502227.5756 | 913714.9486 | 685862.72 | 411487.373 | 227852.2286 | 22411549.1553 | 18673334.9312 | 18291928.1 |  | -3738214.2241 |  | 381406.8312 | 0 | 0 | 0 | 24853936.0508 | 24494637.7638 | 359298.287 | 0.8332 | 1.0209
f. Contingency | [16 empty] | 2146064
g. TOTAL |  | 502227.5756 | 913714.9486 | 685862.72 | 411487.373 | 227852.2286 | 22411549.1553 | 18673334.9312 | 18291928.1 |  | -3738214.2241 |  | 381406.8312 | 0 | 0 | 0 | 27000000.0508
9. RECONCILIATION TO CONTRACT BUDGET BASELINE
a. VARIANCE ADJUSTMENT | [10 empty] | 0 |  | 0
b. TOTAL CONTRACT VARIANCE | [10 empty] | -3738214.2241 |  | 381406.8312 |  |  |  | 0 | 0 | 0
CLASSIFICATION (When Filled In)
[13 empty] | 6202709.6638 |  |  |  | ETC
[13 empty] | 6180601.1196 |  |  |  | BCWR
[13 empty] | 34.6% |  |  |  | % Contingency on ETC
[13 empty] | 34.72% |  |  |  | % Contingency on Remaining Work
[13 empty] | 90.17% |  |  |  | % Planned
[13 empty] | 75.13% |  |  |  | % Complete
[13 empty] | 73.6% |  |  |  | % Spent
Report Options
Criteria: CA (3)
Calendar: 18 Previous, Todate, At Completion
Cost Sets: Scheduled, Performed, Actuals, Estimate at complete, , , Over target baseline
Filter:

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report} | f. Contingency | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | BCWR
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on Remaining Work
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Planned
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Complete
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Spent
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2021-04-30 | PREVIOUS | 11152
2021-05-31 | TODATE | 160
2025-09-30 | ATCOMPLETE | 8672

## Data
CA (3) | Cost Set | Date | Value | Currency
1.01A | Budget | 2021-04-30 | 1865463.1974 | TRUE
1.01A | Budget | 2021-05-31 | 14252.7085 | TRUE
1.01A | Budget | 2025-09-30 | 71962.6252 | TRUE
1.01A | Progress | 2021-04-30 | 1865463.1974 | TRUE
1.01A | Progress | 2021-05-31 | 14252.7085 | TRUE
1.01A | Actuals | 2021-04-30 | 1729878.25 | TRUE
1.01A | Actuals | 2021-05-31 | 2031.01 | TRUE
1.01A | EAC | 2021-04-30 | 1729878.25 | TRUE
1.01A | EAC | 2021-05-31 | 2031.01 | TRUE
1.01A | EAC | 2025-09-30 | 71962.6252 | TRUE
1.02A | Budget | 2021-04-30 | 4698806.6651 | TRUE
1.02A | Budget | 2021-05-31 | 64108.9186 | TRUE
1.02A | Budget | 2025-09-30 | 263859.9058 | TRUE
1.02A | Progress | 2021-04-30 | 3458014.9469 | TRUE
1.02A | Progress | 2021-05-31 | 127173.3818 | TRUE
1.02A | Actuals | 2021-04-30 | 3072622.75 | TRUE
1.02A | Actuals | 2021-05-31 | 214001.08 | TRUE
1.02A | EAC | 2021-04-30 | 3072622.75 | TRUE
1.02A | EAC | 2021-05-31 | 214001.08 | TRUE
1.02A | EAC | 2025-09-30 | 1433914.3289 | TRUE
1.03A | Budget | 2021-04-30 | 5466920.2044 | TRUE
1.03A | Budget | 2021-05-31 | 113615.6317 | TRUE
1.03A | Budget | 2025-09-30 | 489472.6313 | TRUE
1.03A | Progress | 2021-04-30 | 5101466.4901 | TRUE
1.03A | Progress | 2021-05-31 | 161468.294 | TRUE
1.03A | Actuals | 2021-04-30 | 5422788.62 | TRUE
1.03A | Actuals | 2021-05-31 | 121200.35 | TRUE
1.03A | EAC | 2021-04-30 | 5422788.62 | TRUE
1.03A | EAC | 2021-05-31 | 121200.35 | TRUE
1.03A | EAC | 2025-09-30 | 809550.1842 | TRUE
1.04A | Budget | 2021-04-30 | 2842635.3823 | TRUE
1.04A | Budget | 2021-05-31 | 12972.6738 | TRUE
1.04A | Budget | 2025-09-30 | 1243984.2359 | TRUE
1.04A | Progress | 2021-04-30 | 2897873.4894 | TRUE
1.04A | Progress | 2021-05-31 | 141885.9587 | TRUE
1.04A | Actuals | 2021-04-30 | 3159986.03 | TRUE
1.04A | Actuals | 2021-05-31 | 3237.9 | TRUE
1.04A | EAC | 2021-04-30 | 3159986.03 | TRUE
1.04A | EAC | 2021-05-31 | 3237.9 | TRUE
1.04A | EAC | 2025-09-30 | 1059832.8439 | TRUE
1.05A | Budget | 2021-04-30 | 5911711.5969 | TRUE
1.05A | Budget | 2021-05-31 | 141602.0211 | TRUE
1.05A | Budget | 2025-09-30 | 237307.4335 | TRUE
1.05A | Progress | 2021-04-30 | 3811876.0626 | TRUE
1.05A | Progress | 2021-05-31 | 468934.6056 | TRUE
1.05A | Actuals | 2021-04-30 | 3540227.79 | TRUE
1.05A | Actuals | 2021-05-31 | 338878.42 | TRUE
1.05A | EAC | 2021-04-30 | 3540227.79 | TRUE
1.05A | EAC | 2021-05-31 | 338878.42 | TRUE
1.05A | EAC | 2025-09-30 | 2031109.5184 | TRUE
1.06A | Budget | 2021-04-30 | 953614.7101 | TRUE
1.06A | Budget | 2021-05-31 | 155675.6219 | TRUE
1.06A | Budget | 2025-09-30 | 135800.0638 | TRUE
1.06A | Progress | 2021-04-30 | 525778.2454 | TRUE
1.06A | Actuals | 2021-04-30 | 593978.15 | TRUE
1.06A | Actuals | 2021-05-31 | 5129.18 | TRUE
1.06A | EAC | 2021-04-30 | 593978.15 | TRUE
1.06A | EAC | 2021-05-31 | 5129.18 | TRUE
1.06A | EAC | 2025-09-30 | 723897.4451 | TRUE
1.07A | Budget | 2021-04-30 | 170169.8235 | TRUE
1.07A | Progress | 2021-04-30 | 99147.5508 | TRUE
1.07A | Actuals | 2021-04-30 | 86583.79 | TRUE
1.07A | Actuals | 2021-05-31 | 1384.78 | TRUE
1.07A | EAC | 2021-04-30 | 86583.79 | TRUE
1.07A | EAC | 2021-05-31 | 1384.78 | TRUE
1.07A | EAC | 2025-09-30 | 72442.7181 | TRUE