## Report
CLASSIFICATION (When Filled In)
|  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | Dollars | OMB No. 0704-0188
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
Brookhaven Science Associates |  |  |  | sPHENIX |  |  |  |  | sPH MIE Current as of data date
b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | 2020-06-01
Brookhaven National Laboratory | [16 empty] | b. TO (YYYYMMDD)
|  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
[10 empty] | NO | X | YES | 2008-09-15 |  |  |  | 2020-06-30
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
|  | AT COMPLETION |  | BASE
|  | (1) |  | (2) |  | (3) |  | O'Brien, Edward | [5 empty] | Project Director
a. BEST CASE |  | 0 | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
b. WORST CASE |  | 0
c. MOST LIKELY |  | 0 |  | 0 |  | 0
8. PERFORMANCE DATA
CA (3) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
|  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
|  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
1.01A Project Management |  | 23924.547 | 23924.547 | 11744.02 | 0 | 12180.527 | 1693245.0133 | 1693245.0133 | 1544798.69 |  | 0 |  | 148446.3233 | 0 | 0 | 0 | 1951678.531 | 1803232.2077 | 148446.3233 | 1 | 1.0961
1.02A TPC |  | 140312.1672 | 15000.2516 | 90397.51 | -125311.9156 | -75397.2584 | 2240066.5577 | 1697152.6215 | 1673727.05 |  | -542913.9362 |  | 23425.5715 | 0 | 0 | 0 | 4180134.7422 | 4158734.0865 | 21400.6557 | 0.75763 | 1.014
1.03A EMCal |  | 614063.0427 | 599165.263 | 653340.26 | -14897.7797 | -54174.997 | 3662345.4458 | 3481394.9539 | 3514453.18 |  | -180950.4919 |  | -33058.2261 | 0 | 0 | 0 | 5255093.5818 | 5593673.7303 | -338580.1485 | 0.95059 | 0.99059
1.04A HCal |  | 3366.748 | 506309.6865 | 126915.13 | 502942.9385 | 379394.5565 | 1992449.6765 | 1928367.4847 | 1648603.46 |  | -64082.1918 |  | 279764.0247 | 0 | 0 | 0 | 4033109.7921 | 4107747.2984 | -74637.5063 | 0.96784 | 1.1697
1.05A Calorimeter Electronics |  | 83588.6109 | 32577.4862 | 87060.48 | -51011.1247 | -54482.9938 | 2310655.0049 | 2251424.8893 | 2159554.12 |  | -59230.1156 |  | 91870.7693 | 0 | 0 | 0 | 5363466.4277 | 6071679.7261 | -708213.2984 | 0.97437 | 1.0425
1.06A DAQ & Trigger |  | 19180.8771 | 0 | 12626.84 | -19180.8771 | -12626.84 | 242014.2509 | 322827.4875 | 275360.14 |  | 80813.2366 |  | 47467.3475 | 0 | 0 | 0 | 1245090.3958 | 1198006.6659 | 47083.7299 | 1.3339 | 1.1724
1.07A MinBias Trigger Detector |  | 0 | 0 | 0 | 0 | 0 | 99147.5508 | 99147.5508 | 78303.81 |  | 0 |  | 20843.7408 | 0 | 0 | 0 | 170169.8235 | 149326.0827 | 20843.7408 | 1 | 1.2662
b. COST OF MONEY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. GENERAL AND ADMINISTRATIVE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. UNDISTRIBUTED BUDGET | [16 empty] | 0 | 0 | 0
e. SUBTOTAL |  | 884435.9929 | 1176977.2343 | 982084.24 | 292541.2414 | 194892.9943 | 12239923.4999 | 11473560.001 | 10894800.45 |  | -766363.4989 |  | 578759.551 | 0 | 0 | 0 | 22198743.2941 | 23082399.7976 | -883656.5035 | 0.93739 | 1.0531
f. Contingency | [16 empty] | 4801257
g. TOTAL |  | 884435.9929 | 1176977.2343 | 982084.24 | 292541.2414 | 194892.9943 | 12239923.4999 | 11473560.001 | 10894800.45 |  | -766363.4989 |  | 578759.551 | 0 | 0 | 0 | 27000000.2941
9. RECONCILIATION TO CONTRACT BUDGET BASELINE
a. VARIANCE ADJUSTMENT | [10 empty] | 0 |  | 0
b. TOTAL CONTRACT VARIANCE | [10 empty] | -766363.4989 |  | 578759.551 |  |  |  | 0 | 0 | 0
CLASSIFICATION (When Filled In)
[13 empty] | 12187599.3476 |  |  |  | ETC
[13 empty] | 10725183.2931 |  |  |  | BCWR
[13 empty] | 44.77% |  |  |  | % Contingency on Remaining Work
[13 empty] | 55.14% |  |  |  | % Planned
[13 empty] | 51.69% |  |  |  | % Complete
[13 empty] | 49.08% |  |  |  | % Spent
Report Options
Criteria: CA (3)
Calendar: 18 Previous, Todate, At Completion
Cost Sets: Scheduled, Performed, Actuals, Estimate at complete, , , Over target baseline
Filter:

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report} | f. Contingency | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | BCWR
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on Remaining Work
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Planned
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Complete
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Spent
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2020-05-31 | PREVIOUS | 9312
2020-06-30 | TODATE | 176
2025-09-30 | ATCOMPLETE | 10496

## Data
CA (3) | Cost Set | Date | Value | Currency
1.01A | Budget | 2020-05-31 | 1669320.4663 | TRUE
1.01A | Budget | 2020-06-30 | 23924.547 | TRUE
1.01A | Budget | 2025-09-30 | 258433.5177 | TRUE
1.01A | Progress | 2020-05-31 | 1669320.4663 | TRUE
1.01A | Progress | 2020-06-30 | 23924.547 | TRUE
1.01A | Actuals | 2020-05-31 | 1533054.67 | TRUE
1.01A | Actuals | 2020-06-30 | 11744.02 | TRUE
1.01A | EAC | 2020-05-31 | 1533054.67 | TRUE
1.01A | EAC | 2020-06-30 | 11744.02 | TRUE
1.01A | EAC | 2025-09-30 | 258433.5177 | TRUE
1.02A | Budget | 2020-05-31 | 2099754.3905 | TRUE
1.02A | Budget | 2020-06-30 | 140312.1672 | TRUE
1.02A | Budget | 2025-09-30 | 1940068.1845 | TRUE
1.02A | Progress | 2020-05-31 | 1682152.3699 | TRUE
1.02A | Progress | 2020-06-30 | 15000.2516 | TRUE
1.02A | Actuals | 2020-05-31 | 1583329.54 | TRUE
1.02A | Actuals | 2020-06-30 | 90397.51 | TRUE
1.02A | EAC | 2020-05-31 | 1583329.54 | TRUE
1.02A | EAC | 2020-06-30 | 90397.51 | TRUE
1.02A | EAC | 2025-09-30 | 2485007.0365 | TRUE
1.03A | Budget | 2020-05-31 | 3048282.4031 | TRUE
1.03A | Budget | 2020-06-30 | 614063.0427 | TRUE
1.03A | Budget | 2025-09-30 | 1592748.136 | TRUE
1.03A | Progress | 2020-05-31 | 2882229.6909 | TRUE
1.03A | Progress | 2020-06-30 | 599165.263 | TRUE
1.03A | Actuals | 2020-05-31 | 2861112.92 | TRUE
1.03A | Actuals | 2020-06-30 | 653340.26 | TRUE
1.03A | EAC | 2020-05-31 | 2861112.92 | TRUE
1.03A | EAC | 2020-06-30 | 653340.26 | TRUE
1.03A | EAC | 2025-09-30 | 2079220.5503 | TRUE
1.04A | Budget | 2020-05-31 | 1989082.9285 | TRUE
1.04A | Budget | 2020-06-30 | 3366.748 | TRUE
1.04A | Budget | 2025-09-30 | 2040660.1156 | TRUE
1.04A | Progress | 2020-05-31 | 1422057.7982 | TRUE
1.04A | Progress | 2020-06-30 | 506309.6865 | TRUE
1.04A | Actuals | 2020-05-31 | 1521688.33 | TRUE
1.04A | Actuals | 2020-06-30 | 126915.13 | TRUE
1.04A | EAC | 2020-05-31 | 1521688.33 | TRUE
1.04A | EAC | 2020-06-30 | 126915.13 | TRUE
1.04A | EAC | 2025-09-30 | 2459143.8384 | TRUE
1.05A | Budget | 2020-05-31 | 2227066.394 | TRUE
1.05A | Budget | 2020-06-30 | 83588.6109 | TRUE
1.05A | Budget | 2025-09-30 | 3052811.4228 | TRUE
1.05A | Progress | 2020-05-31 | 2218847.4031 | TRUE
1.05A | Progress | 2020-06-30 | 32577.4862 | TRUE
1.05A | Actuals | 2020-05-31 | 2072493.64 | TRUE
1.05A | Actuals | 2020-06-30 | 87060.48 | TRUE
1.05A | EAC | 2020-05-31 | 2072493.64 | TRUE
1.05A | EAC | 2020-06-30 | 87060.48 | TRUE
1.05A | EAC | 2025-09-30 | 3912125.6061 | TRUE
1.06A | Budget | 2020-05-31 | 222833.3738 | TRUE
1.06A | Budget | 2020-06-30 | 19180.8771 | TRUE
1.06A | Budget | 2025-09-30 | 1003076.1449 | TRUE
1.06A | Progress | 2020-05-31 | 322827.4875 | TRUE
1.06A | Actuals | 2020-05-31 | 262733.3 | TRUE
1.06A | Actuals | 2020-06-30 | 12626.84 | TRUE
1.06A | EAC | 2020-05-31 | 262733.3 | TRUE
1.06A | EAC | 2020-06-30 | 12626.84 | TRUE
1.06A | EAC | 2025-09-30 | 922646.5259 | TRUE
1.07A | Budget | 2020-05-31 | 99147.5508 | TRUE
1.07A | Budget | 2025-09-30 | 71022.2727 | TRUE
1.07A | Progress | 2020-05-31 | 99147.5508 | TRUE
1.07A | Actuals | 2020-05-31 | 78303.81 | TRUE
1.07A | EAC | 2020-05-31 | 78303.81 | TRUE
1.07A | EAC | 2025-09-30 | 71022.2727 | TRUE