## Report
CLASSIFICATION (When Filled In)
|  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | Dollars | OMB No. 0704-0188
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
Brookhaven Science Associates |  |  |  | sPHENIX |  |  |  |  | sPH MIE Current as of data date
b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | 2020-07-01
Brookhaven National Laboratory | [16 empty] | b. TO (YYYYMMDD)
|  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
[10 empty] | NO | X | YES | 2008-09-15 |  |  |  | 2020-07-31
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
|  | AT COMPLETION |  | BASE
|  | (1) |  | (2) |  | (3) |  | O'Brien, Edward | [5 empty] | Project Director
a. BEST CASE |  | 0 | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
b. WORST CASE |  | 0
c. MOST LIKELY |  | 0 |  | 0 |  | 0
8. PERFORMANCE DATA
CA (3) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
|  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
|  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
1.01A Project Management |  | 23924.547 | 23924.547 | 19603.43 | 0 | 4321.117 | 1717169.5604 | 1717169.5604 | 1564402.12 |  | 0 |  | 152767.4404 | 0 | 0 | 0 | 1951678.531 | 1798911.0906 | 152767.4404 | 1 | 1.0977
1.02A TPC |  | 70945.1213 | 216680.4152 | 52664.04 | 145735.2939 | 164016.3752 | 2311011.679 | 1913833.0367 | 1726391.09 |  | -397178.6423 |  | 187441.9467 | 0 | 0 | 0 | 4180134.7422 | 3996234.5204 | 183900.2218 | 0.82814 | 1.1086
1.03A EMCal |  | 88565.2145 | 91325.7289 | 177695.44 | 2760.5144 | -86369.7111 | 3750910.6603 | 3572720.6828 | 3692148.62 |  | -178189.9775 |  | -119427.9372 | 0 | 0 | 0 | 5255093.5819 | 5681205.3477 | -426111.7658 | 0.95249 | 0.96765
1.04A HCal |  | 254507.01 | 92325.2107 | 207364.14 | -162181.7993 | -115038.9293 | 2246956.6865 | 2020692.6954 | 1855967.6 |  | -226263.9911 |  | 164725.0954 | 0 | 0 | 0 | 4033109.7921 | 4109425.3022 | -76315.5101 | 0.8993 | 1.0888
1.05A Calorimeter Electronics |  | 10880.4015 | 191.5291 | 65232.08 | -10688.8724 | -65040.5509 | 2321535.4064 | 2251616.4184 | 2224786.2 |  | -69918.988 |  | 26830.2184 | 0 | 0 | 0 | 5363466.4277 | 6136758.0904 | -773291.6627 | 0.96988 | 1.0121
1.06A DAQ & Trigger |  | 0 | 0 | 30443.4 | 0 | -30443.4 | 242014.251 | 322827.4875 | 305803.54 |  | 80813.2365 |  | 17023.9475 | 0 | 0 | 0 | 1245090.3959 | 1228450.0659 | 16640.33 | 1.3339 | 1.0557
1.07A MinBias Trigger Detector |  | 0 | 0 | 0 | 0 | 0 | 99147.5508 | 99147.5508 | 78303.81 |  | 0 |  | 20843.7408 | 0 | 0 | 0 | 170169.8235 | 149326.0827 | 20843.7408 | 1 | 1.2662
b. COST OF MONEY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. GENERAL AND ADMINISTRATIVE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. UNDISTRIBUTED BUDGET | [16 empty] | 0 | 0 | 0
e. SUBTOTAL |  | 448822.2943 | 424447.4309 | 553002.53 | -24374.8634 | -128555.0991 | 12688745.7944 | 11898007.432 | 11447802.98 |  | -790738.3624 |  | 450204.452 | 0 | 0 | 0 | 22198743.2943 | 23100310.4999 | -901567.2056 | 0.93768 | 1.0393
f. Contingency | [16 empty] | 4801257
g. TOTAL |  | 448822.2943 | 424447.4309 | 553002.53 | -24374.8634 | -128555.0991 | 12688745.7944 | 11898007.432 | 11447802.98 |  | -790738.3624 |  | 450204.452 | 0 | 0 | 0 | 27000000.2943
9. RECONCILIATION TO CONTRACT BUDGET BASELINE
a. VARIANCE ADJUSTMENT | [10 empty] | 0 |  | 0
b. TOTAL CONTRACT VARIANCE | [10 empty] | -790738.3624 |  | 450204.452 |  |  |  | 0 | 0 | 0
CLASSIFICATION (When Filled In)
[13 empty] | 11652507.5199 |  |  |  | ETC
[13 empty] | 10300735.8623 |  |  |  | BCWR
[13 empty] | 46.61% |  |  |  | % Contingency on Remaining Work
[13 empty] | 41.2% |  |  |  | % Contingency on ETC
[13 empty] | 57.16% |  |  |  | % Planned
[13 empty] | 53.6% |  |  |  | % Complete
[13 empty] | 51.57% |  |  |  | % Spent
Report Options
Criteria: CA (3)
Calendar: 18 Previous, Todate, At Completion
Cost Sets: Scheduled, Performed, Actuals, Estimate at complete, , , Over target baseline
Filter:

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report} | f. Contingency | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | BCWR
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on Remaining Work
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Planned
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Complete
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Spent
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2020-06-30 | PREVIOUS | 9488
2020-07-31 | TODATE | 176
2025-09-30 | ATCOMPLETE | 10320

## Data
CA (3) | Cost Set | Date | Value | Currency
1.01A | Budget | 2020-06-30 | 1693245.0134 | TRUE
1.01A | Budget | 2020-07-31 | 23924.547 | TRUE
1.01A | Budget | 2025-09-30 | 234508.9706 | TRUE
1.01A | Progress | 2020-06-30 | 1693245.0134 | TRUE
1.01A | Progress | 2020-07-31 | 23924.547 | TRUE
1.01A | Actuals | 2020-06-30 | 1544798.69 | TRUE
1.01A | Actuals | 2020-07-31 | 19603.43 | TRUE
1.01A | EAC | 2020-06-30 | 1544798.69 | TRUE
1.01A | EAC | 2020-07-31 | 19603.43 | TRUE
1.01A | EAC | 2025-09-30 | 234508.9706 | TRUE
1.02A | Budget | 2020-06-30 | 2240066.5577 | TRUE
1.02A | Budget | 2020-07-31 | 70945.1213 | TRUE
1.02A | Budget | 2025-09-30 | 1869123.0632 | TRUE
1.02A | Progress | 2020-06-30 | 1697152.6215 | TRUE
1.02A | Progress | 2020-07-31 | 216680.4152 | TRUE
1.02A | Actuals | 2020-06-30 | 1673727.05 | TRUE
1.02A | Actuals | 2020-07-31 | 52664.04 | TRUE
1.02A | EAC | 2020-06-30 | 1673727.05 | TRUE
1.02A | EAC | 2020-07-31 | 52664.04 | TRUE
1.02A | EAC | 2025-09-30 | 2269843.4304 | TRUE
1.03A | Budget | 2020-06-30 | 3662345.4458 | TRUE
1.03A | Budget | 2020-07-31 | 88565.2145 | TRUE
1.03A | Budget | 2025-09-30 | 1504182.9216 | TRUE
1.03A | Progress | 2020-06-30 | 3481394.9539 | TRUE
1.03A | Progress | 2020-07-31 | 91325.7289 | TRUE
1.03A | Actuals | 2020-06-30 | 3514453.18 | TRUE
1.03A | Actuals | 2020-07-31 | 177695.44 | TRUE
1.03A | EAC | 2020-06-30 | 3514453.18 | TRUE
1.03A | EAC | 2020-07-31 | 177695.44 | TRUE
1.03A | EAC | 2025-09-30 | 1989056.7277 | TRUE
1.04A | Budget | 2020-06-30 | 1992449.6765 | TRUE
1.04A | Budget | 2020-07-31 | 254507.01 | TRUE
1.04A | Budget | 2025-09-30 | 1786153.1056 | TRUE
1.04A | Progress | 2020-06-30 | 1928367.4847 | TRUE
1.04A | Progress | 2020-07-31 | 92325.2107 | TRUE
1.04A | Actuals | 2020-06-30 | 1648603.46 | TRUE
1.04A | Actuals | 2020-07-31 | 207364.14 | TRUE
1.04A | EAC | 2020-06-30 | 1648603.46 | TRUE
1.04A | EAC | 2020-07-31 | 207364.14 | TRUE
1.04A | EAC | 2025-09-30 | 2253457.7022 | TRUE
1.05A | Budget | 2020-06-30 | 2310655.0049 | TRUE
1.05A | Budget | 2020-07-31 | 10880.4015 | TRUE
1.05A | Budget | 2025-09-30 | 3041931.0213 | TRUE
1.05A | Progress | 2020-06-30 | 2251424.8893 | TRUE
1.05A | Progress | 2020-07-31 | 191.5291 | TRUE
1.05A | Actuals | 2020-06-30 | 2159554.12 | TRUE
1.05A | Actuals | 2020-07-31 | 65232.08 | TRUE
1.05A | EAC | 2020-06-30 | 2159554.12 | TRUE
1.05A | EAC | 2020-07-31 | 65232.08 | TRUE
1.05A | EAC | 2025-09-30 | 3911971.8904 | TRUE
1.06A | Budget | 2020-06-30 | 242014.251 | TRUE
1.06A | Budget | 2025-09-30 | 1003076.1449 | TRUE
1.06A | Progress | 2020-06-30 | 322827.4875 | TRUE
1.06A | Actuals | 2020-06-30 | 275360.14 | TRUE
1.06A | Actuals | 2020-07-31 | 30443.4 | TRUE
1.06A | EAC | 2020-06-30 | 275360.14 | TRUE
1.06A | EAC | 2020-07-31 | 30443.4 | TRUE
1.06A | EAC | 2025-09-30 | 922646.5259 | TRUE
1.07A | Budget | 2020-06-30 | 99147.5508 | TRUE
1.07A | Budget | 2025-09-30 | 71022.2727 | TRUE
1.07A | Progress | 2020-06-30 | 99147.5508 | TRUE
1.07A | Actuals | 2020-06-30 | 78303.81 | TRUE
1.07A | EAC | 2020-06-30 | 78303.81 | TRUE
1.07A | EAC | 2025-09-30 | 71022.2727 | TRUE