## Report
CLASSIFICATION (When Filled In)
|  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | Dollars | OMB No. 0704-0188
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
Brookhaven Science Associates |  |  |  | sPHENIX |  |  |  |  | sPH MIE Current as of data date
b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | 2020-08-01
Brookhaven National Laboratory | [16 empty] | b. TO (YYYYMMDD)
|  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
[10 empty] | NO | X | YES | 2008-09-15 |  |  |  | 2020-08-31
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
|  | AT COMPLETION |  | BASE
|  | (1) |  | (2) |  | (3) |  | O'Brien, Edward | [5 empty] | Project Director
a. BEST CASE |  | 0 | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
b. WORST CASE |  | 0
c. MOST LIKELY |  | 0 |  | 0 |  | 0
8. PERFORMANCE DATA
CA (3) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
|  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
|  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
1.01A Project Management |  | 22837.0677 | 22837.0677 | 26469.91 | 0 | -3632.8423 | 1740006.6281 | 1740006.6281 | 1590872.03 |  | 0 |  | 149134.5981 | 0 | 0 | 0 | 1951678.5311 | 1802543.933 | 149134.5981 | 1 | 1.0937
1.02A TPC |  | 59447.2265 | 7736.7574 | 9785.56 | -51710.4691 | -2048.8026 | 2370458.9055 | 1921569.7941 | 1736176.65 |  | -448889.1114 |  | 185393.1441 | 0 | 0 | 0 | 4180134.7421 | 3999704.3156 | 180430.4265 | 0.81063 | 1.1068
1.03A EMCal |  | 78114.4773 | 88227.9607 | 134123.8 | 10113.4834 | -45895.8393 | 3829025.1376 | 3660948.6435 | 3826272.42 |  | -168076.4941 |  | -165323.7765 | 0 | 0 | 0 | 5255093.5819 | 5727691.9189 | -472598.337 | 0.9561 | 0.95679
1.04A HCal |  | 1837.8965 | 361314.7666 | 237413.55 | 359476.8701 | 123901.2166 | 2248794.5829 | 2382007.462 | 2093381.15 |  | 133212.8791 |  | 288626.312 | 0 | 0 | 0 | 4033109.792 | 3985511.4519 | 47598.3401 | 1.0592 | 1.1379
1.05A Calorimeter Electronics |  | 9852.6033 | 165605.4263 | 172901.12 | 155752.823 | -7295.6937 | 2331388.0097 | 2417221.8447 | 2397687.32 |  | 85833.835 |  | 19534.5247 | 0 | 0 | 0 | 5363466.4277 | 6146020.549 | -782554.1213 | 1.0368 | 1.0081
1.06A DAQ & Trigger |  | 0 | 0 | 4165.37 | 0 | -4165.37 | 242014.251 | 322827.4875 | 309968.91 |  | 80813.2365 |  | 12858.5775 | 0 | 0 | 0 | 1245090.3959 | 1232615.4359 | 12474.96 | 1.3339 | 1.0415
1.07A MinBias Trigger Detector |  | 0 | 0 | 0 | 0 | 0 | 99147.5508 | 99147.5508 | 78303.81 |  | 0 |  | 20843.7408 | 0 | 0 | 0 | 170169.8235 | 149326.0827 | 20843.7408 | 1 | 1.2662
b. COST OF MONEY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. GENERAL AND ADMINISTRATIVE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. UNDISTRIBUTED BUDGET | [16 empty] | 0 | 0 | 0
e. SUBTOTAL |  | 172089.2713 | 645721.9787 | 584859.31 | 473632.7074 | 60862.6687 | 12860835.0656 | 12543729.4107 | 12032662.29 |  | -317105.6549 |  | 511067.1207 | 0 | 0 | 0 | 22198743.2942 | 23043413.687 | -844670.3928 | 0.97534 | 1.0425
f. Contingency | [16 empty] | 4801257
g. TOTAL |  | 172089.2713 | 645721.9787 | 584859.31 | 473632.7074 | 60862.6687 | 12860835.0656 | 12543729.4107 | 12032662.29 |  | -317105.6549 |  | 511067.1207 | 0 | 0 | 0 | 27000000.2942
[13 empty] | 11010751.397 |  |  |  | ETC
[13 empty] | 9655013.8835 |  |  |  | BCWR
[13 empty] | 49.73% |  |  |  | % Contingency on Remaining Work
[13 empty] | 57.93% |  |  |  | % Planned
[13 empty] | 56.51% |  |  |  | % Complete
[13 empty] | 54.2% |  |  |  | % Spent
Report Options
Criteria: CA (3)
Calendar: 18 Previous, Todate, At Completion
Cost Sets: Scheduled, Performed, Actuals, Estimate at complete, , , Over target baseline
Filter:

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report} | f. Contingency | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | BCWR
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on Remaining Work
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Planned
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Complete
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Spent
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2020-07-31 | PREVIOUS | 9664
2020-08-31 | TODATE | 168
2025-09-30 | ATCOMPLETE | 10152

## Data
CA (3) | Cost Set | Date | Value | Currency
1.01A | Budget | 2020-07-31 | 1717169.5604 | TRUE
1.01A | Budget | 2020-08-31 | 22837.0677 | TRUE
1.01A | Budget | 2025-09-30 | 211671.903 | TRUE
1.01A | Progress | 2020-07-31 | 1717169.5604 | TRUE
1.01A | Progress | 2020-08-31 | 22837.0677 | TRUE
1.01A | Actuals | 2020-07-31 | 1564402.12 | TRUE
1.01A | Actuals | 2020-08-31 | 26469.91 | TRUE
1.01A | EAC | 2020-07-31 | 1564402.12 | TRUE
1.01A | EAC | 2020-08-31 | 26469.91 | TRUE
1.01A | EAC | 2025-09-30 | 211671.903 | TRUE
1.02A | Budget | 2020-07-31 | 2311011.679 | TRUE
1.02A | Budget | 2020-08-31 | 59447.2265 | TRUE
1.02A | Budget | 2025-09-30 | 1809675.8366 | TRUE
1.02A | Progress | 2020-07-31 | 1913833.0367 | TRUE
1.02A | Progress | 2020-08-31 | 7736.7574 | TRUE
1.02A | Actuals | 2020-07-31 | 1726391.09 | TRUE
1.02A | Actuals | 2020-08-31 | 9785.56 | TRUE
1.02A | EAC | 2020-07-31 | 1726391.09 | TRUE
1.02A | EAC | 2020-08-31 | 9785.56 | TRUE
1.02A | EAC | 2025-09-30 | 2263527.6656 | TRUE
1.03A | Budget | 2020-07-31 | 3750910.6603 | TRUE
1.03A | Budget | 2020-08-31 | 78114.4773 | TRUE
1.03A | Budget | 2025-09-30 | 1426068.4443 | TRUE
1.03A | Progress | 2020-07-31 | 3572720.6828 | TRUE
1.03A | Progress | 2020-08-31 | 88227.9607 | TRUE
1.03A | Actuals | 2020-07-31 | 3692148.62 | TRUE
1.03A | Actuals | 2020-08-31 | 134123.8 | TRUE
1.03A | EAC | 2020-07-31 | 3692148.62 | TRUE
1.03A | EAC | 2020-08-31 | 134123.8 | TRUE
1.03A | EAC | 2025-09-30 | 1901419.4989 | TRUE
1.04A | Budget | 2020-07-31 | 2246956.6864 | TRUE
1.04A | Budget | 2020-08-31 | 1837.8965 | TRUE
1.04A | Budget | 2025-09-30 | 1784315.2091 | TRUE
1.04A | Progress | 2020-07-31 | 2020692.6954 | TRUE
1.04A | Progress | 2020-08-31 | 361314.7666 | TRUE
1.04A | Actuals | 2020-07-31 | 1855967.6 | TRUE
1.04A | Actuals | 2020-08-31 | 237413.55 | TRUE
1.04A | EAC | 2020-07-31 | 1855967.6 | TRUE
1.04A | EAC | 2020-08-31 | 237413.55 | TRUE
1.04A | EAC | 2025-09-30 | 1892130.3019 | TRUE
1.05A | Budget | 2020-07-31 | 2321535.4064 | TRUE
1.05A | Budget | 2020-08-31 | 9852.6033 | TRUE
1.05A | Budget | 2025-09-30 | 3032078.418 | TRUE
1.05A | Progress | 2020-07-31 | 2251616.4184 | TRUE
1.05A | Progress | 2020-08-31 | 165605.4263 | TRUE
1.05A | Actuals | 2020-07-31 | 2224786.2 | TRUE
1.05A | Actuals | 2020-08-31 | 172901.12 | TRUE
1.05A | EAC | 2020-07-31 | 2224786.2 | TRUE
1.05A | EAC | 2020-08-31 | 172901.12 | TRUE
1.05A | EAC | 2025-09-30 | 3748333.229 | TRUE
1.06A | Budget | 2020-07-31 | 242014.251 | TRUE
1.06A | Budget | 2025-09-30 | 1003076.1449 | TRUE
1.06A | Progress | 2020-07-31 | 322827.4875 | TRUE
1.06A | Actuals | 2020-07-31 | 305803.54 | TRUE
1.06A | Actuals | 2020-08-31 | 4165.37 | TRUE
1.06A | EAC | 2020-07-31 | 305803.54 | TRUE
1.06A | EAC | 2020-08-31 | 4165.37 | TRUE
1.06A | EAC | 2025-09-30 | 922646.5259 | TRUE
1.07A | Budget | 2020-07-31 | 99147.5508 | TRUE
1.07A | Budget | 2025-09-30 | 71022.2727 | TRUE
1.07A | Progress | 2020-07-31 | 99147.5508 | TRUE
1.07A | Actuals | 2020-07-31 | 78303.81 | TRUE
1.07A | EAC | 2020-07-31 | 78303.81 | TRUE
1.07A | EAC | 2025-09-30 | 71022.2727 | TRUE