## Report
CLASSIFICATION (When Filled In)
|  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | Dollars | OMB No. 0704-0188
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
Brookhaven Science Associates |  |  |  | sPHENIX |  |  |  |  | sPH MIE Current as of data date
b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | 2020-10-01
Brookhaven National Laboratory | [16 empty] | b. TO (YYYYMMDD)
|  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
[10 empty] | NO | X | YES | 2008-09-15 |  |  |  | 2020-10-31
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
|  | AT COMPLETION |  | BASE
|  | (1) |  | (2) |  | (3) |  | O'Brien, Edward | [5 empty] | Project Director
a. BEST CASE |  | 0 | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
b. WORST CASE |  | 0
c. MOST LIKELY |  | 0 |  | 0 |  | 0
8. PERFORMANCE DATA
CA (3) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
|  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
|  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
1.01A Project Management |  | 14965.344 | 14965.344 | 8168.29 | 0 | 6797.054 | 1777809.0398 | 1777809.0398 | 1617938.76 |  | 0 |  | 159870.2798 | 0 | 0 | 0 | 1951678.531 | 1791808.2512 | 159870.2798 | 1 | 1.0988
1.02A TPC |  | 188845.1101 | 171159.8788 | 27233.34 | -17685.2313 | 143926.5388 | 2599784.493 | 2161619.9506 | 1827285.07 |  | -438164.5424 |  | 334334.8806 | 0 | 0 | 0 | 4702482.7034 | 4376618.6513 | 325864.0521 | 0.83146 | 1.183
1.03A EMCal |  | 150427.9441 | 137424.0001 | 56627.99 | -13003.944 | 80796.0101 | 4115495.7198 | 3901769.8124 | 4262306.99 |  | -213725.9074 |  | -360537.1776 | 0 | 0 | 0 | 5789008.3626 | 6156251.6406 | -367243.278 | 0.94807 | 0.91541
1.04A HCal |  | 1893.0333 | 3101.862 | 11600.47 | 1208.8287 | -8498.608 | 2488430.9164 | 2393284.1137 | 2488907.7 |  | -95146.8027 |  | -95623.5863 | 0 | 0 | 0 | 4160785.0657 | 4262584.2173 | -101799.1516 | 0.96176 | 0.96158
1.05A Calorimeter Electronics |  | 253185.5176 | 20819.644 | 123070.87 | -232365.8736 | -102251.226 | 2644471.8605 | 2622629.3404 | 2599411.62 |  | -21842.5201 |  | 23217.7204 | 0 | 0 | 0 | 6290621.0515 | 6269213.7795 | 21407.272 | 0.99174 | 1.0089
1.06A DAQ & Trigger |  | 0 | 16143.7259 | 4980.88 | 16143.7259 | 11162.8459 | 242014.251 | 338971.2134 | 266767.01 |  | 96956.9624 |  | 72204.2034 | 0 | 0 | 0 | 1245090.3959 | 1173269.81 | 71820.5859 | 1.4006 | 1.2707
1.07A MinBias Trigger Detector |  | 0 | 0 | 0 | 0 | 0 | 99147.5508 | 99147.5508 | 78926.12 |  | 0 |  | 20221.4308 | 0 | 0 | 0 | 170169.8235 | 149948.3927 | 20221.4308 | 1 | 1.2562
b. COST OF MONEY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. GENERAL AND ADMINISTRATIVE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. UNDISTRIBUTED BUDGET | [16 empty] | 0 | 0 | 0
e. SUBTOTAL |  | 609316.9491 | 363614.4548 | 231681.84 | -245702.4943 | 131932.6148 | 13967153.8313 | 13295231.0211 | 13141543.27 |  | -671922.8102 |  | 153687.7511 | 0 | 0 | 0 | 24309835.9336 | 24179694.7426 | 130141.191 | 0.95189 | 1.0117
f. Contingency | [16 empty] | 2690164
g. TOTAL |  | 609316.9491 | 363614.4548 | 231681.84 | -245702.4943 | 131932.6148 | 13967153.8313 | 13295231.0211 | 13141543.27 |  | -671922.8102 |  | 153687.7511 | 0 | 0 | 0 | 26999999.9336
9. RECONCILIATION TO CONTRACT BUDGET BASELINE
a. VARIANCE ADJUSTMENT | [10 empty] | 0 |  | 0
b. TOTAL CONTRACT VARIANCE | [10 empty] | -671922.8102 |  | 153687.7511 |  |  |  | 0 | 0 | 0
CLASSIFICATION (When Filled In)
[13 empty] | 11038151.4726 |  |  |  | ETC
[13 empty] | 11014604.9125 |  |  |  | BCWR
[13 empty] | 24.37% |  |  |  | % Contingency on ETC
[13 empty] | 24.42% |  |  |  | % Contingency on Remaining Work
[13 empty] | 57.45% |  |  |  | % Planned
[13 empty] | 54.69% |  |  |  | % Complete
[13 empty] | 54.06% |  |  |  | % Spent
Report Options
Criteria: CA (3)
Calendar: 18 Previous, Todate, At Completion
Cost Sets: Scheduled, Performed, Actuals, Estimate at complete, , , Over target baseline
Filter:

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16) | SPI | CPI
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)} | #VALUE! | #VALUE!
<Footer>{Report} | f. Contingency | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | BCWR
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on ETC
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Contingency on Remaining Work
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Planned
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Complete
<Footer>{Report} | [13 empty] | #VALUE! |  |  |  | % Spent
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2020-09-30 | PREVIOUS | 10000
2020-10-31 | TODATE | 168
2025-09-30 | ATCOMPLETE | 9816

## Data
CA (3) | Cost Set | Date | Value | Currency
1.01A | Budget | 2020-09-30 | 1762843.6958 | TRUE
1.01A | Budget | 2020-10-31 | 14965.344 | TRUE
1.01A | Budget | 2025-09-30 | 173869.4912 | TRUE
1.01A | Progress | 2020-09-30 | 1762843.6958 | TRUE
1.01A | Progress | 2020-10-31 | 14965.344 | TRUE
1.01A | Actuals | 2020-09-30 | 1609770.47 | TRUE
1.01A | Actuals | 2020-10-31 | 8168.29 | TRUE
1.01A | EAC | 2020-09-30 | 1609770.47 | TRUE
1.01A | EAC | 2020-10-31 | 8168.29 | TRUE
1.01A | EAC | 2025-09-30 | 173869.4912 | TRUE
1.02A | Budget | 2020-09-30 | 2410939.3829 | TRUE
1.02A | Budget | 2020-10-31 | 188845.1101 | TRUE
1.02A | Budget | 2025-09-30 | 2102698.2104 | TRUE
1.02A | Progress | 2020-09-30 | 1990460.0718 | TRUE
1.02A | Progress | 2020-10-31 | 171159.8788 | TRUE
1.02A | Actuals | 2020-09-30 | 1800051.73 | TRUE
1.02A | Actuals | 2020-10-31 | 27233.34 | TRUE
1.02A | EAC | 2020-09-30 | 1800051.73 | TRUE
1.02A | EAC | 2020-10-31 | 27233.34 | TRUE
1.02A | EAC | 2025-09-30 | 2549333.5813 | TRUE
1.03A | Budget | 2020-09-30 | 3965067.7757 | TRUE
1.03A | Budget | 2020-10-31 | 150427.9441 | TRUE
1.03A | Budget | 2025-09-30 | 1673512.6428 | TRUE
1.03A | Progress | 2020-09-30 | 3764345.8123 | TRUE
1.03A | Progress | 2020-10-31 | 137424.0001 | TRUE
1.03A | Actuals | 2020-09-30 | 4205679 | TRUE
1.03A | Actuals | 2020-10-31 | 56627.99 | TRUE
1.03A | EAC | 2020-09-30 | 4205679 | TRUE
1.03A | EAC | 2020-10-31 | 56627.99 | TRUE
1.03A | EAC | 2025-09-30 | 1893944.6506 | TRUE
1.04A | Budget | 2020-09-30 | 2486537.8831 | TRUE
1.04A | Budget | 2020-10-31 | 1893.0333 | TRUE
1.04A | Budget | 2025-09-30 | 1672354.1493 | TRUE
1.04A | Progress | 2020-09-30 | 2390182.2517 | TRUE
1.04A | Progress | 2020-10-31 | 3101.862 | TRUE
1.04A | Actuals | 2020-09-30 | 2477307.23 | TRUE
1.04A | Actuals | 2020-10-31 | 11600.47 | TRUE
1.04A | EAC | 2020-09-30 | 2477307.23 | TRUE
1.04A | EAC | 2020-10-31 | 11600.47 | TRUE
1.04A | EAC | 2025-09-30 | 1773676.5173 | TRUE
1.05A | Budget | 2020-09-30 | 2391286.3429 | TRUE
1.05A | Budget | 2020-10-31 | 253185.5176 | TRUE
1.05A | Budget | 2025-09-30 | 3646149.191 | TRUE
1.05A | Progress | 2020-09-30 | 2601809.6964 | TRUE
1.05A | Progress | 2020-10-31 | 20819.644 | TRUE
1.05A | Actuals | 2020-09-30 | 2476340.75 | TRUE
1.05A | Actuals | 2020-10-31 | 123070.87 | TRUE
1.05A | EAC | 2020-09-30 | 2476340.75 | TRUE
1.05A | EAC | 2020-10-31 | 123070.87 | TRUE
1.05A | EAC | 2025-09-30 | 3669802.1595 | TRUE
1.06A | Budget | 2020-09-30 | 242014.251 | TRUE
1.06A | Budget | 2025-09-30 | 1003076.1449 | TRUE
1.06A | Progress | 2020-09-30 | 322827.4875 | TRUE
1.06A | Progress | 2020-10-31 | 16143.7259 | TRUE
1.06A | Actuals | 2020-09-30 | 261786.13 | TRUE
1.06A | Actuals | 2020-10-31 | 4980.88 | TRUE
1.06A | EAC | 2020-09-30 | 261786.13 | TRUE
1.06A | EAC | 2020-10-31 | 4980.88 | TRUE
1.06A | EAC | 2025-09-30 | 906502.8 | TRUE
1.07A | Budget | 2020-09-30 | 99147.5508 | TRUE
1.07A | Budget | 2025-09-30 | 71022.2727 | TRUE
1.07A | Progress | 2020-09-30 | 99147.5508 | TRUE
1.07A | Actuals | 2020-09-30 | 78926.12 | TRUE
1.07A | EAC | 2020-09-30 | 78926.12 | TRUE
1.07A | EAC | 2025-09-30 | 71022.2727 | TRUE