**Instructions:** 1. Provide detailed attachments as appropriate and check the box to indicate a document is attached.

**Section A**

|  |  |
| --- | --- |
| **Origination** (ddMonyy) (type in expandable field) 2/27/2020 | **PCR title**: Extending the lead time for IHCal Support Rings |
| **WBS No**(s) 1.4.1 IHCal Support Structure & Support Rings |
| **Type of change** (Check all that apply; give details in Section B.)  **Technical**  **Schedule**  **Cost**  **Administrative**  **Use of contingency funds?** Y N | **Directed change?** Y  **Brief reason for change:**  **Level of change** (Level affects signatures needed in Concurrence… section.)  **3**  **2**  **1**  Project Levels  If this PCR requires a phased implementation, check here. |

**Section B**

|  |
| --- |
| **Summary of change:** Extend IHCal Support Rings contract lead time from 30 to 130 d  Attachments? Y |

|  |
| --- |
| **Technical change**  Description (include interfaces with other elements)           Attachments? Y |

|  |
| --- |
| **Detailed cost estimate with basis for estimate**  Description with basis        Total change in $K          Attachments? Y |

|  |
| --- |
| **Cost baseline impact** Orig. cost, $K 22,132.9 Est. revised, $K 22,132.9 Est. change, $K 0 **Final budgeted cost, $K** 22,132.9 |

Description       Attachments? Y  EAC or Risk ID # 

|  |
| --- |
| **Schedule impact**  At Level 3Attachments? Y |

|  |
| --- |
| **Administrative impact** Labor costs  Material costs  Changes WBS dictionary? Y  N  if Y, highest **WBS** **level** affected: 4  3  2 |

Major(>$25K) procurement  Description        Documentation update required? Y  N          Attachments? Y 

**Section C**

**Funding source and impacts on funding and contracts**  MIE Contingency ($K)

|  |  |  |
| --- | --- | --- |
|  | Before: | $ $4,867.1 |
| This requisition: | $ 0 |
| New net: | $ $4,867.1 |

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **MIE Cost Baseline in $K** | |  | FY19 | FY20 | | FY21 | FY22 | | FY23 | TOTAL |
| **Baseline Proposed Change (BCWS)** | |  |  |  | |  |  | |  |  |
| **Total Project Cost (TPC) in $K** | Baseline DOE PCR | | | | Change | | | Proposed Baseline PCR | | |
| **WBS 1.0 sPHENIX MIE Project** |  | | | |  | | |  | | |
| **WBS 1.1 sPHENIX Project Management** | $1,951.7 | | | | $0.0 | | | $1,951.7 | | |
| **WBS 1.2 sPHENIX Time Projection Chamber** | $4,169.6 | | | | $0.0 | | | $4,169.6 | | |
| **WBS 1.3 sPHENIX EMCal** | $5,196.1 | | | | $0.0 | | | $5,196.1 | | |
| **WBS 1.4 sPHENIX HCal** | $4,032.0 | | | | $0.0 | | | $4,032.0 | | |
| **WBS 1.5 sPHENIX Calorimeter Electronics** | $5,373.2 | | | | $0.0 | | | $5,373.2 | | |
| **WBS 1.6 sPHENIX DAQ & Trigger** | $1,240.2 | | | | $0.0 | | | $1,240.2 | | |
| **WBS 1.7 sPHENIX MinBias Trigger Detector** | $170.2 | | | | $0.0 | | | $170.2 | | |
| **Total Cost** | $22,132.9 | | | | $0.0 | | | $22,132.9 | | |
| **MIE Contingency** | $4,867.1 | | | | $0.0 | | | $4,867.1 | | |
| **Total Project Costs** | $27,000.0 | | | | $0.0 | | | $27,000.0 | | |
|  |  | | | |  | | |  | | |
|  |  | | | |  | | |  | | |
|  |  | | | |  | | |  | | |
|  |  | | | |  | | |  | | |
|  |  | | | |  | | |  | | |
|  |  | | | |  | | |  | | |
|  |  | | | |  | | |  | | |
|  |  | | | |  | | |  | | |
|  |  | | | |  | | |  | | |

**Concurrence and approvals**

The originator’s name should be typed in the space provided (27-character limit).

A Level 4 PCR requires concurrence of (sPHENIX Project Controls Manager), and approval from the sPHENIX Project Manager.

A Level 3 PCR requires concurrence of (sPHENIX Project Controls Manager, sPHENIX Resource Coordinator, sPHENIX Project Manager) and approval from the sPHENIX Project Director.

A Level 2 PCR requires concurrence of (sPHENIX Project Controls Manager, sPHENIX Resource Coordinator, sPHENIX Project Manager, sPHENIX Project Director) and approval from the Associate Lab Director NPP.

A Level 1 PCR requires all previous concurrence of (sPHENIX Project Controls Manager, sPHENIX Resource Coordinator, sPHENIX Project Manager, sPHENIX Project Director, Associate Lab Director NPP) and approval from the Lab Director.

A Level 1 PCR requires Level 1 concurrences and approval and in addition approval of the DOE Program Office and BHSO Official(s) named below.

|  |  |  |  |
| --- | --- | --- | --- |
| **Originator/CAM** |  | J. Lajoie |  |
| **sPHENIX Level 2 Manager** |  | J. Lajoie |  |
| **sPHENIX Project Controls Manager** |  | Irina Sourikova |  |
| **sPHENIX Resource Coordinator** |  | Cathleen Lavelle |  |
| **sPHENIX Project Manager** |  | Glenn Young |  |
| **sPHENIX Project Director** |  | Ed O’Brien |  |
| **Associate Lab Director NPP** |  | Berndt Mueller |  |
| **Lab Director** |  | Doon Gibbs |  |

Official’s typed name Signature Date (ddMonyy)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Level 1 Change**  DOE/SC Change Action |  |  |  |  |  |  |

Brookhaven Site Office (BHSO)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Level 1 Change**  DOE/SC Change Action |  |  |  |  |  |  |

Federal Program Manager (NP)