## sPHENIX MIE Cost Book
Date | (All)
Sum of Value |  | Cost Set
Control Account | Work Package | Budget
1.01A Project Management | S1001839 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | 24833.8895
| S102300 Actuals - Labor - A - MIE - sPHENIX Project Management FY17 | 107106.5442
| S102400 Actuals - Labor - A - MIE - sPHENIX Project Management FY18 | 283043.6642
| S102500 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY18 | 610909.3945
| S102605 Actuals - Labor - A - MIE - sPHENIX Project Management FY19M8 | 11566.1701
| S102606 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | 328901.5044
| S102905 Mgmt labor - A - MIE, Phase 1 - FY19 split | 71048.1531
| S102915 Mgmt labor - A - MIE, Phase 2 - FY19 split | 43639.4906
| S103000 Mgmt Labor - A - MIE - FY20 | 245877.1394
| S103200 Mgmt Labor - A - MIE - FY21 | 170568.3938
| S103400 Mgmt labor - A - MIE - FY22 | 11360.9922
| S104010 Travel FY19 Split | 8837.5525
| S104100 Travel FY20 | 27080.1932
| S104200 Travel FY21 | 6905.4493
1.01A Project Management Total |  | 1951678.531
1.02A TPC | S1000759 Actuals - NonLabor - sPHENIX TPC FY19M8 | 431189.2562
| S104600 Actuals - Nonlabor - sPHENIX TPC FY17 | 20960.9947
| S104710 Actuals - Nonlabor - sPHENIX TPC FY18 | 274664.361
| S107905 Procure TPC v1 Central Membrane Parts M&S FY19 Split | 2647.8361
| S108800 Procure TPC Handling Cart M&S | 15088.896
| S109400 Procure TPC v2 Mandrel Parts M&S | 11871.9798
| S110300 Procure TPC v2 Outer Field Cage Parts - Delivery Acceptance | 86285.4989
| S111200 Procure TPC v2 Inner Field Cage Parts - Delivery Acceptance | 39325.5774
| S111500 Procure TPC Field Cage Prototype v2 End Rings | 22758.5158
| S111800 Procure TPC v2 Central Membrane Parts M&S | 9103.4063
| S112800 Procure TPC v2 Field Cage Modification Parts M&S | 6827.5547
| S113050 TPC Module technical Support | 92854.7445
| S117100 Procure TPC v2 Module Strongback M&S | 1365.5109
| S117400 Procure TPC v2 Module Frames M&S | 1137.9258
| S117700 Procure TPC v2 Module Grid Parts M&S | 568.9629
| S118100 Procure TPC v2a Module Padplane M&S | 4210.3254
| S118400 Procure TPC v2a Module GEMs M&S | 7396.5176
| S120000 Procure Trained Technician to work in CERN Shop on TPC GEMs - Delivery Acceptance | 44470.1399
| S120100 Procure Production of TPC GEM foils (includes Technician fees) - Delivery Acceptance | 154001.6745
| S120400 Procure TPC Membrane HV Cables - M&S | 682.7555
| S121400 Procure TPC GEM HV Power Supplies - Delivery Acceptance | 125263.3717
| S121500 Procure TPC GEM HV Membrane Power Supply - Delivery Acceptance | 12245.2194
| S121605 TPC Assembly Mechanical Engineering Support | 156234.2361
| S121650 Procure Piping Fittings | 1279.0741
| S121950 TPC Assembly technical Support | 23253.7097
| S122202 Prepare TPC R1 Factory Tooling Labor Split | 295.0683
| S122302 Prepare TPC R1 Factory Tooling M&S Split | 2647.8361
| S123600 Test TPC R1 Pre-Production Module | 7868.4874
| S123700 Common production line & QA certification | 106168.4475
| S124500 Procure TPC R1 Module Parts (Frames) - Delivery Acceptance | 16614.8545
| S124800 Procure TPC R1 Module Parts (Strongbacks) - Delivery Acceptance | 9349.1983
| S125100 Procure TPC R1 Module Parts (Padplanes) - Delivery Acceptance | 50113.1139
| S125400 Procure TPC R1 Module Parts (Grids) - Delivery Acceptance | 11148.259
| S125500 Build TPC R1 Modules | 63129.6018
| S125600 Test TPC R1 Modules | 63173.4114
| S126502 Prepare TPC R2 Factory Tooling M&S Split | 3971.7542
| S127602 Procure TPC R2 Pre-Production Module GEMs M&S Split | 2758.1626
| S128500 Procure TPC R2 Module Prod. Parts (Frames) - Delivery Acceptance | 16614.8545
| S128800 Procure TPC R2 Module Prod. Parts (Strongbacks) - Delivery Acceptance | 10450.7105
| S129100 Procure TPC R2 Module Prod. Parts (Padplanes) - Delivery Acceptance | 60298.6876
| S129400 Procure TPC R2 Module Prod. Parts (Grids) - Delivery Acceptance | 11148.259
| S130102 Prepare TPC R3a Factory Tooling M&S Split | 3971.7542
| S130502 Prepare TPC R3b Factory Tooling M&S Split | 3971.7542
| S131000 Procure TPC R3 Pre-Production Module frames - M&S | 2206.5301
| S131600 Procure TPC R3 Pre-Production Module GEMs M&S | 11032.6505
| S132700 Procure TPC R3 Module Prod. Parts (Frames) - Delivery Acceptance | 19138.7739
| S133000 Procure TPC R3 Module Prod. Parts (Strongbacks) - Delivery Acceptance | 12246.3574
| S133300 Procure TPC R3 Module Prod. Parts (Padplanes) - Delivery Acceptance | 81668.934
| S133600 Procure TPC R3 Module Prod. Parts (Grids) - Delivery Acceptance | 11706.9805
| S136500 Procure TPC FEE Cooling System - Delivery Acceptance | 69820.9644
| S137000 v2 Procure TPC FEE preproducion prototype components M&S | 6680.7623
| S137200 v2 Fabricate TPC FEE preproduction prototype boards M&S | 1679.5785
| S137400 v2 Modify TPC FEE Test Stand M&S | 9103.4063
| S137600 v2 Assemble and test TPC FEE preproduction prototype M&S | 6406.5222
| S139720 Procure second phase of SAMPA development - Delivery of First Chip Layout | 38614.2768
| S139725 Procure second phase of SAMPA development - Delivery of Final Review of test results | 77228.5535
| S139730 Procure second phase of SAMPA development - Delivery of Eng Design Review | 52405.0899
| S139735 Procure second phase of SAMPA development - Delivery of Eng Run Preparation | 22099.9618
| S140400 Procure Engineering Run of Full SAMPA Chip - Delivery Acceptance | 265136.7091
| S140500 Populate v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip | 3413.7774
| S141500 Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Delivery Acceptance | 34429.3786
| S141800 Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | 309547.5403
| S142500 Procure TPC FEE LV Power Supplies - Delivery Acceptance | 220595.0165
| S143200 Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | 175243.5986
| S143250 TPC Front End Electronics | 174102.6459
| S143270 TPC FEE Electrical Engineering Support 1 | 119731.0981
| S145700 Procure TPC DAM Felix 2.0 Boards Throughput - Delivery Acceptance | 81116.4596
| S145750 Procure Full Set of Data Fibers for Design Validation - M&S | 3172.9903
| S146300 Miscellaneous Parts for TPC DAM FPGA Algorithm Development - Round 1 | 2827.6683
| S147300 Procure TPC DAM Felix 2.0 Boards - Delivery Acceptance | 151309.1275
| S147370 Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Delivery Acceptance | 93719.4543
| S147380 TPC DAM Electrical Engineering Support | 48327.4519
| S148400 Procure TPC EDBC Computers & Peripherals - Delivery Acceptance | 244768.5885
| S149600 Procure TPC Lasers - Delivery Acceptance | 165955.0973
| S149650 TPC Diffuse Lasers | 232136.8612
| S150300 Procure TPC Optics with Mirrors - Delivery Acceptance | 66910.0365
| S150500 Procure TPC mirror bundles with supports M&S | 17060.2217
| S150800 Install &Test TPC Laser safety interlocks M&S | 2275.8516
| S151600 Procure TPC Gas System mass flow meters M&S | 7773.1711
| S152300 Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | 37591.3785
| S152500 Procure TPC Gas System scrubbers M&S | 8792.7526
| S152700 Procure TPC Gas System oxygen and water sensors M&S | 12703.8035
| S153000 Procure TPC Gas System Computer Controller M&S | 20974.8678
| S153700 Procure TPC Gas System Components for Installation - Delivery Acceptance | 39563.0853
| S155000 Procure TPC Cooling System Equipment - Delivery Acceptance | 50454.4916
| S155700 Procure TPC Plumbing - Contract/PO M&S | 13541.7038
| S155900 Set up TPC Cooling System computer controls M&S | 12179.0604
1.02A TPC Total |  | 5026775.4898
1.03A EMCal | S1001879 Actuals - Nonlabor - sPHENIX EMCal FY19M8 | 80811.9584
| S156400 Actuals - Nonlabor - sPHENIX EMCal FY17 | 45714.0043
| S156500 Actuals - Nonlabor - sPHENIX EMCal FY18 | 463282.3548
| S156510 Actuals - Nonlabor - sPHENIX EMCal FY19M8 | 699611.9661
| S161700 Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Delivery acceptance Phase 2 of 2 Phases (Sectors 4-12) | 242078.4174
| S164702 Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Delivery acceptance Split | 36671.427
| S165802 Prepare fiber assemblies for EMCal Prepro Sectors 1-12 Blocks Split | 11004.3648
| S165902 Fabricate EMCAL Prepro blocks sector 1 Split | 7103.6284
| S166000 Fabricate EMCAL Prepro blocks sector 2 | 9425.1431
| S166100 Fabricate EMCAL Prepro blocks sector 3 | 9425.1431
| S166200 Fabricate EMCAL Prepro blocks sector 4 | 9425.1431
| S166300 Fabricate EMCAL Prepro blocks sector 5 | 9425.1431
| S166400 Fabricate EMCAL Prepro blocks sector 6 | 9425.1431
| S166500 Fabricate EMCAL Prepro blocks sector 7 | 9425.1431
| S166600 Fabricate EMCAL Prepro blocks sector 8 | 9425.1431
| S166700 Fabricate EMCAL Prepro blocks sector 9 | 9425.1431
| S166800 Fabricate EMCAL Prepro blocks sector 10 | 9425.1431
| S166900 Fabricate EMCAL Prepro blocks sector 11 | 9425.1431
| S167000 Fabricate EMCAL Prepro blocks sector 12 | 9425.1431
| S167100 Pack and ship EMCAL blocks for Prepro sector 1 to BNL Purchased Services | 865.953
| S167200 Pack and ship EMCAL blocks for Prepro sector 1 to BNL M&S | 1228.9599
| S167300 Pack and ship EMCAL blocks for Prepro sector 2 to BNL Purchased Services | 865.953
| S167400 Pack and ship EMCAL blocks for Prepro sector 2 to BNL M&S | 1228.9599
| S167500 Pack and ship EMCAL blocks for Prepro sector 3 to BNL Purchased Services | 865.953
| S167600 Pack and ship EMCAL blocks for Prepro sector 3 to BNL M&S | 1228.9599
| S167700 Pack and ship EMCAL blocks for Prepro sector 4 to BNL Purchased Services | 865.953
| S167800 Pack and ship EMCAL blocks for Prepro sector 4 to BNL M&S | 1228.9599
| S167900 Pack and ship EMCAL blocks for Prepro sector 5 to BNL Purchased Services | 865.953
| S168000 Pack and ship EMCAL blocks for Prepro sector 5 to BNL M&S | 1228.9599
| S168100 Pack and ship EMCAL blocks for Prepro sector 6 to BNL Purchased Services | 865.953
| S168200 Pack and ship EMCAL blocks for Prepro sector 6 to BNL M&S | 1228.9599
| S168300 Pack and ship EMCAL blocks for Prepro sector 7 to BNL Purchased Services | 865.953
| S168400 Pack and ship EMCAL blocks for Prepro sector 7 to BNL M&S | 1228.9599
| S168500 Pack and ship EMCAL blocks for Prepro sector 8 to BNL Purchased Services | 865.953
| S168600 Pack and ship EMCAL blocks for Prepro sector 8 to BNL M&S | 1228.9599
| S168700 Pack and ship EMCAL blocks for Prepro sector 9 to BNL Purchased Services | 865.953
| S168800 Pack and ship EMCAL blocks for Prepro sector 9 to BNL M&S | 1228.9599
| S168900 Pack and ship EMCAL blocks for Prepro sector 10 to BNL Purchased Services | 865.953
| S169000 Pack and ship EMCAL blocks for Prepro sector 10 to BNL M&S | 1228.9599
| S169100 Pack and ship EMCAL blocks for Prepro sector 11 to BNL Purchased Services | 865.953
| S169200 Pack and ship EMCAL blocks for Prepro sector 11 to BNL M&S | 1228.9599
| S169300 Pack and ship EMCAL blocks for Prepro sector 12 to BNL Purchased Services | 865.953
| S169400 Pack and ship EMCAL blocks for Prepro sector 12 to BNL M&S | 1228.9599
| S169500 Establish EMCAL final blocks contract with UIUC | 1083.4064
| S170200 Procure EMCAL W Powder for Final Blocks - Sectors 13-38 - Delivery Acceptance | 540981.3
| S170210 Procure EMCAL W Powder for Final Blocks - Sectors 39-64 - Delivery Acceptance | 540981.3
| S171003 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 3 | 40405.9792
| S171004 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 4 | 40405.9792
| S171005 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 5 | 40405.9792
| S171006 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 6 | 40405.9792
| S171007 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 7 | 40858.2296
| S171008 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 8 | 40858.2296
| S171009 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 9 | 40858.2296
| S171010 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 10 | 40858.2296
| S171011 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 11 | 40858.2296
| S171012 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 12 | 40858.2296
| S171013 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 13 | 40858.2296
| S171014 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 14 | 40858.2296
| S171015 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 15 | 40858.2296
| S171016 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 16 | 40858.2296
| S171017 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 17 | 40858.2296
| S171018 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 18 | 40858.2296
| S171019 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 19 | 40858.2296
| S171020 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 20 | 40858.2296
| S171021 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 21 | 40858.2296
| S171022 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 22 | 40858.2296
| S171023 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 23 | 38234.3066
| S171200 Procure EMCAL Epoxy for Final Blocks - Provide Requirements to Procurement | 1316.3885
| S171800 Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | 104592.3235
| S172500 Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | 30217.9061
| S172600 Set up factory for final blocks Purchased Services | 7016.603
| S172700 Set up factory for final blocks M&S | 2840.4753
| S172800 Prepare fiber assemblies for final blocks | 163756.7299
| S172850 Supervise EMCal Final Block Production | 60868.4256
| S172870 EMCal Block Production QA | 533914.7808
| S172900 Production Readiness Review, Safety Review - EMCal Blocks | 1579.8758
| S173000 Fabricate final blocks sector 13 | 5012.3259
| S173100 Fabricate final blocks sector 14 | 5012.3259
| S173200 Fabricate final blocks sector 15 | 5012.3259
| S173300 Fabricate final blocks sector 16 | 5012.3259
| S173400 Fabricate final blocks sector 17 | 5012.3259
| S173500 Fabricate final blocks sector 18 | 5012.3259
| S173600 Fabricate final blocks sector 19 | 5012.3259
| S173700 Fabricate final blocks sector 20 | 5012.3259
| S173800 Fabricate final blocks sector 21 | 5012.3259
| S173900 Fabricate final blocks sector 22 | 5012.3259
| S174000 Fabricate final blocks sector 23 | 5012.3259
| S174100 Fabricate final blocks sector 24 | 5012.3259
| S174200 Fabricate final blocks sector 25 | 5062.4491
| S174300 Fabricate final blocks sector 26 | 5162.6956
| S174400 Fabricate final blocks sector 27 | 5162.6956
| S174500 Fabricate final blocks sector 28 | 5162.6956
| S174600 Fabricate final blocks sector 29 | 5162.6956
| S174700 Fabricate final blocks sector 30 | 5162.6956
| S174800 Fabricate final blocks sector 31 | 5162.6956
| S174900 Fabricate final blocks sector 32 | 5162.6956
| S175000 Fabricate final blocks sector 33 | 5162.6956
| S175100 Fabricate final blocks sector 34 | 5162.6956
| S175200 Fabricate final blocks sector 35 | 5162.6956
| S175300 Fabricate final blocks sector 36 | 5162.6956
| S175400 Fabricate final blocks sector 37 | 5162.6956
| S175500 Fabricate final blocks sector 38 | 5162.6956
| S175600 Fabricate final blocks sector 39 | 5162.6956
| S175700 Fabricate final blocks sector 40 | 5162.6956
| S175800 Fabricate final blocks sector 41 | 5162.6956
| S175900 Fabricate final blocks sector 42 | 5162.6956
| S176000 Fabricate final blocks sector 43 | 5162.6956
| S176010 Pack and ship final blocks for sectors 57-64 to BNL - M&S | 7521.2343
| S176100 Fabricate final blocks sector 44 | 5162.6956
| S176200 Fabricate final blocks sector 45 | 5162.6956
| S176300 Fabricate final blocks sector 46 | 5162.6956
| S176400 Fabricate final blocks sector 47 | 5162.6956
| S176500 Fabricate final blocks sector 48 | 5162.6956
| S176600 Fabricate final blocks sector 49 | 5162.6956
| S176700 Fabricate final blocks sector 50 | 5162.6956
| S176800 Fabricate final blocks sector 51 | 5162.6956
| S176900 Fabricate final blocks sector 52 | 5162.6956
| S177000 Fabricate final blocks sector 53 | 5162.6956
| S177100 Fabricate final blocks sector 54 | 5162.6956
| S177200 Fabricate final blocks sector 55 | 5162.6956
| S177300 Fabricate final blocks sector 56 | 5162.6956
| S177400 Fabricate final blocks sector 57 | 5162.6956
| S177500 Fabricate final blocks sector 58 | 5162.6956
| S177600 Fabricate final blocks sector 59 | 5162.6956
| S177700 Fabricate final blocks sector 60 | 5162.6956
| S177800 Fabricate final blocks sector 61 | 5162.6956
| S177900 Fabricate final blocks sector 62 | 5162.6956
| S178000 Fabricate final blocks sector 63 | 5162.6956
| S178100 Fabricate final blocks sector 64 | 5162.6956
| S178300 Pack and ship final blocks for sectors 13-16 to BNL - Purchased Services | 1186.9284
| S178310 Pack and ship final blocks for sectors 13-16 to BNL - M&S | 3686.8796
| S178400 Pack and ship final blocks for sectors 17-24 to BNL - Purchased Services | 2501.6167
| S178410 Pack and ship final blocks for sectors 17-24 to BNL - M&S | 7403.2542
| S178500 Pack and ship final blocks for sectors 25-32 to BNL - Purchased Services | 2561.2974
| S178510 Pack and ship final blocks for sectors 25-32 to BNL - M&S | 7521.2343
| S178600 Pack and ship final blocks for sectors 33-40 to BNL - Purchased Services | 2561.2974
| S178610 Pack and ship final blocks for sectors 33-40 to BNL - M&S | 7521.2343
| S178700 Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | 2561.2974
| S178710 Pack and ship final blocks for sectors 40-48 to BNL - M&S | 7521.2343
| S178800 Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | 2561.2974
| S178900 Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 2561.2974
| S178910 Pack and ship final blocks for sectors 49-56 to BNL - M&S | 7521.2343
| S180402 Set up EMCAL Final module production and sector assembly areas M&S Split | 11198.1403
| S184800 Procure light guides for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | 87930.2245
| S185500 Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | 14961.4483
| S185800 Install reflectors on blocks for modules for Prepro Sectors 1-12 M&S | 398.274
| S187100 Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Delivery Acceptance | 61144.8492
| S187400 Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | 240129.1165
| S187700 Install light guides on final blocks M&S | 1912.3475
| S188100 Install SiPMs daughterboards on final blocks M&S | 348.0061
| S191110 Build mechanical stand/support for preproduction prototype Sector 0 - M&S | 551.6325
| S192800 Procure mechanical parts for Prepro Sectors 1-12, Phase 1 - Delivery Acceptance | 41873.3932
| S192810 Procure mechanical parts for Prepro Sectors 1-12, Phase 2 - Delivery Acceptance | 41873.3932
| S193500 Procure parts for cooling system for Prepro Sectors 1-12 - Delivery Acceptance | 22508.1721
| S193710 Build mechanical stand/support for Prepro Sectors 1-12 - M&S | 568.9629
| S195400 Procure EMCAL Mechanical Parts for Final Sectors - Delivery Acceptance | 291746.1251
| S196100 Procure EMCAL Cooling System for Final Sectors - Delivery Acceptance | 82284.3925
| S196910 Technical support labor for EMCal assembly | 281000.1048
1.03A EMCal Total |  | 6070008.4704
1.04A HCal | S1001919 Actuals - Nonlabor - sPHENIX HCal FY19M8 | 18547.6397
| S197600 Actuals - Nonlabor - sPHENIX HCal FY17 | 3021.0033
| S197700 Actuals - Nonlabor - sPHENIX HCal FY18 | 142473.385
| S197710 Actuals - Nonlabor - sPHENIX HCal FY19M8 | 458015.6204
| S199300 Manufacture Inner HCAL Support Structure - Delivery Acceptance 1 | 264958.211
| S199310 Manufacture Inner HCAL Support Structure - Delivery Acceptance 2 | 264958.211
| S199320 Manufacture Inner HCAL Support Structure - Delivery Acceptance 3 | 264958.211
| S199330 Manufacture Inner HCAL Support Structure - Delivery Acceptance 4 | 264958.211
| S200000 Manufacture Inner HCAL Support Rings - Delivery Acceptance | 141885.9587
| S202512 Outer HCAL Scintillating Tile Acceptance Testing (Preproduction) Split | 2116.8914
| S203002 Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) - M&S Split | 2206.5301
| S203100 Populate Outer HCAL sectors with scintillating tiles (Preproduction) | 3590.6544
| S203200 Populate Outer HCAL sectors with electronics (Preproduction) | 3590.6544
| S203300 Outer HCAL Sector LED testing and Light Tighting (Preproduction) Labor | 3590.6544
| S203400 Outer HCAL Sector LED testing and Light Tighting (Preproduction) M&S | 5462.0438
| S203500 Outer HCAL Cosmics testing and initial calibration (Preproduction) | 3590.6544
| S205100 Procure Outer HCAL Splice Plates - Delivery Acceptance | 303325.4987
| S206200 Procure Outer HCAL Lifting Fixtures & Supports - Delivery Acceptance | 45517.0316
| S208220 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 0 | 204371.0245
| S208300 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 1 | 159650.9884
| S208302 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 2 | 126290.7973
| S208303 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 3 | 126290.7973
| S208304 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 4 | 126290.7973
| S208306 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 5&6 | 252581.5946
| S208308 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 7&8 | 252581.5946
| S208310 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 9&10 | 235905.4037
| S208312 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 11&12 | 235905.4037
| S208400 Outer HCAL Scintillating Tile Acceptance Testing | 11583.1237
| S209600 Procure Outer HCAL Assembly & Testing Equipment- Delivery Acceptance | 87051.323
| S209800 Populate Outer HCAL sectors with scintillating tiles | 15509.3102
| S209900 Populate Outer HCAL sectors with electronics | 15509.3102
| S210000 Outer HCAL Sector LED testing and Light Tighting | 15509.3102
| S210100 Procure Outer HCAL LED Testing & Light Tighting M&S | 22285.1387
| S210200 Outer HCAL Cosmics testing and initial calibration | 15509.3102
1.04A HCal Total |  | 4099592.2919
1.05A Calorimeter Electronics | S1000879 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | 383105.0929
| S1001959 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | 64370.0104
| S211400 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY17 | 33386.9993
| S211500 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY18 | 39192.5851
| S213200 Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 | 1225.9492
| S213210 Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 | 1225.9492
| S213300 Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 | 1072.7055
| S214800 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 5 | 76698.9863
| S214900 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 6 | 76698.9863
| S215000 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 7 | 76698.9863
| S215100 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 8 | 76698.9863
| S215200 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 9 | 77512.2696
| S215300 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 10 | 77557.4519
| S215310 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 11 | 77557.4519
| S215320 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 12 | 77557.4519
| S215400 EMCal/HCal sensors Production - 5K Units - Delivery Acceptance No. 13 | 48473.4074
| S215600 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 | 1276.8609
| S215800 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 | 1276.8609
| S215900 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 | 1276.8609
| S216000 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 | 1276.8609
| S216100 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 | 1276.8609
| S216200 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 | 1276.8609
| S216300 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 | 1276.8609
| S216310 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 | 1276.8609
| S216320 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 | 1276.8609
| S216400 Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 | 798.0381
| S221300 Fabricate EMCal SiPM Boards: Sectors 1-12 - M&S | 29002.3146
| S222200 Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 1 - Delivery Acceptance | 89810.793
| S222201 Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 2 - Delivery Acceptance | 89810.793
| S222300 Test EMCal Preamp Boards: Sectors 1-12 | 1915.2913
| S223000 Fabricate EMCal Interface Board: Sectors 1-12, Phase 1 - Delivery Acceptance | 33494.8456
| S223001 Fabricate EMCal Interface Board: Sectors 1-12, Phase 2 - Delivery Acceptance | 33494.8456
| S223300 Fabricate Calorimeter Controller Boards: Sectors 1-12 M&S | 23009.9974
| S223700 Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 1 - M&S | 47874.8139
| S223701 Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 2 - M&S | 47874.8139
| S223900 Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 1 - M&S | 11959.3769
| S224000 Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 2 - M&S | 47837.5077
| S224300 Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 1 - M&S | 3504.8114
| S224400 Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 2 - M&S | 14019.2457
| S225300 Test Pulse Boards 1-12 - M&S | 4804.3227
| S226300 Procure EMCal External Bias Power System: Sectors 1-12, Phase 1 - Delivery Acceptance | 8663.4842
| S226400 Procure EMCal External Bias Power System: Sectors 1-12, Phase 2 - Delivery Acceptance | 34653.9368
| S227600 Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance Part 1 | 38676.0895
| S227605 Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance Part 2 | 23205.8768
| S228100 Test SiPM Daughter Boards Production Sectors 13-64 | 2887.5729
| S229300 Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Delivery Acceptance | 549642.0532
| S229400 Test EMCal Preamp Boards: Production Sectors 13-64 | 6312.8
| S230100 Fabricate EMCAL Interface Board Sectors 13-64 - Delivery Acceptance | 217848.8374
| S230200 Test EMCal Interface Boards: Production Sectors 13-64 | 6312.8
| S231000 Fabricate Calorimeter Production Controller Boards - Delivery Acceptance | 92154.8519
| S231100 Test Calorimeter Controller Boards: Production Sectors 13-64 | 1972.75
| S231800 Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Delivery Acceptance | 288193.2705
| S232500 Fabricate Test-pulse Boards 13 - 64 - M&S | 8022.3768
| S233200 Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Delivery Acceptance | 205854.3258
| S233250 Trunk Signal Cables - EMCal | 777844.1946
| S234000 Procure EMCal Bias Power System Sectors 13-64 - Delivery Acceptance | 155680.2646
| S234100 EMCal Low Voltage Power System Sectors 13-64 - M&S | 39269.5959
| S234200 EMCal Crates for Controllers - M&S | 5948.4513
| S236200 Fabricate HCal SiPM Boards: (6 Modules) M&S | 31674.7396
| S236800 Fabricate HCal LED Boards: (6 Modules) M&S | 14419.6742
| S237710 Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 1 - M&S Split | 5468.8849
| S237800 Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 2 - M&S | 21875.5394
| S239100 Fabricate HCal SiPM Boards - Delivery Acceptance | 110822.1375
| S240400 Fabricate HCal Preamp Boards - Delivery Acceptance | 48010.5456
| S241700 Fabricate HCal LED Boards - Delivery Acceptance | 50144.9758
| S242000 Fabricate HCal Backplane Boards: Production - M&S | 17542.264
| S242900 Fabricate HCal Interface Boards Production - Delivery Acceptance | 33329.8464
| S243700 Procure HCal Electronics Production Power & Signal Cables (Internal) - Delivery Acceptance | 94394.9726
| S244400 HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | 101939.4206
| S244450 Trunk Signal Cables - OuterHCal | 149310.4291
| S245000 Procure Test stand for SiPMs | 24271.8311
| S248200 Procure 1/2-Crate Digitizer - Contract/PO - Delivery Acceptance for Assembly & Tests | 55163.2525
| S251000 Procure EMCAL 7-Crate Digitizer - Parts - Delivery Acceptance | 195673.9861
| S251100 Procure EMCAL 7-Crate Digitizer (Boards) - Delivery Acceptance | 43436.6483
| S251200 Procure EMCAL 7-Crate Digitizer (Assembly & Tests) - Delivery Acceptance | 90872.4778
| S252700 Procure Production Digitizer (Parts) - Delivery Acceptance | 678538.3667
| S252800 Procure Production Digitizer (Boards) - Delivery Acceptance | 149785.149
| S252900 Procure Production Digitizer (Assembly & Tests) - Delivery Acceptance | 231065.5496
1.05A Calorimeter Electronics Total |  | 6290621.0514
1.06A DAQ & Trigger | S1000959 Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | 23190.6976
| S253500 Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | 2781.5146
| S255900 Procure DAQ Production Boards - Delivery Acceptance | 121502.7545
| S256700 Procure DAQ Production Crates - Delivery Acceptance | 74283.7956
| S257600 Procure DAQ Production SEBs - Delivery Acceptance | 47634.4839
| S258400 Procure DAQ Production ATPs - Delivery Acceptance | 113802.7748
| S258700 Procure DAQ Production jSEB Slow control computers - Delivery Acceptance | 19180.8771
| S259500 Procure DAQ Production Buffer Boxes - Delivery Acceptance | 259459.3698
| S260300 Procure DAQ Production Main Switches - Delivery Acceptance | 99994.1137
| S262500 Procure Prototype V1 Trigger Board - Delivery Acceptance | 196861.1617
| S263600 Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance | 69641.0584
| S264900 Procure Production LL1 System - Delivery Acceptance | 135800.0638
| S267600 Procure Production GL1 Components - final hardware - Delivery Acceptance | 32673.2632
| S270300 Timing System Production (FPGA Boards) - Delivery Acceptance | 48284.4671
1.06A DAQ & Trigger Total |  | 1245090.3958
1.07A MinBias Trigger Detector | S1001039 Actuals - Nonlabor - sPHENIX MinBias Trigger FY19 M8 | 21505.3278
| S271300 Actuals - Nonlabor - sPHENIX MinBias Trigger FY18 | 413.6695
| S272600 Procure Prototype Shaper/Disc Electronics - Delivery Acceptance | 77228.5535
| S273500 Procure Min/Bias Electronics (sPHENIX Production Digitizers) - Delivery Acceptance | 17143.3072
| S273600 Procure MBD Shaper/Disc Board 128 Channels - Delivery Acceptance | 53878.9655
1.07A MinBias Trigger Detector Total |  | 170169.8235

## Data
Control Account | Work Package | Cost Set | Date | Value | Currency
1.01A Project Management | 16700 sPHENIX OPC - Project Management | Actuals | 2018-09-30 | 1001059.55 | TRUE
1.01A Project Management | 16700 sPHENIX OPC - Project Management | Actuals | 2019-09-30 | 348935.51 | TRUE
1.01A Project Management | 16700 sPHENIX OPC - Project Management | Actuals | 2020-09-30 | 6256.11 | TRUE
1.01A Project Management | 16700 sPHENIX OPC - Project Management | EAC | 2018-09-30 | 1001059.55 | TRUE
1.01A Project Management | 16700 sPHENIX OPC - Project Management | EAC | 2019-09-30 | 348935.51 | TRUE
1.01A Project Management | 16700 sPHENIX OPC - Project Management | EAC | 2020-09-30 | 6256.11 | TRUE
1.01A Project Management | 59700 sPHENIX MIE - 1.1 Project Management | Actuals | 2019-09-30 | 91796.06 | TRUE
1.01A Project Management | 59700 sPHENIX MIE - 1.1 Project Management | Actuals | 2020-09-30 | 161723.24 | TRUE
1.01A Project Management | 59700 sPHENIX MIE - 1.1 Project Management | Actuals | 2021-09-30 | 103853.56 | TRUE
1.01A Project Management | 59700 sPHENIX MIE - 1.1 Project Management | EAC | 2019-09-30 | 91796.06 | TRUE
1.01A Project Management | 59700 sPHENIX MIE - 1.1 Project Management | EAC | 2020-09-30 | 161723.24 | TRUE
1.01A Project Management | 59700 sPHENIX MIE - 1.1 Project Management | EAC | 2021-09-30 | 103853.56 | TRUE
1.01A Project Management | 59724 FY21 sPHX MIE - 1.1 Project Mgmt | Actuals | 2021-09-30 | 18285.23 | TRUE
1.01A Project Management | 59724 FY21 sPHX MIE - 1.1 Project Mgmt | EAC | 2021-09-30 | 18285.23 | TRUE
1.01A Project Management | S1001839 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | Budget | 2019-09-30 | 24833.8895 | TRUE
1.01A Project Management | S1001839 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | Progress | 2019-09-30 | 24833.8895 | TRUE
1.01A Project Management | S102300 Actuals - Labor - A - MIE - sPHENIX Project Management FY17 | Budget | 2017-09-30 | 107106.5442 | TRUE
1.01A Project Management | S102300 Actuals - Labor - A - MIE - sPHENIX Project Management FY17 | Progress | 2019-09-30 | 107106.5442 | TRUE
1.01A Project Management | S102400 Actuals - Labor - A - MIE - sPHENIX Project Management FY18 | Budget | 2018-09-30 | 283043.6642 | TRUE
1.01A Project Management | S102400 Actuals - Labor - A - MIE - sPHENIX Project Management FY18 | Progress | 2019-09-30 | 283043.6642 | TRUE
1.01A Project Management | S102500 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY18 | Budget | 2018-09-30 | 610909.3945 | TRUE
1.01A Project Management | S102500 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY18 | Progress | 2019-09-30 | 610909.3945 | TRUE
1.01A Project Management | S102605 Actuals - Labor - A - MIE - sPHENIX Project Management FY19M8 | Budget | 2019-09-30 | 11566.1701 | TRUE
1.01A Project Management | S102605 Actuals - Labor - A - MIE - sPHENIX Project Management FY19M8 | Progress | 2019-09-30 | 11566.1701 | TRUE
1.01A Project Management | S102606 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | Budget | 2019-09-30 | 328901.5044 | TRUE
1.01A Project Management | S102606 Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | Progress | 2019-09-30 | 328901.5044 | TRUE
1.01A Project Management | S102905 Mgmt labor - A - MIE, Phase 1 - FY19 split | Budget | 2019-09-30 | 71048.1531 | TRUE
1.01A Project Management | S102905 Mgmt labor - A - MIE, Phase 1 - FY19 split | Progress | 2019-09-30 | 71048.1531 | TRUE
1.01A Project Management | S102915 Mgmt labor - A - MIE, Phase 2 - FY19 split | Budget | 2019-09-30 | 43639.4906 | TRUE
1.01A Project Management | S102915 Mgmt labor - A - MIE, Phase 2 - FY19 split | Progress | 2019-09-30 | 43639.4906 | TRUE
1.01A Project Management | S103000 Mgmt Labor - A - MIE - FY20 | Budget | 2020-09-30 | 245877.1394 | TRUE
1.01A Project Management | S103000 Mgmt Labor - A - MIE - FY20 | Progress | 2020-09-30 | 245877.1394 | TRUE
1.01A Project Management | S103200 Mgmt Labor - A - MIE - FY21 | Budget | 2021-09-30 | 170568.3938 | TRUE
1.01A Project Management | S103200 Mgmt Labor - A - MIE - FY21 | Progress | 2021-09-30 | 112342.2353 | TRUE
1.01A Project Management | S103200 Mgmt Labor - A - MIE - FY21 | EAC | 2021-09-30 | 58226.1585 | TRUE
1.01A Project Management | S103400 Mgmt labor - A - MIE - FY22 | Budget | 2022-09-30 | 11360.9922 | TRUE
1.01A Project Management | S103400 Mgmt labor - A - MIE - FY22 | EAC | 2022-09-30 | 11360.9922 | TRUE
1.01A Project Management | S104010 Travel FY19 Split | Budget | 2019-09-30 | 8837.5525 | TRUE
1.01A Project Management | S104010 Travel FY19 Split | Progress | 2019-09-30 | 8837.5525 | TRUE
1.01A Project Management | S104100 Travel FY20 | Budget | 2020-09-30 | 27080.1932 | TRUE
1.01A Project Management | S104100 Travel FY20 | Progress | 2020-09-30 | 27080.1932 | TRUE
1.01A Project Management | S104200 Travel FY21 | Budget | 2021-09-30 | 6905.4493 | TRUE
1.01A Project Management | S104200 Travel FY21 | Progress | 2021-09-30 | 4529.9747 | TRUE
1.01A Project Management | S104200 Travel FY21 | EAC | 2021-09-30 | 2375.4746 | TRUE
1.02A TPC | 16701 sPHENIX OPC - Time Projection Chamber | Actuals | 2018-09-30 | 295625.36 | TRUE
1.02A TPC | 16701 sPHENIX OPC - Time Projection Chamber | Actuals | 2019-09-30 | 789844.42 | TRUE
1.02A TPC | 16701 sPHENIX OPC - Time Projection Chamber | Actuals | 2020-09-30 | 144954.26 | TRUE
1.02A TPC | 16701 sPHENIX OPC - Time Projection Chamber | EAC | 2018-09-30 | 295625.36 | TRUE
1.02A TPC | 16701 sPHENIX OPC - Time Projection Chamber | EAC | 2019-09-30 | 789844.42 | TRUE
1.02A TPC | 16701 sPHENIX OPC - Time Projection Chamber | EAC | 2020-09-30 | 144954.26 | TRUE
1.02A TPC | 59702 sPHENIX MIE - 1.2 TPC Mechanics | Actuals | 2020-09-30 | 4349.65 | TRUE
1.02A TPC | 59702 sPHENIX MIE - 1.2 TPC Mechanics | Actuals | 2021-09-30 | 76432.55 | TRUE
1.02A TPC | 59702 sPHENIX MIE - 1.2 TPC Mechanics | EAC | 2020-09-30 | 4349.65 | TRUE
1.02A TPC | 59702 sPHENIX MIE - 1.2 TPC Mechanics | EAC | 2021-09-30 | 76432.55 | TRUE
1.02A TPC | 59703 sPHENIX MIE - 1.2 TPC GEMs (R1, R2, R3) | Actuals | 2020-09-30 | 210680.51 | TRUE
1.02A TPC | 59703 sPHENIX MIE - 1.2 TPC GEMs (R1, R2, R3) | Actuals | 2021-09-30 | 547892.61 | TRUE
1.02A TPC | 59703 sPHENIX MIE - 1.2 TPC GEMs (R1, R2, R3) | EAC | 2020-09-30 | 210680.51 | TRUE
1.02A TPC | 59703 sPHENIX MIE - 1.2 TPC GEMs (R1, R2, R3) | EAC | 2021-09-30 | 547892.61 | TRUE
1.02A TPC | 59704 sPHENIX MIE - 1.2 TPC Front End Electronics | Actuals | 2020-09-30 | 292739.05 | TRUE
1.02A TPC | 59704 sPHENIX MIE - 1.2 TPC Front End Electronics | Actuals | 2021-09-30 | 481804.84 | TRUE
1.02A TPC | 59704 sPHENIX MIE - 1.2 TPC Front End Electronics | EAC | 2020-09-30 | 292739.05 | TRUE
1.02A TPC | 59704 sPHENIX MIE - 1.2 TPC Front End Electronics | EAC | 2021-09-30 | 481804.84 | TRUE
1.02A TPC | 59705 sPHENIX MIE - 1.2 TPC Data Aggregator Modules | Actuals | 2020-09-30 | 26794.9 | TRUE
1.02A TPC | 59705 sPHENIX MIE - 1.2 TPC Data Aggregator Modules | Actuals | 2021-09-30 | 190957.86 | TRUE
1.02A TPC | 59705 sPHENIX MIE - 1.2 TPC Data Aggregator Modules | EAC | 2020-09-30 | 26794.9 | TRUE
1.02A TPC | 59705 sPHENIX MIE - 1.2 TPC Data Aggregator Modules | EAC | 2021-09-30 | 190957.86 | TRUE
1.02A TPC | 59706 sPHENIX MIE - 1.2 TPC Support Systems | Actuals | 2020-09-30 | 35063.58 | TRUE
1.02A TPC | 59706 sPHENIX MIE - 1.2 TPC Support Systems | Actuals | 2021-09-30 | 63007.45 | TRUE
1.02A TPC | 59706 sPHENIX MIE - 1.2 TPC Support Systems | EAC | 2020-09-30 | 35063.58 | TRUE
1.02A TPC | 59706 sPHENIX MIE - 1.2 TPC Support Systems | EAC | 2021-09-30 | 63007.45 | TRUE
1.02A TPC | 59726 FY21 sPHX MIE - 1.2 TPC Mechanics | Actuals | 2021-09-30 | 36712.76 | TRUE
1.02A TPC | 59726 FY21 sPHX MIE - 1.2 TPC Mechanics | EAC | 2021-09-30 | 36712.76 | TRUE
1.02A TPC | 59728 FY21 sPHX MIE - 1.2 TPC Front En | Actuals | 2021-09-30 | 37968.56 | TRUE
1.02A TPC | 59728 FY21 sPHX MIE - 1.2 TPC Front En | EAC | 2021-09-30 | 37968.56 | TRUE
1.02A TPC | 59729 TPC Data Aggreg | Actuals | 2021-09-30 | 45480.42 | TRUE
1.02A TPC | 59729 TPC Data Aggreg | EAC | 2021-09-30 | 45480.42 | TRUE
1.02A TPC | 59730 FY21 SPHX MIE - 1.2 TPC Data Aggreg | Actuals | 2021-09-30 | 6315.05 | TRUE
1.02A TPC | 59730 FY21 SPHX MIE - 1.2 TPC Data Aggreg | EAC | 2021-09-30 | 6315.05 | TRUE
1.02A TPC | S1000759 Actuals - NonLabor - sPHENIX TPC FY19M8 | Budget | 2019-09-30 | 431189.2562 | TRUE
1.02A TPC | S1000759 Actuals - NonLabor - sPHENIX TPC FY19M8 | Progress | 2019-09-30 | 431189.2562 | TRUE
1.02A TPC | S104600 Actuals - Nonlabor - sPHENIX TPC FY17 | Budget | 2017-09-30 | 20960.9947 | TRUE
1.02A TPC | S104600 Actuals - Nonlabor - sPHENIX TPC FY17 | Progress | 2019-09-30 | 20960.9947 | TRUE
1.02A TPC | S104710 Actuals - Nonlabor - sPHENIX TPC FY18 | Budget | 2018-09-30 | 274664.361 | TRUE
1.02A TPC | S104710 Actuals - Nonlabor - sPHENIX TPC FY18 | Progress | 2019-09-30 | 274664.361 | TRUE
1.02A TPC | S107905 Procure TPC v1 Central Membrane Parts M&S FY19 Split | Budget | 2019-09-30 | 2647.8361 | TRUE
1.02A TPC | S107905 Procure TPC v1 Central Membrane Parts M&S FY19 Split | Progress | 2019-09-30 | 2118.2689 | TRUE
1.02A TPC | S107905 Procure TPC v1 Central Membrane Parts M&S FY19 Split | Progress | 2020-09-30 | 529.5672 | TRUE
1.02A TPC | S108800 Procure TPC Handling Cart M&S | Budget | 2021-09-30 | 15088.896 | TRUE
1.02A TPC | S108800 Procure TPC Handling Cart M&S | Progress | 2020-09-30 | 13580.0064 | TRUE
1.02A TPC | S108800 Procure TPC Handling Cart M&S | Progress | 2021-09-30 | 1508.8896 | TRUE
1.02A TPC | S109400 Procure TPC v2 Mandrel Parts M&S | Budget | 2020-09-30 | 11871.9798 | TRUE
1.02A TPC | S109400 Procure TPC v2 Mandrel Parts M&S | Progress | 2020-09-30 | 11871.9798 | TRUE
1.02A TPC | S110300 Procure TPC v2 Outer Field Cage Parts - Delivery Acceptance | Budget | 2020-09-30 | 86285.4989 | TRUE
1.02A TPC | S110300 Procure TPC v2 Outer Field Cage Parts - Delivery Acceptance | Progress | 2020-09-30 | 86285.4989 | TRUE
1.02A TPC | S111200 Procure TPC v2 Inner Field Cage Parts - Delivery Acceptance | Budget | 2020-09-30 | 39325.5774 | TRUE
1.02A TPC | S111200 Procure TPC v2 Inner Field Cage Parts - Delivery Acceptance | Progress | 2020-09-30 | 39325.5774 | TRUE
1.02A TPC | S111500 Procure TPC Field Cage Prototype v2 End Rings | Budget | 2020-09-30 | 22758.5158 | TRUE
1.02A TPC | S111500 Procure TPC Field Cage Prototype v2 End Rings | Progress | 2020-09-30 | 22758.5158 | TRUE
1.02A TPC | S111800 Procure TPC v2 Central Membrane Parts M&S | Budget | 2020-09-30 | 9103.4063 | TRUE
1.02A TPC | S111800 Procure TPC v2 Central Membrane Parts M&S | Progress | 2020-09-30 | 9103.4063 | TRUE
1.02A TPC | S112800 Procure TPC v2 Field Cage Modification Parts M&S | Budget | 2020-09-30 | 6827.5547 | TRUE
1.02A TPC | S112800 Procure TPC v2 Field Cage Modification Parts M&S | Progress | 2021-09-30 | 6827.5547 | TRUE
1.02A TPC | S113050 TPC Module technical Support | Budget | 2021-09-30 | 92854.7445 | TRUE
1.02A TPC | S113050 TPC Module technical Support | Progress | 2021-09-30 | 92854.7445 | TRUE
1.02A TPC | S117100 Procure TPC v2 Module Strongback M&S | Budget | 2020-09-30 | 1365.5109 | TRUE
1.02A TPC | S117100 Procure TPC v2 Module Strongback M&S | Progress | 2020-09-30 | 1365.5109 | TRUE
1.02A TPC | S117400 Procure TPC v2 Module Frames M&S | Budget | 2020-09-30 | 1137.9258 | TRUE
1.02A TPC | S117400 Procure TPC v2 Module Frames M&S | Progress | 2020-09-30 | 1137.9258 | TRUE
1.02A TPC | S117700 Procure TPC v2 Module Grid Parts M&S | Budget | 2020-09-30 | 568.9629 | TRUE
1.02A TPC | S117700 Procure TPC v2 Module Grid Parts M&S | Progress | 2020-09-30 | 568.9629 | TRUE
1.02A TPC | S118100 Procure TPC v2a Module Padplane M&S | Budget | 2020-09-30 | 4210.3254 | TRUE
1.02A TPC | S118100 Procure TPC v2a Module Padplane M&S | Progress | 2020-09-30 | 4210.3254 | TRUE
1.02A TPC | S118400 Procure TPC v2a Module GEMs M&S | Budget | 2020-09-30 | 7396.5176 | TRUE
1.02A TPC | S118400 Procure TPC v2a Module GEMs M&S | Progress | 2020-09-30 | 7396.5176 | TRUE
1.02A TPC | S120000 Procure Trained Technician to work in CERN Shop on TPC GEMs - Delivery Acceptance | Budget | 2020-09-30 | 44470.1399 | TRUE
1.02A TPC | S120000 Procure Trained Technician to work in CERN Shop on TPC GEMs - Delivery Acceptance | Progress | 2020-09-30 | 44470.1399 | TRUE
1.02A TPC | S120100 Procure Production of TPC GEM foils (includes Technician fees) - Delivery Acceptance | Budget | 2020-09-30 | 30073.753 | TRUE
1.02A TPC | S120100 Procure Production of TPC GEM foils (includes Technician fees) - Delivery Acceptance | Budget | 2021-09-30 | 123927.9215 | TRUE
1.02A TPC | S120100 Procure Production of TPC GEM foils (includes Technician fees) - Delivery Acceptance | Progress | 2020-09-30 | 22735.7573 | TRUE
1.02A TPC | S120100 Procure Production of TPC GEM foils (includes Technician fees) - Delivery Acceptance | Progress | 2021-09-30 | 131265.9172 | TRUE
1.02A TPC | S120400 Procure TPC Membrane HV Cables - M&S | Budget | 2020-09-30 | 682.7555 | TRUE
1.02A TPC | S120400 Procure TPC Membrane HV Cables - M&S | Progress | 2020-09-30 | 682.7555 | TRUE
1.02A TPC | S121400 Procure TPC GEM HV Power Supplies - Delivery Acceptance | Budget | 2021-09-30 | 125263.3717 | TRUE
1.02A TPC | S121400 Procure TPC GEM HV Power Supplies - Delivery Acceptance | Progress | 2020-09-30 | 62631.6858 | TRUE
1.02A TPC | S121400 Procure TPC GEM HV Power Supplies - Delivery Acceptance | Progress | 2021-09-30 | 62631.6858 | TRUE
1.02A TPC | S121500 Procure TPC GEM HV Membrane Power Supply - Delivery Acceptance | Budget | 2021-09-30 | 12245.2194 | TRUE
1.02A TPC | S121500 Procure TPC GEM HV Membrane Power Supply - Delivery Acceptance | Progress | 2021-09-30 | 12245.2194 | TRUE
1.02A TPC | S121605 TPC Assembly Mechanical Engineering Support | Budget | 2021-09-30 | 108323.4232 | TRUE
1.02A TPC | S121605 TPC Assembly Mechanical Engineering Support | Budget | 2022-09-30 | 47910.8129 | TRUE
1.02A TPC | S121605 TPC Assembly Mechanical Engineering Support | Progress | 2021-09-30 | 53527.7647 | TRUE
1.02A TPC | S121605 TPC Assembly Mechanical Engineering Support | EAC | 2021-09-30 | 50655.5062 | TRUE
1.02A TPC | S121605 TPC Assembly Mechanical Engineering Support | EAC | 2022-09-30 | 39131.3786 | TRUE
1.02A TPC | S121650 Procure Piping Fittings | Budget | 2021-09-30 | 1279.0741 | TRUE
1.02A TPC | S121650 Procure Piping Fittings | EAC | 2021-09-30 | 1279.0741 | TRUE
1.02A TPC | S121950 TPC Assembly technical Support | Budget | 2021-09-30 | 21212.5063 | TRUE
1.02A TPC | S121950 TPC Assembly technical Support | Budget | 2022-09-30 | 2041.2034 | TRUE
1.02A TPC | S121950 TPC Assembly technical Support | EAC | 2021-09-30 | 11224.7996 | TRUE
1.02A TPC | S121950 TPC Assembly technical Support | EAC | 2022-09-30 | 12228.6642 | TRUE
1.02A TPC | S122202 Prepare TPC R1 Factory Tooling Labor Split | Budget | 2019-09-30 | 295.0683 | TRUE
1.02A TPC | S122202 Prepare TPC R1 Factory Tooling Labor Split | Progress | 2019-09-30 | 295.0683 | TRUE
1.02A TPC | S122302 Prepare TPC R1 Factory Tooling M&S Split | Budget | 2019-09-30 | 2647.8361 | TRUE
1.02A TPC | S122302 Prepare TPC R1 Factory Tooling M&S Split | Progress | 2019-09-30 | 2647.8361 | TRUE
1.02A TPC | S123600 Test TPC R1 Pre-Production Module | Budget | 2019-09-30 | 7868.4874 | TRUE
1.02A TPC | S123600 Test TPC R1 Pre-Production Module | Progress | 2019-09-30 | 7868.4874 | TRUE
1.02A TPC | S123700 Common production line & QA certification | Budget | 2019-09-30 | 61575.9806 | TRUE
1.02A TPC | S123700 Common production line & QA certification | Budget | 2020-09-30 | 44592.4669 | TRUE
1.02A TPC | S123700 Common production line & QA certification | Progress | 2019-09-30 | 95358.1525 | TRUE
1.02A TPC | S123700 Common production line & QA certification | Progress | 2020-09-30 | 10810.295 | TRUE
1.02A TPC | S124500 Procure TPC R1 Module Parts (Frames) - Delivery Acceptance | Budget | 2020-09-30 | 16614.8545 | TRUE
1.02A TPC | S124500 Procure TPC R1 Module Parts (Frames) - Delivery Acceptance | Progress | 2020-09-30 | 16614.8545 | TRUE
1.02A TPC | S124800 Procure TPC R1 Module Parts (Strongbacks) - Delivery Acceptance | Budget | 2020-09-30 | 9349.1983 | TRUE
1.02A TPC | S124800 Procure TPC R1 Module Parts (Strongbacks) - Delivery Acceptance | Progress | 2020-09-30 | 9349.1983 | TRUE
1.02A TPC | S125100 Procure TPC R1 Module Parts (Padplanes) - Delivery Acceptance | Budget | 2020-09-30 | 50113.1139 | TRUE
1.02A TPC | S125100 Procure TPC R1 Module Parts (Padplanes) - Delivery Acceptance | Progress | 2021-09-30 | 50113.1139 | TRUE
1.02A TPC | S125400 Procure TPC R1 Module Parts (Grids) - Delivery Acceptance | Budget | 2020-09-30 | 11148.259 | TRUE
1.02A TPC | S125400 Procure TPC R1 Module Parts (Grids) - Delivery Acceptance | Progress | 2020-09-30 | 11148.259 | TRUE
1.02A TPC | S125500 Build TPC R1 Modules | Budget | 2020-09-30 | 1460.3193 | TRUE
1.02A TPC | S125500 Build TPC R1 Modules | Budget | 2021-09-30 | 61669.2825 | TRUE
1.02A TPC | S125500 Build TPC R1 Modules | Progress | 2021-09-30 | 53653.5901 | TRUE
1.02A TPC | S125500 Build TPC R1 Modules | EAC | 2021-09-30 | 9476.0117 | TRUE
1.02A TPC | S125600 Test TPC R1 Modules | Budget | 2021-09-30 | 63173.4114 | TRUE
1.02A TPC | S125600 Test TPC R1 Modules | Progress | 2021-09-30 | 53697.3997 | TRUE
1.02A TPC | S125600 Test TPC R1 Modules | EAC | 2021-09-30 | 9476.0117 | TRUE
1.02A TPC | S126502 Prepare TPC R2 Factory Tooling M&S Split | Budget | 2019-09-30 | 3971.7542 | TRUE
1.02A TPC | S126502 Prepare TPC R2 Factory Tooling M&S Split | Progress | 2019-09-30 | 3971.7542 | TRUE
1.02A TPC | S127602 Procure TPC R2 Pre-Production Module GEMs M&S Split | Budget | 2019-09-30 | 2758.1626 | TRUE
1.02A TPC | S127602 Procure TPC R2 Pre-Production Module GEMs M&S Split | Progress | 2019-09-30 | 2758.1626 | TRUE
1.02A TPC | S128500 Procure TPC R2 Module Prod. Parts (Frames) - Delivery Acceptance | Budget | 2020-09-30 | 16614.8545 | TRUE
1.02A TPC | S128500 Procure TPC R2 Module Prod. Parts (Frames) - Delivery Acceptance | Progress | 2020-09-30 | 16614.8545 | TRUE
1.02A TPC | S128800 Procure TPC R2 Module Prod. Parts (Strongbacks) - Delivery Acceptance | Budget | 2020-09-30 | 10450.7105 | TRUE
1.02A TPC | S128800 Procure TPC R2 Module Prod. Parts (Strongbacks) - Delivery Acceptance | Progress | 2020-09-30 | 10450.7105 | TRUE
1.02A TPC | S129100 Procure TPC R2 Module Prod. Parts (Padplanes) - Delivery Acceptance | Budget | 2020-09-30 | 60298.6876 | TRUE
1.02A TPC | S129100 Procure TPC R2 Module Prod. Parts (Padplanes) - Delivery Acceptance | Progress | 2020-09-30 | 6029.8688 | TRUE
1.02A TPC | S129100 Procure TPC R2 Module Prod. Parts (Padplanes) - Delivery Acceptance | Progress | 2021-09-30 | 54268.8189 | TRUE
1.02A TPC | S129400 Procure TPC R2 Module Prod. Parts (Grids) - Delivery Acceptance | Budget | 2020-09-30 | 11148.259 | TRUE
1.02A TPC | S129400 Procure TPC R2 Module Prod. Parts (Grids) - Delivery Acceptance | Progress | 2020-09-30 | 11148.259 | TRUE
1.02A TPC | S130102 Prepare TPC R3a Factory Tooling M&S Split | Budget | 2019-09-30 | 3971.7542 | TRUE
1.02A TPC | S130102 Prepare TPC R3a Factory Tooling M&S Split | Progress | 2019-09-30 | 3971.7542 | TRUE
1.02A TPC | S130502 Prepare TPC R3b Factory Tooling M&S Split | Budget | 2019-09-30 | 3971.7542 | TRUE
1.02A TPC | S130502 Prepare TPC R3b Factory Tooling M&S Split | Progress | 2019-09-30 | 3971.7542 | TRUE
1.02A TPC | S131000 Procure TPC R3 Pre-Production Module frames - M&S | Budget | 2019-09-30 | 2206.5301 | TRUE
1.02A TPC | S131000 Procure TPC R3 Pre-Production Module frames - M&S | Progress | 2019-09-30 | 2206.5301 | TRUE
1.02A TPC | S131600 Procure TPC R3 Pre-Production Module GEMs M&S | Budget | 2019-09-30 | 11032.6505 | TRUE
1.02A TPC | S131600 Procure TPC R3 Pre-Production Module GEMs M&S | Progress | 2019-09-30 | 11032.6505 | TRUE
1.02A TPC | S132700 Procure TPC R3 Module Prod. Parts (Frames) - Delivery Acceptance | Budget | 2020-09-30 | 19138.7739 | TRUE
1.02A TPC | S132700 Procure TPC R3 Module Prod. Parts (Frames) - Delivery Acceptance | Progress | 2020-09-30 | 19138.7739 | TRUE
1.02A TPC | S133000 Procure TPC R3 Module Prod. Parts (Strongbacks) - Delivery Acceptance | Budget | 2020-09-30 | 12246.3574 | TRUE
1.02A TPC | S133000 Procure TPC R3 Module Prod. Parts (Strongbacks) - Delivery Acceptance | Progress | 2020-09-30 | 12246.3574 | TRUE
1.02A TPC | S133300 Procure TPC R3 Module Prod. Parts (Padplanes) - Delivery Acceptance | Budget | 2020-09-30 | 81668.934 | TRUE
1.02A TPC | S133300 Procure TPC R3 Module Prod. Parts (Padplanes) - Delivery Acceptance | Progress | 2020-09-30 | 81668.934 | TRUE
1.02A TPC | S133600 Procure TPC R3 Module Prod. Parts (Grids) - Delivery Acceptance | Budget | 2020-09-30 | 11706.9805 | TRUE
1.02A TPC | S133600 Procure TPC R3 Module Prod. Parts (Grids) - Delivery Acceptance | Progress | 2020-09-30 | 11706.9805 | TRUE
1.02A TPC | S136500 Procure TPC FEE Cooling System - Delivery Acceptance | Budget | 2021-09-30 | 69820.9644 | TRUE
1.02A TPC | S136500 Procure TPC FEE Cooling System - Delivery Acceptance | Progress | 2021-09-30 | 12428.1317 | TRUE
1.02A TPC | S136500 Procure TPC FEE Cooling System - Delivery Acceptance | EAC | 2021-09-30 | 57392.8328 | TRUE
1.02A TPC | S137000 v2 Procure TPC FEE preproducion prototype components M&S | Budget | 2020-09-30 | 6680.7623 | TRUE
1.02A TPC | S137000 v2 Procure TPC FEE preproducion prototype components M&S | Progress | 2020-09-30 | 3340.3812 | TRUE
1.02A TPC | S137000 v2 Procure TPC FEE preproducion prototype components M&S | Progress | 2021-09-30 | 3340.3812 | TRUE
1.02A TPC | S137200 v2 Fabricate TPC FEE preproduction prototype boards M&S | Budget | 2020-09-30 | 1679.5785 | TRUE
1.02A TPC | S137200 v2 Fabricate TPC FEE preproduction prototype boards M&S | Progress | 2020-09-30 | 1679.5785 | TRUE
1.02A TPC | S137400 v2 Modify TPC FEE Test Stand M&S | Budget | 2020-09-30 | 9103.4063 | TRUE
1.02A TPC | S137400 v2 Modify TPC FEE Test Stand M&S | Progress | 2020-09-30 | 9103.4063 | TRUE
1.02A TPC | S137600 v2 Assemble and test TPC FEE preproduction prototype M&S | Budget | 2020-09-30 | 6406.5222 | TRUE
1.02A TPC | S137600 v2 Assemble and test TPC FEE preproduction prototype M&S | Progress | 2020-09-30 | 3203.2611 | TRUE
1.02A TPC | S137600 v2 Assemble and test TPC FEE preproduction prototype M&S | Progress | 2021-09-30 | 3203.2611 | TRUE
1.02A TPC | S139720 Procure second phase of SAMPA development - Delivery of First Chip Layout | Budget | 2019-09-30 | 38614.2768 | TRUE
1.02A TPC | S139720 Procure second phase of SAMPA development - Delivery of First Chip Layout | Progress | 2019-09-30 | 38614.2768 | TRUE
1.02A TPC | S139725 Procure second phase of SAMPA development - Delivery of Final Review of test results | Budget | 2019-09-30 | 77228.5535 | TRUE
1.02A TPC | S139725 Procure second phase of SAMPA development - Delivery of Final Review of test results | Progress | 2019-09-30 | 77228.5535 | TRUE
1.02A TPC | S139730 Procure second phase of SAMPA development - Delivery of Eng Design Review | Budget | 2019-09-30 | 52405.0899 | TRUE
1.02A TPC | S139730 Procure second phase of SAMPA development - Delivery of Eng Design Review | Progress | 2019-09-30 | 52405.0899 | TRUE
1.02A TPC | S139735 Procure second phase of SAMPA development - Delivery of Eng Run Preparation | Budget | 2019-09-30 | 20962.036 | TRUE
1.02A TPC | S139735 Procure second phase of SAMPA development - Delivery of Eng Run Preparation | Budget | 2020-09-30 | 1137.9258 | TRUE
1.02A TPC | S139735 Procure second phase of SAMPA development - Delivery of Eng Run Preparation | Progress | 2019-09-30 | 22099.9618 | TRUE
1.02A TPC | S140400 Procure Engineering Run of Full SAMPA Chip - Delivery Acceptance | Budget | 2020-09-30 | 265136.7091 | TRUE
1.02A TPC | S140400 Procure Engineering Run of Full SAMPA Chip - Delivery Acceptance | Progress | 2020-09-30 | 265136.7091 | TRUE
1.02A TPC | S140500 Populate v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip | Budget | 2020-09-30 | 3413.7774 | TRUE
1.02A TPC | S140500 Populate v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip | Progress | 2020-09-30 | 3413.7774 | TRUE
1.02A TPC | S141500 Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Delivery Acceptance | Budget | 2021-09-30 | 34429.3786 | TRUE
1.02A TPC | S141500 Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Delivery Acceptance | Progress | 2021-09-30 | 11430.5537 | TRUE
1.02A TPC | S141500 Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Delivery Acceptance | EAC | 2021-09-30 | 22998.8249 | TRUE
1.02A TPC | S141800 Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | Budget | 2021-09-30 | 309547.5403 | TRUE
1.02A TPC | S141800 Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | Progress | 2021-09-30 | 263115.4093 | TRUE
1.02A TPC | S141800 Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | EAC | 2021-09-30 | 46432.1311 | TRUE
1.02A TPC | S142500 Procure TPC FEE LV Power Supplies - Delivery Acceptance | Budget | 2021-09-30 | 220595.0165 | TRUE
1.02A TPC | S142500 Procure TPC FEE LV Power Supplies - Delivery Acceptance | Progress | 2021-09-30 | 132357.0099 | TRUE
1.02A TPC | S142500 Procure TPC FEE LV Power Supplies - Delivery Acceptance | EAC | 2021-09-30 | 88238.0066 | TRUE
1.02A TPC | S143200 Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | Budget | 2021-09-30 | 175243.5986 | TRUE
1.02A TPC | S143200 Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | EAC | 2021-09-30 | 87621.7993 | TRUE
1.02A TPC | S143200 Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | EAC | 2022-09-30 | 89374.2353 | TRUE
1.02A TPC | S143250 TPC Front End Electronics | Budget | 2021-09-30 | 174102.6459 | TRUE
1.02A TPC | S143250 TPC Front End Electronics | Progress | 2021-09-30 | 57802.0784 | TRUE
1.02A TPC | S143250 TPC Front End Electronics | EAC | 2021-09-30 | 116300.5675 | TRUE
1.02A TPC | S143270 TPC FEE Electrical Engineering Support 1 | Budget | 2021-09-30 | 87809.6923 | TRUE
1.02A TPC | S143270 TPC FEE Electrical Engineering Support 1 | Budget | 2022-09-30 | 31921.4058 | TRUE
1.02A TPC | S143270 TPC FEE Electrical Engineering Support 1 | Progress | 2021-09-30 | 43908.9784 | TRUE
1.02A TPC | S143270 TPC FEE Electrical Engineering Support 1 | EAC | 2021-09-30 | 44114.6838 | TRUE
1.02A TPC | S143270 TPC FEE Electrical Engineering Support 1 | EAC | 2022-09-30 | 31701.0168 | TRUE
1.02A TPC | S145700 Procure TPC DAM Felix 2.0 Boards Throughput - Delivery Acceptance | Budget | 2019-09-30 | 81116.4596 | TRUE
1.02A TPC | S145700 Procure TPC DAM Felix 2.0 Boards Throughput - Delivery Acceptance | Progress | 2019-09-30 | 56781.5217 | TRUE
1.02A TPC | S145700 Procure TPC DAM Felix 2.0 Boards Throughput - Delivery Acceptance | Progress | 2020-09-30 | 24334.9379 | TRUE
1.02A TPC | S145750 Procure Full Set of Data Fibers for Design Validation - M&S | Budget | 2019-09-30 | 3172.9903 | TRUE
1.02A TPC | S145750 Procure Full Set of Data Fibers for Design Validation - M&S | Progress | 2019-09-30 | 3172.9903 | TRUE
1.02A TPC | S146300 Miscellaneous Parts for TPC DAM FPGA Algorithm Development - Round 1 | Budget | 2019-09-30 | 2827.6683 | TRUE
1.02A TPC | S146300 Miscellaneous Parts for TPC DAM FPGA Algorithm Development - Round 1 | Progress | 2019-09-30 | 2827.6683 | TRUE
1.02A TPC | S147300 Procure TPC DAM Felix 2.0 Boards - Delivery Acceptance | Budget | 2021-09-30 | 151309.1275 | TRUE
1.02A TPC | S147300 Procure TPC DAM Felix 2.0 Boards - Delivery Acceptance | Progress | 2021-09-30 | 121047.302 | TRUE
1.02A TPC | S147300 Procure TPC DAM Felix 2.0 Boards - Delivery Acceptance | EAC | 2021-09-30 | 30261.8255 | TRUE
1.02A TPC | S147370 Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Delivery Acceptance | Budget | 2021-09-30 | 93719.4543 | TRUE
1.02A TPC | S147370 Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Delivery Acceptance | EAC | 2021-09-30 | 93719.4543 | TRUE
1.02A TPC | S147380 TPC DAM Electrical Engineering Support | Budget | 2021-09-30 | 35442.9112 | TRUE
1.02A TPC | S147380 TPC DAM Electrical Engineering Support | Budget | 2022-09-30 | 12884.5407 | TRUE
1.02A TPC | S147380 TPC DAM Electrical Engineering Support | Progress | 2021-09-30 | 17262.7827 | TRUE
1.02A TPC | S147380 TPC DAM Electrical Engineering Support | EAC | 2021-09-30 | 18003.1636 | TRUE
1.02A TPC | S147380 TPC DAM Electrical Engineering Support | EAC | 2022-09-30 | 13066.8146 | TRUE
1.02A TPC | S148400 Procure TPC EDBC Computers & Peripherals - Delivery Acceptance | Budget | 2021-09-30 | 244768.5885 | TRUE
1.02A TPC | S148400 Procure TPC EDBC Computers & Peripherals - Delivery Acceptance | EAC | 2021-09-30 | 244768.5885 | TRUE
1.02A TPC | S149600 Procure TPC Lasers - Delivery Acceptance | Budget | 2020-09-30 | 165955.0973 | TRUE
1.02A TPC | S149600 Procure TPC Lasers - Delivery Acceptance | Progress | 2021-09-30 | 82977.5486 | TRUE
1.02A TPC | S149600 Procure TPC Lasers - Delivery Acceptance | EAC | 2021-09-30 | 84637.0996 | TRUE
1.02A TPC | S149650 TPC Diffuse Lasers | Budget | 2021-09-30 | 232136.8612 | TRUE
1.02A TPC | S149650 TPC Diffuse Lasers | Progress | 2021-09-30 | 116068.4306 | TRUE
1.02A TPC | S149650 TPC Diffuse Lasers | EAC | 2021-09-30 | 116068.4306 | TRUE
1.02A TPC | S150300 Procure TPC Optics with Mirrors - Delivery Acceptance | Budget | 2020-09-30 | 66910.0365 | TRUE
1.02A TPC | S150300 Procure TPC Optics with Mirrors - Delivery Acceptance | Progress | 2021-09-30 | 33455.0182 | TRUE
1.02A TPC | S150300 Procure TPC Optics with Mirrors - Delivery Acceptance | EAC | 2021-09-30 | 34124.1186 | TRUE
1.02A TPC | S150500 Procure TPC mirror bundles with supports M&S | Budget | 2019-09-30 | 275.8163 | TRUE
1.02A TPC | S150500 Procure TPC mirror bundles with supports M&S | Budget | 2020-09-30 | 16784.4054 | TRUE
1.02A TPC | S150500 Procure TPC mirror bundles with supports M&S | Progress | 2021-09-30 | 8525.7782 | TRUE
1.02A TPC | S150500 Procure TPC mirror bundles with supports M&S | EAC | 2021-09-30 | 8705.1323 | TRUE
1.02A TPC | S150800 Install &Test TPC Laser safety interlocks M&S | Budget | 2020-09-30 | 2275.8516 | TRUE
1.02A TPC | S150800 Install &Test TPC Laser safety interlocks M&S | EAC | 2021-09-30 | 2321.3686 | TRUE
1.02A TPC | S151600 Procure TPC Gas System mass flow meters M&S | Budget | 2020-09-30 | 7773.1711 | TRUE
1.02A TPC | S151600 Procure TPC Gas System mass flow meters M&S | Progress | 2020-09-30 | 7773.1711 | TRUE
1.02A TPC | S152300 Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | Budget | 2020-09-30 | 37591.3785 | TRUE
1.02A TPC | S152300 Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | Progress | 2021-09-30 | 26313.9649 | TRUE
1.02A TPC | S152300 Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | EAC | 2021-09-30 | 11502.9618 | TRUE
1.02A TPC | S152500 Procure TPC Gas System scrubbers M&S | Budget | 2020-09-30 | 8792.7526 | TRUE
1.02A TPC | S152500 Procure TPC Gas System scrubbers M&S | Progress | 2020-09-30 | 4396.3763 | TRUE
1.02A TPC | S152500 Procure TPC Gas System scrubbers M&S | Progress | 2021-09-30 | 4396.3763 | TRUE
1.02A TPC | S152700 Procure TPC Gas System oxygen and water sensors M&S | Budget | 2020-09-30 | 12703.8035 | TRUE
1.02A TPC | S152700 Procure TPC Gas System oxygen and water sensors M&S | Progress | 2020-09-30 | 6351.9018 | TRUE
1.02A TPC | S152700 Procure TPC Gas System oxygen and water sensors M&S | Progress | 2021-09-30 | 6351.9018 | TRUE
1.02A TPC | S153000 Procure TPC Gas System Computer Controller M&S | Budget | 2020-09-30 | 19144.2034 | TRUE
1.02A TPC | S153000 Procure TPC Gas System Computer Controller M&S | Budget | 2021-09-30 | 1830.6644 | TRUE
1.02A TPC | S153000 Procure TPC Gas System Computer Controller M&S | EAC | 2021-09-30 | 14238.5013 | TRUE
1.02A TPC | S153000 Procure TPC Gas System Computer Controller M&S | EAC | 2022-09-30 | 7261.6357 | TRUE
1.02A TPC | S153700 Procure TPC Gas System Components for Installation - Delivery Acceptance | Budget | 2021-09-30 | 39563.0853 | TRUE
1.02A TPC | S153700 Procure TPC Gas System Components for Installation - Delivery Acceptance | Progress | 2021-09-30 | 27694.1597 | TRUE
1.02A TPC | S153700 Procure TPC Gas System Components for Installation - Delivery Acceptance | EAC | 2021-09-30 | 11868.9256 | TRUE
1.02A TPC | S155000 Procure TPC Cooling System Equipment - Delivery Acceptance | Budget | 2020-09-30 | 50454.4916 | TRUE
1.02A TPC | S155000 Procure TPC Cooling System Equipment - Delivery Acceptance | Progress | 2021-09-30 | 50454.4916 | TRUE
1.02A TPC | S155700 Procure TPC Plumbing - Contract/PO M&S | Budget | 2021-09-30 | 13541.7038 | TRUE
1.02A TPC | S155700 Procure TPC Plumbing - Contract/PO M&S | EAC | 2021-09-30 | 13541.7038 | TRUE
1.02A TPC | S155900 Set up TPC Cooling System computer controls M&S | Budget | 2021-09-30 | 12179.0604 | TRUE
1.02A TPC | S155900 Set up TPC Cooling System computer controls M&S | EAC | 2021-09-30 | 12179.0604 | TRUE
1.03A EMCal | 16702 sPHENIX OPC - ElectroMagnetic Calorimeter | Actuals | 2018-09-30 | 508996.36 | TRUE
1.03A EMCal | 16702 sPHENIX OPC - ElectroMagnetic Calorimeter | Actuals | 2019-09-30 | 904263.02 | TRUE
1.03A EMCal | 16702 sPHENIX OPC - ElectroMagnetic Calorimeter | Actuals | 2020-09-30 | 589640.99 | TRUE
1.03A EMCal | 16702 sPHENIX OPC - ElectroMagnetic Calorimeter | Actuals | 2021-09-30 | 73261.25 | TRUE
1.03A EMCal | 16702 sPHENIX OPC - ElectroMagnetic Calorimeter | EAC | 2018-09-30 | 508996.36 | TRUE
1.03A EMCal | 16702 sPHENIX OPC - ElectroMagnetic Calorimeter | EAC | 2019-09-30 | 904263.02 | TRUE
1.03A EMCal | 16702 sPHENIX OPC - ElectroMagnetic Calorimeter | EAC | 2020-09-30 | 589640.99 | TRUE
1.03A EMCal | 16702 sPHENIX OPC - ElectroMagnetic Calorimeter | EAC | 2021-09-30 | 73261.25 | TRUE
1.03A EMCal | 59708 sPHENIX MIE - 1.3 EMCal Blocks | Actuals | 2019-09-30 | 242866.32 | TRUE
1.03A EMCal | 59708 sPHENIX MIE - 1.3 EMCal Blocks | Actuals | 2020-09-30 | 1828708.5 | TRUE
1.03A EMCal | 59708 sPHENIX MIE - 1.3 EMCal Blocks | Actuals | 2021-09-30 | 696636.83 | TRUE
1.03A EMCal | 59708 sPHENIX MIE - 1.3 EMCal Blocks | EAC | 2019-09-30 | 242866.32 | TRUE
1.03A EMCal | 59708 sPHENIX MIE - 1.3 EMCal Blocks | EAC | 2020-09-30 | 1828708.5 | TRUE
1.03A EMCal | 59708 sPHENIX MIE - 1.3 EMCal Blocks | EAC | 2021-09-30 | 696636.83 | TRUE
1.03A EMCal | 59709 sPHENIX MIE - 1.3 EMCAl Modules & Sectors | Actuals | 2020-09-30 | 131203.81 | TRUE
1.03A EMCal | 59709 sPHENIX MIE - 1.3 EMCAl Modules & Sectors | Actuals | 2021-09-30 | 472073.82 | TRUE
1.03A EMCal | 59709 sPHENIX MIE - 1.3 EMCAl Modules & Sectors | EAC | 2020-09-30 | 131203.81 | TRUE
1.03A EMCal | 59709 sPHENIX MIE - 1.3 EMCAl Modules & Sectors | EAC | 2021-09-30 | 472073.82 | TRUE
1.03A EMCal | 59731 FY21 sPHX MIE - 1.3 EMCal Blocks | Actuals | 2021-09-30 | 1415.15 | TRUE
1.03A EMCal | 59731 FY21 sPHX MIE - 1.3 EMCal Blocks | EAC | 2021-09-30 | 1415.15 | TRUE
1.03A EMCal | 59732 FY21 SPHX MIE - 1.3 EMCAL Modules | Actuals | 2021-09-30 | 94922.92 | TRUE
1.03A EMCal | 59732 FY21 SPHX MIE - 1.3 EMCAL Modules | EAC | 2021-09-30 | 94922.92 | TRUE
1.03A EMCal | S1001879 Actuals - Nonlabor - sPHENIX EMCal FY19M8 | Budget | 2019-09-30 | 80811.9584 | TRUE
1.03A EMCal | S1001879 Actuals - Nonlabor - sPHENIX EMCal FY19M8 | Progress | 2019-09-30 | 80811.9584 | TRUE
1.03A EMCal | S156400 Actuals - Nonlabor - sPHENIX EMCal FY17 | Budget | 2017-09-30 | 45714.0043 | TRUE
1.03A EMCal | S156400 Actuals - Nonlabor - sPHENIX EMCal FY17 | Progress | 2019-09-30 | 45714.0043 | TRUE
1.03A EMCal | S156500 Actuals - Nonlabor - sPHENIX EMCal FY18 | Budget | 2018-09-30 | 463282.3548 | TRUE
1.03A EMCal | S156500 Actuals - Nonlabor - sPHENIX EMCal FY18 | Progress | 2019-09-30 | 463282.3548 | TRUE
1.03A EMCal | S156510 Actuals - Nonlabor - sPHENIX EMCal FY19M8 | Budget | 2019-09-30 | 699611.9661 | TRUE
1.03A EMCal | S156510 Actuals - Nonlabor - sPHENIX EMCal FY19M8 | Progress | 2019-09-30 | 699611.9661 | TRUE
1.03A EMCal | S161700 Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Delivery acceptance Phase 2 of 2 Phases (Sectors 4-12) | Budget | 2019-09-30 | 242078.4174 | TRUE
1.03A EMCal | S161700 Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Delivery acceptance Phase 2 of 2 Phases (Sectors 4-12) | Progress | 2019-09-30 | 242078.4174 | TRUE
1.03A EMCal | S164702 Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Delivery acceptance Split | Budget | 2019-09-30 | 36671.427 | TRUE
1.03A EMCal | S164702 Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Delivery acceptance Split | Progress | 2019-09-30 | 7334.2854 | TRUE
1.03A EMCal | S164702 Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Delivery acceptance Split | Progress | 2020-09-30 | 29337.1416 | TRUE
1.03A EMCal | S165802 Prepare fiber assemblies for EMCal Prepro Sectors 1-12 Blocks Split | Budget | 2019-09-30 | 11004.3648 | TRUE
1.03A EMCal | S165802 Prepare fiber assemblies for EMCal Prepro Sectors 1-12 Blocks Split | Progress | 2019-09-30 | 11004.3648 | TRUE
1.03A EMCal | S165902 Fabricate EMCAL Prepro blocks sector 1 Split | Budget | 2020-09-30 | 7103.6284 | TRUE
1.03A EMCal | S165902 Fabricate EMCAL Prepro blocks sector 1 Split | Progress | 2019-09-30 | 7103.6284 | TRUE
1.03A EMCal | S166000 Fabricate EMCAL Prepro blocks sector 2 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166000 Fabricate EMCAL Prepro blocks sector 2 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166100 Fabricate EMCAL Prepro blocks sector 3 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166100 Fabricate EMCAL Prepro blocks sector 3 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166200 Fabricate EMCAL Prepro blocks sector 4 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166200 Fabricate EMCAL Prepro blocks sector 4 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166300 Fabricate EMCAL Prepro blocks sector 5 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166300 Fabricate EMCAL Prepro blocks sector 5 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166400 Fabricate EMCAL Prepro blocks sector 6 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166400 Fabricate EMCAL Prepro blocks sector 6 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166500 Fabricate EMCAL Prepro blocks sector 7 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166500 Fabricate EMCAL Prepro blocks sector 7 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166600 Fabricate EMCAL Prepro blocks sector 8 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166600 Fabricate EMCAL Prepro blocks sector 8 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166700 Fabricate EMCAL Prepro blocks sector 9 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166700 Fabricate EMCAL Prepro blocks sector 9 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166800 Fabricate EMCAL Prepro blocks sector 10 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166800 Fabricate EMCAL Prepro blocks sector 10 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166900 Fabricate EMCAL Prepro blocks sector 11 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S166900 Fabricate EMCAL Prepro blocks sector 11 | Progress | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S167000 Fabricate EMCAL Prepro blocks sector 12 | Budget | 2020-09-30 | 9425.1431 | TRUE
1.03A EMCal | S167000 Fabricate EMCAL Prepro blocks sector 12 | Progress | 2020-09-30 | 6597.6001 | TRUE
1.03A EMCal | S167000 Fabricate EMCAL Prepro blocks sector 12 | Progress | 2021-09-30 | 2827.5429 | TRUE
1.03A EMCal | S167100 Pack and ship EMCAL blocks for Prepro sector 1 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S167100 Pack and ship EMCAL blocks for Prepro sector 1 to BNL Purchased Services | Progress | 2019-09-30 | 216.4883 | TRUE
1.03A EMCal | S167100 Pack and ship EMCAL blocks for Prepro sector 1 to BNL Purchased Services | Progress | 2020-09-30 | 649.4647 | TRUE
1.03A EMCal | S167200 Pack and ship EMCAL blocks for Prepro sector 1 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S167200 Pack and ship EMCAL blocks for Prepro sector 1 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S167300 Pack and ship EMCAL blocks for Prepro sector 2 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S167300 Pack and ship EMCAL blocks for Prepro sector 2 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S167400 Pack and ship EMCAL blocks for Prepro sector 2 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S167400 Pack and ship EMCAL blocks for Prepro sector 2 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S167500 Pack and ship EMCAL blocks for Prepro sector 3 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S167500 Pack and ship EMCAL blocks for Prepro sector 3 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S167600 Pack and ship EMCAL blocks for Prepro sector 3 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S167600 Pack and ship EMCAL blocks for Prepro sector 3 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S167700 Pack and ship EMCAL blocks for Prepro sector 4 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S167700 Pack and ship EMCAL blocks for Prepro sector 4 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S167800 Pack and ship EMCAL blocks for Prepro sector 4 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S167800 Pack and ship EMCAL blocks for Prepro sector 4 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S167900 Pack and ship EMCAL blocks for Prepro sector 5 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S167900 Pack and ship EMCAL blocks for Prepro sector 5 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168000 Pack and ship EMCAL blocks for Prepro sector 5 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168000 Pack and ship EMCAL blocks for Prepro sector 5 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168100 Pack and ship EMCAL blocks for Prepro sector 6 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168100 Pack and ship EMCAL blocks for Prepro sector 6 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168200 Pack and ship EMCAL blocks for Prepro sector 6 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168200 Pack and ship EMCAL blocks for Prepro sector 6 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168300 Pack and ship EMCAL blocks for Prepro sector 7 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168300 Pack and ship EMCAL blocks for Prepro sector 7 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168400 Pack and ship EMCAL blocks for Prepro sector 7 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168400 Pack and ship EMCAL blocks for Prepro sector 7 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168500 Pack and ship EMCAL blocks for Prepro sector 8 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168500 Pack and ship EMCAL blocks for Prepro sector 8 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168600 Pack and ship EMCAL blocks for Prepro sector 8 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168600 Pack and ship EMCAL blocks for Prepro sector 8 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168700 Pack and ship EMCAL blocks for Prepro sector 9 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168700 Pack and ship EMCAL blocks for Prepro sector 9 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168800 Pack and ship EMCAL blocks for Prepro sector 9 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168800 Pack and ship EMCAL blocks for Prepro sector 9 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S168900 Pack and ship EMCAL blocks for Prepro sector 10 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S168900 Pack and ship EMCAL blocks for Prepro sector 10 to BNL Purchased Services | Progress | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S169000 Pack and ship EMCAL blocks for Prepro sector 10 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S169000 Pack and ship EMCAL blocks for Prepro sector 10 to BNL M&S | Progress | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S169100 Pack and ship EMCAL blocks for Prepro sector 11 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S169100 Pack and ship EMCAL blocks for Prepro sector 11 to BNL Purchased Services | Progress | 2021-09-30 | 865.953 | TRUE
1.03A EMCal | S169200 Pack and ship EMCAL blocks for Prepro sector 11 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S169200 Pack and ship EMCAL blocks for Prepro sector 11 to BNL M&S | Progress | 2021-09-30 | 1228.9599 | TRUE
1.03A EMCal | S169300 Pack and ship EMCAL blocks for Prepro sector 12 to BNL Purchased Services | Budget | 2020-09-30 | 865.953 | TRUE
1.03A EMCal | S169300 Pack and ship EMCAL blocks for Prepro sector 12 to BNL Purchased Services | Progress | 2021-09-30 | 865.953 | TRUE
1.03A EMCal | S169400 Pack and ship EMCAL blocks for Prepro sector 12 to BNL M&S | Budget | 2020-09-30 | 1228.9599 | TRUE
1.03A EMCal | S169400 Pack and ship EMCAL blocks for Prepro sector 12 to BNL M&S | Progress | 2021-09-30 | 1228.9599 | TRUE
1.03A EMCal | S169500 Establish EMCAL final blocks contract with UIUC | Budget | 2019-09-30 | 1083.4064 | TRUE
1.03A EMCal | S169500 Establish EMCAL final blocks contract with UIUC | Progress | 2019-09-30 | 54.1703 | TRUE
1.03A EMCal | S169500 Establish EMCAL final blocks contract with UIUC | Progress | 2020-09-30 | 1029.2361 | TRUE
1.03A EMCal | S170200 Procure EMCAL W Powder for Final Blocks - Sectors 13-38 - Delivery Acceptance | Budget | 2020-09-30 | 540981.3 | TRUE
1.03A EMCal | S170200 Procure EMCAL W Powder for Final Blocks - Sectors 13-38 - Delivery Acceptance | Progress | 2020-09-30 | 540981.3 | TRUE
1.03A EMCal | S170210 Procure EMCAL W Powder for Final Blocks - Sectors 39-64 - Delivery Acceptance | Budget | 2020-09-30 | 540981.3 | TRUE
1.03A EMCal | S170210 Procure EMCAL W Powder for Final Blocks - Sectors 39-64 - Delivery Acceptance | Progress | 2020-09-30 | 540981.3 | TRUE
1.03A EMCal | S171003 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 3 | Budget | 2019-09-30 | 40405.9792 | TRUE
1.03A EMCal | S171003 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 3 | Progress | 2019-09-30 | 40405.9792 | TRUE
1.03A EMCal | S171004 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 4 | Budget | 2019-09-30 | 40405.9792 | TRUE
1.03A EMCal | S171004 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 4 | Progress | 2019-09-30 | 40405.9792 | TRUE
1.03A EMCal | S171005 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 5 | Budget | 2019-09-30 | 40405.9792 | TRUE
1.03A EMCal | S171005 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 5 | Progress | 2019-09-30 | 40405.9792 | TRUE
1.03A EMCal | S171006 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 6 | Budget | 2019-09-30 | 40405.9792 | TRUE
1.03A EMCal | S171006 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 6 | Progress | 2019-09-30 | 40405.9792 | TRUE
1.03A EMCal | S171007 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 7 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171007 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 7 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171008 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 8 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171008 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 8 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171009 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 9 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171009 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 9 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171010 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 10 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171010 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 10 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171011 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 11 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171011 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 11 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171012 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 12 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171012 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 12 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171013 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 13 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171013 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 13 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171014 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 14 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171014 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 14 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171015 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 15 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171015 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 15 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171016 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 16 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171016 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 16 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171017 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 17 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171017 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 17 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171018 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 18 | Budget | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171018 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 18 | Progress | 2020-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171019 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 19 | Budget | 2021-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171019 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 19 | Progress | 2021-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171020 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 20 | Budget | 2021-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171020 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 20 | Progress | 2021-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171021 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 21 | Budget | 2021-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171021 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 21 | Progress | 2021-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171022 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 22 | Budget | 2021-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171022 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 22 | Progress | 2021-09-30 | 40858.2296 | TRUE
1.03A EMCal | S171023 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 23 | Budget | 2021-09-30 | 38234.3066 | TRUE
1.03A EMCal | S171023 Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 23 | Progress | 2021-09-30 | 38234.3066 | TRUE
1.03A EMCal | S171200 Procure EMCAL Epoxy for Final Blocks - Provide Requirements to Procurement | Budget | 2020-09-30 | 1316.3885 | TRUE
1.03A EMCal | S171200 Procure EMCAL Epoxy for Final Blocks - Provide Requirements to Procurement | Progress | 2020-09-30 | 1316.3885 | TRUE
1.03A EMCal | S171800 Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | Budget | 2020-09-30 | 31359.5415 | TRUE
1.03A EMCal | S171800 Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | Budget | 2021-09-30 | 73232.782 | TRUE
1.03A EMCal | S171800 Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | Progress | 2020-09-30 | 16505.0219 | TRUE
1.03A EMCal | S171800 Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | Progress | 2021-09-30 | 40738.5202 | TRUE
1.03A EMCal | S171800 Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | EAC | 2021-09-30 | 47348.7815 | TRUE
1.03A EMCal | S172500 Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | Budget | 2020-09-30 | 11342.1615 | TRUE
1.03A EMCal | S172500 Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | Budget | 2021-09-30 | 18875.7446 | TRUE
1.03A EMCal | S172500 Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | Progress | 2020-09-30 | 5969.5587 | TRUE
1.03A EMCal | S172500 Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | Progress | 2021-09-30 | 16637.1601 | TRUE
1.03A EMCal | S172500 Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | EAC | 2021-09-30 | 7611.1873 | TRUE
1.03A EMCal | S172600 Set up factory for final blocks Purchased Services | Budget | 2019-09-30 | 3008.593 | TRUE
1.03A EMCal | S172600 Set up factory for final blocks Purchased Services | Budget | 2020-09-30 | 4008.01 | TRUE
1.03A EMCal | S172600 Set up factory for final blocks Purchased Services | Progress | 2019-09-30 | 4517.0622 | TRUE
1.03A EMCal | S172600 Set up factory for final blocks Purchased Services | Progress | 2020-09-30 | 2499.5408 | TRUE
1.03A EMCal | S172700 Set up factory for final blocks M&S | Budget | 2019-09-30 | 1224.7368 | TRUE
1.03A EMCal | S172700 Set up factory for final blocks M&S | Budget | 2020-09-30 | 1615.7385 | TRUE
1.03A EMCal | S172700 Set up factory for final blocks M&S | Progress | 2019-09-30 | 1832.842 | TRUE
1.03A EMCal | S172700 Set up factory for final blocks M&S | Progress | 2020-09-30 | 1007.6333 | TRUE
1.03A EMCal | S172800 Prepare fiber assemblies for final blocks | Budget | 2019-09-30 | 8945.6501 | TRUE
1.03A EMCal | S172800 Prepare fiber assemblies for final blocks | Budget | 2020-09-30 | 83521.5833 | TRUE
1.03A EMCal | S172800 Prepare fiber assemblies for final blocks | Budget | 2021-09-30 | 71289.4965 | TRUE
1.03A EMCal | S172800 Prepare fiber assemblies for final blocks | Progress | 2019-09-30 | 32038.8688 | TRUE
1.03A EMCal | S172800 Prepare fiber assemblies for final blocks | Progress | 2020-09-30 | 55097.6246 | TRUE
1.03A EMCal | S172800 Prepare fiber assemblies for final blocks | Progress | 2021-09-30 | 58259.7639 | TRUE
1.03A EMCal | S172800 Prepare fiber assemblies for final blocks | EAC | 2021-09-30 | 18360.4727 | TRUE
1.03A EMCal | S172850 Supervise EMCal Final Block Production | Budget | 2020-09-30 | 20785.291 | TRUE
1.03A EMCal | S172850 Supervise EMCal Final Block Production | Budget | 2021-09-30 | 40083.1346 | TRUE
1.03A EMCal | S172850 Supervise EMCal Final Block Production | Progress | 2021-09-30 | 38193.2969 | TRUE
1.03A EMCal | S172850 Supervise EMCal Final Block Production | EAC | 2021-09-30 | 16314.2977 | TRUE
1.03A EMCal | S172850 Supervise EMCal Final Block Production | EAC | 2022-09-30 | 6488.0475 | TRUE
1.03A EMCal | S172870 EMCal Block Production QA | Budget | 2021-09-30 | 533914.7808 | TRUE
1.03A EMCal | S172870 EMCal Block Production QA | Progress | 2021-09-30 | 320348.8685 | TRUE
1.03A EMCal | S172870 EMCal Block Production QA | EAC | 2021-09-30 | 213565.9123 | TRUE
1.03A EMCal | S172900 Production Readiness Review, Safety Review - EMCal Blocks | Budget | 2019-09-30 | 1579.8758 | TRUE
1.03A EMCal | S172900 Production Readiness Review, Safety Review - EMCal Blocks | Progress | 2020-09-30 | 1579.8758 | TRUE
1.03A EMCal | S173000 Fabricate final blocks sector 13 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173000 Fabricate final blocks sector 13 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173100 Fabricate final blocks sector 14 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173100 Fabricate final blocks sector 14 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173200 Fabricate final blocks sector 15 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173200 Fabricate final blocks sector 15 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173300 Fabricate final blocks sector 16 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173300 Fabricate final blocks sector 16 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173400 Fabricate final blocks sector 17 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173400 Fabricate final blocks sector 17 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173500 Fabricate final blocks sector 18 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173500 Fabricate final blocks sector 18 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173600 Fabricate final blocks sector 19 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173600 Fabricate final blocks sector 19 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173700 Fabricate final blocks sector 20 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173700 Fabricate final blocks sector 20 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173800 Fabricate final blocks sector 21 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173800 Fabricate final blocks sector 21 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173900 Fabricate final blocks sector 22 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S173900 Fabricate final blocks sector 22 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S174000 Fabricate final blocks sector 23 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S174000 Fabricate final blocks sector 23 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S174100 Fabricate final blocks sector 24 | Budget | 2020-09-30 | 5012.3259 | TRUE
1.03A EMCal | S174100 Fabricate final blocks sector 24 | Progress | 2021-09-30 | 5012.3259 | TRUE
1.03A EMCal | S174200 Fabricate final blocks sector 25 | Budget | 2020-09-30 | 3341.5506 | TRUE
1.03A EMCal | S174200 Fabricate final blocks sector 25 | Budget | 2021-09-30 | 1720.8985 | TRUE
1.03A EMCal | S174200 Fabricate final blocks sector 25 | Progress | 2021-09-30 | 5062.4491 | TRUE
1.03A EMCal | S174300 Fabricate final blocks sector 26 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174300 Fabricate final blocks sector 26 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174400 Fabricate final blocks sector 27 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174400 Fabricate final blocks sector 27 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174500 Fabricate final blocks sector 28 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174500 Fabricate final blocks sector 28 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174600 Fabricate final blocks sector 29 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174600 Fabricate final blocks sector 29 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174700 Fabricate final blocks sector 30 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174700 Fabricate final blocks sector 30 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174800 Fabricate final blocks sector 31 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174800 Fabricate final blocks sector 31 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174900 Fabricate final blocks sector 32 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S174900 Fabricate final blocks sector 32 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175000 Fabricate final blocks sector 33 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175000 Fabricate final blocks sector 33 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175100 Fabricate final blocks sector 34 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175100 Fabricate final blocks sector 34 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175200 Fabricate final blocks sector 35 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175200 Fabricate final blocks sector 35 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175300 Fabricate final blocks sector 36 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175300 Fabricate final blocks sector 36 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175400 Fabricate final blocks sector 37 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175400 Fabricate final blocks sector 37 | Progress | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175500 Fabricate final blocks sector 38 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175500 Fabricate final blocks sector 38 | Progress | 2021-09-30 | 4852.9338 | TRUE
1.03A EMCal | S175500 Fabricate final blocks sector 38 | EAC | 2021-09-30 | 309.7617 | TRUE
1.03A EMCal | S175600 Fabricate final blocks sector 39 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175600 Fabricate final blocks sector 39 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175700 Fabricate final blocks sector 40 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175700 Fabricate final blocks sector 40 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175800 Fabricate final blocks sector 41 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175800 Fabricate final blocks sector 41 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175900 Fabricate final blocks sector 42 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S175900 Fabricate final blocks sector 42 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176000 Fabricate final blocks sector 43 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176000 Fabricate final blocks sector 43 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176010 Pack and ship final blocks for sectors 57-64 to BNL - M&S | Budget | 2021-09-30 | 7521.2343 | TRUE
1.03A EMCal | S176010 Pack and ship final blocks for sectors 57-64 to BNL - M&S | EAC | 2022-09-30 | 7671.659 | TRUE
1.03A EMCal | S176100 Fabricate final blocks sector 44 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176100 Fabricate final blocks sector 44 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176200 Fabricate final blocks sector 45 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176200 Fabricate final blocks sector 45 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176300 Fabricate final blocks sector 46 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176300 Fabricate final blocks sector 46 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176400 Fabricate final blocks sector 47 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176400 Fabricate final blocks sector 47 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176500 Fabricate final blocks sector 48 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176500 Fabricate final blocks sector 48 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176600 Fabricate final blocks sector 49 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176600 Fabricate final blocks sector 49 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176700 Fabricate final blocks sector 50 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176700 Fabricate final blocks sector 50 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176800 Fabricate final blocks sector 51 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176800 Fabricate final blocks sector 51 | EAC | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176900 Fabricate final blocks sector 52 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S176900 Fabricate final blocks sector 52 | EAC | 2021-09-30 | 2581.3478 | TRUE
1.03A EMCal | S176900 Fabricate final blocks sector 52 | EAC | 2022-09-30 | 2658.7882 | TRUE
1.03A EMCal | S177000 Fabricate final blocks sector 53 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177000 Fabricate final blocks sector 53 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177100 Fabricate final blocks sector 54 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177100 Fabricate final blocks sector 54 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177200 Fabricate final blocks sector 55 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177200 Fabricate final blocks sector 55 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177300 Fabricate final blocks sector 56 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177300 Fabricate final blocks sector 56 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177400 Fabricate final blocks sector 57 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177400 Fabricate final blocks sector 57 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177500 Fabricate final blocks sector 58 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177500 Fabricate final blocks sector 58 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177600 Fabricate final blocks sector 59 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177600 Fabricate final blocks sector 59 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177700 Fabricate final blocks sector 60 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177700 Fabricate final blocks sector 60 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177800 Fabricate final blocks sector 61 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177800 Fabricate final blocks sector 61 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S177900 Fabricate final blocks sector 62 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S177900 Fabricate final blocks sector 62 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S178000 Fabricate final blocks sector 63 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S178000 Fabricate final blocks sector 63 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S178100 Fabricate final blocks sector 64 | Budget | 2021-09-30 | 5162.6956 | TRUE
1.03A EMCal | S178100 Fabricate final blocks sector 64 | EAC | 2022-09-30 | 5317.5764 | TRUE
1.03A EMCal | S178300 Pack and ship final blocks for sectors 13-16 to BNL - Purchased Services | Budget | 2020-09-30 | 1186.9284 | TRUE
1.03A EMCal | S178300 Pack and ship final blocks for sectors 13-16 to BNL - Purchased Services | Progress | 2021-09-30 | 1186.9284 | TRUE
1.03A EMCal | S178310 Pack and ship final blocks for sectors 13-16 to BNL - M&S | Budget | 2020-09-30 | 3686.8796 | TRUE
1.03A EMCal | S178310 Pack and ship final blocks for sectors 13-16 to BNL - M&S | Progress | 2021-09-30 | 3686.8796 | TRUE
1.03A EMCal | S178400 Pack and ship final blocks for sectors 17-24 to BNL - Purchased Services | Budget | 2020-09-30 | 1989.3572 | TRUE
1.03A EMCal | S178400 Pack and ship final blocks for sectors 17-24 to BNL - Purchased Services | Budget | 2021-09-30 | 512.2595 | TRUE
1.03A EMCal | S178400 Pack and ship final blocks for sectors 17-24 to BNL - Purchased Services | Progress | 2021-09-30 | 2501.6167 | TRUE
1.03A EMCal | S178410 Pack and ship final blocks for sectors 17-24 to BNL - M&S | Budget | 2020-09-30 | 5899.0073 | TRUE
1.03A EMCal | S178410 Pack and ship final blocks for sectors 17-24 to BNL - M&S | Budget | 2021-09-30 | 1504.2469 | TRUE
1.03A EMCal | S178410 Pack and ship final blocks for sectors 17-24 to BNL - M&S | Progress | 2021-09-30 | 7403.2542 | TRUE
1.03A EMCal | S178500 Pack and ship final blocks for sectors 25-32 to BNL - Purchased Services | Budget | 2021-09-30 | 2561.2974 | TRUE
1.03A EMCal | S178500 Pack and ship final blocks for sectors 25-32 to BNL - Purchased Services | Progress | 2021-09-30 | 2561.2974 | TRUE
1.03A EMCal | S178510 Pack and ship final blocks for sectors 25-32 to BNL - M&S | Budget | 2021-09-30 | 7521.2343 | TRUE
1.03A EMCal | S178510 Pack and ship final blocks for sectors 25-32 to BNL - M&S | Progress | 2021-09-30 | 7521.2343 | TRUE
1.03A EMCal | S178600 Pack and ship final blocks for sectors 33-40 to BNL - Purchased Services | Budget | 2021-09-30 | 2561.2974 | TRUE
1.03A EMCal | S178600 Pack and ship final blocks for sectors 33-40 to BNL - Purchased Services | EAC | 2021-09-30 | 2561.2974 | TRUE
1.03A EMCal | S178610 Pack and ship final blocks for sectors 33-40 to BNL - M&S | Budget | 2021-09-30 | 7521.2343 | TRUE
1.03A EMCal | S178610 Pack and ship final blocks for sectors 33-40 to BNL - M&S | EAC | 2021-09-30 | 7521.2343 | TRUE
1.03A EMCal | S178700 Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | Budget | 2021-09-30 | 2561.2974 | TRUE
1.03A EMCal | S178700 Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | EAC | 2021-09-30 | 2561.2974 | TRUE
1.03A EMCal | S178710 Pack and ship final blocks for sectors 40-48 to BNL - M&S | Budget | 2021-09-30 | 7521.2343 | TRUE
1.03A EMCal | S178710 Pack and ship final blocks for sectors 40-48 to BNL - M&S | EAC | 2021-09-30 | 7521.2343 | TRUE
1.03A EMCal | S178800 Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | Budget | 2021-09-30 | 2561.2974 | TRUE
1.03A EMCal | S178800 Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | EAC | 2022-09-30 | 2638.1363 | TRUE
1.03A EMCal | S178900 Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | Budget | 2021-09-30 | 2561.2974 | TRUE
1.03A EMCal | S178900 Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | EAC | 2022-09-30 | 2638.1363 | TRUE
1.03A EMCal | S178910 Pack and ship final blocks for sectors 49-56 to BNL - M&S | Budget | 2021-09-30 | 7521.2343 | TRUE
1.03A EMCal | S178910 Pack and ship final blocks for sectors 49-56 to BNL - M&S | EAC | 2022-09-30 | 7671.659 | TRUE
1.03A EMCal | S180402 Set up EMCAL Final module production and sector assembly areas M&S Split | Budget | 2019-09-30 | 11198.1403 | TRUE
1.03A EMCal | S180402 Set up EMCAL Final module production and sector assembly areas M&S Split | Progress | 2019-09-30 | 11198.1403 | TRUE
1.03A EMCal | S184800 Procure light guides for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | Budget | 2019-09-30 | 87930.2245 | TRUE
1.03A EMCal | S184800 Procure light guides for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | Progress | 2019-09-30 | 4396.5112 | TRUE
1.03A EMCal | S184800 Procure light guides for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | Progress | 2020-09-30 | 48361.6235 | TRUE
1.03A EMCal | S184800 Procure light guides for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | Progress | 2021-09-30 | 35172.0898 | TRUE
1.03A EMCal | S185500 Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | Budget | 2020-09-30 | 14961.4483 | TRUE
1.03A EMCal | S185500 Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | Progress | 2020-09-30 | 14961.4483 | TRUE
1.03A EMCal | S185800 Install reflectors on blocks for modules for Prepro Sectors 1-12 M&S | Budget | 2020-09-30 | 398.274 | TRUE
1.03A EMCal | S185800 Install reflectors on blocks for modules for Prepro Sectors 1-12 M&S | Progress | 2020-09-30 | 306.671 | TRUE
1.03A EMCal | S185800 Install reflectors on blocks for modules for Prepro Sectors 1-12 M&S | Progress | 2021-09-30 | 91.603 | TRUE
1.03A EMCal | S187100 Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Delivery Acceptance | Budget | 2021-09-30 | 61144.8492 | TRUE
1.03A EMCal | S187100 Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Delivery Acceptance | Progress | 2021-09-30 | 61144.8492 | TRUE
1.03A EMCal | S187400 Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | Budget | 2020-09-30 | 48025.8233 | TRUE
1.03A EMCal | S187400 Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | Budget | 2021-09-30 | 192103.2932 | TRUE
1.03A EMCal | S187400 Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | Progress | 2021-09-30 | 165689.0904 | TRUE
1.03A EMCal | S187400 Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | EAC | 2021-09-30 | 74440.0261 | TRUE
1.03A EMCal | S187700 Install light guides on final blocks M&S | Budget | 2020-09-30 | 139.0798 | TRUE
1.03A EMCal | S187700 Install light guides on final blocks M&S | Budget | 2021-09-30 | 1773.2677 | TRUE
1.03A EMCal | S187700 Install light guides on final blocks M&S | Progress | 2021-09-30 | 533.4546 | TRUE
1.03A EMCal | S187700 Install light guides on final blocks M&S | EAC | 2021-09-30 | 701.6881 | TRUE
1.03A EMCal | S187700 Install light guides on final blocks M&S | EAC | 2022-09-30 | 690.749 | TRUE
1.03A EMCal | S188100 Install SiPMs daughterboards on final blocks M&S | Budget | 2020-09-30 | 17.7011 | TRUE
1.03A EMCal | S188100 Install SiPMs daughterboards on final blocks M&S | Budget | 2021-09-30 | 322.4123 | TRUE
1.03A EMCal | S188100 Install SiPMs daughterboards on final blocks M&S | Budget | 2022-09-30 | 7.8927 | TRUE
1.03A EMCal | S188100 Install SiPMs daughterboards on final blocks M&S | Progress | 2021-09-30 | 93.6614 | TRUE
1.03A EMCal | S188100 Install SiPMs daughterboards on final blocks M&S | EAC | 2021-09-30 | 122.3606 | TRUE
1.03A EMCal | S188100 Install SiPMs daughterboards on final blocks M&S | EAC | 2022-09-30 | 134.4658 | TRUE
1.03A EMCal | S191110 Build mechanical stand/support for preproduction prototype Sector 0 - M&S | Budget | 2019-09-30 | 551.6325 | TRUE
1.03A EMCal | S191110 Build mechanical stand/support for preproduction prototype Sector 0 - M&S | Progress | 2019-09-30 | 551.6325 | TRUE
1.03A EMCal | S192800 Procure mechanical parts for Prepro Sectors 1-12, Phase 1 - Delivery Acceptance | Budget | 2020-09-30 | 41873.3932 | TRUE
1.03A EMCal | S192800 Procure mechanical parts for Prepro Sectors 1-12, Phase 1 - Delivery Acceptance | Progress | 2020-09-30 | 41873.3932 | TRUE
1.03A EMCal | S192810 Procure mechanical parts for Prepro Sectors 1-12, Phase 2 - Delivery Acceptance | Budget | 2020-09-30 | 41873.3932 | TRUE
1.03A EMCal | S192810 Procure mechanical parts for Prepro Sectors 1-12, Phase 2 - Delivery Acceptance | Progress | 2020-09-30 | 41873.3932 | TRUE
1.03A EMCal | S193500 Procure parts for cooling system for Prepro Sectors 1-12 - Delivery Acceptance | Budget | 2020-09-30 | 22508.1721 | TRUE
1.03A EMCal | S193500 Procure parts for cooling system for Prepro Sectors 1-12 - Delivery Acceptance | Progress | 2020-09-30 | 20257.3549 | TRUE
1.03A EMCal | S193500 Procure parts for cooling system for Prepro Sectors 1-12 - Delivery Acceptance | Progress | 2021-09-30 | 2250.8172 | TRUE
1.03A EMCal | S193710 Build mechanical stand/support for Prepro Sectors 1-12 - M&S | Budget | 2020-09-30 | 568.9629 | TRUE
1.03A EMCal | S193710 Build mechanical stand/support for Prepro Sectors 1-12 - M&S | Progress | 2020-09-30 | 568.9629 | TRUE
1.03A EMCal | S195400 Procure EMCAL Mechanical Parts for Final Sectors - Delivery Acceptance | Budget | 2021-09-30 | 291746.1251 | TRUE
1.03A EMCal | S195400 Procure EMCAL Mechanical Parts for Final Sectors - Delivery Acceptance | Progress | 2020-09-30 | 14587.3063 | TRUE
1.03A EMCal | S195400 Procure EMCAL Mechanical Parts for Final Sectors - Delivery Acceptance | Progress | 2021-09-30 | 247984.2064 | TRUE
1.03A EMCal | S195400 Procure EMCAL Mechanical Parts for Final Sectors - Delivery Acceptance | EAC | 2021-09-30 | 29174.6125 | TRUE
1.03A EMCal | S196100 Procure EMCAL Cooling System for Final Sectors - Delivery Acceptance | Budget | 2021-09-30 | 82284.3925 | TRUE
1.03A EMCal | S196100 Procure EMCAL Cooling System for Final Sectors - Delivery Acceptance | Progress | 2021-09-30 | 28799.5374 | TRUE
1.03A EMCal | S196100 Procure EMCAL Cooling System for Final Sectors - Delivery Acceptance | EAC | 2021-09-30 | 53484.8551 | TRUE
1.03A EMCal | S196910 Technical support labor for EMCal assembly | Budget | 2021-09-30 | 205022.4668 | TRUE
1.03A EMCal | S196910 Technical support labor for EMCal assembly | Budget | 2022-09-30 | 75977.638 | TRUE
1.03A EMCal | S196910 Technical support labor for EMCal assembly | Progress | 2021-09-30 | 117090.6088 | TRUE
1.03A EMCal | S196910 Technical support labor for EMCal assembly | EAC | 2021-09-30 | 89841.1598 | TRUE
1.03A EMCal | S196910 Technical support labor for EMCal assembly | EAC | 2022-09-30 | 74011.0571 | TRUE
1.04A HCal | 16703 sPHENIX OPC - Hadronic Calorimeter | Actuals | 2018-09-30 | 145494.39 | TRUE
1.04A HCal | 16703 sPHENIX OPC - Hadronic Calorimeter | Actuals | 2019-09-30 | 506770.56 | TRUE
1.04A HCal | 16703 sPHENIX OPC - Hadronic Calorimeter | Actuals | 2020-09-30 | 15856.11 | TRUE
1.04A HCal | 16703 sPHENIX OPC - Hadronic Calorimeter | EAC | 2018-09-30 | 145494.39 | TRUE
1.04A HCal | 16703 sPHENIX OPC - Hadronic Calorimeter | EAC | 2019-09-30 | 506770.56 | TRUE
1.04A HCal | 16703 sPHENIX OPC - Hadronic Calorimeter | EAC | 2020-09-30 | 15856.11 | TRUE
1.04A HCal | 59710 sPHENIX MIE - 1.4 Inner HCal | Actuals | 2020-09-30 | 2195.99 | TRUE
1.04A HCal | 59710 sPHENIX MIE - 1.4 Inner HCal | Actuals | 2021-09-30 | 142066.21 | TRUE
1.04A HCal | 59710 sPHENIX MIE - 1.4 Inner HCal | EAC | 2020-09-30 | 2195.99 | TRUE
1.04A HCal | 59710 sPHENIX MIE - 1.4 Inner HCal | EAC | 2021-09-30 | 142066.21 | TRUE
1.04A HCal | 59711 sPHENIX MIE - 1.4 Outer HCal Sector Mechanics | Actuals | 2020-09-30 | 93024.87 | TRUE
1.04A HCal | 59711 sPHENIX MIE - 1.4 Outer HCal Sector Mechanics | Actuals | 2021-09-30 | 194836.55 | TRUE
1.04A HCal | 59711 sPHENIX MIE - 1.4 Outer HCal Sector Mechanics | EAC | 2020-09-30 | 93024.87 | TRUE
1.04A HCal | 59711 sPHENIX MIE - 1.4 Outer HCal Sector Mechanics | EAC | 2021-09-30 | 194836.55 | TRUE
1.04A HCal | 59712 sPHENIX MIE - 1.4 Outer HCal Scintillating Tiles | Actuals | 2019-09-30 | 193780.04 | TRUE
1.04A HCal | 59712 sPHENIX MIE - 1.4 Outer HCal Scintillating Tiles | Actuals | 2020-09-30 | 1498803.71 | TRUE
1.04A HCal | 59712 sPHENIX MIE - 1.4 Outer HCal Scintillating Tiles | Actuals | 2021-09-30 | 214287.49 | TRUE
1.04A HCal | 59712 sPHENIX MIE - 1.4 Outer HCal Scintillating Tiles | EAC | 2019-09-30 | 193780.04 | TRUE
1.04A HCal | 59712 sPHENIX MIE - 1.4 Outer HCal Scintillating Tiles | EAC | 2020-09-30 | 1498803.71 | TRUE
1.04A HCal | 59712 sPHENIX MIE - 1.4 Outer HCal Scintillating Tiles | EAC | 2021-09-30 | 214287.49 | TRUE
1.04A HCal | 59713 sPHENIX MIE - 1.4 Outer HCal Sector Assembly and Testing | Actuals | 2020-09-30 | 21381.56 | TRUE
1.04A HCal | 59713 sPHENIX MIE - 1.4 Outer HCal Sector Assembly and Testing | Actuals | 2021-09-30 | 119473.39 | TRUE
1.04A HCal | 59713 sPHENIX MIE - 1.4 Outer HCal Sector Assembly and Testing | EAC | 2020-09-30 | 21381.56 | TRUE
1.04A HCal | 59713 sPHENIX MIE - 1.4 Outer HCal Sector Assembly and Testing | EAC | 2021-09-30 | 119473.39 | TRUE
1.04A HCal | 59736 FY21 SPHX MIE - 1.4 Outer HCal Sect | Actuals | 2021-09-30 | 15253.06 | TRUE
1.04A HCal | 59736 FY21 SPHX MIE - 1.4 Outer HCal Sect | EAC | 2021-09-30 | 15253.06 | TRUE
1.04A HCal | S1001919 Actuals - Nonlabor - sPHENIX HCal FY19M8 | Budget | 2019-09-30 | 18547.6397 | TRUE
1.04A HCal | S1001919 Actuals - Nonlabor - sPHENIX HCal FY19M8 | Progress | 2019-09-30 | 18547.6397 | TRUE
1.04A HCal | S197600 Actuals - Nonlabor - sPHENIX HCal FY17 | Budget | 2017-09-30 | 3021.0033 | TRUE
1.04A HCal | S197600 Actuals - Nonlabor - sPHENIX HCal FY17 | Progress | 2019-09-30 | 3021.0033 | TRUE
1.04A HCal | S197700 Actuals - Nonlabor - sPHENIX HCal FY18 | Budget | 2018-09-30 | 142473.385 | TRUE
1.04A HCal | S197700 Actuals - Nonlabor - sPHENIX HCal FY18 | Progress | 2019-09-30 | 142473.385 | TRUE
1.04A HCal | S197710 Actuals - Nonlabor - sPHENIX HCal FY19M8 | Budget | 2019-09-30 | 458015.6204 | TRUE
1.04A HCal | S197710 Actuals - Nonlabor - sPHENIX HCal FY19M8 | Progress | 2019-09-30 | 458015.6204 | TRUE
1.04A HCal | S199300 Manufacture Inner HCAL Support Structure - Delivery Acceptance 1 | Budget | 2021-09-30 | 264958.211 | TRUE
1.04A HCal | S199300 Manufacture Inner HCAL Support Structure - Delivery Acceptance 1 | EAC | 2021-09-30 | 264958.211 | TRUE
1.04A HCal | S199310 Manufacture Inner HCAL Support Structure - Delivery Acceptance 2 | Budget | 2021-09-30 | 264958.211 | TRUE
1.04A HCal | S199310 Manufacture Inner HCAL Support Structure - Delivery Acceptance 2 | EAC | 2021-09-30 | 264958.211 | TRUE
1.04A HCal | S199320 Manufacture Inner HCAL Support Structure - Delivery Acceptance 3 | Budget | 2021-09-30 | 264958.211 | TRUE
1.04A HCal | S199320 Manufacture Inner HCAL Support Structure - Delivery Acceptance 3 | EAC | 2021-09-30 | 264958.211 | TRUE
1.04A HCal | S199330 Manufacture Inner HCAL Support Structure - Delivery Acceptance 4 | Budget | 2022-09-30 | 264958.211 | TRUE
1.04A HCal | S199330 Manufacture Inner HCAL Support Structure - Delivery Acceptance 4 | EAC | 2022-09-30 | 264958.211 | TRUE
1.04A HCal | S200000 Manufacture Inner HCAL Support Rings - Delivery Acceptance | Budget | 2021-09-30 | 141885.9587 | TRUE
1.04A HCal | S200000 Manufacture Inner HCAL Support Rings - Delivery Acceptance | Progress | 2021-09-30 | 141885.9587 | TRUE
1.04A HCal | S202512 Outer HCAL Scintillating Tile Acceptance Testing (Preproduction) Split | Budget | 2019-09-30 | 2116.8914 | TRUE
1.04A HCal | S202512 Outer HCAL Scintillating Tile Acceptance Testing (Preproduction) Split | Progress | 2019-09-30 | 2116.8914 | TRUE
1.04A HCal | S203002 Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) - M&S Split | Budget | 2019-09-30 | 2206.5301 | TRUE
1.04A HCal | S203002 Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) - M&S Split | Progress | 2019-09-30 | 441.306 | TRUE
1.04A HCal | S203002 Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) - M&S Split | Progress | 2020-09-30 | 1765.2241 | TRUE
1.04A HCal | S203100 Populate Outer HCAL sectors with scintillating tiles (Preproduction) | Budget | 2020-09-30 | 3590.6544 | TRUE
1.04A HCal | S203100 Populate Outer HCAL sectors with scintillating tiles (Preproduction) | Progress | 2019-09-30 | 3590.6544 | TRUE
1.04A HCal | S203200 Populate Outer HCAL sectors with electronics (Preproduction) | Budget | 2020-09-30 | 3590.6544 | TRUE
1.04A HCal | S203200 Populate Outer HCAL sectors with electronics (Preproduction) | Progress | 2019-09-30 | 1795.3272 | TRUE
1.04A HCal | S203200 Populate Outer HCAL sectors with electronics (Preproduction) | Progress | 2020-09-30 | 1184.916 | TRUE
1.04A HCal | S203200 Populate Outer HCAL sectors with electronics (Preproduction) | Progress | 2021-09-30 | 610.4113 | TRUE
1.04A HCal | S203300 Outer HCAL Sector LED testing and Light Tighting (Preproduction) Labor | Budget | 2020-09-30 | 3590.6544 | TRUE
1.04A HCal | S203300 Outer HCAL Sector LED testing and Light Tighting (Preproduction) Labor | Progress | 2020-09-30 | 2980.2432 | TRUE
1.04A HCal | S203300 Outer HCAL Sector LED testing and Light Tighting (Preproduction) Labor | Progress | 2021-09-30 | 610.4113 | TRUE
1.04A HCal | S203400 Outer HCAL Sector LED testing and Light Tighting (Preproduction) M&S | Budget | 2020-09-30 | 5462.0438 | TRUE
1.04A HCal | S203400 Outer HCAL Sector LED testing and Light Tighting (Preproduction) M&S | Progress | 2020-09-30 | 4533.4963 | TRUE
1.04A HCal | S203400 Outer HCAL Sector LED testing and Light Tighting (Preproduction) M&S | Progress | 2021-09-30 | 928.5474 | TRUE
1.04A HCal | S203500 Outer HCAL Cosmics testing and initial calibration (Preproduction) | Budget | 2020-09-30 | 3590.6544 | TRUE
1.04A HCal | S203500 Outer HCAL Cosmics testing and initial calibration (Preproduction) | Progress | 2020-09-30 | 1795.3272 | TRUE
1.04A HCal | S203500 Outer HCAL Cosmics testing and initial calibration (Preproduction) | Progress | 2021-09-30 | 1795.3272 | TRUE
1.04A HCal | S205100 Procure Outer HCAL Splice Plates - Delivery Acceptance | Budget | 2020-09-30 | 303325.4987 | TRUE
1.04A HCal | S205100 Procure Outer HCAL Splice Plates - Delivery Acceptance | Progress | 2021-09-30 | 303325.4987 | TRUE
1.04A HCal | S206200 Procure Outer HCAL Lifting Fixtures & Supports - Delivery Acceptance | Budget | 2020-09-30 | 45517.0316 | TRUE
1.04A HCal | S206200 Procure Outer HCAL Lifting Fixtures & Supports - Delivery Acceptance | Progress | 2020-09-30 | 45517.0316 | TRUE
1.04A HCal | S208220 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 0 | Budget | 2019-09-30 | 204371.0245 | TRUE
1.04A HCal | S208220 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 0 | Progress | 2019-09-30 | 204371.0245 | TRUE
1.04A HCal | S208300 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 1 | Budget | 2020-09-30 | 159650.9884 | TRUE
1.04A HCal | S208300 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 1 | Progress | 2019-09-30 | 79825.4942 | TRUE
1.04A HCal | S208300 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 1 | Progress | 2020-09-30 | 79825.4942 | TRUE
1.04A HCal | S208302 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 2 | Budget | 2020-09-30 | 126290.7973 | TRUE
1.04A HCal | S208302 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 2 | Progress | 2020-09-30 | 126290.7973 | TRUE
1.04A HCal | S208303 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 3 | Budget | 2020-09-30 | 126290.7973 | TRUE
1.04A HCal | S208303 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 3 | Progress | 2020-09-30 | 126290.7973 | TRUE
1.04A HCal | S208304 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 4 | Budget | 2020-09-30 | 126290.7973 | TRUE
1.04A HCal | S208304 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 4 | Progress | 2020-09-30 | 126290.7973 | TRUE
1.04A HCal | S208306 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 5&6 | Budget | 2020-09-30 | 252581.5946 | TRUE
1.04A HCal | S208306 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 5&6 | Progress | 2020-09-30 | 252581.5946 | TRUE
1.04A HCal | S208308 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 7&8 | Budget | 2020-09-30 | 252581.5946 | TRUE
1.04A HCal | S208308 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 7&8 | Progress | 2020-09-30 | 252581.5946 | TRUE
1.04A HCal | S208310 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 9&10 | Budget | 2020-09-30 | 235905.4037 | TRUE
1.04A HCal | S208310 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 9&10 | Progress | 2020-09-30 | 235905.4037 | TRUE
1.04A HCal | S208312 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 11&12 | Budget | 2021-09-30 | 235905.4037 | TRUE
1.04A HCal | S208312 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 11&12 | Progress | 2020-09-30 | 117952.7018 | TRUE
1.04A HCal | S208312 Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 11&12 | Progress | 2021-09-30 | 117952.7018 | TRUE
1.04A HCal | S208400 Outer HCAL Scintillating Tile Acceptance Testing | Budget | 2020-09-30 | 7526.6237 | TRUE
1.04A HCal | S208400 Outer HCAL Scintillating Tile Acceptance Testing | Budget | 2021-09-30 | 4056.5 | TRUE
1.04A HCal | S208400 Outer HCAL Scintillating Tile Acceptance Testing | Progress | 2020-09-30 | 11110.7669 | TRUE
1.04A HCal | S208400 Outer HCAL Scintillating Tile Acceptance Testing | Progress | 2021-09-30 | 472.3569 | TRUE
1.04A HCal | S209600 Procure Outer HCAL Assembly & Testing Equipment- Delivery Acceptance | Budget | 2021-09-30 | 87051.323 | TRUE
1.04A HCal | S209600 Procure Outer HCAL Assembly & Testing Equipment- Delivery Acceptance | Progress | 2020-09-30 | 87051.323 | TRUE
1.04A HCal | S209800 Populate Outer HCAL sectors with scintillating tiles | Budget | 2021-09-30 | 15509.3102 | TRUE
1.04A HCal | S209800 Populate Outer HCAL sectors with scintillating tiles | Progress | 2020-09-30 | 2326.3965 | TRUE
1.04A HCal | S209800 Populate Outer HCAL sectors with scintillating tiles | Progress | 2021-09-30 | 13182.9137 | TRUE
1.04A HCal | S209900 Populate Outer HCAL sectors with electronics | Budget | 2021-09-30 | 15509.3102 | TRUE
1.04A HCal | S209900 Populate Outer HCAL sectors with electronics | Progress | 2021-09-30 | 15509.3102 | TRUE
1.04A HCal | S210000 Outer HCAL Sector LED testing and Light Tighting | Budget | 2021-09-30 | 15509.3102 | TRUE
1.04A HCal | S210000 Outer HCAL Sector LED testing and Light Tighting | Progress | 2021-09-30 | 15509.3102 | TRUE
1.04A HCal | S210100 Procure Outer HCAL LED Testing & Light Tighting M&S | Budget | 2021-09-30 | 22285.1387 | TRUE
1.04A HCal | S210100 Procure Outer HCAL LED Testing & Light Tighting M&S | Progress | 2021-09-30 | 22285.1387 | TRUE
1.04A HCal | S210200 Outer HCAL Cosmics testing and initial calibration | Budget | 2021-09-30 | 15509.3102 | TRUE
1.04A HCal | S210200 Outer HCAL Cosmics testing and initial calibration | Progress | 2021-09-30 | 15509.3102 | TRUE
1.05A Calorimeter Electronics | 16704 sPHENIX OPC - Calorimeter Electronics | Actuals | 2018-09-30 | 72579.59 | TRUE
1.05A Calorimeter Electronics | 16704 sPHENIX OPC - Calorimeter Electronics | Actuals | 2019-09-30 | 689333.24 | TRUE
1.05A Calorimeter Electronics | 16704 sPHENIX OPC - Calorimeter Electronics | Actuals | 2020-09-30 | 183138.7 | TRUE
1.05A Calorimeter Electronics | 16704 sPHENIX OPC - Calorimeter Electronics | Actuals | 2021-09-30 | 14805.12 | TRUE
1.05A Calorimeter Electronics | 16704 sPHENIX OPC - Calorimeter Electronics | EAC | 2018-09-30 | 72579.59 | TRUE
1.05A Calorimeter Electronics | 16704 sPHENIX OPC - Calorimeter Electronics | EAC | 2019-09-30 | 689333.24 | TRUE
1.05A Calorimeter Electronics | 16704 sPHENIX OPC - Calorimeter Electronics | EAC | 2020-09-30 | 183138.7 | TRUE
1.05A Calorimeter Electronics | 16704 sPHENIX OPC - Calorimeter Electronics | EAC | 2021-09-30 | 14805.12 | TRUE
1.05A Calorimeter Electronics | 59714 sPHENIX MIE - 1.5 CalE SiPMs | Actuals | 2019-09-30 | 340725.35 | TRUE
1.05A Calorimeter Electronics | 59714 sPHENIX MIE - 1.5 CalE SiPMs | Actuals | 2020-09-30 | 396700.94 | TRUE
1.05A Calorimeter Electronics | 59714 sPHENIX MIE - 1.5 CalE SiPMs | EAC | 2019-09-30 | 340725.35 | TRUE
1.05A Calorimeter Electronics | 59714 sPHENIX MIE - 1.5 CalE SiPMs | EAC | 2020-09-30 | 396700.94 | TRUE
1.05A Calorimeter Electronics | 59715 sPHENIX MIE - 1.5 CalE Front End Electronics | Actuals | 2020-09-30 | 793862.93 | TRUE
1.05A Calorimeter Electronics | 59715 sPHENIX MIE - 1.5 CalE Front End Electronics | Actuals | 2021-09-30 | 1014637.05 | TRUE
1.05A Calorimeter Electronics | 59715 sPHENIX MIE - 1.5 CalE Front End Electronics | EAC | 2020-09-30 | 793862.93 | TRUE
1.05A Calorimeter Electronics | 59715 sPHENIX MIE - 1.5 CalE Front End Electronics | EAC | 2021-09-30 | 1014637.05 | TRUE
1.05A Calorimeter Electronics | 59716 sPHENIX MIE - 1.5 CalE Digitizer | Actuals | 2021-09-30 | 146349.14 | TRUE
1.05A Calorimeter Electronics | 59716 sPHENIX MIE - 1.5 CalE Digitizer | EAC | 2021-09-30 | 146349.14 | TRUE
1.05A Calorimeter Electronics | 59738 FY21 sPHX MIE - 1.5 CalE Front End | Actuals | 2021-09-30 | 57688.33 | TRUE
1.05A Calorimeter Electronics | 59738 FY21 sPHX MIE - 1.5 CalE Front End | EAC | 2021-09-30 | 57688.33 | TRUE
1.05A Calorimeter Electronics | 59739 FY21 SPHX MIE - 1.5 CalE Digitizer | Actuals | 2021-09-30 | 169285.82 | TRUE
1.05A Calorimeter Electronics | 59739 FY21 SPHX MIE - 1.5 CalE Digitizer | EAC | 2021-09-30 | 169285.82 | TRUE
1.05A Calorimeter Electronics | S1000879 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | Budget | 2019-09-30 | 383105.0929 | TRUE
1.05A Calorimeter Electronics | S1000879 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | Progress | 2019-09-30 | 383105.0929 | TRUE
1.05A Calorimeter Electronics | S1001959 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | Budget | 2019-09-30 | 64370.0104 | TRUE
1.05A Calorimeter Electronics | S1001959 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | Progress | 2019-09-30 | 64370.0104 | TRUE
1.05A Calorimeter Electronics | S211400 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY17 | Budget | 2017-09-30 | 33386.9993 | TRUE
1.05A Calorimeter Electronics | S211400 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY17 | Progress | 2019-09-30 | 33386.9993 | TRUE
1.05A Calorimeter Electronics | S211500 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY18 | Budget | 2018-09-30 | 39192.5851 | TRUE
1.05A Calorimeter Electronics | S211500 Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY18 | Progress | 2019-09-30 | 39192.5851 | TRUE
1.05A Calorimeter Electronics | S213200 Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 | Budget | 2019-09-30 | 1225.9492 | TRUE
1.05A Calorimeter Electronics | S213200 Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 | Progress | 2019-09-30 | 1225.9492 | TRUE
1.05A Calorimeter Electronics | S213210 Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 | Budget | 2019-09-30 | 1225.9492 | TRUE
1.05A Calorimeter Electronics | S213210 Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 | Progress | 2019-09-30 | 1225.9492 | TRUE
1.05A Calorimeter Electronics | S213300 Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 | Budget | 2019-09-30 | 1072.7055 | TRUE
1.05A Calorimeter Electronics | S213300 Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 | Progress | 2019-09-30 | 1072.7055 | TRUE
1.05A Calorimeter Electronics | S214800 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 5 | Budget | 2019-09-30 | 76698.9863 | TRUE
1.05A Calorimeter Electronics | S214800 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 5 | Progress | 2019-09-30 | 76698.9863 | TRUE
1.05A Calorimeter Electronics | S214900 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 6 | Budget | 2019-09-30 | 76698.9863 | TRUE
1.05A Calorimeter Electronics | S214900 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 6 | Progress | 2019-09-30 | 76698.9863 | TRUE
1.05A Calorimeter Electronics | S215000 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 7 | Budget | 2019-09-30 | 76698.9863 | TRUE
1.05A Calorimeter Electronics | S215000 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 7 | Progress | 2019-09-30 | 76698.9863 | TRUE
1.05A Calorimeter Electronics | S215100 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 8 | Budget | 2019-09-30 | 76698.9863 | TRUE
1.05A Calorimeter Electronics | S215100 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 8 | Progress | 2020-09-30 | 76698.9863 | TRUE
1.05A Calorimeter Electronics | S215200 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 9 | Budget | 2019-09-30 | 4036.7888 | TRUE
1.05A Calorimeter Electronics | S215200 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 9 | Budget | 2020-09-30 | 73475.4808 | TRUE
1.05A Calorimeter Electronics | S215200 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 9 | Progress | 2020-09-30 | 77512.2695 | TRUE
1.05A Calorimeter Electronics | S215300 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 10 | Budget | 2020-09-30 | 77557.4519 | TRUE
1.05A Calorimeter Electronics | S215300 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 10 | Progress | 2020-09-30 | 77557.4519 | TRUE
1.05A Calorimeter Electronics | S215310 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 11 | Budget | 2020-09-30 | 77557.4519 | TRUE
1.05A Calorimeter Electronics | S215310 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 11 | Progress | 2020-09-30 | 77557.4519 | TRUE
1.05A Calorimeter Electronics | S215320 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 12 | Budget | 2020-09-30 | 77557.4519 | TRUE
1.05A Calorimeter Electronics | S215320 EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 12 | Progress | 2020-09-30 | 77557.4519 | TRUE
1.05A Calorimeter Electronics | S215400 EMCal/HCal sensors Production - 5K Units - Delivery Acceptance No. 13 | Budget | 2020-09-30 | 48473.4074 | TRUE
1.05A Calorimeter Electronics | S215400 EMCal/HCal sensors Production - 5K Units - Delivery Acceptance No. 13 | Progress | 2020-09-30 | 48473.4074 | TRUE
1.05A Calorimeter Electronics | S215600 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S215600 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 | Progress | 2019-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S215800 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S215800 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 | Progress | 2019-09-30 | 638.4304 | TRUE
1.05A Calorimeter Electronics | S215800 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 | Progress | 2020-09-30 | 638.4304 | TRUE
1.05A Calorimeter Electronics | S215900 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S215900 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 | Progress | 2019-09-30 | 638.4304 | TRUE
1.05A Calorimeter Electronics | S215900 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 | Progress | 2020-09-30 | 638.4304 | TRUE
1.05A Calorimeter Electronics | S216000 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216000 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 | Progress | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216100 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216100 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 | Progress | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216200 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216200 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 | Progress | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216300 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216300 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 | Progress | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216310 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216310 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 | Progress | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216320 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 | Budget | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216320 Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 | Progress | 2020-09-30 | 1276.8609 | TRUE
1.05A Calorimeter Electronics | S216400 Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 | Budget | 2020-09-30 | 798.0381 | TRUE
1.05A Calorimeter Electronics | S216400 Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 | Progress | 2020-09-30 | 798.0381 | TRUE
1.05A Calorimeter Electronics | S221300 Fabricate EMCal SiPM Boards: Sectors 1-12 - M&S | Budget | 2020-09-30 | 29002.3146 | TRUE
1.05A Calorimeter Electronics | S221300 Fabricate EMCal SiPM Boards: Sectors 1-12 - M&S | Progress | 2020-09-30 | 29002.3146 | TRUE
1.05A Calorimeter Electronics | S222200 Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 1 - Delivery Acceptance | Budget | 2020-09-30 | 89810.793 | TRUE
1.05A Calorimeter Electronics | S222200 Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 1 - Delivery Acceptance | Progress | 2020-09-30 | 89810.793 | TRUE
1.05A Calorimeter Electronics | S222201 Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 2 - Delivery Acceptance | Budget | 2020-09-30 | 89810.793 | TRUE
1.05A Calorimeter Electronics | S222201 Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 2 - Delivery Acceptance | Progress | 2020-09-30 | 89810.793 | TRUE
1.05A Calorimeter Electronics | S222300 Test EMCal Preamp Boards: Sectors 1-12 | Budget | 2020-09-30 | 1915.2913 | TRUE
1.05A Calorimeter Electronics | S222300 Test EMCal Preamp Boards: Sectors 1-12 | Progress | 2020-09-30 | 1915.2913 | TRUE
1.05A Calorimeter Electronics | S223000 Fabricate EMCal Interface Board: Sectors 1-12, Phase 1 - Delivery Acceptance | Budget | 2020-09-30 | 33494.8456 | TRUE
1.05A Calorimeter Electronics | S223000 Fabricate EMCal Interface Board: Sectors 1-12, Phase 1 - Delivery Acceptance | Progress | 2020-09-30 | 33494.8456 | TRUE
1.05A Calorimeter Electronics | S223001 Fabricate EMCal Interface Board: Sectors 1-12, Phase 2 - Delivery Acceptance | Budget | 2020-09-30 | 33494.8456 | TRUE
1.05A Calorimeter Electronics | S223001 Fabricate EMCal Interface Board: Sectors 1-12, Phase 2 - Delivery Acceptance | Progress | 2020-09-30 | 33494.8456 | TRUE
1.05A Calorimeter Electronics | S223300 Fabricate Calorimeter Controller Boards: Sectors 1-12 M&S | Budget | 2020-09-30 | 23009.9974 | TRUE
1.05A Calorimeter Electronics | S223300 Fabricate Calorimeter Controller Boards: Sectors 1-12 M&S | Progress | 2019-09-30 | 23009.9974 | TRUE
1.05A Calorimeter Electronics | S223700 Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 1 - M&S | Budget | 2020-09-30 | 47874.8139 | TRUE
1.05A Calorimeter Electronics | S223700 Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 1 - M&S | Progress | 2020-09-30 | 47874.8139 | TRUE
1.05A Calorimeter Electronics | S223701 Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 2 - M&S | Budget | 2020-09-30 | 47874.8139 | TRUE
1.05A Calorimeter Electronics | S223701 Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 2 - M&S | Progress | 2020-09-30 | 47874.8139 | TRUE
1.05A Calorimeter Electronics | S223900 Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 1 - M&S | Budget | 2020-09-30 | 11959.3769 | TRUE
1.05A Calorimeter Electronics | S223900 Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 1 - M&S | Progress | 2020-09-30 | 11959.3769 | TRUE
1.05A Calorimeter Electronics | S224000 Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 2 - M&S | Budget | 2020-09-30 | 47837.5077 | TRUE
1.05A Calorimeter Electronics | S224000 Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 2 - M&S | Progress | 2020-09-30 | 47837.5077 | TRUE
1.05A Calorimeter Electronics | S224300 Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 1 - M&S | Budget | 2020-09-30 | 3504.8114 | TRUE
1.05A Calorimeter Electronics | S224300 Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 1 - M&S | Progress | 2020-09-30 | 525.7217 | TRUE
1.05A Calorimeter Electronics | S224300 Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 1 - M&S | Progress | 2021-09-30 | 2979.0897 | TRUE
1.05A Calorimeter Electronics | S224400 Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 2 - M&S | Budget | 2020-09-30 | 14019.2457 | TRUE
1.05A Calorimeter Electronics | S224400 Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 2 - M&S | Progress | 2020-09-30 | 2102.8869 | TRUE
1.05A Calorimeter Electronics | S224400 Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 2 - M&S | Progress | 2021-09-30 | 11916.3589 | TRUE
1.05A Calorimeter Electronics | S225300 Test Pulse Boards 1-12 - M&S | Budget | 2020-09-30 | 4804.3227 | TRUE
1.05A Calorimeter Electronics | S225300 Test Pulse Boards 1-12 - M&S | Progress | 2020-09-30 | 4804.3227 | TRUE
1.05A Calorimeter Electronics | S226300 Procure EMCal External Bias Power System: Sectors 1-12, Phase 1 - Delivery Acceptance | Budget | 2020-09-30 | 8663.4842 | TRUE
1.05A Calorimeter Electronics | S226300 Procure EMCal External Bias Power System: Sectors 1-12, Phase 1 - Delivery Acceptance | Progress | 2021-09-30 | 8663.4842 | TRUE
1.05A Calorimeter Electronics | S226400 Procure EMCal External Bias Power System: Sectors 1-12, Phase 2 - Delivery Acceptance | Budget | 2020-09-30 | 34653.9368 | TRUE
1.05A Calorimeter Electronics | S226400 Procure EMCal External Bias Power System: Sectors 1-12, Phase 2 - Delivery Acceptance | Progress | 2021-09-30 | 34653.9368 | TRUE
1.05A Calorimeter Electronics | S227600 Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance Part 1 | Budget | 2020-09-30 | 38676.0895 | TRUE
1.05A Calorimeter Electronics | S227600 Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance Part 1 | Progress | 2020-09-30 | 38676.0895 | TRUE
1.05A Calorimeter Electronics | S227605 Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance Part 2 | Budget | 2021-09-30 | 23205.8768 | TRUE
1.05A Calorimeter Electronics | S227605 Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance Part 2 | Progress | 2021-09-30 | 23205.8768 | TRUE
1.05A Calorimeter Electronics | S228100 Test SiPM Daughter Boards Production Sectors 13-64 | Budget | 2020-09-30 | 193.1252 | TRUE
1.05A Calorimeter Electronics | S228100 Test SiPM Daughter Boards Production Sectors 13-64 | Budget | 2021-09-30 | 2694.4477 | TRUE
1.05A Calorimeter Electronics | S228100 Test SiPM Daughter Boards Production Sectors 13-64 | Progress | 2021-09-30 | 1585.5579 | TRUE
1.05A Calorimeter Electronics | S228100 Test SiPM Daughter Boards Production Sectors 13-64 | EAC | 2021-09-30 | 1302.015 | TRUE
1.05A Calorimeter Electronics | S229300 Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Delivery Acceptance | Budget | 2021-09-30 | 549642.0532 | TRUE
1.05A Calorimeter Electronics | S229300 Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Delivery Acceptance | Progress | 2021-09-30 | 549642.0532 | TRUE
1.05A Calorimeter Electronics | S229400 Test EMCal Preamp Boards: Production Sectors 13-64 | Budget | 2021-09-30 | 6312.8 | TRUE
1.05A Calorimeter Electronics | S229400 Test EMCal Preamp Boards: Production Sectors 13-64 | Progress | 2021-09-30 | 1893.84 | TRUE
1.05A Calorimeter Electronics | S229400 Test EMCal Preamp Boards: Production Sectors 13-64 | EAC | 2021-09-30 | 4418.96 | TRUE
1.05A Calorimeter Electronics | S230100 Fabricate EMCAL Interface Board Sectors 13-64 - Delivery Acceptance | Budget | 2021-09-30 | 217848.8374 | TRUE
1.05A Calorimeter Electronics | S230100 Fabricate EMCAL Interface Board Sectors 13-64 - Delivery Acceptance | Progress | 2021-09-30 | 217848.8374 | TRUE
1.05A Calorimeter Electronics | S230200 Test EMCal Interface Boards: Production Sectors 13-64 | Budget | 2021-09-30 | 6312.8 | TRUE
1.05A Calorimeter Electronics | S230200 Test EMCal Interface Boards: Production Sectors 13-64 | Progress | 2021-09-30 | 6312.8 | TRUE
1.05A Calorimeter Electronics | S231000 Fabricate Calorimeter Production Controller Boards - Delivery Acceptance | Budget | 2021-09-30 | 92154.8519 | TRUE
1.05A Calorimeter Electronics | S231000 Fabricate Calorimeter Production Controller Boards - Delivery Acceptance | Progress | 2020-09-30 | 92154.8519 | TRUE
1.05A Calorimeter Electronics | S231100 Test Calorimeter Controller Boards: Production Sectors 13-64 | Budget | 2021-09-30 | 1972.75 | TRUE
1.05A Calorimeter Electronics | S231100 Test Calorimeter Controller Boards: Production Sectors 13-64 | Progress | 2020-09-30 | 1972.75 | TRUE
1.05A Calorimeter Electronics | S231800 Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Delivery Acceptance | Budget | 2021-09-30 | 288193.2705 | TRUE
1.05A Calorimeter Electronics | S231800 Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Delivery Acceptance | Progress | 2021-09-30 | 288193.2705 | TRUE
1.05A Calorimeter Electronics | S232500 Fabricate Test-pulse Boards 13 - 64 - M&S | Budget | 2020-09-30 | 8022.3768 | TRUE
1.05A Calorimeter Electronics | S232500 Fabricate Test-pulse Boards 13 - 64 - M&S | Progress | 2021-09-30 | 8022.3768 | TRUE
1.05A Calorimeter Electronics | S233200 Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Delivery Acceptance | Budget | 2021-09-30 | 205854.3258 | TRUE
1.05A Calorimeter Electronics | S233200 Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Delivery Acceptance | EAC | 2022-09-30 | 209971.4123 | TRUE
1.05A Calorimeter Electronics | S233250 Trunk Signal Cables - EMCal | Budget | 2021-09-30 | 777844.1946 | TRUE
1.05A Calorimeter Electronics | S233250 Trunk Signal Cables - EMCal | EAC | 2021-09-30 | 250947.3533 | TRUE
1.05A Calorimeter Electronics | S233250 Trunk Signal Cables - EMCal | EAC | 2022-09-30 | 537434.7782 | TRUE
1.05A Calorimeter Electronics | S234000 Procure EMCal Bias Power System Sectors 13-64 - Delivery Acceptance | Budget | 2021-09-30 | 155680.2646 | TRUE
1.05A Calorimeter Electronics | S234000 Procure EMCal Bias Power System Sectors 13-64 - Delivery Acceptance | Progress | 2021-09-30 | 155680.2646 | TRUE
1.05A Calorimeter Electronics | S234100 EMCal Low Voltage Power System Sectors 13-64 - M&S | Budget | 2020-09-30 | 32537.6652 | TRUE
1.05A Calorimeter Electronics | S234100 EMCal Low Voltage Power System Sectors 13-64 - M&S | Budget | 2021-09-30 | 6731.9307 | TRUE
1.05A Calorimeter Electronics | S234100 EMCal Low Voltage Power System Sectors 13-64 - M&S | Progress | 2020-09-30 | 392.696 | TRUE
1.05A Calorimeter Electronics | S234100 EMCal Low Voltage Power System Sectors 13-64 - M&S | Progress | 2021-09-30 | 27096.0212 | TRUE
1.05A Calorimeter Electronics | S234100 EMCal Low Voltage Power System Sectors 13-64 - M&S | EAC | 2021-09-30 | 11780.8788 | TRUE
1.05A Calorimeter Electronics | S234200 EMCal Crates for Controllers - M&S | Budget | 2020-09-30 | 4928.7168 | TRUE
1.05A Calorimeter Electronics | S234200 EMCal Crates for Controllers - M&S | Budget | 2021-09-30 | 1019.7345 | TRUE
1.05A Calorimeter Electronics | S234200 EMCal Crates for Controllers - M&S | Progress | 2021-09-30 | 5948.4513 | TRUE
1.05A Calorimeter Electronics | S236200 Fabricate HCal SiPM Boards: (6 Modules) M&S | Budget | 2019-09-30 | 31674.7396 | TRUE
1.05A Calorimeter Electronics | S236200 Fabricate HCal SiPM Boards: (6 Modules) M&S | Progress | 2019-09-30 | 31674.7396 | TRUE
1.05A Calorimeter Electronics | S236800 Fabricate HCal LED Boards: (6 Modules) M&S | Budget | 2019-09-30 | 14419.6742 | TRUE
1.05A Calorimeter Electronics | S236800 Fabricate HCal LED Boards: (6 Modules) M&S | Progress | 2019-09-30 | 14419.6742 | TRUE
1.05A Calorimeter Electronics | S237710 Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 1 - M&S Split | Budget | 2019-09-30 | 5468.8849 | TRUE
1.05A Calorimeter Electronics | S237710 Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 1 - M&S Split | Progress | 2019-09-30 | 5468.8849 | TRUE
1.05A Calorimeter Electronics | S237800 Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 2 - M&S | Budget | 2019-09-30 | 21875.5394 | TRUE
1.05A Calorimeter Electronics | S237800 Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 2 - M&S | Progress | 2019-09-30 | 21875.5394 | TRUE
1.05A Calorimeter Electronics | S239100 Fabricate HCal SiPM Boards - Delivery Acceptance | Budget | 2021-09-30 | 110822.1375 | TRUE
1.05A Calorimeter Electronics | S239100 Fabricate HCal SiPM Boards - Delivery Acceptance | Progress | 2020-09-30 | 110822.1375 | TRUE
1.05A Calorimeter Electronics | S240400 Fabricate HCal Preamp Boards - Delivery Acceptance | Budget | 2021-09-30 | 48010.5456 | TRUE
1.05A Calorimeter Electronics | S240400 Fabricate HCal Preamp Boards - Delivery Acceptance | Progress | 2020-09-30 | 48010.5456 | TRUE
1.05A Calorimeter Electronics | S241700 Fabricate HCal LED Boards - Delivery Acceptance | Budget | 2020-09-30 | 50144.9758 | TRUE
1.05A Calorimeter Electronics | S241700 Fabricate HCal LED Boards - Delivery Acceptance | Progress | 2020-09-30 | 50144.9758 | TRUE
1.05A Calorimeter Electronics | S242000 Fabricate HCal Backplane Boards: Production - M&S | Budget | 2020-09-30 | 17542.264 | TRUE
1.05A Calorimeter Electronics | S242000 Fabricate HCal Backplane Boards: Production - M&S | Progress | 2020-09-30 | 17542.264 | TRUE
1.05A Calorimeter Electronics | S242900 Fabricate HCal Interface Boards Production - Delivery Acceptance | Budget | 2020-09-30 | 33329.8464 | TRUE
1.05A Calorimeter Electronics | S242900 Fabricate HCal Interface Boards Production - Delivery Acceptance | Progress | 2021-09-30 | 33329.8464 | TRUE
1.05A Calorimeter Electronics | S243700 Procure HCal Electronics Production Power & Signal Cables (Internal) - Delivery Acceptance | Budget | 2021-09-30 | 94394.9726 | TRUE
1.05A Calorimeter Electronics | S243700 Procure HCal Electronics Production Power & Signal Cables (Internal) - Delivery Acceptance | Progress | 2020-09-30 | 94394.9726 | TRUE
1.05A Calorimeter Electronics | S244400 HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | Budget | 2021-09-30 | 101939.4206 | TRUE
1.05A Calorimeter Electronics | S244400 HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | Progress | 2021-09-30 | 50969.7103 | TRUE
1.05A Calorimeter Electronics | S244400 HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | EAC | 2021-09-30 | 50969.7103 | TRUE
1.05A Calorimeter Electronics | S244450 Trunk Signal Cables - OuterHCal | Budget | 2021-09-30 | 149310.4291 | TRUE
1.05A Calorimeter Electronics | S244450 Trunk Signal Cables - OuterHCal | EAC | 2021-09-30 | 48170.3885 | TRUE
1.05A Calorimeter Electronics | S244450 Trunk Signal Cables - OuterHCal | EAC | 2022-09-30 | 103162.8415 | TRUE
1.05A Calorimeter Electronics | S245000 Procure Test stand for SiPMs | Budget | 2019-09-30 | 24271.8311 | TRUE
1.05A Calorimeter Electronics | S245000 Procure Test stand for SiPMs | Progress | 2019-09-30 | 12135.9156 | TRUE
1.05A Calorimeter Electronics | S245000 Procure Test stand for SiPMs | Progress | 2020-09-30 | 12135.9156 | TRUE
1.05A Calorimeter Electronics | S248200 Procure 1/2-Crate Digitizer - Contract/PO - Delivery Acceptance for Assembly & Tests | Budget | 2019-09-30 | 55163.2525 | TRUE
1.05A Calorimeter Electronics | S248200 Procure 1/2-Crate Digitizer - Contract/PO - Delivery Acceptance for Assembly & Tests | Progress | 2019-09-30 | 55163.2525 | TRUE
1.05A Calorimeter Electronics | S251000 Procure EMCAL 7-Crate Digitizer - Parts - Delivery Acceptance | Budget | 2019-09-30 | 195673.9861 | TRUE
1.05A Calorimeter Electronics | S251000 Procure EMCAL 7-Crate Digitizer - Parts - Delivery Acceptance | Progress | 2019-09-30 | 146755.4896 | TRUE
1.05A Calorimeter Electronics | S251000 Procure EMCAL 7-Crate Digitizer - Parts - Delivery Acceptance | Progress | 2020-09-30 | 48918.4965 | TRUE
1.05A Calorimeter Electronics | S251100 Procure EMCAL 7-Crate Digitizer (Boards) - Delivery Acceptance | Budget | 2019-09-30 | 43436.6483 | TRUE
1.05A Calorimeter Electronics | S251100 Procure EMCAL 7-Crate Digitizer (Boards) - Delivery Acceptance | Progress | 2020-09-30 | 43436.6483 | TRUE
1.05A Calorimeter Electronics | S251200 Procure EMCAL 7-Crate Digitizer (Assembly & Tests) - Delivery Acceptance | Budget | 2020-09-30 | 90872.4778 | TRUE
1.05A Calorimeter Electronics | S251200 Procure EMCAL 7-Crate Digitizer (Assembly & Tests) - Delivery Acceptance | Progress | 2020-09-30 | 90872.4778 | TRUE
1.05A Calorimeter Electronics | S252700 Procure Production Digitizer (Parts) - Delivery Acceptance | Budget | 2021-09-30 | 678538.3667 | TRUE
1.05A Calorimeter Electronics | S252700 Procure Production Digitizer (Parts) - Delivery Acceptance | Progress | 2021-09-30 | 251059.1957 | TRUE
1.05A Calorimeter Electronics | S252700 Procure Production Digitizer (Parts) - Delivery Acceptance | EAC | 2021-09-30 | 427479.171 | TRUE
1.05A Calorimeter Electronics | S252800 Procure Production Digitizer (Boards) - Delivery Acceptance | Budget | 2021-09-30 | 149785.149 | TRUE
1.05A Calorimeter Electronics | S252800 Procure Production Digitizer (Boards) - Delivery Acceptance | EAC | 2021-09-30 | 149785.149 | TRUE
1.05A Calorimeter Electronics | S252900 Procure Production Digitizer (Assembly & Tests) - Delivery Acceptance | Budget | 2021-09-30 | 231065.5496 | TRUE
1.05A Calorimeter Electronics | S252900 Procure Production Digitizer (Assembly & Tests) - Delivery Acceptance | EAC | 2022-09-30 | 235686.8606 | TRUE
1.06A DAQ & Trigger | 16705 sPHENIX OPC - DAQ/Trigger | Actuals | 2018-09-30 | 2781.52 | TRUE
1.06A DAQ & Trigger | 16705 sPHENIX OPC - DAQ/Trigger | Actuals | 2019-09-30 | 24172.47 | TRUE
1.06A DAQ & Trigger | 16705 sPHENIX OPC - DAQ/Trigger | Actuals | 2020-09-30 | 876.81 | TRUE
1.06A DAQ & Trigger | 16705 sPHENIX OPC - DAQ/Trigger | EAC | 2018-09-30 | 2781.52 | TRUE
1.06A DAQ & Trigger | 16705 sPHENIX OPC - DAQ/Trigger | EAC | 2019-09-30 | 24172.47 | TRUE
1.06A DAQ & Trigger | 16705 sPHENIX OPC - DAQ/Trigger | EAC | 2020-09-30 | 876.81 | TRUE
1.06A DAQ & Trigger | 59718 sPHENIX MIE - 1.6 DAQ | Actuals | 2020-09-30 | 48738.29 | TRUE
1.06A DAQ & Trigger | 59718 sPHENIX MIE - 1.6 DAQ | Actuals | 2021-09-30 | 321194.02 | TRUE
1.06A DAQ & Trigger | 59718 sPHENIX MIE - 1.6 DAQ | EAC | 2020-09-30 | 48738.29 | TRUE
1.06A DAQ & Trigger | 59718 sPHENIX MIE - 1.6 DAQ | EAC | 2021-09-30 | 321194.02 | TRUE
1.06A DAQ & Trigger | 59719 sPHENIX MIE - 1.6 Local Level 1 Trigger | Actuals | 2020-09-30 | 185217.04 | TRUE
1.06A DAQ & Trigger | 59719 sPHENIX MIE - 1.6 Local Level 1 Trigger | Actuals | 2021-09-30 | 7307.17 | TRUE
1.06A DAQ & Trigger | 59719 sPHENIX MIE - 1.6 Local Level 1 Trigger | EAC | 2020-09-30 | 185217.04 | TRUE
1.06A DAQ & Trigger | 59719 sPHENIX MIE - 1.6 Local Level 1 Trigger | EAC | 2021-09-30 | 7307.17 | TRUE
1.06A DAQ & Trigger | 59721 sPHENIX MIE - 1.6 Timing System | Actuals | 2021-09-30 | 7896.75 | TRUE
1.06A DAQ & Trigger | 59721 sPHENIX MIE - 1.6 Timing System | EAC | 2021-09-30 | 7896.75 | TRUE
1.06A DAQ & Trigger | 59740 FY21 sPHX MIE - 1.6 DAQ | Actuals | 2021-09-30 | 923.26 | TRUE
1.06A DAQ & Trigger | 59740 FY21 sPHX MIE - 1.6 DAQ | EAC | 2021-09-30 | 923.26 | TRUE
1.06A DAQ & Trigger | S1000959 Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | Budget | 2019-09-30 | 23190.6976 | TRUE
1.06A DAQ & Trigger | S1000959 Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | Progress | 2019-09-30 | 23190.6976 | TRUE
1.06A DAQ & Trigger | S253500 Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | Budget | 2018-09-30 | 2781.5146 | TRUE
1.06A DAQ & Trigger | S253500 Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | Progress | 2019-09-30 | 2781.5146 | TRUE
1.06A DAQ & Trigger | S255900 Procure DAQ Production Boards - Delivery Acceptance | Budget | 2021-09-30 | 121502.7545 | TRUE
1.06A DAQ & Trigger | S255900 Procure DAQ Production Boards - Delivery Acceptance | EAC | 2021-09-30 | 121502.7545 | TRUE
1.06A DAQ & Trigger | S256700 Procure DAQ Production Crates - Delivery Acceptance | Budget | 2021-09-30 | 74283.7956 | TRUE
1.06A DAQ & Trigger | S256700 Procure DAQ Production Crates - Delivery Acceptance | EAC | 2022-09-30 | 75769.4715 | TRUE
1.06A DAQ & Trigger | S257600 Procure DAQ Production SEBs - Delivery Acceptance | Budget | 2021-09-30 | 47634.4839 | TRUE
1.06A DAQ & Trigger | S257600 Procure DAQ Production SEBs - Delivery Acceptance | Progress | 2021-09-30 | 47634.4839 | TRUE
1.06A DAQ & Trigger | S258400 Procure DAQ Production ATPs - Delivery Acceptance | Budget | 2021-09-30 | 113802.7748 | TRUE
1.06A DAQ & Trigger | S258400 Procure DAQ Production ATPs - Delivery Acceptance | Progress | 2021-09-30 | 113802.7748 | TRUE
1.06A DAQ & Trigger | S258700 Procure DAQ Production jSEB Slow control computers - Delivery Acceptance | Budget | 2020-09-30 | 19180.8771 | TRUE
1.06A DAQ & Trigger | S258700 Procure DAQ Production jSEB Slow control computers - Delivery Acceptance | EAC | 2021-09-30 | 19564.4947 | TRUE
1.06A DAQ & Trigger | S259500 Procure DAQ Production Buffer Boxes - Delivery Acceptance | Budget | 2021-09-30 | 259459.3698 | TRUE
1.06A DAQ & Trigger | S259500 Procure DAQ Production Buffer Boxes - Delivery Acceptance | Progress | 2021-09-30 | 41513.4992 | TRUE
1.06A DAQ & Trigger | S259500 Procure DAQ Production Buffer Boxes - Delivery Acceptance | EAC | 2021-09-30 | 217945.8706 | TRUE
1.06A DAQ & Trigger | S260300 Procure DAQ Production Main Switches - Delivery Acceptance | Budget | 2021-09-30 | 99994.1137 | TRUE
1.06A DAQ & Trigger | S260300 Procure DAQ Production Main Switches - Delivery Acceptance | Progress | 2020-09-30 | 99994.1137 | TRUE
1.06A DAQ & Trigger | S262500 Procure Prototype V1 Trigger Board - Delivery Acceptance | Budget | 2020-09-30 | 196861.1617 | TRUE
1.06A DAQ & Trigger | S262500 Procure Prototype V1 Trigger Board - Delivery Acceptance | Progress | 2020-09-30 | 196861.1617 | TRUE
1.06A DAQ & Trigger | S263600 Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance | Budget | 2021-09-30 | 69641.0584 | TRUE
1.06A DAQ & Trigger | S263600 Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance | EAC | 2021-09-30 | 69641.0584 | TRUE
1.06A DAQ & Trigger | S264900 Procure Production LL1 System - Delivery Acceptance | Budget | 2021-09-30 | 135800.0638 | TRUE
1.06A DAQ & Trigger | S264900 Procure Production LL1 System - Delivery Acceptance | EAC | 2022-09-30 | 138516.0651 | TRUE
1.06A DAQ & Trigger | S267600 Procure Production GL1 Components - final hardware - Delivery Acceptance | Budget | 2021-09-30 | 32673.2632 | TRUE
1.06A DAQ & Trigger | S267600 Procure Production GL1 Components - final hardware - Delivery Acceptance | EAC | 2021-09-30 | 32673.2632 | TRUE
1.06A DAQ & Trigger | S270300 Timing System Production (FPGA Boards) - Delivery Acceptance | Budget | 2021-09-30 | 48284.4671 | TRUE
1.06A DAQ & Trigger | S270300 Timing System Production (FPGA Boards) - Delivery Acceptance | EAC | 2021-09-30 | 48284.4671 | TRUE
1.07A MinBias Trigger Detector | 16706 sPHENIX OPC - Min Bias Trigger Det | Actuals | 2018-09-30 | 413.67 | TRUE
1.07A MinBias Trigger Detector | 16706 sPHENIX OPC - Min Bias Trigger Det | Actuals | 2019-09-30 | 76795.27 | TRUE
1.07A MinBias Trigger Detector | 16706 sPHENIX OPC - Min Bias Trigger Det | Actuals | 2020-09-30 | 1717.18 | TRUE
1.07A MinBias Trigger Detector | 16706 sPHENIX OPC - Min Bias Trigger Det | EAC | 2018-09-30 | 413.67 | TRUE
1.07A MinBias Trigger Detector | 16706 sPHENIX OPC - Min Bias Trigger Det | EAC | 2019-09-30 | 76795.27 | TRUE
1.07A MinBias Trigger Detector | 16706 sPHENIX OPC - Min Bias Trigger Det | EAC | 2020-09-30 | 1717.18 | TRUE
1.07A MinBias Trigger Detector | 59722 sPHENIX MIE - 1.7 Min Bias Trigger Det | Actuals | 2021-09-30 | 9042.45 | TRUE
1.07A MinBias Trigger Detector | 59722 sPHENIX MIE - 1.7 Min Bias Trigger Det | EAC | 2021-09-30 | 9042.45 | TRUE
1.07A MinBias Trigger Detector | S1001039 Actuals - Nonlabor - sPHENIX MinBias Trigger FY19 M8 | Budget | 2019-09-30 | 21505.3278 | TRUE
1.07A MinBias Trigger Detector | S1001039 Actuals - Nonlabor - sPHENIX MinBias Trigger FY19 M8 | Progress | 2019-09-30 | 21505.3278 | TRUE
1.07A MinBias Trigger Detector | S271300 Actuals - Nonlabor - sPHENIX MinBias Trigger FY18 | Budget | 2018-09-30 | 413.6695 | TRUE
1.07A MinBias Trigger Detector | S271300 Actuals - Nonlabor - sPHENIX MinBias Trigger FY18 | Progress | 2019-09-30 | 413.6695 | TRUE
1.07A MinBias Trigger Detector | S272600 Procure Prototype Shaper/Disc Electronics - Delivery Acceptance | Budget | 2019-09-30 | 77228.5535 | TRUE
1.07A MinBias Trigger Detector | S272600 Procure Prototype Shaper/Disc Electronics - Delivery Acceptance | Progress | 2019-09-30 | 77228.5535 | TRUE
1.07A MinBias Trigger Detector | S273500 Procure Min/Bias Electronics (sPHENIX Production Digitizers) - Delivery Acceptance | Budget | 2021-09-30 | 17143.3072 | TRUE
1.07A MinBias Trigger Detector | S273500 Procure Min/Bias Electronics (sPHENIX Production Digitizers) - Delivery Acceptance | EAC | 2022-09-30 | 17486.1733 | TRUE
1.07A MinBias Trigger Detector | S273600 Procure MBD Shaper/Disc Board 128 Channels - Delivery Acceptance | Budget | 2021-09-30 | 53878.9655 | TRUE
1.07A MinBias Trigger Detector | S273600 Procure MBD Shaper/Disc Board 128 Channels - Delivery Acceptance | EAC | 2022-09-30 | 54956.5448 | TRUE