## Slide 1: sPHENIX Installation Schedule with RHIC Run 22 Ending April 4 2022
Glenn Young
July 8, BNL

## Slide 2: sPHENIX Assembly Sequence
(I) Assembly Hall Work
May-21’ to April-22’
(II) IR Hall Work
April-22’ to Oct-22’
AH work through end of CY 21’
Complete
Complete
You are here

## Slide 3: sPHENIX Roll-in Date to 1008 IR
Roll-in date, from 2019 I&F Baselining, is March 22-28, 2022
  Plan has been to remove shield wall earlier in February-March 2022
  Co-ordination with EMCal installation is required
Shift of Run 22 end date to Monday April 4, 2022, requires some re-planning – have to add time to remove shield wall
  Analysis of effort for removing shield wall, making any adjustments to tracks, and actual roll-in suggests that 15 days are needed
  Result is a 4 week shift later in arrival of sPHENIX in position in the IR
  Connection of cryogenics jumpers (U-tubes) and power bus has to await completion of this step
  Magnet cool-down necessarily awaits completion of the above

## Slide 4: Work Post Roll-in & Contingency
Baseline had ORR performed 9/14/2022 – 10/12/2022
  Contingency is 71 work days before a Run 23 start on 1/30/2023
Revised schedule puts ORR 10/19/2022 – 11/21/2022
Work subsequent to roll-in includes
  Cryogenic, power-bus, control line hookup for magnet
  Magnet pumpdown, cooldown, power-up, mapping
  Installation of TPC, beampipe (w/bakeout), INTT, MVTX, MBD
  ORR for all of sPHENIX plus addressing any action items

## Slide 5
Sequential Build Steps | Locate | Start | End | J-21 | F-21 | M-21 | A-21 | M-21 | J-21 | J-21 | A-21 | S-21 | O-21 | N-21 | D-21 | J-22 | F-22 | M-22 | A-22 | M-22
AH Track Upgrades (started 3/1) | AH | 3/1/21 | 5/3/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 3/1/21 | 5/14/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cradle-Base | AH | 5/4/21 | 6/2/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 5/17/21 | 6/25/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Outer HCAL 1-13 | AH | 6/4/21 | 8/25/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 6/28/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Secure Magnet in oHCAL, Tests | AH | 8/26/21 | 9/29/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Large Support Rings | AH | 9/30/21 | 10/6/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Outer HCAL 14-32 | AH | 10/7/21 | 12/10/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Inner HCAL Barrel Install | AH | 1/10/22 | 1/28/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EMCAL | AH | 2/7/22 | 3/21/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Carriage, Platforms, Cable Tray and Pipe Supports, Pole Tips | AH | 11/15/21 | 3/28/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LN2/Helium Line Infrastructure | IR | 7/15/21 | 11/15/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IR Track Upgrades | IR | 7/15/21 | 11/15/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Magnet Valve Assembly | AH | 3/28/22 | 4/5/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Move sPHENIX to IR | AH to IR | 4/6/22 | 4/20/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Magnet Cryo and Electric Connect | IR | 4/6/21 | 6/13/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
sPHENIX AH Installation Schedule
RHIC Run FY21
1/30/21 to 7/15/21
RHIC Run FY22
11/15/21 to 4/3/22
`
EMCAL sector factory
ohCAL sector factory
iHCAL factory and barrel fab
Current Status
Shield Wall Removal
sPHENIX = ~200 tons
LSR Procurement
Install tool procure and fab
Platform procurement
Pole Tip procurement`
Shield Wall Install
sPHENIX = ~650 tons
Shield Wall Remove
sPHENIX = ~870 tons
Install structures procure
If EMCAL not done, resume in IR before magnet map start
Magnet supports
Dates from April 21’ I&F review
Actual AH starts

## Slide 6
Sequential Build Steps | Locate | Start | End | M-22 | A-22 | M-22 | J-22 | J-22 | A-22 | S-22 | O-22 | N-22 | D-22 | J-23 | F-23 | M-23 | A-23 | M-23 | J-23 | J-23
Move sPHENIX to IR | AH to IR | 4/6/22 | 4/20/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Magnet Cryo and Electric Connect | IR | 4/6/22 | 6/13/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Complete EMCAL (if needed, not in P6) |  | 4/6/22 | 6/13/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Magnet Mapping | IR | 6/14/22 | 7/6/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TPC | IR | 7/11/22 | 7/22/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Platforms, INTT Support, Beam Pipe Install and Bake | IR | 8/1/22 | 8/30/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
INTT | IR | 8/31/22 | 9/22/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MVTX | IR | 9/23/22 | 10/18/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MBD And Final Beam Pipe Supports | IR | 9/8/22 | 10/18/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Carriage Stairs and Seismic Supports | IR | 4/20/22 | 6/26/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Racks | IR | 4/20/22 | 10/18/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Carriage Infrastructure (continued) | IR | 4/20/22 | 10/18/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Other 1008 Infrastructure | IR | 4/20/22 | 10/18/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ORR (Early Finish) | IR | 10/19/22 | 11/21/22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
sPHENIX IR Installation Schedule
RHIC Run FY23
Model (Jan to June)
RHIC Run FY22
11/15/21 to 4/3/22
BNL NEG coating
CERN team arrival
Eqpt set up
TPC install structures set up
Contingency

## Slide 8: OuterHCal and EMCal Installation
 | Fabrication Complete | Installation Date | Delta (wk)
OHCal Sector 1 & Splice Plates | Week 8, 2021 | Week 25, 2021 | 17
OHCal Sector 13 | Week 5, 2021 | Week 36, 2021 | 31
SC Magnet Coil | 2018 (testing at BNL) | Week 39, 2021 | >100
OHCal Sector 14 | Week 5, 2021 | Week 43, 2021 | 38
OHCal Sector 32 | Week 17, 2021 | Week 48, 2021 | 31
EMCal Sector 1 | Week 14, 2020 | Week 1, 2022 | 91
EMCal Sector 32 | Week 26, 2021 | Week 5, 2022 | 31
EMCal Sector 59 | Week 52, 2021 | Week 10, 2022 | 10
EMCal Sector 64 | Week 5, 2022 | Week 11, 2022 | 6

## Slide 9: TPC and Electronics Installation
 | Fabrication Complete | Installation Date | Delta (wk)
TPC | Week 4, 2022 | Week 28, 2022 | 24
OHCal Cabling | Week 3, 2022 | Week 5, 2022 | 2
EMCal Cabling | Week 3, 2022 | Week 5, 2022 | 2
Digitizers | Week 44, 2021 | Week 17, 2022 | 25
Trigger & Timing Systems | Week 4, 2022 | Week 17, 2022 | 13
Beampipe | Week 8, 2022 | Week 32, 2022 | 24
TPC, EMCal and OHCal on-detector electronics are installed as part of detector fabrication
Digitizer, Trigger and Timing installed after roll-in during April 2022
EMCal & HCal cabling starts only after Upper Platform in placed and essential cryogenics work is underway