## Read Me
USER PROCEDURE
Column | Column Name | Action | Description
A | WBS Id (Optional) | Optional: Select EIC WBS | pull down menue
B | WBS Name | Please fill in the detector you cost | pull down menue
C | Activity Description | Describe what you want to buy or do
D | Activity Type (Optional) | Optional: Select Type of Activity | Identifies type of activity in typicaly activity string -- Pull down menue
E | Unit | Number of things of the same type
F | Unit Price | Price per part
G | Basis of estimate for Costing | give the info where the cost came from | pull down menue
H | Labor Hours | give the hours needed to do the activity (1760 hours in a year == 1 FTE)
I | Resource Name | give the skill set needed to do the work | pull down menue
J | Funding Source | please provide the primary funding source | pull down menue
K | % of cost to Project | give the procentage of the cost charged to the project (1 to 100)
L | % of cost inkind | give the procentage of the cost being in-kind (1 to 100) | calculated --> no action needed
M | Direct Materials Total $$ (Calculated) | calculated from column E and F
N | Total Labor $$ (Calculated) | calculated from H I and AD | no action needed
O | Total Cost to Project $$ (calculated) | calculated from (N2+M2)*K2/100 | no action needed
P | Total Inkind Cost $$ (calculated) | calculated from (N2+M2)*L2/100 | no action needed
Q | Duration of activity in work days | give the work days needed for the activity
R | % of a working year (calculated) |  | no action needed
S | Projected Start Date of activity | give date activity starts
T,U,V,W,X,Y |  | get automatically calculated | no action needed
Z | Info | give any additional info you think can be useful

## Activities & Resources
WBS ID | WBS Name | Activity Description (Separate between conceptual design, preliminary design, final design, long lead procurements etc.) | Activity Type (Pull Down) | Units | Unit Pricing | Basis of Estimate for costing (Pull Down) | Labor Hours | Resource Name (Pull Down) | Funding Source (Pull Down) | % of cost to Project | % of cost Inkind | Direct Materials Total $$ (Calculated) | Total Labor cost $$ (Calculated) | Total Cost to project $$ (Calculated) | Total Inkind Cost $$ (Calculated) | Duration (Working Days) | # of working years (Calculated) | Projected Start Date | Projected Start Date (Calculated) | Projected Finish Date excluding Weedends and Holidays (Calculated) | Projected Finish Date excluding Holidays (Calculated) | Projected Finish Date including Weekends & Holidays (Calculated) | Cost Total (Calculated) | Escalated Cost Total (Calculated) | Notes | [5 empty] | ROW | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35
ECE06.10.04.03 | Hadron Endcap PID | eRICh R&D - includes prototyping, tests beams etc. [2022-2024 mainly] Most of the R&D activities are performed withing the dRICH In particular sensors and aerogel will be the same testing and studies on prototypes will be independent | [23 empty] | Labor Skill Set | Cost per hour for each skill set | Holiday | When | Date | 0
|  | Electronics+Sensors+Cooling small scale prototype "final" implementation, including simulation | Other | 1 | 50000 | Expert Opinion | 0 | Mechanical Designer | Project | 100 | 0 | 50000 | #N/A | #N/A | #N/A | 782 | #REF! | 2022-01-01 | 2022-01-01 | 2024-02-22 | 2024-12-31 | 2025-01-23 | #N/A | #REF! |  | Electrical Tech | 101.01 | Labor Day | The 1st Monday in September | 2021-09-06 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test beams / irradiation tests | Other | 1 | 20000 | Expert Opinion | 0 | Scientist | Project | 100 | 0 | 20000 | #N/A | #N/A | #N/A | 782 | #REF! | 2022-01-01 | 2022-01-01 | 2024-02-22 | 2024-12-31 | 2025-01-23 | #N/A | #REF! |  | Software Expert | 178.24 | Columbus Day | The 2nd Monday in October | 2021-10-11 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | prototype beam tests and analysis of the data (postDocs) | Other | 0 | 0 | Expert Opinion | 5280 | PostDoc | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 782 | #REF! | 2022-01-01 | 2022-01-01 | 2024-02-22 | 2024-12-31 | 2025-01-23 | #N/A | #REF! | eRD-102 and eRD-110 | Other | 0
|  | consolidate prototype toward final design (postDcos) | Other | 0 | 0 | Expert Opinion | 5280 | PostDoc | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 400 | #REF! | 2025-01-01 | 2025-01-01 | 2026-02-05 | 2026-07-15 | 2026-07-15 | #N/A | #REF! | eRD-102 and eRD-110 |  |  | Veteran's Day | November 11 | 2021-11-11 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[28 empty] | Thanksgiving Day | The 4th Thursday in November | 2021-11-25 | 0
|  | eRICh Final Design (some of this completed early 2026) | [25 empty] | Christmas Day | December 25 | 2021-12-25 | 0
|  | Project coordination | Other | 0 | 0 | Expert Opinion | 4500 | Scientist | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 2300 | #REF! | 2022-01-01 | 2022-01-01 | 2028-04-19 | 2030-10-25 | 2031-01-02 | #N/A | #REF! | assumes 9 years up to end construction/first commissioning |  |  | New Year's Day | January 1 | 2022-01-01 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overall eRICH design optimization | Conceptual Design | 0 | 0 | Expert Opinion | 1320 | Scientist | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 500 | #REF! | 2022-01-01 | 2022-01-01 | 2023-05-16 | 2023-12-01 | 2023-12-20 | #N/A | #REF! |  |  |  | Martin Luther King Jr. Day | The 3rd Monday in January | 2022-01-17 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overall eRICH design optimization | Conceptual Design | 0 | 0 | Expert Opinion | 2640 | PhD Student | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 500 | #REF! | 2022-01-01 | 2022-01-01 | 2023-05-16 | 2023-12-01 | 2023-12-20 | #N/A | #REF! |  |  |  | President's Day | The 3rd Monday in February | 2022-02-21 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Software porting to chosen simulation and analysis framework | Conceptual Design | 0 | 0 | Expert Opinion | 880 | PostDoc | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 500 | #REF! | 2022-01-01 | 2022-01-01 | 2023-05-16 | 2023-12-01 | 2023-12-20 | #N/A | #REF! |  |  |  | Memorial Day | The last Monday in May | 2022-05-30 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Finalize design with simulation and performance analysis | Final Design | 0 | 0 | Expert Opinion | 880 | PostDoc | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2024-01-01 | 2024-01-01 | 2025-06-24 | 2026-01-26 | 2026-01-29 | #N/A | #REF! |  |  |  | Independence Day | July 4 | 2022-07-04 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Radiators subsystems | Final Design | 0 | 0 | Expert Opinion | 440 | Mechanical Engineer | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2024-01-01 | 2024-01-01 | 2025-06-24 | 2026-01-26 | 2026-01-29 | #N/A | #REF! |  |  |  | Labor Day | The 1st Monday in September | 2022-09-05 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical structure | Final Design | 0 | 0 | Expert Opinion | 660 | Mechanical Designer | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2024-01-01 | 2024-01-01 | 2025-06-24 | 2026-01-26 | 2026-01-29 | #N/A | #REF! |  |  |  | Veteran's Day | November 11 | 2022-11-11 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical structure - executive drawings | Final Design | 0 | 0 | Expert Opinion | 1320 | Mechanical Designer | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2024-01-01 | 2024-01-01 | 2025-06-24 | 2026-01-26 | 2026-01-29 | #N/A | #REF! |  |  |  | Thanksgiving Day | The 4th Thursday in November | 2022-11-24 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sensor ancillary components (e.g. cooling) | Final Design | 0 | 0 | Expert Opinion | 0 | Mechanical Designer | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2024-01-01 | 2024-01-01 | 2025-06-24 | 2026-01-26 | 2026-01-29 | #N/A | #REF! |  |  |  | Christmas Day | December 25 | 2022-12-25 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cooling systema (plant/ distribution etc) | Final Design | 0 | 0 | Expert Opinion | 180 | Mechanical Engineer | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | 5.08 | 2024-01-01 | 2024-01-01 | 2025-06-24 | 2026-01-26 | 2026-01-29 | $67.395 | $79.376 | In cost sharing with eRICH. dRICH share only here (57%)
|  | Cooling systema (plant/ distribution etc) | Final Design | 0 | 0 | Expert Opinion | 180 | Mechanical Designer | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | 5.08 | 2024-01-01 | 2024-01-01 | 2025-06-24 | 2026-01-26 | 2026-01-29 | $67.395 | $79.376 | In cost sharing with eRICH. dRICH share only here (57%)
[28 empty] | New Year's Day | January 1 | 2023-01-01 | 0 |  | 0 | [9 empty] | 0
|  | eRICh Production (includes labour costs for preparing procurements/tenders etc.) | [25 empty] | Martin Luther King Jr. Day | The 3rd Monday in January | 2023-01-16 | 0 |  | 0 | [9 empty] | 0
|  | Sensors (SiPM) (matrix: see note field) | Procurement of Material/ Vendor Fabrication/Leadtime | 15328 | 74 | Expert Opinion | 0 | Scientist | Project | 100 | 0 | 1134272 | #N/A | #N/A | #N/A | 540 | #REF! | 2026-01-01 | 2026-01-01 | 2027-06-25 | 2028-01-27 | 2028-02-03 | #N/A | #REF! | Based on information exchange with a company/main SiPM producer. Unit here is tile 4x4 but total sensors fits. Assume 3.3 m^2 area. |  |  | President's Day | The 3rd Monday in February | 2023-02-20 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sensors (SiPM (labour cost only) | Procurement of Material/ Vendor Fabrication/Leadtime | 0 | 0 | Expert Opinion | 140 | Scientist | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2026-01-01 | 2026-01-01 | 2027-06-25 | 2028-01-27 | 2028-02-03 | #N/A | #REF!
|  | Power Supply for Sensors (SiPM) (256 sensors segmentation, cost/channel include mainframes and filters) | Procurement of Material/ Vendor Fabrication/Leadtime | 958 | 330 | Expert Opinion | 0 | Scientist | Project | 100 | 0 | 316140 | #N/A | 0 | #N/A | 540 | #REF! | 2028-01-01 | 2028-01-01 | 2029-06-24 | 2030-01-25 | 2030-02-22 | #N/A | #REF! | Based on information exchange with a company/main P.S. producer + recent DarkSide quote |  |  | Memorial Day | The last Monday in May | 2023-05-29 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power Supply for Sensors (SiPM) (labour cost only) | Procurement of Material/ Vendor Fabrication/Leadtime | 0 | 0 | Expert Opinion | 70 | Scientist | Project | 100 | 0 | 0 | #N/A | 0 | #N/A | 540 | #REF! | 2028-01-01 | 2028-01-01 | 2029-06-24 | 2030-01-25 | 2030-02-22 | #N/A | #REF!
|  | Electronics, PS, services (see detailed breakdown) | Procurement of Material/ Vendor Fabrication/Leadtime | 245248 | 6 | Expert Opinion | 0 | Scientist | Project | 100 | 0 | 1471488 | #N/A | #N/A | #N/A | 800 | #REF! | 2025-01-01 | 2025-01-01 | 2027-03-12 | 2028-01-26 | 2028-02-02 | #N/A | #REF! | ASIC, boards, concentrators, links, cabling, ...(a detailed breakdown was tested against this average number). Assumes no VAT payment@BNL, contacts with company, costs of fibers etc.. Timeline is long because includes ASIC production |  |  | Independence Day | July 4 | 2023-07-04 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electronics, PS, services (see detailed breakdown) (labour cost only) | Procurement of Material/ Vendor Fabrication/Leadtime | 0 | 0 | Expert Opinion | 140 | Scientist | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 800 | #REF! | 2025-01-01 | 2025-01-01 | 2027-03-12 | 2028-01-26 | 2028-02-02 | #N/A | #REF!
|  | Aerogel Radiator | Procurement of Material/ Vendor Fabrication/Leadtime | 125 | 3800 | Historical Costs | 0 | Scientist | Project | 100 | 0 | 475000 | #N/A | #N/A | #N/A | 800 | #REF! | 2025-01-01 | 2025-01-01 | 2027-03-12 | 2028-01-26 | 2028-02-02 | #N/A | #REF! | CLAS12 expertise tile is 20x20x2 cm^3. 5 m^2 entrance area. 4 cm thickens --> 50 tiles/m^2 |  |  | Labor Day | The 1st Monday in September | 2023-09-04 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Aerogel Radiator (labour cost only) | Procurement of Material/ Vendor Fabrication/Leadtime | 0 | 0 | Historical Costs | 70 | Scientist | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2026-01-01 | 2026-01-01 | 2027-06-25 | 2028-01-27 | 2028-02-03 | #N/A | #REF!
|  | Mechanics (vessel, mirror and readout supports, etc.) | Procurement of Material/ Vendor Fabrication/Leadtime | 1 | 500000 | Expert Opinion | 0 | Scientist | Project | 100 | 0 | 500000 | #N/A | #N/A | #N/A | 540 | #REF! | 2027-01-01 | 2027-01-01 | 2028-06-24 | 2029-01-26 | 2029-02-15 | #N/A | #REF! | CLAS12/COMPASS expertise |  |  | Thanksgiving Day | The 4th Thursday in November | 2023-11-23 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanics (labour costs only) | Procurement of Material/ Vendor Fabrication/Leadtime | 0 | 0 | Expert Opinion | 140 | Scientist | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2027-01-01 | 2027-01-01 | 2028-06-24 | 2029-01-26 | 2029-02-15 | #N/A | #REF!
|  | Cooling system | Procurement of Material/ Vendor Fabrication/Leadtime | 1 | 393000 | Expert Opinion | 0 | Scientist | Project | 100 | 0 | 393000 | #N/A | #N/A | #N/A | 540 | #REF! | 2027-01-01 | 2027-01-01 | 2028-06-24 | 2029-01-26 | 2029-02-15 | #N/A | #REF! | LHCb recent expertise and costing. Assumes 12 kw for dRICH and sharing of cost with eRICH (note cost quoted here is only dRICH share). Sharing is dRICH 57% eRICH 43% |  |  | New Year's Day | January 1 | 2024-01-01 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cooling system | Procurement of Material/ Vendor Fabrication/Leadtime | 0 | 0 | Expert Opinion | 70 | Scientist | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 540 | #REF! | 2027-01-01 | 2027-01-01 | 2028-06-24 | 2029-01-26 | 2029-02-15 | #N/A | #REF!
eRICH costruction, assembly, QA
|  | Assembly (tile sandwich) | In-House Assembly |  |  | Expert Opinion | 3960 | Mechanical Tech | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 200 | #REF! | 2028-03-01 | 2028-03-01 | 2028-09-17 | 2028-12-06 | 2028-12-13 | #N/A | #REF! |  |  |  | Martin Luther King Jr. Day | The 3rd Monday in January | 2024-01-15 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test tile sandwich - test stations for sensors/cooling/daq cards | In-House Testing | 2 | 50000 | Expert Opinion | 0 | PhD Student | Project | 100 | 0 | 100000 | #N/A | #N/A | #N/A | 200 | #REF! | 2022-01-01 | 2022-01-01 | 2022-07-20 | 2022-10-07 | 2022-10-14 | #N/A | #REF! | 2 sites for testing cards / QA |  |  | President's Day | The 3rd Monday in February | 2024-02-19 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | In house test of sensors/cards (labour costs) | In-House Testing | 0 | 0 | Expert Opinion | 1320 | PhD Student | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 200 | #REF! | 2022-01-01 | 2022-01-01 | 2022-07-20 | 2022-10-07 | 2022-10-14 | #N/A | #REF!
|  | Shipping costs | Installation | 2 | 5000 | Expert Opinion | 140 | Scientist | Project | 100 | 0 | 10000 | #N/A | #N/A | #N/A | 20 | #REF! | 2029-01-01 | 2029-01-01 | 2029-01-21 | 2029-01-29 | 2029-01-30 | #N/A | #REF! | CLAS12 expertise
|  | Installation / commissioning cooling system | Installation |  |  | Expert Opinion | 180 | Mechanical Tech | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 60 | #REF! | 2029-03-01 | 2029-03-01 | 2029-04-30 | 2029-05-24 | 2029-05-24 | #N/A | #REF! | shared with dRICH
|  | Assembly in situ - all mechanics (vessel, mirrors, readout support) | Installation |  |  | Expert Opinion | 880 | Mechanical Tech | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 200 | #REF! | 2029-02-01 | 2029-02-01 | 2029-08-20 | 2029-11-08 | 2029-11-15 | #N/A | #REF! | half time than needed for dRICH because simpler
|  | Assembly in situ - all components | Installation |  |  | Expert Opinion | 880 | PhD Student | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 200 | #REF! | 2029-02-01 | 2029-02-01 | 2029-08-20 | 2029-11-08 | 2029-11-15 | #N/A | #REF! | half time than needed for dRICH because simpler |  |  | Labor Day | The 1st Monday in September | 2024-09-02 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assembly in situ - all components | Installation |  |  | Expert Opinion | 880 | PostDoc | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 200 | #REF! | 2029-02-01 | 2029-02-01 | 2029-08-20 | 2029-11-08 | 2029-11-15 | #N/A | #REF! | half time than needed for dRICH because simpler |  |  | Memorial Day | The last Monday in May | 2027-05-31 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assembly in situ - all components | Installation |  |  | Expert Opinion | 880 | Electrical Tech | Project | 100 | 0 | 0 | 88888.8 | 88888.8 | 0 | 200 | #REF! | 2029-02-01 | 2029-02-01 | 2029-08-20 | 2029-11-08 | 2029-11-15 | 88888.8 | #REF! | half time than needed for dRICH because simpler |  |  | Independence Day | July 4 | 2027-07-04 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assembly in situ - all components | Installation |  |  | Expert Opinion | 880 | Mechanical Tech | Project | 100 | 0 | 0 | #N/A | #N/A | #N/A | 200 | #REF! | 2029-02-01 | 2029-02-01 | 2029-08-20 | 2029-11-08 | 2029-11-15 | #N/A | #REF! | half time than needed for dRICH because simpler |  |  | Labor Day | The 1st Monday in September | 2027-09-06 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[28 empty] | Veteran's Day | November 11 | 2027-11-11 | 0 |  | 0 | [9 empty] | 0
[28 empty] | Thanksgiving Day | The 4th Thursday in November | 2027-11-25 | 0 |  | 0 | [9 empty] | 0
[28 empty] | Christmas Day | December 25 | 2027-12-25 | 0 |  | 0 | [9 empty] | 0
|  | Totals | [9 empty] | 4469900 | #N/A | #N/A | #N/A | [7 empty] | #N/A | #REF! |  |  |  | New Year's Day | January 1 | 2028-01-01 | 0 |  | 0 | [9 empty] | 0
[28 empty] | Martin Luther King Jr. Day | The 3rd Monday in January | 2028-01-17 | 0 |  | 0 | [9 empty] | 0
[28 empty] | President's Day | The 3rd Monday in February | 2028-02-21 | 0 |  | 0 | [9 empty] | 0
[28 empty] | Memorial Day | The last Monday in May | 2028-05-29 | 0 |  | 0 | [9 empty] | 0
[28 empty] | Independence Day | July 4 | 2028-07-04 | 0 |  | 0 | [9 empty] | 0
[28 empty] | Labor Day | The 1st Monday in September | 2028-09-04 | 0
[28 empty] | Columbus Day | The 2nd Monday in October | 2028-10-09 | 0
[28 empty] | Veteran's Day | November 11 | 2028-11-11 | 0
[28 empty] | Thanksgiving Day | The 4th Thursday in November | 2028-11-23 | 0
[28 empty] | Christmas Day | December 25 | 2028-12-25 | 0
[28 empty] | New Year's Day | January 1 | 2029-01-01 | 0
[28 empty] | Martin Luther King Jr. Day | The 3rd Monday in January | 2029-01-15 | 0
[28 empty] | President's Day | The 3rd Monday in February | 2029-02-19 | 0
[28 empty] | Memorial Day | The last Monday in May | 2029-05-28 | 0
[28 empty] | Independence Day | July 4 | 2029-07-04 | 0
[28 empty] | Labor Day | The 1st Monday in September | 2029-09-03 | 0
[28 empty] | Columbus Day | The 2nd Monday in October | 2029-10-08 | 0
[28 empty] | Veteran's Day | November 11 | 2029-11-11 | 0
[28 empty] | Thanksgiving Day | The 4th Thursday in November | 2029-11-22 | 0
[28 empty] | Christmas Day | December 25 | 2029-12-25 | 0
[28 empty] | New Year's Day | January 1 | 2030-01-01 | 0
[28 empty] | Martin Luther King Jr. Day | The 3rd Monday in January | 2030-01-21 | 0
[28 empty] | President's Day | The 3rd Monday in February | 2030-02-18
[28 empty] | Memorial Day | The last Monday in May | 2030-05-27
[28 empty] | Independence Day | July 4 | 2030-07-04
[28 empty] | Labor Day | The 1st Monday in September | 2030-09-02
[12 empty] | 4469900 | #N/A | #N/A | #N/A | [12 empty] | Columbus Day | The 2nd Monday in October | 2030-10-14
[28 empty] | Veteran's Day | November 11 | 2030-11-11
[28 empty] | Thanksgiving Day | The 4th Thursday in November | 2030-11-28
[28 empty] | Christmas Day | December 25 | 2030-12-25
[28 empty] | New Year's Day | January 1 | 2031-01-01
[28 empty] | Martin Luther King Jr. Day | The 3rd Monday in January | 2031-01-20
[28 empty] | President's Day | The 3rd Monday in February | 2031-02-17
[28 empty] | Memorial Day | The last Monday in May | 2031-05-26
[28 empty] | Independence Day | July 4 | 2031-07-04
[28 empty] | Labor Day | The 1st Monday in September | 2031-09-01
[28 empty] | Columbus Day | The 2nd Monday in October | 2031-10-13
[28 empty] | Veteran's Day | November 11 | 2031-11-11
[28 empty] | Thanksgiving Day | The 4th Thursday in November | 2031-11-27
[28 empty] | Christmas Day | December 25 | 2031-12-25
[28 empty] | New Year's Day | January 1 | 2032-01-01
[28 empty] | Martin Luther King Jr. Day | The 3rd Monday in January | 2032-01-19
[28 empty] | President's Day | The 3rd Monday in February | 2032-02-16
[28 empty] | Memorial Day | The last Monday in May | 2032-05-31
[28 empty] | Independence Day | July 4 | 2032-07-04
[28 empty] | Labor Day | The 1st Monday in September | 2032-09-06
[28 empty] | Columbus Day | The 2nd Monday in October | 2032-10-11
[28 empty] | Veteran's Day | November 11 | 2032-11-11
[28 empty] | Thanksgiving Day | The 4th Thursday in November | 2032-11-25
[28 empty] | Christmas Day | December 25 | 2032-12-25
**Do not add activities beyond this row
Formulas:
Projected Start Date (Calculated) = IF(NOT([Duration (Working Days)]=""),IF(NOT([Projected Start Date]=""),[Projected Start Date],#REF!),"")
Note on E83: Unknown User: 1 engineering run: 1.470 chip/FET * 12 FET = 17.640 ASIC (32ch) = 564.000 canali
Note on Y3: lewis: Material escalates at 3.5% per year

## dRICH readout
Readout Scheme |  |  | Sensor area
Target total channels | 317440 |  | Total area to be covered (m^2) | 3.3
|  |  | S13361-3050NE-08 linear dimension (mm) | 25.8
Channel/ASIC | 64 |  | S13361-3050NE-08 area (mm2) | 665.64 |  |  |  | DCR (Hz/mm^2) | 300
Sensors XY (cm) | 0.3 |  | Number of tiles (8x8) | 4957.6348 |  |  |  | DCR x sensor (Hz) | 2700
Sensors Matrix | 64 |  | dRICH tile sensors | 1240 |  |  |  | irr+ann. penalty | 100
Matrix area (cm^2) | 5.76 |  | # of channels | 317440 |  |  |  | DCR x sensor(Hz) ann | 270000
[# matrix]/(dRICH tile) | 4 | [6 empty] | bit x hit (incl. TOT) | 64
dRICH tile sensors | 256
dRICH tile area (cm^2) | 23.04
dRICH tile linear dimension XY (cm) | 4.8
dRICH tile: total number | 1240
Total channels (true) | 317440
concentrator: tile readout | 4
concentrator: total channels | 1024
concentrator: total ALCOR | 16
concentrator: # of concentrators | 310 | [6 empty] | settori | 6
concentrator: fibers to DAQ | 310 | [6 empty] | canali per settore | 52906.6667
Bandwidth on Readout Scheme | [7 empty] | dRich settore rate | 142848000
concentrator aggregated bandwidth (b/s) | 176947200 | [6 empty] | throughput settore | 9142272000
concentrator aggregated bandwidth (after annealing) (b/s) | 17694720000 | [6 empty] | throughput totale | 54853632000
dRICH aggregagate bandwidth | 54853632000 | [6 empty] | dRICH total | 54853632000
dRICH aggregate bandwidth (Gb/s) | 54.8536 | [6 empty] | dRICH total (Gb/s) | 54.8536
dRICH aggregated bandwidth after ann (Gb/s) | 5485.3632 | [6 empty] | dRICH total after ann(Gb/s) | 5485.3632
Data reduction
Data reduction at concentrator level via timing (BC) | 3
concentrator aggregated bandwidth (Mb/s) | 58982400
concentrator aggregated bandwidth (after annealing) (Mb/s) | 5898240000
dRICH aggregagate bandwidth | 18284544000
dRICH aggregate bandwidth (Gb/s) | 18.2845
dRICH aggregated bandwidth after ann (Gb/s) | 1828.4544
Breakdown of main elctronics cost
Item | Activity Type | Units | Unit Pricing | Source | Labour hours |  | Material Cost
ASIC production (engineering run) |  | 1 | 162000 | Vendor Quote |  | Scientist | 162000
ASIC board - close to sensor - includes 20% spares |  | 1300 | 290 | Historical Costs | 300 | Engineer | 377000
Concentrator boards (FPGA, intermediate cards: 1 x 16 ASIC) - includes 20% spares |  | 350 | 1200 | Engineer Estimate |  | Engineer | 420000
Optical fibers (60 m) |  | 300 | 200 | Expert Opinion |  | Engineer | 60000
LV Power Supplies (5-6 V for each ALCOR board + concentrator) |  | 1500 | 300 |  |  | Engineer | 450000
LV Mainframe |  | 8 | 6000 |  |  | Engineer | 48000
ASIC packaging |  | 1 | 25000 | Historical Costs |  | Engineer | 25000
Total (raw cost) | [6 empty] | 1542000
Cables: LV, HV,... in contingency (+20%) | [6 empty] | 1850400
VAT 20% | [6 empty] | 2220480
[6 empty] | cost per channel | 6.995
[6 empty] | cost per channel (NO VAT) | 5.8291
Note on C43: Unknown User: 1 engineering run: 1.470 chip/FET * 12 FET = 17.640 ASIC (32ch) = 564.000 canali
Note this choice implies data reduction at concentrator level or elsewhere. DAQ limit is 10 Gb/s. So this scheme will need additional filtering, before going to FELIX. We can assume the 10 Gb/s will be overcome in future, or we reduce factor 3 here (timing), see below

## WBS Reference & User Procedure
WBS Code | WBS Name | Activity Type | Funding Source | Cost Basis | Labor Skill Set | Cost per hour for each skill set
ECE06.10 | EIC Detector | Conceptual Design | Project | Vendor Quote | Scientist | 157.05
ECE06.10.03 | Tracking | Final Design | In-kind | Historical Costs | PostDoc | 70.99
ECE06.10.03.01 | Barrel Tracking | Procurement Support | Project / In-kind | Existing Purchase Order | PhD Student | 20
ECE06.10.03.02 | Electron EndCap Tracking | Procurement of Material | repurpose | Engineering Estimate | Undergrad | 20
ECE06.10.03.03 | Hadron Endcap Tracking | Vendor Fabrication | not decided | Expert Opinion | Mechanical Engineer | 153.17
ECE06.10.04 | PID | In House Assembly |  |  | Mechanical Designer | 116.1
ECE06.10.04.01 | Barrel PID | In House Fabrication |  |  | Mechanical Tech | 101.01
ECE06.10.04.02 | Electron EndCap PID | Q&A / Testing |  |  | Electrical Engineer | 153.17
ECE06.10.04.03 | Hadron Endcap PID | Installation |  |  | Electrical Designer | 116.1
ECE06.10.05 | Electromagnetic Calorimetry | Transpoert |  |  | Electrical Tech | 101.01
ECE06.10.05.01 | Barrel Electromagnetic Calorimetry | Travel |  |  | Software Expert | 178.24
ECE06.10.05.02 | Electron Endcap Electromagnetic Calorimetry | Level-of-Effort |  |  | Other | 0
ECE06.10.05.03 | Hadron Endcap Electromagnetic Calorimetry | Other
ECE06.10.06 | Hadronic Calorimetry
ECE06.10.06.01 | Barrel Hadronic Calorimetry
ECE06.10.06.02 | Electron Endcap Hadronic Calorimetry
ECE06.10.06.03 | Hadron Endcap Hadronic Calorimetry
ECE06.10.07 | Magnets
ECE06.10.08 | Electronics
ECE06.10.09 | DAQ / Computing
ECE06.10.11 | IR Integration & Auxiliary Detectors
ECE06.10.11.01 | Roman Pot, B0-Detectors, Off-Momentum Detectors
ECE06.10.11.02 | Zero Degree Calorimeter
ECE06.10.11.03 | Low-Q2 tracker
ECE06.10.14 | Polarimetry and Luminosity
ECE06.10.14.01 | e-Polarimetry
ECE06.10.14.02 | h-Polarimetry
ECE06.10.14.03 | Luminosity Monitor

## LookUps (hidden)
System (PS, RF, Magnets etc. | Activity Type (Design/Procurement/Assembly or In-House Fabrication/ Testing/ Installation | Resource Name | Skill Level | Key Predecessor
Management | Conceptual Design | Physicist | High | A_010 - CD-0 – Approve Mission Need (FY19Q1) 30-Sep-19)
Accelerator Physics/Design | preliminary Design | Post Doc | Medium | A_030 - CD-1 – Approve Alternative Selection and Cost Range (FY21Q2-3)
Magnets | Final Design | Scientist | Low | A_040 - CD-2– Approve Performance Baseline(FY22Q4)
RF Systems | Procurement of Material/ Vendor Fabrication/Leadtime | Control Room Operators |  | A_050 - CD-3 – Approve Start of Construction (FY23Q4)
Vacuum | Procurement Support | Designer Electrical |  | A_070 - CD-4a – Approve Start of Operations or Project Completion (FY29Q4)
Power Supplies | In-House Assembly | Designer General |  | A_075 - CD-4b – Approve Start of Operations or Project Completion (FY32Q4)
Instrumentation | In-House Fabrication | Designer Mechanical |  | B_0010 - Start Conceptual Design - (2-Jan-20)
Pulsed Devices | In-House Testing | Applications Engineer (Programmer) |  | B_0040 - Start Preliminary Design - (31-Mar-21)
Detector Interfaces | Installation | Controls Engineer |  | B_0070 - Start Final Design (1-Aug-22)
Accelerator Support - Cryogenics | Other | Controls Tech |  | B_0110 - Destructive (RHIC Run Components) Installation Starts (1-Jul-25)
Accelerator Support - Controls |  | Digital Engineer |  | B_0120 - Final Design Complete (31-May-24)
Accelerator Support - Removals |  | Systems Engineer/ Systems Architect |  | B_0130 - Construction of Components Complete (30-Mar-28)
Accelerator Support - Installation |  | Cryogenics Electrical Engineer |  | B_0140 - Final Installation Complete (30-Dec-27)
Infrastructure - Civil Construction |  | Cryogenics Mechanical Engineer |  | B_0180 - Start Beam Commissioning (2-Oct-28)
Infrastructure - Electrical Power Systems |  | Cryogenics Electrical Tech |  | B_0090 - Start Construction (2-Oct-23)
Infrastructure - Cooling Systems |  | Cryogenics Mechanical Tech |  | B_0100 - Start Installation (Nondestructive - Components not affecting RHIC Run '25) (2-Oct-23)
Pre-Operations |  | Instrumentation Electrical Engineer |  | B_0085 - Start Long Lead Procurements (2-Oct-23)
Other |  | Instrumentation Electrical Tech |  | #VALUE!
TBD |  | Instrumentation Mechanical Engineer |  | #VALUE!
|  | Instrumentation Mechanical Tech |  | #VALUE!
|  | Survey Engineer |  | #VALUE!
|  | Survey Tech |  | #VALUE!
|  | Cable Pullers |  | #VALUE!
|  | Facility/Utility Engineer |  | #VALUE!
|  | Facility/Utility Tech |  | #VALUE!
|  | Engineering Construction Services |  | #VALUE!
|  | Magnet Engineer |  | #VALUE!
|  | Magnet Tech |  | #VALUE!
|  | Power Supply Engineer |  | #VALUE!
|  | Power Supply Tech |  | #VALUE!
|  | RF/SRF Engineer |  | #VALUE!
|  | RF/SRF Tech |  | #VALUE!
|  | Vacuum Electrical Engineer |  | #VALUE!
|  | Vacuum Electrical Tech |  | #VALUE!
|  | Vacuum Mechanical Engineer |  | #VALUE!
|  | Vacuum Mechanical Tech |  | #VALUE!
|  | Electrical Engineer General |  | #VALUE!
|  | Electrical Tech General |  | #VALUE!
|  | Engineer General |  | #VALUE!
|  | Mechanical Engineer General |  | #VALUE!
|  | Mechanical Tech General |  | #VALUE!
|  | Tech General |  | #VALUE!
|  | Central Shops_RC |  | #VALUE!
|  | Building Trades Assigned - Carpenters |  | #VALUE!
|  | Building Trades Unassigned - Carpenters |  | #VALUE!
|  | Building Trades Assigned - Electrical |  | #VALUE!
|  | Building Trades Unassigned - Electrical |  | #VALUE!
|  | Building Trades Assigned - Plumbers |  | #VALUE!
|  | Building Trades Unassigned - Plumbers |  | #VALUE!
|  | Building Trades Assigned - Riggers |  | #VALUE!
|  | Building Trades Unassigned - Riggers |  | #VALUE!
|  | Building Trades - General |  | #VALUE!
|  | Building Trades Assigned - General |  | #VALUE!
|  | Building Trades Assigned - Welders |  | #VALUE!
|  | Building Trades Unassigned - Welders |  | #VALUE!
|  | Division Manager |  | #VALUE!
|  | Group Manager |  | #VALUE!
|  | ESHQ Professional |  | #VALUE!
|  | QA Professional |  | #VALUE!
|  | Radiation Tech |  | #VALUE!
|  | Administrative |  | #VALUE!
|  | Business Operations |  | #VALUE!
|  | Human Resources |  | #VALUE!
|  | IT Professional |  | #VALUE!
|  | Procurement |  | #VALUE!
|  | Project Controls |  | #VALUE!
|  | NonLabor - Purchases Construction |  | #VALUE!
|  | NonLabor - Purchases<$2M |  | #VALUE!
|  | NonLabor - Purchases>$2M (Portion Over) |  | #VALUE!
|  | NonLabor - Travel |  | #VALUE!
|  | NonLabor - Electrical Power |  | #VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!

## Project Settings (hidden)
PWB Light | RESOURCE NAME | #REF! | RATE SETS | #REF! | RESOURCE STRUCTURE | C-AD | WORK GROUP SETS | C-AD | WORK GROUP LIST | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | NSLS-II | #REF! | NSLS-II | #REF! | #REF!
|  | #REF! |  | #REF! | #REF! | LTS |  |  |  | #REF!
|  | #REF! |  | #REF! |  | NEXO |  |  |  | #REF!
|  | #REF! |  | #REF! |  | EIC |  |  |  | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! |  | #REF! | [5 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
|  | #REF! | [7 empty] | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Work Group List (hidden)
C-AD | Work Group ID | Work Group Name | Work Group & ID | Work Group Manager | NSLS-II | Work Group ID | Work Group Name | Work Group & ID | Work Group Manager
| ADCA | Accelerator Management | ADCA - Accelerator Management | Wolfram Fischer |  | PSAA | Management | PSAA - Management | Hill, John
| ADCG | LEReC | ADCG - LEReC | Wolfram Fischer |  | PSAB | ES&H | PSAB - ES&H | Lee,Robert J
| ADDA | LARP | ADDA - LARP | Wolfram Fischer |  | PQQA | Quality | PQQA - Quality | Porretto, Chris
| ADAD | Accelerator Physics | ADAD - Accelerator Physics | Michael Blaskiewicz |  | PSAD | Project Management | PSAD - Project Management | Johnson,Erik D
| ADAH | Accelerator Physics - Injector Group | ADAH - Accelerator Physics - Injector Group | Michael Blaskiewicz |  | PSBA | Accelerator Div. Mgmt | PSBA - Accelerator Div. Mgmt | Shaftan,Timur V
| ADHL | ATF | ADHL - ATF | Mark Palmer |  | PSBB | Accelerator Physics | PSBB - Accelerator Physics | Smalyuk,Victor
| ADAA | C-AD Management | ADAA - C-AD Management | Susan Pankowski |  | PSBC | Insertion Devices | PSBC - Insertion Devices | Tanabe,Toshiya
| ADAB | Administrative Support | ADAB - Administrative Support | Susan Pankowski |  | PSBD | RF Group | PSBD - RF Group | Rose,James T
| DBAA | ALD NPP | DBAA - ALD NPP | Susan Pankowski |  | PSBE | Instrumentation | PSBE - Instrumentation | Padrazo,Danny
| ADCE | CeC | ADCE - CeC | Vladimir Litvinenko |  | PSBF | Accelerator Coordination | PSBF - Accelerator Coordination | Wang,Guimei
| ADEH | Communications & Electronic Support | ADEH - Communications & Electronic Support | Frank Naase |  | PSBG | Vacuum | PSBG - Vacuum | Hetzel,Charles
| ADEM | Controls - Access Controls | ADEM - Controls - Access Controls | Kevin Brown |  | PSBJ | Beam Operations | PSBJ - Beam Operations | Zitvogel,Emil P
| ADFA | Controls - Management | ADFA - Controls - Management | Kevin Brown |  | PSBK | Electrical Engineering | PSBK - Electrical Engineering | Ganetis,George L
| ADFB | Controls - System Administration | ADFB - Controls - System Administration | Kevin Brown |  | PSBN | PPS Electrical Engineering | PSBN - PPS Electrical Engineering | Buda,Scott W
| ADFC | Controls - Applications | ADFC - Controls - Applications | Kevin Brown |  | PSBO | Electrical Designers | PSBO - Electrical Designers | Malley Jr,Jerome C
| ADFG | Controls - Hardware | ADFG - Controls - Hardware | Kevin Brown |  | PSBL | Mechanical Engineering | PSBL - Mechanical Engineering | Sharma,Sushil K
| ADFH | Controls - Front End Systems | ADFH - Controls - Front End Systems | Kevin Brown |  | PSBP | Mechanical Designers | PSBP - Mechanical Designers | Loftus,Michael J
| ADFI | Controls - Accelerator Controls Techs | ADFI - Controls - Accelerator Controls Techs | Charlie Thiesen |  | PSBQ | Mech Eng - Survey | PSBQ - Mech Eng - Survey | Karl,Francis X
| ADGF | Controls - Software | ADGF - Controls - Software | Kevin Brown |  | PSBM | Utilities | PSBM - Utilities | Gosman,John w
| ADCU | Cryo – Mechanical Engineering | ADCU - Cryo – Mechanical Engineering | Roberto Than |  | PSCB | Procurement | PSCB - Procurement | Schlock, Janet
| ADCV | Cryo - Electronic Techs | ADCV - Cryo - Electronic Techs | Roberto Than |  | PSCC | Human Resources | PSCC - Human Resources | Williams, Joann
| ADCW | Cryo - Mechanical Techs | ADCW - Cryo - Mechanical Techs | Roberto Than |  | PSCD | Enterprise Computing | PSCD - Enterprise Computing | Allen Levine
| ADDE | Cryo - Management | ADDE - Cryo - Management | Roberto Than |  | PSCE | Business Systems Development | PSCE - Business Systems Development | Brian Bindert
| ADPC | Cryo – Ctrls/Instr. Engineering | ADPC - Cryo – Ctrls/Instr. Engineering | Roberto Than |  | PSAE | Facilities | PSAE - Facilities | Lee,Robert J
| ADCR | Design Room - Designers | ADCR - Design Room - Designers | Anthony Arno |  | PSCI | Business Operations | PSCI - Business Operations | Madonia, Christine
| ADGA | Design Room - Management | ADGA - Design Room - Management | Anthony Arno |  | PSCJ | Administrative Support | PSCJ - Administrative Support | Stein,Tammy A
| ADCC | Elec - Management | ADCC - Elec - Management | Jon Sandberg |  | PSEA | Photon Division Management | PSEA - Photon Division Management | Zschack,Paul R
| ADCF | Elec - Pulsed Power Engr. & Techs | ADCF - Elec - Pulsed Power Engr. & Techs | Jon Sandberg |  | PSEB | Complex Scattering | PSEB - Complex Scattering | Pindak,Ronald S
| ADCJ | Elec - AGS/ Booster Power Supply Techs | ADCJ - Elec - AGS/ Booster Power Supply Techs | Jon Sandberg |  | PSED | Soft X-ray Scattering Spectroscopy | PSED - Soft X-ray Scattering Spectroscopy | Wilkins,Stuart B
| ADCK | Elec - Collider Power Supply Eng & Tech | ADCK - Elec - Collider Power Supply Eng & Tech | Jon Sandberg |  | PSEG | Diffraction & In-Situ Scattering | PSEG - Diffraction & In-Situ Scattering | Dooryhee,Eric Y
| ADDO | Elec - Ring Power Supply Systems | ADDO - Elec - Ring Power Supply Systems | Jon Sandberg |  | PSEH | Imaging & Microscopy | PSEH - Imaging & Microscopy | Chu, Yong
| ADEF | Fac & Exp - Power Distribution | ADEF - Fac & Exp - Power Distribution | Jon Sandberg |  | PSEI | Hard X-ray Spectroscopy | PSEI - Hard X-ray Spectroscopy | Attenkofer,Klaus
| ADHK | eRHIC R&D | ADHK - eRHIC R&D | Ferdinand Willeke |  | PSEO | User Services, Comm, Education & Outreach | PSEO - User Services, Comm, Education & Outreach | Miller,Lisa M
| ADCD | Conduct of Operations | ADCD - Conduct of Operations | Peter Cirnigliaro |  | PSEP | Exp Dev - Res Ops Support Grp | PSEP - Exp Dev - Res Ops Support Grp | Buckley,Michael F
| ADIA | ESSHQ | ADIA - ESSHQ | Peter Cirnigliaro |  | PSER | Experiment Development | PSER - Experiment Development | W.K. Lee
| ADEA | Exp - Management | ADEA - Exp - Management | William Christie |  | PSET | Exp Dev - Optics & Metrology Grp | PSET - Exp Dev - Optics & Metrology Grp | Idir,Mourad
| ADCL | Fac & Exp - EAG - Management | ADCL - Fac & Exp - EAG - Management | Charles Folz |  | PSEU | Detectors | PSEU - Detectors | Siddons,David P
| ADEC | Exp - Facilities & Experiments | ADEC - Exp - Facilities & Experiments | Charles Folz |  | PSEV | Exp Dev - Beamline Eng Grp | PSEV - Exp Dev - Beamline Eng Grp | Carlucci-Dayton,Mary
| ADED | Fac & Exp - Engineering | ADED - Fac & Exp - Engineering | Charles Folz |  | PSEW | Technical Support | PSEW - Technical Support | Bennett,Steven
| ADEG | Fac & Exp - Water Systems | ADEG - Fac & Exp - Water Systems | Charles Folz |  | PSFE | Structural Biology | PSFE - Structural Biology | McSweeney,Sean M
| ADEI | Fac & Exp - Survey | ADEI - Fac & Exp - Survey | Charles Folz |  | PSHA | Controls | PSHA - Controls | Farnsworth,Richard I
| ADEJ | Fac & Exp - EAG - C-A Support | ADEJ - Fac & Exp - EAG - C-A Support | Charles Folz |  | PSHB | Accelerator Controls | PSHB - Accelerator Controls | Tian,Yuke
| ADEK | Fac & Exp - EAG - Beam & Exp Services | ADEK - Fac & Exp - EAG - Beam & Exp Services | Charles Folz |  | PSHC | Motion Controls (EPS) | PSHC - Motion Controls (EPS) | Bassan,Harmanpreet S
| Trades | BNL Trades/Crafts | Trades - BNL Trades/Crafts | Charles Folz |  | PSHD | Data Acquisition, Management and Analysis | PSHD - Data Acquisition, Management and Analysis | Campbell,Stuart
| ADCX | Instr - Beam Comp. & Instrumentation Engineering | ADCX - Instr - Beam Comp. & Instrumentation Engineering | Michiko Minty |  | PSHE | IT Infrastructure | PSHE - IT Infrastructure | Petkus,Robert A
| ADCY | Instr - Beam Comp. & Instrumentation Techs | ADCY - Instr - Beam Comp. & Instrumentation Techs | Michiko Minty |  | PSHH | Beamline Controls | PSHH - Beamline Controls | Yin,Zhijian
| ADHB | Instr - Instrumentation Systems | ADHB - Instr - Instrumentation Systems | Michiko Minty |  | PQPM | Project Controls | PQPM - Project Controls | Lavelle, Cathy
| ADHF | Instr - Beam Diagnostics & Control | ADHF - Instr - Beam Diagnostics & Control | Michiko Minty |  | OTHER | OTHER including Trades | OTHER - OTHER including Trades | NA
| ADMO | Machine Operations & Maint | ADMO - Machine Operations & Maint | Michiko Minty |  | AELE | Assigned Electricians | AELE - Assigned Electricians | Ganetis,George L
| ADCP | Mechanical Systems | ADCP - Mechanical Systems | Gary McIntyre |  | RIGG | Riggers | RIGG - Riggers | Fries,Greg
| ADJA | BLIP/RRPL Group | ADJA - BLIP/RRPL Group | Cathy Cutler |  | UC | Uncategorized | UC - Uncategorized | NA
| INST | Instrumentation Division | INST - Instrumentation Division | Name TBD |  | Partner | Partner Funded Activities | Partner - Partner Funded Activities | NA
| MAGT | Magnet Division | MAGT - Magnet Division | Name TBD
| PHYS | Physics Department | PHYS - Physics Department | Name TBD
| ADEB | Exp - Physics Support | ADEB - Exp - Physics Support | Adam Rusek
| ADCZ | PREINJEC SCI/ENGR/TECH (Injection System Management) | ADCZ - PREINJEC SCI/ENGR/TECH (Injection System Management) | Deepak Raparia
| ADDH | LINAC | ADDH - LINAC | Deepak Raparia
| ADPA | Tandem Techs | ADPA - Tandem Techs | Deepak Raparia
| ADCQ | SRF Techs | ADCQ - SRF Techs | Alexander Zaltsman
| ADCS | RF/SRF Scientific/ Engineering | ADCS - RF/SRF Scientific/ Engineering | Alexander Zaltsman
| ADCT | RF - Techs | ADCT - RF - Techs | Alexander Zaltsman
| Contractor | BNL Contracted Labor | Contractor - BNL Contracted Labor | Name TBD
| EXT | External Department | EXT - External Department | Name TBD
| MISC | Miscellaneous | MISC - Miscellaneous | Name TBD
| NS | To Be Determined | NS - To Be Determined | Name TBD
| Partner | Partner Labor | Partner - Partner Labor | Name TBD
| ADDB | Vacuum - Engineering | ADDB - Vacuum - Engineering | Michael Mapes
| ADDC | Vacuum - Techs | ADDC - Vacuum - Techs | Michael Mapes
| NLBR | Nonlabor | NLBR - Nonlabor | Name TBD

## Resource Structure 1 (hidden)
RESOURCE STRUCTURE: | C-AD |  |  | C-AD DOE Funded Projects |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | FY18_CAD |  |  | Superconducting Magnet Div. (DOE Funded) |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | FY18_eRHIC_SMD |  |  | NPP Directorate (Overhead Funded) FY19 Base |  |  | Burdens per FY19 Trim1_20181020 developed by KWJ on 20181101 | [13 empty] | FY19_NPPOH |  |  | NPP C-AD DOE Ext Const Rate (eRHIC) FY19 Base |  |  | Burdens per FY19 Trim1_20181020 developed by KWJ on 20181101 | [13 empty] | FY19_eRHICex |  |  | NPP C-AD DOE Ext Const Rate (eRHIC) 5/3_1760 |  |  | This rate set normalizes the rates in the trim file (sheet "180120LaborRates") to 1760 hrs per year. | [13 empty] | FY18_eRHICex |  |  | NPP C-AD DOE Ext Const Rate (eRHIC) 5/3 |  |  | This rate set normalizes the rates in the trim file (sheet "180120LaborRates") to 1780 hrs per year. | [13 empty] | FY18_eRHICex_1780 |  |  | NPP C-AD DOE Ext Const Rate NSLS2 (eRHIC) 5/3 |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | FY18_eRHICex_NSLS2 |  |  | NPP C-AD DOE Ext Const Rate (eRHIC) 5/3_1760 |  |  | This rate set normalizes the rates in the trim file (sheet "180120LaborRates") to 1760 hrs per year. | [13 empty] | FY18_eRHICex |  |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) |  |  | These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 | [13 empty] | FY20_eRHICex |  |  | C-AD FY20 |  |  | These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 | [13 empty] | RESOURCE ID SUFFIX |  |  | C-AD FY20_CeC |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | FY20_CAD_CL |  |  | NPP C-AD DOE Ext Const(EIC FY20 Base Yr) |  |  | "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 | [13 empty] | FY20_EIC |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX
Resource ID | Description | Resource Type | Combined Name | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35
Purch<$2M | Purchases<$2M_NonLabor | NonLabor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 0.97752; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 1; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 1.023; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 1.0465; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 1.0706; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 1.0952; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 1.1204; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 1.1462; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 1.1725; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 1.1995; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 1.2271; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 1.2553; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 1.2842; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 1.3137; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 1.1133; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 1.1389; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 1.1651; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 1.1919; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 1.2193; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 1.2473; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 1.276; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 1.3054; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 1.3354; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 1.3661; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 1.3975; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 1.4297; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 1.4626; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 1.4962; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.1133; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.1389; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.1651; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.1919; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.2193; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.2473; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.276; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.3054; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.3354; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.3661; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.3975; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.4297; Insert Notes About Rate Set - Date, Origin, Etc FY31: 1.4626; Insert Notes About Rate Set - Date, Origin, Etc FY32: 1.4962; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 0.97752; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 1; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 1.023; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 1.0465; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 1.0706; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 1.0952; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 1.1204; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 1.1462; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 1.1725; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 1.1995; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 1.2271; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 1.2553; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 1.2842; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 1.3137
Purch>$2M | Purchases>$2M (Portion Over)_NonLabor | NonLabor |  | 0 | 0 | 1.023 | 1.0435 | 1.0643 | 1.0856 | 1.1073 | 1.1295 | 1.1521 | 1.1751 | 1.1986 | 1.2226 | 1.247 | 1.272 | 1.2974 | 1.3234 | 1.3498 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.0435 | 1.0643 | 1.0856 | 1.1073 | 1.1295 | 1.1521 | 1.1751 | 1.1986 | 1.2226 | 1.247 | 1.272 | 1.2974 | 1.3234 | 1.3498 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.3439 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.3439 |  |  |  | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97752 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.344 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97752 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purch_Const | Purchases_Construction Contract_NonLabor | NonLabor |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1057 | 1.1389 | 1.1731 | 1.2083 | 1.2445 | 1.2818 | 1.3203 | 1.3599 | 1.4007 | 1.4427 | 1.486 | 1.5306 | 1.5765 | 1.6238 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1057 | 1.1389 | 1.1731 | 1.2083 | 1.2445 | 1.2818 | 1.3203 | 1.3599 | 1.4007 | 1.4427 | 1.486 | 1.5306 | 1.5765 | 1.6238 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRAVEL | Travel_NonLabor | NonLabor |  | 0 | 0 | 1.5462 | 1.6944 | 1.7282 | 1.7628 | 1.7981 | 1.834 | 1.8707 | 1.9081 | 1.9463 | 1.9852 | 2.0249 | 2.0654 | 2.1067 | 2.1488 | 2.1918 | 0 | 0 | 0 | 0 | 0 | 1.5462 | 1.6944 | 1.7282 | 1.7628 | 1.7981 | 1.834 | 1.8707 | 1.9081 | 1.9463 | 1.9852 | 2.0249 | 2.0654 | 2.1067 | 2.1488 | 2.1918 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2071 | 1.2348 | 1.2632 | 1.2923 | 1.322 | 1.3524 | 1.3835 | 1.4154 | 1.4479 | 1.4812 | 1.5153 | 1.5501 | 1.5858 | 1.6223 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2071 | 1.2348 | 1.2632 | 1.2923 | 1.322 | 1.3524 | 1.3835 | 1.4154 | 1.4479 | 1.4812 | 1.5153 | 1.5501 | 1.5858 | 1.6223 |  |  |  | 0 | 0 | 1.2768 | 1.2312 | 1.2558 | 1.281 | 1.3066 | 1.3327 | 1.3594 | 1.3866 | 1.4143 | 1.4426 | 1.4714 | 1.5009 | 1.5309 | 1.5615 | 1.5927 | 0 | 0 | 0 | 0 | 0 | 1.2768 | 1.2312 | 1.2558 | 1.281 | 1.3066 | 1.3327 | 1.3594 | 1.3866 | 1.4143 | 1.4426 | 1.4714 | 1.5009 | 1.5309 | 1.5615 | 1.5927 | 0 | 0 | 0 | 0 | 0 | 1.2768 | 1.1298 | 1.1523 | 1.1754 | 1.1989 | 1.2229 | 1.2473 | 1.2723 | 1.2977 | 1.3237 | 1.3502 | 1.3772 | 1.4047 | 1.4328 | 1.4615 | 0 | 0 | 0 | 0 | 0 | 1.2768 | 1.2312 | 1.2558 | 1.281 | 1.3066 | 1.3327 | 1.3594 | 1.3866 | 1.4143 | 1.4426 | 1.4714 | 1.5009 | 1.5309 | 1.5615 | 1.5927 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2059 | 1.2336 | 1.262 | 1.291 | 1.3207 | 1.3511 | 1.3822 | 1.414 | 1.4465 | 1.4798 | 1.5138 | 1.5486 | 1.5842 | 1.6207 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6238 | 1.6611 | 1.6993 | 1.7384 | 1.7784 | 1.8193 | 1.8612 | 1.904 | 1.9478 | 1.9925 | 2.0384 | 2.0853 | 2.1332 | 2.1823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2122 | 1.24 | 1.2839 | 1.3078 | 1.3379 | 1.3687 | 1.4001 | 1.4323 | 1.4653 | 1.499 | 1.5335 | 1.5687 | 1.6048 | 1.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DES_L | Designer_Low | Labor |  | 0 | 0 | 132.4687 | 140.9761 | 145.3463 | 149.8521 | 154.4975 | 159.2869 | 164.2248 | 169.3158 | 174.5645 | 179.976 | 185.5553 | 191.3075 | 197.238 | 203.3524 | 209.6564 | 0 | 0 | 0 | 0 | 0 | 146.6818 | 153.0052 | 157.7483 | 162.6385 | 167.6803 | 172.8784 | 178.2376 | 183.763 | 189.4596 | 195.3329 | 201.3882 | 207.6313 | 214.0678 | 220.7039 | 227.5457 | 0 | 0 | 0 | 0 | 0 | 0 | 89.445 | 92.1283 | 94.8922 | 97.7389 | 100.6711 | 103.6912 | 106.802 | 110.006 | 113.3062 | 116.7054 | 120.2065 | 123.8127 | 127.5271 | 131.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 89.445 | 92.1283 | 94.8922 | 97.7389 | 100.6711 | 103.6912 | 106.802 | 110.006 | 113.3062 | 116.7054 | 120.2065 | 123.8127 | 127.5271 | 131.3529 | 0 | 0 | 0 | 0 | 0 | 87.9173 | 88.9808 | 91.7392 | 94.5832 | 97.5152 | 100.5382 | 103.6549 | 106.8682 | 110.1811 | 113.5967 | 117.1182 | 120.7489 | 124.4921 | 128.3513 | 132.3302 | 0 | 0 | 0 | 0 | 0 | 86.9295 | 87.981 | 90.7085 | 93.5204 | 96.4196 | 99.4086 | 102.4902 | 105.6674 | 108.9431 | 112.3203 | 115.8023 | 119.3922 | 123.0933 | 126.9092 | 130.8434 | 0 | 0 | 0 | 0 | 0 | 86.9295 | 80.7299 | 83.2326 | 85.8128 | 88.473 | 91.2156 | 94.0433 | 96.9587 | 99.9644 | 103.0633 | 106.2582 | 109.5522 | 112.9484 | 116.4497 | 120.0597 | 0 | 0 | 0 | 0 | 0 | 87.9173 | 88.9808 | 91.7392 | 94.5832 | 97.5152 | 100.5382 | 103.6549 | 106.8682 | 110.1811 | 113.5967 | 117.1182 | 120.7489 | 124.4921 | 128.3513 | 132.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 90.746 | 93.9221 | 97.2094 | 100.6118 | 104.1332 | 107.7778 | 111.55 | 115.4543 | 119.4952 | 123.6775 | 128.0062 | 132.4865 | 137.1235 | 141.9228 | 0 | 0 | 0 | 0 | 0 | 0 | 141.8334 | 146.7976 | 151.9355 | 157.2533 | 162.7571 | 168.4536 | 174.3495 | 180.4518 | 186.7676 | 193.3044 | 200.0701 | 207.0725 | 214.3201 | 221.8213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.2179 | 94.4105 | 98.8942 | 101.9195 | 105.4867 | 109.1788 | 113 | 116.955 | 121.0484 | 125.2851 | 129.6701 | 134.2086 | 138.9059 | 143.7676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DES_M | Designer_Med | Labor |  | 0 | 0 | 150.9888 | 160.6855 | 165.6667 | 170.8024 | 176.0973 | 181.5563 | 187.1845 | 192.9872 | 198.9699 | 205.1379 | 211.4972 | 218.0536 | 224.8133 | 231.7825 | 238.9677 | 0 | 0 | 0 | 0 | 0 | 167.1889 | 174.3963 | 179.8026 | 185.3765 | 191.1232 | 197.048 | 203.1565 | 209.4543 | 215.9474 | 222.6418 | 229.5437 | 236.6595 | 243.996 | 251.5598 | 259.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 100.2814 | 103.3901 | 106.5952 | 109.8997 | 113.3066 | 116.8191 | 120.4404 | 124.1741 | 128.0235 | 131.9922 | 136.084 | 140.3026 | 144.652 | 149.1362 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 92.0165 | 94.869 | 97.81 | 100.8421 | 103.9682 | 107.1912 | 110.5141 | 113.9401 | 117.4722 | 121.1138 | 124.8684 | 128.7393 | 132.7302 | 136.8449 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8811 | 107.5169 | 111.28 | 115.1748 | 119.206 | 123.3782 | 127.6964 | 132.1658 | 136.7916 | 141.5793 | 146.5346 | 151.6633 | 156.9715 | 162.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 162.3632 | 168.0459 | 173.9275 | 180.015 | 186.3155 | 192.8365 | 199.5858 | 206.5713 | 213.8013 | 221.2843 | 229.0293 | 237.0453 | 245.3419 | 253.9289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4212 | 108.076 | 113.2086 | 116.6719 | 120.7554 | 124.9819 | 129.3562 | 133.8837 | 138.5696 | 143.4196 | 148.4392 | 153.6346 | 159.0118 | 164.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DES_H | Designer_High | Labor |  | 0 | 0 | 172.684 | 183.774 | 189.471 | 195.3446 | 201.4003 | 207.6437 | 214.0807 | 220.7172 | 227.5594 | 234.6138 | 241.8868 | 249.3853 | 257.1162 | 265.0868 | 273.3045 | 0 | 0 | 0 | 0 | 0 | 191.2119 | 199.455 | 205.6381 | 212.0129 | 218.5853 | 225.3614 | 232.3476 | 239.5504 | 246.9764 | 254.6327 | 262.5263 | 270.6646 | 279.0552 | 287.706 | 296.6248 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 114.6906 | 118.246 | 121.9117 | 125.6909 | 129.5873 | 133.6046 | 137.7463 | 142.0164 | 146.4189 | 150.9579 | 155.6376 | 160.4624 | 165.4367 | 170.5653 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 105.2382 | 108.5006 | 111.8641 | 115.3319 | 118.9072 | 122.5933 | 126.3937 | 130.3119 | 134.3516 | 138.5165 | 142.8105 | 147.2376 | 151.802 | 156.5078 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 118.6801 | 122.8339 | 127.1331 | 131.5828 | 136.1882 | 140.9547 | 145.8882 | 150.9942 | 156.279 | 161.7488 | 167.41 | 173.2694 | 179.3338 | 185.6105 | 0 | 0 | 0 | 0 | 0 | 0 | 185.4936 | 191.9859 | 198.7054 | 205.6601 | 212.8582 | 220.3082 | 228.019 | 235.9997 | 244.2597 | 252.8087 | 261.657 | 270.815 | 280.2936 | 290.1038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.2972 | 123.4726 | 129.3364 | 133.2931 | 137.9584 | 142.7869 | 147.7844 | 152.9569 | 158.3104 | 163.8513 | 169.5861 | 175.5216 | 181.6648 | 188.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ET_L | Electrical Technician_Low | Labor |  | 0 | 0 | 102.9641 | 109.5765 | 112.9734 | 116.4756 | 120.0863 | 123.809 | 127.6471 | 131.6042 | 135.6839 | 139.8901 | 144.2267 | 148.6977 | 153.3073 | 158.0599 | 162.9597 | 0 | 0 | 0 | 0 | 0 | 114.0114 | 118.9264 | 122.6131 | 126.4141 | 130.333 | 134.3733 | 138.5389 | 142.8336 | 147.2614 | 151.8265 | 156.5331 | 161.3857 | 166.3886 | 171.5467 | 176.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 68.3851 | 70.505 | 72.6907 | 74.9441 | 77.2674 | 79.6626 | 82.1322 | 84.6783 | 87.3033 | 90.0097 | 92.8 | 95.6768 | 98.6428 | 101.7007 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 62.749 | 64.6942 | 66.6997 | 68.7674 | 70.8992 | 73.0971 | 75.3631 | 77.6994 | 80.108 | 82.5914 | 85.1517 | 87.7914 | 90.513 | 93.3189 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5186 | 72.9868 | 75.5413 | 78.1853 | 80.9217 | 83.754 | 86.6854 | 89.7194 | 92.8596 | 96.1097 | 99.4735 | 102.9551 | 106.5585 | 110.288 | 0 | 0 | 0 | 0 | 0 | 0 | 110.2186 | 114.0762 | 118.0689 | 122.2013 | 126.4784 | 130.9051 | 135.4868 | 140.2288 | 145.1368 | 150.2166 | 155.4742 | 160.9158 | 166.5479 | 172.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8853 | 73.3663 | 76.8505 | 79.2015 | 81.9736 | 84.8427 | 87.8122 | 90.8856 | 94.0666 | 97.3589 | 100.7665 | 104.2933 | 107.9436 | 111.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ET_M | Electrical Technician_Med | Labor |  | 0 | 0 | 132.4687 | 140.9761 | 145.3463 | 149.8521 | 154.4975 | 159.2869 | 164.2248 | 169.3158 | 174.5645 | 179.976 | 185.5553 | 191.3075 | 197.238 | 203.3524 | 209.6564 | 0 | 0 | 0 | 0 | 0 | 146.6818 | 153.0052 | 157.7483 | 162.6385 | 167.6803 | 172.8784 | 178.2376 | 183.763 | 189.4596 | 195.3329 | 201.3882 | 207.6313 | 214.0678 | 220.7039 | 227.5457 | 0 | 0 | 0 | 0 | 0 | 0 | 89.445 | 92.1283 | 94.8922 | 97.7389 | 100.6711 | 103.6912 | 106.802 | 110.006 | 113.3062 | 116.7054 | 120.2065 | 123.8127 | 127.5271 | 131.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 89.445 | 92.1283 | 94.8922 | 97.7389 | 100.6711 | 103.6912 | 106.802 | 110.006 | 113.3062 | 116.7054 | 120.2065 | 123.8127 | 127.5271 | 131.3529 | 0 | 0 | 0 | 0 | 0 | 87.9173 | 88.9808 | 91.7392 | 94.5832 | 97.5152 | 100.5382 | 103.6549 | 106.8682 | 110.1811 | 113.5967 | 117.1182 | 120.7489 | 124.4921 | 128.3513 | 132.3302 | 0 | 0 | 0 | 0 | 0 | 86.9295 | 87.981 | 90.7085 | 93.5204 | 96.4196 | 99.4086 | 102.4902 | 105.6674 | 108.9431 | 112.3203 | 115.8023 | 119.3922 | 123.0933 | 126.9092 | 130.8434 | 0 | 0 | 0 | 0 | 0 | 86.9295 | 80.7299 | 83.2326 | 85.8128 | 88.473 | 91.2156 | 94.0433 | 96.9587 | 99.9644 | 103.0633 | 106.2582 | 109.5522 | 112.9484 | 116.4497 | 120.0597 | 0 | 0 | 0 | 0 | 0 | 87.9173 | 88.9808 | 91.7392 | 94.5832 | 97.5152 | 100.5382 | 103.6549 | 106.8682 | 110.1811 | 113.5967 | 117.1182 | 120.7489 | 124.4921 | 128.3513 | 132.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 90.746 | 93.9221 | 97.2094 | 100.6118 | 104.1332 | 107.7778 | 111.55 | 115.4543 | 119.4952 | 123.6775 | 128.0062 | 132.4865 | 137.1235 | 141.9228 | 0 | 0 | 0 | 0 | 0 | 0 | 141.8334 | 146.7976 | 151.9355 | 157.2533 | 162.7571 | 168.4536 | 174.3495 | 180.4518 | 186.7676 | 193.3044 | 200.0701 | 207.0725 | 214.3201 | 221.8213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.2179 | 94.4105 | 98.8942 | 101.9195 | 105.4867 | 109.1788 | 113 | 116.955 | 121.0484 | 125.2851 | 129.6701 | 134.2086 | 138.9059 | 143.7676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ET_H | Electrical Technician_High | Labor |  | 0 | 0 | 150.9888 | 160.6855 | 165.6667 | 170.8024 | 176.0973 | 181.5563 | 187.1845 | 192.9872 | 198.9699 | 205.1379 | 211.4972 | 218.0536 | 224.8133 | 231.7825 | 238.9677 | 0 | 0 | 0 | 0 | 0 | 167.1889 | 174.3963 | 179.8026 | 185.3765 | 191.1232 | 197.048 | 203.1565 | 209.4543 | 215.9474 | 222.6418 | 229.5437 | 236.6595 | 243.996 | 251.5598 | 259.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 100.2814 | 103.3901 | 106.5952 | 109.8997 | 113.3066 | 116.8191 | 120.4404 | 124.1741 | 128.0235 | 131.9922 | 136.084 | 140.3026 | 144.652 | 149.1362 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 92.0165 | 94.869 | 97.81 | 100.8421 | 103.9682 | 107.1912 | 110.5141 | 113.9401 | 117.4722 | 121.1138 | 124.8684 | 128.7393 | 132.7302 | 136.8449 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8811 | 107.5169 | 111.28 | 115.1748 | 119.206 | 123.3782 | 127.6964 | 132.1658 | 136.7916 | 141.5793 | 146.5346 | 151.6633 | 156.9715 | 162.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 162.3632 | 168.0459 | 173.9275 | 180.015 | 186.3155 | 192.8365 | 199.5858 | 206.5713 | 213.8013 | 221.2843 | 229.0293 | 237.0453 | 245.3419 | 253.9289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4212 | 108.076 | 113.2086 | 116.6719 | 120.7554 | 124.9819 | 129.3562 | 133.8837 | 138.5696 | 143.4196 | 148.4392 | 153.6346 | 159.0118 | 164.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EMT_L | Electro-Mechanical Technician_Low | Labor |  | 0 | 0 | 102.9641 | 109.5765 | 112.9734 | 116.4756 | 120.0863 | 123.809 | 127.6471 | 131.6042 | 135.6839 | 139.8901 | 144.2267 | 148.6977 | 153.3073 | 158.0599 | 162.9597 | 0 | 0 | 0 | 0 | 0 | 114.0114 | 118.9264 | 122.6131 | 126.4141 | 130.333 | 134.3733 | 138.5389 | 142.8336 | 147.2614 | 151.8265 | 156.5331 | 161.3857 | 166.3886 | 171.5467 | 176.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 68.3851 | 70.505 | 72.6907 | 74.9441 | 77.2674 | 79.6626 | 82.1322 | 84.6783 | 87.3033 | 90.0097 | 92.8 | 95.6768 | 98.6428 | 101.7007 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 62.749 | 64.6942 | 66.6997 | 68.7674 | 70.8992 | 73.0971 | 75.3631 | 77.6994 | 80.108 | 82.5914 | 85.1517 | 87.7914 | 90.513 | 93.3189 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5186 | 72.9868 | 75.5413 | 78.1853 | 80.9217 | 83.754 | 86.6854 | 89.7194 | 92.8596 | 96.1097 | 99.4735 | 102.9551 | 106.5585 | 110.288 | 0 | 0 | 0 | 0 | 0 | 0 | 110.2186 | 114.0762 | 118.0689 | 122.2013 | 126.4784 | 130.9051 | 135.4868 | 140.2288 | 145.1368 | 150.2166 | 155.4742 | 160.9158 | 166.5479 | 172.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8853 | 73.3663 | 76.8505 | 79.2015 | 81.9736 | 84.8427 | 87.8122 | 90.8856 | 94.0666 | 97.3589 | 100.7665 | 104.2933 | 107.9436 | 111.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EMT_M | Electro-Mechanical Technician_Med | Labor |  | 0 | 0 | 132.4687 | 140.9761 | 145.3463 | 149.8521 | 154.4975 | 159.2869 | 164.2248 | 169.3158 | 174.5645 | 179.976 | 185.5553 | 191.3075 | 197.238 | 203.3524 | 209.6564 | 0 | 0 | 0 | 0 | 0 | 146.6818 | 153.0052 | 157.7483 | 162.6385 | 167.6803 | 172.8784 | 178.2376 | 183.763 | 189.4596 | 195.3329 | 201.3882 | 207.6313 | 214.0678 | 220.7039 | 227.5457 | 0 | 0 | 0 | 0 | 0 | 0 | 89.445 | 92.1283 | 94.8922 | 97.7389 | 100.6711 | 103.6912 | 106.802 | 110.006 | 113.3062 | 116.7054 | 120.2065 | 123.8127 | 127.5271 | 131.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 89.445 | 92.1283 | 94.8922 | 97.7389 | 100.6711 | 103.6912 | 106.802 | 110.006 | 113.3062 | 116.7054 | 120.2065 | 123.8127 | 127.5271 | 131.3529 | 0 | 0 | 0 | 0 | 0 | 87.9173 | 88.9808 | 91.7392 | 94.5832 | 97.5152 | 100.5382 | 103.6549 | 106.8682 | 110.1811 | 113.5967 | 117.1182 | 120.7489 | 124.4921 | 128.3513 | 132.3302 | 0 | 0 | 0 | 0 | 0 | 86.9295 | 87.981 | 90.7085 | 93.5204 | 96.4196 | 99.4086 | 102.4902 | 105.6674 | 108.9431 | 112.3203 | 115.8023 | 119.3922 | 123.0933 | 126.9092 | 130.8434 | 0 | 0 | 0 | 0 | 0 | 86.9295 | 80.7299 | 83.2326 | 85.8128 | 88.473 | 91.2156 | 94.0433 | 96.9587 | 99.9644 | 103.0633 | 106.2582 | 109.5522 | 112.9484 | 116.4497 | 120.0597 | 0 | 0 | 0 | 0 | 0 | 87.9173 | 88.9808 | 91.7392 | 94.5832 | 97.5152 | 100.5382 | 103.6549 | 106.8682 | 110.1811 | 113.5967 | 117.1182 | 120.7489 | 124.4921 | 128.3513 | 132.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 90.746 | 93.9221 | 97.2094 | 100.6118 | 104.1332 | 107.7778 | 111.55 | 115.4543 | 119.4952 | 123.6775 | 128.0062 | 132.4865 | 137.1235 | 141.9228 | 0 | 0 | 0 | 0 | 0 | 0 | 141.8334 | 146.7976 | 151.9355 | 157.2533 | 162.7571 | 168.4536 | 174.3495 | 180.4518 | 186.7676 | 193.3044 | 200.0701 | 207.0725 | 214.3201 | 221.8213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.2179 | 94.4105 | 98.8942 | 101.9195 | 105.4867 | 109.1788 | 113 | 116.955 | 121.0484 | 125.2851 | 129.6701 | 134.2086 | 138.9059 | 143.7676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EMT_H | Electro-Mechanical Technician_High | Labor |  | 0 | 0 | 150.9888 | 160.6855 | 165.6667 | 170.8024 | 176.0973 | 181.5563 | 187.1845 | 192.9872 | 198.9699 | 205.1379 | 211.4972 | 218.0536 | 224.8133 | 231.7825 | 238.9677 | 0 | 0 | 0 | 0 | 0 | 167.1889 | 174.3963 | 179.8026 | 185.3765 | 191.1232 | 197.048 | 203.1565 | 209.4543 | 215.9474 | 222.6418 | 229.5437 | 236.6595 | 243.996 | 251.5598 | 259.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 100.2814 | 103.3901 | 106.5952 | 109.8997 | 113.3066 | 116.8191 | 120.4404 | 124.1741 | 128.0235 | 131.9922 | 136.084 | 140.3026 | 144.652 | 149.1362 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 92.0165 | 94.869 | 97.81 | 100.8421 | 103.9682 | 107.1912 | 110.5141 | 113.9401 | 117.4722 | 121.1138 | 124.8684 | 128.7393 | 132.7302 | 136.8449 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8811 | 107.5169 | 111.28 | 115.1748 | 119.206 | 123.3782 | 127.6964 | 132.1658 | 136.7916 | 141.5793 | 146.5346 | 151.6633 | 156.9715 | 162.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 162.3632 | 168.0459 | 173.9275 | 180.015 | 186.3155 | 192.8365 | 199.5858 | 206.5713 | 213.8013 | 221.2843 | 229.0293 | 237.0453 | 245.3419 | 253.9289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4212 | 108.076 | 113.2086 | 116.6719 | 120.7554 | 124.9819 | 129.3562 | 133.8837 | 138.5696 | 143.4196 | 148.4392 | 153.6346 | 159.0118 | 164.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MT_L | Mechanical Technician_Low | Labor |  | 0 | 0 | 102.9641 | 109.5765 | 112.9734 | 116.4756 | 120.0863 | 123.809 | 127.6471 | 131.6042 | 135.6839 | 139.8901 | 144.2267 | 148.6977 | 153.3073 | 158.0599 | 162.9597 | 0 | 0 | 0 | 0 | 0 | 114.0114 | 118.9264 | 122.6131 | 126.4141 | 130.333 | 134.3733 | 138.5389 | 142.8336 | 147.2614 | 151.8265 | 156.5331 | 161.3857 | 166.3886 | 171.5467 | 176.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 68.3851 | 70.505 | 72.6907 | 74.9441 | 77.2674 | 79.6626 | 82.1322 | 84.6783 | 87.3033 | 90.0097 | 92.8 | 95.6768 | 98.6428 | 101.7007 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 62.749 | 64.6942 | 66.6997 | 68.7674 | 70.8992 | 73.0971 | 75.3631 | 77.6994 | 80.108 | 82.5914 | 85.1517 | 87.7914 | 90.513 | 93.3189 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5186 | 72.9868 | 75.5413 | 78.1853 | 80.9217 | 83.754 | 86.6854 | 89.7194 | 92.8596 | 96.1097 | 99.4735 | 102.9551 | 106.5585 | 110.288 | 0 | 0 | 0 | 0 | 0 | 0 | 110.2186 | 114.0762 | 118.0689 | 122.2013 | 126.4784 | 130.9051 | 135.4868 | 140.2288 | 145.1368 | 150.2166 | 155.4742 | 160.9158 | 166.5479 | 172.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8853 | 73.3663 | 76.8505 | 79.2015 | 81.9736 | 84.8427 | 87.8122 | 90.8856 | 94.0666 | 97.3589 | 100.7665 | 104.2933 | 107.9436 | 111.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MT_M | Mechanical Technician_Med | Labor |  | 0 | 0 | 132.4687 | 140.9761 | 145.3463 | 149.8521 | 154.4975 | 159.2869 | 164.2248 | 169.3158 | 174.5645 | 179.976 | 185.5553 | 191.3075 | 197.238 | 203.3524 | 209.6564 | 0 | 0 | 0 | 0 | 0 | 146.6818 | 153.0052 | 157.7483 | 162.6385 | 167.6803 | 172.8784 | 178.2376 | 183.763 | 189.4596 | 195.3329 | 201.3882 | 207.6313 | 214.0678 | 220.7039 | 227.5457 | 0 | 0 | 0 | 0 | 0 | 0 | 89.445 | 92.1283 | 94.8922 | 97.7389 | 100.6711 | 103.6912 | 106.802 | 110.006 | 113.3062 | 116.7054 | 120.2065 | 123.8127 | 127.5271 | 131.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 89.445 | 92.1283 | 94.8922 | 97.7389 | 100.6711 | 103.6912 | 106.802 | 110.006 | 113.3062 | 116.7054 | 120.2065 | 123.8127 | 127.5271 | 131.3529 | 0 | 0 | 0 | 0 | 0 | 87.9173 | 88.9808 | 91.7392 | 94.5832 | 97.5152 | 100.5382 | 103.6549 | 106.8682 | 110.1811 | 113.5967 | 117.1182 | 120.7489 | 124.4921 | 128.3513 | 132.3302 | 0 | 0 | 0 | 0 | 0 | 86.9295 | 87.981 | 90.7085 | 93.5204 | 96.4196 | 99.4086 | 102.4902 | 105.6674 | 108.9431 | 112.3203 | 115.8023 | 119.3922 | 123.0933 | 126.9092 | 130.8434 | 0 | 0 | 0 | 0 | 0 | 86.9295 | 80.7299 | 83.2326 | 85.8128 | 88.473 | 91.2156 | 94.0433 | 96.9587 | 99.9644 | 103.0633 | 106.2582 | 109.5522 | 112.9484 | 116.4497 | 120.0597 | 0 | 0 | 0 | 0 | 0 | 87.9173 | 88.9808 | 91.7392 | 94.5832 | 97.5152 | 100.5382 | 103.6549 | 106.8682 | 110.1811 | 113.5967 | 117.1182 | 120.7489 | 124.4921 | 128.3513 | 132.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 90.746 | 93.9221 | 97.2094 | 100.6118 | 104.1332 | 107.7778 | 111.55 | 115.4543 | 119.4952 | 123.6775 | 128.0062 | 132.4865 | 137.1235 | 141.9228 | 0 | 0 | 0 | 0 | 0 | 0 | 141.8334 | 146.7976 | 151.9355 | 157.2533 | 162.7571 | 168.4536 | 174.3495 | 180.4518 | 186.7676 | 193.3044 | 200.0701 | 207.0725 | 214.3201 | 221.8213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.2179 | 94.4105 | 98.8942 | 101.9195 | 105.4867 | 109.1788 | 113 | 116.955 | 121.0484 | 125.2851 | 129.6701 | 134.2086 | 138.9059 | 143.7676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MT_H | Mechanical Technician_High | Labor |  | 0 | 0 | 150.9888 | 160.6855 | 165.6667 | 170.8024 | 176.0973 | 181.5563 | 187.1845 | 192.9872 | 198.9699 | 205.1379 | 211.4972 | 218.0536 | 224.8133 | 231.7825 | 238.9677 | 0 | 0 | 0 | 0 | 0 | 167.1889 | 174.3963 | 179.8026 | 185.3765 | 191.1232 | 197.048 | 203.1565 | 209.4543 | 215.9474 | 222.6418 | 229.5437 | 236.6595 | 243.996 | 251.5598 | 259.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 100.2814 | 103.3901 | 106.5952 | 109.8997 | 113.3066 | 116.8191 | 120.4404 | 124.1741 | 128.0235 | 131.9922 | 136.084 | 140.3026 | 144.652 | 149.1362 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 92.0165 | 94.869 | 97.81 | 100.8421 | 103.9682 | 107.1912 | 110.5141 | 113.9401 | 117.4722 | 121.1138 | 124.8684 | 128.7393 | 132.7302 | 136.8449 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8811 | 107.5169 | 111.28 | 115.1748 | 119.206 | 123.3782 | 127.6964 | 132.1658 | 136.7916 | 141.5793 | 146.5346 | 151.6633 | 156.9715 | 162.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 162.3632 | 168.0459 | 173.9275 | 180.015 | 186.3155 | 192.8365 | 199.5858 | 206.5713 | 213.8013 | 221.2843 | 229.0293 | 237.0453 | 245.3419 | 253.9289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4212 | 108.076 | 113.2086 | 116.6719 | 120.7554 | 124.9819 | 129.3562 | 133.8837 | 138.5696 | 143.4196 | 148.4392 | 153.6346 | 159.0118 | 164.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ST_L | Survey Tech_Low | Labor |  | 0 | 0 | 102.9641 | 109.5765 | 112.9734 | 116.4756 | 120.0863 | 123.809 | 127.6471 | 131.6042 | 135.6839 | 139.8901 | 144.2267 | 148.6977 | 153.3073 | 158.0599 | 162.9597 | 0 | 0 | 0 | 0 | 0 | 114.0114 | 118.9264 | 122.6131 | 126.4141 | 130.333 | 134.3733 | 138.5389 | 142.8336 | 147.2614 | 151.8265 | 156.5331 | 161.3857 | 166.3886 | 171.5467 | 176.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 68.3851 | 70.505 | 72.6907 | 74.9441 | 77.2674 | 79.6626 | 82.1322 | 84.6783 | 87.3033 | 90.0097 | 92.8 | 95.6768 | 98.6428 | 101.7007 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 62.749 | 64.6942 | 66.6997 | 68.7674 | 70.8992 | 73.0971 | 75.3631 | 77.6994 | 80.108 | 82.5914 | 85.1517 | 87.7914 | 90.513 | 93.3189 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5186 | 72.9868 | 75.5413 | 78.1853 | 80.9217 | 83.754 | 86.6854 | 89.7194 | 92.8596 | 96.1097 | 99.4735 | 102.9551 | 106.5585 | 110.288 | 0 | 0 | 0 | 0 | 0 | 0 | 110.2186 | 114.0762 | 118.0689 | 122.2013 | 126.4784 | 130.9051 | 135.4868 | 140.2288 | 145.1368 | 150.2166 | 155.4742 | 160.9158 | 166.5479 | 172.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8853 | 73.3663 | 76.8505 | 79.2015 | 81.9736 | 84.8427 | 87.8122 | 90.8856 | 94.0666 | 97.3589 | 100.7665 | 104.2933 | 107.9436 | 111.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ST_M | Survey Tech_Med | Labor |  | 0 | 0 | 150.9888 | 160.6855 | 165.6667 | 170.8024 | 176.0973 | 181.5563 | 187.1845 | 192.9872 | 198.9699 | 205.1379 | 211.4972 | 218.0536 | 224.8133 | 231.7825 | 238.9677 | 0 | 0 | 0 | 0 | 0 | 167.1889 | 174.3963 | 179.8026 | 185.3765 | 191.1232 | 197.048 | 203.1565 | 209.4543 | 215.9474 | 222.6418 | 229.5437 | 236.6595 | 243.996 | 251.5598 | 259.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 100.2814 | 103.3901 | 106.5952 | 109.8997 | 113.3066 | 116.8191 | 120.4404 | 124.1741 | 128.0235 | 131.9922 | 136.084 | 140.3026 | 144.652 | 149.1362 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 92.0165 | 94.869 | 97.81 | 100.8421 | 103.9682 | 107.1912 | 110.5141 | 113.9401 | 117.4722 | 121.1138 | 124.8684 | 128.7393 | 132.7302 | 136.8449 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8811 | 107.5169 | 111.28 | 115.1748 | 119.206 | 123.3782 | 127.6964 | 132.1658 | 136.7916 | 141.5793 | 146.5346 | 151.6633 | 156.9715 | 162.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 162.3632 | 168.0459 | 173.9275 | 180.015 | 186.3155 | 192.8365 | 199.5858 | 206.5713 | 213.8013 | 221.2843 | 229.0293 | 237.0453 | 245.3419 | 253.9289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4212 | 108.076 | 113.2086 | 116.6719 | 120.7554 | 124.9819 | 129.3562 | 133.8837 | 138.5696 | 143.4196 | 148.4392 | 153.6346 | 159.0118 | 164.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ST_H | Survey Tech_High | Labor |  | 0 | 0 | 172.684 | 183.774 | 189.471 | 195.3446 | 201.4003 | 207.6437 | 214.0807 | 220.7172 | 227.5594 | 234.6138 | 241.8868 | 249.3853 | 257.1162 | 265.0868 | 273.3045 | 0 | 0 | 0 | 0 | 0 | 191.2119 | 199.455 | 205.6381 | 212.0129 | 218.5853 | 225.3614 | 232.3476 | 239.5504 | 246.9764 | 254.6327 | 262.5263 | 270.6646 | 279.0552 | 287.706 | 296.6248 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 114.6906 | 118.246 | 121.9117 | 125.6909 | 129.5873 | 133.6046 | 137.7463 | 142.0164 | 146.4189 | 150.9579 | 155.6376 | 160.4624 | 165.4367 | 170.5653 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 105.2382 | 108.5006 | 111.8641 | 115.3319 | 118.9072 | 122.5933 | 126.3937 | 130.3119 | 134.3516 | 138.5165 | 142.8105 | 147.2376 | 151.802 | 156.5078 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 118.6801 | 122.8339 | 127.1331 | 131.5828 | 136.1882 | 140.9547 | 145.8882 | 150.9942 | 156.279 | 161.7488 | 167.41 | 173.2694 | 179.3338 | 185.6105 | 0 | 0 | 0 | 0 | 0 | 0 | 185.4936 | 191.9859 | 198.7054 | 205.6601 | 212.8582 | 220.3082 | 228.019 | 235.9997 | 244.2597 | 252.8087 | 261.657 | 270.815 | 280.2936 | 290.1038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.2972 | 123.4726 | 129.3364 | 133.2931 | 137.9584 | 142.7869 | 147.7844 | 152.9569 | 158.3104 | 163.8513 | 169.5861 | 175.5216 | 181.6648 | 188.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T_L | Technician_Low | Labor |  | 0 | 0 | 102.9641 | 109.5765 | 112.9734 | 116.4756 | 120.0863 | 123.809 | 127.6471 | 131.6042 | 135.6839 | 139.8901 | 144.2267 | 148.6977 | 153.3073 | 158.0599 | 162.9597 | 0 | 0 | 0 | 0 | 0 | 114.0114 | 118.9264 | 122.6131 | 126.4141 | 130.333 | 134.3733 | 138.5389 | 142.8336 | 147.2614 | 151.8265 | 156.5331 | 161.3857 | 166.3886 | 171.5467 | 176.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 68.3851 | 70.505 | 72.6907 | 74.9441 | 77.2674 | 79.6626 | 82.1322 | 84.6783 | 87.3033 | 90.0097 | 92.8 | 95.6768 | 98.6428 | 101.7007 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 62.749 | 64.6942 | 66.6997 | 68.7674 | 70.8992 | 73.0971 | 75.3631 | 77.6994 | 80.108 | 82.5914 | 85.1517 | 87.7914 | 90.513 | 93.3189 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5186 | 72.9868 | 75.5413 | 78.1853 | 80.9217 | 83.754 | 86.6854 | 89.7194 | 92.8596 | 96.1097 | 99.4735 | 102.9551 | 106.5585 | 110.288 | 0 | 0 | 0 | 0 | 0 | 0 | 110.2186 | 114.0762 | 118.0689 | 122.2013 | 126.4784 | 130.9051 | 135.4868 | 140.2288 | 145.1368 | 150.2166 | 155.4742 | 160.9158 | 166.5479 | 172.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8853 | 73.3663 | 76.8505 | 79.2015 | 81.9736 | 84.8427 | 87.8122 | 90.8856 | 94.0666 | 97.3589 | 100.7665 | 104.2933 | 107.9436 | 111.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T_M | Technician_Med | Labor |  | 0 | 0 | 150.9888 | 160.6855 | 165.6667 | 170.8024 | 176.0973 | 181.5563 | 187.1845 | 192.9872 | 198.9699 | 205.1379 | 211.4972 | 218.0536 | 224.8133 | 231.7825 | 238.9677 | 0 | 0 | 0 | 0 | 0 | 167.1889 | 174.3963 | 179.8026 | 185.3765 | 191.1232 | 197.048 | 203.1565 | 209.4543 | 215.9474 | 222.6418 | 229.5437 | 236.6595 | 243.996 | 251.5598 | 259.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 100.2814 | 103.3901 | 106.5952 | 109.8997 | 113.3066 | 116.8191 | 120.4404 | 124.1741 | 128.0235 | 131.9922 | 136.084 | 140.3026 | 144.652 | 149.1362 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 92.0165 | 94.869 | 97.81 | 100.8421 | 103.9682 | 107.1912 | 110.5141 | 113.9401 | 117.4722 | 121.1138 | 124.8684 | 128.7393 | 132.7302 | 136.8449 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8811 | 107.5169 | 111.28 | 115.1748 | 119.206 | 123.3782 | 127.6964 | 132.1658 | 136.7916 | 141.5793 | 146.5346 | 151.6633 | 156.9715 | 162.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 162.3632 | 168.0459 | 173.9275 | 180.015 | 186.3155 | 192.8365 | 199.5858 | 206.5713 | 213.8013 | 221.2843 | 229.0293 | 237.0453 | 245.3419 | 253.9289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4212 | 108.076 | 113.2086 | 116.6719 | 120.7554 | 124.9819 | 129.3562 | 133.8837 | 138.5696 | 143.4196 | 148.4392 | 153.6346 | 159.0118 | 164.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T_H | Technician_High | Labor |  | 0 | 0 | 172.684 | 183.774 | 189.471 | 195.3446 | 201.4003 | 207.6437 | 214.0807 | 220.7172 | 227.5594 | 234.6138 | 241.8868 | 249.3853 | 257.1162 | 265.0868 | 273.3045 | 0 | 0 | 0 | 0 | 0 | 191.2119 | 199.455 | 205.6381 | 212.0129 | 218.5853 | 225.3614 | 232.3476 | 239.5504 | 246.9764 | 254.6327 | 262.5263 | 270.6646 | 279.0552 | 287.706 | 296.6248 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 114.6906 | 118.246 | 121.9117 | 125.6909 | 129.5873 | 133.6046 | 137.7463 | 142.0164 | 146.4189 | 150.9579 | 155.6376 | 160.4624 | 165.4367 | 170.5653 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 105.2382 | 108.5006 | 111.8641 | 115.3319 | 118.9072 | 122.5933 | 126.3937 | 130.3119 | 134.3516 | 138.5165 | 142.8105 | 147.2376 | 151.802 | 156.5078 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 118.6801 | 122.8339 | 127.1331 | 131.5828 | 136.1882 | 140.9547 | 145.8882 | 150.9942 | 156.279 | 161.7488 | 167.41 | 173.2694 | 179.3338 | 185.6105 | 0 | 0 | 0 | 0 | 0 | 0 | 185.4936 | 191.9859 | 198.7054 | 205.6601 | 212.8582 | 220.3082 | 228.019 | 235.9997 | 244.2597 | 252.8087 | 261.657 | 270.815 | 280.2936 | 290.1038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.2972 | 123.4726 | 129.3364 | 133.2931 | 137.9584 | 142.7869 | 147.7844 | 152.9569 | 158.3104 | 163.8513 | 169.5861 | 175.5216 | 181.6648 | 188.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FT_L | Facility Tech_Low | Labor |  | 0 | 0 | 102.9641 | 109.5765 | 112.9734 | 116.4756 | 120.0863 | 123.809 | 127.6471 | 131.6042 | 135.6839 | 139.8901 | 144.2267 | 148.6977 | 153.3073 | 158.0599 | 162.9597 | 0 | 0 | 0 | 0 | 0 | 114.0114 | 118.9264 | 122.6131 | 126.4141 | 130.333 | 134.3733 | 138.5389 | 142.8336 | 147.2614 | 151.8265 | 156.5331 | 161.3857 | 166.3886 | 171.5467 | 176.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 68.3851 | 70.505 | 72.6907 | 74.9441 | 77.2674 | 79.6626 | 82.1322 | 84.6783 | 87.3033 | 90.0097 | 92.8 | 95.6768 | 98.6428 | 101.7007 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 62.749 | 64.6942 | 66.6997 | 68.7674 | 70.8992 | 73.0971 | 75.3631 | 77.6994 | 80.108 | 82.5914 | 85.1517 | 87.7914 | 90.513 | 93.3189 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5186 | 72.9868 | 75.5413 | 78.1853 | 80.9217 | 83.754 | 86.6854 | 89.7194 | 92.8596 | 96.1097 | 99.4735 | 102.9551 | 106.5585 | 110.288 | 0 | 0 | 0 | 0 | 0 | 0 | 110.2186 | 114.0762 | 118.0689 | 122.2013 | 126.4784 | 130.9051 | 135.4868 | 140.2288 | 145.1368 | 150.2166 | 155.4742 | 160.9158 | 166.5479 | 172.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8853 | 73.3663 | 76.8505 | 79.2015 | 81.9736 | 84.8427 | 87.8122 | 90.8856 | 94.0666 | 97.3589 | 100.7665 | 104.2933 | 107.9436 | 111.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FT_M | Facility Tech_Med | Labor |  | 0 | 0 | 150.9888 | 160.6855 | 165.6667 | 170.8024 | 176.0973 | 181.5563 | 187.1845 | 192.9872 | 198.9699 | 205.1379 | 211.4972 | 218.0536 | 224.8133 | 231.7825 | 238.9677 | 0 | 0 | 0 | 0 | 0 | 167.1889 | 174.3963 | 179.8026 | 185.3765 | 191.1232 | 197.048 | 203.1565 | 209.4543 | 215.9474 | 222.6418 | 229.5437 | 236.6595 | 243.996 | 251.5598 | 259.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 100.2814 | 103.3901 | 106.5952 | 109.8997 | 113.3066 | 116.8191 | 120.4404 | 124.1741 | 128.0235 | 131.9922 | 136.084 | 140.3026 | 144.652 | 149.1362 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 92.0165 | 94.869 | 97.81 | 100.8421 | 103.9682 | 107.1912 | 110.5141 | 113.9401 | 117.4722 | 121.1138 | 124.8684 | 128.7393 | 132.7302 | 136.8449 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8811 | 107.5169 | 111.28 | 115.1748 | 119.206 | 123.3782 | 127.6964 | 132.1658 | 136.7916 | 141.5793 | 146.5346 | 151.6633 | 156.9715 | 162.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 162.3632 | 168.0459 | 173.9275 | 180.015 | 186.3155 | 192.8365 | 199.5858 | 206.5713 | 213.8013 | 221.2843 | 229.0293 | 237.0453 | 245.3419 | 253.9289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4212 | 108.076 | 113.2086 | 116.6719 | 120.7554 | 124.9819 | 129.3562 | 133.8837 | 138.5696 | 143.4196 | 148.4392 | 153.6346 | 159.0118 | 164.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FT_H | Facility Tech_High | Labor |  | 0 | 0 | 172.684 | 183.774 | 189.471 | 195.3446 | 201.4003 | 207.6437 | 214.0807 | 220.7172 | 227.5594 | 234.6138 | 241.8868 | 249.3853 | 257.1162 | 265.0868 | 273.3045 | 0 | 0 | 0 | 0 | 0 | 191.2119 | 199.455 | 205.6381 | 212.0129 | 218.5853 | 225.3614 | 232.3476 | 239.5504 | 246.9764 | 254.6327 | 262.5263 | 270.6646 | 279.0552 | 287.706 | 296.6248 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 114.6906 | 118.246 | 121.9117 | 125.6909 | 129.5873 | 133.6046 | 137.7463 | 142.0164 | 146.4189 | 150.9579 | 155.6376 | 160.4624 | 165.4367 | 170.5653 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 105.2382 | 108.5006 | 111.8641 | 115.3319 | 118.9072 | 122.5933 | 126.3937 | 130.3119 | 134.3516 | 138.5165 | 142.8105 | 147.2376 | 151.802 | 156.5078 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 118.6801 | 122.8339 | 127.1331 | 131.5828 | 136.1882 | 140.9547 | 145.8882 | 150.9942 | 156.279 | 161.7488 | 167.41 | 173.2694 | 179.3338 | 185.6105 | 0 | 0 | 0 | 0 | 0 | 0 | 185.4936 | 191.9859 | 198.7054 | 205.6601 | 212.8582 | 220.3082 | 228.019 | 235.9997 | 244.2597 | 252.8087 | 261.657 | 270.815 | 280.2936 | 290.1038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.2972 | 123.4726 | 129.3364 | 133.2931 | 137.9584 | 142.7869 | 147.7844 | 152.9569 | 158.3104 | 163.8513 | 169.5861 | 175.5216 | 181.6648 | 188.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EE_L | Electrical Engineer_Low | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EE_M | Electrical Engineer_Med | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EE_H | Electrical Engineer_High | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME_L | Mechanical Engineer_Low | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME_M | Mechanical Engineer_Med | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME_H | Mechanical Engineer_High | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SE_L | Survey Engineer_Low | Labor |  | 0 | 0 | 137.1672 | 145.9762 | 150.5015 | 155.167 | 159.9772 | 164.9365 | 170.0495 | 175.3211 | 180.756 | 186.3595 | 192.1366 | 198.0929 | 204.2337 | 210.565 | 217.0925 | 0 | 0 | 0 | 0 | 0 | 151.8843 | 158.432 | 163.3434 | 168.407 | 173.6276 | 179.0101 | 184.5594 | 190.2807 | 196.1794 | 202.261 | 208.5311 | 214.9956 | 221.6604 | 228.5319 | 235.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 91.1016 | 93.9257 | 96.8374 | 99.8394 | 102.9344 | 106.1254 | 109.4153 | 112.8071 | 116.3042 | 119.9096 | 123.6268 | 127.4592 | 131.4104 | 135.4842 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 83.5933 | 86.1847 | 88.8564 | 91.6109 | 94.4509 | 97.3789 | 100.3976 | 103.5099 | 106.7187 | 110.027 | 113.4379 | 116.9544 | 120.58 | 124.318 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 94.9162 | 98.2383 | 101.6766 | 105.2353 | 108.9185 | 112.7307 | 116.6763 | 120.7599 | 124.9865 | 129.3611 | 133.8887 | 138.5748 | 143.4249 | 148.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3513 | 153.5436 | 158.9176 | 164.4798 | 170.2366 | 176.1948 | 182.3617 | 188.7443 | 195.3504 | 202.1876 | 209.2642 | 216.5884 | 224.169 | 232.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.4097 | 98.7491 | 103.4388 | 106.6032 | 110.3343 | 114.196 | 118.1929 | 122.3296 | 126.6111 | 131.0425 | 135.629 | 140.376 | 145.2892 | 150.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SE_M | Survey Engineer_Med | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SE_H | Survey Engineer_High | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E_L | Engineer_Low | Labor |  | 0 | 0 | 137.1672 | 145.9762 | 150.5015 | 155.167 | 159.9772 | 164.9365 | 170.0495 | 175.3211 | 180.756 | 186.3595 | 192.1366 | 198.0929 | 204.2337 | 210.565 | 217.0925 | 0 | 0 | 0 | 0 | 0 | 151.8843 | 158.432 | 163.3434 | 168.407 | 173.6276 | 179.0101 | 184.5594 | 190.2807 | 196.1794 | 202.261 | 208.5311 | 214.9956 | 221.6604 | 228.5319 | 235.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 91.1016 | 93.9257 | 96.8374 | 99.8394 | 102.9344 | 106.1254 | 109.4153 | 112.8071 | 116.3042 | 119.9096 | 123.6268 | 127.4592 | 131.4104 | 135.4842 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 83.5933 | 86.1847 | 88.8564 | 91.6109 | 94.4509 | 97.3789 | 100.3976 | 103.5099 | 106.7187 | 110.027 | 113.4379 | 116.9544 | 120.58 | 124.318 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 94.9162 | 98.2383 | 101.6766 | 105.2353 | 108.9185 | 112.7307 | 116.6763 | 120.7599 | 124.9865 | 129.3611 | 133.8887 | 138.5748 | 143.4249 | 148.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3513 | 153.5436 | 158.9176 | 164.4798 | 170.2366 | 176.1948 | 182.3617 | 188.7443 | 195.3504 | 202.1876 | 209.2642 | 216.5884 | 224.169 | 232.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.4097 | 98.7491 | 103.4388 | 106.6032 | 110.3343 | 114.196 | 118.1929 | 122.3296 | 126.6111 | 131.0425 | 135.629 | 140.376 | 145.2892 | 150.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E_M | Engineer_Med | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E_H | Engineer_High | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE_L | Facility Engineer_Low | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE_M | Facility Engineer_Med | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE_H | Facility Engineer_High | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIENT_L | Scientist_Low | Labor |  | 0 | 0 | 164.4796 | 175.0427 | 180.4691 | 186.0636 | 191.8316 | 197.7784 | 203.9095 | 210.2307 | 216.7478 | 223.467 | 230.3945 | 237.5367 | 244.9004 | 252.4923 | 260.3195 | 0 | 0 | 0 | 0 | 0 | 182.1272 | 189.9786 | 195.868 | 201.9399 | 208.2 | 214.6542 | 221.3085 | 228.1691 | 235.2423 | 242.5348 | 250.0534 | 257.8051 | 265.797 | 274.0367 | 282.5319 | 0 | 0 | 0 | 0 | 0 | 0 | 112.4112 | 115.7835 | 119.257 | 122.8347 | 126.5197 | 130.3153 | 134.2248 | 138.2515 | 142.3991 | 146.6711 | 151.0712 | 155.6033 | 160.2714 | 165.0796 | 0 | 0 | 0 | 0 | 0 | 0 | 112.4112 | 115.7835 | 119.257 | 122.8347 | 126.5197 | 130.3153 | 134.2248 | 138.2515 | 142.3991 | 146.6711 | 151.0712 | 155.6033 | 160.2714 | 165.0796 | 0 | 0 | 0 | 0 | 0 | 109.1624 | 110.4829 | 113.9079 | 117.439 | 121.0797 | 124.8331 | 128.703 | 132.6927 | 136.8062 | 141.0472 | 145.4197 | 149.9277 | 154.5754 | 159.3673 | 164.3077 | 0 | 0 | 0 | 0 | 0 | 107.9359 | 109.2415 | 112.628 | 116.1195 | 119.7192 | 123.4305 | 127.2569 | 131.2018 | 135.2691 | 139.4624 | 143.7857 | 148.2431 | 152.8386 | 157.5766 | 162.4615 | 0 | 0 | 0 | 0 | 0 | 107.9359 | 100.2382 | 103.3456 | 106.5493 | 109.8523 | 113.2578 | 116.7687 | 120.3886 | 124.1206 | 127.9684 | 131.9354 | 136.0254 | 140.2422 | 144.5897 | 149.072 | 0 | 0 | 0 | 0 | 0 | 109.1624 | 110.4829 | 113.9079 | 117.439 | 121.0797 | 124.8331 | 128.703 | 132.6927 | 136.8062 | 141.0472 | 145.4197 | 149.9277 | 154.5754 | 159.3673 | 164.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 112.9866 | 116.9411 | 121.034 | 125.2702 | 129.6547 | 134.1926 | 138.8893 | 143.7505 | 148.7817 | 153.9891 | 159.3787 | 164.957 | 170.7304 | 176.706 | 0 | 0 | 0 | 0 | 0 | 0 | 176.5947 | 182.7756 | 189.1727 | 195.7938 | 202.6465 | 209.7392 | 217.08 | 224.6778 | 232.5416 | 240.6805 | 249.1043 | 257.823 | 266.8468 | 276.1864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.574 | 117.5491 | 123.1317 | 126.8985 | 131.34 | 135.9369 | 140.6946 | 145.619 | 150.7156 | 155.9907 | 161.4503 | 167.1011 | 172.9496 | 179.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIENT_M | Scientist_Med | Labor |  | 0 | 0 | 203.582 | 216.6563 | 223.3726 | 230.2972 | 237.4364 | 244.7969 | 252.3856 | 260.2096 | 268.2761 | 276.5926 | 285.167 | 294.0072 | 303.1214 | 312.5182 | 322.2062 | 0 | 0 | 0 | 0 | 0 | 225.425 | 235.143 | 242.4324 | 249.9478 | 257.6962 | 265.6848 | 273.921 | 282.4125 | 291.1673 | 300.1935 | 309.4995 | 319.094 | 328.9859 | 339.1845 | 349.6992 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6838 | 142.8443 | 147.1297 | 151.5435 | 156.0898 | 160.7725 | 165.5957 | 170.5636 | 175.6805 | 180.9509 | 186.3794 | 191.9708 | 197.7299 | 203.6618 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6838 | 142.8443 | 147.1297 | 151.5435 | 156.0898 | 160.7725 | 165.5957 | 170.5636 | 175.6805 | 180.9509 | 186.3794 | 191.9708 | 197.7299 | 203.6618 | 0 | 0 | 0 | 0 | 0 | 135.114 | 136.7484 | 140.9876 | 145.3582 | 149.8644 | 154.5102 | 159.3 | 164.2383 | 169.3296 | 174.5789 | 179.9908 | 185.5705 | 191.3232 | 197.2542 | 203.3691 | 0 | 0 | 0 | 0 | 0 | 133.5958 | 135.2119 | 139.4035 | 143.725 | 148.1805 | 152.7741 | 157.5101 | 162.3929 | 167.4271 | 172.6173 | 177.9684 | 183.4855 | 189.1735 | 195.0379 | 201.0841 | 0 | 0 | 0 | 0 | 0 | 133.5958 | 124.0682 | 127.9143 | 131.8797 | 135.9679 | 140.1829 | 144.5286 | 149.009 | 153.6283 | 158.3907 | 163.3009 | 168.3632 | 173.5824 | 178.9635 | 184.5114 | 0 | 0 | 0 | 0 | 0 | 135.114 | 136.7484 | 140.9876 | 145.3582 | 149.8644 | 154.5102 | 159.3 | 164.2383 | 169.3296 | 174.5789 | 179.9908 | 185.5705 | 191.3232 | 197.2542 | 203.3691 | 0 | 0 | 0 | 0 | 0 | 0 | 140.6772 | 145.6009 | 150.697 | 155.9714 | 161.4304 | 167.0804 | 172.9282 | 178.9807 | 185.2451 | 191.7286 | 198.4391 | 205.3845 | 212.573 | 220.013 | 0 | 0 | 0 | 0 | 0 | 0 | 219.8745 | 227.5701 | 235.535 | 243.7788 | 252.311 | 261.1419 | 270.2819 | 279.7417 | 289.5327 | 299.6663 | 310.1547 | 321.0101 | 332.2454 | 343.874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.4087 | 146.358 | 153.3087 | 157.9987 | 163.5287 | 169.2522 | 175.176 | 181.3072 | 187.6529 | 194.2208 | 201.0185 | 208.0541 | 215.336 | 222.8728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIENT_H | Scientist_High | Labor |  | 0 | 0 | 281.8477 | 299.9484 | 309.2468 | 318.8334 | 328.7172 | 338.9075 | 349.4136 | 360.2454 | 371.413 | 382.9269 | 394.7976 | 407.0363 | 419.6544 | 432.6637 | 446.0763 | 0 | 0 | 0 | 0 | 0 | 312.0881 | 325.5421 | 335.6339 | 346.0386 | 356.7658 | 367.8255 | 379.2281 | 390.9842 | 403.1047 | 415.6009 | 428.4846 | 441.7676 | 455.4624 | 469.5817 | 484.1387 | 0 | 0 | 0 | 0 | 0 | 0 | 191.5356 | 197.2817 | 203.2002 | 209.2962 | 215.5751 | 222.0423 | 228.7036 | 235.5647 | 242.6316 | 249.9106 | 257.4079 | 265.1301 | 273.084 | 281.2765 | 0 | 0 | 0 | 0 | 0 | 0 | 191.5356 | 197.2817 | 203.2002 | 209.2962 | 215.5751 | 222.0423 | 228.7036 | 235.5647 | 242.6316 | 249.9106 | 257.4079 | 265.1301 | 273.084 | 281.2765 | 0 | 0 | 0 | 0 | 0 | 187.0577 | 189.3205 | 195.1894 | 201.2403 | 207.4787 | 213.9106 | 220.5418 | 227.3786 | 234.4273 | 241.6946 | 249.1871 | 256.9119 | 264.8762 | 273.0873 | 281.553 | 0 | 0 | 0 | 0 | 0 | 184.9559 | 187.1933 | 192.9963 | 198.9792 | 205.1475 | 211.5071 | 218.0638 | 224.8238 | 231.7933 | 238.9789 | 246.3873 | 254.0253 | 261.9 | 270.0189 | 278.3895 | 0 | 0 | 0 | 0 | 0 | 184.9559 | 171.7654 | 177.0901 | 182.5799 | 188.2399 | 194.0753 | 200.0917 | 206.2945 | 212.6897 | 219.283 | 226.0808 | 233.0893 | 240.3151 | 247.7648 | 255.4456 | 0 | 0 | 0 | 0 | 0 | 187.0577 | 189.3205 | 195.1894 | 201.2403 | 207.4787 | 213.9106 | 220.5418 | 227.3786 | 234.4273 | 241.6946 | 249.1871 | 256.9119 | 264.8762 | 273.0873 | 281.553 | 0 | 0 | 0 | 0 | 0 | 0 | 195.0773 | 201.905 | 208.9717 | 216.2857 | 223.8557 | 231.6907 | 239.7999 | 248.1928 | 256.8796 | 265.8704 | 275.1758 | 284.807 | 294.7752 | 305.0924 | 0 | 0 | 0 | 0 | 0 | 0 | 304.9003 | 315.5718 | 326.6168 | 338.0484 | 349.8801 | 362.1259 | 374.8003 | 387.9183 | 401.4954 | 415.5478 | 430.0919 | 445.1452 | 460.7252 | 476.8506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.0916 | 202.9548 | 212.5934 | 219.0971 | 226.7655 | 234.7023 | 242.9168 | 251.4189 | 260.2186 | 269.3262 | 278.7527 | 288.509 | 298.6068 | 309.0581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PHYSIC_L | Physicist_Low | Labor |  | 0 | 0 | 203.582 | 216.6563 | 223.3726 | 230.2972 | 237.4364 | 244.7969 | 252.3856 | 260.2096 | 268.2761 | 276.5926 | 285.167 | 294.0072 | 303.1214 | 312.5182 | 322.2062 | 0 | 0 | 0 | 0 | 0 | 225.425 | 235.143 | 242.4324 | 249.9478 | 257.6962 | 265.6848 | 273.921 | 282.4125 | 291.1673 | 300.1935 | 309.4995 | 319.094 | 328.9859 | 339.1845 | 349.6992 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6838 | 142.8443 | 147.1297 | 151.5435 | 156.0898 | 160.7725 | 165.5957 | 170.5636 | 175.6805 | 180.9509 | 186.3794 | 191.9708 | 197.7299 | 203.6618 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6838 | 142.8443 | 147.1297 | 151.5435 | 156.0898 | 160.7725 | 165.5957 | 170.5636 | 175.6805 | 180.9509 | 186.3794 | 191.9708 | 197.7299 | 203.6618 | 0 | 0 | 0 | 0 | 0 | 135.114 | 136.7484 | 140.9876 | 145.3582 | 149.8644 | 154.5102 | 159.3 | 164.2383 | 169.3296 | 174.5789 | 179.9908 | 185.5705 | 191.3232 | 197.2542 | 203.3691 | 0 | 0 | 0 | 0 | 0 | 133.5958 | 135.2119 | 139.4035 | 143.725 | 148.1805 | 152.7741 | 157.5101 | 162.3929 | 167.4271 | 172.6173 | 177.9684 | 183.4855 | 189.1735 | 195.0379 | 201.0841 | 0 | 0 | 0 | 0 | 0 | 133.5958 | 124.0682 | 127.9143 | 131.8797 | 135.9679 | 140.1829 | 144.5286 | 149.009 | 153.6283 | 158.3907 | 163.3009 | 168.3632 | 173.5824 | 178.9635 | 184.5114 | 0 | 0 | 0 | 0 | 0 | 135.114 | 136.7484 | 140.9876 | 145.3582 | 149.8644 | 154.5102 | 159.3 | 164.2383 | 169.3296 | 174.5789 | 179.9908 | 185.5705 | 191.3232 | 197.2542 | 203.3691 | 0 | 0 | 0 | 0 | 0 | 0 | 140.6772 | 145.6009 | 150.697 | 155.9714 | 161.4304 | 167.0804 | 172.9282 | 178.9807 | 185.2451 | 191.7286 | 198.4391 | 205.3845 | 212.573 | 220.013 | 0 | 0 | 0 | 0 | 0 | 0 | 219.8745 | 227.5701 | 235.535 | 243.7788 | 252.311 | 261.1419 | 270.2819 | 279.7417 | 289.5327 | 299.6663 | 310.1547 | 321.0101 | 332.2454 | 343.874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.4087 | 146.358 | 153.3087 | 157.9987 | 163.5287 | 169.2522 | 175.176 | 181.3072 | 187.6529 | 194.2208 | 201.0185 | 208.0541 | 215.336 | 222.8728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PHYSIC_M | Physicist_Med | Labor |  | 0 | 0 | 235.417 | 250.5358 | 258.3024 | 266.3098 | 274.5654 | 283.077 | 291.8523 | 300.8998 | 310.2277 | 319.8447 | 329.7599 | 339.9825 | 350.5219 | 361.3881 | 372.5911 | 0 | 0 | 0 | 0 | 0 | 260.6757 | 271.9134 | 280.3427 | 289.0333 | 297.9933 | 307.2311 | 316.7553 | 326.5747 | 336.6985 | 347.1362 | 357.8974 | 368.9922 | 380.431 | 392.2243 | 404.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 159.5315 | 164.3175 | 169.247 | 174.3244 | 179.5542 | 184.9408 | 190.489 | 196.2037 | 202.0898 | 208.1525 | 214.397 | 220.829 | 227.4538 | 234.2774 | 0 | 0 | 0 | 0 | 0 | 0 | 159.5315 | 164.3175 | 169.247 | 174.3244 | 179.5542 | 184.9408 | 190.489 | 196.2037 | 202.0898 | 208.1525 | 214.397 | 220.829 | 227.4538 | 234.2774 | 0 | 0 | 0 | 0 | 0 | 156.2424 | 158.1324 | 163.0345 | 168.0886 | 173.2993 | 178.6716 | 184.2104 | 189.921 | 195.8085 | 201.8786 | 208.1368 | 214.5891 | 221.2413 | 228.0998 | 235.1709 | 0 | 0 | 0 | 0 | 0 | 154.4869 | 156.3557 | 161.2027 | 166.2 | 171.3522 | 176.6641 | 182.1407 | 187.787 | 193.6084 | 199.6103 | 205.7982 | 212.178 | 218.7555 | 225.5369 | 232.5285 | 0 | 0 | 0 | 0 | 0 | 154.4869 | 143.4693 | 147.9169 | 152.5023 | 157.2299 | 162.104 | 167.1292 | 172.3102 | 177.6518 | 183.159 | 188.837 | 194.6909 | 200.7263 | 206.9489 | 213.3643 | 0 | 0 | 0 | 0 | 0 | 156.2424 | 158.1324 | 163.0345 | 168.0886 | 173.2993 | 178.6716 | 184.2104 | 189.921 | 195.8085 | 201.8786 | 208.1368 | 214.5891 | 221.2413 | 228.0998 | 235.1709 | 0 | 0 | 0 | 0 | 0 | 0 | 161.823 | 167.4868 | 173.3488 | 179.4161 | 185.6956 | 192.195 | 198.9218 | 205.8841 | 213.09 | 220.5481 | 228.2673 | 236.2567 | 244.5257 | 253.0841 | 0 | 0 | 0 | 0 | 0 | 0 | 252.9247 | 261.7771 | 270.9393 | 280.4221 | 290.2369 | 300.3952 | 310.909 | 321.7909 | 333.0535 | 344.7104 | 356.7753 | 369.2624 | 382.1866 | 395.5631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162.6644 | 168.3576 | 176.3532 | 181.7482 | 188.1093 | 194.6932 | 201.5074 | 208.5602 | 215.8598 | 223.4149 | 231.2344 | 239.3276 | 247.7041 | 256.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PHYSIC_H | Physicist_High | Labor |  | 0 | 0 | 281.8477 | 299.9484 | 309.2468 | 318.8334 | 328.7172 | 338.9075 | 349.4136 | 360.2454 | 371.413 | 382.9269 | 394.7976 | 407.0363 | 419.6544 | 432.6637 | 446.0763 | 0 | 0 | 0 | 0 | 0 | 312.0881 | 325.5421 | 335.6339 | 346.0386 | 356.7658 | 367.8255 | 379.2281 | 390.9842 | 403.1047 | 415.6009 | 428.4846 | 441.7676 | 455.4624 | 469.5817 | 484.1387 | 0 | 0 | 0 | 0 | 0 | 0 | 191.5356 | 197.2817 | 203.2002 | 209.2962 | 215.5751 | 222.0423 | 228.7036 | 235.5647 | 242.6316 | 249.9106 | 257.4079 | 265.1301 | 273.084 | 281.2765 | 0 | 0 | 0 | 0 | 0 | 0 | 191.5356 | 197.2817 | 203.2002 | 209.2962 | 215.5751 | 222.0423 | 228.7036 | 235.5647 | 242.6316 | 249.9106 | 257.4079 | 265.1301 | 273.084 | 281.2765 | 0 | 0 | 0 | 0 | 0 | 187.0577 | 189.3205 | 195.1894 | 201.2403 | 207.4787 | 213.9106 | 220.5418 | 227.3786 | 234.4273 | 241.6946 | 249.1871 | 256.9119 | 264.8762 | 273.0873 | 281.553 | 0 | 0 | 0 | 0 | 0 | 184.9559 | 187.1933 | 192.9963 | 198.9792 | 205.1475 | 211.5071 | 218.0638 | 224.8238 | 231.7933 | 238.9789 | 246.3873 | 254.0253 | 261.9 | 270.0189 | 278.3895 | 0 | 0 | 0 | 0 | 0 | 184.9559 | 171.7654 | 177.0901 | 182.5799 | 188.2399 | 194.0753 | 200.0917 | 206.2945 | 212.6897 | 219.283 | 226.0808 | 233.0893 | 240.3151 | 247.7648 | 255.4456 | 0 | 0 | 0 | 0 | 0 | 187.0577 | 189.3205 | 195.1894 | 201.2403 | 207.4787 | 213.9106 | 220.5418 | 227.3786 | 234.4273 | 241.6946 | 249.1871 | 256.9119 | 264.8762 | 273.0873 | 281.553 | 0 | 0 | 0 | 0 | 0 | 0 | 195.0773 | 201.905 | 208.9717 | 216.2857 | 223.8557 | 231.6907 | 239.7999 | 248.1928 | 256.8796 | 265.8704 | 275.1758 | 284.807 | 294.7752 | 305.0924 | 0 | 0 | 0 | 0 | 0 | 0 | 304.9003 | 315.5718 | 326.6168 | 338.0484 | 349.8801 | 362.1259 | 374.8003 | 387.9183 | 401.4954 | 415.5478 | 430.0919 | 445.1452 | 460.7252 | 476.8506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.0916 | 202.9548 | 212.5934 | 219.0971 | 226.7655 | 234.7023 | 242.9168 | 251.4189 | 260.2186 | 269.3262 | 278.7527 | 288.509 | 298.6068 | 309.0581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PHYMGR_H | Physicist Manager_High | Labor |  | 0 | 0 | 344.3618 | 366.4771 | 377.8379 | 389.5509 | 401.627 | 414.0774 | 426.9138 | 440.1481 | 453.7927 | 467.8603 | 482.364 | 497.3173 | 512.7341 | 528.6288 | 545.0163 | 0 | 0 | 0 | 0 | 0 | 381.3095 | 397.7476 | 410.0778 | 422.7902 | 435.8967 | 449.4095 | 463.3412 | 477.7048 | 492.5136 | 507.7815 | 523.5227 | 539.752 | 556.4843 | 573.7353 | 591.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 237.4344 | 244.5574 | 251.8941 | 259.4509 | 267.2345 | 275.2515 | 283.509 | 292.0143 | 300.7747 | 309.798 | 319.0919 | 328.6647 | 338.5246 | 348.6804 | 0 | 0 | 0 | 0 | 0 | 0 | 237.4344 | 244.5574 | 251.8941 | 259.4509 | 267.2345 | 275.2515 | 283.509 | 292.0143 | 300.7747 | 309.798 | 319.0919 | 328.6647 | 338.5246 | 348.6804 | 0 | 0 | 0 | 0 | 0 | 228.5472 | 231.3119 | 238.4826 | 245.8755 | 253.4977 | 261.3561 | 269.4581 | 277.8113 | 286.4235 | 295.3026 | 304.457 | 313.8952 | 323.6259 | 333.6583 | 344.0017 | 0 | 0 | 0 | 0 | 0 | 225.9793 | 228.7129 | 235.803 | 243.1129 | 250.6494 | 258.4195 | 266.4305 | 274.6899 | 283.2052 | 291.9846 | 301.0361 | 310.3682 | 319.9897 | 329.9093 | 340.1365 | 0 | 0 | 0 | 0 | 0 | 225.9793 | 209.8631 | 216.3689 | 223.0763 | 229.9917 | 237.1214 | 244.4722 | 252.0508 | 259.8644 | 267.9202 | 276.2257 | 284.7887 | 293.6171 | 302.7193 | 312.1036 | 0 | 0 | 0 | 0 | 0 | 228.5472 | 231.3119 | 238.4826 | 245.8755 | 253.4977 | 261.3561 | 269.4581 | 277.8113 | 286.4235 | 295.3026 | 304.457 | 313.8952 | 323.6259 | 333.6583 | 344.0017 | 0 | 0 | 0 | 0 | 0 | 0 | 246.7531 | 255.3894 | 264.328 | 273.5795 | 283.1548 | 293.0652 | 303.3225 | 313.9388 | 324.9266 | 336.2991 | 348.0695 | 360.252 | 372.8608 | 385.9109 | 0 | 0 | 0 | 0 | 0 | 0 | 385.6679 | 399.1663 | 413.1371 | 427.5969 | 442.5628 | 458.0525 | 474.0844 | 490.6773 | 507.851 | 525.6258 | 544.0227 | 563.0635 | 582.7707 | 603.1677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.036 | 256.7173 | 268.9091 | 277.1356 | 286.8353 | 296.8746 | 307.2652 | 318.0195 | 329.1501 | 340.6704 | 352.5939 | 364.9346 | 377.7073 | 390.9271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
POSTDocBNL | Post Doc (BNL) | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 63.2389; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 65.4523; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 67.7431; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 70.1141; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 72.5681; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 75.108; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 77.7368; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 80.4576; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 83.2736; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 86.1882; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 89.2048; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 92.3269; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 95.5584; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 98.9029; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 98.8407; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 102.3001; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 105.8806; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 109.5864; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 113.4219; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 117.3917; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 121.5004; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 125.7529; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 130.1543; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 134.7097; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 139.4245; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 144.3044; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 149.355; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 154.5824; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 63.5677; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 65.7926; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 68.9172; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 71.0255; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 73.5114; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 76.0843; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 78.7473; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 81.5034; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 84.356; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 87.3085; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 90.3643; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 93.527; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 96.8005; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 100.1885
RASCIEN_L | Research Associate_Low | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 57.4862; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 59.4982; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 61.5806; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 63.7359; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 65.9667; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 68.2755; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 70.6652; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 73.1385; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 75.6983; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 78.3478; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 81.0899; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 83.9281; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 86.8656; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 89.9058; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 89.8492; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 92.994; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 96.2487; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 99.6175; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 103.1041; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 106.7127; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 110.4477; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 114.3133; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 118.3143; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 122.4553; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 126.7412; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 131.1772; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 135.7684; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 140.5203; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 57.7851; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 59.8075; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 62.6479; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 64.5644; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 66.8242; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 69.163; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 71.5837; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 74.0891; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 76.6823; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 79.3661; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 82.144; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 85.019; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 87.9947; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 91.0745
RASCIEN_M | Research Associate_Med | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 63.2389; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 65.4523; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 67.7431; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 70.1141; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 72.5681; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 75.108; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 77.7368; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 80.4576; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 83.2736; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 86.1882; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 89.2048; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 92.3269; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 95.5584; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 98.9029; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 98.8407; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 102.3001; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 105.8806; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 109.5864; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 113.4219; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 117.3917; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 121.5004; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 125.7529; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 130.1543; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 134.7097; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 139.4245; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 144.3044; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 149.355; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 154.5824; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 63.5677; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 65.7926; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 68.9172; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 71.0255; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 73.5114; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 76.0843; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 78.7473; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 81.5034; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 84.356; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 87.3085; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 90.3643; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 93.527; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 96.8005; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 100.1885
RASCIEN_H | Research Associate_High | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 80.9292; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 83.7617; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 86.6933; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 89.7276; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 92.8681; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 96.1184; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 99.4826; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 102.9645; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 106.5682; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 110.2981; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 114.1586; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 118.1541; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 122.2895; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 126.5696; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 126.4899; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 130.9171; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 135.4992; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 140.2417; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 145.1501; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 150.2304; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 155.4884; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 160.9305; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 166.5631; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 172.3928; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 178.4265; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 184.6715; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 191.135; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 197.8247; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 81.3499; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 84.1972; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 88.1958; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 90.8939; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 94.0752; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 97.3678; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 100.7757; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 104.3028; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 107.9534; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 111.7318; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 115.6424; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 119.6899; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 123.8791; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 128.2148
PHYAS_L | Physics Associate_Low | Labor |  | 0 | 0 | 95.8681 | 102.0249 | 105.1877 | 108.4485 | 111.8104 | 115.2765 | 118.8501 | 122.5345 | 126.333 | 130.2493 | 134.2871 | 138.45 | 142.7419 | 147.1669 | 151.7291 | 0 | 0 | 0 | 0 | 0 | 106.1541 | 110.7304 | 114.1631 | 117.7021 | 121.3509 | 125.1128 | 128.9912 | 132.99 | 137.1127 | 141.3632 | 145.7454 | 150.2635 | 154.9217 | 159.7243 | 164.6757 | 0 | 0 | 0 | 0 | 0 | 0 | 64.5482 | 66.4847 | 68.4792 | 70.5336 | 72.6496 | 74.8291 | 77.074 | 79.3862 | 81.7678 | 84.2208 | 86.7474 | 89.3498 | 92.0303 | 94.7912 | 0 | 0 | 0 | 0 | 0 | 0 | 64.5482 | 66.4847 | 68.4792 | 70.5336 | 72.6496 | 74.8291 | 77.074 | 79.3862 | 81.7678 | 84.2208 | 86.7474 | 89.3498 | 92.0303 | 94.7912 | 0 | 0 | 0 | 0 | 0 | 63.6261 | 64.3958 | 66.392 | 68.4502 | 70.5721 | 72.7599 | 75.0154 | 77.3409 | 79.7385 | 82.2104 | 84.7589 | 87.3864 | 90.0954 | 92.8884 | 95.7679 | 0 | 0 | 0 | 0 | 0 | 62.9112 | 63.6722 | 65.6461 | 67.6811 | 69.7792 | 71.9424 | 74.1726 | 76.4719 | 78.8425 | 81.2867 | 83.8065 | 86.4046 | 89.0831 | 91.8447 | 94.6919 | 0 | 0 | 0 | 0 | 0 | 62.9112 | 58.4246 | 60.2357 | 62.103 | 64.0282 | 66.0131 | 68.0595 | 70.1693 | 72.3446 | 74.5873 | 76.8995 | 79.2834 | 81.7411 | 84.2751 | 86.8877 | 0 | 0 | 0 | 0 | 0 | 63.6261 | 64.3958 | 66.392 | 68.4502 | 70.5721 | 72.7599 | 75.0154 | 77.3409 | 79.7385 | 82.2104 | 84.7589 | 87.3864 | 90.0954 | 92.8884 | 95.7679 | 0 | 0 | 0 | 0 | 0 | 0 | 65.7119 | 68.0118 | 70.3923 | 72.856 | 75.4059 | 78.0451 | 80.7767 | 83.6039 | 86.53 | 89.5586 | 92.6932 | 95.9374 | 99.2952 | 102.7706 | 0 | 0 | 0 | 0 | 0 | 0 | 102.7058 | 106.3005 | 110.0211 | 113.8718 | 117.8573 | 121.9823 | 126.2517 | 130.6705 | 135.244 | 139.9775 | 144.8767 | 149.9474 | 155.1956 | 160.6274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.0536 | 68.3655 | 71.6122 | 73.803 | 76.3861 | 79.0596 | 81.8267 | 84.6906 | 87.6548 | 90.7227 | 93.898 | 97.1844 | 100.5859 | 104.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PHYAS_M | Physics Associate_Med | Labor |  | 0 | 0 | 137.1672 | 145.9762 | 150.5015 | 155.167 | 159.9772 | 164.9365 | 170.0495 | 175.3211 | 180.756 | 186.3595 | 192.1366 | 198.0929 | 204.2337 | 210.565 | 217.0925 | 0 | 0 | 0 | 0 | 0 | 151.8843 | 158.432 | 163.3434 | 168.407 | 173.6276 | 179.0101 | 184.5594 | 190.2807 | 196.1794 | 202.261 | 208.5311 | 214.9956 | 221.6604 | 228.5319 | 235.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 91.1016 | 93.9257 | 96.8374 | 99.8394 | 102.9344 | 106.1254 | 109.4153 | 112.8071 | 116.3042 | 119.9096 | 123.6268 | 127.4592 | 131.4104 | 135.4842 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 83.5933 | 86.1847 | 88.8564 | 91.6109 | 94.4509 | 97.3789 | 100.3976 | 103.5099 | 106.7187 | 110.027 | 113.4379 | 116.9544 | 120.58 | 124.318 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 94.9162 | 98.2383 | 101.6766 | 105.2353 | 108.9185 | 112.7307 | 116.6763 | 120.7599 | 124.9865 | 129.3611 | 133.8887 | 138.5748 | 143.4249 | 148.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3513 | 153.5436 | 158.9176 | 164.4798 | 170.2366 | 176.1948 | 182.3617 | 188.7443 | 195.3504 | 202.1876 | 209.2642 | 216.5884 | 224.169 | 232.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.4097 | 98.7491 | 103.4388 | 106.6032 | 110.3343 | 114.196 | 118.1929 | 122.3296 | 126.6111 | 131.0425 | 135.629 | 140.376 | 145.2892 | 150.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PHYAS_H | Physics Associate_High | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTAC_R | Building Trades Assigned - Carpenters_RC | Labor |  | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 111.2359 | 114.6843 | 118.2395 | 121.9049 | 125.6839 | 129.5802 | 133.5971 | 137.7386 | 142.0085 | 146.4108 | 150.9495 | 155.629 | 160.4535 | 165.4275 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 0 | 117.8113 | 120.1675 | 122.5709 | 125.0223 | 127.5227 | 130.0732 | 132.6746 | 135.3281 | 138.0347 | 140.7954 | 143.6113 | 146.4835 | 149.4132 | 152.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 118.4238 | 120.7923 | 124.6951 | 126.6473 | 129.1803 | 131.7639 | 134.3992 | 137.0872 | 139.8289 | 142.6255 | 145.478 | 148.3876 | 151.3553 | 154.3824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTAE_R | Building Trades Assigned - Electrical_RC | Labor |  | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 111.2359 | 114.6843 | 118.2395 | 121.9049 | 125.6839 | 129.5802 | 133.5971 | 137.7386 | 142.0085 | 146.4108 | 150.9495 | 155.629 | 160.4535 | 165.4275 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 0 | 117.8113 | 120.1675 | 122.5709 | 125.0223 | 127.5227 | 130.0732 | 132.6746 | 135.3281 | 138.0347 | 140.7954 | 143.6113 | 146.4835 | 149.4132 | 152.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 118.4238 | 120.7923 | 124.6951 | 126.6473 | 129.1803 | 131.7639 | 134.3992 | 137.0872 | 139.8289 | 142.6255 | 145.478 | 148.3876 | 151.3553 | 154.3824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTGG_R | Building Trades - General_RC | Labor |  | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 111.2359 | 114.6843 | 118.2395 | 121.9049 | 125.6839 | 129.5802 | 133.5971 | 137.7386 | 142.0085 | 146.4108 | 150.9495 | 155.629 | 160.4535 | 165.4275 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 0 | 117.8113 | 120.1675 | 122.5709 | 125.0223 | 127.5227 | 130.0732 | 132.6746 | 135.3281 | 138.0347 | 140.7954 | 143.6113 | 146.4835 | 149.4132 | 152.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 118.4238 | 120.7923 | 124.6951 | 126.6473 | 129.1803 | 131.7639 | 134.3992 | 137.0872 | 139.8289 | 142.6255 | 145.478 | 148.3876 | 151.3553 | 154.3824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTAP_R | Building Trades Assigned - Plumbers_RC | Labor |  | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 111.2359 | 114.6843 | 118.2395 | 121.9049 | 125.6839 | 129.5802 | 133.5971 | 137.7386 | 142.0085 | 146.4108 | 150.9495 | 155.629 | 160.4535 | 165.4275 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 0 | 117.8113 | 120.1675 | 122.5709 | 125.0223 | 127.5227 | 130.0732 | 132.6746 | 135.3281 | 138.0347 | 140.7954 | 143.6113 | 146.4835 | 149.4132 | 152.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 118.4238 | 120.7923 | 124.6951 | 126.6473 | 129.1803 | 131.7639 | 134.3992 | 137.0872 | 139.8289 | 142.6255 | 145.478 | 148.3876 | 151.3553 | 154.3824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTAR_R | Building Trades Assigned - Riggers_RC | Labor |  | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 131.8874 | 155.1878 | 159.9986 | 164.9586 | 170.0723 | 175.3445 | 180.7802 | 186.3844 | 192.1623 | 198.1194 | 204.2611 | 210.5932 | 217.1215 | 223.8523 | 230.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5821 | 121.1095 | 124.7428 | 128.4851 | 132.3396 | 136.3098 | 140.3991 | 144.6111 | 148.9494 | 153.4179 | 158.0204 | 162.7611 | 167.6439 | 172.6732 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 111.2359 | 114.6843 | 118.2395 | 121.9049 | 125.6839 | 129.5802 | 133.5971 | 137.7386 | 142.0085 | 146.4108 | 150.9495 | 155.629 | 160.4535 | 165.4275 | 0 | 0 | 0 | 0 | 0 | 109.2169 | 121.2271 | 124.9851 | 128.8597 | 132.8543 | 136.9728 | 141.219 | 145.5968 | 150.1103 | 154.7637 | 159.5613 | 164.5077 | 169.6075 | 174.8653 | 180.2861 | 0 | 0 | 0 | 0 | 0 | 0 | 117.8113 | 120.1675 | 122.5709 | 125.0223 | 127.5227 | 130.0732 | 132.6746 | 135.3281 | 138.0347 | 140.7954 | 143.6113 | 146.4835 | 149.4132 | 152.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 147.5702 | 150.5216 | 153.5321 | 156.6027 | 159.7348 | 162.9295 | 166.188 | 169.5118 | 172.902 | 176.3601 | 179.8873 | 183.485 | 187.1547 | 190.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 118.4238 | 120.7923 | 124.6951 | 126.6473 | 129.1803 | 131.7639 | 134.3992 | 137.0872 | 139.8289 | 142.6255 | 145.478 | 148.3876 | 151.3553 | 154.3824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTUC_R | Building Trades Unassigned - Carpenters_RC | Labor |  | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 131.5396 | 135.6173 | 139.8214 | 144.1559 | 148.6247 | 153.2321 | 157.9823 | 162.8797 | 167.929 | 173.1348 | 178.502 | 184.0355 | 189.7406 | 195.6226 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 139.3151 | 142.1014 | 144.9434 | 147.8423 | 150.7991 | 153.8151 | 156.8914 | 160.0292 | 163.2298 | 166.4944 | 169.8243 | 173.2208 | 176.6852 | 180.2189 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 140.0394 | 142.8402 | 147.4554 | 149.764 | 152.7592 | 155.8144 | 158.9307 | 162.1093 | 165.3515 | 168.6586 | 172.0317 | 175.4724 | 178.9818 | 182.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTUE_R | Building Trades Unassigned - Electrical_RC | Labor |  | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 131.5396 | 135.6173 | 139.8214 | 144.1559 | 148.6247 | 153.2321 | 157.9823 | 162.8797 | 167.929 | 173.1348 | 178.502 | 184.0355 | 189.7406 | 195.6226 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 139.3151 | 142.1014 | 144.9434 | 147.8423 | 150.7991 | 153.8151 | 156.8914 | 160.0292 | 163.2298 | 166.4944 | 169.8243 | 173.2208 | 176.6852 | 180.2189 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 140.0394 | 142.8402 | 147.4554 | 149.764 | 152.7592 | 155.8144 | 158.9307 | 162.1093 | 165.3515 | 168.6586 | 172.0317 | 175.4724 | 178.9818 | 182.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTUP_R | Building Trades Unassigned - Plumbers_RC | Labor |  | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 131.5396 | 135.6173 | 139.8214 | 144.1559 | 148.6247 | 153.2321 | 157.9823 | 162.8797 | 167.929 | 173.1348 | 178.502 | 184.0355 | 189.7406 | 195.6226 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 139.3151 | 142.1014 | 144.9434 | 147.8423 | 150.7991 | 153.8151 | 156.8914 | 160.0292 | 163.2298 | 166.4944 | 169.8243 | 173.2208 | 176.6852 | 180.2189 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 140.0394 | 142.8402 | 147.4554 | 149.764 | 152.7592 | 155.8144 | 158.9307 | 162.1093 | 165.3515 | 168.6586 | 172.0317 | 175.4724 | 178.9818 | 182.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BTUR_R | Building Trades Unassigned - Riggers_RC | Labor |  | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 131.5396 | 135.6173 | 139.8214 | 144.1559 | 148.6247 | 153.2321 | 157.9823 | 162.8797 | 167.929 | 173.1348 | 178.502 | 184.0355 | 189.7406 | 195.6226 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 139.3151 | 142.1014 | 144.9434 | 147.8423 | 150.7991 | 153.8151 | 156.8914 | 160.0292 | 163.2298 | 166.4944 | 169.8243 | 173.2208 | 176.6852 | 180.2189 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 140.0394 | 142.8402 | 147.4554 | 149.764 | 152.7592 | 155.8144 | 158.9307 | 162.1093 | 165.3515 | 168.6586 | 172.0317 | 175.4724 | 178.9818 | 182.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CS_R | Central Shops_RC | Labor |  | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 155.9605 | 183.5138 | 189.2028 | 195.0681 | 201.1152 | 207.3497 | 213.7776 | 220.4047 | 227.2372 | 234.2816 | 241.5443 | 249.0322 | 256.7522 | 264.7115 | 272.9176 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 0 | 139.044 | 143.2153 | 147.5118 | 151.9371 | 156.4953 | 161.1901 | 166.0258 | 171.0066 | 176.1368 | 181.4209 | 186.8635 | 192.4694 | 198.2435 | 204.1908 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 131.5396 | 135.6173 | 139.8214 | 144.1559 | 148.6247 | 153.2321 | 157.9823 | 162.8797 | 167.929 | 173.1348 | 178.502 | 184.0355 | 189.7406 | 195.6226 | 0 | 0 | 0 | 0 | 0 | 129.1519 | 143.3544 | 147.7984 | 152.3801 | 157.1039 | 161.9741 | 166.9953 | 172.1722 | 177.5095 | 183.0123 | 188.6857 | 194.5349 | 200.5655 | 206.783 | 213.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 139.3151 | 142.1014 | 144.9434 | 147.8423 | 150.7991 | 153.8151 | 156.8914 | 160.0292 | 163.2298 | 166.4944 | 169.8243 | 173.2208 | 176.6852 | 180.2189 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5058 | 177.996 | 181.5559 | 185.187 | 188.8907 | 192.6686 | 196.5219 | 200.4524 | 204.4614 | 208.5506 | 212.7217 | 216.9761 | 221.3156 | 225.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 140.0394 | 142.8402 | 147.4554 | 149.764 | 152.7592 | 155.8144 | 158.9307 | 162.1093 | 165.3515 | 168.6586 | 172.0317 | 175.4724 | 178.9818 | 182.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ECS_R | Engineering Construction Services _RC | Labor |  | These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 182.0585; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 188.4306; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 195.0256; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 201.8515; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 208.9163; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 216.2284; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 223.7964; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 231.6293; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 239.7363; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 248.1271; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 176.8165; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 183.0051; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 191.6963; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 197.5606; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 204.4753; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 211.6319; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 219.039; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 226.7054; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 234.6401; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 242.8525; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 251.3523; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 260.1496; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 269.2549; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 278.6788
APPLIC_L | Applications Engineer (Programmer)_Low | Labor |  | 0 | 0 | 137.1672 | 145.9762 | 150.5015 | 155.167 | 159.9772 | 164.9365 | 170.0495 | 175.3211 | 180.756 | 186.3595 | 192.1366 | 198.0929 | 204.2337 | 210.565 | 217.0925 | 0 | 0 | 0 | 0 | 0 | 151.8843 | 158.432 | 163.3434 | 168.407 | 173.6276 | 179.0101 | 184.5594 | 190.2807 | 196.1794 | 202.261 | 208.5311 | 214.9956 | 221.6604 | 228.5319 | 235.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 91.1016 | 93.9257 | 96.8374 | 99.8394 | 102.9344 | 106.1254 | 109.4153 | 112.8071 | 116.3042 | 119.9096 | 123.6268 | 127.4592 | 131.4104 | 135.4842 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 83.5933 | 86.1847 | 88.8564 | 91.6109 | 94.4509 | 97.3789 | 100.3976 | 103.5099 | 106.7187 | 110.027 | 113.4379 | 116.9544 | 120.58 | 124.318 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 94.9162 | 98.2383 | 101.6766 | 105.2353 | 108.9185 | 112.7307 | 116.6763 | 120.7599 | 124.9865 | 129.3611 | 133.8887 | 138.5748 | 143.4249 | 148.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3513 | 153.5436 | 158.9176 | 164.4798 | 170.2366 | 176.1948 | 182.3617 | 188.7443 | 195.3504 | 202.1876 | 209.2642 | 216.5884 | 224.169 | 232.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.4097 | 98.7491 | 103.4388 | 106.6032 | 110.3343 | 114.196 | 118.1929 | 122.3296 | 126.6111 | 131.0425 | 135.629 | 140.376 | 145.2892 | 150.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
APPLIC_M | Applications Engineer (Programmer)_Med | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
APPLIC_H | Applications Engineer (Programmer)_High | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SYS_L | Systems Architect/ Systems Engineer_Low | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SYS_M | Systems Architect/ Systems Engineer_Med | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SYS_H | Systems Architect/ Systems Engineer_High | Labor |  | 0 | 0 | 271.9017 | 289.3636 | 298.3339 | 307.5822 | 317.1173 | 326.9479 | 337.0833 | 347.5329 | 358.3064 | 369.4139 | 380.8657 | 392.6726 | 404.8454 | 417.3956 | 430.3349 | 0 | 0 | 0 | 0 | 0 | 301.075 | 314.0542 | 323.7899 | 333.8274 | 344.176 | 354.8455 | 365.8457 | 377.1869 | 388.8797 | 400.935 | 413.3639 | 426.1782 | 439.3897 | 453.0108 | 467.0542 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4098 | 186.8521 | 192.4577 | 198.2314 | 204.1784 | 210.3037 | 216.6128 | 223.1112 | 229.8045 | 236.6987 | 243.7996 | 251.1136 | 258.647 | 266.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4098 | 186.8521 | 192.4577 | 198.2314 | 204.1784 | 210.3037 | 216.6128 | 223.1112 | 229.8045 | 236.6987 | 243.7996 | 251.1136 | 258.647 | 266.4064 | 0 | 0 | 0 | 0 | 0 | 180.4567 | 182.6396 | 188.3014 | 194.1388 | 200.1571 | 206.362 | 212.7592 | 219.3547 | 226.1547 | 233.1655 | 240.3936 | 247.8458 | 255.5291 | 263.4505 | 271.6174 | 0 | 0 | 0 | 0 | 0 | 178.4291 | 180.5875 | 186.1857 | 191.9575 | 197.9081 | 204.0433 | 210.3686 | 216.8901 | 223.6136 | 230.5457 | 237.6926 | 245.0611 | 252.6579 | 260.4903 | 268.5655 | 0 | 0 | 0 | 0 | 0 | 178.4291 | 165.704 | 170.8409 | 176.1369 | 181.5972 | 187.2267 | 193.0307 | 199.0147 | 205.1841 | 211.5448 | 218.1027 | 224.8639 | 231.8347 | 239.0216 | 246.4312 | 0 | 0 | 0 | 0 | 0 | 180.4567 | 182.6396 | 188.3014 | 194.1388 | 200.1571 | 206.362 | 212.7592 | 219.3547 | 226.1547 | 233.1655 | 240.3936 | 247.8458 | 255.5291 | 263.4505 | 271.6174 | 0 | 0 | 0 | 0 | 0 | 0 | 183.0693 | 189.4767 | 196.1084 | 202.9722 | 210.0762 | 217.4289 | 225.0389 | 232.9153 | 241.0673 | 249.5047 | 258.2373 | 267.2756 | 276.6303 | 286.3123 | 0 | 0 | 0 | 0 | 0 | 0 | 286.1321 | 296.1467 | 306.5118 | 317.2397 | 328.3431 | 339.8351 | 351.7294 | 364.0399 | 376.7813 | 389.9686 | 403.6175 | 417.7441 | 432.3652 | 447.498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.0211 | 190.4619 | 199.5072 | 205.6105 | 212.8069 | 220.2551 | 227.964 | 235.9428 | 244.2008 | 252.7478 | 261.594 | 270.7498 | 280.226 | 290.0339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TECHE_L | Technology Engineer (Controls)_Low | Labor |  | 0 | 0 | 137.1672 | 145.9762 | 150.5015 | 155.167 | 159.9772 | 164.9365 | 170.0495 | 175.3211 | 180.756 | 186.3595 | 192.1366 | 198.0929 | 204.2337 | 210.565 | 217.0925 | 0 | 0 | 0 | 0 | 0 | 151.8843 | 158.432 | 163.3434 | 168.407 | 173.6276 | 179.0101 | 184.5594 | 190.2807 | 196.1794 | 202.261 | 208.5311 | 214.9956 | 221.6604 | 228.5319 | 235.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 91.1016 | 93.9257 | 96.8374 | 99.8394 | 102.9344 | 106.1254 | 109.4153 | 112.8071 | 116.3042 | 119.9096 | 123.6268 | 127.4592 | 131.4104 | 135.4842 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 83.5933 | 86.1847 | 88.8564 | 91.6109 | 94.4509 | 97.3789 | 100.3976 | 103.5099 | 106.7187 | 110.027 | 113.4379 | 116.9544 | 120.58 | 124.318 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 94.9162 | 98.2383 | 101.6766 | 105.2353 | 108.9185 | 112.7307 | 116.6763 | 120.7599 | 124.9865 | 129.3611 | 133.8887 | 138.5748 | 143.4249 | 148.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3513 | 153.5436 | 158.9176 | 164.4798 | 170.2366 | 176.1948 | 182.3617 | 188.7443 | 195.3504 | 202.1876 | 209.2642 | 216.5884 | 224.169 | 232.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.4097 | 98.7491 | 103.4388 | 106.6032 | 110.3343 | 114.196 | 118.1929 | 122.3296 | 126.6111 | 131.0425 | 135.629 | 140.376 | 145.2892 | 150.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TECHE_M | Technology Engineer (Controls)_Med | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TECHE_H | Technology Engineer (Controls)_High | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ITNET_L | IT Professional (Network-Bus Support)_Low | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ITNET_M | IT Professional (Network-Bus Support)_Med | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ITNET_H | IT Professional (Network-Bus Support)_High | Labor |  | 0 | 0 | 271.9017 | 289.3636 | 298.3339 | 307.5822 | 317.1173 | 326.9479 | 337.0833 | 347.5329 | 358.3064 | 369.4139 | 380.8657 | 392.6726 | 404.8454 | 417.3956 | 430.3349 | 0 | 0 | 0 | 0 | 0 | 301.075 | 314.0542 | 323.7899 | 333.8274 | 344.176 | 354.8455 | 365.8457 | 377.1869 | 388.8797 | 400.935 | 413.3639 | 426.1782 | 439.3897 | 453.0108 | 467.0542 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4098 | 186.8521 | 192.4577 | 198.2314 | 204.1784 | 210.3037 | 216.6128 | 223.1112 | 229.8045 | 236.6987 | 243.7996 | 251.1136 | 258.647 | 266.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4098 | 186.8521 | 192.4577 | 198.2314 | 204.1784 | 210.3037 | 216.6128 | 223.1112 | 229.8045 | 236.6987 | 243.7996 | 251.1136 | 258.647 | 266.4064 | 0 | 0 | 0 | 0 | 0 | 180.4567 | 182.6396 | 188.3014 | 194.1388 | 200.1571 | 206.362 | 212.7592 | 219.3547 | 226.1547 | 233.1655 | 240.3936 | 247.8458 | 255.5291 | 263.4505 | 271.6174 | 0 | 0 | 0 | 0 | 0 | 178.4291 | 180.5875 | 186.1857 | 191.9575 | 197.9081 | 204.0433 | 210.3686 | 216.8901 | 223.6136 | 230.5457 | 237.6926 | 245.0611 | 252.6579 | 260.4903 | 268.5655 | 0 | 0 | 0 | 0 | 0 | 178.4291 | 165.704 | 170.8409 | 176.1369 | 181.5972 | 187.2267 | 193.0307 | 199.0147 | 205.1841 | 211.5448 | 218.1027 | 224.8639 | 231.8347 | 239.0216 | 246.4312 | 0 | 0 | 0 | 0 | 0 | 180.4567 | 182.6396 | 188.3014 | 194.1388 | 200.1571 | 206.362 | 212.7592 | 219.3547 | 226.1547 | 233.1655 | 240.3936 | 247.8458 | 255.5291 | 263.4505 | 271.6174 | 0 | 0 | 0 | 0 | 0 | 0 | 183.0693 | 189.4767 | 196.1084 | 202.9722 | 210.0762 | 217.4289 | 225.0389 | 232.9153 | 241.0673 | 249.5047 | 258.2373 | 267.2756 | 276.6303 | 286.3123 | 0 | 0 | 0 | 0 | 0 | 0 | 286.1321 | 296.1467 | 306.5118 | 317.2397 | 328.3431 | 339.8351 | 351.7294 | 364.0399 | 376.7813 | 389.9686 | 403.6175 | 417.7441 | 432.3652 | 447.498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.0211 | 190.4619 | 199.5072 | 205.6105 | 212.8069 | 220.2551 | 227.964 | 235.9428 | 244.2008 | 252.7478 | 261.594 | 270.7498 | 280.226 | 290.0339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA_L | QA Professional_Low | Labor |  | 0 | 0 | 119.1131 | 126.7627 | 130.6923 | 134.7438 | 138.9209 | 143.2274 | 147.6675 | 152.2451 | 156.9647 | 161.8306 | 166.8474 | 172.0197 | 177.3523 | 182.8502 | 188.5186 | 0 | 0 | 0 | 0 | 0 | 131.8931 | 137.579 | 141.8439 | 146.2411 | 150.7746 | 155.4486 | 160.2675 | 165.2358 | 170.3581 | 175.6392 | 181.084 | 186.6976 | 192.4853 | 198.4523 | 204.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 79.1107 | 81.5631 | 84.0916 | 86.6984 | 89.3861 | 92.157 | 95.0139 | 97.9593 | 100.9961 | 104.127 | 107.3549 | 110.6829 | 114.1141 | 117.6516 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 72.5906 | 74.841 | 77.161 | 79.553 | 82.0192 | 84.5618 | 87.1832 | 89.8858 | 92.6723 | 95.5451 | 98.507 | 101.5608 | 104.7091 | 107.9551 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 0 | 82.4704 | 85.3568 | 88.3443 | 91.4364 | 94.6366 | 97.9489 | 101.3771 | 104.9253 | 108.5977 | 112.3986 | 116.3326 | 120.4042 | 124.6184 | 128.98 | 0 | 0 | 0 | 0 | 0 | 0 | 128.8988 | 133.4103 | 138.0796 | 142.9124 | 147.9143 | 153.0913 | 158.4495 | 163.9953 | 169.7351 | 175.6758 | 181.8245 | 188.1884 | 194.7749 | 201.5921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.8992 | 85.8006 | 89.8754 | 92.6249 | 95.8668 | 99.2221 | 102.6949 | 106.2892 | 110.0093 | 113.8596 | 117.8447 | 121.9693 | 126.2382 | 130.6565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA_M | QA Professional_Med | Labor |  | 0 | 0 | 176.3049 | 187.6274 | 193.4439 | 199.4406 | 205.6233 | 211.9976 | 218.5695 | 225.3452 | 232.3309 | 239.5331 | 246.9587 | 254.6144 | 262.5074 | 270.6452 | 279.0352 | 0 | 0 | 0 | 0 | 0 | 195.2212 | 203.6371 | 209.9499 | 216.4583 | 223.1685 | 230.0868 | 237.2194 | 244.5733 | 252.155 | 259.9718 | 268.031 | 276.3399 | 284.9065 | 293.7386 | 302.8444 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 117.0954 | 120.7254 | 124.4679 | 128.3264 | 132.3045 | 136.406 | 140.6345 | 144.9942 | 149.489 | 154.1232 | 158.901 | 163.8269 | 168.9056 | 174.1417 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 107.4448 | 110.7756 | 114.2097 | 117.7502 | 121.4004 | 125.1638 | 129.0439 | 133.0443 | 137.1686 | 141.4209 | 145.8049 | 150.3249 | 154.9849 | 159.7895 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 121.1321 | 125.3717 | 129.7597 | 134.3013 | 139.0018 | 143.8669 | 148.9022 | 154.1138 | 159.5078 | 165.0906 | 170.8688 | 176.8492 | 183.0389 | 189.4452 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3259 | 195.9524 | 202.8107 | 209.9091 | 217.2559 | 224.8598 | 232.7299 | 240.8755 | 249.3061 | 258.0318 | 267.0629 | 276.4102 | 286.0845 | 296.0975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.7619 | 126.0235 | 132.0086 | 136.047 | 140.8086 | 145.7369 | 150.8377 | 156.117 | 161.5811 | 167.2365 | 173.0897 | 179.1479 | 185.4181 | 191.9077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA_H | QA Professional_High | Labor |  | 0 | 0 | 231.2839 | 246.1372 | 253.7675 | 261.6343 | 269.7449 | 278.107 | 286.7283 | 295.6169 | 304.781 | 314.2292 | 323.9703 | 334.0134 | 344.3678 | 355.0432 | 366.0496 | 0 | 0 | 0 | 0 | 0 | 256.0991 | 267.1394 | 275.4207 | 283.9588 | 292.7615 | 301.8371 | 311.1941 | 320.8411 | 330.7871 | 341.0415 | 351.6138 | 362.5139 | 373.7518 | 385.3381 | 397.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 159.016 | 163.7864 | 168.7 | 173.761 | 178.9739 | 184.3431 | 189.8734 | 195.5696 | 201.4367 | 207.4798 | 213.7042 | 220.1153 | 226.7187 | 233.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 159.016 | 163.7864 | 168.7 | 173.761 | 178.9739 | 184.3431 | 189.8734 | 195.5696 | 201.4367 | 207.4798 | 213.7042 | 220.1153 | 226.7187 | 233.5203 | 0 | 0 | 0 | 0 | 0 | 153.4993 | 155.3561 | 160.1722 | 165.1375 | 170.2568 | 175.5347 | 180.9763 | 186.5866 | 192.3707 | 198.3342 | 204.4826 | 210.8216 | 217.357 | 224.0951 | 231.042 | 0 | 0 | 0 | 0 | 0 | 151.7746 | 153.6105 | 158.3725 | 163.282 | 168.3438 | 173.5624 | 178.9428 | 184.4901 | 190.2093 | 196.1058 | 202.185 | 208.4528 | 214.9148 | 221.5772 | 228.4461 | 0 | 0 | 0 | 0 | 0 | 151.7746 | 140.9505 | 145.3199 | 149.8248 | 154.4694 | 159.258 | 164.195 | 169.285 | 174.5328 | 179.9433 | 185.5216 | 191.2728 | 197.2022 | 203.3155 | 209.6183 | 0 | 0 | 0 | 0 | 0 | 153.4993 | 155.3561 | 160.1722 | 165.1375 | 170.2568 | 175.5347 | 180.9763 | 186.5866 | 192.3707 | 198.3342 | 204.4826 | 210.8216 | 217.357 | 224.0951 | 231.042 | 0 | 0 | 0 | 0 | 0 | 0 | 160.1788 | 165.7851 | 171.5875 | 177.5931 | 183.8089 | 190.2422 | 196.9006 | 203.7922 | 210.9249 | 218.3073 | 225.948 | 233.8562 | 242.0412 | 250.5126 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3549 | 259.1173 | 268.1864 | 277.5729 | 287.288 | 297.343 | 307.75 | 318.5213 | 329.6695 | 341.208 | 353.1503 | 365.5105 | 378.3034 | 391.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.0116 | 166.647 | 174.5613 | 179.9015 | 186.1981 | 192.715 | 199.46 | 206.4411 | 213.6665 | 221.1449 | 228.8849 | 236.8959 | 245.1873 | 253.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ESH_L | ES&H Engineer_Low | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ESH_M | ES&H Engineer_Med | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ESH_H | ES&H Engineer_High | Labor |  | 0 | 0 | 271.9017 | 289.3636 | 298.3339 | 307.5822 | 317.1173 | 326.9479 | 337.0833 | 347.5329 | 358.3064 | 369.4139 | 380.8657 | 392.6726 | 404.8454 | 417.3956 | 430.3349 | 0 | 0 | 0 | 0 | 0 | 301.075 | 314.0542 | 323.7899 | 333.8274 | 344.176 | 354.8455 | 365.8457 | 377.1869 | 388.8797 | 400.935 | 413.3639 | 426.1782 | 439.3897 | 453.0108 | 467.0542 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4098 | 186.8521 | 192.4577 | 198.2314 | 204.1784 | 210.3037 | 216.6128 | 223.1112 | 229.8045 | 236.6987 | 243.7996 | 251.1136 | 258.647 | 266.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4098 | 186.8521 | 192.4577 | 198.2314 | 204.1784 | 210.3037 | 216.6128 | 223.1112 | 229.8045 | 236.6987 | 243.7996 | 251.1136 | 258.647 | 266.4064 | 0 | 0 | 0 | 0 | 0 | 180.4567 | 182.6396 | 188.3014 | 194.1388 | 200.1571 | 206.362 | 212.7592 | 219.3547 | 226.1547 | 233.1655 | 240.3936 | 247.8458 | 255.5291 | 263.4505 | 271.6174 | 0 | 0 | 0 | 0 | 0 | 178.4291 | 180.5875 | 186.1857 | 191.9575 | 197.9081 | 204.0433 | 210.3686 | 216.8901 | 223.6136 | 230.5457 | 237.6926 | 245.0611 | 252.6579 | 260.4903 | 268.5655 | 0 | 0 | 0 | 0 | 0 | 178.4291 | 165.704 | 170.8409 | 176.1369 | 181.5972 | 187.2267 | 193.0307 | 199.0147 | 205.1841 | 211.5448 | 218.1027 | 224.8639 | 231.8347 | 239.0216 | 246.4312 | 0 | 0 | 0 | 0 | 0 | 180.4567 | 182.6396 | 188.3014 | 194.1388 | 200.1571 | 206.362 | 212.7592 | 219.3547 | 226.1547 | 233.1655 | 240.3936 | 247.8458 | 255.5291 | 263.4505 | 271.6174 | 0 | 0 | 0 | 0 | 0 | 0 | 183.0693 | 189.4767 | 196.1084 | 202.9722 | 210.0762 | 217.4289 | 225.0389 | 232.9153 | 241.0673 | 249.5047 | 258.2373 | 267.2756 | 276.6303 | 286.3123 | 0 | 0 | 0 | 0 | 0 | 0 | 286.1321 | 296.1467 | 306.5118 | 317.2397 | 328.3431 | 339.8351 | 351.7294 | 364.0399 | 376.7813 | 389.9686 | 403.6175 | 417.7441 | 432.3652 | 447.498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.0211 | 190.4619 | 199.5072 | 205.6105 | 212.8069 | 220.2551 | 227.964 | 235.9428 | 244.2008 | 252.7478 | 261.594 | 270.7498 | 280.226 | 290.0339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGMT_L | Group Manager_Low | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGMT_M | Group Manager_Med | Labor |  | 0 | 0 | 231.3483 | 246.2058 | 253.8382 | 261.7072 | 269.8201 | 278.1845 | 286.8083 | 295.6993 | 304.866 | 314.3168 | 324.0607 | 334.1065 | 344.4639 | 355.1422 | 366.1516 | 0 | 0 | 0 | 0 | 0 | 256.1705 | 267.2139 | 275.4975 | 284.0379 | 292.8431 | 301.9213 | 311.2808 | 320.9305 | 330.8794 | 341.1366 | 351.7119 | 362.6149 | 373.856 | 385.4455 | 397.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 156.1601 | 160.8449 | 165.6702 | 170.6403 | 175.7596 | 181.0323 | 186.4633 | 192.0572 | 197.8189 | 203.7535 | 209.8661 | 216.1621 | 222.6469 | 229.3263 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 153.6534 | 158.4166 | 163.3275 | 168.3907 | 173.6108 | 178.9927 | 184.5415 | 190.2623 | 196.1604 | 202.2414 | 208.5109 | 214.9747 | 221.6389 | 228.5097 | 0 | 0 | 0 | 0 | 0 | 151.8169 | 140.9897 | 145.3604 | 149.8666 | 154.5125 | 159.3024 | 164.2407 | 169.3322 | 174.5815 | 179.9935 | 185.5733 | 191.3261 | 197.2572 | 203.3722 | 209.6767 | 0 | 0 | 0 | 0 | 0 | 153.5421 | 155.3994 | 160.2168 | 165.1835 | 170.3042 | 175.5837 | 181.0267 | 186.6386 | 192.4244 | 198.3895 | 204.5396 | 210.8803 | 217.4176 | 224.1576 | 231.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 157.6064 | 163.1226 | 168.8319 | 174.741 | 180.857 | 187.187 | 193.7385 | 200.5194 | 207.5375 | 214.8013 | 222.3194 | 230.1006 | 238.1541 | 246.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 246.3343 | 254.956 | 263.8794 | 273.1152 | 282.6742 | 292.5678 | 302.8077 | 313.406 | 324.3752 | 335.7283 | 347.4788 | 359.6406 | 372.228 | 385.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.4258 | 163.9707 | 171.7579 | 177.0124 | 183.2078 | 189.6201 | 196.2568 | 203.1258 | 210.2352 | 217.5934 | 225.2092 | 233.0915 | 241.2497 | 249.6934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGMT_H | Group Manager_High | Labor |  | 0 | 0 | 271.9017 | 289.3636 | 298.3339 | 307.5822 | 317.1173 | 326.9479 | 337.0833 | 347.5329 | 358.3064 | 369.4139 | 380.8657 | 392.6726 | 404.8454 | 417.3956 | 430.3349 | 0 | 0 | 0 | 0 | 0 | 301.075 | 314.0542 | 323.7899 | 333.8274 | 344.176 | 354.8455 | 365.8457 | 377.1869 | 388.8797 | 400.935 | 413.3639 | 426.1782 | 439.3897 | 453.0108 | 467.0542 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4098 | 186.8521 | 192.4577 | 198.2314 | 204.1784 | 210.3037 | 216.6128 | 223.1112 | 229.8045 | 236.6987 | 243.7996 | 251.1136 | 258.647 | 266.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4098 | 186.8521 | 192.4577 | 198.2314 | 204.1784 | 210.3037 | 216.6128 | 223.1112 | 229.8045 | 236.6987 | 243.7996 | 251.1136 | 258.647 | 266.4064 | 0 | 0 | 0 | 0 | 0 | 180.4567 | 182.6396 | 188.3014 | 194.1388 | 200.1571 | 206.362 | 212.7592 | 219.3547 | 226.1547 | 233.1655 | 240.3936 | 247.8458 | 255.5291 | 263.4505 | 271.6174 | 0 | 0 | 0 | 0 | 0 | 178.4291 | 180.5875 | 186.1857 | 191.9575 | 197.9081 | 204.0433 | 210.3686 | 216.8901 | 223.6136 | 230.5457 | 237.6926 | 245.0611 | 252.6579 | 260.4903 | 268.5655 | 0 | 0 | 0 | 0 | 0 | 178.4291 | 165.704 | 170.8409 | 176.1369 | 181.5972 | 187.2267 | 193.0307 | 199.0147 | 205.1841 | 211.5448 | 218.1027 | 224.8639 | 231.8347 | 239.0216 | 246.4312 | 0 | 0 | 0 | 0 | 0 | 180.4567 | 182.6396 | 188.3014 | 194.1388 | 200.1571 | 206.362 | 212.7592 | 219.3547 | 226.1547 | 233.1655 | 240.3936 | 247.8458 | 255.5291 | 263.4505 | 271.6174 | 0 | 0 | 0 | 0 | 0 | 0 | 183.0693 | 189.4767 | 196.1084 | 202.9722 | 210.0762 | 217.4289 | 225.0389 | 232.9153 | 241.0673 | 249.5047 | 258.2373 | 267.2756 | 276.6303 | 286.3123 | 0 | 0 | 0 | 0 | 0 | 0 | 286.1321 | 296.1467 | 306.5118 | 317.2397 | 328.3431 | 339.8351 | 351.7294 | 364.0399 | 376.7813 | 389.9686 | 403.6175 | 417.7441 | 432.3652 | 447.498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.0211 | 190.4619 | 199.5072 | 205.6105 | 212.8069 | 220.2551 | 227.964 | 235.9428 | 244.2008 | 252.7478 | 261.594 | 270.7498 | 280.226 | 290.0339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMGMT_L | Division Manager_Low | Labor |  | 0 | 0 | 468.6491 | 498.7463 | 514.2075 | 530.1479 | 546.5825 | 563.5266 | 580.9959 | 599.0068 | 617.576 | 636.7208 | 656.4592 | 676.8094 | 697.7905 | 719.422 | 741.7241 | 0 | 0 | 0 | 0 | 0 | 518.932 | 541.303 | 558.0834 | 575.384 | 593.2209 | 611.6107 | 630.5706 | 650.1183 | 670.272 | 691.0504 | 712.473 | 734.5597 | 757.331 | 780.8083 | 805.0133 | 0 | 0 | 0 | 0 | 0 | 0 | 311.4338 | 320.7768 | 330.4001 | 340.3121 | 350.5214 | 361.0371 | 371.8682 | 383.0242 | 394.515 | 406.3504 | 418.5409 | 431.0972 | 444.0301 | 457.351 | 0 | 0 | 0 | 0 | 0 | 0 | 311.4338 | 320.7768 | 330.4001 | 340.3121 | 350.5214 | 361.0371 | 371.8682 | 383.0242 | 394.515 | 406.3504 | 418.5409 | 431.0972 | 444.0301 | 457.351 | 0 | 0 | 0 | 0 | 0 | 311.0346 | 314.7972 | 324.5559 | 334.6171 | 344.9902 | 355.6849 | 366.7112 | 378.0792 | 389.7997 | 401.8835 | 414.3418 | 427.1864 | 440.4292 | 454.0825 | 468.1591 | 0 | 0 | 0 | 0 | 0 | 307.5399 | 311.2601 | 320.9092 | 330.8574 | 341.1139 | 351.6885 | 362.5908 | 373.8311 | 385.4199 | 397.3679 | 409.6863 | 422.3866 | 435.4806 | 448.9805 | 462.8989 | 0 | 0 | 0 | 0 | 0 | 307.5399 | 285.6071 | 294.4609 | 303.5892 | 313.0004 | 322.7034 | 332.7072 | 343.0212 | 353.6548 | 364.6181 | 375.9213 | 387.5748 | 399.5897 | 411.9769 | 424.7482 | 0 | 0 | 0 | 0 | 0 | 311.0346 | 314.7972 | 324.5559 | 334.6171 | 344.9902 | 355.6849 | 366.7112 | 378.0792 | 389.7997 | 401.8835 | 414.3418 | 427.1864 | 440.4292 | 454.0825 | 468.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 310.5816 | 321.452 | 332.7028 | 344.3474 | 356.3995 | 368.8735 | 381.7841 | 395.1465 | 408.9767 | 423.2908 | 438.106 | 453.4397 | 469.3101 | 485.736 | 0 | 0 | 0 | 0 | 0 | 0 | 485.4301 | 502.4202 | 520.0049 | 538.2051 | 557.0422 | 576.5387 | 596.7176 | 617.6027 | 639.2188 | 661.5914 | 684.7471 | 708.7133 | 733.5183 | 759.1914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312.1964 | 323.1233 | 338.4689 | 348.8233 | 361.0321 | 373.6682 | 386.7466 | 400.2828 | 414.2927 | 428.7929 | 443.8006 | 459.3337 | 475.4103 | 492.0497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMGMT_M | Division Manager_Med | Labor |  | 0 | 0 | 526.7314 | 560.5588 | 577.9361 | 595.8521 | 614.3235 | 633.3675 | 653.0019 | 673.245 | 694.1156 | 715.6332 | 737.8178 | 760.6902 | 784.2716 | 808.584 | 833.6501 | 0 | 0 | 0 | 0 | 0 | 583.2461 | 608.3897 | 627.2498 | 646.6945 | 666.742 | 687.411 | 708.7208 | 730.6911 | 753.3425 | 776.6962 | 800.7737 | 825.5977 | 851.1913 | 877.5782 | 904.7831 | 0 | 0 | 0 | 0 | 0 | 0 | 358.1125 | 368.8559 | 379.9216 | 391.3192 | 403.0588 | 415.1506 | 427.6051 | 440.4332 | 453.6462 | 467.2556 | 481.2733 | 495.7115 | 510.5828 | 525.9003 | 0 | 0 | 0 | 0 | 0 | 0 | 358.1125 | 368.8559 | 379.9216 | 391.3192 | 403.0588 | 415.1506 | 427.6051 | 440.4332 | 453.6462 | 467.2556 | 481.2733 | 495.7115 | 510.5828 | 525.9003 | 0 | 0 | 0 | 0 | 0 | 349.5829 | 353.8117 | 364.7799 | 376.0881 | 387.7468 | 399.767 | 412.1597 | 424.9367 | 438.1097 | 451.6911 | 465.6935 | 480.13 | 495.0141 | 510.3595 | 526.1807 | 0 | 0 | 0 | 0 | 0 | 345.655 | 349.8363 | 360.6812 | 371.8624 | 383.3901 | 395.2752 | 407.5287 | 420.1621 | 433.1871 | 446.6159 | 460.461 | 474.7353 | 489.4521 | 504.6251 | 520.2685 | 0 | 0 | 0 | 0 | 0 | 345.655 | 321.0039 | 330.955 | 341.2147 | 351.7923 | 362.6979 | 373.9415 | 385.5337 | 397.4852 | 409.8073 | 422.5113 | 435.6092 | 449.113 | 463.0355 | 477.3896 | 0 | 0 | 0 | 0 | 0 | 349.5829 | 353.8117 | 364.7799 | 376.0881 | 387.7468 | 399.767 | 412.1597 | 424.9367 | 438.1097 | 451.6911 | 465.6935 | 480.13 | 495.0141 | 510.3595 | 526.1807 | 0 | 0 | 0 | 0 | 0 | 0 | 360.7886 | 373.4162 | 386.4858 | 400.0128 | 414.0133 | 428.5037 | 443.5013 | 459.0239 | 475.0897 | 491.7179 | 508.928 | 526.7405 | 545.1764 | 564.2576 | 0 | 0 | 0 | 0 | 0 | 0 | 563.9023 | 583.6388 | 604.0662 | 625.2085 | 647.0908 | 669.739 | 693.1799 | 717.4412 | 742.5516 | 768.5409 | 795.4398 | 823.2802 | 852.095 | 881.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362.6645 | 375.3577 | 393.184 | 405.2123 | 419.3947 | 434.0735 | 449.2661 | 464.9904 | 481.2651 | 498.1093 | 515.5432 | 533.5872 | 552.2627 | 571.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMGMT_H | Division Manager_High | Labor |  | 0 | 0 | 663.0055 | 705.5846 | 727.4577 | 750.0089 | 773.2592 | 797.2302 | 821.9444 | 847.4247 | 873.6948 | 900.7794 | 928.7035 | 957.4933 | 987.1756 | 1017.7781 | 1049.3292 | 0 | 0 | 0 | 0 | 0 | 734.1416 | 765.7902 | 789.5297 | 814.0051 | 839.2393 | 865.2557 | 892.0786 | 919.733 | 948.2448 | 977.6404 | 1007.9472 | 1039.1936 | 1071.4086 | 1104.6222 | 1138.8655 | 0 | 0 | 0 | 0 | 0 | 0 | 448.3835 | 461.835 | 475.6901 | 489.9608 | 504.6596 | 519.7994 | 535.3934 | 551.4552 | 567.9988 | 585.0388 | 602.59 | 620.6677 | 639.2877 | 658.4663 | 0 | 0 | 0 | 0 | 0 | 0 | 448.3835 | 461.835 | 475.6901 | 489.9608 | 504.6596 | 519.7994 | 535.3934 | 551.4552 | 567.9988 | 585.0388 | 602.59 | 620.6677 | 639.2877 | 658.4663 | 0 | 0 | 0 | 0 | 0 | 440.0258 | 445.3487 | 459.1545 | 473.3883 | 488.0633 | 503.1933 | 518.7923 | 534.8749 | 551.456 | 568.5511 | 586.1762 | 604.3477 | 623.0824 | 642.398 | 662.3123 | 0 | 0 | 0 | 0 | 0 | 435.0817 | 440.3448 | 453.9955 | 468.0693 | 482.5795 | 497.5394 | 512.9632 | 528.865 | 545.2598 | 562.1629 | 579.5899 | 597.5572 | 616.0815 | 635.18 | 654.8706 | 0 | 0 | 0 | 0 | 0 | 435.0817 | 404.053 | 416.5786 | 429.4926 | 442.8068 | 456.5338 | 470.6864 | 485.2777 | 500.3213 | 515.8312 | 531.822 | 548.3085 | 565.306 | 582.8305 | 600.8983 | 0 | 0 | 0 | 0 | 0 | 440.0258 | 445.3487 | 459.1545 | 473.3883 | 488.0633 | 503.1933 | 518.7923 | 534.8749 | 551.456 | 568.5511 | 586.1762 | 604.3477 | 623.0824 | 642.398 | 662.3123 | 0 | 0 | 0 | 0 | 0 | 0 | 452.5805 | 468.4208 | 484.8156 | 501.7841 | 519.3466 | 537.5237 | 556.337 | 575.8088 | 595.9621 | 616.8208 | 638.4095 | 660.7538 | 683.8802 | 707.816 | 0 | 0 | 0 | 0 | 0 | 0 | 707.3703 | 732.1283 | 757.7528 | 784.2741 | 811.7237 | 840.1341 | 869.5388 | 899.9726 | 931.4717 | 964.0732 | 997.8157 | 1032.7393 | 1068.8852 | 1106.2961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.9336 | 470.8563 | 493.2179 | 508.3064 | 526.0972 | 544.5106 | 563.5684 | 583.2933 | 603.7086 | 624.8384 | 646.7077 | 669.3425 | 692.7695 | 717.0164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGMTSCI_H | Manager-Scientist_High | Labor |  | 0 | 0 | 344.3618 | 366.4771 | 377.8379 | 389.5509 | 401.627 | 414.0774 | 426.9138 | 440.1481 | 453.7927 | 467.8603 | 482.364 | 497.3173 | 512.7341 | 528.6288 | 545.0163 | 0 | 0 | 0 | 0 | 0 | 381.3095 | 397.7476 | 410.0778 | 422.7902 | 435.8967 | 449.4095 | 463.3412 | 477.7048 | 492.5136 | 507.7815 | 523.5227 | 539.752 | 556.4843 | 573.7353 | 591.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 237.4344 | 244.5574 | 251.8941 | 259.4509 | 267.2345 | 275.2515 | 283.509 | 292.0143 | 300.7747 | 309.798 | 319.0919 | 328.6647 | 338.5246 | 348.6804 | 0 | 0 | 0 | 0 | 0 | 0 | 237.4344 | 244.5574 | 251.8941 | 259.4509 | 267.2345 | 275.2515 | 283.509 | 292.0143 | 300.7747 | 309.798 | 319.0919 | 328.6647 | 338.5246 | 348.6804 | 0 | 0 | 0 | 0 | 0 | 228.5472 | 231.3119 | 238.4826 | 245.8755 | 253.4977 | 261.3561 | 269.4581 | 277.8113 | 286.4235 | 295.3026 | 304.457 | 313.8952 | 323.6259 | 333.6583 | 344.0017 | 0 | 0 | 0 | 0 | 0 | 225.9793 | 228.7129 | 235.803 | 243.1129 | 250.6494 | 258.4195 | 266.4305 | 274.6899 | 283.2052 | 291.9846 | 301.0361 | 310.3682 | 319.9897 | 329.9093 | 340.1365 | 0 | 0 | 0 | 0 | 0 | 225.9793 | 209.8631 | 216.3689 | 223.0763 | 229.9917 | 237.1214 | 244.4722 | 252.0508 | 259.8644 | 267.9202 | 276.2257 | 284.7887 | 293.6171 | 302.7193 | 312.1036 | 0 | 0 | 0 | 0 | 0 | 228.5472 | 231.3119 | 238.4826 | 245.8755 | 253.4977 | 261.3561 | 269.4581 | 277.8113 | 286.4235 | 295.3026 | 304.457 | 313.8952 | 323.6259 | 333.6583 | 344.0017 | 0 | 0 | 0 | 0 | 0 | 0 | 246.7531 | 255.3894 | 264.328 | 273.5795 | 283.1548 | 293.0652 | 303.3225 | 313.9388 | 324.9266 | 336.2991 | 348.0695 | 360.252 | 372.8608 | 385.9109 | 0 | 0 | 0 | 0 | 0 | 0 | 385.6679 | 399.1663 | 413.1371 | 427.5969 | 442.5628 | 458.0525 | 474.0844 | 490.6773 | 507.851 | 525.6258 | 544.0227 | 563.0635 | 582.7707 | 603.1677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.036 | 256.7173 | 268.9091 | 277.1356 | 286.8353 | 296.8746 | 307.2652 | 318.0195 | 329.1501 | 340.6704 | 352.5939 | 364.9346 | 377.7073 | 390.9271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADMN_L | Administrative_Low | Labor |  | 0 | 0 | 99.5845 | 105.98 | 109.2654 | 112.6526 | 116.1448 | 119.7453 | 123.4574 | 127.2846 | 131.2304 | 135.2986 | 139.4928 | 143.8171 | 148.2754 | 152.872 | 157.611 | 0 | 0 | 0 | 0 | 0 | 110.2693 | 115.023 | 118.5887 | 122.2649 | 126.0551 | 129.9628 | 133.9917 | 138.1454 | 142.4279 | 146.8432 | 151.3953 | 156.0886 | 160.9273 | 165.9161 | 171.0595 | 0 | 0 | 0 | 0 | 0 | 0 | 68.1734 | 70.2186 | 72.3251 | 74.4949 | 76.7297 | 79.0316 | 81.4026 | 83.8447 | 86.36 | 88.9508 | 91.6193 | 94.3679 | 97.1989 | 100.1149 | 0 | 0 | 0 | 0 | 0 | 0 | 68.1734 | 70.2186 | 72.3251 | 74.4949 | 76.7297 | 79.0316 | 81.4026 | 83.8447 | 86.36 | 88.9508 | 91.6193 | 94.3679 | 97.1989 | 100.1149 | 0 | 0 | 0 | 0 | 0 | 66.0926 | 66.8921 | 68.9658 | 71.1037 | 73.3079 | 75.5805 | 77.9235 | 80.3391 | 82.8296 | 85.3973 | 88.0446 | 90.774 | 93.588 | 96.4892 | 99.4804 | 0 | 0 | 0 | 0 | 0 | 65.35 | 66.1405 | 68.1909 | 70.3048 | 72.4842 | 74.7313 | 77.0479 | 79.4364 | 81.8989 | 84.4378 | 87.0554 | 89.7541 | 92.5365 | 95.4051 | 98.3627 | 0 | 0 | 0 | 0 | 0 | 65.35 | 60.6894 | 62.5708 | 64.5105 | 66.5103 | 68.5721 | 70.6979 | 72.8895 | 75.1491 | 77.4787 | 79.8805 | 82.3568 | 84.9099 | 87.5421 | 90.2559 | 0 | 0 | 0 | 0 | 0 | 66.0926 | 66.8921 | 68.9658 | 71.1037 | 73.3079 | 75.5805 | 77.9235 | 80.3391 | 82.8296 | 85.3973 | 88.0446 | 90.774 | 93.588 | 96.4892 | 99.4804 | 0 | 0 | 0 | 0 | 0 | 0 | 68.4377 | 70.833 | 73.3122 | 75.8781 | 78.5339 | 81.2825 | 84.1274 | 87.0719 | 90.1194 | 93.2736 | 96.5382 | 99.917 | 103.4141 | 107.0336 | 0 | 0 | 0 | 0 | 0 | 0 | 106.9662 | 110.71 | 114.5849 | 118.5953 | 122.7462 | 127.0423 | 131.4888 | 136.0909 | 140.854 | 145.7839 | 150.8864 | 156.1674 | 161.6332 | 167.2904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.7935 | 71.2013 | 74.5828 | 76.8644 | 79.5547 | 82.3391 | 85.2209 | 88.2037 | 91.2908 | 94.486 | 97.793 | 101.2157 | 104.7583 | 108.4248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADMN_M | Administrative_Med | Labor |  | 0 | 0 | 119.1131 | 126.7627 | 130.6923 | 134.7438 | 138.9209 | 143.2274 | 147.6675 | 152.2451 | 156.9647 | 161.8306 | 166.8474 | 172.0197 | 177.3523 | 182.8502 | 188.5186 | 0 | 0 | 0 | 0 | 0 | 131.8931 | 137.579 | 141.8439 | 146.2411 | 150.7746 | 155.4486 | 160.2675 | 165.2358 | 170.3581 | 175.6392 | 181.084 | 186.6976 | 192.4853 | 198.4523 | 204.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 79.1107 | 81.5631 | 84.0916 | 86.6984 | 89.3861 | 92.157 | 95.0139 | 97.9593 | 100.9961 | 104.127 | 107.3549 | 110.6829 | 114.1141 | 117.6516 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 72.5906 | 74.841 | 77.161 | 79.553 | 82.0192 | 84.5618 | 87.1832 | 89.8858 | 92.6723 | 95.5451 | 98.507 | 101.5608 | 104.7091 | 107.9551 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 0 | 82.4704 | 85.3568 | 88.3443 | 91.4364 | 94.6366 | 97.9489 | 101.3771 | 104.9253 | 108.5977 | 112.3986 | 116.3326 | 120.4042 | 124.6184 | 128.98 | 0 | 0 | 0 | 0 | 0 | 0 | 128.8988 | 133.4103 | 138.0796 | 142.9124 | 147.9143 | 153.0913 | 158.4495 | 163.9953 | 169.7351 | 175.6758 | 181.8245 | 188.1884 | 194.7749 | 201.5921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.8992 | 85.8006 | 89.8754 | 92.6249 | 95.8668 | 99.2221 | 102.6949 | 106.2892 | 110.0093 | 113.8596 | 117.8447 | 121.9693 | 126.2382 | 130.6565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADMN_H | Administrative_High | Labor |  | 0 | 0 | 176.3049 | 187.6274 | 193.4439 | 199.4406 | 205.6233 | 211.9976 | 218.5695 | 225.3452 | 232.3309 | 239.5331 | 246.9587 | 254.6144 | 262.5074 | 270.6452 | 279.0352 | 0 | 0 | 0 | 0 | 0 | 195.2212 | 203.6371 | 209.9499 | 216.4583 | 223.1685 | 230.0868 | 237.2194 | 244.5733 | 252.155 | 259.9718 | 268.031 | 276.3399 | 284.9065 | 293.7386 | 302.8444 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 117.0954 | 120.7254 | 124.4679 | 128.3264 | 132.3045 | 136.406 | 140.6345 | 144.9942 | 149.489 | 154.1232 | 158.901 | 163.8269 | 168.9056 | 174.1417 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 107.4448 | 110.7756 | 114.2097 | 117.7502 | 121.4004 | 125.1638 | 129.0439 | 133.0443 | 137.1686 | 141.4209 | 145.8049 | 150.3249 | 154.9849 | 159.7895 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 121.1321 | 125.3717 | 129.7597 | 134.3013 | 139.0018 | 143.8669 | 148.9022 | 154.1138 | 159.5078 | 165.0906 | 170.8688 | 176.8492 | 183.0389 | 189.4452 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3259 | 195.9524 | 202.8107 | 209.9091 | 217.2559 | 224.8598 | 232.7299 | 240.8755 | 249.3061 | 258.0318 | 267.0629 | 276.4102 | 286.0845 | 296.0975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.7619 | 126.0235 | 132.0086 | 136.047 | 140.8086 | 145.7369 | 150.8377 | 156.117 | 161.5811 | 167.2365 | 173.0897 | 179.1479 | 185.4181 | 191.9077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BUSOP_L | Business Ops_Low | Labor |  | 0 | 0 | 119.1131 | 126.7627 | 130.6923 | 134.7438 | 138.9209 | 143.2274 | 147.6675 | 152.2451 | 156.9647 | 161.8306 | 166.8474 | 172.0197 | 177.3523 | 182.8502 | 188.5186 | 0 | 0 | 0 | 0 | 0 | 131.8931 | 137.579 | 141.8439 | 146.2411 | 150.7746 | 155.4486 | 160.2675 | 165.2358 | 170.3581 | 175.6392 | 181.084 | 186.6976 | 192.4853 | 198.4523 | 204.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 79.1107 | 81.5631 | 84.0916 | 86.6984 | 89.3861 | 92.157 | 95.0139 | 97.9593 | 100.9961 | 104.127 | 107.3549 | 110.6829 | 114.1141 | 117.6516 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 72.5906 | 74.841 | 77.161 | 79.553 | 82.0192 | 84.5618 | 87.1832 | 89.8858 | 92.6723 | 95.5451 | 98.507 | 101.5608 | 104.7091 | 107.9551 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 0 | 82.4704 | 85.3568 | 88.3443 | 91.4364 | 94.6366 | 97.9489 | 101.3771 | 104.9253 | 108.5977 | 112.3986 | 116.3326 | 120.4042 | 124.6184 | 128.98 | 0 | 0 | 0 | 0 | 0 | 0 | 128.8988 | 133.4103 | 138.0796 | 142.9124 | 147.9143 | 153.0913 | 158.4495 | 163.9953 | 169.7351 | 175.6758 | 181.8245 | 188.1884 | 194.7749 | 201.5921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.8992 | 85.8006 | 89.8754 | 92.6249 | 95.8668 | 99.2221 | 102.6949 | 106.2892 | 110.0093 | 113.8596 | 117.8447 | 121.9693 | 126.2382 | 130.6565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BUSOP_M | Business Ops_Med | Labor |  | 0 | 0 | 176.3049 | 187.6274 | 193.4439 | 199.4406 | 205.6233 | 211.9976 | 218.5695 | 225.3452 | 232.3309 | 239.5331 | 246.9587 | 254.6144 | 262.5074 | 270.6452 | 279.0352 | 0 | 0 | 0 | 0 | 0 | 195.2212 | 203.6371 | 209.9499 | 216.4583 | 223.1685 | 230.0868 | 237.2194 | 244.5733 | 252.155 | 259.9718 | 268.031 | 276.3399 | 284.9065 | 293.7386 | 302.8444 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 117.0954 | 120.7254 | 124.4679 | 128.3264 | 132.3045 | 136.406 | 140.6345 | 144.9942 | 149.489 | 154.1232 | 158.901 | 163.8269 | 168.9056 | 174.1417 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 107.4448 | 110.7756 | 114.2097 | 117.7502 | 121.4004 | 125.1638 | 129.0439 | 133.0443 | 137.1686 | 141.4209 | 145.8049 | 150.3249 | 154.9849 | 159.7895 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 121.1321 | 125.3717 | 129.7597 | 134.3013 | 139.0018 | 143.8669 | 148.9022 | 154.1138 | 159.5078 | 165.0906 | 170.8688 | 176.8492 | 183.0389 | 189.4452 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3259 | 195.9524 | 202.8107 | 209.9091 | 217.2559 | 224.8598 | 232.7299 | 240.8755 | 249.3061 | 258.0318 | 267.0629 | 276.4102 | 286.0845 | 296.0975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.7619 | 126.0235 | 132.0086 | 136.047 | 140.8086 | 145.7369 | 150.8377 | 156.117 | 161.5811 | 167.2365 | 173.0897 | 179.1479 | 185.4181 | 191.9077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BUSOP_H | Business Ops_High | Labor |  | 0 | 0 | 304.1082 | 323.6385 | 333.6713 | 344.0151 | 354.6796 | 365.6746 | 377.0105 | 388.6979 | 400.7475 | 413.1707 | 425.979 | 439.1843 | 452.799 | 466.8358 | 481.3077 | 0 | 0 | 0 | 0 | 0 | 336.737 | 351.2537 | 362.1425 | 373.3689 | 384.9434 | 396.8766 | 409.1798 | 421.8644 | 434.9422 | 448.4254 | 462.3266 | 476.6587 | 491.4351 | 506.6696 | 522.3763 | 0 | 0 | 0 | 0 | 0 | 0 | 208.8746 | 215.1409 | 221.5951 | 228.2429 | 235.0902 | 242.1429 | 249.4072 | 256.8894 | 264.5961 | 272.534 | 280.71 | 289.1313 | 297.8053 | 306.7394 | 0 | 0 | 0 | 0 | 0 | 0 | 208.8746 | 215.1409 | 221.5951 | 228.2429 | 235.0902 | 242.1429 | 249.4072 | 256.8894 | 264.5961 | 272.534 | 280.71 | 289.1313 | 297.8053 | 306.7394 | 0 | 0 | 0 | 0 | 0 | 201.8316 | 204.2731 | 210.6056 | 217.1344 | 223.8655 | 230.8054 | 237.9603 | 245.3371 | 252.9426 | 260.7838 | 268.8681 | 277.203 | 285.7963 | 294.656 | 303.7903 | 0 | 0 | 0 | 0 | 0 | 199.5638 | 201.9779 | 208.2392 | 214.6947 | 221.3502 | 228.212 | 235.2866 | 242.5805 | 250.1005 | 257.8536 | 265.8471 | 274.0883 | 282.5851 | 291.3452 | 300.3769 | 0 | 0 | 0 | 0 | 0 | 199.5638 | 185.3315 | 191.0768 | 197.0002 | 203.1072 | 209.4035 | 215.895 | 222.5878 | 229.488 | 236.6021 | 243.9368 | 251.4989 | 259.2953 | 267.3335 | 275.6208 | 0 | 0 | 0 | 0 | 0 | 201.8316 | 204.2731 | 210.6056 | 217.1344 | 223.8655 | 230.8054 | 237.9603 | 245.3371 | 252.9426 | 260.7838 | 268.8681 | 277.203 | 285.7963 | 294.656 | 303.7903 | 0 | 0 | 0 | 0 | 0 | 0 | 217.6438 | 225.2613 | 233.1454 | 241.3055 | 249.7512 | 258.4925 | 267.5398 | 276.9037 | 286.5953 | 296.6261 | 307.008 | 317.7533 | 328.8747 | 340.3853 | 0 | 0 | 0 | 0 | 0 | 0 | 340.171 | 352.0769 | 364.3996 | 377.1536 | 390.354 | 404.0164 | 418.157 | 432.7925 | 447.9402 | 463.6181 | 479.8447 | 496.6393 | 514.0217 | 532.0124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218.7754 | 226.4325 | 237.1861 | 244.4421 | 252.9976 | 261.8525 | 271.0173 | 280.5029 | 290.3205 | 300.4817 | 310.9986 | 321.8836 | 333.1495 | 344.8097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROC_L | Procurement_Low | Labor |  | 0 | 0 | 119.1131 | 126.7627 | 130.6923 | 134.7438 | 138.9209 | 143.2274 | 147.6675 | 152.2451 | 156.9647 | 161.8306 | 166.8474 | 172.0197 | 177.3523 | 182.8502 | 188.5186 | 0 | 0 | 0 | 0 | 0 | 131.8931 | 137.579 | 141.8439 | 146.2411 | 150.7746 | 155.4486 | 160.2675 | 165.2358 | 170.3581 | 175.6392 | 181.084 | 186.6976 | 192.4853 | 198.4523 | 204.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 79.1107 | 81.5631 | 84.0916 | 86.6984 | 89.3861 | 92.157 | 95.0139 | 97.9593 | 100.9961 | 104.127 | 107.3549 | 110.6829 | 114.1141 | 117.6516 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 72.5906 | 74.841 | 77.161 | 79.553 | 82.0192 | 84.5618 | 87.1832 | 89.8858 | 92.6723 | 95.5451 | 98.507 | 101.5608 | 104.7091 | 107.9551 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 0 | 82.4704 | 85.3568 | 88.3443 | 91.4364 | 94.6366 | 97.9489 | 101.3771 | 104.9253 | 108.5977 | 112.3986 | 116.3326 | 120.4042 | 124.6184 | 128.98 | 0 | 0 | 0 | 0 | 0 | 0 | 128.8988 | 133.4103 | 138.0796 | 142.9124 | 147.9143 | 153.0913 | 158.4495 | 163.9953 | 169.7351 | 175.6758 | 181.8245 | 188.1884 | 194.7749 | 201.5921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.8992 | 85.8006 | 89.8754 | 92.6249 | 95.8668 | 99.2221 | 102.6949 | 106.2892 | 110.0093 | 113.8596 | 117.8447 | 121.9693 | 126.2382 | 130.6565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROC_M | Procurement_Med | Labor |  | 0 | 0 | 176.3049 | 187.6274 | 193.4439 | 199.4406 | 205.6233 | 211.9976 | 218.5695 | 225.3452 | 232.3309 | 239.5331 | 246.9587 | 254.6144 | 262.5074 | 270.6452 | 279.0352 | 0 | 0 | 0 | 0 | 0 | 195.2212 | 203.6371 | 209.9499 | 216.4583 | 223.1685 | 230.0868 | 237.2194 | 244.5733 | 252.155 | 259.9718 | 268.031 | 276.3399 | 284.9065 | 293.7386 | 302.8444 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 117.0954 | 120.7254 | 124.4679 | 128.3264 | 132.3045 | 136.406 | 140.6345 | 144.9942 | 149.489 | 154.1232 | 158.901 | 163.8269 | 168.9056 | 174.1417 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 107.4448 | 110.7756 | 114.2097 | 117.7502 | 121.4004 | 125.1638 | 129.0439 | 133.0443 | 137.1686 | 141.4209 | 145.8049 | 150.3249 | 154.9849 | 159.7895 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 121.1321 | 125.3717 | 129.7597 | 134.3013 | 139.0018 | 143.8669 | 148.9022 | 154.1138 | 159.5078 | 165.0906 | 170.8688 | 176.8492 | 183.0389 | 189.4452 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3259 | 195.9524 | 202.8107 | 209.9091 | 217.2559 | 224.8598 | 232.7299 | 240.8755 | 249.3061 | 258.0318 | 267.0629 | 276.4102 | 286.0845 | 296.0975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.7619 | 126.0235 | 132.0086 | 136.047 | 140.8086 | 145.7369 | 150.8377 | 156.117 | 161.5811 | 167.2365 | 173.0897 | 179.1479 | 185.4181 | 191.9077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROC_H | Procurement_High | Labor |  | 0 | 0 | 231.2839 | 246.1372 | 253.7675 | 261.6343 | 269.7449 | 278.107 | 286.7283 | 295.6169 | 304.781 | 314.2292 | 323.9703 | 334.0134 | 344.3678 | 355.0432 | 366.0496 | 0 | 0 | 0 | 0 | 0 | 256.0991 | 267.1394 | 275.4207 | 283.9588 | 292.7615 | 301.8371 | 311.1941 | 320.8411 | 330.7871 | 341.0415 | 351.6138 | 362.5139 | 373.7518 | 385.3381 | 397.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 159.016 | 163.7864 | 168.7 | 173.761 | 178.9739 | 184.3431 | 189.8734 | 195.5696 | 201.4367 | 207.4798 | 213.7042 | 220.1153 | 226.7187 | 233.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 159.016 | 163.7864 | 168.7 | 173.761 | 178.9739 | 184.3431 | 189.8734 | 195.5696 | 201.4367 | 207.4798 | 213.7042 | 220.1153 | 226.7187 | 233.5203 | 0 | 0 | 0 | 0 | 0 | 153.4993 | 155.3561 | 160.1722 | 165.1375 | 170.2568 | 175.5347 | 180.9763 | 186.5866 | 192.3707 | 198.3342 | 204.4826 | 210.8216 | 217.357 | 224.0951 | 231.042 | 0 | 0 | 0 | 0 | 0 | 151.7746 | 153.6105 | 158.3725 | 163.282 | 168.3438 | 173.5624 | 178.9428 | 184.4901 | 190.2093 | 196.1058 | 202.185 | 208.4528 | 214.9148 | 221.5772 | 228.4461 | 0 | 0 | 0 | 0 | 0 | 151.7746 | 140.9505 | 145.3199 | 149.8248 | 154.4694 | 159.258 | 164.195 | 169.285 | 174.5328 | 179.9433 | 185.5216 | 191.2728 | 197.2022 | 203.3155 | 209.6183 | 0 | 0 | 0 | 0 | 0 | 153.4993 | 155.3561 | 160.1722 | 165.1375 | 170.2568 | 175.5347 | 180.9763 | 186.5866 | 192.3707 | 198.3342 | 204.4826 | 210.8216 | 217.357 | 224.0951 | 231.042 | 0 | 0 | 0 | 0 | 0 | 0 | 160.1788 | 165.7851 | 171.5875 | 177.5931 | 183.8089 | 190.2422 | 196.9006 | 203.7922 | 210.9249 | 218.3073 | 225.948 | 233.8562 | 242.0412 | 250.5126 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3549 | 259.1173 | 268.1864 | 277.5729 | 287.288 | 297.343 | 307.75 | 318.5213 | 329.6695 | 341.208 | 353.1503 | 365.5105 | 378.3034 | 391.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.0116 | 166.647 | 174.5613 | 179.9015 | 186.1981 | 192.715 | 199.46 | 206.4411 | 213.6665 | 221.1449 | 228.8849 | 236.8959 | 245.1873 | 253.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC_L | Project Controls_Low | Labor |  | 0 | 0 | 119.1131 | 126.7627 | 130.6923 | 134.7438 | 138.9209 | 143.2274 | 147.6675 | 152.2451 | 156.9647 | 161.8306 | 166.8474 | 172.0197 | 177.3523 | 182.8502 | 188.5186 | 0 | 0 | 0 | 0 | 0 | 131.8931 | 137.579 | 141.8439 | 146.2411 | 150.7746 | 155.4486 | 160.2675 | 165.2358 | 170.3581 | 175.6392 | 181.084 | 186.6976 | 192.4853 | 198.4523 | 204.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2404 | 83.6776 | 86.1879 | 88.7736 | 91.4368 | 94.1799 | 97.0053 | 99.9154 | 102.9129 | 106.0003 | 109.1803 | 112.4557 | 115.8294 | 119.3042 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 79.1107 | 81.5631 | 84.0916 | 86.6984 | 89.3861 | 92.157 | 95.0139 | 97.9593 | 100.9961 | 104.127 | 107.3549 | 110.6829 | 114.1141 | 117.6516 | 0 | 0 | 0 | 0 | 0 | 78.1651 | 72.5906 | 74.841 | 77.161 | 79.553 | 82.0192 | 84.5618 | 87.1832 | 89.8858 | 92.6723 | 95.5451 | 98.507 | 101.5608 | 104.7091 | 107.9551 | 0 | 0 | 0 | 0 | 0 | 79.0534 | 80.0097 | 82.49 | 85.0472 | 87.6836 | 90.4018 | 93.2043 | 96.0936 | 99.0725 | 102.1438 | 105.3102 | 108.5748 | 111.9407 | 115.4108 | 118.9886 | 0 | 0 | 0 | 0 | 0 | 0 | 82.4704 | 85.3568 | 88.3443 | 91.4364 | 94.6366 | 97.9489 | 101.3771 | 104.9253 | 108.5977 | 112.3986 | 116.3326 | 120.4042 | 124.6184 | 128.98 | 0 | 0 | 0 | 0 | 0 | 0 | 128.8988 | 133.4103 | 138.0796 | 142.9124 | 147.9143 | 153.0913 | 158.4495 | 163.9953 | 169.7351 | 175.6758 | 181.8245 | 188.1884 | 194.7749 | 201.5921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.8992 | 85.8006 | 89.8754 | 92.6249 | 95.8668 | 99.2221 | 102.6949 | 106.2892 | 110.0093 | 113.8596 | 117.8447 | 121.9693 | 126.2382 | 130.6565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC_M | Project Controls_Med | Labor |  | 0 | 0 | 176.3049 | 187.6274 | 193.4439 | 199.4406 | 205.6233 | 211.9976 | 218.5695 | 225.3452 | 232.3309 | 239.5331 | 246.9587 | 254.6144 | 262.5074 | 270.6452 | 279.0352 | 0 | 0 | 0 | 0 | 0 | 195.2212 | 203.6371 | 209.9499 | 216.4583 | 223.1685 | 230.0868 | 237.2194 | 244.5733 | 252.155 | 259.9718 | 268.031 | 276.3399 | 284.9065 | 293.7386 | 302.8444 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 119.9939 | 123.5937 | 127.3015 | 131.1206 | 135.0542 | 139.1058 | 143.279 | 147.5774 | 152.0047 | 156.5648 | 161.2618 | 166.0996 | 171.0826 | 176.2151 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 117.0954 | 120.7254 | 124.4679 | 128.3264 | 132.3045 | 136.406 | 140.6345 | 144.9942 | 149.489 | 154.1232 | 158.901 | 163.8269 | 168.9056 | 174.1417 | 0 | 0 | 0 | 0 | 0 | 115.6959 | 107.4448 | 110.7756 | 114.2097 | 117.7502 | 121.4004 | 125.1638 | 129.0439 | 133.0443 | 137.1686 | 141.4209 | 145.8049 | 150.3249 | 154.9849 | 159.7895 | 0 | 0 | 0 | 0 | 0 | 117.0106 | 118.4261 | 122.0973 | 125.8823 | 129.7847 | 133.808 | 137.956 | 142.2327 | 146.6419 | 151.1878 | 155.8746 | 160.7067 | 165.6886 | 170.825 | 176.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 121.1321 | 125.3717 | 129.7597 | 134.3013 | 139.0018 | 143.8669 | 148.9022 | 154.1138 | 159.5078 | 165.0906 | 170.8688 | 176.8492 | 183.0389 | 189.4452 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3259 | 195.9524 | 202.8107 | 209.9091 | 217.2559 | 224.8598 | 232.7299 | 240.8755 | 249.3061 | 258.0318 | 267.0629 | 276.4102 | 286.0845 | 296.0975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.7619 | 126.0235 | 132.0086 | 136.047 | 140.8086 | 145.7369 | 150.8377 | 156.117 | 161.5811 | 167.2365 | 173.0897 | 179.1479 | 185.4181 | 191.9077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC_H | Project Controls_High | Labor |  | 0 | 0 | 231.2839 | 246.1372 | 253.7675 | 261.6343 | 269.7449 | 278.107 | 286.7283 | 295.6169 | 304.781 | 314.2292 | 323.9703 | 334.0134 | 344.3678 | 355.0432 | 366.0496 | 0 | 0 | 0 | 0 | 0 | 256.0991 | 267.1394 | 275.4207 | 283.9588 | 292.7615 | 301.8371 | 311.1941 | 320.8411 | 330.7871 | 341.0415 | 351.6138 | 362.5139 | 373.7518 | 385.3381 | 397.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 159.016 | 163.7864 | 168.7 | 173.761 | 178.9739 | 184.3431 | 189.8734 | 195.5696 | 201.4367 | 207.4798 | 213.7042 | 220.1153 | 226.7187 | 233.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 159.016 | 163.7864 | 168.7 | 173.761 | 178.9739 | 184.3431 | 189.8734 | 195.5696 | 201.4367 | 207.4798 | 213.7042 | 220.1153 | 226.7187 | 233.5203 | 0 | 0 | 0 | 0 | 0 | 153.4993 | 155.3561 | 160.1722 | 165.1375 | 170.2568 | 175.5347 | 180.9763 | 186.5866 | 192.3707 | 198.3342 | 204.4826 | 210.8216 | 217.357 | 224.0951 | 231.042 | 0 | 0 | 0 | 0 | 0 | 151.7746 | 153.6105 | 158.3725 | 163.282 | 168.3438 | 173.5624 | 178.9428 | 184.4901 | 190.2093 | 196.1058 | 202.185 | 208.4528 | 214.9148 | 221.5772 | 228.4461 | 0 | 0 | 0 | 0 | 0 | 151.7746 | 140.9505 | 145.3199 | 149.8248 | 154.4694 | 159.258 | 164.195 | 169.285 | 174.5328 | 179.9433 | 185.5216 | 191.2728 | 197.2022 | 203.3155 | 209.6183 | 0 | 0 | 0 | 0 | 0 | 153.4993 | 155.3561 | 160.1722 | 165.1375 | 170.2568 | 175.5347 | 180.9763 | 186.5866 | 192.3707 | 198.3342 | 204.4826 | 210.8216 | 217.357 | 224.0951 | 231.042 | 0 | 0 | 0 | 0 | 0 | 0 | 160.1788 | 165.7851 | 171.5875 | 177.5931 | 183.8089 | 190.2422 | 196.9006 | 203.7922 | 210.9249 | 218.3073 | 225.948 | 233.8562 | 242.0412 | 250.5126 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3549 | 259.1173 | 268.1864 | 277.5729 | 287.288 | 297.343 | 307.75 | 318.5213 | 329.6695 | 341.208 | 353.1503 | 365.5105 | 378.3034 | 391.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.0116 | 166.647 | 174.5613 | 179.9015 | 186.1981 | 192.715 | 199.46 | 206.4411 | 213.6665 | 221.1449 | 228.8849 | 236.8959 | 245.1873 | 253.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OPTR_L | Operators_Low | Labor |  | 0 | 0 | 102.9641 | 109.5765 | 112.9734 | 116.4756 | 120.0863 | 123.809 | 127.6471 | 131.6042 | 135.6839 | 139.8901 | 144.2267 | 148.6977 | 153.3073 | 158.0599 | 162.9597 | 0 | 0 | 0 | 0 | 0 | 114.0114 | 118.9264 | 122.6131 | 126.4141 | 130.333 | 134.3733 | 138.5389 | 142.8336 | 147.2614 | 151.8265 | 156.5331 | 161.3857 | 166.3886 | 171.5467 | 176.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 69.1872 | 71.2628 | 73.4007 | 75.6027 | 77.8708 | 80.2069 | 82.6131 | 85.0915 | 87.6442 | 90.2736 | 92.9818 | 95.7712 | 98.6443 | 101.6037 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 68.3851 | 70.505 | 72.6907 | 74.9441 | 77.2674 | 79.6626 | 82.1322 | 84.6783 | 87.3033 | 90.0097 | 92.8 | 95.6768 | 98.6428 | 101.7007 | 0 | 0 | 0 | 0 | 0 | 67.5677 | 62.749 | 64.6942 | 66.6997 | 68.7674 | 70.8992 | 73.0971 | 75.3631 | 77.6994 | 80.108 | 82.5914 | 85.1517 | 87.7914 | 90.513 | 93.3189 | 0 | 0 | 0 | 0 | 0 | 68.3355 | 69.1622 | 71.3062 | 73.5167 | 75.7957 | 78.1454 | 80.5679 | 83.0655 | 85.6405 | 88.2954 | 91.0325 | 93.8546 | 96.764 | 99.7637 | 102.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5186 | 72.9868 | 75.5413 | 78.1853 | 80.9217 | 83.754 | 86.6854 | 89.7194 | 92.8596 | 96.1097 | 99.4735 | 102.9551 | 106.5585 | 110.288 | 0 | 0 | 0 | 0 | 0 | 0 | 110.2186 | 114.0762 | 118.0689 | 122.2013 | 126.4784 | 130.9051 | 135.4868 | 140.2288 | 145.1368 | 150.2166 | 155.4742 | 160.9158 | 166.5479 | 172.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8853 | 73.3663 | 76.8505 | 79.2015 | 81.9736 | 84.8427 | 87.8122 | 90.8856 | 94.0666 | 97.3589 | 100.7665 | 104.2933 | 107.9436 | 111.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OPTR_M | Operators_Med | Labor |  | 0 | 0 | 150.9888 | 160.6855 | 165.6667 | 170.8024 | 176.0973 | 181.5563 | 187.1845 | 192.9872 | 198.9699 | 205.1379 | 211.4972 | 218.0536 | 224.8133 | 231.7825 | 238.9677 | 0 | 0 | 0 | 0 | 0 | 167.1889 | 174.3963 | 179.8026 | 185.3765 | 191.1232 | 197.048 | 203.1565 | 209.4543 | 215.9474 | 222.6418 | 229.5437 | 236.6595 | 243.996 | 251.5598 | 259.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 102.4363 | 105.5094 | 108.6746 | 111.9349 | 115.2929 | 118.7517 | 122.3143 | 125.9837 | 129.7632 | 133.6561 | 137.6658 | 141.7958 | 146.0496 | 150.4311 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 100.2814 | 103.3901 | 106.5952 | 109.8997 | 113.3066 | 116.8191 | 120.4404 | 124.1741 | 128.0235 | 131.9922 | 136.084 | 140.3026 | 144.652 | 149.1362 | 0 | 0 | 0 | 0 | 0 | 99.0828 | 92.0165 | 94.869 | 97.81 | 100.8421 | 103.9682 | 107.1912 | 110.5141 | 113.9401 | 117.4722 | 121.1138 | 124.8684 | 128.7393 | 132.7302 | 136.8449 | 0 | 0 | 0 | 0 | 0 | 100.2087 | 101.421 | 104.565 | 107.8065 | 111.1485 | 114.5941 | 118.1465 | 121.8091 | 125.5852 | 129.4783 | 133.4921 | 137.6304 | 141.8969 | 146.2957 | 150.8309 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8811 | 107.5169 | 111.28 | 115.1748 | 119.206 | 123.3782 | 127.6964 | 132.1658 | 136.7916 | 141.5793 | 146.5346 | 151.6633 | 156.9715 | 162.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 162.3632 | 168.0459 | 173.9275 | 180.015 | 186.3155 | 192.8365 | 199.5858 | 206.5713 | 213.8013 | 221.2843 | 229.0293 | 237.0453 | 245.3419 | 253.9289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4212 | 108.076 | 113.2086 | 116.6719 | 120.7554 | 124.9819 | 129.3562 | 133.8837 | 138.5696 | 143.4196 | 148.4392 | 153.6346 | 159.0118 | 164.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OPTR_H | Operators_High | Labor |  | 0 | 0 | 172.684 | 183.774 | 189.471 | 195.3446 | 201.4003 | 207.6437 | 214.0807 | 220.7172 | 227.5594 | 234.6138 | 241.8868 | 249.3853 | 257.1162 | 265.0868 | 273.3045 | 0 | 0 | 0 | 0 | 0 | 191.2119 | 199.455 | 205.6381 | 212.0129 | 218.5853 | 225.3614 | 232.3476 | 239.5504 | 246.9764 | 254.6327 | 262.5263 | 270.6646 | 279.0552 | 287.706 | 296.6248 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 117.3642 | 120.8851 | 124.5116 | 128.247 | 132.0944 | 136.0572 | 140.1389 | 144.3431 | 148.6734 | 153.1336 | 157.7276 | 162.4594 | 167.3332 | 172.3532 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 114.6906 | 118.246 | 121.9117 | 125.6909 | 129.5873 | 133.6046 | 137.7463 | 142.0164 | 146.4189 | 150.9579 | 155.6376 | 160.4624 | 165.4367 | 170.5653 | 0 | 0 | 0 | 0 | 0 | 113.3198 | 105.2382 | 108.5006 | 111.8641 | 115.3319 | 118.9072 | 122.5933 | 126.3937 | 130.3119 | 134.3516 | 138.5165 | 142.8105 | 147.2376 | 151.802 | 156.5078 | 0 | 0 | 0 | 0 | 0 | 114.6075 | 115.9939 | 119.5897 | 123.297 | 127.1192 | 131.0599 | 135.1228 | 139.3116 | 143.6303 | 148.0828 | 152.6734 | 157.4062 | 162.2858 | 167.3167 | 172.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 118.6801 | 122.8339 | 127.1331 | 131.5828 | 136.1882 | 140.9547 | 145.8882 | 150.9942 | 156.279 | 161.7488 | 167.41 | 173.2694 | 179.3338 | 185.6105 | 0 | 0 | 0 | 0 | 0 | 0 | 185.4936 | 191.9859 | 198.7054 | 205.6601 | 212.8582 | 220.3082 | 228.019 | 235.9997 | 244.2597 | 252.8087 | 261.657 | 270.815 | 280.2936 | 290.1038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.2972 | 123.4726 | 129.3364 | 133.2931 | 137.9584 | 142.7869 | 147.7844 | 152.9569 | 158.3104 | 163.8513 | 169.5861 | 175.5216 | 181.6648 | 188.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ASPHY | Associate Physicist | Labor |  | 0 | 0 | 164.4796 | 175.0427 | 180.4691 | 186.0636 | 191.8316 | 197.7784 | 203.9095 | 210.2307 | 216.7478 | 223.467 | 230.3945 | 237.5367 | 244.9004 | 252.4923 | 260.3195 | 0 | 0 | 0 | 0 | 0 | 182.1272 | 189.9786 | 195.868 | 201.9399 | 208.2 | 214.6542 | 221.3085 | 228.1691 | 235.2423 | 242.5348 | 250.0534 | 257.8051 | 265.797 | 274.0367 | 282.5319 | 0 | 0 | 0 | 0 | 0 | 0 | 112.4112 | 115.7835 | 119.257 | 122.8347 | 126.5197 | 130.3153 | 134.2248 | 138.2515 | 142.3991 | 146.6711 | 151.0712 | 155.6033 | 160.2714 | 165.0796 | 0 | 0 | 0 | 0 | 0 | 0 | 112.4112 | 115.7835 | 119.257 | 122.8347 | 126.5197 | 130.3153 | 134.2248 | 138.2515 | 142.3991 | 146.6711 | 151.0712 | 155.6033 | 160.2714 | 165.0796 | 0 | 0 | 0 | 0 | 0 | 109.1624 | 110.4829 | 113.9079 | 117.439 | 121.0797 | 124.8331 | 128.703 | 132.6927 | 136.8062 | 141.0472 | 145.4197 | 149.9277 | 154.5754 | 159.3673 | 164.3077 | 0 | 0 | 0 | 0 | 0 | 107.9359 | 109.2415 | 112.628 | 116.1195 | 119.7192 | 123.4305 | 127.2569 | 131.2018 | 135.2691 | 139.4624 | 143.7857 | 148.2431 | 152.8386 | 157.5766 | 162.4615 | 0 | 0 | 0 | 0 | 0 | 107.9359 | 100.2382 | 103.3456 | 106.5493 | 109.8523 | 113.2578 | 116.7687 | 120.3886 | 124.1206 | 127.9684 | 131.9354 | 136.0254 | 140.2422 | 144.5897 | 149.072 | 0 | 0 | 0 | 0 | 0 | 109.1624 | 110.4829 | 113.9079 | 117.439 | 121.0797 | 124.8331 | 128.703 | 132.6927 | 136.8062 | 141.0472 | 145.4197 | 149.9277 | 154.5754 | 159.3673 | 164.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 112.9866 | 116.9411 | 121.034 | 125.2702 | 129.6547 | 134.1926 | 138.8893 | 143.7505 | 148.7817 | 153.9891 | 159.3787 | 164.957 | 170.7304 | 176.706 | 0 | 0 | 0 | 0 | 0 | 0 | 176.5947 | 182.7756 | 189.1727 | 195.7938 | 202.6465 | 209.7392 | 217.08 | 224.6778 | 232.5416 | 240.6805 | 249.1043 | 257.823 | 266.8468 | 276.1864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.574 | 117.5491 | 123.1317 | 126.8985 | 131.34 | 135.9369 | 140.6946 | 145.619 | 150.7156 | 155.9907 | 161.4503 | 167.1011 | 172.9496 | 179.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHEMAS | Chemistry Associate | Labor |  | 0 | 0 | 137.1672 | 145.9762 | 150.5015 | 155.167 | 159.9772 | 164.9365 | 170.0495 | 175.3211 | 180.756 | 186.3595 | 192.1366 | 198.0929 | 204.2337 | 210.565 | 217.0925 | 0 | 0 | 0 | 0 | 0 | 151.8843 | 158.432 | 163.3434 | 168.407 | 173.6276 | 179.0101 | 184.5594 | 190.2807 | 196.1794 | 202.261 | 208.5311 | 214.9956 | 221.6604 | 228.5319 | 235.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 91.1016 | 93.9257 | 96.8374 | 99.8394 | 102.9344 | 106.1254 | 109.4153 | 112.8071 | 116.3042 | 119.9096 | 123.6268 | 127.4592 | 131.4104 | 135.4842 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 83.5933 | 86.1847 | 88.8564 | 91.6109 | 94.4509 | 97.3789 | 100.3976 | 103.5099 | 106.7187 | 110.027 | 113.4379 | 116.9544 | 120.58 | 124.318 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 94.9162 | 98.2383 | 101.6766 | 105.2353 | 108.9185 | 112.7307 | 116.6763 | 120.7599 | 124.9865 | 129.3611 | 133.8887 | 138.5748 | 143.4249 | 148.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3513 | 153.5436 | 158.9176 | 164.4798 | 170.2366 | 176.1948 | 182.3617 | 188.7443 | 195.3504 | 202.1876 | 209.2642 | 216.5884 | 224.169 | 232.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.4097 | 98.7491 | 103.4388 | 106.6032 | 110.3343 | 114.196 | 118.1929 | 122.3296 | 126.6111 | 131.0425 | 135.629 | 140.376 | 145.2892 | 150.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MEDAS | Medical Associate | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RACHEM_L | Research Associate Chemistry_Low | Labor |  | 0 | 0 | 85.4014 | 90.886 | 93.7035 | 96.6083 | 99.6032 | 102.6909 | 105.8743 | 109.1564 | 112.5402 | 116.029 | 119.6259 | 123.3343 | 127.1576 | 131.0995 | 135.1636 | 0 | 0 | 0 | 0 | 0 | 94.5644 | 98.6411 | 101.6989 | 104.8516 | 108.102 | 111.4532 | 114.9082 | 118.4704 | 122.143 | 125.9294 | 129.8332 | 133.858 | 138.0076 | 142.2859 | 146.6967 | 0 | 0 | 0 | 0 | 0 | 0 | 58.1903 | 59.936 | 61.734 | 63.5861 | 65.4936 | 67.4585 | 69.4822 | 71.5667 | 73.7137 | 75.9251 | 78.2028 | 80.5489 | 82.9654 | 85.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 58.1903 | 59.936 | 61.734 | 63.5861 | 65.4936 | 67.4585 | 69.4822 | 71.5667 | 73.7137 | 75.9251 | 78.2028 | 80.5489 | 82.9654 | 85.4543 | 0 | 0 | 0 | 0 | 0 | 56.6795 | 57.3652 | 59.1435 | 60.9769 | 62.8672 | 64.8161 | 66.8254 | 68.897 | 71.0328 | 73.2348 | 75.5051 | 77.8457 | 80.259 | 82.747 | 85.3121 | 0 | 0 | 0 | 0 | 0 | 56.0427 | 56.7206 | 58.4789 | 60.2918 | 62.1608 | 64.0878 | 66.0745 | 68.1229 | 70.2347 | 72.4119 | 74.6567 | 76.9711 | 79.3572 | 81.8172 | 84.3536 | 0 | 0 | 0 | 0 | 0 | 56.0427 | 52.0459 | 53.6593 | 55.3227 | 57.0377 | 58.8059 | 60.6289 | 62.5084 | 64.4461 | 66.444 | 68.5037 | 70.6274 | 72.8168 | 75.0741 | 77.4014 | 0 | 0 | 0 | 0 | 0 | 56.6795 | 57.3652 | 59.1435 | 60.9769 | 62.8672 | 64.8161 | 66.8254 | 68.897 | 71.0328 | 73.2348 | 75.5051 | 77.8457 | 80.259 | 82.747 | 85.3121 | 0 | 0 | 0 | 0 | 0 | 0 | 57.4862 | 59.4982 | 61.5806 | 63.7359 | 65.9667 | 68.2755 | 70.6652 | 73.1385 | 75.6983 | 78.3478 | 81.0899 | 83.9281 | 86.8656 | 89.9058 | 0 | 0 | 0 | 0 | 0 | 0 | 89.8492 | 92.994 | 96.2487 | 99.6175 | 103.1041 | 106.7127 | 110.4477 | 114.3133 | 118.3143 | 122.4553 | 126.7412 | 131.1772 | 135.7684 | 140.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.7851 | 59.8075 | 62.6479 | 64.5644 | 66.8242 | 69.163 | 71.5837 | 74.0891 | 76.6823 | 79.3661 | 82.144 | 85.019 | 87.9947 | 91.0745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RACHEM_M | Research Associate Chemistry_Med | Labor |  | 0 | 0 | 89.5531 | 95.3043 | 98.2588 | 101.3048 | 104.4452 | 107.683 | 111.0212 | 114.4629 | 118.0112 | 121.6696 | 125.4413 | 129.33 | 133.3392 | 137.4728 | 141.7344 | 0 | 0 | 0 | 0 | 0 | 99.1616 | 103.4364 | 106.6429 | 109.9489 | 113.3573 | 116.8713 | 120.4944 | 124.2297 | 128.0808 | 132.0513 | 136.1449 | 140.3654 | 144.7167 | 149.2029 | 153.8282 | 0 | 0 | 0 | 0 | 0 | 0 | 62.3556 | 64.2262 | 66.153 | 68.1376 | 70.1817 | 72.2872 | 74.4558 | 76.6895 | 78.9901 | 81.3598 | 83.8006 | 86.3147 | 88.9041 | 91.5712 | 0 | 0 | 0 | 0 | 0 | 0 | 62.3556 | 64.2262 | 66.153 | 68.1376 | 70.1817 | 72.2872 | 74.4558 | 76.6895 | 78.9901 | 81.3598 | 83.8006 | 86.3147 | 88.9041 | 91.5712 | 0 | 0 | 0 | 0 | 0 | 59.4349 | 60.1539 | 62.0187 | 63.9412 | 65.9234 | 67.9671 | 70.074 | 72.2463 | 74.486 | 76.795 | 79.1757 | 81.6301 | 84.1607 | 86.7696 | 89.4595 | 0 | 0 | 0 | 0 | 0 | 58.7671 | 59.478 | 61.3218 | 63.2228 | 65.1827 | 67.2034 | 69.2867 | 71.4346 | 73.649 | 75.9322 | 78.2861 | 80.7129 | 83.215 | 85.7947 | 88.4543 | 0 | 0 | 0 | 0 | 0 | 58.7671 | 54.576 | 56.2679 | 58.0122 | 59.8106 | 61.6647 | 63.5763 | 65.5472 | 67.5791 | 69.6741 | 71.834 | 74.0608 | 76.3567 | 78.7238 | 81.1642 | 0 | 0 | 0 | 0 | 0 | 59.4349 | 60.1539 | 62.0187 | 63.9412 | 65.9234 | 67.9671 | 70.074 | 72.2463 | 74.486 | 76.795 | 79.1757 | 81.6301 | 84.1607 | 86.7696 | 89.4595 | 0 | 0 | 0 | 0 | 0 | 0 | 63.2389 | 65.4523 | 67.7431 | 70.1141 | 72.5681 | 75.108 | 77.7368 | 80.4576 | 83.2736 | 86.1882 | 89.2048 | 92.3269 | 95.5584 | 98.9029 | 0 | 0 | 0 | 0 | 0 | 0 | 98.8407 | 102.3001 | 105.8806 | 109.5864 | 113.4219 | 117.3917 | 121.5004 | 125.7529 | 130.1543 | 134.7097 | 139.4245 | 144.3044 | 149.355 | 154.5824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.5677 | 65.7926 | 68.9172 | 71.0255 | 73.5114 | 76.0843 | 78.7473 | 81.5034 | 84.356 | 87.3085 | 90.3643 | 93.527 | 96.8005 | 100.1885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RACHEM_H | Research Associate Chemistry_High | Labor |  | 0 | 0 | 96.6272 | 102.8327 | 106.0205 | 109.3071 | 112.6956 | 116.1892 | 119.7911 | 123.5046 | 127.3332 | 131.2806 | 135.3503 | 139.5461 | 143.8721 | 148.3321 | 152.9304 | 0 | 0 | 0 | 0 | 0 | 106.9946 | 111.6071 | 115.0669 | 118.634 | 122.3117 | 126.1033 | 130.0125 | 134.0429 | 138.1982 | 142.4824 | 146.8993 | 151.4532 | 156.1483 | 160.9889 | 165.9795 | 0 | 0 | 0 | 0 | 0 | 0 | 69.9103 | 72.0076 | 74.1678 | 76.3929 | 78.6846 | 81.0452 | 83.4765 | 85.9808 | 88.5603 | 91.2171 | 93.9536 | 96.7722 | 99.6754 | 102.6656 | 0 | 0 | 0 | 0 | 0 | 0 | 69.9103 | 72.0076 | 74.1678 | 76.3929 | 78.6846 | 81.0452 | 83.4765 | 85.9808 | 88.5603 | 91.2171 | 93.9536 | 96.7722 | 99.6754 | 102.6656 | 0 | 0 | 0 | 0 | 0 | 64.1298 | 64.9056 | 66.9177 | 68.9921 | 71.1309 | 73.3359 | 75.6094 | 77.9532 | 80.3698 | 82.8613 | 85.43 | 88.0783 | 90.8087 | 93.6238 | 96.5261 | 0 | 0 | 0 | 0 | 0 | 63.4093 | 64.1763 | 66.1658 | 68.2169 | 70.3317 | 72.5119 | 74.7598 | 77.0774 | 79.4668 | 81.9302 | 84.4701 | 87.0886 | 89.7884 | 92.5718 | 95.4416 | 0 | 0 | 0 | 0 | 0 | 63.4093 | 58.8871 | 60.7126 | 62.5947 | 64.5352 | 66.5357 | 68.5984 | 70.7249 | 72.9174 | 75.1778 | 77.5083 | 79.9111 | 82.3883 | 84.9424 | 87.5756 | 0 | 0 | 0 | 0 | 0 | 64.1298 | 64.9056 | 66.9177 | 68.9921 | 71.1309 | 73.3359 | 75.6094 | 77.9532 | 80.3698 | 82.8613 | 85.43 | 88.0783 | 90.8087 | 93.6238 | 96.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 80.9292 | 83.7617 | 86.6933 | 89.7276 | 92.8681 | 96.1184 | 99.4826 | 102.9645 | 106.5682 | 110.2981 | 114.1586 | 118.1541 | 122.2895 | 126.5696 | 0 | 0 | 0 | 0 | 0 | 0 | 126.4899 | 130.9171 | 135.4992 | 140.2417 | 145.1501 | 150.2304 | 155.4884 | 160.9305 | 166.5631 | 172.3928 | 178.4265 | 184.6715 | 191.135 | 197.8247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.3499 | 84.1972 | 88.1958 | 90.8939 | 94.0752 | 97.3678 | 100.7757 | 104.3028 | 107.9534 | 111.7318 | 115.6424 | 119.6899 | 123.8791 | 128.2148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAPHYS_L | Research Associate Physics_Low | Labor |  | 0 | 0 | 85.4014 | 90.886 | 93.7035 | 96.6083 | 99.6032 | 102.6909 | 105.8743 | 109.1564 | 112.5402 | 116.029 | 119.6259 | 123.3343 | 127.1576 | 131.0995 | 135.1636 | 0 | 0 | 0 | 0 | 0 | 94.5644 | 98.6411 | 101.6989 | 104.8516 | 108.102 | 111.4532 | 114.9082 | 118.4704 | 122.143 | 125.9294 | 129.8332 | 133.858 | 138.0076 | 142.2859 | 146.6967 | 0 | 0 | 0 | 0 | 0 | 0 | 58.1903 | 59.936 | 61.734 | 63.5861 | 65.4936 | 67.4585 | 69.4822 | 71.5667 | 73.7137 | 75.9251 | 78.2028 | 80.5489 | 82.9654 | 85.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 58.1903 | 59.936 | 61.734 | 63.5861 | 65.4936 | 67.4585 | 69.4822 | 71.5667 | 73.7137 | 75.9251 | 78.2028 | 80.5489 | 82.9654 | 85.4543 | 0 | 0 | 0 | 0 | 0 | 56.6795 | 57.3652 | 59.1435 | 60.9769 | 62.8672 | 64.8161 | 66.8254 | 68.897 | 71.0328 | 73.2348 | 75.5051 | 77.8457 | 80.259 | 82.747 | 85.3121 | 0 | 0 | 0 | 0 | 0 | 56.0427 | 56.7206 | 58.4789 | 60.2918 | 62.1608 | 64.0878 | 66.0745 | 68.1229 | 70.2347 | 72.4119 | 74.6567 | 76.9711 | 79.3572 | 81.8172 | 84.3536 | 0 | 0 | 0 | 0 | 0 | 56.0427 | 52.0459 | 53.6593 | 55.3227 | 57.0377 | 58.8059 | 60.6289 | 62.5084 | 64.4461 | 66.444 | 68.5037 | 70.6274 | 72.8168 | 75.0741 | 77.4014 | 0 | 0 | 0 | 0 | 0 | 56.6795 | 57.3652 | 59.1435 | 60.9769 | 62.8672 | 64.8161 | 66.8254 | 68.897 | 71.0328 | 73.2348 | 75.5051 | 77.8457 | 80.259 | 82.747 | 85.3121 | 0 | 0 | 0 | 0 | 0 | 0 | 57.4862 | 59.4982 | 61.5806 | 63.7359 | 65.9667 | 68.2755 | 70.6652 | 73.1385 | 75.6983 | 78.3478 | 81.0899 | 83.9281 | 86.8656 | 89.9058 | 0 | 0 | 0 | 0 | 0 | 0 | 89.8492 | 92.994 | 96.2487 | 99.6175 | 103.1041 | 106.7127 | 110.4477 | 114.3133 | 118.3143 | 122.4553 | 126.7412 | 131.1772 | 135.7684 | 140.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.7851 | 59.8075 | 62.6479 | 64.5644 | 66.8242 | 69.163 | 71.5837 | 74.0891 | 76.6823 | 79.3661 | 82.144 | 85.019 | 87.9947 | 91.0745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAPHYS_M | Research Associate Physics_Med | Labor |  | 0 | 0 | 89.5531 | 95.3043 | 98.2588 | 101.3048 | 104.4452 | 107.683 | 111.0212 | 114.4629 | 118.0112 | 121.6696 | 125.4413 | 129.33 | 133.3392 | 137.4728 | 141.7344 | 0 | 0 | 0 | 0 | 0 | 99.1616 | 103.4364 | 106.6429 | 109.9489 | 113.3573 | 116.8713 | 120.4944 | 124.2297 | 128.0808 | 132.0513 | 136.1449 | 140.3654 | 144.7167 | 149.2029 | 153.8282 | 0 | 0 | 0 | 0 | 0 | 0 | 62.3556 | 64.2262 | 66.153 | 68.1376 | 70.1817 | 72.2872 | 74.4558 | 76.6895 | 78.9901 | 81.3598 | 83.8006 | 86.3147 | 88.9041 | 91.5712 | 0 | 0 | 0 | 0 | 0 | 0 | 62.3556 | 64.2262 | 66.153 | 68.1376 | 70.1817 | 72.2872 | 74.4558 | 76.6895 | 78.9901 | 81.3598 | 83.8006 | 86.3147 | 88.9041 | 91.5712 | 0 | 0 | 0 | 0 | 0 | 59.4349 | 60.1539 | 62.0187 | 63.9412 | 65.9234 | 67.9671 | 70.074 | 72.2463 | 74.486 | 76.795 | 79.1757 | 81.6301 | 84.1607 | 86.7696 | 89.4595 | 0 | 0 | 0 | 0 | 0 | 58.7671 | 59.478 | 61.3218 | 63.2228 | 65.1827 | 67.2034 | 69.2867 | 71.4346 | 73.649 | 75.9322 | 78.2861 | 80.7129 | 83.215 | 85.7947 | 88.4543 | 0 | 0 | 0 | 0 | 0 | 58.7671 | 54.576 | 56.2679 | 58.0122 | 59.8106 | 61.6647 | 63.5763 | 65.5472 | 67.5791 | 69.6741 | 71.834 | 74.0608 | 76.3567 | 78.7238 | 81.1642 | 0 | 0 | 0 | 0 | 0 | 59.4349 | 60.1539 | 62.0187 | 63.9412 | 65.9234 | 67.9671 | 70.074 | 72.2463 | 74.486 | 76.795 | 79.1757 | 81.6301 | 84.1607 | 86.7696 | 89.4595 | 0 | 0 | 0 | 0 | 0 | 0 | 63.2389 | 65.4523 | 67.7431 | 70.1141 | 72.5681 | 75.108 | 77.7368 | 80.4576 | 83.2736 | 86.1882 | 89.2048 | 92.3269 | 95.5584 | 98.9029 | 0 | 0 | 0 | 0 | 0 | 0 | 98.8407 | 102.3001 | 105.8806 | 109.5864 | 113.4219 | 117.3917 | 121.5004 | 125.7529 | 130.1543 | 134.7097 | 139.4245 | 144.3044 | 149.355 | 154.5824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.5677 | 65.7926 | 68.9172 | 71.0255 | 73.5114 | 76.0843 | 78.7473 | 81.5034 | 84.356 | 87.3085 | 90.3643 | 93.527 | 96.8005 | 100.1885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAPHYS_H | Research Associate Physics_High | Labor |  | 0 | 0 | 96.6272 | 102.8327 | 106.0205 | 109.3071 | 112.6956 | 116.1892 | 119.7911 | 123.5046 | 127.3332 | 131.2806 | 135.3503 | 139.5461 | 143.8721 | 148.3321 | 152.9304 | 0 | 0 | 0 | 0 | 0 | 106.9946 | 111.6071 | 115.0669 | 118.634 | 122.3117 | 126.1033 | 130.0125 | 134.0429 | 138.1982 | 142.4824 | 146.8993 | 151.4532 | 156.1483 | 160.9889 | 165.9795 | 0 | 0 | 0 | 0 | 0 | 0 | 69.9103 | 72.0076 | 74.1678 | 76.3929 | 78.6846 | 81.0452 | 83.4765 | 85.9808 | 88.5603 | 91.2171 | 93.9536 | 96.7722 | 99.6754 | 102.6656 | 0 | 0 | 0 | 0 | 0 | 0 | 69.9103 | 72.0076 | 74.1678 | 76.3929 | 78.6846 | 81.0452 | 83.4765 | 85.9808 | 88.5603 | 91.2171 | 93.9536 | 96.7722 | 99.6754 | 102.6656 | 0 | 0 | 0 | 0 | 0 | 64.1298 | 64.9056 | 66.9177 | 68.9921 | 71.1309 | 73.3359 | 75.6094 | 77.9532 | 80.3698 | 82.8613 | 85.43 | 88.0783 | 90.8087 | 93.6238 | 96.5261 | 0 | 0 | 0 | 0 | 0 | 63.4093 | 64.1763 | 66.1658 | 68.2169 | 70.3317 | 72.5119 | 74.7598 | 77.0774 | 79.4668 | 81.9302 | 84.4701 | 87.0886 | 89.7884 | 92.5718 | 95.4416 | 0 | 0 | 0 | 0 | 0 | 63.4093 | 58.8871 | 60.7126 | 62.5947 | 64.5352 | 66.5357 | 68.5984 | 70.7249 | 72.9174 | 75.1778 | 77.5083 | 79.9111 | 82.3883 | 84.9424 | 87.5756 | 0 | 0 | 0 | 0 | 0 | 64.1298 | 64.9056 | 66.9177 | 68.9921 | 71.1309 | 73.3359 | 75.6094 | 77.9532 | 80.3698 | 82.8613 | 85.43 | 88.0783 | 90.8087 | 93.6238 | 96.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 80.9292 | 83.7617 | 86.6933 | 89.7276 | 92.8681 | 96.1184 | 99.4826 | 102.9645 | 106.5682 | 110.2981 | 114.1586 | 118.1541 | 122.2895 | 126.5696 | 0 | 0 | 0 | 0 | 0 | 0 | 126.4899 | 130.9171 | 135.4992 | 140.2417 | 145.1501 | 150.2304 | 155.4884 | 160.9305 | 166.5631 | 172.3928 | 178.4265 | 184.6715 | 191.135 | 197.8247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.3499 | 84.1972 | 88.1958 | 90.8939 | 94.0752 | 97.3678 | 100.7757 | 104.3028 | 107.9534 | 111.7318 | 115.6424 | 119.6899 | 123.8791 | 128.2148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIAS_L | Scientist Associate_Low | Labor |  | 0 | 0 | 137.1672 | 145.9762 | 150.5015 | 155.167 | 159.9772 | 164.9365 | 170.0495 | 175.3211 | 180.756 | 186.3595 | 192.1366 | 198.0929 | 204.2337 | 210.565 | 217.0925 | 0 | 0 | 0 | 0 | 0 | 151.8843 | 158.432 | 163.3434 | 168.407 | 173.6276 | 179.0101 | 184.5594 | 190.2807 | 196.1794 | 202.261 | 208.5311 | 214.9956 | 221.6604 | 228.5319 | 235.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 93.0062 | 95.7964 | 98.6703 | 101.6304 | 104.6793 | 107.8197 | 111.0543 | 114.3859 | 117.8175 | 121.352 | 124.9926 | 128.7423 | 132.6046 | 136.5827 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 91.1016 | 93.9257 | 96.8374 | 99.8394 | 102.9344 | 106.1254 | 109.4153 | 112.8071 | 116.3042 | 119.9096 | 123.6268 | 127.4592 | 131.4104 | 135.4842 | 0 | 0 | 0 | 0 | 0 | 90.0127 | 83.5933 | 86.1847 | 88.8564 | 91.6109 | 94.4509 | 97.3789 | 100.3976 | 103.5099 | 106.7187 | 110.027 | 113.4379 | 116.9544 | 120.58 | 124.318 | 0 | 0 | 0 | 0 | 0 | 91.0356 | 92.1368 | 94.9931 | 97.9379 | 100.9739 | 104.1041 | 107.3313 | 110.6586 | 114.089 | 117.6258 | 121.2722 | 125.0316 | 128.9076 | 132.9037 | 137.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 94.9162 | 98.2383 | 101.6766 | 105.2353 | 108.9185 | 112.7307 | 116.6763 | 120.7599 | 124.9865 | 129.3611 | 133.8887 | 138.5748 | 143.4249 | 148.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3513 | 153.5436 | 158.9176 | 164.4798 | 170.2366 | 176.1948 | 182.3617 | 188.7443 | 195.3504 | 202.1876 | 209.2642 | 216.5884 | 224.169 | 232.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.4097 | 98.7491 | 103.4388 | 106.6032 | 110.3343 | 114.196 | 118.1929 | 122.3296 | 126.6111 | 131.0425 | 135.629 | 140.376 | 145.2892 | 150.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIAS_M | Scientist Associate_Med | Labor |  | 0 | 0 | 172.3802 | 183.4507 | 189.1377 | 195.001 | 201.046 | 207.2784 | 213.7041 | 220.3289 | 227.1591 | 234.201 | 241.4612 | 248.9465 | 256.6639 | 264.6205 | 272.8237 | 0 | 0 | 0 | 0 | 0 | 190.8755 | 199.1041 | 205.2763 | 211.6399 | 218.2007 | 224.9649 | 231.9388 | 239.1289 | 246.5419 | 254.1847 | 262.0645 | 270.1885 | 278.5643 | 287.1998 | 296.103 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 116.1671 | 119.6521 | 123.2417 | 126.939 | 130.7471 | 134.6695 | 138.7096 | 142.8709 | 147.157 | 151.5718 | 156.1189 | 160.8025 | 165.6266 | 170.5953 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 114.4888 | 118.038 | 121.6972 | 125.4698 | 129.3594 | 133.3695 | 137.504 | 141.7666 | 146.1613 | 150.6923 | 155.3638 | 160.1801 | 165.1457 | 170.2652 | 0 | 0 | 0 | 0 | 0 | 113.1205 | 105.053 | 108.3097 | 111.6673 | 115.129 | 118.698 | 122.3776 | 126.1713 | 130.0826 | 134.1152 | 138.2728 | 142.5592 | 146.9786 | 151.5349 | 156.2325 | 0 | 0 | 0 | 0 | 0 | 114.4059 | 115.7899 | 119.3793 | 123.0801 | 126.8956 | 130.8294 | 134.8851 | 139.0665 | 143.3776 | 147.8223 | 152.4048 | 157.1293 | 162.0003 | 167.0223 | 172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9049 | 122.0316 | 126.3027 | 130.7233 | 135.2986 | 140.0341 | 144.9353 | 150.008 | 155.2583 | 160.6923 | 166.3166 | 172.1376 | 178.1625 | 184.3981 | 0 | 0 | 0 | 0 | 0 | 0 | 184.282 | 190.7319 | 197.4075 | 204.3168 | 211.4679 | 218.8692 | 226.5297 | 234.4582 | 242.6642 | 251.1575 | 259.948 | 269.0462 | 278.4628 | 288.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.518 | 122.6661 | 128.4917 | 132.4225 | 137.0573 | 141.8543 | 146.8192 | 151.9579 | 157.2764 | 162.7811 | 168.4784 | 174.3751 | 180.4783 | 186.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIAS_H | Scientist Associate_High | Labor |  | 0 | 0 | 199.0953 | 211.8814 | 218.4498 | 225.2217 | 232.2036 | 239.4019 | 246.8233 | 254.4749 | 262.3636 | 270.4969 | 278.8823 | 287.5276 | 296.441 | 305.6306 | 315.1052 | 0 | 0 | 0 | 0 | 0 | 220.4569 | 229.9607 | 237.0895 | 244.4392 | 252.0169 | 259.8294 | 267.8841 | 276.1885 | 284.7503 | 293.5776 | 302.6785 | 312.0615 | 321.7355 | 331.7092 | 341.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 0 | 134.746 | 138.7884 | 142.952 | 147.2406 | 151.6578 | 156.2076 | 160.8938 | 165.7206 | 170.6922 | 175.813 | 181.0874 | 186.52 | 192.1156 | 197.8791 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 132.232 | 136.3312 | 140.5575 | 144.9148 | 149.4071 | 154.0387 | 158.8139 | 163.7372 | 168.813 | 174.0462 | 179.4417 | 185.0044 | 190.7395 | 196.6524 | 0 | 0 | 0 | 0 | 0 | 130.6516 | 121.3339 | 125.0952 | 128.9732 | 132.9714 | 137.0935 | 141.3434 | 145.725 | 150.2425 | 154.9 | 159.7019 | 164.6527 | 169.7569 | 175.0194 | 180.445 | 0 | 0 | 0 | 0 | 0 | 132.1362 | 133.7347 | 137.8804 | 142.1547 | 146.5615 | 151.1049 | 155.7892 | 160.6187 | 165.5978 | 170.7314 | 176.024 | 181.4808 | 187.1067 | 192.907 | 198.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 136.8481 | 141.6378 | 146.5951 | 151.726 | 157.0364 | 162.5326 | 168.2213 | 174.109 | 180.2029 | 186.51 | 193.0378 | 199.7941 | 206.7869 | 214.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 213.8897 | 221.3758 | 229.124 | 237.1433 | 245.4433 | 254.0339 | 262.925 | 272.1274 | 281.6519 | 291.5097 | 301.7125 | 312.2725 | 323.202 | 334.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.5596 | 142.3742 | 149.1358 | 153.6981 | 159.0776 | 164.6453 | 170.4079 | 176.3722 | 182.5452 | 188.9343 | 195.547 | 202.3911 | 209.4748 | 216.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIMED_L | Scientist Medical_Low | Labor |  | 0 | 0 | 203.582 | 216.6563 | 223.3726 | 230.2972 | 237.4364 | 244.7969 | 252.3856 | 260.2096 | 268.2761 | 276.5926 | 285.167 | 294.0072 | 303.1214 | 312.5182 | 322.2062 | 0 | 0 | 0 | 0 | 0 | 225.425 | 235.143 | 242.4324 | 249.9478 | 257.6962 | 265.6848 | 273.921 | 282.4125 | 291.1673 | 300.1935 | 309.4995 | 319.094 | 328.9859 | 339.1845 | 349.6992 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6838 | 142.8443 | 147.1297 | 151.5435 | 156.0898 | 160.7725 | 165.5957 | 170.5636 | 175.6805 | 180.9509 | 186.3794 | 191.9708 | 197.7299 | 203.6618 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6838 | 142.8443 | 147.1297 | 151.5435 | 156.0898 | 160.7725 | 165.5957 | 170.5636 | 175.6805 | 180.9509 | 186.3794 | 191.9708 | 197.7299 | 203.6618 | 0 | 0 | 0 | 0 | 0 | 135.114 | 136.7484 | 140.9876 | 145.3582 | 149.8644 | 154.5102 | 159.3 | 164.2383 | 169.3296 | 174.5789 | 179.9908 | 185.5705 | 191.3232 | 197.2542 | 203.3691 | 0 | 0 | 0 | 0 | 0 | 133.5958 | 135.2119 | 139.4035 | 143.725 | 148.1805 | 152.7741 | 157.5101 | 162.3929 | 167.4271 | 172.6173 | 177.9684 | 183.4855 | 189.1735 | 195.0379 | 201.0841 | 0 | 0 | 0 | 0 | 0 | 133.5958 | 124.0682 | 127.9143 | 131.8797 | 135.9679 | 140.1829 | 144.5286 | 149.009 | 153.6283 | 158.3907 | 163.3009 | 168.3632 | 173.5824 | 178.9635 | 184.5114 | 0 | 0 | 0 | 0 | 0 | 135.114 | 136.7484 | 140.9876 | 145.3582 | 149.8644 | 154.5102 | 159.3 | 164.2383 | 169.3296 | 174.5789 | 179.9908 | 185.5705 | 191.3232 | 197.2542 | 203.3691 | 0 | 0 | 0 | 0 | 0 | 0 | 140.6772 | 145.6009 | 150.697 | 155.9714 | 161.4304 | 167.0804 | 172.9282 | 178.9807 | 185.2451 | 191.7286 | 198.4391 | 205.3845 | 212.573 | 220.013 | 0 | 0 | 0 | 0 | 0 | 0 | 219.8745 | 227.5701 | 235.535 | 243.7788 | 252.311 | 261.1419 | 270.2819 | 279.7417 | 289.5327 | 299.6663 | 310.1547 | 321.0101 | 332.2454 | 343.874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.4087 | 146.358 | 153.3087 | 157.9987 | 163.5287 | 169.2522 | 175.176 | 181.3072 | 187.6529 | 194.2208 | 201.0185 | 208.0541 | 215.336 | 222.8728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIMED_M | Scientist Medical_Med | Labor |  | 0 | 0 | 235.417 | 250.5358 | 258.3024 | 266.3098 | 274.5654 | 283.077 | 291.8523 | 300.8998 | 310.2277 | 319.8447 | 329.7599 | 339.9825 | 350.5219 | 361.3881 | 372.5911 | 0 | 0 | 0 | 0 | 0 | 260.6757 | 271.9134 | 280.3427 | 289.0333 | 297.9933 | 307.2311 | 316.7553 | 326.5747 | 336.6985 | 347.1362 | 357.8974 | 368.9922 | 380.431 | 392.2243 | 404.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 159.5315 | 164.3175 | 169.247 | 174.3244 | 179.5542 | 184.9408 | 190.489 | 196.2037 | 202.0898 | 208.1525 | 214.397 | 220.829 | 227.4538 | 234.2774 | 0 | 0 | 0 | 0 | 0 | 0 | 159.5315 | 164.3175 | 169.247 | 174.3244 | 179.5542 | 184.9408 | 190.489 | 196.2037 | 202.0898 | 208.1525 | 214.397 | 220.829 | 227.4538 | 234.2774 | 0 | 0 | 0 | 0 | 0 | 156.2424 | 158.1324 | 163.0345 | 168.0886 | 173.2993 | 178.6716 | 184.2104 | 189.921 | 195.8085 | 201.8786 | 208.1368 | 214.5891 | 221.2413 | 228.0998 | 235.1709 | 0 | 0 | 0 | 0 | 0 | 154.4869 | 156.3557 | 161.2027 | 166.2 | 171.3522 | 176.6641 | 182.1407 | 187.787 | 193.6084 | 199.6103 | 205.7982 | 212.178 | 218.7555 | 225.5369 | 232.5285 | 0 | 0 | 0 | 0 | 0 | 154.4869 | 143.4693 | 147.9169 | 152.5023 | 157.2299 | 162.104 | 167.1292 | 172.3102 | 177.6518 | 183.159 | 188.837 | 194.6909 | 200.7263 | 206.9489 | 213.3643 | 0 | 0 | 0 | 0 | 0 | 156.2424 | 158.1324 | 163.0345 | 168.0886 | 173.2993 | 178.6716 | 184.2104 | 189.921 | 195.8085 | 201.8786 | 208.1368 | 214.5891 | 221.2413 | 228.0998 | 235.1709 | 0 | 0 | 0 | 0 | 0 | 0 | 161.823 | 167.4868 | 173.3488 | 179.4161 | 185.6956 | 192.195 | 198.9218 | 205.8841 | 213.09 | 220.5481 | 228.2673 | 236.2567 | 244.5257 | 253.0841 | 0 | 0 | 0 | 0 | 0 | 0 | 252.9247 | 261.7771 | 270.9393 | 280.4221 | 290.2369 | 300.3952 | 310.909 | 321.7909 | 333.0535 | 344.7104 | 356.7753 | 369.2624 | 382.1866 | 395.5631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162.6644 | 168.3576 | 176.3532 | 181.7482 | 188.1093 | 194.6932 | 201.5074 | 208.5602 | 215.8598 | 223.4149 | 231.2344 | 239.3276 | 247.7041 | 256.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCIMED_H | Scientist Medical_High | Labor |  | 0 | 0 | 281.8477 | 299.9484 | 309.2468 | 318.8334 | 328.7172 | 338.9075 | 349.4136 | 360.2454 | 371.413 | 382.9269 | 394.7976 | 407.0363 | 419.6544 | 432.6637 | 446.0763 | 0 | 0 | 0 | 0 | 0 | 312.0881 | 325.5421 | 335.6339 | 346.0386 | 356.7658 | 367.8255 | 379.2281 | 390.9842 | 403.1047 | 415.6009 | 428.4846 | 441.7676 | 455.4624 | 469.5817 | 484.1387 | 0 | 0 | 0 | 0 | 0 | 0 | 191.5356 | 197.2817 | 203.2002 | 209.2962 | 215.5751 | 222.0423 | 228.7036 | 235.5647 | 242.6316 | 249.9106 | 257.4079 | 265.1301 | 273.084 | 281.2765 | 0 | 0 | 0 | 0 | 0 | 0 | 191.5356 | 197.2817 | 203.2002 | 209.2962 | 215.5751 | 222.0423 | 228.7036 | 235.5647 | 242.6316 | 249.9106 | 257.4079 | 265.1301 | 273.084 | 281.2765 | 0 | 0 | 0 | 0 | 0 | 187.0577 | 189.3205 | 195.1894 | 201.2403 | 207.4787 | 213.9106 | 220.5418 | 227.3786 | 234.4273 | 241.6946 | 249.1871 | 256.9119 | 264.8762 | 273.0873 | 281.553 | 0 | 0 | 0 | 0 | 0 | 184.9559 | 187.1933 | 192.9963 | 198.9792 | 205.1475 | 211.5071 | 218.0638 | 224.8238 | 231.7933 | 238.9789 | 246.3873 | 254.0253 | 261.9 | 270.0189 | 278.3895 | 0 | 0 | 0 | 0 | 0 | 184.9559 | 171.7654 | 177.0901 | 182.5799 | 188.2399 | 194.0753 | 200.0917 | 206.2945 | 212.6897 | 219.283 | 226.0808 | 233.0893 | 240.3151 | 247.7648 | 255.4456 | 0 | 0 | 0 | 0 | 0 | 187.0577 | 189.3205 | 195.1894 | 201.2403 | 207.4787 | 213.9106 | 220.5418 | 227.3786 | 234.4273 | 241.6946 | 249.1871 | 256.9119 | 264.8762 | 273.0873 | 281.553 | 0 | 0 | 0 | 0 | 0 | 0 | 195.0773 | 201.905 | 208.9717 | 216.2857 | 223.8557 | 231.6907 | 239.7999 | 248.1928 | 256.8796 | 265.8704 | 275.1758 | 284.807 | 294.7752 | 305.0924 | 0 | 0 | 0 | 0 | 0 | 0 | 304.9003 | 315.5718 | 326.6168 | 338.0484 | 349.8801 | 362.1259 | 374.8003 | 387.9183 | 401.4954 | 415.5478 | 430.0919 | 445.1452 | 460.7252 | 476.8506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.0916 | 202.9548 | 212.5934 | 219.0971 | 226.7655 | 234.7023 | 242.9168 | 251.4189 | 260.2186 | 269.3262 | 278.7527 | 288.509 | 298.6068 | 309.0581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTP_L | Contracted Labor (Proc)_Low | Labor |  | 0 | 0 | 150.0444 | 144.9731 | 149.4673 | 154.1008 | 158.8779 | 163.8031 | 168.881 | 174.1163 | 179.5139 | 185.0789 | 190.8163 | 196.7316 | 202.8303 | 209.118 | 215.6007 | 0 | 0 | 0 | 0 | 0 | 150.0444 | 144.9731 | 149.4673 | 154.1008 | 158.8779 | 163.8031 | 168.881 | 174.1163 | 179.5139 | 185.0789 | 190.8163 | 196.7316 | 202.8303 | 209.118 | 215.6007 | 0 | 0 | 0 | 0 | 0 | 0 | 129.3697 | 133.2508 | 137.2483 | 141.3658 | 145.6067 | 149.9749 | 154.4742 | 159.1084 | 163.8817 | 168.7981 | 173.862 | 179.0779 | 184.4502 | 189.9838 | 0 | 0 | 0 | 0 | 0 | 0 | 129.3697 | 133.2508 | 137.2483 | 141.3658 | 145.6067 | 149.9749 | 154.4742 | 159.1084 | 163.8817 | 168.7981 | 173.862 | 179.0779 | 184.4502 | 189.9838 | 0 | 0 | 0 | 0 | 0 | 147.1668 | 128.7395 | 132.7305 | 136.8451 | 141.0873 | 145.461 | 149.9703 | 154.6194 | 159.4126 | 164.3544 | 169.4494 | 174.7023 | 180.1181 | 185.7017 | 191.4585 | 0 | 0 | 0 | 0 | 0 | 145.5132 | 127.293 | 131.2391 | 135.3075 | 139.502 | 143.8266 | 148.2852 | 152.8821 | 157.6214 | 162.5077 | 167.5454 | 172.7393 | 178.0943 | 183.6152 | 189.3072 | 0 | 0 | 0 | 0 | 0 | 145.5132 | 127.293 | 131.2391 | 135.3075 | 139.502 | 143.8266 | 148.2852 | 152.8821 | 157.6214 | 162.5077 | 167.5454 | 172.7393 | 178.0943 | 183.6152 | 189.3072 | 0 | 0 | 0 | 0 | 0 | 147.1668 | 128.7395 | 132.7305 | 136.8451 | 141.0873 | 145.461 | 149.9703 | 154.6194 | 159.4126 | 164.3544 | 169.4494 | 174.7023 | 180.1181 | 185.7017 | 191.4585 | 0 | 0 | 0 | 0 | 0 | 0 | 127.7587 | 132.2302 | 136.8583 | 141.6483 | 146.606 | 151.7372 | 157.048 | 162.5447 | 168.2338 | 174.1219 | 180.2162 | 186.5238 | 193.0521 | 199.8089 | 0 | 0 | 0 | 0 | 0 | 0 | 145.5034 | 150.5961 | 155.8669 | 161.3223 | 166.9685 | 172.8124 | 178.8609 | 185.121 | 191.6002 | 198.3063 | 205.247 | 212.4306 | 219.8657 | 227.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.7587 | 132.2302 | 136.8583 | 141.6483 | 146.606 | 151.7372 | 157.048 | 162.5447 | 168.2338 | 174.1219 | 180.2162 | 186.5238 | 193.0521 | 199.8089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTP_M | Contracted Labor (Proc)_Med | Labor |  | 0 | 0 | 176.3459 | 170.3857 | 175.6676 | 181.1133 | 186.7278 | 192.5164 | 198.4844 | 204.6374 | 210.9812 | 217.5216 | 224.2648 | 231.217 | 238.3847 | 245.7746 | 253.3937 | 0 | 0 | 0 | 0 | 0 | 176.3459 | 170.3857 | 175.6676 | 181.1133 | 186.7278 | 192.5164 | 198.4844 | 204.6374 | 210.9812 | 217.5216 | 224.2648 | 231.217 | 238.3847 | 245.7746 | 253.3937 | 0 | 0 | 0 | 0 | 0 | 0 | 150.2877 | 154.7963 | 159.4402 | 164.2234 | 169.1501 | 174.2246 | 179.4513 | 184.8349 | 190.3799 | 196.0913 | 201.974 | 208.0333 | 214.2743 | 220.7025 | 0 | 0 | 0 | 0 | 0 | 0 | 150.2877 | 154.7963 | 159.4402 | 164.2234 | 169.1501 | 174.2246 | 179.4513 | 184.8349 | 190.3799 | 196.0913 | 201.974 | 208.0333 | 214.2743 | 220.7025 | 0 | 0 | 0 | 0 | 0 | 172.9638 | 151.3065 | 155.997 | 160.8329 | 165.8187 | 170.9591 | 176.2588 | 181.7228 | 187.3562 | 193.1643 | 199.1524 | 205.3261 | 211.6912 | 218.2536 | 225.0195 | 0 | 0 | 0 | 0 | 0 | 171.0204 | 149.6064 | 154.2442 | 159.0258 | 163.9556 | 169.0382 | 174.2784 | 179.681 | 185.2511 | 190.9939 | 196.9147 | 203.0191 | 209.3126 | 215.8013 | 222.4912 | 0 | 0 | 0 | 0 | 0 | 171.0204 | 149.6064 | 154.2442 | 159.0258 | 163.9556 | 169.0382 | 174.2784 | 179.681 | 185.2511 | 190.9939 | 196.9147 | 203.0191 | 209.3126 | 215.8013 | 222.4912 | 0 | 0 | 0 | 0 | 0 | 172.9638 | 151.3065 | 155.997 | 160.8329 | 165.8187 | 170.9591 | 176.2588 | 181.7228 | 187.3562 | 193.1643 | 199.1524 | 205.3261 | 211.6912 | 218.2536 | 225.0195 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3994 | 153.5933 | 158.9691 | 164.533 | 170.2917 | 176.2519 | 182.4207 | 188.8054 | 195.4136 | 202.2531 | 209.3319 | 216.6586 | 224.2416 | 232.0901 | 0 | 0 | 0 | 0 | 0 | 0 | 169.011 | 174.9264 | 181.0488 | 187.3855 | 193.944 | 200.732 | 207.7577 | 215.0292 | 222.5552 | 230.3446 | 238.4067 | 246.7509 | 255.3872 | 264.3258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148.3994 | 153.5933 | 158.9691 | 164.533 | 170.2917 | 176.2519 | 182.4207 | 188.8054 | 195.4136 | 202.2531 | 209.3319 | 216.6586 | 224.2416 | 232.0901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTP_H | Contracted Labor (Proc)_High | Labor |  | 0 | 0 | 235.4637 | 227.5054 | 234.5581 | 241.8294 | 249.3261 | 257.0552 | 265.0239 | 273.2396 | 281.7101 | 290.4431 | 299.4468 | 308.7297 | 318.3003 | 328.1676 | 338.3408 | 0 | 0 | 0 | 0 | 0 | 235.4637 | 227.5054 | 234.5581 | 241.8294 | 249.3261 | 257.0552 | 265.0239 | 273.2396 | 281.7101 | 290.4431 | 299.4468 | 308.7297 | 318.3003 | 328.1676 | 338.3408 | 0 | 0 | 0 | 0 | 0 | 0 | 203.8825 | 209.999 | 216.299 | 222.7879 | 229.4716 | 236.3557 | 243.4464 | 250.7498 | 258.2723 | 266.0204 | 274.0011 | 282.2211 | 290.6877 | 299.4084 | 0 | 0 | 0 | 0 | 0 | 0 | 203.8825 | 209.999 | 216.299 | 222.7879 | 229.4716 | 236.3557 | 243.4464 | 250.7498 | 258.2723 | 266.0204 | 274.0011 | 282.2211 | 290.6877 | 299.4084 | 0 | 0 | 0 | 0 | 0 | 230.9479 | 202.0301 | 208.2931 | 214.7501 | 221.4074 | 228.271 | 235.3474 | 242.6432 | 250.1651 | 257.9203 | 265.9158 | 274.1592 | 282.6581 | 291.4205 | 300.4545 | 0 | 0 | 0 | 0 | 0 | 228.3529 | 199.7601 | 205.9527 | 212.3372 | 218.9197 | 225.7062 | 232.7031 | 239.9169 | 247.3543 | 255.0223 | 262.928 | 271.0787 | 279.4822 | 288.1461 | 297.0786 | 0 | 0 | 0 | 0 | 0 | 228.3529 | 199.7601 | 205.9527 | 212.3372 | 218.9197 | 225.7062 | 232.7031 | 239.9169 | 247.3543 | 255.0223 | 262.928 | 271.0787 | 279.4822 | 288.1461 | 297.0786 | 0 | 0 | 0 | 0 | 0 | 230.9479 | 202.0301 | 208.2931 | 214.7501 | 221.4074 | 228.271 | 235.3474 | 242.6432 | 250.1651 | 257.9203 | 265.9158 | 274.1592 | 282.6581 | 291.4205 | 300.4545 | 0 | 0 | 0 | 0 | 0 | 0 | 202.1223 | 209.1965 | 216.5184 | 224.0966 | 231.9399 | 240.0578 | 248.4599 | 257.156 | 266.1564 | 275.4719 | 285.1134 | 295.0924 | 305.4206 | 316.1103 | 0 | 0 | 0 | 0 | 0 | 0 | 230.1956 | 238.2525 | 246.5913 | 255.222 | 264.1548 | 273.4002 | 282.9692 | 292.8731 | 303.1237 | 313.733 | 324.7137 | 336.0787 | 347.8414 | 360.0159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.1223 | 209.1965 | 216.5184 | 224.0966 | 231.9399 | 240.0578 | 248.4599 | 257.156 | 266.1564 | 275.4719 | 285.1134 | 295.0924 | 305.4206 | 316.1103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTJS_L | Contracted Labor (JobShop)_Low | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 157.6064; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 163.1226; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 168.8319; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 174.741; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 180.857; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 187.187; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 193.7385; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 200.5194; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 207.5375; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 214.8013; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 222.3194; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 230.1006; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 238.1541; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 246.4895; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 197.4175; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 204.3271; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 211.4786; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 218.8803; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 226.5412; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 234.4701; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 242.6766; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 251.1702; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 259.9612; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 269.0598; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 278.4769; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 288.2236; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 298.3114; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 308.7523; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 158.4258; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 163.9707; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 171.7579; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 177.0124; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 183.2078; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 189.6201; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 196.2568; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 203.1258; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 210.2352; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 217.5934; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 225.2092; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 233.0915; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 241.2497; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 249.6934
CONTJS_M | Contracted Labor (JobShop)_Med | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 183.0693; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 189.4767; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 196.1084; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 202.9722; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 210.0762; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 217.4289; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 225.0389; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 232.9153; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 241.0673; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 249.5047; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 258.2373; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 267.2756; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 276.6303; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 286.3123; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 229.3123; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 237.3383; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 245.6451; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 254.2427; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 263.1412; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 272.3511; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 281.8834; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 291.7493; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 301.9605; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 312.5292; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 323.4677; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 334.789; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 346.5067; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 358.6344; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 184.0211; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 190.4619; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 199.5072; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 205.6105; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 212.8069; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 220.2551; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 227.964; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 235.9428; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 244.2008; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 252.7478; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 261.594; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 270.7498; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 280.226; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 290.0339
CONTJS_H | Contracted Labor (JobShop)_High | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 249.3433; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 258.0703; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 267.1028; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 276.4514; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 286.1271; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 296.1416; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 306.5066; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 317.2343; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 328.3375; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 339.8293; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 351.7233; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 364.0336; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 376.7748; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 389.9619; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 312.327; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 323.2584; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 334.5725; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 346.2825; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 358.4024; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 370.9465; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 383.9296; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 397.3672; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 411.275; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 425.6696; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 440.5681; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 455.988; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 471.9475; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 488.4657; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 250.6397; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 259.4121; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 271.7319; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 280.0447; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 289.8463; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 299.9909; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 310.4906; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 321.3578; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 332.6053; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 344.2465; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 356.2951; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 368.7654; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 381.6722; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 395.0308
PROJ_R | Project Management Specialist_RC | Labor |  | 0 | 0 | 196.3214 | 231.0054 | 238.1665 | 245.5497 | 253.1617 | 261.0097 | 269.101 | 277.4432 | 286.0439 | 294.9113 | 304.0535 | 313.4792 | 323.197 | 333.2161 | 343.5458 | 0 | 0 | 0 | 0 | 0 | 196.3214 | 231.0054 | 238.1665 | 245.5497 | 253.1617 | 261.0097 | 269.101 | 277.4432 | 286.0439 | 294.9113 | 304.0535 | 313.4792 | 323.197 | 333.2161 | 343.5458 | 0 | 0 | 0 | 0 | 0 | 0 | 175.0272 | 180.278 | 185.6863 | 191.2569 | 196.9946 | 202.9045 | 208.9916 | 215.2614 | 221.7192 | 228.3708 | 235.2219 | 242.2786 | 249.5469 | 257.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 175.0272 | 180.278 | 185.6863 | 191.2569 | 196.9946 | 202.9045 | 208.9916 | 215.2614 | 221.7192 | 228.3708 | 235.2219 | 242.2786 | 249.5469 | 257.0333 | 0 | 0 | 0 | 0 | 0 | 162.5752 | 180.453 | 186.0471 | 191.8145 | 197.7608 | 203.8914 | 210.212 | 216.7286 | 223.4471 | 230.374 | 237.5156 | 244.8786 | 252.4698 | 260.2964 | 268.3656 | 0 | 0 | 0 | 0 | 0 | 162.5752 | 180.453 | 186.0471 | 191.8145 | 197.7608 | 203.8914 | 210.212 | 216.7286 | 223.4471 | 230.374 | 237.5156 | 244.8786 | 252.4698 | 260.2964 | 268.3656 | 0 | 0 | 0 | 0 | 0 | 162.5752 | 165.5807 | 170.7137 | 176.0058 | 181.462 | 187.0873 | 192.887 | 198.8665 | 205.0314 | 211.3873 | 217.9403 | 224.6965 | 231.6621 | 238.8436 | 246.2477 | 0 | 0 | 0 | 0 | 0 | 162.5752 | 180.453 | 186.0471 | 191.8145 | 197.7608 | 203.8914 | 210.212 | 216.7286 | 223.4471 | 230.374 | 237.5156 | 244.8786 | 252.4698 | 260.2964 | 268.3656 | 0 | 0 | 0 | 0 | 0 | 0 | 147.7967 | 152.9696 | 158.3236 | 163.8649 | 169.6002 | 175.5362 | 181.6799 | 188.0387 | 194.6201 | 201.4318 | 208.4819 | 215.7788 | 223.331 | 231.1476 | 0 | 0 | 0 | 0 | 0 | 0 | 185.13 | 191.6095 | 198.3158 | 205.2569 | 212.4409 | 219.8763 | 227.572 | 235.537 | 243.7808 | 252.3131 | 261.1441 | 270.2841 | 279.7441 | 289.5351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148.5652 | 153.765 | 161.0675 | 165.9948 | 171.8047 | 177.8178 | 184.0415 | 190.4829 | 197.1498 | 204.05 | 211.1918 | 218.5835 | 226.2339 | 234.1521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
POSTDocnonBNL | Post Doc (nonBNL) | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 0.96618; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 1; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 1.035; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 1.0712; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 1.1087; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 1.1475; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 1.1877; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 1.2293; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 1.2723; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 1.3168; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 1.3629; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 1.4106; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 1.46; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 1.5111; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 1.1004; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 1.1389; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 1.1788; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 1.22; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 1.2627; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 1.3069; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 1.3526; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 1.4; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 1.449; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 1.4997; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 1.5522; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 1.6065; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 1.6627; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 1.7209; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 0.96618; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 1; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 1.035; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 1.0712; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 1.1087; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 1.1475; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 1.1877; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 1.2293; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 1.2723; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 1.3168; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 1.3629; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 1.4106; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 1.46; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 1.5111
STUDENTBNL | Graduate Student (BNL) | Labor |  | 0 | 0 | 85.4014 | 90.886 | 93.7035 | 96.6083 | 99.6032 | 102.6909 | 105.8743 | 109.1564 | 112.5402 | 116.029 | 119.6259 | 123.3343 | 127.1576 | 131.0995 | 135.1636 | 0 | 0 | 0 | 0 | 0 | 94.5644 | 98.6411 | 101.6989 | 104.8516 | 108.102 | 111.4532 | 114.9082 | 118.4704 | 122.143 | 125.9294 | 129.8332 | 133.858 | 138.0076 | 142.2859 | 146.6967 | 0 | 0 | 0 | 0 | 0 | 0 | 58.1903 | 59.936 | 61.734 | 63.5861 | 65.4936 | 67.4585 | 69.4822 | 71.5667 | 73.7137 | 75.9251 | 78.2028 | 80.5489 | 82.9654 | 85.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 58.1903 | 59.936 | 61.734 | 63.5861 | 65.4936 | 67.4585 | 69.4822 | 71.5667 | 73.7137 | 75.9251 | 78.2028 | 80.5489 | 82.9654 | 85.4543 | 0 | 0 | 0 | 0 | 0 | 56.6795 | 57.3652 | 59.1435 | 60.9769 | 62.8672 | 64.8161 | 66.8254 | 68.897 | 71.0328 | 73.2348 | 75.5051 | 77.8457 | 80.259 | 82.747 | 85.3121 | 0 | 0 | 0 | 0 | 0 | 56.0427 | 56.7206 | 58.4789 | 60.2918 | 62.1608 | 64.0878 | 66.0745 | 68.1229 | 70.2347 | 72.4119 | 74.6567 | 76.9711 | 79.3572 | 81.8172 | 84.3536 | 0 | 0 | 0 | 0 | 0 | 56.0427 | 52.0459 | 53.6593 | 55.3227 | 57.0377 | 58.8059 | 60.6289 | 62.5084 | 64.4461 | 66.444 | 68.5037 | 70.6274 | 72.8168 | 75.0741 | 77.4014 | 0 | 0 | 0 | 0 | 0 | 56.6795 | 57.3652 | 59.1435 | 60.9769 | 62.8672 | 64.8161 | 66.8254 | 68.897 | 71.0328 | 73.2348 | 75.5051 | 77.8457 | 80.259 | 82.747 | 85.3121 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96618 | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877 | 1.2293 | 1.2723 | 1.3168 | 1.3629 | 1.4106 | 1.46 | 1.5111 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1004 | 1.1389 | 1.1788 | 1.22 | 1.2627 | 1.3069 | 1.3526 | 1.4 | 1.449 | 1.4997 | 1.5522 | 1.6065 | 1.6627 | 1.7209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96618 | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877 | 1.2293 | 1.2723 | 1.3168 | 1.3629 | 1.4106 | 1.46 | 1.5111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STUDENTnonBNL | Graduate Student (nonBNL) | Labor |  | C-AD DOE Funded Projects FY16: 0; C-AD DOE Funded Projects FY17: 0; C-AD DOE Funded Projects FY18: 0; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 0.96618; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 1; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 1.035; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 1.0712; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 1.1087; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 1.1475; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 1.1877; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 1.2293; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 1.2723; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 1.3168; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 1.3629; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 1.4106; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 1.46; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 1.5111; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 1.1004; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 1.1389; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 1.1788; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 1.22; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 1.2627; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 1.3069; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 1.3526; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 1.4; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 1.449; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 1.4997; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 1.5522; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 1.6065; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 1.6627; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 1.7209; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 0.96618; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 1; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 1.035; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 1.0712; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 1.1087; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 1.1475; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 1.1877; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 1.2293; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 1.2723; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 1.3168; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 1.3629; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 1.4106; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 1.46; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 1.5111
DOEPNR | DOE Partner Laboratories | Labor |  | NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 0.96618; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 1; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 1.035; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 1.0712; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 1.1087; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 1.1475; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 1.1877; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 1.2293; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 1.2723; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 1.3168; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 1.3629; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 1.4106; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 1.46; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 1.5111; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 1.0782; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 1.1159; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 1.1549; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 1.1954; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 1.2372; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 1.2805; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 1.3253; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 1.3717; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 1.4197; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 1.4694; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 1.5208; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 1.5741; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 1.6292; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 1.6862; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 0.96618; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 1; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 1.035; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 1.0712; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 1.1087; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 1.1475; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 1.1877; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 1.2293; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 1.2723; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 1.3168; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 1.3629; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 1.4106; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 1.46; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 1.5111
EDUCINST | Educational Institutions | Labor |  | C-AD DOE Funded Projects FY16: 0; C-AD DOE Funded Projects FY17: 0; C-AD DOE Funded Projects FY18: 0; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Extr. Constr.(eRHIC FY20 Base Yr) FY18: 0; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY19: 0.96618; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY20: 1; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY21: 1.035; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY22: 1.0712; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY23: 1.1087; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY24: 1.1475; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY25: 1.1877; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY26: 1.2293; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY27: 1.2723; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY28: 1.3168; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY29: 1.3629; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY30: 1.4106; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY31: 1.46; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx" (eRHIC Estimate Basis, FY20 Esc, new EPR G&A)_PSH_190703 FY32: 1.5111; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY19: 0.98841; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY20: 1.023; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY21: 1.0588; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY22: 1.0959; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY23: 1.1342; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY24: 1.1739; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY25: 1.215; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY26: 1.2575; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY27: 1.3015; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY28: 1.3471; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY29: 1.3942; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY30: 1.443; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY31: 1.4935; These rates are based on "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision - 2019_05_06_normalized to 1760 KWJ.xlsx")_PSH_190703 FY32: 1.5458; Insert Notes About Rate Set - Date, Origin, Etc FY19: 0; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY16: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY17: 0; NPP C-AD DOE Ext Const(EIC FY20 Base Yr) FY18: 0; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY19: 0.96618; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY20: 1; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY21: 1.035; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY22: 1.0712; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY23: 1.1087; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY24: 1.1475; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY25: 1.1877; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY26: 1.2293; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY27: 1.2723; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY28: 1.3168; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY29: 1.3629; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY30: 1.4106; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY31: 1.46; "190626 eRHIC C_AD Cost Estimate Models FY19 Trim3 Revision" - Changed to FY20 base year where Common EPR is 16.0% (FT20), 17.4% (FY21), 16.9% beyond with G&A 6.9%_PH_200123 FY32: 1.5111
ELECT | Electric_NonLabor | NonLabor |  | 0 | 0 | 1.023 | 1.0435 | 1.0643 | 1.0856 | 1.1073 | 1.1295 | 1.1521 | 1.1751 | 1.1986 | 1.2226 | 1.247 | 1.272 | 1.2974 | 1.3234 | 1.3498 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.0435 | 1.0643 | 1.0856 | 1.1073 | 1.1295 | 1.1521 | 1.1751 | 1.1986 | 1.2226 | 1.247 | 1.272 | 1.2974 | 1.3234 | 1.3498 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.3439 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.3439 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97752 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97752 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELECTne | Electric_No Escalation_NonLabor | NonLabor |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MISC01 | TLD Badges, Vehicles_NonLabor | NonLabor |  | 0 | 0 | 1.3539 | 1.5761 | 1.6077 | 1.6398 | 1.6726 | 1.7061 | 1.7402 | 1.775 | 1.8105 | 1.8467 | 1.8836 | 1.9213 | 1.9597 | 1.9989 | 2.0389 | 0 | 0 | 0 | 0 | 0 | 1.3539 | 1.5761 | 1.6077 | 1.6398 | 1.6726 | 1.7061 | 1.7402 | 1.775 | 1.8105 | 1.8467 | 1.8836 | 1.9213 | 1.9597 | 1.9989 | 2.0389 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2071 | 1.2348 | 1.2632 | 1.2923 | 1.322 | 1.3524 | 1.3835 | 1.4154 | 1.4479 | 1.4812 | 1.5153 | 1.5501 | 1.5858 | 1.6223 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2071 | 1.2348 | 1.2632 | 1.2923 | 1.322 | 1.3524 | 1.3835 | 1.4154 | 1.4479 | 1.4812 | 1.5153 | 1.5501 | 1.5858 | 1.6223 |  |  |  | 0 | 0 | 1.1212 | 1.2312 | 1.2558 | 1.281 | 1.3066 | 1.3327 | 1.3594 | 1.3866 | 1.4143 | 1.4426 | 1.4714 | 1.5009 | 1.5309 | 1.5615 | 1.5927 | 0 | 0 | 0 | 0 | 0 | 1.1212 | 1.2312 | 1.2558 | 1.281 | 1.3066 | 1.3327 | 1.3594 | 1.3866 | 1.4143 | 1.4426 | 1.4714 | 1.5009 | 1.5309 | 1.5615 | 1.5927 | 0 | 0 | 0 | 0 | 0 | 1.1212 | 1.1298 | 1.1523 | 1.1754 | 1.1989 | 1.2229 | 1.2473 | 1.2723 | 1.2977 | 1.3237 | 1.3502 | 1.3772 | 1.4047 | 1.4328 | 1.4615 | 0 | 0 | 0 | 0 | 0 | 1.1212 | 1.2312 | 1.2558 | 1.281 | 1.3066 | 1.3327 | 1.3594 | 1.3866 | 1.4143 | 1.4426 | 1.4714 | 1.5009 | 1.5309 | 1.5615 | 1.5927 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2059 | 1.2336 | 1.262 | 1.291 | 1.3207 | 1.3511 | 1.3822 | 1.414 | 1.4465 | 1.4798 | 1.5138 | 1.5486 | 1.5842 | 1.6207 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5105 | 1.5452 | 1.5808 | 1.6171 | 1.6543 | 1.6924 | 1.7313 | 1.7711 | 1.8119 | 1.8535 | 1.8962 | 1.9398 | 1.9844 | 2.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2122 | 1.24 | 1.2839 | 1.3078 | 1.3379 | 1.3687 | 1.4001 | 1.4323 | 1.4653 | 1.499 | 1.5335 | 1.5687 | 1.6048 | 1.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPACE | Space_NonLabor | NonLabor |  | 0 | 0 | 1.023 | 1.0435 | 1.0643 | 1.0856 | 1.1073 | 1.1295 | 1.1521 | 1.1751 | 1.1986 | 1.2226 | 1.247 | 1.272 | 1.2974 | 1.3234 | 1.3498 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.0435 | 1.0643 | 1.0856 | 1.1073 | 1.1295 | 1.1521 | 1.1751 | 1.1986 | 1.2226 | 1.247 | 1.272 | 1.2974 | 1.3234 | 1.3498 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.3439 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1204 | 1.1462 | 1.1725 | 1.1995 | 1.2271 | 1.2553 | 1.2842 | 1.3137 | 1.3439 |  |  |  | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2059 | 1.2336 | 1.262 | 1.291 | 1.3207 | 1.3511 | 1.3822 | 1.414 | 1.4465 | 1.4798 | 1.5138 | 1.5486 | 1.5842 | 1.6207 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5105 | 1.5452 | 1.5808 | 1.6171 | 1.6543 | 1.6924 | 1.7313 | 1.7711 | 1.8119 | 1.8535 | 1.8962 | 1.9398 | 1.9844 | 2.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2122 | 1.24 | 1.2839 | 1.3078 | 1.3379 | 1.3687 | 1.4001 | 1.4323 | 1.4653 | 1.499 | 1.5335 | 1.5687 | 1.6048 | 1.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purch<$2Mne | Purchases<$2M_NonLabor No Escalation | NonLabor |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 0 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purch>$2Mne | Purchases>$2M (Portion Over)_NonLabor No Escalation | NonLabor |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 0 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purch_Indirect | Purchases_Burdens&Esc for ne resources_NonLabor | Nonlabor |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 0 | 0 | 0 | 0 | 0 | 0 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 1.023 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Resource Structure 2 (hidden)
RESOURCE STRUCTURE: | NSLS-II |  |  | EPR_FY19 |  |  | NEXTII Rates from HT 2/6/19 | [13 empty] | EPR_FY19 |  |  | OPS_FY19 |  |  | Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 | [13 empty] | OPS19 |  |  | EPR_SS_FY19 |  |  | Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 | [13 empty] | EPRSS19 |  |  | ACT_FY19 |  |  | Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 | [13 empty] | ACT19 |  |  | Std. Operating Ovhd - FY18 Base Year |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | FY18_OPS |  |  | MIE |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | MIE |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX
Resource ID | Description | Resource Type | Combined Name | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35
MO1 | Labor_ME - Survey Engineer_MO1 | Labor | Labor_ME - Survey Engineer_MO1 | NEXTII Rates from HT 2/6/19 FY19: 128.1939; NEXTII Rates from HT 2/6/19 FY20: 132.0397; NEXTII Rates from HT 2/6/19 FY21: 136.0009; NEXTII Rates from HT 2/6/19 FY22: 140.0809; NEXTII Rates from HT 2/6/19 FY23: 144.2834; NEXTII Rates from HT 2/6/19 FY24: 148.6119; NEXTII Rates from HT 2/6/19 FY25: 153.0702; NEXTII Rates from HT 2/6/19 FY26: 157.6623; NEXTII Rates from HT 2/6/19 FY27: 162.3922; NEXTII Rates from HT 2/6/19 FY28: 167.264; NEXTII Rates from HT 2/6/19 FY29: 172.2819; NEXTII Rates from HT 2/6/19 FY30: 177.4503; NEXTII Rates from HT 2/6/19 FY31: 182.7738; NEXTII Rates from HT 2/6/19 FY32: 188.2571; EPR_FY19 FY33: 193.9048; EPR_FY19 FY34: 199.7219; EPR_FY19 FY35: 205.7136; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 173.2279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 178.4248; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 183.7775; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 189.2908; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 194.9696; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 200.8187; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 206.8432; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 213.0485; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 219.44; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 226.0232; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 232.8039; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 239.788; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 246.9816; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 254.3911; OPS19 FY33: 262.0228; OPS19 FY34: 269.8835; OPS19 FY35: 277.98; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 129.9042; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 133.8013; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 137.8153; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 141.9498; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 146.2083; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 150.5945; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 155.1124; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 159.7657; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 164.5587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 169.4955; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 174.5803; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 179.8177; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 185.2123; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 190.7686; EPRSS19 FY33: 196.4917; EPRSS19 FY34: 202.3864; EPRSS19 FY35: 208.458; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 165.6718; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 170.6419; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 175.7612; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 181.034; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 186.465; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 192.059; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 197.8208; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 203.7554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 209.8681; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 216.1641; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 222.649; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 229.3285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 236.2083; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 243.2946; ACT19 FY33: 250.5934; ACT19 FY34: 258.1112; ACT19 FY35: 265.8546; Std. Operating Ovhd - FY18 Base Year FY16: 111.0443; Std. Operating Ovhd - FY18 Base Year FY17: 111.0443; Std. Operating Ovhd - FY18 Base Year FY18: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY20: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY21: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY22: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY23: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY24: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY25: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 2; Insert Notes About Rate Set - Date, Origin, Etc FY20: 132.3036; Insert Notes About Rate Set - Date, Origin, Etc FY21: 136.2727; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.3609; Insert Notes About Rate Set - Date, Origin, Etc FY23: 144.5717; Insert Notes About Rate Set - Date, Origin, Etc FY24: 148.9089; Insert Notes About Rate Set - Date, Origin, Etc FY25: 153.3762; Insert Notes About Rate Set - Date, Origin, Etc FY26: 157.9774; Insert Notes About Rate Set - Date, Origin, Etc FY27: 162.7168; Insert Notes About Rate Set - Date, Origin, Etc FY28: 167.5983; Insert Notes About Rate Set - Date, Origin, Etc FY29: 172.6262; Insert Notes About Rate Set - Date, Origin, Etc FY30: 177.805; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MO2 | Labor_ME - Survey Technician_MO2 | Labor | Labor_ME - Survey Technician_MO2 | NEXTII Rates from HT 2/6/19 FY19: 97.8554; NEXTII Rates from HT 2/6/19 FY20: 100.7911; NEXTII Rates from HT 2/6/19 FY21: 103.8148; NEXTII Rates from HT 2/6/19 FY22: 106.9293; NEXTII Rates from HT 2/6/19 FY23: 110.1372; NEXTII Rates from HT 2/6/19 FY24: 113.4413; NEXTII Rates from HT 2/6/19 FY25: 116.8445; NEXTII Rates from HT 2/6/19 FY26: 120.3498; NEXTII Rates from HT 2/6/19 FY27: 123.9603; NEXTII Rates from HT 2/6/19 FY28: 127.6791; NEXTII Rates from HT 2/6/19 FY29: 131.5095; NEXTII Rates from HT 2/6/19 FY30: 135.4548; NEXTII Rates from HT 2/6/19 FY31: 139.5184; NEXTII Rates from HT 2/6/19 FY32: 143.704; EPR_FY19 FY33: 148.0151; EPR_FY19 FY34: 152.4556; EPR_FY19 FY35: 157.0292; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 132.2317; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 136.1986; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 140.2846; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 144.4931; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 148.8279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 153.2928; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 157.8915; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 162.6283; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 167.5071; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 172.5324; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 177.7083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 183.0396; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 188.5308; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 194.1867; OPS19 FY33: 200.0123; OPS19 FY34: 206.0127; OPS19 FY35: 212.193; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 99.1609; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 102.1358; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 105.1998; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 108.3558; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 111.6065; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 114.9547; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 118.4033; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 121.9554; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 125.6141; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 129.3825; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 133.264; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 137.2619; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 141.3798; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 145.6212; EPRSS19 FY33: 149.9898; EPRSS19 FY34: 154.4895; EPRSS19 FY35: 159.1242; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 126.4638; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 130.2577; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 134.1654; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 138.1904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 142.3361; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 146.6062; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 151.0044; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 155.5345; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 160.2005; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 165.0065; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 169.9567; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 175.0554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 180.3071; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 185.7163; ACT19 FY33: 191.2878; ACT19 FY34: 197.0264; ACT19 FY35: 202.9372; Std. Operating Ovhd - FY18 Base Year FY16: 94.65; Std. Operating Ovhd - FY18 Base Year FY17: 94.65; Std. Operating Ovhd - FY18 Base Year FY18: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY19: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY20: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY21: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY23: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY24: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY25: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY19: 3; Insert Notes About Rate Set - Date, Origin, Etc FY20: 98.2563; Insert Notes About Rate Set - Date, Origin, Etc FY21: 101.204; Insert Notes About Rate Set - Date, Origin, Etc FY22: 104.2401; Insert Notes About Rate Set - Date, Origin, Etc FY23: 107.3673; Insert Notes About Rate Set - Date, Origin, Etc FY24: 110.5883; Insert Notes About Rate Set - Date, Origin, Etc FY25: 113.906; Insert Notes About Rate Set - Date, Origin, Etc FY26: 117.3231; Insert Notes About Rate Set - Date, Origin, Etc FY27: 120.8428; Insert Notes About Rate Set - Date, Origin, Etc FY28: 124.4681; Insert Notes About Rate Set - Date, Origin, Etc FY29: 128.2022; Insert Notes About Rate Set - Date, Origin, Etc FY30: 132.0482; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MO3 | Labor_ME - Utility Engineer_MO3 | Labor | Labor_ME - Utility Engineer_MO3 | NEXTII Rates from HT 2/6/19 FY19: 128.1939; NEXTII Rates from HT 2/6/19 FY20: 132.0397; NEXTII Rates from HT 2/6/19 FY21: 136.0009; NEXTII Rates from HT 2/6/19 FY22: 140.0809; NEXTII Rates from HT 2/6/19 FY23: 144.2834; NEXTII Rates from HT 2/6/19 FY24: 148.6119; NEXTII Rates from HT 2/6/19 FY25: 153.0702; NEXTII Rates from HT 2/6/19 FY26: 157.6623; NEXTII Rates from HT 2/6/19 FY27: 162.3922; NEXTII Rates from HT 2/6/19 FY28: 167.264; NEXTII Rates from HT 2/6/19 FY29: 172.2819; NEXTII Rates from HT 2/6/19 FY30: 177.4503; NEXTII Rates from HT 2/6/19 FY31: 182.7738; NEXTII Rates from HT 2/6/19 FY32: 188.2571; EPR_FY19 FY33: 193.9048; EPR_FY19 FY34: 199.7219; EPR_FY19 FY35: 205.7136; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 173.2279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 178.4248; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 183.7775; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 189.2908; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 194.9696; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 200.8187; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 206.8432; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 213.0485; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 219.44; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 226.0232; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 232.8039; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 239.788; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 246.9816; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 254.3911; OPS19 FY33: 262.0228; OPS19 FY34: 269.8835; OPS19 FY35: 277.98; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 129.9042; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 133.8013; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 137.8153; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 141.9498; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 146.2083; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 150.5945; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 155.1124; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 159.7657; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 164.5587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 169.4955; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 174.5803; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 179.8177; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 185.2123; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 190.7686; EPRSS19 FY33: 196.4917; EPRSS19 FY34: 202.3864; EPRSS19 FY35: 208.458; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 165.6718; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 170.6419; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 175.7612; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 181.034; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 186.465; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 192.059; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 197.8208; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 203.7554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 209.8681; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 216.1641; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 222.649; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 229.3285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 236.2083; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 243.2946; ACT19 FY33: 250.5934; ACT19 FY34: 258.1112; ACT19 FY35: 265.8546; Std. Operating Ovhd - FY18 Base Year FY16: 111.0443; Std. Operating Ovhd - FY18 Base Year FY17: 111.0443; Std. Operating Ovhd - FY18 Base Year FY18: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY20: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY21: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY22: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY23: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY24: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY25: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 4; Insert Notes About Rate Set - Date, Origin, Etc FY20: 132.3036; Insert Notes About Rate Set - Date, Origin, Etc FY21: 136.2727; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.3609; Insert Notes About Rate Set - Date, Origin, Etc FY23: 144.5717; Insert Notes About Rate Set - Date, Origin, Etc FY24: 148.9089; Insert Notes About Rate Set - Date, Origin, Etc FY25: 153.3762; Insert Notes About Rate Set - Date, Origin, Etc FY26: 157.9774; Insert Notes About Rate Set - Date, Origin, Etc FY27: 162.7168; Insert Notes About Rate Set - Date, Origin, Etc FY28: 167.5983; Insert Notes About Rate Set - Date, Origin, Etc FY29: 172.6262; Insert Notes About Rate Set - Date, Origin, Etc FY30: 177.805; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MO4 | Labor_ME - Utility Technician_MO4 | Labor | Labor_ME - Utility Technician_MO4 | NEXTII Rates from HT 2/6/19 FY19: 96.7449; NEXTII Rates from HT 2/6/19 FY20: 99.6472; NEXTII Rates from HT 2/6/19 FY21: 102.6366; NEXTII Rates from HT 2/6/19 FY22: 105.7157; NEXTII Rates from HT 2/6/19 FY23: 108.8872; NEXTII Rates from HT 2/6/19 FY24: 112.1538; NEXTII Rates from HT 2/6/19 FY25: 115.5184; NEXTII Rates from HT 2/6/19 FY26: 118.984; NEXTII Rates from HT 2/6/19 FY27: 122.5535; NEXTII Rates from HT 2/6/19 FY28: 126.2301; NEXTII Rates from HT 2/6/19 FY29: 130.017; NEXTII Rates from HT 2/6/19 FY30: 133.9175; NEXTII Rates from HT 2/6/19 FY31: 137.9351; NEXTII Rates from HT 2/6/19 FY32: 142.0731; EPR_FY19 FY33: 146.3353; EPR_FY19 FY34: 150.7254; EPR_FY19 FY35: 155.2471; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 130.731; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 134.6529; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 138.6925; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 142.8533; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 147.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 151.553; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 156.0996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 160.7826; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 165.6061; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 170.5743; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 175.6915; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 180.9623; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 186.3911; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 191.9829; OPS19 FY33: 197.7423; OPS19 FY34: 203.6746; OPS19 FY35: 209.7849; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 98.0356; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 100.9766; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 104.0059; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 107.1261; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 110.3399; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 113.6501; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 117.0596; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 120.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 124.1885; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 127.9142; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 131.7516; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 135.7041; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 139.7753; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 143.9685; EPRSS19 FY33: 148.2876; EPRSS19 FY34: 152.7362; EPRSS19 FY35: 157.3183; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 125.0285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 128.7794; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 132.6428; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 136.6221; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 140.7207; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 144.9423; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 149.2906; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 153.7693; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 158.3824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 163.1339; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 168.0279; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 173.0687; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 178.2608; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 183.6086; ACT19 FY33: 189.1169; ACT19 FY34: 194.7904; ACT19 FY35: 200.6341; Std. Operating Ovhd - FY18 Base Year FY16: 86.7334; Std. Operating Ovhd - FY18 Base Year FY17: 86.7334; Std. Operating Ovhd - FY18 Base Year FY18: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY20: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY21: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY22: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY23: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY24: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY25: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 5; Insert Notes About Rate Set - Date, Origin, Etc FY20: 96.826; Insert Notes About Rate Set - Date, Origin, Etc FY21: 99.7308; Insert Notes About Rate Set - Date, Origin, Etc FY22: 102.7228; Insert Notes About Rate Set - Date, Origin, Etc FY23: 105.8044; Insert Notes About Rate Set - Date, Origin, Etc FY24: 108.9786; Insert Notes About Rate Set - Date, Origin, Etc FY25: 112.2479; Insert Notes About Rate Set - Date, Origin, Etc FY26: 115.6154; Insert Notes About Rate Set - Date, Origin, Etc FY27: 119.0838; Insert Notes About Rate Set - Date, Origin, Etc FY28: 122.6563; Insert Notes About Rate Set - Date, Origin, Etc FY29: 126.336; Insert Notes About Rate Set - Date, Origin, Etc FY30: 130.1261; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MO5 | Labor_ME - Vacuum Engineer_MO5 | Labor | Labor_ME - Vacuum Engineer_MO5 | NEXTII Rates from HT 2/6/19 FY19: 128.1939; NEXTII Rates from HT 2/6/19 FY20: 132.0397; NEXTII Rates from HT 2/6/19 FY21: 136.0009; NEXTII Rates from HT 2/6/19 FY22: 140.0809; NEXTII Rates from HT 2/6/19 FY23: 144.2834; NEXTII Rates from HT 2/6/19 FY24: 148.6119; NEXTII Rates from HT 2/6/19 FY25: 153.0702; NEXTII Rates from HT 2/6/19 FY26: 157.6623; NEXTII Rates from HT 2/6/19 FY27: 162.3922; NEXTII Rates from HT 2/6/19 FY28: 167.264; NEXTII Rates from HT 2/6/19 FY29: 172.2819; NEXTII Rates from HT 2/6/19 FY30: 177.4503; NEXTII Rates from HT 2/6/19 FY31: 182.7738; NEXTII Rates from HT 2/6/19 FY32: 188.2571; EPR_FY19 FY33: 193.9048; EPR_FY19 FY34: 199.7219; EPR_FY19 FY35: 205.7136; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 173.2279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 178.4248; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 183.7775; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 189.2908; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 194.9696; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 200.8187; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 206.8432; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 213.0485; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 219.44; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 226.0232; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 232.8039; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 239.788; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 246.9816; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 254.3911; OPS19 FY33: 262.0228; OPS19 FY34: 269.8835; OPS19 FY35: 277.98; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 129.9042; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 133.8013; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 137.8153; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 141.9498; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 146.2083; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 150.5945; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 155.1124; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 159.7657; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 164.5587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 169.4955; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 174.5803; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 179.8177; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 185.2123; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 190.7686; EPRSS19 FY33: 196.4917; EPRSS19 FY34: 202.3864; EPRSS19 FY35: 208.458; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 165.6718; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 170.6419; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 175.7612; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 181.034; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 186.465; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 192.059; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 197.8208; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 203.7554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 209.8681; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 216.1641; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 222.649; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 229.3285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 236.2083; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 243.2946; ACT19 FY33: 250.5934; ACT19 FY34: 258.1112; ACT19 FY35: 265.8546; Std. Operating Ovhd - FY18 Base Year FY16: 111.0443; Std. Operating Ovhd - FY18 Base Year FY17: 111.0443; Std. Operating Ovhd - FY18 Base Year FY18: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY20: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY21: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY22: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY23: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY24: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY25: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 6; Insert Notes About Rate Set - Date, Origin, Etc FY20: 132.3036; Insert Notes About Rate Set - Date, Origin, Etc FY21: 136.2727; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.3609; Insert Notes About Rate Set - Date, Origin, Etc FY23: 144.5717; Insert Notes About Rate Set - Date, Origin, Etc FY24: 148.9089; Insert Notes About Rate Set - Date, Origin, Etc FY25: 153.3762; Insert Notes About Rate Set - Date, Origin, Etc FY26: 157.9774; Insert Notes About Rate Set - Date, Origin, Etc FY27: 162.7168; Insert Notes About Rate Set - Date, Origin, Etc FY28: 167.5983; Insert Notes About Rate Set - Date, Origin, Etc FY29: 172.6262; Insert Notes About Rate Set - Date, Origin, Etc FY30: 177.805; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MO6 | Labor_ME - Vacuum Technician_MO6 | Labor | Labor_ME - Vacuum Technician_MO6 | NEXTII Rates from HT 2/6/19 FY19: 96.7449; NEXTII Rates from HT 2/6/19 FY20: 99.6472; NEXTII Rates from HT 2/6/19 FY21: 102.6366; NEXTII Rates from HT 2/6/19 FY22: 105.7157; NEXTII Rates from HT 2/6/19 FY23: 108.8872; NEXTII Rates from HT 2/6/19 FY24: 112.1538; NEXTII Rates from HT 2/6/19 FY25: 115.5184; NEXTII Rates from HT 2/6/19 FY26: 118.984; NEXTII Rates from HT 2/6/19 FY27: 122.5535; NEXTII Rates from HT 2/6/19 FY28: 126.2301; NEXTII Rates from HT 2/6/19 FY29: 130.017; NEXTII Rates from HT 2/6/19 FY30: 133.9175; NEXTII Rates from HT 2/6/19 FY31: 137.9351; NEXTII Rates from HT 2/6/19 FY32: 142.0731; EPR_FY19 FY33: 146.3353; EPR_FY19 FY34: 150.7254; EPR_FY19 FY35: 155.2471; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 130.731; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 134.6529; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 138.6925; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 142.8533; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 147.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 151.553; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 156.0996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 160.7826; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 165.6061; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 170.5743; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 175.6915; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 180.9623; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 186.3911; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 191.9829; OPS19 FY33: 197.7423; OPS19 FY34: 203.6746; OPS19 FY35: 209.7849; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 98.0356; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 100.9766; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 104.0059; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 107.1261; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 110.3399; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 113.6501; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 117.0596; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 120.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 124.1885; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 127.9142; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 131.7516; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 135.7041; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 139.7753; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 143.9685; EPRSS19 FY33: 148.2876; EPRSS19 FY34: 152.7362; EPRSS19 FY35: 157.3183; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 125.0285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 128.7794; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 132.6428; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 136.6221; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 140.7207; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 144.9423; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 149.2906; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 153.7693; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 158.3824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 163.1339; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 168.0279; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 173.0687; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 178.2608; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 183.6086; ACT19 FY33: 189.1169; ACT19 FY34: 194.7904; ACT19 FY35: 200.6341; Std. Operating Ovhd - FY18 Base Year FY16: 86.7334; Std. Operating Ovhd - FY18 Base Year FY17: 86.7334; Std. Operating Ovhd - FY18 Base Year FY18: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY20: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY21: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY22: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY23: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY24: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY25: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 7; Insert Notes About Rate Set - Date, Origin, Etc FY20: 96.826; Insert Notes About Rate Set - Date, Origin, Etc FY21: 99.7308; Insert Notes About Rate Set - Date, Origin, Etc FY22: 102.7228; Insert Notes About Rate Set - Date, Origin, Etc FY23: 105.8044; Insert Notes About Rate Set - Date, Origin, Etc FY24: 108.9786; Insert Notes About Rate Set - Date, Origin, Etc FY25: 112.2479; Insert Notes About Rate Set - Date, Origin, Etc FY26: 115.6154; Insert Notes About Rate Set - Date, Origin, Etc FY27: 119.0838; Insert Notes About Rate Set - Date, Origin, Etc FY28: 122.6563; Insert Notes About Rate Set - Date, Origin, Etc FY29: 126.336; Insert Notes About Rate Set - Date, Origin, Etc FY30: 130.1261; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MO7 | Labor_Project Engineer_MO7 | Labor | Labor_Project Engineer_MO7 | NEXTII Rates from HT 2/6/19 FY19: 128.1939; NEXTII Rates from HT 2/6/19 FY20: 132.0397; NEXTII Rates from HT 2/6/19 FY21: 136.0009; NEXTII Rates from HT 2/6/19 FY22: 140.0809; NEXTII Rates from HT 2/6/19 FY23: 144.2834; NEXTII Rates from HT 2/6/19 FY24: 148.6119; NEXTII Rates from HT 2/6/19 FY25: 153.0702; NEXTII Rates from HT 2/6/19 FY26: 157.6623; NEXTII Rates from HT 2/6/19 FY27: 162.3922; NEXTII Rates from HT 2/6/19 FY28: 167.264; NEXTII Rates from HT 2/6/19 FY29: 172.2819; NEXTII Rates from HT 2/6/19 FY30: 177.4503; NEXTII Rates from HT 2/6/19 FY31: 182.7738; NEXTII Rates from HT 2/6/19 FY32: 188.2571; EPR_FY19 FY33: 193.9048; EPR_FY19 FY34: 199.7219; EPR_FY19 FY35: 205.7136; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 173.2279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 178.4248; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 183.7775; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 189.2908; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 194.9696; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 200.8187; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 206.8432; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 213.0485; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 219.44; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 226.0232; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 232.8039; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 239.788; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 246.9816; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 254.3911; OPS19 FY33: 262.0228; OPS19 FY34: 269.8835; OPS19 FY35: 277.98; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 129.9042; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 133.8013; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 137.8153; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 141.9498; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 146.2083; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 150.5945; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 155.1124; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 159.7657; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 164.5587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 169.4955; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 174.5803; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 179.8177; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 185.2123; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 190.7686; EPRSS19 FY33: 196.4917; EPRSS19 FY34: 202.3864; EPRSS19 FY35: 208.458; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 165.6718; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 170.6419; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 175.7612; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 181.034; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 186.465; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 192.059; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 197.8208; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 203.7554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 209.8681; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 216.1641; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 222.649; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 229.3285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 236.2083; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 243.2946; ACT19 FY33: 250.5934; ACT19 FY34: 258.1112; ACT19 FY35: 265.8546; Std. Operating Ovhd - FY18 Base Year FY16: 111.0443; Std. Operating Ovhd - FY18 Base Year FY17: 111.0443; Std. Operating Ovhd - FY18 Base Year FY18: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY20: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY21: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY22: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY23: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY24: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY25: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 8; Insert Notes About Rate Set - Date, Origin, Etc FY20: 132.3036; Insert Notes About Rate Set - Date, Origin, Etc FY21: 136.2727; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.3609; Insert Notes About Rate Set - Date, Origin, Etc FY23: 144.5717; Insert Notes About Rate Set - Date, Origin, Etc FY24: 148.9089; Insert Notes About Rate Set - Date, Origin, Etc FY25: 153.3762; Insert Notes About Rate Set - Date, Origin, Etc FY26: 157.9774; Insert Notes About Rate Set - Date, Origin, Etc FY27: 162.7168; Insert Notes About Rate Set - Date, Origin, Etc FY28: 167.5983; Insert Notes About Rate Set - Date, Origin, Etc FY29: 172.6262; Insert Notes About Rate Set - Date, Origin, Etc FY30: 177.805; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NA1 | Labor_Manager_NA1 | Labor | Labor_Manager_NA1 | NEXTII Rates from HT 2/6/19 FY19: 212.1926; NEXTII Rates from HT 2/6/19 FY20: 218.5584; NEXTII Rates from HT 2/6/19 FY21: 225.1151; NEXTII Rates from HT 2/6/19 FY22: 231.8686; NEXTII Rates from HT 2/6/19 FY23: 238.8246; NEXTII Rates from HT 2/6/19 FY24: 245.9894; NEXTII Rates from HT 2/6/19 FY25: 253.369; NEXTII Rates from HT 2/6/19 FY26: 260.9701; NEXTII Rates from HT 2/6/19 FY27: 268.7992; NEXTII Rates from HT 2/6/19 FY28: 276.8632; NEXTII Rates from HT 2/6/19 FY29: 285.1691; NEXTII Rates from HT 2/6/19 FY30: 293.7242; NEXTII Rates from HT 2/6/19 FY31: 302.5359; NEXTII Rates from HT 2/6/19 FY32: 311.612; EPR_FY19 FY33: 320.9603; EPR_FY19 FY34: 330.5891; EPR_FY19 FY35: 340.5068; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 286.735; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 295.3371; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 304.1972; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 313.3231; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 322.7228; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 332.4045; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 342.3766; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 352.6479; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 363.2274; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 374.1242; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 385.3479; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 396.9084; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 408.8156; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 421.0801; OPS19 FY33: 433.7125; OPS19 FY34: 446.7239; OPS19 FY35: 460.1256; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 215.0235; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 221.4742; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 228.1184; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 234.962; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 242.0108; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 249.2711; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 256.7493; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 264.4518; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 272.3853; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 280.5569; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 288.9736; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 297.6428; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 306.5721; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 315.7692; EPRSS19 FY33: 325.2423; EPRSS19 FY34: 334.9996; EPRSS19 FY35: 345.0496; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 274.2277; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 282.4546; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 290.9282; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 299.656; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 308.6457; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 317.9051; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 327.4423; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 337.2655; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 347.3835; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 357.805; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 368.5391; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 379.5953; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 390.9832; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 402.7127; ACT19 FY33: 414.794; ACT19 FY34: 427.2379; ACT19 FY35: 440.055; Std. Operating Ovhd - FY18 Base Year FY16: 203.844; Std. Operating Ovhd - FY18 Base Year FY17: 203.844; Std. Operating Ovhd - FY18 Base Year FY18: 203.844; Insert Notes About Rate Set - Date, Origin, Etc FY19: 203.844; Insert Notes About Rate Set - Date, Origin, Etc FY20: 203.844; Insert Notes About Rate Set - Date, Origin, Etc FY21: 203.844; Insert Notes About Rate Set - Date, Origin, Etc FY22: 203.844; Insert Notes About Rate Set - Date, Origin, Etc FY23: 203.844; Insert Notes About Rate Set - Date, Origin, Etc FY24: 203.844; Insert Notes About Rate Set - Date, Origin, Etc FY25: 203.844; Insert Notes About Rate Set - Date, Origin, Etc FY19: 9; Insert Notes About Rate Set - Date, Origin, Etc FY20: 210.815; Insert Notes About Rate Set - Date, Origin, Etc FY21: 217.1394; Insert Notes About Rate Set - Date, Origin, Etc FY22: 223.6536; Insert Notes About Rate Set - Date, Origin, Etc FY23: 230.3632; Insert Notes About Rate Set - Date, Origin, Etc FY24: 237.2741; Insert Notes About Rate Set - Date, Origin, Etc FY25: 244.3924; Insert Notes About Rate Set - Date, Origin, Etc FY26: 251.7241; Insert Notes About Rate Set - Date, Origin, Etc FY27: 259.2758; Insert Notes About Rate Set - Date, Origin, Etc FY28: 267.0541; Insert Notes About Rate Set - Date, Origin, Etc FY29: 275.0657; Insert Notes About Rate Set - Date, Origin, Etc FY30: 283.3177; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NA2 | Labor_Administrative_NA2 | Labor | Labor_Administrative_NA2 | NEXTII Rates from HT 2/6/19 FY19: 82.2066; NEXTII Rates from HT 2/6/19 FY20: 84.6728; NEXTII Rates from HT 2/6/19 FY21: 87.213; NEXTII Rates from HT 2/6/19 FY22: 89.8294; NEXTII Rates from HT 2/6/19 FY23: 92.5243; NEXTII Rates from HT 2/6/19 FY24: 95.3; NEXTII Rates from HT 2/6/19 FY25: 98.159; NEXTII Rates from HT 2/6/19 FY26: 101.1038; NEXTII Rates from HT 2/6/19 FY27: 104.1369; NEXTII Rates from HT 2/6/19 FY28: 107.261; NEXTII Rates from HT 2/6/19 FY29: 110.4789; NEXTII Rates from HT 2/6/19 FY30: 113.7932; NEXTII Rates from HT 2/6/19 FY31: 117.207; NEXTII Rates from HT 2/6/19 FY32: 120.7232; EPR_FY19 FY33: 124.3449; EPR_FY19 FY34: 128.0753; EPR_FY19 FY35: 131.9175; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 111.0855; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 114.4181; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 117.8506; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 121.3862; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 125.0277; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 128.7786; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 132.6419; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 136.6212; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 140.7198; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 144.9414; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 149.2897; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 153.7684; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 158.3814; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 163.1328; OPS19 FY33: 168.0268; OPS19 FY34: 173.0676; OPS19 FY35: 178.2597; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 83.3034; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 85.8025; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 88.3765; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 91.0278; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 93.7587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 96.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 99.4686; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 102.4526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 105.5262; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 108.692; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 111.9528; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 115.3113; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 118.7707; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 122.3338; EPRSS19 FY33: 126.0038; EPRSS19 FY34: 129.7839; EPRSS19 FY35: 133.6775; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 106.24; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 109.4272; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 112.71; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 116.0913; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 119.5741; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 123.1613; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 126.8561; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 130.6618; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 134.5817; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 138.6191; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 142.7777; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 147.061; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 151.4728; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 156.017; ACT19 FY33: 160.6975; ACT19 FY34: 165.5185; ACT19 FY35: 170.484; Std. Operating Ovhd - FY18 Base Year FY16: 85.2623; Std. Operating Ovhd - FY18 Base Year FY17: 85.2623; Std. Operating Ovhd - FY18 Base Year FY18: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY19: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY20: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY21: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY22: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY23: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY24: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY25: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY19: 10; Insert Notes About Rate Set - Date, Origin, Etc FY20: 83.0299; Insert Notes About Rate Set - Date, Origin, Etc FY21: 85.5208; Insert Notes About Rate Set - Date, Origin, Etc FY22: 88.0864; Insert Notes About Rate Set - Date, Origin, Etc FY23: 90.729; Insert Notes About Rate Set - Date, Origin, Etc FY24: 93.4509; Insert Notes About Rate Set - Date, Origin, Etc FY25: 96.2544; Insert Notes About Rate Set - Date, Origin, Etc FY26: 99.1421; Insert Notes About Rate Set - Date, Origin, Etc FY27: 102.1163; Insert Notes About Rate Set - Date, Origin, Etc FY28: 105.1798; Insert Notes About Rate Set - Date, Origin, Etc FY29: 108.3352; Insert Notes About Rate Set - Date, Origin, Etc FY30: 111.5853; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NA3 | Labor_Administrative Secretary_NA3 | Labor | Labor_Administrative Secretary_NA3 | NEXTII Rates from HT 2/6/19 FY19: 71.0001; NEXTII Rates from HT 2/6/19 FY20: 73.1301; NEXTII Rates from HT 2/6/19 FY21: 75.324; NEXTII Rates from HT 2/6/19 FY22: 77.5837; NEXTII Rates from HT 2/6/19 FY23: 79.9112; NEXTII Rates from HT 2/6/19 FY24: 82.3086; NEXTII Rates from HT 2/6/19 FY25: 84.7778; NEXTII Rates from HT 2/6/19 FY26: 87.3212; NEXTII Rates from HT 2/6/19 FY27: 89.9408; NEXTII Rates from HT 2/6/19 FY28: 92.639; NEXTII Rates from HT 2/6/19 FY29: 95.4182; NEXTII Rates from HT 2/6/19 FY30: 98.2807; NEXTII Rates from HT 2/6/19 FY31: 101.2291; NEXTII Rates from HT 2/6/19 FY32: 104.266; EPR_FY19 FY33: 107.394; EPR_FY19 FY34: 110.6158; EPR_FY19 FY35: 113.9343; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 95.9422; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 98.8204; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 101.785; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 104.8386; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 107.9837; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 111.2232; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 114.5599; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 117.9967; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 121.5366; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 125.1827; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 128.9382; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 132.8064; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 136.7906; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 140.8943; OPS19 FY33: 145.1211; OPS19 FY34: 149.4747; OPS19 FY35: 153.959; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 71.9473; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 74.1057; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 76.3289; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 78.6188; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 80.9773; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 83.4067; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 85.9089; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 88.4861; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 91.1407; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 93.8749; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 96.6912; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 99.5919; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 102.5797; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 105.6571; EPRSS19 FY33: 108.8268; EPRSS19 FY34: 112.0916; EPRSS19 FY35: 115.4543; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 91.7572; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 94.5099; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 97.3452; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 100.2655; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 103.2735; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 106.3717; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 109.5629; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 112.8498; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 116.2352; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 119.7223; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 123.314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 127.0134; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 130.8238; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 134.7485; ACT19 FY33: 138.791; ACT19 FY34: 142.9547; ACT19 FY35: 147.2433; Std. Operating Ovhd - FY18 Base Year FY16: 63.378; Std. Operating Ovhd - FY18 Base Year FY17: 63.378; Std. Operating Ovhd - FY18 Base Year FY18: 63.378; Insert Notes About Rate Set - Date, Origin, Etc FY19: 63.378; Insert Notes About Rate Set - Date, Origin, Etc FY20: 63.378; Insert Notes About Rate Set - Date, Origin, Etc FY21: 63.378; Insert Notes About Rate Set - Date, Origin, Etc FY22: 63.378; Insert Notes About Rate Set - Date, Origin, Etc FY23: 63.378; Insert Notes About Rate Set - Date, Origin, Etc FY24: 63.378; Insert Notes About Rate Set - Date, Origin, Etc FY25: 63.378; Insert Notes About Rate Set - Date, Origin, Etc FY19: 11; Insert Notes About Rate Set - Date, Origin, Etc FY20: 73.8156; Insert Notes About Rate Set - Date, Origin, Etc FY21: 76.0301; Insert Notes About Rate Set - Date, Origin, Etc FY22: 78.311; Insert Notes About Rate Set - Date, Origin, Etc FY23: 80.6603; Insert Notes About Rate Set - Date, Origin, Etc FY24: 83.0801; Insert Notes About Rate Set - Date, Origin, Etc FY25: 85.5725; Insert Notes About Rate Set - Date, Origin, Etc FY26: 88.1397; Insert Notes About Rate Set - Date, Origin, Etc FY27: 90.7839; Insert Notes About Rate Set - Date, Origin, Etc FY28: 93.5074; Insert Notes About Rate Set - Date, Origin, Etc FY29: 96.3126; Insert Notes About Rate Set - Date, Origin, Etc FY30: 99.202; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NA4 | Labor_ES&H Professional_NA4 | Labor | Labor_ES&H Professional_NA4 | NEXTII Rates from HT 2/6/19 FY19: 145.8998; NEXTII Rates from HT 2/6/19 FY20: 150.2767; NEXTII Rates from HT 2/6/19 FY21: 154.785; NEXTII Rates from HT 2/6/19 FY22: 159.4286; NEXTII Rates from HT 2/6/19 FY23: 164.2115; NEXTII Rates from HT 2/6/19 FY24: 169.1378; NEXTII Rates from HT 2/6/19 FY25: 174.2119; NEXTII Rates from HT 2/6/19 FY26: 179.4383; NEXTII Rates from HT 2/6/19 FY27: 184.8214; NEXTII Rates from HT 2/6/19 FY28: 190.3661; NEXTII Rates from HT 2/6/19 FY29: 196.0771; NEXTII Rates from HT 2/6/19 FY30: 201.9594; NEXTII Rates from HT 2/6/19 FY31: 208.0182; NEXTII Rates from HT 2/6/19 FY32: 214.2587; EPR_FY19 FY33: 220.6865; EPR_FY19 FY34: 227.3071; EPR_FY19 FY35: 234.1263; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 197.1538; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 203.0684; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 209.1605; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 215.4353; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 221.8983; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 228.5553; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 235.4119; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 242.4743; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 249.7485; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 257.241; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 264.9582; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 272.907; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 281.0942; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 289.527; OPS19 FY33: 298.2128; OPS19 FY34: 307.1592; OPS19 FY35: 316.374; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 147.8462; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 152.2816; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 156.8501; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 161.5556; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 166.4022; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 171.3943; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 176.5361; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 181.8322; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 187.2872; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 192.9058; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 198.693; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 204.6538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 210.7934; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 217.1172; EPRSS19 FY33: 223.6307; EPRSS19 FY34: 230.3396; EPRSS19 FY35: 237.2498; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 188.554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 194.2106; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 200.0369; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 206.038; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 212.2192; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 218.5858; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 225.1433; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 231.8976; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 238.8546; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 246.0202; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 253.4008; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 261.0028; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 268.8329; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 276.8979; ACT19 FY33: 285.2048; ACT19 FY34: 293.761; ACT19 FY35: 302.5738; Std. Operating Ovhd - FY18 Base Year FY16: 134.0206; Std. Operating Ovhd - FY18 Base Year FY17: 134.0206; Std. Operating Ovhd - FY18 Base Year FY18: 134.0206; Insert Notes About Rate Set - Date, Origin, Etc FY19: 134.0206; Insert Notes About Rate Set - Date, Origin, Etc FY20: 134.0206; Insert Notes About Rate Set - Date, Origin, Etc FY21: 134.0206; Insert Notes About Rate Set - Date, Origin, Etc FY22: 134.0206; Insert Notes About Rate Set - Date, Origin, Etc FY23: 134.0206; Insert Notes About Rate Set - Date, Origin, Etc FY24: 134.0206; Insert Notes About Rate Set - Date, Origin, Etc FY25: 134.0206; Insert Notes About Rate Set - Date, Origin, Etc FY19: 12; Insert Notes About Rate Set - Date, Origin, Etc FY20: 153.251; Insert Notes About Rate Set - Date, Origin, Etc FY21: 157.8485; Insert Notes About Rate Set - Date, Origin, Etc FY22: 162.5839; Insert Notes About Rate Set - Date, Origin, Etc FY23: 167.4615; Insert Notes About Rate Set - Date, Origin, Etc FY24: 172.4853; Insert Notes About Rate Set - Date, Origin, Etc FY25: 177.6599; Insert Notes About Rate Set - Date, Origin, Etc FY26: 182.9897; Insert Notes About Rate Set - Date, Origin, Etc FY27: 188.4793; Insert Notes About Rate Set - Date, Origin, Etc FY28: 194.1337; Insert Notes About Rate Set - Date, Origin, Etc FY29: 199.9577; Insert Notes About Rate Set - Date, Origin, Etc FY30: 205.9565; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NA5 | Labor_QA Professional_NA5 | Labor | Labor_QA Professional_NA5 | NEXTII Rates from HT 2/6/19 FY19: 131.0965; NEXTII Rates from HT 2/6/19 FY20: 135.0294; NEXTII Rates from HT 2/6/19 FY21: 139.0803; NEXTII Rates from HT 2/6/19 FY22: 143.2527; NEXTII Rates from HT 2/6/19 FY23: 147.5503; NEXTII Rates from HT 2/6/19 FY24: 151.9768; NEXTII Rates from HT 2/6/19 FY25: 156.5361; NEXTII Rates from HT 2/6/19 FY26: 161.2322; NEXTII Rates from HT 2/6/19 FY27: 166.0691; NEXTII Rates from HT 2/6/19 FY28: 171.0512; NEXTII Rates from HT 2/6/19 FY29: 176.1827; NEXTII Rates from HT 2/6/19 FY30: 181.4682; NEXTII Rates from HT 2/6/19 FY31: 186.9123; NEXTII Rates from HT 2/6/19 FY32: 192.5196; EPR_FY19 FY33: 198.2952; EPR_FY19 FY34: 204.2441; EPR_FY19 FY35: 210.3714; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 177.1502; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 182.4647; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 187.9387; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 193.5768; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 199.3841; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 205.3656; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 211.5266; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 217.8724; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 224.4086; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 231.1408; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 238.0751; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 245.2173; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 252.5738; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 260.151; OPS19 FY33: 267.9556; OPS19 FY34: 275.9942; OPS19 FY35: 284.2741; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 132.8455; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 136.8308; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 140.9358; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 145.1638; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 149.5188; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 154.0043; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 158.6244; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 163.3832; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 168.2847; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 173.3332; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 178.5332; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 183.8892; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 189.4059; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 195.0881; EPRSS19 FY33: 200.9407; EPRSS19 FY34: 206.9689; EPRSS19 FY35: 213.178; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 169.423; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 174.5057; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 179.7408; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 185.133; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 190.687; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 196.4076; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 202.2999; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 208.3689; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 214.6199; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 221.0585; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 227.6903; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 234.521; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 241.5566; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 248.8033; ACT19 FY33: 256.2674; ACT19 FY34: 263.9555; ACT19 FY35: 271.8741; Std. Operating Ovhd - FY18 Base Year FY16: 125.4822; Std. Operating Ovhd - FY18 Base Year FY17: 125.4822; Std. Operating Ovhd - FY18 Base Year FY18: 125.4822; Insert Notes About Rate Set - Date, Origin, Etc FY19: 125.4822; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.4822; Insert Notes About Rate Set - Date, Origin, Etc FY21: 125.4822; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.4822; Insert Notes About Rate Set - Date, Origin, Etc FY23: 125.4822; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.4822; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.4822; Insert Notes About Rate Set - Date, Origin, Etc FY19: 13; Insert Notes About Rate Set - Date, Origin, Etc FY20: 135.278; Insert Notes About Rate Set - Date, Origin, Etc FY21: 139.3364; Insert Notes About Rate Set - Date, Origin, Etc FY22: 143.5164; Insert Notes About Rate Set - Date, Origin, Etc FY23: 147.8219; Insert Notes About Rate Set - Date, Origin, Etc FY24: 152.2566; Insert Notes About Rate Set - Date, Origin, Etc FY25: 156.8243; Insert Notes About Rate Set - Date, Origin, Etc FY26: 161.529; Insert Notes About Rate Set - Date, Origin, Etc FY27: 166.3749; Insert Notes About Rate Set - Date, Origin, Etc FY28: 171.3661; Insert Notes About Rate Set - Date, Origin, Etc FY29: 176.5071; Insert Notes About Rate Set - Date, Origin, Etc FY30: 181.8023; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NA6 | Labor_Other Professional_NA6 | Labor | Labor_Other Professional_NA6 | NEXTII Rates from HT 2/6/19 FY19: 126.263; NEXTII Rates from HT 2/6/19 FY20: 130.0509; NEXTII Rates from HT 2/6/19 FY21: 133.9525; NEXTII Rates from HT 2/6/19 FY22: 137.971; NEXTII Rates from HT 2/6/19 FY23: 142.1102; NEXTII Rates from HT 2/6/19 FY24: 146.3735; NEXTII Rates from HT 2/6/19 FY25: 150.7647; NEXTII Rates from HT 2/6/19 FY26: 155.2876; NEXTII Rates from HT 2/6/19 FY27: 159.9462; NEXTII Rates from HT 2/6/19 FY28: 164.7446; NEXTII Rates from HT 2/6/19 FY29: 169.687; NEXTII Rates from HT 2/6/19 FY30: 174.7776; NEXTII Rates from HT 2/6/19 FY31: 180.0209; NEXTII Rates from HT 2/6/19 FY32: 185.4215; EPR_FY19 FY33: 190.9842; EPR_FY19 FY34: 196.7137; EPR_FY19 FY35: 202.6151; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 170.6188; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 175.7373; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 181.0095; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 186.4397; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 192.0329; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 197.7939; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 203.7277; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 209.8396; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 216.1348; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 222.6188; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 229.2974; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 236.1763; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 243.2616; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 250.5594; OPS19 FY33: 258.0762; OPS19 FY34: 265.8185; OPS19 FY35: 273.793; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 127.9475; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 131.786; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 135.7395; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 139.8117; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 144.0061; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 148.3263; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 152.776; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 157.3593; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 162.0801; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 166.9425; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 171.9508; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 177.1093; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 182.4226; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 187.8953; EPRSS19 FY33: 193.5321; EPRSS19 FY34: 199.3381; EPRSS19 FY35: 205.3182; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 163.1764; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 168.0717; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 173.1139; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 178.3073; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 183.6565; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 189.1662; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 194.8412; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 200.6864; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 206.707; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 212.9082; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 219.2955; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 225.8743; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 232.6506; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 239.6301; ACT19 FY33: 246.819; ACT19 FY34: 254.2236; ACT19 FY35: 261.8503; Std. Operating Ovhd - FY18 Base Year FY16: 128.8489; Std. Operating Ovhd - FY18 Base Year FY17: 128.8489; Std. Operating Ovhd - FY18 Base Year FY18: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY19: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY20: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY21: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY22: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY23: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY24: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY25: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY19: 14; Insert Notes About Rate Set - Date, Origin, Etc FY20: 131.6961; Insert Notes About Rate Set - Date, Origin, Etc FY21: 135.647; Insert Notes About Rate Set - Date, Origin, Etc FY22: 139.7164; Insert Notes About Rate Set - Date, Origin, Etc FY23: 143.9079; Insert Notes About Rate Set - Date, Origin, Etc FY24: 148.2251; Insert Notes About Rate Set - Date, Origin, Etc FY25: 152.6719; Insert Notes About Rate Set - Date, Origin, Etc FY26: 157.252; Insert Notes About Rate Set - Date, Origin, Etc FY27: 161.9696; Insert Notes About Rate Set - Date, Origin, Etc FY28: 166.8287; Insert Notes About Rate Set - Date, Origin, Etc FY29: 171.8335; Insert Notes About Rate Set - Date, Origin, Etc FY30: 176.9885; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NA7 | Labor_IT Professional (Software)_NA7 | Labor | Labor_IT Professional (Software)_NA7 | NEXTII Rates from HT 2/6/19 FY19: 115.7253; NEXTII Rates from HT 2/6/19 FY20: 119.1971; NEXTII Rates from HT 2/6/19 FY21: 122.773; NEXTII Rates from HT 2/6/19 FY22: 126.4562; NEXTII Rates from HT 2/6/19 FY23: 130.2499; NEXTII Rates from HT 2/6/19 FY24: 134.1574; NEXTII Rates from HT 2/6/19 FY25: 138.1821; NEXTII Rates from HT 2/6/19 FY26: 142.3276; NEXTII Rates from HT 2/6/19 FY27: 146.5974; NEXTII Rates from HT 2/6/19 FY28: 150.9953; NEXTII Rates from HT 2/6/19 FY29: 155.5252; NEXTII Rates from HT 2/6/19 FY30: 160.1909; NEXTII Rates from HT 2/6/19 FY31: 164.9967; NEXTII Rates from HT 2/6/19 FY32: 169.9466; EPR_FY19 FY33: 175.045; EPR_FY19 FY34: 180.2963; EPR_FY19 FY35: 185.7052; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 156.3792; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 161.0706; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 165.9027; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 170.8798; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 176.0062; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 181.2864; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 186.725; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 192.3267; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 198.0965; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 204.0394; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 210.1606; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 216.4654; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 222.9594; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 229.6482; OPS19 FY33: 236.5376; OPS19 FY34: 243.6337; OPS19 FY35: 250.9428; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 117.2693; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 120.7873; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 124.411; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 128.1433; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 131.9876; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 135.9472; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 140.0256; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 144.2264; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 148.5532; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 153.0098; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 157.6001; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 162.3281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 167.1979; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 172.2139; EPRSS19 FY33: 177.3803; EPRSS19 FY34: 182.7017; EPRSS19 FY35: 188.1827; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 149.558; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 154.0447; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 158.6661; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 163.4261; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 168.3289; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 173.3787; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 178.5801; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 183.9375; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 189.4556; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 195.1393; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 200.9935; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 207.0233; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 213.234; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 219.631; ACT19 FY33: 226.2199; ACT19 FY34: 233.0065; ACT19 FY35: 239.9967; Std. Operating Ovhd - FY18 Base Year FY16: 109.1182; Std. Operating Ovhd - FY18 Base Year FY17: 109.1182; Std. Operating Ovhd - FY18 Base Year FY18: 109.1182; Insert Notes About Rate Set - Date, Origin, Etc FY19: 109.1182; Insert Notes About Rate Set - Date, Origin, Etc FY20: 109.1182; Insert Notes About Rate Set - Date, Origin, Etc FY21: 109.1182; Insert Notes About Rate Set - Date, Origin, Etc FY22: 109.1182; Insert Notes About Rate Set - Date, Origin, Etc FY23: 109.1182; Insert Notes About Rate Set - Date, Origin, Etc FY24: 109.1182; Insert Notes About Rate Set - Date, Origin, Etc FY25: 109.1182; Insert Notes About Rate Set - Date, Origin, Etc FY19: 15; Insert Notes About Rate Set - Date, Origin, Etc FY20: 114.5712; Insert Notes About Rate Set - Date, Origin, Etc FY21: 117.2063; Insert Notes About Rate Set - Date, Origin, Etc FY22: 119.902; Insert Notes About Rate Set - Date, Origin, Etc FY23: 122.6598; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.481; Insert Notes About Rate Set - Date, Origin, Etc FY25: 128.367; Insert Notes About Rate Set - Date, Origin, Etc FY26: 131.3195; Insert Notes About Rate Set - Date, Origin, Etc FY27: 134.3398; Insert Notes About Rate Set - Date, Origin, Etc FY28: 137.4296; Insert Notes About Rate Set - Date, Origin, Etc FY29: 140.5905; Insert Notes About Rate Set - Date, Origin, Etc FY30: 143.8241; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NB1 | Labor_Project Controls_NB1 | Labor | Labor_Project Controls_NB1 | NEXTII Rates from HT 2/6/19 FY19: 156.4879; NEXTII Rates from HT 2/6/19 FY20: 161.1826; NEXTII Rates from HT 2/6/19 FY21: 166.018; NEXTII Rates from HT 2/6/19 FY22: 170.9986; NEXTII Rates from HT 2/6/19 FY23: 176.1285; NEXTII Rates from HT 2/6/19 FY24: 181.4124; NEXTII Rates from HT 2/6/19 FY25: 186.8548; NEXTII Rates from HT 2/6/19 FY26: 192.4604; NEXTII Rates from HT 2/6/19 FY27: 198.2342; NEXTII Rates from HT 2/6/19 FY28: 204.1812; NEXTII Rates from HT 2/6/19 FY29: 210.3067; NEXTII Rates from HT 2/6/19 FY30: 216.6159; NEXTII Rates from HT 2/6/19 FY31: 223.1144; NEXTII Rates from HT 2/6/19 FY32: 229.8078; EPR_FY19 FY33: 236.702; EPR_FY19 FY34: 243.8031; EPR_FY19 FY35: 251.1172; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 191.6096; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 197.3579; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 203.2786; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 209.3769; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 215.6583; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 222.128; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 228.7918; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 235.6556; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 242.7253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 250.007; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 257.5072; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 265.2325; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 273.1894; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 281.3851; OPS19 FY33: 289.8267; OPS19 FY34: 298.5215; OPS19 FY35: 307.4771; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 158.5757; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 163.3329; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 168.2329; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 173.2799; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 178.4783; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 183.8326; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 189.3476; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 195.0281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 200.8789; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 206.9053; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 213.1124; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 219.5058; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 226.091; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 232.8737; EPRSS19 FY33: 239.8599; EPRSS19 FY34: 247.0557; EPRSS19 FY35: 254.4674; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 202.2377; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 208.3048; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 214.5539; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 220.9905; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 227.6203; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 234.4489; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 241.4823; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 248.7268; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 256.1886; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 263.8743; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 271.7905; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 279.9442; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 288.3425; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 296.9928; ACT19 FY33: 305.9026; ACT19 FY34: 315.0797; ACT19 FY35: 324.5321; Std. Operating Ovhd - FY18 Base Year FY16: 128.8489; Std. Operating Ovhd - FY18 Base Year FY17: 128.8489; Std. Operating Ovhd - FY18 Base Year FY18: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY19: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY20: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY21: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY22: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY23: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY24: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY25: 128.8489; Insert Notes About Rate Set - Date, Origin, Etc FY19: 16; Insert Notes About Rate Set - Date, Origin, Etc FY20: 164.4144; Insert Notes About Rate Set - Date, Origin, Etc FY21: 168.196; Insert Notes About Rate Set - Date, Origin, Etc FY22: 172.0645; Insert Notes About Rate Set - Date, Origin, Etc FY23: 176.022; Insert Notes About Rate Set - Date, Origin, Etc FY24: 180.0705; Insert Notes About Rate Set - Date, Origin, Etc FY25: 184.2121; Insert Notes About Rate Set - Date, Origin, Etc FY26: 188.449; Insert Notes About Rate Set - Date, Origin, Etc FY27: 192.7833; Insert Notes About Rate Set - Date, Origin, Etc FY28: 197.2173; Insert Notes About Rate Set - Date, Origin, Etc FY29: 201.7533; Insert Notes About Rate Set - Date, Origin, Etc FY30: 206.3936; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NB2 | Labor_Business Ops_NB2 | Labor | Labor_Business Ops_NB2 | NEXTII Rates from HT 2/6/19 FY19: 82.2066; NEXTII Rates from HT 2/6/19 FY20: 84.6728; NEXTII Rates from HT 2/6/19 FY21: 87.213; NEXTII Rates from HT 2/6/19 FY22: 89.8294; NEXTII Rates from HT 2/6/19 FY23: 92.5243; NEXTII Rates from HT 2/6/19 FY24: 95.3; NEXTII Rates from HT 2/6/19 FY25: 98.159; NEXTII Rates from HT 2/6/19 FY26: 101.1038; NEXTII Rates from HT 2/6/19 FY27: 104.1369; NEXTII Rates from HT 2/6/19 FY28: 107.261; NEXTII Rates from HT 2/6/19 FY29: 110.4789; NEXTII Rates from HT 2/6/19 FY30: 113.7932; NEXTII Rates from HT 2/6/19 FY31: 117.207; NEXTII Rates from HT 2/6/19 FY32: 120.7232; EPR_FY19 FY33: 124.3449; EPR_FY19 FY34: 128.0753; EPR_FY19 FY35: 131.9175; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 111.0855; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 114.4181; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 117.8506; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 121.3862; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 125.0277; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 128.7786; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 132.6419; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 136.6212; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 140.7198; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 144.9414; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 149.2897; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 153.7684; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 158.3814; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 163.1328; OPS19 FY33: 168.0268; OPS19 FY34: 173.0676; OPS19 FY35: 178.2597; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 83.3034; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 85.8025; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 88.3765; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 91.0278; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 93.7587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 96.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 99.4686; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 102.4526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 105.5262; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 108.692; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 111.9528; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 115.3113; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 118.7707; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 122.3338; EPRSS19 FY33: 126.0038; EPRSS19 FY34: 129.7839; EPRSS19 FY35: 133.6775; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 106.24; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 109.4272; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 112.71; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 116.0913; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 119.5741; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 123.1613; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 126.8561; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 130.6618; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 134.5817; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 138.6191; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 142.7777; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 147.061; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 151.4728; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 156.017; ACT19 FY33: 160.6975; ACT19 FY34: 165.5185; ACT19 FY35: 170.484; Std. Operating Ovhd - FY18 Base Year FY16: 85.2623; Std. Operating Ovhd - FY18 Base Year FY17: 85.2623; Std. Operating Ovhd - FY18 Base Year FY18: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY19: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY20: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY21: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY22: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY23: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY24: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY25: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY19: 17; Insert Notes About Rate Set - Date, Origin, Etc FY20: 83.0299; Insert Notes About Rate Set - Date, Origin, Etc FY21: 85.5208; Insert Notes About Rate Set - Date, Origin, Etc FY22: 88.0864; Insert Notes About Rate Set - Date, Origin, Etc FY23: 90.729; Insert Notes About Rate Set - Date, Origin, Etc FY24: 93.4509; Insert Notes About Rate Set - Date, Origin, Etc FY25: 96.2544; Insert Notes About Rate Set - Date, Origin, Etc FY26: 99.1421; Insert Notes About Rate Set - Date, Origin, Etc FY27: 102.1163; Insert Notes About Rate Set - Date, Origin, Etc FY28: 105.1798; Insert Notes About Rate Set - Date, Origin, Etc FY29: 108.3352; Insert Notes About Rate Set - Date, Origin, Etc FY30: 111.5853; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NB3 | Labor_Procurement_NB3 | Labor | Labor_Procurement_NB3 | NEXTII Rates from HT 2/6/19 FY19: 82.2066; NEXTII Rates from HT 2/6/19 FY20: 84.6728; NEXTII Rates from HT 2/6/19 FY21: 87.213; NEXTII Rates from HT 2/6/19 FY22: 89.8294; NEXTII Rates from HT 2/6/19 FY23: 92.5243; NEXTII Rates from HT 2/6/19 FY24: 95.3; NEXTII Rates from HT 2/6/19 FY25: 98.159; NEXTII Rates from HT 2/6/19 FY26: 101.1038; NEXTII Rates from HT 2/6/19 FY27: 104.1369; NEXTII Rates from HT 2/6/19 FY28: 107.261; NEXTII Rates from HT 2/6/19 FY29: 110.4789; NEXTII Rates from HT 2/6/19 FY30: 113.7932; NEXTII Rates from HT 2/6/19 FY31: 117.207; NEXTII Rates from HT 2/6/19 FY32: 120.7232; EPR_FY19 FY33: 124.3449; EPR_FY19 FY34: 128.0753; EPR_FY19 FY35: 131.9175; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 111.0855; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 114.4181; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 117.8506; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 121.3862; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 125.0277; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 128.7786; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 132.6419; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 136.6212; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 140.7198; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 144.9414; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 149.2897; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 153.7684; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 158.3814; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 163.1328; OPS19 FY33: 168.0268; OPS19 FY34: 173.0676; OPS19 FY35: 178.2597; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 83.3034; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 85.8025; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 88.3765; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 91.0278; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 93.7587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 96.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 99.4686; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 102.4526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 105.5262; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 108.692; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 111.9528; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 115.3113; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 118.7707; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 122.3338; EPRSS19 FY33: 126.0038; EPRSS19 FY34: 129.7839; EPRSS19 FY35: 133.6775; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 106.24; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 109.4272; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 112.71; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 116.0913; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 119.5741; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 123.1613; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 126.8561; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 130.6618; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 134.5817; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 138.6191; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 142.7777; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 147.061; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 151.4728; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 156.017; ACT19 FY33: 160.6975; ACT19 FY34: 165.5185; ACT19 FY35: 170.484; Std. Operating Ovhd - FY18 Base Year FY16: 85.2623; Std. Operating Ovhd - FY18 Base Year FY17: 85.2623; Std. Operating Ovhd - FY18 Base Year FY18: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY19: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY20: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY21: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY22: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY23: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY24: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY25: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY19: 18; Insert Notes About Rate Set - Date, Origin, Etc FY20: 83.0299; Insert Notes About Rate Set - Date, Origin, Etc FY21: 85.5208; Insert Notes About Rate Set - Date, Origin, Etc FY22: 88.0864; Insert Notes About Rate Set - Date, Origin, Etc FY23: 90.729; Insert Notes About Rate Set - Date, Origin, Etc FY24: 93.4509; Insert Notes About Rate Set - Date, Origin, Etc FY25: 96.2544; Insert Notes About Rate Set - Date, Origin, Etc FY26: 99.1421; Insert Notes About Rate Set - Date, Origin, Etc FY27: 102.1163; Insert Notes About Rate Set - Date, Origin, Etc FY28: 105.1798; Insert Notes About Rate Set - Date, Origin, Etc FY29: 108.3352; Insert Notes About Rate Set - Date, Origin, Etc FY30: 111.5853; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NB4 | Labor_Human Resources_NB4 | Labor | Labor_Human Resources_NB4 | NEXTII Rates from HT 2/6/19 FY19: 0; NEXTII Rates from HT 2/6/19 FY20: 0; NEXTII Rates from HT 2/6/19 FY21: 0; NEXTII Rates from HT 2/6/19 FY22: 0; NEXTII Rates from HT 2/6/19 FY23: 0; NEXTII Rates from HT 2/6/19 FY24: 0; NEXTII Rates from HT 2/6/19 FY25: 0; NEXTII Rates from HT 2/6/19 FY26: 0; NEXTII Rates from HT 2/6/19 FY27: 0; NEXTII Rates from HT 2/6/19 FY28: 0; NEXTII Rates from HT 2/6/19 FY29: 0; NEXTII Rates from HT 2/6/19 FY30: 0; NEXTII Rates from HT 2/6/19 FY31: 0; NEXTII Rates from HT 2/6/19 FY32: 0; EPR_FY19 FY33: 0; EPR_FY19 FY34: 0; EPR_FY19 FY35: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 0; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 0; OPS19 FY33: 0; OPS19 FY34: 0; OPS19 FY35: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 0; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 0; EPRSS19 FY33: 0; EPRSS19 FY34: 0; EPRSS19 FY35: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 0; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 0; ACT19 FY33: 0; ACT19 FY34: 0; ACT19 FY35: 0; Std. Operating Ovhd - FY18 Base Year FY16: 85.2623; Std. Operating Ovhd - FY18 Base Year FY17: 85.2623; Std. Operating Ovhd - FY18 Base Year FY18: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY19: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY20: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY21: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY22: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY23: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY24: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY25: 85.2623; Insert Notes About Rate Set - Date, Origin, Etc FY19: #N/A; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NE1 | Labor_Electrical Engineer_NE1 | Labor | Labor_Electrical Engineer_NE1 | NEXTII Rates from HT 2/6/19 FY19: 132.0809; NEXTII Rates from HT 2/6/19 FY20: 136.0433; NEXTII Rates from HT 2/6/19 FY21: 140.1246; NEXTII Rates from HT 2/6/19 FY22: 144.3283; NEXTII Rates from HT 2/6/19 FY23: 148.6582; NEXTII Rates from HT 2/6/19 FY24: 153.1179; NEXTII Rates from HT 2/6/19 FY25: 157.7115; NEXTII Rates from HT 2/6/19 FY26: 162.4428; NEXTII Rates from HT 2/6/19 FY27: 167.3161; NEXTII Rates from HT 2/6/19 FY28: 172.3356; NEXTII Rates from HT 2/6/19 FY29: 177.5056; NEXTII Rates from HT 2/6/19 FY30: 182.8308; NEXTII Rates from HT 2/6/19 FY31: 188.3157; NEXTII Rates from HT 2/6/19 FY32: 193.9652; EPR_FY19 FY33: 199.7841; EPR_FY19 FY34: 205.7777; EPR_FY19 FY35: 211.951; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 178.4804; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 183.8348; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 189.3498; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 195.0303; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 200.8812; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 206.9077; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 213.1149; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 219.5083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 226.0936; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 232.8764; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 239.8627; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 247.0586; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 254.4703; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 262.1044; OPS19 FY33: 269.9676; OPS19 FY34: 278.0666; OPS19 FY35: 286.4086; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 133.843; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 137.8583; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 141.994; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 146.2538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 150.6414; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 155.1607; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 159.8155; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 164.61; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 169.5483; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 174.6347; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 179.8738; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 185.27; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 190.8281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 196.5529; EPRSS19 FY33: 202.4495; EPRSS19 FY34: 208.523; EPRSS19 FY35: 214.7787; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 170.6951; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 175.816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 181.0904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 186.5231; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 192.1188; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 197.8824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 203.8189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 209.9334; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 216.2314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 222.7184; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 229.3999; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 236.2819; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 243.3704; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 250.6715; ACT19 FY33: 258.1917; ACT19 FY34: 265.9374; ACT19 FY35: 273.9155; Std. Operating Ovhd - FY18 Base Year FY16: 125.8309; Std. Operating Ovhd - FY18 Base Year FY17: 125.8309; Std. Operating Ovhd - FY18 Base Year FY18: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY21: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY23: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 20; Insert Notes About Rate Set - Date, Origin, Etc FY20: 137.1386; Insert Notes About Rate Set - Date, Origin, Etc FY21: 141.2528; Insert Notes About Rate Set - Date, Origin, Etc FY22: 145.4903; Insert Notes About Rate Set - Date, Origin, Etc FY23: 149.855; Insert Notes About Rate Set - Date, Origin, Etc FY24: 154.3507; Insert Notes About Rate Set - Date, Origin, Etc FY25: 158.9812; Insert Notes About Rate Set - Date, Origin, Etc FY26: 163.7507; Insert Notes About Rate Set - Date, Origin, Etc FY27: 168.6632; Insert Notes About Rate Set - Date, Origin, Etc FY28: 173.7231; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9348; Insert Notes About Rate Set - Date, Origin, Etc FY30: 184.3028; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NE2 | Labor_Electrical Designer_NE2 | Labor | Labor_Electrical Designer_NE2 | NEXTII Rates from HT 2/6/19 FY19: 106.0837; NEXTII Rates from HT 2/6/19 FY20: 109.2662; NEXTII Rates from HT 2/6/19 FY21: 112.5442; NEXTII Rates from HT 2/6/19 FY22: 115.9205; NEXTII Rates from HT 2/6/19 FY23: 119.3981; NEXTII Rates from HT 2/6/19 FY24: 122.98; NEXTII Rates from HT 2/6/19 FY25: 126.6694; NEXTII Rates from HT 2/6/19 FY26: 130.4695; NEXTII Rates from HT 2/6/19 FY27: 134.3836; NEXTII Rates from HT 2/6/19 FY28: 138.4151; NEXTII Rates from HT 2/6/19 FY29: 142.5676; NEXTII Rates from HT 2/6/19 FY30: 146.8446; NEXTII Rates from HT 2/6/19 FY31: 151.2499; NEXTII Rates from HT 2/6/19 FY32: 155.7874; EPR_FY19 FY33: 160.4611; EPR_FY19 FY34: 165.2749; EPR_FY19 FY35: 170.2331; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 143.3505; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 147.651; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 152.0805; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 156.6429; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 161.3422; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 166.1825; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 171.168; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 176.303; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 181.5921; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 187.0398; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 192.651; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 198.4306; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 204.3835; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 210.515; OPS19 FY33: 216.8304; OPS19 FY34: 223.3354; OPS19 FY35: 230.0354; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 107.4989; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 110.7239; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 114.0456; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 117.467; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 120.991; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 124.6207; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 128.3594; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 132.2101; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 136.1764; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 140.2617; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 144.4696; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 148.8037; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 153.2678; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 157.8658; EPRSS19 FY33: 162.6018; EPRSS19 FY34: 167.4799; EPRSS19 FY35: 172.5043; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 137.0976; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 141.2105; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 145.4468; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 149.8102; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 154.3045; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 158.9336; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 163.7017; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 168.6127; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 173.6711; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 178.8812; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 184.2476; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 189.7751; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 195.4683; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 201.3324; ACT19 FY33: 207.3724; ACT19 FY34: 213.5935; ACT19 FY35: 220.0013; Std. Operating Ovhd - FY18 Base Year FY16: 98.8964; Std. Operating Ovhd - FY18 Base Year FY17: 98.8964; Std. Operating Ovhd - FY18 Base Year FY18: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY19: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY20: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY21: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY22: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY23: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY24: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY25: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY19: 21; Insert Notes About Rate Set - Date, Origin, Etc FY20: 108.1414; Insert Notes About Rate Set - Date, Origin, Etc FY21: 111.3857; Insert Notes About Rate Set - Date, Origin, Etc FY22: 114.7272; Insert Notes About Rate Set - Date, Origin, Etc FY23: 118.169; Insert Notes About Rate Set - Date, Origin, Etc FY24: 121.7141; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.3655; Insert Notes About Rate Set - Date, Origin, Etc FY26: 129.1265; Insert Notes About Rate Set - Date, Origin, Etc FY27: 133.0003; Insert Notes About Rate Set - Date, Origin, Etc FY28: 136.9903; Insert Notes About Rate Set - Date, Origin, Etc FY29: 141.1; Insert Notes About Rate Set - Date, Origin, Etc FY30: 145.333; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NE3 | Labor_Electrical Technician_NE3 | Labor | Labor_Electrical Technician_NE3 | NEXTII Rates from HT 2/6/19 FY19: 90.7756; NEXTII Rates from HT 2/6/19 FY20: 93.4989; NEXTII Rates from HT 2/6/19 FY21: 96.3039; NEXTII Rates from HT 2/6/19 FY22: 99.193; NEXTII Rates from HT 2/6/19 FY23: 102.1688; NEXTII Rates from HT 2/6/19 FY24: 105.2338; NEXTII Rates from HT 2/6/19 FY25: 108.3908; NEXTII Rates from HT 2/6/19 FY26: 111.6426; NEXTII Rates from HT 2/6/19 FY27: 114.9918; NEXTII Rates from HT 2/6/19 FY28: 118.4416; NEXTII Rates from HT 2/6/19 FY29: 121.9948; NEXTII Rates from HT 2/6/19 FY30: 125.6547; NEXTII Rates from HT 2/6/19 FY31: 129.4243; NEXTII Rates from HT 2/6/19 FY32: 133.3071; EPR_FY19 FY33: 137.3063; EPR_FY19 FY34: 141.4255; EPR_FY19 FY35: 145.6682; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 122.6648; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 126.3447; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 130.135; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 134.0391; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 138.0603; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 142.2021; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 146.4681; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 150.8622; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 155.388; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 160.0497; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 164.8512; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 169.7967; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 174.8906; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 180.1373; OPS19 FY33: 185.5414; OPS19 FY34: 191.1077; OPS19 FY35: 196.8409; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 91.9867; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 94.7463; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 97.5887; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 100.5163; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 103.5318; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 106.6378; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 109.8369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 113.132; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 116.526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 120.0217; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 123.6224; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 127.3311; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 131.151; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 135.0855; EPRSS19 FY33: 139.1381; EPRSS19 FY34: 143.3122; EPRSS19 FY35: 147.6116; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 117.3141; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 120.8336; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 124.4586; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 128.1923; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 132.0381; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 135.9992; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 140.0792; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 144.2816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 148.6101; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 153.0684; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 157.6604; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 162.3902; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 167.2619; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 172.2798; ACT19 FY33: 177.4482; ACT19 FY34: 182.7716; ACT19 FY35: 188.2548; Std. Operating Ovhd - FY18 Base Year FY16: 94.2254; Std. Operating Ovhd - FY18 Base Year FY17: 94.2254; Std. Operating Ovhd - FY18 Base Year FY18: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY20: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY21: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY23: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY24: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY25: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 22; Insert Notes About Rate Set - Date, Origin, Etc FY20: 89.1179; Insert Notes About Rate Set - Date, Origin, Etc FY21: 91.7915; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.5452; Insert Notes About Rate Set - Date, Origin, Etc FY23: 97.3816; Insert Notes About Rate Set - Date, Origin, Etc FY24: 100.303; Insert Notes About Rate Set - Date, Origin, Etc FY25: 103.3121; Insert Notes About Rate Set - Date, Origin, Etc FY26: 106.4115; Insert Notes About Rate Set - Date, Origin, Etc FY27: 109.6038; Insert Notes About Rate Set - Date, Origin, Etc FY28: 112.8919; Insert Notes About Rate Set - Date, Origin, Etc FY29: 116.2787; Insert Notes About Rate Set - Date, Origin, Etc FY30: 119.7671; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NE4 | Labor_Controls Engineer_NE4 | Labor | Labor_Controls Engineer_NE4 | NEXTII Rates from HT 2/6/19 FY19: 132.0809; NEXTII Rates from HT 2/6/19 FY20: 136.0433; NEXTII Rates from HT 2/6/19 FY21: 140.1246; NEXTII Rates from HT 2/6/19 FY22: 144.3283; NEXTII Rates from HT 2/6/19 FY23: 148.6582; NEXTII Rates from HT 2/6/19 FY24: 153.1179; NEXTII Rates from HT 2/6/19 FY25: 157.7115; NEXTII Rates from HT 2/6/19 FY26: 162.4428; NEXTII Rates from HT 2/6/19 FY27: 167.3161; NEXTII Rates from HT 2/6/19 FY28: 172.3356; NEXTII Rates from HT 2/6/19 FY29: 177.5056; NEXTII Rates from HT 2/6/19 FY30: 182.8308; NEXTII Rates from HT 2/6/19 FY31: 188.3157; NEXTII Rates from HT 2/6/19 FY32: 193.9652; EPR_FY19 FY33: 199.7841; EPR_FY19 FY34: 205.7777; EPR_FY19 FY35: 211.951; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 178.4804; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 183.8348; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 189.3498; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 195.0303; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 200.8812; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 206.9077; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 213.1149; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 219.5083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 226.0936; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 232.8764; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 239.8627; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 247.0586; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 254.4703; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 262.1044; OPS19 FY33: 269.9676; OPS19 FY34: 278.0666; OPS19 FY35: 286.4086; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 133.843; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 137.8583; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 141.994; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 146.2538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 150.6414; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 155.1607; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 159.8155; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 164.61; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 169.5483; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 174.6347; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 179.8738; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 185.27; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 190.8281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 196.5529; EPRSS19 FY33: 202.4495; EPRSS19 FY34: 208.523; EPRSS19 FY35: 214.7787; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 170.6951; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 175.816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 181.0904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 186.5231; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 192.1188; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 197.8824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 203.8189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 209.9334; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 216.2314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 222.7184; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 229.3999; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 236.2819; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 243.3704; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 250.6715; ACT19 FY33: 258.1917; ACT19 FY34: 265.9374; ACT19 FY35: 273.9155; Std. Operating Ovhd - FY18 Base Year FY16: 125.831; Std. Operating Ovhd - FY18 Base Year FY17: 125.831; Std. Operating Ovhd - FY18 Base Year FY18: 125.831; Insert Notes About Rate Set - Date, Origin, Etc FY19: 125.831; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.831; Insert Notes About Rate Set - Date, Origin, Etc FY21: 125.831; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.831; Insert Notes About Rate Set - Date, Origin, Etc FY23: 125.831; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.831; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.831; Insert Notes About Rate Set - Date, Origin, Etc FY19: 23; Insert Notes About Rate Set - Date, Origin, Etc FY20: 137.1386; Insert Notes About Rate Set - Date, Origin, Etc FY21: 141.2528; Insert Notes About Rate Set - Date, Origin, Etc FY22: 145.4903; Insert Notes About Rate Set - Date, Origin, Etc FY23: 149.855; Insert Notes About Rate Set - Date, Origin, Etc FY24: 154.3507; Insert Notes About Rate Set - Date, Origin, Etc FY25: 158.9812; Insert Notes About Rate Set - Date, Origin, Etc FY26: 163.7507; Insert Notes About Rate Set - Date, Origin, Etc FY27: 168.6632; Insert Notes About Rate Set - Date, Origin, Etc FY28: 173.7231; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9348; Insert Notes About Rate Set - Date, Origin, Etc FY30: 184.3028; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO1 | Labor_Mechanical Engineer_NO1 | Labor | Labor_Mechanical Engineer_NO1 | NEXTII Rates from HT 2/6/19 FY19: 128.1939; NEXTII Rates from HT 2/6/19 FY20: 132.0397; NEXTII Rates from HT 2/6/19 FY21: 136.0009; NEXTII Rates from HT 2/6/19 FY22: 140.0809; NEXTII Rates from HT 2/6/19 FY23: 144.2834; NEXTII Rates from HT 2/6/19 FY24: 148.6119; NEXTII Rates from HT 2/6/19 FY25: 153.0702; NEXTII Rates from HT 2/6/19 FY26: 157.6623; NEXTII Rates from HT 2/6/19 FY27: 162.3922; NEXTII Rates from HT 2/6/19 FY28: 167.264; NEXTII Rates from HT 2/6/19 FY29: 172.2819; NEXTII Rates from HT 2/6/19 FY30: 177.4503; NEXTII Rates from HT 2/6/19 FY31: 182.7738; NEXTII Rates from HT 2/6/19 FY32: 188.2571; EPR_FY19 FY33: 193.9048; EPR_FY19 FY34: 199.7219; EPR_FY19 FY35: 205.7136; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 173.2279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 178.4248; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 183.7775; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 189.2908; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 194.9696; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 200.8187; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 206.8432; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 213.0485; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 219.44; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 226.0232; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 232.8039; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 239.788; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 246.9816; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 254.3911; OPS19 FY33: 262.0228; OPS19 FY34: 269.8835; OPS19 FY35: 277.98; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 129.9042; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 133.8013; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 137.8153; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 141.9498; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 146.2083; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 150.5945; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 155.1124; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 159.7657; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 164.5587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 169.4955; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 174.5803; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 179.8177; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 185.2123; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 190.7686; EPRSS19 FY33: 196.4917; EPRSS19 FY34: 202.3864; EPRSS19 FY35: 208.458; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 165.6718; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 170.6419; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 175.7612; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 181.034; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 186.465; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 192.059; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 197.8208; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 203.7554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 209.8681; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 216.1641; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 222.649; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 229.3285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 236.2083; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 243.2946; ACT19 FY33: 250.5934; ACT19 FY34: 258.1112; ACT19 FY35: 265.8546; Std. Operating Ovhd - FY18 Base Year FY16: 111.0442; Std. Operating Ovhd - FY18 Base Year FY17: 111.0442; Std. Operating Ovhd - FY18 Base Year FY18: 111.0442; Insert Notes About Rate Set - Date, Origin, Etc FY19: 111.0442; Insert Notes About Rate Set - Date, Origin, Etc FY20: 111.0442; Insert Notes About Rate Set - Date, Origin, Etc FY21: 111.0442; Insert Notes About Rate Set - Date, Origin, Etc FY22: 111.0442; Insert Notes About Rate Set - Date, Origin, Etc FY23: 111.0442; Insert Notes About Rate Set - Date, Origin, Etc FY24: 111.0442; Insert Notes About Rate Set - Date, Origin, Etc FY25: 111.0442; Insert Notes About Rate Set - Date, Origin, Etc FY19: 24; Insert Notes About Rate Set - Date, Origin, Etc FY20: 132.3036; Insert Notes About Rate Set - Date, Origin, Etc FY21: 136.2727; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.3609; Insert Notes About Rate Set - Date, Origin, Etc FY23: 144.5717; Insert Notes About Rate Set - Date, Origin, Etc FY24: 148.9089; Insert Notes About Rate Set - Date, Origin, Etc FY25: 153.3762; Insert Notes About Rate Set - Date, Origin, Etc FY26: 157.9774; Insert Notes About Rate Set - Date, Origin, Etc FY27: 162.7168; Insert Notes About Rate Set - Date, Origin, Etc FY28: 167.5983; Insert Notes About Rate Set - Date, Origin, Etc FY29: 172.6262; Insert Notes About Rate Set - Date, Origin, Etc FY30: 177.805; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO2 | Labor_Mechanical Designer_NO2 | Labor | Labor_Mechanical Designer_NO2 | NEXTII Rates from HT 2/6/19 FY19: 100.329; NEXTII Rates from HT 2/6/19 FY20: 103.3388; NEXTII Rates from HT 2/6/19 FY21: 106.439; NEXTII Rates from HT 2/6/19 FY22: 109.6322; NEXTII Rates from HT 2/6/19 FY23: 112.9211; NEXTII Rates from HT 2/6/19 FY24: 116.3088; NEXTII Rates from HT 2/6/19 FY25: 119.798; NEXTII Rates from HT 2/6/19 FY26: 123.392; NEXTII Rates from HT 2/6/19 FY27: 127.0937; NEXTII Rates from HT 2/6/19 FY28: 130.9065; NEXTII Rates from HT 2/6/19 FY29: 134.8337; NEXTII Rates from HT 2/6/19 FY30: 138.8787; NEXTII Rates from HT 2/6/19 FY31: 143.0451; NEXTII Rates from HT 2/6/19 FY32: 147.3365; EPR_FY19 FY33: 151.7565; EPR_FY19 FY34: 156.3092; EPR_FY19 FY35: 160.9985; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 135.5741; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 139.6414; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 143.8306; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 148.1455; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 152.5899; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 157.1676; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 161.8826; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 166.7391; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 171.7413; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 176.8935; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 182.2003; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 187.6663; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 193.2963; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 199.0952; OPS19 FY33: 205.068; OPS19 FY34: 211.2201; OPS19 FY35: 217.5567; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 101.6675; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 104.7175; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 107.859; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 111.0948; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 114.4276; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 117.8604; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 121.3963; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 125.0381; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 128.7893; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 132.653; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 136.6326; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 140.7315; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 144.9535; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 149.3021; EPRSS19 FY33: 153.7811; EPRSS19 FY34: 158.3946; EPRSS19 FY35: 163.1464; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 129.6604; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 133.5502; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 137.5567; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 141.6835; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 145.934; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 150.312; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 154.8213; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 159.466; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 164.25; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 169.1775; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 174.2528; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 179.4804; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 184.8648; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 190.4107; ACT19 FY33: 196.123; ACT19 FY34: 202.0067; ACT19 FY35: 208.0669; Std. Operating Ovhd - FY18 Base Year FY16: 94.7713; Std. Operating Ovhd - FY18 Base Year FY17: 94.7713; Std. Operating Ovhd - FY18 Base Year FY18: 94.7713; Insert Notes About Rate Set - Date, Origin, Etc FY19: 94.7713; Insert Notes About Rate Set - Date, Origin, Etc FY20: 94.7713; Insert Notes About Rate Set - Date, Origin, Etc FY21: 94.7713; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.7713; Insert Notes About Rate Set - Date, Origin, Etc FY23: 94.7713; Insert Notes About Rate Set - Date, Origin, Etc FY24: 94.7713; Insert Notes About Rate Set - Date, Origin, Etc FY25: 94.7713; Insert Notes About Rate Set - Date, Origin, Etc FY19: 25; Insert Notes About Rate Set - Date, Origin, Etc FY20: 101.6863; Insert Notes About Rate Set - Date, Origin, Etc FY21: 104.7369; Insert Notes About Rate Set - Date, Origin, Etc FY22: 107.879; Insert Notes About Rate Set - Date, Origin, Etc FY23: 111.1154; Insert Notes About Rate Set - Date, Origin, Etc FY24: 114.4489; Insert Notes About Rate Set - Date, Origin, Etc FY25: 117.8823; Insert Notes About Rate Set - Date, Origin, Etc FY26: 121.4188; Insert Notes About Rate Set - Date, Origin, Etc FY27: 125.0614; Insert Notes About Rate Set - Date, Origin, Etc FY28: 128.8132; Insert Notes About Rate Set - Date, Origin, Etc FY29: 132.6776; Insert Notes About Rate Set - Date, Origin, Etc FY30: 136.6579; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO3 | Labor_Mechanical Technician_NO3 | Labor | Labor_Mechanical Technician_NO3 | NEXTII Rates from HT 2/6/19 FY19: 96.7449; NEXTII Rates from HT 2/6/19 FY20: 99.6472; NEXTII Rates from HT 2/6/19 FY21: 102.6366; NEXTII Rates from HT 2/6/19 FY22: 105.7157; NEXTII Rates from HT 2/6/19 FY23: 108.8872; NEXTII Rates from HT 2/6/19 FY24: 112.1538; NEXTII Rates from HT 2/6/19 FY25: 115.5184; NEXTII Rates from HT 2/6/19 FY26: 118.984; NEXTII Rates from HT 2/6/19 FY27: 122.5535; NEXTII Rates from HT 2/6/19 FY28: 126.2301; NEXTII Rates from HT 2/6/19 FY29: 130.017; NEXTII Rates from HT 2/6/19 FY30: 133.9175; NEXTII Rates from HT 2/6/19 FY31: 137.9351; NEXTII Rates from HT 2/6/19 FY32: 142.0731; EPR_FY19 FY33: 146.3353; EPR_FY19 FY34: 150.7254; EPR_FY19 FY35: 155.2471; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 130.731; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 134.6529; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 138.6925; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 142.8533; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 147.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 151.553; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 156.0996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 160.7826; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 165.6061; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 170.5743; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 175.6915; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 180.9623; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 186.3911; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 191.9829; OPS19 FY33: 197.7423; OPS19 FY34: 203.6746; OPS19 FY35: 209.7849; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 98.0356; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 100.9766; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 104.0059; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 107.1261; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 110.3399; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 113.6501; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 117.0596; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 120.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 124.1885; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 127.9142; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 131.7516; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 135.7041; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 139.7753; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 143.9685; EPRSS19 FY33: 148.2876; EPRSS19 FY34: 152.7362; EPRSS19 FY35: 157.3183; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 125.0285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 128.7794; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 132.6428; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 136.6221; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 140.7207; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 144.9423; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 149.2906; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 153.7693; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 158.3824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 163.1339; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 168.0279; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 173.0687; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 178.2608; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 183.6086; ACT19 FY33: 189.1169; ACT19 FY34: 194.7904; ACT19 FY35: 200.6341; Std. Operating Ovhd - FY18 Base Year FY16: 86.7334; Std. Operating Ovhd - FY18 Base Year FY17: 86.7334; Std. Operating Ovhd - FY18 Base Year FY18: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY20: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY21: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY22: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY23: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY24: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY25: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 26; Insert Notes About Rate Set - Date, Origin, Etc FY20: 96.826; Insert Notes About Rate Set - Date, Origin, Etc FY21: 99.7308; Insert Notes About Rate Set - Date, Origin, Etc FY22: 102.7228; Insert Notes About Rate Set - Date, Origin, Etc FY23: 105.8044; Insert Notes About Rate Set - Date, Origin, Etc FY24: 108.9786; Insert Notes About Rate Set - Date, Origin, Etc FY25: 112.2479; Insert Notes About Rate Set - Date, Origin, Etc FY26: 115.6154; Insert Notes About Rate Set - Date, Origin, Etc FY27: 119.0838; Insert Notes About Rate Set - Date, Origin, Etc FY28: 122.6563; Insert Notes About Rate Set - Date, Origin, Etc FY29: 126.336; Insert Notes About Rate Set - Date, Origin, Etc FY30: 130.1261; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO4 | Labor_Facilities Technician_NO4 | Labor | Labor_Facilities Technician_NO4 | NEXTII Rates from HT 2/6/19 FY19: 73.6377; NEXTII Rates from HT 2/6/19 FY20: 75.8468; NEXTII Rates from HT 2/6/19 FY21: 78.1222; NEXTII Rates from HT 2/6/19 FY22: 80.4659; NEXTII Rates from HT 2/6/19 FY23: 82.8798; NEXTII Rates from HT 2/6/19 FY24: 85.3662; NEXTII Rates from HT 2/6/19 FY25: 87.9272; NEXTII Rates from HT 2/6/19 FY26: 90.565; NEXTII Rates from HT 2/6/19 FY27: 93.282; NEXTII Rates from HT 2/6/19 FY28: 96.0805; NEXTII Rates from HT 2/6/19 FY29: 98.9629; NEXTII Rates from HT 2/6/19 FY30: 101.9318; NEXTII Rates from HT 2/6/19 FY31: 104.9897; NEXTII Rates from HT 2/6/19 FY32: 108.1394; EPR_FY19 FY33: 111.3836; EPR_FY19 FY34: 114.7251; EPR_FY19 FY35: 118.1668; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 99.5063; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 102.4915; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 105.5662; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 108.7332; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 111.9952; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 115.3551; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 118.8157; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 122.3802; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 126.0516; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 129.8332; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 133.7281; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 137.74; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 141.8722; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 146.1284; OPS19 FY33: 150.5122; OPS19 FY34: 155.0276; OPS19 FY35: 159.6784; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 74.6201; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 76.8587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 79.1644; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 81.5394; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 83.9856; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 86.5051; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 89.1003; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 91.7733; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 94.5265; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 97.3623; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 100.2831; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 103.2916; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 106.3904; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 109.5821; EPRSS19 FY33: 112.8696; EPRSS19 FY34: 116.2556; EPRSS19 FY35: 119.7433; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 95.1659; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 98.0208; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 100.9615; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 103.9903; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 107.11; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 110.3233; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 113.633; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 117.042; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 120.5533; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 124.1699; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 127.895; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 131.7318; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 135.6838; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 139.7543; ACT19 FY33: 143.9469; ACT19 FY34: 148.2653; ACT19 FY35: 152.7133; Std. Operating Ovhd - FY18 Base Year FY16: 119.5979; Std. Operating Ovhd - FY18 Base Year FY17: 119.5979; Std. Operating Ovhd - FY18 Base Year FY18: 119.5979; Insert Notes About Rate Set - Date, Origin, Etc FY19: 119.5979; Insert Notes About Rate Set - Date, Origin, Etc FY20: 119.5979; Insert Notes About Rate Set - Date, Origin, Etc FY21: 119.5979; Insert Notes About Rate Set - Date, Origin, Etc FY22: 119.5979; Insert Notes About Rate Set - Date, Origin, Etc FY23: 119.5979; Insert Notes About Rate Set - Date, Origin, Etc FY24: 119.5979; Insert Notes About Rate Set - Date, Origin, Etc FY25: 119.5979; Insert Notes About Rate Set - Date, Origin, Etc FY19: 27; Insert Notes About Rate Set - Date, Origin, Etc FY20: 76.1951; Insert Notes About Rate Set - Date, Origin, Etc FY21: 78.481; Insert Notes About Rate Set - Date, Origin, Etc FY22: 80.8354; Insert Notes About Rate Set - Date, Origin, Etc FY23: 83.2605; Insert Notes About Rate Set - Date, Origin, Etc FY24: 85.7583; Insert Notes About Rate Set - Date, Origin, Etc FY25: 88.3311; Insert Notes About Rate Set - Date, Origin, Etc FY26: 90.981; Insert Notes About Rate Set - Date, Origin, Etc FY27: 93.7104; Insert Notes About Rate Set - Date, Origin, Etc FY28: 96.5217; Insert Notes About Rate Set - Date, Origin, Etc FY29: 99.4174; Insert Notes About Rate Set - Date, Origin, Etc FY30: 102.3999; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO5 | Labor_Other Technician_NO5 | Labor | Labor_Other Technician_NO5 | NEXTII Rates from HT 2/6/19 FY19: 97.8554; NEXTII Rates from HT 2/6/19 FY20: 100.7911; NEXTII Rates from HT 2/6/19 FY21: 103.8148; NEXTII Rates from HT 2/6/19 FY22: 106.9293; NEXTII Rates from HT 2/6/19 FY23: 110.1372; NEXTII Rates from HT 2/6/19 FY24: 113.4413; NEXTII Rates from HT 2/6/19 FY25: 116.8445; NEXTII Rates from HT 2/6/19 FY26: 120.3498; NEXTII Rates from HT 2/6/19 FY27: 123.9603; NEXTII Rates from HT 2/6/19 FY28: 127.6791; NEXTII Rates from HT 2/6/19 FY29: 131.5095; NEXTII Rates from HT 2/6/19 FY30: 135.4548; NEXTII Rates from HT 2/6/19 FY31: 139.5184; NEXTII Rates from HT 2/6/19 FY32: 143.704; EPR_FY19 FY33: 148.0151; EPR_FY19 FY34: 152.4556; EPR_FY19 FY35: 157.0292; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 132.2317; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 136.1986; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 140.2846; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 144.4931; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 148.8279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 153.2928; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 157.8915; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 162.6283; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 167.5071; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 172.5324; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 177.7083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 183.0396; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 188.5308; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 194.1867; OPS19 FY33: 200.0123; OPS19 FY34: 206.0127; OPS19 FY35: 212.193; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 99.1609; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 102.1358; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 105.1998; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 108.3558; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 111.6065; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 114.9547; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 118.4033; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 121.9554; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 125.6141; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 129.3825; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 133.264; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 137.2619; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 141.3798; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 145.6212; EPRSS19 FY33: 149.9898; EPRSS19 FY34: 154.4895; EPRSS19 FY35: 159.1242; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 126.4638; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 130.2577; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 134.1654; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 138.1904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 142.3361; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 146.6062; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 151.0044; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 155.5345; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 160.2005; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 165.0065; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 169.9567; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 175.0554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 180.3071; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 185.7163; ACT19 FY33: 191.2878; ACT19 FY34: 197.0264; ACT19 FY35: 202.9372; Std. Operating Ovhd - FY18 Base Year FY16: 94.65; Std. Operating Ovhd - FY18 Base Year FY17: 94.65; Std. Operating Ovhd - FY18 Base Year FY18: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY19: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY20: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY21: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY23: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY24: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY25: 94.65; Insert Notes About Rate Set - Date, Origin, Etc FY19: 28; Insert Notes About Rate Set - Date, Origin, Etc FY20: 98.2563; Insert Notes About Rate Set - Date, Origin, Etc FY21: 101.204; Insert Notes About Rate Set - Date, Origin, Etc FY22: 104.2401; Insert Notes About Rate Set - Date, Origin, Etc FY23: 107.3673; Insert Notes About Rate Set - Date, Origin, Etc FY24: 110.5883; Insert Notes About Rate Set - Date, Origin, Etc FY25: 113.906; Insert Notes About Rate Set - Date, Origin, Etc FY26: 117.3231; Insert Notes About Rate Set - Date, Origin, Etc FY27: 120.8428; Insert Notes About Rate Set - Date, Origin, Etc FY28: 124.4681; Insert Notes About Rate Set - Date, Origin, Etc FY29: 128.2022; Insert Notes About Rate Set - Date, Origin, Etc FY30: 132.0482; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO6 | Labor_ME - D&I Engineer_NO6 | Labor | Labor_ME - D&I Engineer_NO6 | NEXTII Rates from HT 2/6/19 FY19: 128.1939; NEXTII Rates from HT 2/6/19 FY20: 132.0397; NEXTII Rates from HT 2/6/19 FY21: 136.0009; NEXTII Rates from HT 2/6/19 FY22: 140.0809; NEXTII Rates from HT 2/6/19 FY23: 144.2834; NEXTII Rates from HT 2/6/19 FY24: 148.6119; NEXTII Rates from HT 2/6/19 FY25: 153.0702; NEXTII Rates from HT 2/6/19 FY26: 157.6623; NEXTII Rates from HT 2/6/19 FY27: 162.3922; NEXTII Rates from HT 2/6/19 FY28: 167.264; NEXTII Rates from HT 2/6/19 FY29: 172.2819; NEXTII Rates from HT 2/6/19 FY30: 177.4503; NEXTII Rates from HT 2/6/19 FY31: 182.7738; NEXTII Rates from HT 2/6/19 FY32: 188.2571; EPR_FY19 FY33: 193.9048; EPR_FY19 FY34: 199.7219; EPR_FY19 FY35: 205.7136; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 173.2279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 178.4248; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 183.7775; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 189.2908; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 194.9696; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 200.8187; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 206.8432; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 213.0485; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 219.44; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 226.0232; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 232.8039; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 239.788; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 246.9816; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 254.3911; OPS19 FY33: 262.0228; OPS19 FY34: 269.8835; OPS19 FY35: 277.98; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 129.9042; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 133.8013; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 137.8153; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 141.9498; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 146.2083; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 150.5945; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 155.1124; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 159.7657; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 164.5587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 169.4955; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 174.5803; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 179.8177; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 185.2123; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 190.7686; EPRSS19 FY33: 196.4917; EPRSS19 FY34: 202.3864; EPRSS19 FY35: 208.458; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 165.6718; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 170.6419; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 175.7612; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 181.034; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 186.465; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 192.059; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 197.8208; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 203.7554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 209.8681; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 216.1641; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 222.649; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 229.3285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 236.2083; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 243.2946; ACT19 FY33: 250.5934; ACT19 FY34: 258.1112; ACT19 FY35: 265.8546; Std. Operating Ovhd - FY18 Base Year FY16: 111.0443; Std. Operating Ovhd - FY18 Base Year FY17: 111.0443; Std. Operating Ovhd - FY18 Base Year FY18: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY20: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY21: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY22: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY23: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY24: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY25: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 29; Insert Notes About Rate Set - Date, Origin, Etc FY20: 132.3036; Insert Notes About Rate Set - Date, Origin, Etc FY21: 136.2727; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.3609; Insert Notes About Rate Set - Date, Origin, Etc FY23: 144.5717; Insert Notes About Rate Set - Date, Origin, Etc FY24: 148.9089; Insert Notes About Rate Set - Date, Origin, Etc FY25: 153.3762; Insert Notes About Rate Set - Date, Origin, Etc FY26: 157.9774; Insert Notes About Rate Set - Date, Origin, Etc FY27: 162.7168; Insert Notes About Rate Set - Date, Origin, Etc FY28: 167.5983; Insert Notes About Rate Set - Date, Origin, Etc FY29: 172.6262; Insert Notes About Rate Set - Date, Origin, Etc FY30: 177.805; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO7 | Labor_ME - D&I Technician_NO7 | Labor | Labor_ME - D&I Technician_NO7 | NEXTII Rates from HT 2/6/19 FY19: 96.7449; NEXTII Rates from HT 2/6/19 FY20: 99.6472; NEXTII Rates from HT 2/6/19 FY21: 102.6366; NEXTII Rates from HT 2/6/19 FY22: 105.7157; NEXTII Rates from HT 2/6/19 FY23: 108.8872; NEXTII Rates from HT 2/6/19 FY24: 112.1538; NEXTII Rates from HT 2/6/19 FY25: 115.5184; NEXTII Rates from HT 2/6/19 FY26: 118.984; NEXTII Rates from HT 2/6/19 FY27: 122.5535; NEXTII Rates from HT 2/6/19 FY28: 126.2301; NEXTII Rates from HT 2/6/19 FY29: 130.017; NEXTII Rates from HT 2/6/19 FY30: 133.9175; NEXTII Rates from HT 2/6/19 FY31: 137.9351; NEXTII Rates from HT 2/6/19 FY32: 142.0731; EPR_FY19 FY33: 146.3353; EPR_FY19 FY34: 150.7254; EPR_FY19 FY35: 155.2471; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 130.731; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 134.6529; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 138.6925; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 142.8533; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 147.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 151.553; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 156.0996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 160.7826; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 165.6061; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 170.5743; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 175.6915; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 180.9623; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 186.3911; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 191.9829; OPS19 FY33: 197.7423; OPS19 FY34: 203.6746; OPS19 FY35: 209.7849; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 98.0356; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 100.9766; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 104.0059; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 107.1261; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 110.3399; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 113.6501; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 117.0596; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 120.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 124.1885; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 127.9142; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 131.7516; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 135.7041; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 139.7753; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 143.9685; EPRSS19 FY33: 148.2876; EPRSS19 FY34: 152.7362; EPRSS19 FY35: 157.3183; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 125.0285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 128.7794; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 132.6428; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 136.6221; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 140.7207; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 144.9423; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 149.2906; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 153.7693; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 158.3824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 163.1339; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 168.0279; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 173.0687; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 178.2608; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 183.6086; ACT19 FY33: 189.1169; ACT19 FY34: 194.7904; ACT19 FY35: 200.6341; Std. Operating Ovhd - FY18 Base Year FY16: 86.7334; Std. Operating Ovhd - FY18 Base Year FY17: 86.7334; Std. Operating Ovhd - FY18 Base Year FY18: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY20: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY21: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY22: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY23: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY24: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY25: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 30; Insert Notes About Rate Set - Date, Origin, Etc FY20: 96.826; Insert Notes About Rate Set - Date, Origin, Etc FY21: 99.7308; Insert Notes About Rate Set - Date, Origin, Etc FY22: 102.7228; Insert Notes About Rate Set - Date, Origin, Etc FY23: 105.8044; Insert Notes About Rate Set - Date, Origin, Etc FY24: 108.9786; Insert Notes About Rate Set - Date, Origin, Etc FY25: 112.2479; Insert Notes About Rate Set - Date, Origin, Etc FY26: 115.6154; Insert Notes About Rate Set - Date, Origin, Etc FY27: 119.0838; Insert Notes About Rate Set - Date, Origin, Etc FY28: 122.6563; Insert Notes About Rate Set - Date, Origin, Etc FY29: 126.336; Insert Notes About Rate Set - Date, Origin, Etc FY30: 130.1261; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO8 | Labor_ME - Insertion Device Engineer_NO8 | Labor | Labor_ME - Insertion Device Engineer_NO8 | NEXTII Rates from HT 2/6/19 FY19: 128.1939; NEXTII Rates from HT 2/6/19 FY20: 132.0397; NEXTII Rates from HT 2/6/19 FY21: 136.0009; NEXTII Rates from HT 2/6/19 FY22: 140.0809; NEXTII Rates from HT 2/6/19 FY23: 144.2834; NEXTII Rates from HT 2/6/19 FY24: 148.6119; NEXTII Rates from HT 2/6/19 FY25: 153.0702; NEXTII Rates from HT 2/6/19 FY26: 157.6623; NEXTII Rates from HT 2/6/19 FY27: 162.3922; NEXTII Rates from HT 2/6/19 FY28: 167.264; NEXTII Rates from HT 2/6/19 FY29: 172.2819; NEXTII Rates from HT 2/6/19 FY30: 177.4503; NEXTII Rates from HT 2/6/19 FY31: 182.7738; NEXTII Rates from HT 2/6/19 FY32: 188.2571; EPR_FY19 FY33: 193.9048; EPR_FY19 FY34: 199.7219; EPR_FY19 FY35: 205.7136; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 173.2279; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 178.4248; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 183.7775; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 189.2908; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 194.9696; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 200.8187; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 206.8432; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 213.0485; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 219.44; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 226.0232; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 232.8039; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 239.788; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 246.9816; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 254.3911; OPS19 FY33: 262.0228; OPS19 FY34: 269.8835; OPS19 FY35: 277.98; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 129.9042; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 133.8013; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 137.8153; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 141.9498; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 146.2083; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 150.5945; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 155.1124; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 159.7657; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 164.5587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 169.4955; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 174.5803; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 179.8177; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 185.2123; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 190.7686; EPRSS19 FY33: 196.4917; EPRSS19 FY34: 202.3864; EPRSS19 FY35: 208.458; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 165.6718; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 170.6419; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 175.7612; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 181.034; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 186.465; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 192.059; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 197.8208; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 203.7554; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 209.8681; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 216.1641; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 222.649; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 229.3285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 236.2083; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 243.2946; ACT19 FY33: 250.5934; ACT19 FY34: 258.1112; ACT19 FY35: 265.8546; Std. Operating Ovhd - FY18 Base Year FY16: 111.0443; Std. Operating Ovhd - FY18 Base Year FY17: 111.0443; Std. Operating Ovhd - FY18 Base Year FY18: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY20: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY21: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY22: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY23: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY24: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY25: 111.0443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 31; Insert Notes About Rate Set - Date, Origin, Etc FY20: 132.3036; Insert Notes About Rate Set - Date, Origin, Etc FY21: 136.2727; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.3609; Insert Notes About Rate Set - Date, Origin, Etc FY23: 144.5717; Insert Notes About Rate Set - Date, Origin, Etc FY24: 148.9089; Insert Notes About Rate Set - Date, Origin, Etc FY25: 153.3762; Insert Notes About Rate Set - Date, Origin, Etc FY26: 157.9774; Insert Notes About Rate Set - Date, Origin, Etc FY27: 162.7168; Insert Notes About Rate Set - Date, Origin, Etc FY28: 167.5983; Insert Notes About Rate Set - Date, Origin, Etc FY29: 172.6262; Insert Notes About Rate Set - Date, Origin, Etc FY30: 177.805; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NO9 | Labor_ME - Insertion Device Technician_NO9 | Labor | Labor_ME - Insertion Device Technician_NO9 | NEXTII Rates from HT 2/6/19 FY19: 96.7449; NEXTII Rates from HT 2/6/19 FY20: 99.6472; NEXTII Rates from HT 2/6/19 FY21: 102.6366; NEXTII Rates from HT 2/6/19 FY22: 105.7157; NEXTII Rates from HT 2/6/19 FY23: 108.8872; NEXTII Rates from HT 2/6/19 FY24: 112.1538; NEXTII Rates from HT 2/6/19 FY25: 115.5184; NEXTII Rates from HT 2/6/19 FY26: 118.984; NEXTII Rates from HT 2/6/19 FY27: 122.5535; NEXTII Rates from HT 2/6/19 FY28: 126.2301; NEXTII Rates from HT 2/6/19 FY29: 130.017; NEXTII Rates from HT 2/6/19 FY30: 133.9175; NEXTII Rates from HT 2/6/19 FY31: 137.9351; NEXTII Rates from HT 2/6/19 FY32: 142.0731; EPR_FY19 FY33: 146.3353; EPR_FY19 FY34: 150.7254; EPR_FY19 FY35: 155.2471; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 130.731; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 134.6529; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 138.6925; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 142.8533; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 147.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 151.553; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 156.0996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 160.7826; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 165.6061; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 170.5743; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 175.6915; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 180.9623; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 186.3911; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 191.9829; OPS19 FY33: 197.7423; OPS19 FY34: 203.6746; OPS19 FY35: 209.7849; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 98.0356; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 100.9766; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 104.0059; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 107.1261; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 110.3399; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 113.6501; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 117.0596; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 120.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 124.1885; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 127.9142; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 131.7516; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 135.7041; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 139.7753; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 143.9685; EPRSS19 FY33: 148.2876; EPRSS19 FY34: 152.7362; EPRSS19 FY35: 157.3183; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 125.0285; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 128.7794; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 132.6428; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 136.6221; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 140.7207; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 144.9423; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 149.2906; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 153.7693; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 158.3824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 163.1339; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 168.0279; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 173.0687; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 178.2608; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 183.6086; ACT19 FY33: 189.1169; ACT19 FY34: 194.7904; ACT19 FY35: 200.6341; Std. Operating Ovhd - FY18 Base Year FY16: 86.7334; Std. Operating Ovhd - FY18 Base Year FY17: 86.7334; Std. Operating Ovhd - FY18 Base Year FY18: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY20: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY21: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY22: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY23: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY24: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY25: 86.7334; Insert Notes About Rate Set - Date, Origin, Etc FY19: 32; Insert Notes About Rate Set - Date, Origin, Etc FY20: 96.826; Insert Notes About Rate Set - Date, Origin, Etc FY21: 99.7308; Insert Notes About Rate Set - Date, Origin, Etc FY22: 102.7228; Insert Notes About Rate Set - Date, Origin, Etc FY23: 105.8044; Insert Notes About Rate Set - Date, Origin, Etc FY24: 108.9786; Insert Notes About Rate Set - Date, Origin, Etc FY25: 112.2479; Insert Notes About Rate Set - Date, Origin, Etc FY26: 115.6154; Insert Notes About Rate Set - Date, Origin, Etc FY27: 119.0838; Insert Notes About Rate Set - Date, Origin, Etc FY28: 122.6563; Insert Notes About Rate Set - Date, Origin, Etc FY29: 126.336; Insert Notes About Rate Set - Date, Origin, Etc FY30: 130.1261; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NS1 | Labor_Scientist_NS1 | Labor | Labor_Scientist_NS1 | NEXTII Rates from HT 2/6/19 FY19: 165.5112; NEXTII Rates from HT 2/6/19 FY20: 170.4766; NEXTII Rates from HT 2/6/19 FY21: 175.5909; NEXTII Rates from HT 2/6/19 FY22: 180.8586; NEXTII Rates from HT 2/6/19 FY23: 186.2843; NEXTII Rates from HT 2/6/19 FY24: 191.8729; NEXTII Rates from HT 2/6/19 FY25: 197.6291; NEXTII Rates from HT 2/6/19 FY26: 203.5579; NEXTII Rates from HT 2/6/19 FY27: 209.6647; NEXTII Rates from HT 2/6/19 FY28: 215.9546; NEXTII Rates from HT 2/6/19 FY29: 222.4332; NEXTII Rates from HT 2/6/19 FY30: 229.1062; NEXTII Rates from HT 2/6/19 FY31: 235.9794; NEXTII Rates from HT 2/6/19 FY32: 243.0588; EPR_FY19 FY33: 250.3506; EPR_FY19 FY34: 257.8611; EPR_FY19 FY35: 265.5969; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 223.6547; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 230.3643; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 237.2753; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 244.3935; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 251.7253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 259.2771; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 267.0554; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 275.0671; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 283.3191; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 291.8186; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 300.5732; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 309.5904; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 318.8781; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 328.4445; OPS19 FY33: 338.2978; OPS19 FY34: 348.4467; OPS19 FY35: 358.9001; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 167.7193; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 172.7509; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 177.9334; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 183.2714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 188.7696; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 194.4327; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 200.2657; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 206.2736; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 212.4618; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 218.8357; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 225.4008; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 232.1628; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 239.1277; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 246.3015; EPRSS19 FY33: 253.6905; EPRSS19 FY34: 261.3013; EPRSS19 FY35: 269.1403; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 213.8989; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 220.3159; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 226.9254; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 233.7331; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 240.7451; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 247.9675; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 255.4065; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 263.0687; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 270.9608; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 279.0896; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 287.4623; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 296.0861; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 304.9687; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 314.1178; ACT19 FY33: 323.5413; ACT19 FY34: 333.2476; ACT19 FY35: 343.245; Std. Operating Ovhd - FY18 Base Year FY16: 166.5815; Std. Operating Ovhd - FY18 Base Year FY17: 166.5815; Std. Operating Ovhd - FY18 Base Year FY18: 166.5815; Insert Notes About Rate Set - Date, Origin, Etc FY19: 166.5815; Insert Notes About Rate Set - Date, Origin, Etc FY20: 166.5815; Insert Notes About Rate Set - Date, Origin, Etc FY21: 166.5815; Insert Notes About Rate Set - Date, Origin, Etc FY22: 166.5815; Insert Notes About Rate Set - Date, Origin, Etc FY23: 166.5815; Insert Notes About Rate Set - Date, Origin, Etc FY24: 166.5815; Insert Notes About Rate Set - Date, Origin, Etc FY25: 166.5815; Insert Notes About Rate Set - Date, Origin, Etc FY19: 33; Insert Notes About Rate Set - Date, Origin, Etc FY20: 167.7432; Insert Notes About Rate Set - Date, Origin, Etc FY21: 172.7755; Insert Notes About Rate Set - Date, Origin, Etc FY22: 177.9588; Insert Notes About Rate Set - Date, Origin, Etc FY23: 183.2975; Insert Notes About Rate Set - Date, Origin, Etc FY24: 188.7965; Insert Notes About Rate Set - Date, Origin, Etc FY25: 194.4604; Insert Notes About Rate Set - Date, Origin, Etc FY26: 200.2942; Insert Notes About Rate Set - Date, Origin, Etc FY27: 206.303; Insert Notes About Rate Set - Date, Origin, Etc FY28: 212.4921; Insert Notes About Rate Set - Date, Origin, Etc FY29: 218.8669; Insert Notes About Rate Set - Date, Origin, Etc FY30: 225.4329; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NS2 | Labor_Assistant/Associate Scientist_NS2 | Labor | Labor_Assistant/Associate Scientist_NS2 | NEXTII Rates from HT 2/6/19 FY19: 116.4321; NEXTII Rates from HT 2/6/19 FY20: 119.925; NEXTII Rates from HT 2/6/19 FY21: 123.5228; NEXTII Rates from HT 2/6/19 FY22: 127.2285; NEXTII Rates from HT 2/6/19 FY23: 131.0453; NEXTII Rates from HT 2/6/19 FY24: 134.9767; NEXTII Rates from HT 2/6/19 FY25: 139.026; NEXTII Rates from HT 2/6/19 FY26: 143.1968; NEXTII Rates from HT 2/6/19 FY27: 147.4927; NEXTII Rates from HT 2/6/19 FY28: 151.9174; NEXTII Rates from HT 2/6/19 FY29: 156.475; NEXTII Rates from HT 2/6/19 FY30: 161.1692; NEXTII Rates from HT 2/6/19 FY31: 166.0043; NEXTII Rates from HT 2/6/19 FY32: 170.9844; EPR_FY19 FY33: 176.1139; EPR_FY19 FY34: 181.3974; EPR_FY19 FY35: 186.8393; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 157.3342; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 162.0542; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 166.9159; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 171.9233; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 177.081; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 182.3935; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 187.8653; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 193.5012; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 199.3063; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 205.2855; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 211.444; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 217.7873; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 224.321; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 231.0506; OPS19 FY33: 237.9821; OPS19 FY34: 245.1216; OPS19 FY35: 252.4752; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 117.9854; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 121.525; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 125.1707; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 128.9258; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 132.7936; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 136.7774; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 140.8807; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 145.1072; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 149.4604; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 153.9442; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 158.5625; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 163.3194; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 168.219; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 173.2655; EPRSS19 FY33: 178.4635; EPRSS19 FY34: 183.8174; EPRSS19 FY35: 189.3319; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 150.4713; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 154.9855; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 159.635; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 164.4241; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 169.3568; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 174.4375; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 179.6706; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 185.0608; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 190.6126; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 196.331; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 202.2209; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 208.2875; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 214.5361; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 220.9722; ACT19 FY33: 227.6014; ACT19 FY34: 234.4294; ACT19 FY35: 241.4623; Std. Operating Ovhd - FY18 Base Year FY16: 117.4443; Std. Operating Ovhd - FY18 Base Year FY17: 117.4443; Std. Operating Ovhd - FY18 Base Year FY18: 117.4443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 117.4443; Insert Notes About Rate Set - Date, Origin, Etc FY20: 117.4443; Insert Notes About Rate Set - Date, Origin, Etc FY21: 117.4443; Insert Notes About Rate Set - Date, Origin, Etc FY22: 117.4443; Insert Notes About Rate Set - Date, Origin, Etc FY23: 117.4443; Insert Notes About Rate Set - Date, Origin, Etc FY24: 117.4443; Insert Notes About Rate Set - Date, Origin, Etc FY25: 117.4443; Insert Notes About Rate Set - Date, Origin, Etc FY19: 34; Insert Notes About Rate Set - Date, Origin, Etc FY20: 118.3556; Insert Notes About Rate Set - Date, Origin, Etc FY21: 121.9063; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.5635; Insert Notes About Rate Set - Date, Origin, Etc FY23: 129.3304; Insert Notes About Rate Set - Date, Origin, Etc FY24: 133.2103; Insert Notes About Rate Set - Date, Origin, Etc FY25: 137.2066; Insert Notes About Rate Set - Date, Origin, Etc FY26: 141.3228; Insert Notes About Rate Set - Date, Origin, Etc FY27: 145.5625; Insert Notes About Rate Set - Date, Origin, Etc FY28: 149.9293; Insert Notes About Rate Set - Date, Origin, Etc FY29: 154.4272; Insert Notes About Rate Set - Date, Origin, Etc FY30: 159.06; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NS3 | Labor_Scientific Associate_NS3 | Labor | Labor_Scientific Associate_NS3 | NEXTII Rates from HT 2/6/19 FY19: 103.7742; NEXTII Rates from HT 2/6/19 FY20: 106.8874; NEXTII Rates from HT 2/6/19 FY21: 110.0941; NEXTII Rates from HT 2/6/19 FY22: 113.3969; NEXTII Rates from HT 2/6/19 FY23: 116.7988; NEXTII Rates from HT 2/6/19 FY24: 120.3028; NEXTII Rates from HT 2/6/19 FY25: 123.9118; NEXTII Rates from HT 2/6/19 FY26: 127.6292; NEXTII Rates from HT 2/6/19 FY27: 131.4581; NEXTII Rates from HT 2/6/19 FY28: 135.4018; NEXTII Rates from HT 2/6/19 FY29: 139.4639; NEXTII Rates from HT 2/6/19 FY30: 143.6478; NEXTII Rates from HT 2/6/19 FY31: 147.9572; NEXTII Rates from HT 2/6/19 FY32: 152.3959; EPR_FY19 FY33: 156.9678; EPR_FY19 FY34: 161.6768; EPR_FY19 FY35: 166.5271; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 140.2297; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 144.4366; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 148.7697; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 153.2328; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 157.8298; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 162.5647; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 167.4416; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 172.4648; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 177.6388; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 182.968; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 188.457; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 194.1107; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 199.934; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 205.932; OPS19 FY33: 212.11; OPS19 FY34: 218.4733; OPS19 FY35: 225.0275; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 105.1587; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 108.3134; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 111.5628; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 114.9097; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 118.357; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 121.9077; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 125.565; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 129.3319; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 133.2119; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 137.2082; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 141.3245; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 145.5642; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 149.9311; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 154.4291; EPRSS19 FY33: 159.0619; EPRSS19 FY34: 163.8338; EPRSS19 FY35: 168.7488; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 134.1129; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 138.1363; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 142.2804; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 146.5488; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 150.9453; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 155.4736; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 160.1378; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 164.942; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 169.8902; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 174.9869; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 180.2365; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 185.6436; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 191.213; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 196.9493; ACT19 FY33: 202.8578; ACT19 FY34: 208.9436; ACT19 FY35: 215.2119; Std. Operating Ovhd - FY18 Base Year FY16: 93.3154; Std. Operating Ovhd - FY18 Base Year FY17: 93.3154; Std. Operating Ovhd - FY18 Base Year FY18: 93.3154; Insert Notes About Rate Set - Date, Origin, Etc FY19: 93.3154; Insert Notes About Rate Set - Date, Origin, Etc FY20: 93.3154; Insert Notes About Rate Set - Date, Origin, Etc FY21: 93.3154; Insert Notes About Rate Set - Date, Origin, Etc FY22: 93.3154; Insert Notes About Rate Set - Date, Origin, Etc FY23: 93.3154; Insert Notes About Rate Set - Date, Origin, Etc FY24: 93.3154; Insert Notes About Rate Set - Date, Origin, Etc FY25: 93.3154; Insert Notes About Rate Set - Date, Origin, Etc FY19: 35; Insert Notes About Rate Set - Date, Origin, Etc FY20: 106.0657; Insert Notes About Rate Set - Date, Origin, Etc FY21: 109.2476; Insert Notes About Rate Set - Date, Origin, Etc FY22: 112.5251; Insert Notes About Rate Set - Date, Origin, Etc FY23: 115.9008; Insert Notes About Rate Set - Date, Origin, Etc FY24: 119.3778; Insert Notes About Rate Set - Date, Origin, Etc FY25: 122.9592; Insert Notes About Rate Set - Date, Origin, Etc FY26: 126.6479; Insert Notes About Rate Set - Date, Origin, Etc FY27: 130.4474; Insert Notes About Rate Set - Date, Origin, Etc FY28: 134.3608; Insert Notes About Rate Set - Date, Origin, Etc FY29: 138.3916; Insert Notes About Rate Set - Date, Origin, Etc FY30: 142.5434; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NS4 | Labor_Post Doc/ Research Associate_NS4 | Labor | Labor_Post Doc/ Research Associate_NS4 | NEXTII Rates from HT 2/6/19 FY19: 61.5099; NEXTII Rates from HT 2/6/19 FY20: 63.3551; NEXTII Rates from HT 2/6/19 FY21: 65.2558; NEXTII Rates from HT 2/6/19 FY22: 67.2135; NEXTII Rates from HT 2/6/19 FY23: 69.2299; NEXTII Rates from HT 2/6/19 FY24: 71.3068; NEXTII Rates from HT 2/6/19 FY25: 73.446; NEXTII Rates from HT 2/6/19 FY26: 75.6494; NEXTII Rates from HT 2/6/19 FY27: 77.9188; NEXTII Rates from HT 2/6/19 FY28: 80.2564; NEXTII Rates from HT 2/6/19 FY29: 82.6641; NEXTII Rates from HT 2/6/19 FY30: 85.144; NEXTII Rates from HT 2/6/19 FY31: 87.6983; NEXTII Rates from HT 2/6/19 FY32: 90.3293; EPR_FY19 FY33: 93.0392; EPR_FY19 FY34: 95.8303; EPR_FY19 FY35: 98.7053; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 83.118; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 85.6116; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 88.1799; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 90.8253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 93.5501; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 96.3566; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 99.2473; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 102.2247; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 105.2914; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 108.4502; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 111.7037; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 115.0548; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 118.5064; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 122.0616; OPS19 FY33: 125.7235; OPS19 FY34: 129.4952; OPS19 FY35: 133.38; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 62.3305; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 64.2004; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 66.1264; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 68.1102; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 70.1535; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 72.2581; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 74.4258; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 76.6586; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 78.9584; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 81.3271; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 83.7669; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 86.2799; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 88.8683; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 91.5344; EPRSS19 FY33: 94.2804; EPRSS19 FY34: 97.1088; EPRSS19 FY35: 100.0221; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 79.4924; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 81.8772; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 84.3335; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 86.8635; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 89.4694; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 92.1535; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 94.9181; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 97.7657; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 100.6986; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 103.7196; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 106.8312; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 110.0361; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 113.3372; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 116.7373; ACT19 FY33: 120.2395; ACT19 FY34: 123.8466; ACT19 FY35: 127.562; Std. Operating Ovhd - FY18 Base Year FY16: 61.0273; Std. Operating Ovhd - FY18 Base Year FY17: 61.0273; Std. Operating Ovhd - FY18 Base Year FY18: 61.0273; Insert Notes About Rate Set - Date, Origin, Etc FY19: 61.0273; Insert Notes About Rate Set - Date, Origin, Etc FY20: 61.0273; Insert Notes About Rate Set - Date, Origin, Etc FY21: 61.0273; Insert Notes About Rate Set - Date, Origin, Etc FY22: 61.0273; Insert Notes About Rate Set - Date, Origin, Etc FY23: 61.0273; Insert Notes About Rate Set - Date, Origin, Etc FY24: 61.0273; Insert Notes About Rate Set - Date, Origin, Etc FY25: 61.0273; Insert Notes About Rate Set - Date, Origin, Etc FY19: 36; Insert Notes About Rate Set - Date, Origin, Etc FY20: 63.8293; Insert Notes About Rate Set - Date, Origin, Etc FY21: 65.7441; Insert Notes About Rate Set - Date, Origin, Etc FY22: 67.7165; Insert Notes About Rate Set - Date, Origin, Etc FY23: 69.7479; Insert Notes About Rate Set - Date, Origin, Etc FY24: 71.8404; Insert Notes About Rate Set - Date, Origin, Etc FY25: 73.9956; Insert Notes About Rate Set - Date, Origin, Etc FY26: 76.2155; Insert Notes About Rate Set - Date, Origin, Etc FY27: 78.5019; Insert Notes About Rate Set - Date, Origin, Etc FY28: 80.857; Insert Notes About Rate Set - Date, Origin, Etc FY29: 83.2827; Insert Notes About Rate Set - Date, Origin, Etc FY30: 85.7812; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
SE1 | Labor_EL - Survey Engineer_SE1 | Labor | Labor_EL - Survey Engineer_SE1 | NEXTII Rates from HT 2/6/19 FY19: 132.0809; NEXTII Rates from HT 2/6/19 FY20: 136.0433; NEXTII Rates from HT 2/6/19 FY21: 140.1246; NEXTII Rates from HT 2/6/19 FY22: 144.3283; NEXTII Rates from HT 2/6/19 FY23: 148.6582; NEXTII Rates from HT 2/6/19 FY24: 153.1179; NEXTII Rates from HT 2/6/19 FY25: 157.7115; NEXTII Rates from HT 2/6/19 FY26: 162.4428; NEXTII Rates from HT 2/6/19 FY27: 167.3161; NEXTII Rates from HT 2/6/19 FY28: 172.3356; NEXTII Rates from HT 2/6/19 FY29: 177.5056; NEXTII Rates from HT 2/6/19 FY30: 182.8308; NEXTII Rates from HT 2/6/19 FY31: 188.3157; NEXTII Rates from HT 2/6/19 FY32: 193.9652; EPR_FY19 FY33: 199.7841; EPR_FY19 FY34: 205.7777; EPR_FY19 FY35: 211.951; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 178.4804; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 183.8348; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 189.3498; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 195.0303; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 200.8812; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 206.9077; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 213.1149; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 219.5083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 226.0936; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 232.8764; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 239.8627; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 247.0586; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 254.4703; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 262.1044; OPS19 FY33: 269.9676; OPS19 FY34: 278.0666; OPS19 FY35: 286.4086; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 133.843; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 137.8583; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 141.994; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 146.2538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 150.6414; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 155.1607; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 159.8155; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 164.61; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 169.5483; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 174.6347; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 179.8738; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 185.27; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 190.8281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 196.5529; EPRSS19 FY33: 202.4495; EPRSS19 FY34: 208.523; EPRSS19 FY35: 214.7787; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 170.6951; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 175.816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 181.0904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 186.5231; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 192.1188; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 197.8824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 203.8189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 209.9334; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 216.2314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 222.7184; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 229.3999; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 236.2819; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 243.3704; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 250.6715; ACT19 FY33: 258.1917; ACT19 FY34: 265.9374; ACT19 FY35: 273.9155; Std. Operating Ovhd - FY18 Base Year FY16: 125.8309; Std. Operating Ovhd - FY18 Base Year FY17: 125.8309; Std. Operating Ovhd - FY18 Base Year FY18: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY21: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY23: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 37; Insert Notes About Rate Set - Date, Origin, Etc FY20: 137.1386; Insert Notes About Rate Set - Date, Origin, Etc FY21: 141.2528; Insert Notes About Rate Set - Date, Origin, Etc FY22: 145.4903; Insert Notes About Rate Set - Date, Origin, Etc FY23: 149.855; Insert Notes About Rate Set - Date, Origin, Etc FY24: 154.3507; Insert Notes About Rate Set - Date, Origin, Etc FY25: 158.9812; Insert Notes About Rate Set - Date, Origin, Etc FY26: 163.7507; Insert Notes About Rate Set - Date, Origin, Etc FY27: 168.6632; Insert Notes About Rate Set - Date, Origin, Etc FY28: 173.7231; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9348; Insert Notes About Rate Set - Date, Origin, Etc FY30: 184.3028; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
SE2 | Labor_EL - Survey Technician_SE2 | Labor | Labor_EL - Survey Technician_SE2 | NEXTII Rates from HT 2/6/19 FY19: 90.7756; NEXTII Rates from HT 2/6/19 FY20: 93.4989; NEXTII Rates from HT 2/6/19 FY21: 96.3039; NEXTII Rates from HT 2/6/19 FY22: 99.193; NEXTII Rates from HT 2/6/19 FY23: 102.1688; NEXTII Rates from HT 2/6/19 FY24: 105.2338; NEXTII Rates from HT 2/6/19 FY25: 108.3908; NEXTII Rates from HT 2/6/19 FY26: 111.6426; NEXTII Rates from HT 2/6/19 FY27: 114.9918; NEXTII Rates from HT 2/6/19 FY28: 118.4416; NEXTII Rates from HT 2/6/19 FY29: 121.9948; NEXTII Rates from HT 2/6/19 FY30: 125.6547; NEXTII Rates from HT 2/6/19 FY31: 129.4243; NEXTII Rates from HT 2/6/19 FY32: 133.3071; EPR_FY19 FY33: 137.3063; EPR_FY19 FY34: 141.4255; EPR_FY19 FY35: 145.6682; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 122.6648; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 126.3447; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 130.135; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 134.0391; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 138.0603; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 142.2021; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 146.4681; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 150.8622; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 155.388; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 160.0497; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 164.8512; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 169.7967; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 174.8906; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 180.1373; OPS19 FY33: 185.5414; OPS19 FY34: 191.1077; OPS19 FY35: 196.8409; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 91.9867; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 94.7463; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 97.5887; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 100.5163; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 103.5318; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 106.6378; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 109.8369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 113.132; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 116.526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 120.0217; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 123.6224; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 127.3311; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 131.151; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 135.0855; EPRSS19 FY33: 139.1381; EPRSS19 FY34: 143.3122; EPRSS19 FY35: 147.6116; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 117.3141; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 120.8336; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 124.4586; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 128.1923; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 132.0381; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 135.9992; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 140.0792; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 144.2816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 148.6101; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 153.0684; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 157.6604; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 162.3902; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 167.2619; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 172.2798; ACT19 FY33: 177.4482; ACT19 FY34: 182.7716; ACT19 FY35: 188.2548; Std. Operating Ovhd - FY18 Base Year FY16: 94.2254; Std. Operating Ovhd - FY18 Base Year FY17: 94.2254; Std. Operating Ovhd - FY18 Base Year FY18: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY20: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY21: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY23: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY24: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY25: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 38; Insert Notes About Rate Set - Date, Origin, Etc FY20: 89.1179; Insert Notes About Rate Set - Date, Origin, Etc FY21: 91.7915; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.5452; Insert Notes About Rate Set - Date, Origin, Etc FY23: 97.3816; Insert Notes About Rate Set - Date, Origin, Etc FY24: 100.303; Insert Notes About Rate Set - Date, Origin, Etc FY25: 103.3121; Insert Notes About Rate Set - Date, Origin, Etc FY26: 106.4115; Insert Notes About Rate Set - Date, Origin, Etc FY27: 109.6038; Insert Notes About Rate Set - Date, Origin, Etc FY28: 112.8919; Insert Notes About Rate Set - Date, Origin, Etc FY29: 116.2787; Insert Notes About Rate Set - Date, Origin, Etc FY30: 119.7671; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
SE3 | Labor_EL - Utility Engineer_SE3 | Labor | Labor_EL - Utility Engineer_SE3 | NEXTII Rates from HT 2/6/19 FY19: 132.0809; NEXTII Rates from HT 2/6/19 FY20: 136.0433; NEXTII Rates from HT 2/6/19 FY21: 140.1246; NEXTII Rates from HT 2/6/19 FY22: 144.3283; NEXTII Rates from HT 2/6/19 FY23: 148.6582; NEXTII Rates from HT 2/6/19 FY24: 153.1179; NEXTII Rates from HT 2/6/19 FY25: 157.7115; NEXTII Rates from HT 2/6/19 FY26: 162.4428; NEXTII Rates from HT 2/6/19 FY27: 167.3161; NEXTII Rates from HT 2/6/19 FY28: 172.3356; NEXTII Rates from HT 2/6/19 FY29: 177.5056; NEXTII Rates from HT 2/6/19 FY30: 182.8308; NEXTII Rates from HT 2/6/19 FY31: 188.3157; NEXTII Rates from HT 2/6/19 FY32: 193.9652; EPR_FY19 FY33: 199.7841; EPR_FY19 FY34: 205.7777; EPR_FY19 FY35: 211.951; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 178.4804; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 183.8348; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 189.3498; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 195.0303; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 200.8812; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 206.9077; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 213.1149; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 219.5083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 226.0936; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 232.8764; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 239.8627; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 247.0586; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 254.4703; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 262.1044; OPS19 FY33: 269.9676; OPS19 FY34: 278.0666; OPS19 FY35: 286.4086; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 133.843; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 137.8583; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 141.994; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 146.2538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 150.6414; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 155.1607; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 159.8155; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 164.61; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 169.5483; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 174.6347; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 179.8738; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 185.27; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 190.8281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 196.5529; EPRSS19 FY33: 202.4495; EPRSS19 FY34: 208.523; EPRSS19 FY35: 214.7787; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 170.6951; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 175.816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 181.0904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 186.5231; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 192.1188; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 197.8824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 203.8189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 209.9334; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 216.2314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 222.7184; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 229.3999; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 236.2819; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 243.3704; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 250.6715; ACT19 FY33: 258.1917; ACT19 FY34: 265.9374; ACT19 FY35: 273.9155; Std. Operating Ovhd - FY18 Base Year FY16: 125.8309; Std. Operating Ovhd - FY18 Base Year FY17: 125.8309; Std. Operating Ovhd - FY18 Base Year FY18: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY21: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY23: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 39; Insert Notes About Rate Set - Date, Origin, Etc FY20: 137.1386; Insert Notes About Rate Set - Date, Origin, Etc FY21: 141.2528; Insert Notes About Rate Set - Date, Origin, Etc FY22: 145.4903; Insert Notes About Rate Set - Date, Origin, Etc FY23: 149.855; Insert Notes About Rate Set - Date, Origin, Etc FY24: 154.3507; Insert Notes About Rate Set - Date, Origin, Etc FY25: 158.9812; Insert Notes About Rate Set - Date, Origin, Etc FY26: 163.7507; Insert Notes About Rate Set - Date, Origin, Etc FY27: 168.6632; Insert Notes About Rate Set - Date, Origin, Etc FY28: 173.7231; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9348; Insert Notes About Rate Set - Date, Origin, Etc FY30: 184.3028; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
SE4 | Labor_EL - Utility Technician_SE4 | Labor | Labor_EL - Utility Technician_SE4 | NEXTII Rates from HT 2/6/19 FY19: 90.7756; NEXTII Rates from HT 2/6/19 FY20: 93.4989; NEXTII Rates from HT 2/6/19 FY21: 96.3039; NEXTII Rates from HT 2/6/19 FY22: 99.193; NEXTII Rates from HT 2/6/19 FY23: 102.1688; NEXTII Rates from HT 2/6/19 FY24: 105.2338; NEXTII Rates from HT 2/6/19 FY25: 108.3908; NEXTII Rates from HT 2/6/19 FY26: 111.6426; NEXTII Rates from HT 2/6/19 FY27: 114.9918; NEXTII Rates from HT 2/6/19 FY28: 118.4416; NEXTII Rates from HT 2/6/19 FY29: 121.9948; NEXTII Rates from HT 2/6/19 FY30: 125.6547; NEXTII Rates from HT 2/6/19 FY31: 129.4243; NEXTII Rates from HT 2/6/19 FY32: 133.3071; EPR_FY19 FY33: 137.3063; EPR_FY19 FY34: 141.4255; EPR_FY19 FY35: 145.6682; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 122.6648; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 126.3447; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 130.135; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 134.0391; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 138.0603; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 142.2021; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 146.4681; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 150.8622; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 155.388; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 160.0497; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 164.8512; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 169.7967; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 174.8906; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 180.1373; OPS19 FY33: 185.5414; OPS19 FY34: 191.1077; OPS19 FY35: 196.8409; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 91.9867; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 94.7463; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 97.5887; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 100.5163; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 103.5318; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 106.6378; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 109.8369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 113.132; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 116.526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 120.0217; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 123.6224; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 127.3311; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 131.151; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 135.0855; EPRSS19 FY33: 139.1381; EPRSS19 FY34: 143.3122; EPRSS19 FY35: 147.6116; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 117.3141; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 120.8336; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 124.4586; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 128.1923; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 132.0381; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 135.9992; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 140.0792; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 144.2816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 148.6101; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 153.0684; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 157.6604; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 162.3902; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 167.2619; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 172.2798; ACT19 FY33: 177.4482; ACT19 FY34: 182.7716; ACT19 FY35: 188.2548; Std. Operating Ovhd - FY18 Base Year FY16: 94.2254; Std. Operating Ovhd - FY18 Base Year FY17: 94.2254; Std. Operating Ovhd - FY18 Base Year FY18: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY20: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY21: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY23: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY24: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY25: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 40; Insert Notes About Rate Set - Date, Origin, Etc FY20: 89.1179; Insert Notes About Rate Set - Date, Origin, Etc FY21: 91.7915; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.5452; Insert Notes About Rate Set - Date, Origin, Etc FY23: 97.3816; Insert Notes About Rate Set - Date, Origin, Etc FY24: 100.303; Insert Notes About Rate Set - Date, Origin, Etc FY25: 103.3121; Insert Notes About Rate Set - Date, Origin, Etc FY26: 106.4115; Insert Notes About Rate Set - Date, Origin, Etc FY27: 109.6038; Insert Notes About Rate Set - Date, Origin, Etc FY28: 112.8919; Insert Notes About Rate Set - Date, Origin, Etc FY29: 116.2787; Insert Notes About Rate Set - Date, Origin, Etc FY30: 119.7671; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
SE5 | Labor_EL - Vacuum Engineer_SE5 | Labor | Labor_EL - Vacuum Engineer_SE5 | NEXTII Rates from HT 2/6/19 FY19: 132.0809; NEXTII Rates from HT 2/6/19 FY20: 136.0433; NEXTII Rates from HT 2/6/19 FY21: 140.1246; NEXTII Rates from HT 2/6/19 FY22: 144.3283; NEXTII Rates from HT 2/6/19 FY23: 148.6582; NEXTII Rates from HT 2/6/19 FY24: 153.1179; NEXTII Rates from HT 2/6/19 FY25: 157.7115; NEXTII Rates from HT 2/6/19 FY26: 162.4428; NEXTII Rates from HT 2/6/19 FY27: 167.3161; NEXTII Rates from HT 2/6/19 FY28: 172.3356; NEXTII Rates from HT 2/6/19 FY29: 177.5056; NEXTII Rates from HT 2/6/19 FY30: 182.8308; NEXTII Rates from HT 2/6/19 FY31: 188.3157; NEXTII Rates from HT 2/6/19 FY32: 193.9652; EPR_FY19 FY33: 199.7841; EPR_FY19 FY34: 205.7777; EPR_FY19 FY35: 211.951; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 178.4804; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 183.8348; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 189.3498; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 195.0303; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 200.8812; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 206.9077; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 213.1149; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 219.5083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 226.0936; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 232.8764; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 239.8627; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 247.0586; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 254.4703; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 262.1044; OPS19 FY33: 269.9676; OPS19 FY34: 278.0666; OPS19 FY35: 286.4086; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 133.843; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 137.8583; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 141.994; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 146.2538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 150.6414; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 155.1607; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 159.8155; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 164.61; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 169.5483; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 174.6347; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 179.8738; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 185.27; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 190.8281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 196.5529; EPRSS19 FY33: 202.4495; EPRSS19 FY34: 208.523; EPRSS19 FY35: 214.7787; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 170.6951; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 175.816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 181.0904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 186.5231; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 192.1188; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 197.8824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 203.8189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 209.9334; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 216.2314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 222.7184; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 229.3999; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 236.2819; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 243.3704; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 250.6715; ACT19 FY33: 258.1917; ACT19 FY34: 265.9374; ACT19 FY35: 273.9155; Std. Operating Ovhd - FY18 Base Year FY16: 125.8309; Std. Operating Ovhd - FY18 Base Year FY17: 125.8309; Std. Operating Ovhd - FY18 Base Year FY18: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY21: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY23: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 41; Insert Notes About Rate Set - Date, Origin, Etc FY20: 137.1386; Insert Notes About Rate Set - Date, Origin, Etc FY21: 141.2528; Insert Notes About Rate Set - Date, Origin, Etc FY22: 145.4903; Insert Notes About Rate Set - Date, Origin, Etc FY23: 149.855; Insert Notes About Rate Set - Date, Origin, Etc FY24: 154.3507; Insert Notes About Rate Set - Date, Origin, Etc FY25: 158.9812; Insert Notes About Rate Set - Date, Origin, Etc FY26: 163.7507; Insert Notes About Rate Set - Date, Origin, Etc FY27: 168.6632; Insert Notes About Rate Set - Date, Origin, Etc FY28: 173.7231; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9348; Insert Notes About Rate Set - Date, Origin, Etc FY30: 184.3028; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
SE6 | Labor_EL - Vacuum Technician_SE6 | Labor | Labor_EL - Vacuum Technician_SE6 | NEXTII Rates from HT 2/6/19 FY19: 90.7756; NEXTII Rates from HT 2/6/19 FY20: 93.4989; NEXTII Rates from HT 2/6/19 FY21: 96.3039; NEXTII Rates from HT 2/6/19 FY22: 99.193; NEXTII Rates from HT 2/6/19 FY23: 102.1688; NEXTII Rates from HT 2/6/19 FY24: 105.2338; NEXTII Rates from HT 2/6/19 FY25: 108.3908; NEXTII Rates from HT 2/6/19 FY26: 111.6426; NEXTII Rates from HT 2/6/19 FY27: 114.9918; NEXTII Rates from HT 2/6/19 FY28: 118.4416; NEXTII Rates from HT 2/6/19 FY29: 121.9948; NEXTII Rates from HT 2/6/19 FY30: 125.6547; NEXTII Rates from HT 2/6/19 FY31: 129.4243; NEXTII Rates from HT 2/6/19 FY32: 133.3071; EPR_FY19 FY33: 137.3063; EPR_FY19 FY34: 141.4255; EPR_FY19 FY35: 145.6682; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 122.6648; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 126.3447; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 130.135; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 134.0391; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 138.0603; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 142.2021; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 146.4681; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 150.8622; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 155.388; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 160.0497; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 164.8512; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 169.7967; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 174.8906; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 180.1373; OPS19 FY33: 185.5414; OPS19 FY34: 191.1077; OPS19 FY35: 196.8409; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 91.9867; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 94.7463; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 97.5887; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 100.5163; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 103.5318; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 106.6378; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 109.8369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 113.132; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 116.526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 120.0217; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 123.6224; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 127.3311; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 131.151; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 135.0855; EPRSS19 FY33: 139.1381; EPRSS19 FY34: 143.3122; EPRSS19 FY35: 147.6116; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 117.3141; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 120.8336; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 124.4586; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 128.1923; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 132.0381; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 135.9992; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 140.0792; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 144.2816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 148.6101; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 153.0684; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 157.6604; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 162.3902; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 167.2619; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 172.2798; ACT19 FY33: 177.4482; ACT19 FY34: 182.7716; ACT19 FY35: 188.2548; Std. Operating Ovhd - FY18 Base Year FY16: 94.2254; Std. Operating Ovhd - FY18 Base Year FY17: 94.2254; Std. Operating Ovhd - FY18 Base Year FY18: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY20: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY21: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY23: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY24: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY25: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 42; Insert Notes About Rate Set - Date, Origin, Etc FY20: 89.1179; Insert Notes About Rate Set - Date, Origin, Etc FY21: 91.7915; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.5452; Insert Notes About Rate Set - Date, Origin, Etc FY23: 97.3816; Insert Notes About Rate Set - Date, Origin, Etc FY24: 100.303; Insert Notes About Rate Set - Date, Origin, Etc FY25: 103.3121; Insert Notes About Rate Set - Date, Origin, Etc FY26: 106.4115; Insert Notes About Rate Set - Date, Origin, Etc FY27: 109.6038; Insert Notes About Rate Set - Date, Origin, Etc FY28: 112.8919; Insert Notes About Rate Set - Date, Origin, Etc FY29: 116.2787; Insert Notes About Rate Set - Date, Origin, Etc FY30: 119.7671; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
TE1 | Labor_EL - D&I Engineer_TE1 | Labor | Labor_EL - D&I Engineer_TE1 | NEXTII Rates from HT 2/6/19 FY19: 132.0809; NEXTII Rates from HT 2/6/19 FY20: 136.0433; NEXTII Rates from HT 2/6/19 FY21: 140.1246; NEXTII Rates from HT 2/6/19 FY22: 144.3283; NEXTII Rates from HT 2/6/19 FY23: 148.6582; NEXTII Rates from HT 2/6/19 FY24: 153.1179; NEXTII Rates from HT 2/6/19 FY25: 157.7115; NEXTII Rates from HT 2/6/19 FY26: 162.4428; NEXTII Rates from HT 2/6/19 FY27: 167.3161; NEXTII Rates from HT 2/6/19 FY28: 172.3356; NEXTII Rates from HT 2/6/19 FY29: 177.5056; NEXTII Rates from HT 2/6/19 FY30: 182.8308; NEXTII Rates from HT 2/6/19 FY31: 188.3157; NEXTII Rates from HT 2/6/19 FY32: 193.9652; EPR_FY19 FY33: 199.7841; EPR_FY19 FY34: 205.7777; EPR_FY19 FY35: 211.951; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 178.4804; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 183.8348; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 189.3498; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 195.0303; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 200.8812; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 206.9077; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 213.1149; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 219.5083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 226.0936; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 232.8764; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 239.8627; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 247.0586; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 254.4703; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 262.1044; OPS19 FY33: 269.9676; OPS19 FY34: 278.0666; OPS19 FY35: 286.4086; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 133.843; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 137.8583; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 141.994; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 146.2538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 150.6414; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 155.1607; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 159.8155; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 164.61; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 169.5483; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 174.6347; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 179.8738; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 185.27; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 190.8281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 196.5529; EPRSS19 FY33: 202.4495; EPRSS19 FY34: 208.523; EPRSS19 FY35: 214.7787; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 170.6951; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 175.816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 181.0904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 186.5231; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 192.1188; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 197.8824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 203.8189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 209.9334; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 216.2314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 222.7184; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 229.3999; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 236.2819; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 243.3704; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 250.6715; ACT19 FY33: 258.1917; ACT19 FY34: 265.9374; ACT19 FY35: 273.9155; Std. Operating Ovhd - FY18 Base Year FY16: 125.8309; Std. Operating Ovhd - FY18 Base Year FY17: 125.8309; Std. Operating Ovhd - FY18 Base Year FY18: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY21: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY23: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 43; Insert Notes About Rate Set - Date, Origin, Etc FY20: 137.1386; Insert Notes About Rate Set - Date, Origin, Etc FY21: 141.2528; Insert Notes About Rate Set - Date, Origin, Etc FY22: 145.4903; Insert Notes About Rate Set - Date, Origin, Etc FY23: 149.855; Insert Notes About Rate Set - Date, Origin, Etc FY24: 154.3507; Insert Notes About Rate Set - Date, Origin, Etc FY25: 158.9812; Insert Notes About Rate Set - Date, Origin, Etc FY26: 163.7507; Insert Notes About Rate Set - Date, Origin, Etc FY27: 168.6632; Insert Notes About Rate Set - Date, Origin, Etc FY28: 173.7231; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9348; Insert Notes About Rate Set - Date, Origin, Etc FY30: 184.3028; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
TE2 | Labor_EL - D&I Technician_TE2 | Labor | Labor_EL - D&I Technician_TE2 | NEXTII Rates from HT 2/6/19 FY19: 90.7756; NEXTII Rates from HT 2/6/19 FY20: 93.4989; NEXTII Rates from HT 2/6/19 FY21: 96.3039; NEXTII Rates from HT 2/6/19 FY22: 99.193; NEXTII Rates from HT 2/6/19 FY23: 102.1688; NEXTII Rates from HT 2/6/19 FY24: 105.2338; NEXTII Rates from HT 2/6/19 FY25: 108.3908; NEXTII Rates from HT 2/6/19 FY26: 111.6426; NEXTII Rates from HT 2/6/19 FY27: 114.9918; NEXTII Rates from HT 2/6/19 FY28: 118.4416; NEXTII Rates from HT 2/6/19 FY29: 121.9948; NEXTII Rates from HT 2/6/19 FY30: 125.6547; NEXTII Rates from HT 2/6/19 FY31: 129.4243; NEXTII Rates from HT 2/6/19 FY32: 133.3071; EPR_FY19 FY33: 137.3063; EPR_FY19 FY34: 141.4255; EPR_FY19 FY35: 145.6682; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 122.6648; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 126.3447; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 130.135; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 134.0391; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 138.0603; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 142.2021; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 146.4681; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 150.8622; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 155.388; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 160.0497; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 164.8512; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 169.7967; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 174.8906; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 180.1373; OPS19 FY33: 185.5414; OPS19 FY34: 191.1077; OPS19 FY35: 196.8409; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 91.9867; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 94.7463; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 97.5887; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 100.5163; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 103.5318; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 106.6378; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 109.8369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 113.132; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 116.526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 120.0217; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 123.6224; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 127.3311; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 131.151; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 135.0855; EPRSS19 FY33: 139.1381; EPRSS19 FY34: 143.3122; EPRSS19 FY35: 147.6116; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 117.3141; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 120.8336; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 124.4586; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 128.1923; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 132.0381; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 135.9992; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 140.0792; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 144.2816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 148.6101; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 153.0684; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 157.6604; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 162.3902; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 167.2619; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 172.2798; ACT19 FY33: 177.4482; ACT19 FY34: 182.7716; ACT19 FY35: 188.2548; Std. Operating Ovhd - FY18 Base Year FY16: 98.8964; Std. Operating Ovhd - FY18 Base Year FY17: 98.8964; Std. Operating Ovhd - FY18 Base Year FY18: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY19: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY20: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY21: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY22: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY23: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY24: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY25: 98.8964; Insert Notes About Rate Set - Date, Origin, Etc FY19: 44; Insert Notes About Rate Set - Date, Origin, Etc FY20: 89.1179; Insert Notes About Rate Set - Date, Origin, Etc FY21: 91.7915; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.5452; Insert Notes About Rate Set - Date, Origin, Etc FY23: 97.3816; Insert Notes About Rate Set - Date, Origin, Etc FY24: 100.303; Insert Notes About Rate Set - Date, Origin, Etc FY25: 103.3121; Insert Notes About Rate Set - Date, Origin, Etc FY26: 106.4115; Insert Notes About Rate Set - Date, Origin, Etc FY27: 109.6038; Insert Notes About Rate Set - Date, Origin, Etc FY28: 112.8919; Insert Notes About Rate Set - Date, Origin, Etc FY29: 116.2787; Insert Notes About Rate Set - Date, Origin, Etc FY30: 119.7671; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
TE4 | Labor_EL - Insertion Device Engineer_TE4 | Labor | Labor_EL - Insertion Device Engineer_TE4 | NEXTII Rates from HT 2/6/19 FY19: 132.0809; NEXTII Rates from HT 2/6/19 FY20: 136.0433; NEXTII Rates from HT 2/6/19 FY21: 140.1246; NEXTII Rates from HT 2/6/19 FY22: 144.3283; NEXTII Rates from HT 2/6/19 FY23: 148.6582; NEXTII Rates from HT 2/6/19 FY24: 153.1179; NEXTII Rates from HT 2/6/19 FY25: 157.7115; NEXTII Rates from HT 2/6/19 FY26: 162.4428; NEXTII Rates from HT 2/6/19 FY27: 167.3161; NEXTII Rates from HT 2/6/19 FY28: 172.3356; NEXTII Rates from HT 2/6/19 FY29: 177.5056; NEXTII Rates from HT 2/6/19 FY30: 182.8308; NEXTII Rates from HT 2/6/19 FY31: 188.3157; NEXTII Rates from HT 2/6/19 FY32: 193.9652; EPR_FY19 FY33: 199.7841; EPR_FY19 FY34: 205.7777; EPR_FY19 FY35: 211.951; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 178.4804; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 183.8348; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 189.3498; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 195.0303; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 200.8812; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 206.9077; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 213.1149; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 219.5083; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 226.0936; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 232.8764; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 239.8627; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 247.0586; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 254.4703; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 262.1044; OPS19 FY33: 269.9676; OPS19 FY34: 278.0666; OPS19 FY35: 286.4086; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 133.843; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 137.8583; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 141.994; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 146.2538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 150.6414; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 155.1607; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 159.8155; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 164.61; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 169.5483; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 174.6347; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 179.8738; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 185.27; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 190.8281; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 196.5529; EPRSS19 FY33: 202.4495; EPRSS19 FY34: 208.523; EPRSS19 FY35: 214.7787; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 170.6951; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 175.816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 181.0904; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 186.5231; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 192.1188; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 197.8824; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 203.8189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 209.9334; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 216.2314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 222.7184; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 229.3999; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 236.2819; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 243.3704; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 250.6715; ACT19 FY33: 258.1917; ACT19 FY34: 265.9374; ACT19 FY35: 273.9155; Std. Operating Ovhd - FY18 Base Year FY16: 125.8309; Std. Operating Ovhd - FY18 Base Year FY17: 125.8309; Std. Operating Ovhd - FY18 Base Year FY18: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY21: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY22: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY23: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY24: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY25: 125.8309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 45; Insert Notes About Rate Set - Date, Origin, Etc FY20: 137.1386; Insert Notes About Rate Set - Date, Origin, Etc FY21: 141.2528; Insert Notes About Rate Set - Date, Origin, Etc FY22: 145.4903; Insert Notes About Rate Set - Date, Origin, Etc FY23: 149.855; Insert Notes About Rate Set - Date, Origin, Etc FY24: 154.3507; Insert Notes About Rate Set - Date, Origin, Etc FY25: 158.9812; Insert Notes About Rate Set - Date, Origin, Etc FY26: 163.7507; Insert Notes About Rate Set - Date, Origin, Etc FY27: 168.6632; Insert Notes About Rate Set - Date, Origin, Etc FY28: 173.7231; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9348; Insert Notes About Rate Set - Date, Origin, Etc FY30: 184.3028; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
TE5 | Labor_EL - Insertion Device Technician_TE5 | Labor | Labor_EL - Insertion Device Technician_TE5 | NEXTII Rates from HT 2/6/19 FY19: 90.7756; NEXTII Rates from HT 2/6/19 FY20: 93.4989; NEXTII Rates from HT 2/6/19 FY21: 96.3039; NEXTII Rates from HT 2/6/19 FY22: 99.193; NEXTII Rates from HT 2/6/19 FY23: 102.1688; NEXTII Rates from HT 2/6/19 FY24: 105.2338; NEXTII Rates from HT 2/6/19 FY25: 108.3908; NEXTII Rates from HT 2/6/19 FY26: 111.6426; NEXTII Rates from HT 2/6/19 FY27: 114.9918; NEXTII Rates from HT 2/6/19 FY28: 118.4416; NEXTII Rates from HT 2/6/19 FY29: 121.9948; NEXTII Rates from HT 2/6/19 FY30: 125.6547; NEXTII Rates from HT 2/6/19 FY31: 129.4243; NEXTII Rates from HT 2/6/19 FY32: 133.3071; EPR_FY19 FY33: 137.3063; EPR_FY19 FY34: 141.4255; EPR_FY19 FY35: 145.6682; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 122.6648; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 126.3447; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 130.135; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 134.0391; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 138.0603; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 142.2021; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 146.4681; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 150.8622; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 155.388; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 160.0497; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 164.8512; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 169.7967; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 174.8906; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 180.1373; OPS19 FY33: 185.5414; OPS19 FY34: 191.1077; OPS19 FY35: 196.8409; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 91.9867; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 94.7463; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 97.5887; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 100.5163; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 103.5318; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 106.6378; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 109.8369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 113.132; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 116.526; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 120.0217; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 123.6224; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 127.3311; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 131.151; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 135.0855; EPRSS19 FY33: 139.1381; EPRSS19 FY34: 143.3122; EPRSS19 FY35: 147.6116; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 117.3141; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 120.8336; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 124.4586; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 128.1923; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 132.0381; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 135.9992; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 140.0792; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 144.2816; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 148.6101; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 153.0684; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 157.6604; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 162.3902; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 167.2619; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 172.2798; ACT19 FY33: 177.4482; ACT19 FY34: 182.7716; ACT19 FY35: 188.2548; Std. Operating Ovhd - FY18 Base Year FY16: 94.2254; Std. Operating Ovhd - FY18 Base Year FY17: 94.2254; Std. Operating Ovhd - FY18 Base Year FY18: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY20: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY21: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY23: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY24: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY25: 94.2254; Insert Notes About Rate Set - Date, Origin, Etc FY19: 46; Insert Notes About Rate Set - Date, Origin, Etc FY20: 89.1179; Insert Notes About Rate Set - Date, Origin, Etc FY21: 91.7915; Insert Notes About Rate Set - Date, Origin, Etc FY22: 94.5452; Insert Notes About Rate Set - Date, Origin, Etc FY23: 97.3816; Insert Notes About Rate Set - Date, Origin, Etc FY24: 100.303; Insert Notes About Rate Set - Date, Origin, Etc FY25: 103.3121; Insert Notes About Rate Set - Date, Origin, Etc FY26: 106.4115; Insert Notes About Rate Set - Date, Origin, Etc FY27: 109.6038; Insert Notes About Rate Set - Date, Origin, Etc FY28: 112.8919; Insert Notes About Rate Set - Date, Origin, Etc FY29: 116.2787; Insert Notes About Rate Set - Date, Origin, Etc FY30: 119.7671; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NST | Labor_Building Trades Unassigned_NST | Labor | Labor_Building Trades Unassigned_NST | NEXTII Rates from HT 2/6/19 FY19: 145.3697; NEXTII Rates from HT 2/6/19 FY20: 148.7132; NEXTII Rates from HT 2/6/19 FY21: 152.1336; NEXTII Rates from HT 2/6/19 FY22: 155.6327; NEXTII Rates from HT 2/6/19 FY23: 159.2122; NEXTII Rates from HT 2/6/19 FY24: 162.8741; NEXTII Rates from HT 2/6/19 FY25: 166.6202; NEXTII Rates from HT 2/6/19 FY26: 170.4525; NEXTII Rates from HT 2/6/19 FY27: 174.3729; NEXTII Rates from HT 2/6/19 FY28: 178.3835; NEXTII Rates from HT 2/6/19 FY29: 182.4863; NEXTII Rates from HT 2/6/19 FY30: 186.6835; NEXTII Rates from HT 2/6/19 FY31: 190.9772; NEXTII Rates from HT 2/6/19 FY32: 195.3697; EPR_FY19 FY33: 199.8632; EPR_FY19 FY34: 204.46; EPR_FY19 FY35: 209.1626; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 196.4375; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 200.9556; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 205.5776; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 210.3059; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 215.1429; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 220.0912; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 225.1533; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 230.3318; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 235.6295; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 241.0489; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 246.5931; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 252.2647; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 258.0668; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 264.0023; OPS19 FY33: 270.0744; OPS19 FY34: 276.2861; OPS19 FY35: 282.6407; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 147.3091; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 150.6972; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 154.1633; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 157.709; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 161.3363; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 165.0471; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 168.8431; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 172.7265; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 176.6992; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 180.7633; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 184.9209; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 189.1741; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 193.5251; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 197.9761; EPRSS19 FY33: 202.5296; EPRSS19 FY34: 207.1878; EPRSS19 FY35: 211.9531; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 187.869; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 192.19; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 196.6103; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 201.1324; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 205.7584; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 210.4909; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 215.3322; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 220.2848; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 225.3514; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 230.5344; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 235.8367; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 241.261; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 246.81; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 252.4866; ACT19 FY33: 258.2938; ACT19 FY34: 264.2346; ACT19 FY35: 270.312; Std. Operating Ovhd - FY18 Base Year FY16: 147.2355; Std. Operating Ovhd - FY18 Base Year FY17: 147.2355; Std. Operating Ovhd - FY18 Base Year FY18: 147.2355; Insert Notes About Rate Set - Date, Origin, Etc FY19: 147.2355; Insert Notes About Rate Set - Date, Origin, Etc FY20: 147.2355; Insert Notes About Rate Set - Date, Origin, Etc FY21: 147.2355; Insert Notes About Rate Set - Date, Origin, Etc FY22: 147.2355; Insert Notes About Rate Set - Date, Origin, Etc FY23: 147.2355; Insert Notes About Rate Set - Date, Origin, Etc FY24: 147.2355; Insert Notes About Rate Set - Date, Origin, Etc FY25: 147.2355; Insert Notes About Rate Set - Date, Origin, Etc FY19: 47; Insert Notes About Rate Set - Date, Origin, Etc FY20: 145.796; Insert Notes About Rate Set - Date, Origin, Etc FY21: 149.1493; Insert Notes About Rate Set - Date, Origin, Etc FY22: 152.5797; Insert Notes About Rate Set - Date, Origin, Etc FY23: 156.0891; Insert Notes About Rate Set - Date, Origin, Etc FY24: 159.6791; Insert Notes About Rate Set - Date, Origin, Etc FY25: 163.3517; Insert Notes About Rate Set - Date, Origin, Etc FY26: 167.1088; Insert Notes About Rate Set - Date, Origin, Etc FY27: 170.9523; Insert Notes About Rate Set - Date, Origin, Etc FY28: 174.8842; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9066; Insert Notes About Rate Set - Date, Origin, Etc FY30: 183.0214; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NSU | Labor_Building Surveyor_NSU | Labor | Labor_Building Surveyor_NSU | NEXTII Rates from HT 2/6/19 FY19: 186.2459; NEXTII Rates from HT 2/6/19 FY20: 190.5295; NEXTII Rates from HT 2/6/19 FY21: 194.9117; NEXTII Rates from HT 2/6/19 FY22: 199.3947; NEXTII Rates from HT 2/6/19 FY23: 203.9808; NEXTII Rates from HT 2/6/19 FY24: 208.6723; NEXTII Rates from HT 2/6/19 FY25: 213.4718; NEXTII Rates from HT 2/6/19 FY26: 218.3816; NEXTII Rates from HT 2/6/19 FY27: 223.4044; NEXTII Rates from HT 2/6/19 FY28: 228.5427; NEXTII Rates from HT 2/6/19 FY29: 233.7992; NEXTII Rates from HT 2/6/19 FY30: 239.1766; NEXTII Rates from HT 2/6/19 FY31: 244.6776; NEXTII Rates from HT 2/6/19 FY32: 250.3052; EPR_FY19 FY33: 256.0622; EPR_FY19 FY34: 261.9517; EPR_FY19 FY35: 267.9765; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 228.0463; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 233.2914; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 238.6571; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 244.1462; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 249.7615; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 255.506; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 261.3827; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 267.3945; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 273.5446; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 279.8361; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 286.2723; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 292.8566; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 299.5923; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 306.4829; OPS19 FY33: 313.532; OPS19 FY34: 320.7432; OPS19 FY35: 328.1203; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 188.7306; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 193.0714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 197.5121; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 202.0548; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 206.7021; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 211.4562; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 216.3197; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 221.2951; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 226.3849; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 231.5917; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 236.9183; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 242.3675; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 247.9419; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 253.6446; EPRSS19 FY33: 259.4784; EPRSS19 FY34: 265.4464; EPRSS19 FY35: 271.5517; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 240.6954; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 246.2314; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 251.8947; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 257.6883; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 263.6152; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 269.6783; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 275.8809; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 282.2262; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 288.7174; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 295.3579; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 302.1511; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 309.1006; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 316.2099; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 323.4827; ACT19 FY33: 330.9228; ACT19 FY34: 338.534; ACT19 FY35: 346.3203; Std. Operating Ovhd - FY18 Base Year FY16: 206.346; Std. Operating Ovhd - FY18 Base Year FY17: 206.346; Std. Operating Ovhd - FY18 Base Year FY18: 206.346; Insert Notes About Rate Set - Date, Origin, Etc FY19: 206.346; Insert Notes About Rate Set - Date, Origin, Etc FY20: 206.346; Insert Notes About Rate Set - Date, Origin, Etc FY21: 206.346; Insert Notes About Rate Set - Date, Origin, Etc FY22: 206.346; Insert Notes About Rate Set - Date, Origin, Etc FY23: 206.346; Insert Notes About Rate Set - Date, Origin, Etc FY24: 206.346; Insert Notes About Rate Set - Date, Origin, Etc FY25: 206.346; Insert Notes About Rate Set - Date, Origin, Etc FY19: 48; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 191.0882; Insert Notes About Rate Set - Date, Origin, Etc FY22: 195.4833; Insert Notes About Rate Set - Date, Origin, Etc FY23: 199.9794; Insert Notes About Rate Set - Date, Origin, Etc FY24: 204.5789; Insert Notes About Rate Set - Date, Origin, Etc FY25: 209.2842; Insert Notes About Rate Set - Date, Origin, Etc FY26: 214.0977; Insert Notes About Rate Set - Date, Origin, Etc FY27: 219.022; Insert Notes About Rate Set - Date, Origin, Etc FY28: 224.0595; Insert Notes About Rate Set - Date, Origin, Etc FY29: 229.2129; Insert Notes About Rate Set - Date, Origin, Etc FY30: 234.4848; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTS | Labor_Plant Engineering-Building Trades Riggers_BTS | Labor | Labor_Plant Engineering-Building Trades Riggers_BTS | NEXTII Rates from HT 2/6/19 FY19: 122.9314; NEXTII Rates from HT 2/6/19 FY20: 125.7588; NEXTII Rates from HT 2/6/19 FY21: 128.6512; NEXTII Rates from HT 2/6/19 FY22: 131.6102; NEXTII Rates from HT 2/6/19 FY23: 134.6372; NEXTII Rates from HT 2/6/19 FY24: 137.7339; NEXTII Rates from HT 2/6/19 FY25: 140.9018; NEXTII Rates from HT 2/6/19 FY26: 144.1425; NEXTII Rates from HT 2/6/19 FY27: 147.4578; NEXTII Rates from HT 2/6/19 FY28: 150.8493; NEXTII Rates from HT 2/6/19 FY29: 154.3189; NEXTII Rates from HT 2/6/19 FY30: 157.8682; NEXTII Rates from HT 2/6/19 FY31: 161.4992; NEXTII Rates from HT 2/6/19 FY32: 165.2137; EPR_FY19 FY33: 169.0136; EPR_FY19 FY34: 172.9009; EPR_FY19 FY35: 176.8776; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 150.5217; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 153.9837; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 157.5253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 161.1484; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 164.8548; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 168.6465; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 172.5253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 176.4934; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 180.5528; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 184.7055; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 188.9537; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 193.2996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 197.7455; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 202.2937; OPS19 FY33: 206.9464; OPS19 FY34: 211.7062; OPS19 FY35: 216.5754; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 124.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 127.4365; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 130.3676; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 133.366; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 136.4335; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 139.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 142.7816; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 146.0656; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 149.4251; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 152.8618; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 156.3777; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 159.9743; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 163.6538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 167.4178; EPRSS19 FY33: 171.2684; EPRSS19 FY34: 175.2076; EPRSS19 FY35: 179.2373; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 158.8707; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 162.5247; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 166.2628; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 170.0869; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 173.9989; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 178.0008; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 182.0949; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 186.283; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 190.5675; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 194.9506; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 199.4345; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 204.0215; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 208.714; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 213.5144; ACT19 FY33: 218.4252; ACT19 FY34: 223.449; ACT19 FY35: 228.5883; Std. Operating Ovhd - FY18 Base Year FY16: 124.7112; Std. Operating Ovhd - FY18 Base Year FY17: 124.7112; Std. Operating Ovhd - FY18 Base Year FY18: 124.7112; Insert Notes About Rate Set - Date, Origin, Etc FY19: 124.7112; Insert Notes About Rate Set - Date, Origin, Etc FY20: 124.7112; Insert Notes About Rate Set - Date, Origin, Etc FY21: 124.7112; Insert Notes About Rate Set - Date, Origin, Etc FY22: 124.7112; Insert Notes About Rate Set - Date, Origin, Etc FY23: 124.7112; Insert Notes About Rate Set - Date, Origin, Etc FY24: 124.7112; Insert Notes About Rate Set - Date, Origin, Etc FY25: 124.7112; Insert Notes About Rate Set - Date, Origin, Etc FY19: #N/A; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTE | Labor_Plant Engineering-Building Trades Electrician_BTE | Labor | Labor_Plant Engineering-Building Trades Electrician_BTE | NEXTII Rates from HT 2/6/19 FY19: 122.9314; NEXTII Rates from HT 2/6/19 FY20: 125.7588; NEXTII Rates from HT 2/6/19 FY21: 128.6512; NEXTII Rates from HT 2/6/19 FY22: 131.6102; NEXTII Rates from HT 2/6/19 FY23: 134.6372; NEXTII Rates from HT 2/6/19 FY24: 137.7339; NEXTII Rates from HT 2/6/19 FY25: 140.9018; NEXTII Rates from HT 2/6/19 FY26: 144.1425; NEXTII Rates from HT 2/6/19 FY27: 147.4578; NEXTII Rates from HT 2/6/19 FY28: 150.8493; NEXTII Rates from HT 2/6/19 FY29: 154.3189; NEXTII Rates from HT 2/6/19 FY30: 157.8682; NEXTII Rates from HT 2/6/19 FY31: 161.4992; NEXTII Rates from HT 2/6/19 FY32: 165.2137; EPR_FY19 FY33: 169.0136; EPR_FY19 FY34: 172.9009; EPR_FY19 FY35: 176.8776; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 150.5217; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 153.9837; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 157.5253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 161.1484; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 164.8548; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 168.6465; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 172.5253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 176.4934; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 180.5528; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 184.7055; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 188.9537; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 193.2996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 197.7455; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 202.2937; OPS19 FY33: 206.9464; OPS19 FY34: 211.7062; OPS19 FY35: 216.5754; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 124.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 127.4365; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 130.3676; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 133.366; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 136.4335; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 139.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 142.7816; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 146.0656; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 149.4251; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 152.8618; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 156.3777; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 159.9743; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 163.6538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 167.4178; EPRSS19 FY33: 171.2684; EPRSS19 FY34: 175.2076; EPRSS19 FY35: 179.2373; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 158.8707; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 162.5247; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 166.2628; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 170.0869; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 173.9989; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 178.0008; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 182.0949; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 186.283; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 190.5675; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 194.9506; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 199.4345; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 204.0215; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 208.714; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 213.5144; ACT19 FY33: 218.4252; ACT19 FY34: 223.449; ACT19 FY35: 228.5883; Std. Operating Ovhd - FY18 Base Year FY16: 140.2612; Std. Operating Ovhd - FY18 Base Year FY17: 140.2612; Std. Operating Ovhd - FY18 Base Year FY18: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY19: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY20: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY21: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY23: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY24: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY25: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY19: #N/A; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTP | Labor_Plant Engineering-Building Trades Plumber_BTP | Labor | Labor_Plant Engineering-Building Trades Plumber_BTP | NEXTII Rates from HT 2/6/19 FY19: 122.9314; NEXTII Rates from HT 2/6/19 FY20: 125.7588; NEXTII Rates from HT 2/6/19 FY21: 128.6512; NEXTII Rates from HT 2/6/19 FY22: 131.6102; NEXTII Rates from HT 2/6/19 FY23: 134.6372; NEXTII Rates from HT 2/6/19 FY24: 137.7339; NEXTII Rates from HT 2/6/19 FY25: 140.9018; NEXTII Rates from HT 2/6/19 FY26: 144.1425; NEXTII Rates from HT 2/6/19 FY27: 147.4578; NEXTII Rates from HT 2/6/19 FY28: 150.8493; NEXTII Rates from HT 2/6/19 FY29: 154.3189; NEXTII Rates from HT 2/6/19 FY30: 157.8682; NEXTII Rates from HT 2/6/19 FY31: 161.4992; NEXTII Rates from HT 2/6/19 FY32: 165.2137; EPR_FY19 FY33: 169.0136; EPR_FY19 FY34: 172.9009; EPR_FY19 FY35: 176.8776; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 150.5217; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 153.9837; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 157.5253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 161.1484; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 164.8548; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 168.6465; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 172.5253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 176.4934; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 180.5528; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 184.7055; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 188.9537; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 193.2996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 197.7455; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 202.2937; OPS19 FY33: 206.9464; OPS19 FY34: 211.7062; OPS19 FY35: 216.5754; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 124.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 127.4365; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 130.3676; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 133.366; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 136.4335; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 139.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 142.7816; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 146.0656; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 149.4251; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 152.8618; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 156.3777; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 159.9743; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 163.6538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 167.4178; EPRSS19 FY33: 171.2684; EPRSS19 FY34: 175.2076; EPRSS19 FY35: 179.2373; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 158.8707; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 162.5247; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 166.2628; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 170.0869; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 173.9989; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 178.0008; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 182.0949; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 186.283; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 190.5675; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 194.9506; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 199.4345; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 204.0215; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 208.714; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 213.5144; ACT19 FY33: 218.4252; ACT19 FY34: 223.449; ACT19 FY35: 228.5883; Std. Operating Ovhd - FY18 Base Year FY16: 140.2612; Std. Operating Ovhd - FY18 Base Year FY17: 140.2612; Std. Operating Ovhd - FY18 Base Year FY18: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY19: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY20: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY21: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY23: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY24: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY25: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY19: #N/A; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTC | Labor_Plant Engineering-Building Trades Carpenter_BTC | Labor | Labor_Plant Engineering-Building Trades Carpenter_BTC | NEXTII Rates from HT 2/6/19 FY19: 122.9314; NEXTII Rates from HT 2/6/19 FY20: 125.7588; NEXTII Rates from HT 2/6/19 FY21: 128.6512; NEXTII Rates from HT 2/6/19 FY22: 131.6102; NEXTII Rates from HT 2/6/19 FY23: 134.6372; NEXTII Rates from HT 2/6/19 FY24: 137.7339; NEXTII Rates from HT 2/6/19 FY25: 140.9018; NEXTII Rates from HT 2/6/19 FY26: 144.1425; NEXTII Rates from HT 2/6/19 FY27: 147.4578; NEXTII Rates from HT 2/6/19 FY28: 150.8493; NEXTII Rates from HT 2/6/19 FY29: 154.3189; NEXTII Rates from HT 2/6/19 FY30: 157.8682; NEXTII Rates from HT 2/6/19 FY31: 161.4992; NEXTII Rates from HT 2/6/19 FY32: 165.2137; EPR_FY19 FY33: 169.0136; EPR_FY19 FY34: 172.9009; EPR_FY19 FY35: 176.8776; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 150.5217; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 153.9837; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 157.5253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 161.1484; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 164.8548; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 168.6465; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 172.5253; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 176.4934; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 180.5528; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 184.7055; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 188.9537; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 193.2996; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 197.7455; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 202.2937; OPS19 FY33: 206.9464; OPS19 FY34: 211.7062; OPS19 FY35: 216.5754; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 124.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 127.4365; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 130.3676; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 133.366; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 136.4335; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 139.5714; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 142.7816; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 146.0656; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 149.4251; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 152.8618; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 156.3777; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 159.9743; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 163.6538; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 167.4178; EPRSS19 FY33: 171.2684; EPRSS19 FY34: 175.2076; EPRSS19 FY35: 179.2373; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 158.8707; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 162.5247; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 166.2628; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 170.0869; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 173.9989; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 178.0008; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 182.0949; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 186.283; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 190.5675; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 194.9506; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 199.4345; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 204.0215; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 208.714; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 213.5144; ACT19 FY33: 218.4252; ACT19 FY34: 223.449; ACT19 FY35: 228.5883; Std. Operating Ovhd - FY18 Base Year FY16: 140.2612; Std. Operating Ovhd - FY18 Base Year FY17: 140.2612; Std. Operating Ovhd - FY18 Base Year FY18: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY19: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY20: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY21: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY23: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY24: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY25: 140.2612; Insert Notes About Rate Set - Date, Origin, Etc FY19: #N/A; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NEQ | Material_Capital Equipment_NEQ | Material | Material_Capital Equipment_NEQ | NEXTII Rates from HT 2/6/19 FY19: 1.1177; NEXTII Rates from HT 2/6/19 FY20: 1.1434; NEXTII Rates from HT 2/6/19 FY21: 1.1697; NEXTII Rates from HT 2/6/19 FY22: 1.1966; NEXTII Rates from HT 2/6/19 FY23: 1.2241; NEXTII Rates from HT 2/6/19 FY24: 1.2522; NEXTII Rates from HT 2/6/19 FY25: 1.281; NEXTII Rates from HT 2/6/19 FY26: 1.3105; NEXTII Rates from HT 2/6/19 FY27: 1.3406; NEXTII Rates from HT 2/6/19 FY28: 1.3715; NEXTII Rates from HT 2/6/19 FY29: 1.403; NEXTII Rates from HT 2/6/19 FY30: 1.4353; NEXTII Rates from HT 2/6/19 FY31: 1.4683; NEXTII Rates from HT 2/6/19 FY32: 1.5021; EPR_FY19 FY33: 1.5366; EPR_FY19 FY34: 1.572; EPR_FY19 FY35: 1.6081; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 1.1651; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 1.1919; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 1.2193; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 1.2473; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 1.276; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 1.3054; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 1.3354; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 1.3661; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 1.3975; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 1.4297; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 1.4626; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 1.4962; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 1.5306; OPS19 FY33: 1.5658; OPS19 FY34: 1.6018; OPS19 FY35: 1.6387; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 1.1446; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 1.171; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 1.1979; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 1.2255; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 1.2536; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 1.2825; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 1.312; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 1.3422; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 1.373; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 1.4046; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 1.4369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 1.47; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 1.5038; EPRSS19 FY33: 1.5384; EPRSS19 FY34: 1.5737; EPRSS19 FY35: 1.6099; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 1.2031; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 1.2307; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 1.259; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 1.288; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 1.3176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 1.3479; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 1.3789; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 1.4106; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 1.4431; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 1.4763; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 1.5102; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 1.545; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 1.5805; ACT19 FY33: 1.6168; ACT19 FY34: 1.654; ACT19 FY35: 1.6921; Std. Operating Ovhd - FY18 Base Year FY16: 1.21; Std. Operating Ovhd - FY18 Base Year FY17: 1.21; Std. Operating Ovhd - FY18 Base Year FY18: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY19: 59; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.1402; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.1665; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.1933; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.2207; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.2488; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.2775; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.3069; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.337; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.3677; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.3992; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NEQ_Fixed | Material_Capital Equipment (Fixed Rate)_NEQ_Fixed | Material | Material_Capital Equipment (Fixed Rate)_NEQ_Fixed | NEXTII Rates from HT 2/6/19 FY19: 1.1177; NEXTII Rates from HT 2/6/19 FY20: 1.1177; NEXTII Rates from HT 2/6/19 FY21: 1.1177; NEXTII Rates from HT 2/6/19 FY22: 1.1177; NEXTII Rates from HT 2/6/19 FY23: 1.1177; NEXTII Rates from HT 2/6/19 FY24: 1.1177; NEXTII Rates from HT 2/6/19 FY25: 1.1177; NEXTII Rates from HT 2/6/19 FY26: 1.1177; NEXTII Rates from HT 2/6/19 FY27: 1.1177; NEXTII Rates from HT 2/6/19 FY28: 1.1177; NEXTII Rates from HT 2/6/19 FY29: 1.1177; NEXTII Rates from HT 2/6/19 FY30: 1.1177; NEXTII Rates from HT 2/6/19 FY31: 1.1177; NEXTII Rates from HT 2/6/19 FY32: 1.1177; EPR_FY19 FY33: 1.1177; EPR_FY19 FY34: 1.1177; EPR_FY19 FY35: 1.1177; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 1.1389; OPS19 FY33: 1.1389; OPS19 FY34: 1.1389; OPS19 FY35: 1.1389; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 1.1189; EPRSS19 FY33: 1.1189; EPRSS19 FY34: 1.1189; EPRSS19 FY35: 1.1189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 1.176; ACT19 FY33: 1.176; ACT19 FY34: 1.176; ACT19 FY35: 1.176; Std. Operating Ovhd - FY18 Base Year FY16: 1.21; Std. Operating Ovhd - FY18 Base Year FY17: 1.21; Std. Operating Ovhd - FY18 Base Year FY18: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY19: 60; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NLP | Material_Large Procurment (> $2M)_NLP | Material | Material_Large Procurment (> $2M)_NLP | NEXTII Rates from HT 2/6/19 FY19: 1.023; NEXTII Rates from HT 2/6/19 FY20: 1.0465; NEXTII Rates from HT 2/6/19 FY21: 1.0706; NEXTII Rates from HT 2/6/19 FY22: 1.0952; NEXTII Rates from HT 2/6/19 FY23: 1.1204; NEXTII Rates from HT 2/6/19 FY24: 1.1462; NEXTII Rates from HT 2/6/19 FY25: 1.1725; NEXTII Rates from HT 2/6/19 FY26: 1.1995; NEXTII Rates from HT 2/6/19 FY27: 1.2271; NEXTII Rates from HT 2/6/19 FY28: 1.2553; NEXTII Rates from HT 2/6/19 FY29: 1.2842; NEXTII Rates from HT 2/6/19 FY30: 1.3137; NEXTII Rates from HT 2/6/19 FY31: 1.3439; NEXTII Rates from HT 2/6/19 FY32: 1.3749; EPR_FY19 FY33: 1.4065; EPR_FY19 FY34: 1.4388; EPR_FY19 FY35: 1.4719; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 1.023; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 1.0465; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 1.0706; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 1.0952; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 1.1204; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 1.1462; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 1.1725; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 1.1995; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 1.2271; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 1.2553; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 1.2842; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 1.3137; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 1.3439; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 1.3749; OPS19 FY33: 1.4065; OPS19 FY34: 1.4388; OPS19 FY35: 1.4719; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 1.023; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 1.0465; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 1.0706; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 1.0952; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 1.1204; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 1.1462; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 1.1725; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 1.1995; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 1.2271; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 1.2553; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 1.2842; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 1.3137; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 1.3439; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 1.3749; EPRSS19 FY33: 1.4065; EPRSS19 FY34: 1.4388; EPRSS19 FY35: 1.4719; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 1.0537; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 1.0779; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 1.1027; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 1.1281; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 1.154; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 1.1806; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 1.2077; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 1.2355; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 1.2639; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 1.293; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 1.3227; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 1.3531; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 1.3843; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 1.4161; ACT19 FY33: 1.4487; ACT19 FY34: 1.482; ACT19 FY35: 1.5161; Std. Operating Ovhd - FY18 Base Year FY16: 1.4274; Std. Operating Ovhd - FY18 Base Year FY17: 1.4274; Std. Operating Ovhd - FY18 Base Year FY18: 1.4274; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.4274; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.4274; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.4274; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.4274; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.4274; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.4274; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.4274; Insert Notes About Rate Set - Date, Origin, Etc FY19: 61; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.0496; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.0737; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.0984; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.1237; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.1495; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.176; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.203; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.2307; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.259; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.288; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NSM | Material_Material (Purchase >$25k)_NSM | Material | Material_Material (Purchase >$25k)_NSM | NEXTII Rates from HT 2/6/19 FY19: 1.1177; NEXTII Rates from HT 2/6/19 FY20: 1.1434; NEXTII Rates from HT 2/6/19 FY21: 1.1697; NEXTII Rates from HT 2/6/19 FY22: 1.1966; NEXTII Rates from HT 2/6/19 FY23: 1.2241; NEXTII Rates from HT 2/6/19 FY24: 1.2522; NEXTII Rates from HT 2/6/19 FY25: 1.281; NEXTII Rates from HT 2/6/19 FY26: 1.3105; NEXTII Rates from HT 2/6/19 FY27: 1.3406; NEXTII Rates from HT 2/6/19 FY28: 1.3715; NEXTII Rates from HT 2/6/19 FY29: 1.403; NEXTII Rates from HT 2/6/19 FY30: 1.4353; NEXTII Rates from HT 2/6/19 FY31: 1.4683; NEXTII Rates from HT 2/6/19 FY32: 1.5021; EPR_FY19 FY33: 1.5366; EPR_FY19 FY34: 1.572; EPR_FY19 FY35: 1.6081; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 1.1651; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 1.1919; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 1.2193; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 1.2473; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 1.276; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 1.3054; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 1.3354; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 1.3661; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 1.3975; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 1.4297; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 1.4626; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 1.4962; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 1.5306; OPS19 FY33: 1.5658; OPS19 FY34: 1.6018; OPS19 FY35: 1.6387; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 1.1446; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 1.171; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 1.1979; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 1.2255; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 1.2536; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 1.2825; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 1.312; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 1.3422; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 1.373; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 1.4046; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 1.4369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 1.47; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 1.5038; EPRSS19 FY33: 1.5384; EPRSS19 FY34: 1.5737; EPRSS19 FY35: 1.6099; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 1.2031; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 1.2307; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 1.259; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 1.288; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 1.3176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 1.3479; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 1.3789; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 1.4106; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 1.4431; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 1.4763; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 1.5102; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 1.545; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 1.5805; ACT19 FY33: 1.6168; ACT19 FY34: 1.654; ACT19 FY35: 1.6921; Std. Operating Ovhd - FY18 Base Year FY16: 1.4273; Std. Operating Ovhd - FY18 Base Year FY17: 1.4273; Std. Operating Ovhd - FY18 Base Year FY18: 1.4273; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.4273; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.4273; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.4273; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.4273; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.4273; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.4273; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.4273; Insert Notes About Rate Set - Date, Origin, Etc FY19: 63; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.1402; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.1665; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.1933; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.2207; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.2488; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.2775; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.3069; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.337; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.3677; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.3992; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NSM_Fixed | Material_Special Material (Fixed Rate)_NSM_Fixed | Material | Material_Special Material (Fixed Rate)_NSM_Fixed | NEXTII Rates from HT 2/6/19 FY19: 1.1177; NEXTII Rates from HT 2/6/19 FY20: 1.1177; NEXTII Rates from HT 2/6/19 FY21: 1.1177; NEXTII Rates from HT 2/6/19 FY22: 1.1177; NEXTII Rates from HT 2/6/19 FY23: 1.1177; NEXTII Rates from HT 2/6/19 FY24: 1.1177; NEXTII Rates from HT 2/6/19 FY25: 1.1177; NEXTII Rates from HT 2/6/19 FY26: 1.1177; NEXTII Rates from HT 2/6/19 FY27: 1.1177; NEXTII Rates from HT 2/6/19 FY28: 1.1177; NEXTII Rates from HT 2/6/19 FY29: 1.1177; NEXTII Rates from HT 2/6/19 FY30: 1.1177; NEXTII Rates from HT 2/6/19 FY31: 1.1177; NEXTII Rates from HT 2/6/19 FY32: 1.1177; EPR_FY19 FY33: 1.1177; EPR_FY19 FY34: 1.1177; EPR_FY19 FY35: 1.1177; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 1.1389; OPS19 FY33: 1.1389; OPS19 FY34: 1.1389; OPS19 FY35: 1.1389; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 1.1189; EPRSS19 FY33: 1.1189; EPRSS19 FY34: 1.1189; EPRSS19 FY35: 1.1189; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 1.176; ACT19 FY33: 1.176; ACT19 FY34: 1.176; ACT19 FY35: 1.176; Std. Operating Ovhd - FY18 Base Year FY16: 1.2584; Std. Operating Ovhd - FY18 Base Year FY17: 1.2584; Std. Operating Ovhd - FY18 Base Year FY18: 1.2584; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.2584; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.2584; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.2584; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.2584; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.2584; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.2584; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.2584; Insert Notes About Rate Set - Date, Origin, Etc FY19: 64; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NMA | Material_Material (Purchase <$25k)_NMA | Material | Material_Material (Purchase <$25k)_NMA | NEXTII Rates from HT 2/6/19 FY19: 1.1177; NEXTII Rates from HT 2/6/19 FY20: 1.1434; NEXTII Rates from HT 2/6/19 FY21: 1.1697; NEXTII Rates from HT 2/6/19 FY22: 1.1966; NEXTII Rates from HT 2/6/19 FY23: 1.2241; NEXTII Rates from HT 2/6/19 FY24: 1.2522; NEXTII Rates from HT 2/6/19 FY25: 1.281; NEXTII Rates from HT 2/6/19 FY26: 1.3105; NEXTII Rates from HT 2/6/19 FY27: 1.3406; NEXTII Rates from HT 2/6/19 FY28: 1.3715; NEXTII Rates from HT 2/6/19 FY29: 1.403; NEXTII Rates from HT 2/6/19 FY30: 1.4353; NEXTII Rates from HT 2/6/19 FY31: 1.4683; NEXTII Rates from HT 2/6/19 FY32: 1.5021; EPR_FY19 FY33: 1.5366; EPR_FY19 FY34: 1.572; EPR_FY19 FY35: 1.6081; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 1.1389; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 1.1651; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 1.1919; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 1.2193; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 1.2473; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 1.276; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 1.3054; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 1.3354; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 1.3661; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 1.3975; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 1.4297; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 1.4626; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 1.4962; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 1.5306; OPS19 FY33: 1.5658; OPS19 FY34: 1.6018; OPS19 FY35: 1.6387; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 1.1189; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 1.1446; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 1.171; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 1.1979; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 1.2255; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 1.2536; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 1.2825; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 1.312; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 1.3422; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 1.373; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 1.4046; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 1.4369; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 1.47; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 1.5038; EPRSS19 FY33: 1.5384; EPRSS19 FY34: 1.5737; EPRSS19 FY35: 1.6099; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 1.176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 1.2031; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 1.2307; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 1.259; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 1.288; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 1.3176; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 1.3479; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 1.3789; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 1.4106; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 1.4431; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 1.4763; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 1.5102; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 1.545; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 1.5805; ACT19 FY33: 1.6168; ACT19 FY34: 1.654; ACT19 FY35: 1.6921; Std. Operating Ovhd - FY18 Base Year FY16: 1.5166; Std. Operating Ovhd - FY18 Base Year FY17: 1.5166; Std. Operating Ovhd - FY18 Base Year FY18: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY19: 65; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.1146; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.1402; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.1665; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.1933; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.2207; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.2488; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.2775; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.3069; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.337; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.3677; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.3992; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NTR | Nonlabor_Travel Cost_NTR | Material | Nonlabor_Travel Cost_NTR | NEXTII Rates from HT 2/6/19 FY19: 1.3566; NEXTII Rates from HT 2/6/19 FY20: 1.3879; NEXTII Rates from HT 2/6/19 FY21: 1.4198; NEXTII Rates from HT 2/6/19 FY22: 1.4524; NEXTII Rates from HT 2/6/19 FY23: 1.4858; NEXTII Rates from HT 2/6/19 FY24: 1.52; NEXTII Rates from HT 2/6/19 FY25: 1.555; NEXTII Rates from HT 2/6/19 FY26: 1.5907; NEXTII Rates from HT 2/6/19 FY27: 1.6273; NEXTII Rates from HT 2/6/19 FY28: 1.6647; NEXTII Rates from HT 2/6/19 FY29: 1.703; NEXTII Rates from HT 2/6/19 FY30: 1.7422; NEXTII Rates from HT 2/6/19 FY31: 1.7823; NEXTII Rates from HT 2/6/19 FY32: 1.8233; EPR_FY19 FY33: 1.8652; EPR_FY19 FY34: 1.9081; EPR_FY19 FY35: 1.952; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY19: 1.6611; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY20: 1.6993; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY21: 1.7384; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY22: 1.7784; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY23: 1.8193; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY24: 1.8612; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY25: 1.904; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY26: 1.9478; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY27: 1.9925; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY28: 2.0384; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY29: 2.0853; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY30: 2.1332; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY31: 2.1823; Direct rates from HT 2/6/19, burden rates from HT via Rich 5/7/18 FY32: 2.2325; OPS19 FY33: 2.2838; OPS19 FY34: 2.3364; OPS19 FY35: 2.3901; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY19: 1.3747; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY20: 1.4064; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY21: 1.4387; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY22: 1.4718; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY23: 1.5057; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY24: 1.5403; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY25: 1.5757; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY26: 1.612; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY27: 1.649; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY28: 1.687; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY29: 1.7258; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY30: 1.7654; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY31: 1.8061; Direct rates from HT 2/6/19, HEX burden rates from HT 5/14/18 FY32: 1.8476; EPRSS19 FY33: 1.8901; EPRSS19 FY34: 1.9336; EPRSS19 FY35: 1.978; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY19: 1.7533; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY20: 1.7936; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY21: 1.8348; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY22: 1.8771; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY23: 1.9202; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY24: 1.9644; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY25: 2.0096; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY26: 2.0558; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY27: 2.1031; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY28: 2.1514; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY29: 2.2009; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY30: 2.2515; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY31: 2.3033; Direct rates from HT 2/6/19, CryoEM burden rates from HT 12/27/18 FY32: 2.3563; ACT19 FY33: 2.4105; ACT19 FY34: 2.4659; ACT19 FY35: 2.5227; Std. Operating Ovhd - FY18 Base Year FY16: 1.5166; Std. Operating Ovhd - FY18 Base Year FY17: 1.5166; Std. Operating Ovhd - FY18 Base Year FY18: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.5166; Insert Notes About Rate Set - Date, Origin, Etc FY19: 67; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.3543; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.3854; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.4173; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.4499; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.4833; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.5174; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.5523; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.588; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.6245; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.6619; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.7001; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
OPD | Not BNL costs (postdoc) | Material | Material_Not BNL cost (postdoc) | Std. Operating Ovhd - FY18 Base Year FY16: 1; Std. Operating Ovhd - FY18 Base Year FY17: 1; Std. Operating Ovhd - FY18 Base Year FY18: 1; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1; Insert Notes About Rate Set - Date, Origin, Etc FY19: #N/A; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
OPM | Not BNL costs (instrument) | Material | Material_Not BNL cost (instrument) | Std. Operating Ovhd - FY18 Base Year FY16: 1; Std. Operating Ovhd - FY18 Base Year FY17: 1; Std. Operating Ovhd - FY18 Base Year FY18: 1; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1; Insert Notes About Rate Set - Date, Origin, Etc FY19: #N/A; Insert Notes About Rate Set - Date, Origin, Etc FY20: 0; Insert Notes About Rate Set - Date, Origin, Etc FY21: 0; Insert Notes About Rate Set - Date, Origin, Etc FY22: 0; Insert Notes About Rate Set - Date, Origin, Etc FY23: 0; Insert Notes About Rate Set - Date, Origin, Etc FY24: 0; Insert Notes About Rate Set - Date, Origin, Etc FY25: 0; Insert Notes About Rate Set - Date, Origin, Etc FY26: 0; Insert Notes About Rate Set - Date, Origin, Etc FY27: 0; Insert Notes About Rate Set - Date, Origin, Etc FY28: 0; Insert Notes About Rate Set - Date, Origin, Etc FY29: 0; Insert Notes About Rate Set - Date, Origin, Etc FY30: 0; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTA | Building Trades Assigned | Labor | Labor_Building Trades Assigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 49; Insert Notes About Rate Set - Date, Origin, Etc FY20: 123.2918; Insert Notes About Rate Set - Date, Origin, Etc FY21: 126.1275; Insert Notes About Rate Set - Date, Origin, Etc FY22: 129.0285; Insert Notes About Rate Set - Date, Origin, Etc FY23: 131.9961; Insert Notes About Rate Set - Date, Origin, Etc FY24: 135.032; Insert Notes About Rate Set - Date, Origin, Etc FY25: 138.1378; Insert Notes About Rate Set - Date, Origin, Etc FY26: 141.315; Insert Notes About Rate Set - Date, Origin, Etc FY27: 144.5652; Insert Notes About Rate Set - Date, Origin, Etc FY28: 147.8902; Insert Notes About Rate Set - Date, Origin, Etc FY29: 151.2917; Insert Notes About Rate Set - Date, Origin, Etc FY30: 154.7714; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTAC | Building Trades Carpenter - Assigned | Labor | Labor_Building Trades Carpenter - Assigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 50; Insert Notes About Rate Set - Date, Origin, Etc FY20: 123.2918; Insert Notes About Rate Set - Date, Origin, Etc FY21: 126.1275; Insert Notes About Rate Set - Date, Origin, Etc FY22: 129.0285; Insert Notes About Rate Set - Date, Origin, Etc FY23: 131.9961; Insert Notes About Rate Set - Date, Origin, Etc FY24: 135.032; Insert Notes About Rate Set - Date, Origin, Etc FY25: 138.1378; Insert Notes About Rate Set - Date, Origin, Etc FY26: 141.315; Insert Notes About Rate Set - Date, Origin, Etc FY27: 144.5652; Insert Notes About Rate Set - Date, Origin, Etc FY28: 147.8902; Insert Notes About Rate Set - Date, Origin, Etc FY29: 151.2917; Insert Notes About Rate Set - Date, Origin, Etc FY30: 154.7714; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTAE | Building Trades Electrician - Assigned | Labor | Labor_Building Trades Electrician - Assigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 51; Insert Notes About Rate Set - Date, Origin, Etc FY20: 123.2918; Insert Notes About Rate Set - Date, Origin, Etc FY21: 126.1275; Insert Notes About Rate Set - Date, Origin, Etc FY22: 129.0285; Insert Notes About Rate Set - Date, Origin, Etc FY23: 131.9961; Insert Notes About Rate Set - Date, Origin, Etc FY24: 135.032; Insert Notes About Rate Set - Date, Origin, Etc FY25: 138.1378; Insert Notes About Rate Set - Date, Origin, Etc FY26: 141.315; Insert Notes About Rate Set - Date, Origin, Etc FY27: 144.5652; Insert Notes About Rate Set - Date, Origin, Etc FY28: 147.8902; Insert Notes About Rate Set - Date, Origin, Etc FY29: 151.2917; Insert Notes About Rate Set - Date, Origin, Etc FY30: 154.7714; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTAP | Building Trades Plumber - Assigned | Labor | Labor_Building Trades Plumber - Assigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 52; Insert Notes About Rate Set - Date, Origin, Etc FY20: 123.2918; Insert Notes About Rate Set - Date, Origin, Etc FY21: 126.1275; Insert Notes About Rate Set - Date, Origin, Etc FY22: 129.0285; Insert Notes About Rate Set - Date, Origin, Etc FY23: 131.9961; Insert Notes About Rate Set - Date, Origin, Etc FY24: 135.032; Insert Notes About Rate Set - Date, Origin, Etc FY25: 138.1378; Insert Notes About Rate Set - Date, Origin, Etc FY26: 141.315; Insert Notes About Rate Set - Date, Origin, Etc FY27: 144.5652; Insert Notes About Rate Set - Date, Origin, Etc FY28: 147.8902; Insert Notes About Rate Set - Date, Origin, Etc FY29: 151.2917; Insert Notes About Rate Set - Date, Origin, Etc FY30: 154.7714; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTAR | Building Trades Riggers - Assigned | Labor | Labor_Building Trades Riggers - Assigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 53; Insert Notes About Rate Set - Date, Origin, Etc FY20: 123.2918; Insert Notes About Rate Set - Date, Origin, Etc FY21: 126.1275; Insert Notes About Rate Set - Date, Origin, Etc FY22: 129.0285; Insert Notes About Rate Set - Date, Origin, Etc FY23: 131.9961; Insert Notes About Rate Set - Date, Origin, Etc FY24: 135.032; Insert Notes About Rate Set - Date, Origin, Etc FY25: 138.1378; Insert Notes About Rate Set - Date, Origin, Etc FY26: 141.315; Insert Notes About Rate Set - Date, Origin, Etc FY27: 144.5652; Insert Notes About Rate Set - Date, Origin, Etc FY28: 147.8902; Insert Notes About Rate Set - Date, Origin, Etc FY29: 151.2917; Insert Notes About Rate Set - Date, Origin, Etc FY30: 154.7714; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTU | Building Trades Unassigned | Labor | Labor_Building Trades Unassigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 54; Insert Notes About Rate Set - Date, Origin, Etc FY20: 145.796; Insert Notes About Rate Set - Date, Origin, Etc FY21: 149.1493; Insert Notes About Rate Set - Date, Origin, Etc FY22: 152.5797; Insert Notes About Rate Set - Date, Origin, Etc FY23: 156.0891; Insert Notes About Rate Set - Date, Origin, Etc FY24: 159.6791; Insert Notes About Rate Set - Date, Origin, Etc FY25: 163.3517; Insert Notes About Rate Set - Date, Origin, Etc FY26: 167.1088; Insert Notes About Rate Set - Date, Origin, Etc FY27: 170.9523; Insert Notes About Rate Set - Date, Origin, Etc FY28: 174.8842; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9066; Insert Notes About Rate Set - Date, Origin, Etc FY30: 183.0214; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTUC | Building Trades Carpenter - Unassigned | Labor | Labor_Building Trades Carpenter - Unassigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 55; Insert Notes About Rate Set - Date, Origin, Etc FY20: 145.796; Insert Notes About Rate Set - Date, Origin, Etc FY21: 149.1493; Insert Notes About Rate Set - Date, Origin, Etc FY22: 152.5797; Insert Notes About Rate Set - Date, Origin, Etc FY23: 156.0891; Insert Notes About Rate Set - Date, Origin, Etc FY24: 159.6791; Insert Notes About Rate Set - Date, Origin, Etc FY25: 163.3517; Insert Notes About Rate Set - Date, Origin, Etc FY26: 167.1088; Insert Notes About Rate Set - Date, Origin, Etc FY27: 170.9523; Insert Notes About Rate Set - Date, Origin, Etc FY28: 174.8842; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9066; Insert Notes About Rate Set - Date, Origin, Etc FY30: 183.0214; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTUE | Building Trades Electrician - Unassigned | Labor | Labor_Building Trades Electrician - Unassigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 56; Insert Notes About Rate Set - Date, Origin, Etc FY20: 145.796; Insert Notes About Rate Set - Date, Origin, Etc FY21: 149.1493; Insert Notes About Rate Set - Date, Origin, Etc FY22: 152.5797; Insert Notes About Rate Set - Date, Origin, Etc FY23: 156.0891; Insert Notes About Rate Set - Date, Origin, Etc FY24: 159.6791; Insert Notes About Rate Set - Date, Origin, Etc FY25: 163.3517; Insert Notes About Rate Set - Date, Origin, Etc FY26: 167.1088; Insert Notes About Rate Set - Date, Origin, Etc FY27: 170.9523; Insert Notes About Rate Set - Date, Origin, Etc FY28: 174.8842; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9066; Insert Notes About Rate Set - Date, Origin, Etc FY30: 183.0214; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTUP | Building Trades Plumber - Unassigned | Labor | Labor_Building Trades Plumber - Unassigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 57; Insert Notes About Rate Set - Date, Origin, Etc FY20: 145.796; Insert Notes About Rate Set - Date, Origin, Etc FY21: 149.1493; Insert Notes About Rate Set - Date, Origin, Etc FY22: 152.5797; Insert Notes About Rate Set - Date, Origin, Etc FY23: 156.0891; Insert Notes About Rate Set - Date, Origin, Etc FY24: 159.6791; Insert Notes About Rate Set - Date, Origin, Etc FY25: 163.3517; Insert Notes About Rate Set - Date, Origin, Etc FY26: 167.1088; Insert Notes About Rate Set - Date, Origin, Etc FY27: 170.9523; Insert Notes About Rate Set - Date, Origin, Etc FY28: 174.8842; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9066; Insert Notes About Rate Set - Date, Origin, Etc FY30: 183.0214; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
BTUR | Building Trades Riggers - Unassigned | Labor | Labor_Building Trades Riggers - Unassigned | Insert Notes About Rate Set - Date, Origin, Etc FY19: 58; Insert Notes About Rate Set - Date, Origin, Etc FY20: 145.796; Insert Notes About Rate Set - Date, Origin, Etc FY21: 149.1493; Insert Notes About Rate Set - Date, Origin, Etc FY22: 152.5797; Insert Notes About Rate Set - Date, Origin, Etc FY23: 156.0891; Insert Notes About Rate Set - Date, Origin, Etc FY24: 159.6791; Insert Notes About Rate Set - Date, Origin, Etc FY25: 163.3517; Insert Notes About Rate Set - Date, Origin, Etc FY26: 167.1088; Insert Notes About Rate Set - Date, Origin, Etc FY27: 170.9523; Insert Notes About Rate Set - Date, Origin, Etc FY28: 174.8842; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.9066; Insert Notes About Rate Set - Date, Origin, Etc FY30: 183.0214; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NLP_Fixed | Large Procurment (portion >$2M) (Fixed Rate) | Labor | Labor_Large Procurment (portion >$2M) (Fixed Rate) | Insert Notes About Rate Set - Date, Origin, Etc FY19: 62; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.026; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NCT_Fixed | Purchased Professionl Labor (Fixed Rate) | Labor | Labor_Purchased Professionl Labor (Fixed Rate) | Insert Notes About Rate Set - Date, Origin, Etc FY19: 68; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
NCT | Purchased Professionl Labor | Labor | Labor_Purchased Professionl Labor | Insert Notes About Rate Set - Date, Origin, Etc FY19: 69; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.2657; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.3037; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.3428; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.3831; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.4246; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.4673; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.5113; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.5567; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.6034; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.6515; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.701; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_ADM | MPO Administrative | Labor | Labor_MPO Administrative | Insert Notes About Rate Set - Date, Origin, Etc FY19: 70; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_ARC | MPO Architect | Labor | Labor_MPO Architect | Insert Notes About Rate Set - Date, Origin, Etc FY19: 71; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_CAM | MPO CAM | Labor | Labor_MPO CAM | Insert Notes About Rate Set - Date, Origin, Etc FY19: 72; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_CON | MPO Consultants | Labor | Labor_MPO Consultants | Insert Notes About Rate Set - Date, Origin, Etc FY19: 73; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_EEP | MPO Project Electrical Engineer | Labor | Labor_MPO Project Electrical Engineer | Insert Notes About Rate Set - Date, Origin, Etc FY19: 74; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_EES | MPO Senior Electrical Engineer | Labor | Labor_MPO Senior Electrical Engineer | Insert Notes About Rate Set - Date, Origin, Etc FY19: 75; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_EI | MPO Electrical Inspector | Labor | Labor_MPO Electrical Inspector | Insert Notes About Rate Set - Date, Origin, Etc FY19: 76; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_MEP | MPO Project Mechanical Engineer | Labor | Labor_MPO Project Mechanical Engineer | Insert Notes About Rate Set - Date, Origin, Etc FY19: 77; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_MES | MPO Senior Mechanical Engineer | Labor | Labor_MPO Senior Mechanical Engineer | Insert Notes About Rate Set - Date, Origin, Etc FY19: 78; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_MGR | MPO Manager | Labor | Labor_MPO Manager | Insert Notes About Rate Set - Date, Origin, Etc FY19: 79; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_MI | MPO Mechanical Inspector | Labor | Labor_MPO Mechanical Inspector | Insert Notes About Rate Set - Date, Origin, Etc FY19: 80; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_OTH | MPO Other Professional | Labor | Labor_MPO Other Professional | Insert Notes About Rate Set - Date, Origin, Etc FY19: 81; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_SAF | MPO Safety Engineer | Labor | Labor_MPO Safety Engineer | Insert Notes About Rate Set - Date, Origin, Etc FY19: 82; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_SE | MPO Structural Engineer | Labor | Labor_MPO Structural Engineer | Insert Notes About Rate Set - Date, Origin, Etc FY19: 83; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_Shops | MPO Job Shop Resource | Labor | Labor_MPO Job Shop Resource | Insert Notes About Rate Set - Date, Origin, Etc FY19: 84; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0
MPO_SI | MPO Structural Inspector | Labor | Labor_MPO Structural Inspector | Insert Notes About Rate Set - Date, Origin, Etc FY19: 85; Insert Notes About Rate Set - Date, Origin, Etc FY20: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY21: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY22: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY23: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY24: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY25: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY26: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY27: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY28: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY29: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY30: 186.792; Insert Notes About Rate Set - Date, Origin, Etc FY31: 0; Insert Notes About Rate Set - Date, Origin, Etc FY32: 0; MIE FY33: 0; MIE FY34: 0; MIE FY35: 0

## Resource Structure 3 (hidden)
RESOURCE STRUCTURE: | LTS |  |  | LTS FY_19 Rates |  |  | Created by Jaclyn from P6 Rates on 2/14/19 | [13 empty] | NEED TO ADD P6 SUFFIX |  |  | LTS FY_19 Direct Rates |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX |  |  | RATE SET NAME |  |  | Insert Notes About Rate Set - Date, Origin, Etc | [13 empty] | RESOURCE ID SUFFIX
Resource ID | Description | Resource Type | Combined Name | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35
FY19_18264 | Admin Asst, ADMIN2, LTS | Labor | Admin Asst, ADMIN2, LTS | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 48.1054; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 48.472; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 49.9747; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 51.5239; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 53.1211; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 54.7679; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 56.4657; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 58.2161; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 60.0208; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 61.8815; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 63.7998; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 63.7998; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 67.8167; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 69.919; NEED TO ADD P6 SUFFIX FY33: 72.0865; NEED TO ADD P6 SUFFIX FY34: 74.3212; NEED TO ADD P6 SUFFIX FY35: 76.6251; Insert Notes About Rate Set - Date, Origin, Etc FY19: 88.25; Insert Notes About Rate Set - Date, Origin, Etc FY20: 91.78; Insert Notes About Rate Set - Date, Origin, Etc FY21: 95.45; Insert Notes About Rate Set - Date, Origin, Etc FY22: 99.27; Insert Notes About Rate Set - Date, Origin, Etc FY23: 103.24; Insert Notes About Rate Set - Date, Origin, Etc FY24: 107.37; Insert Notes About Rate Set - Date, Origin, Etc FY25: 111.66; Insert Notes About Rate Set - Date, Origin, Etc FY26: 116.13; Insert Notes About Rate Set - Date, Origin, Etc FY27: 120.78; Insert Notes About Rate Set - Date, Origin, Etc FY28: 125.61; Insert Notes About Rate Set - Date, Origin, Etc FY29: 130.63; Insert Notes About Rate Set - Date, Origin, Etc FY30: 135.86; Insert Notes About Rate Set - Date, Origin, Etc FY31: 141.29; Insert Notes About Rate Set - Date, Origin, Etc FY32: 146.94; RESOURCE ID SUFFIX FY33: 152.82; RESOURCE ID SUFFIX FY34: 158.93; RESOURCE ID SUFFIX FY35: 165.29
FY19_Q7045 | WMD Technical | Labor | ADMIN5, LTS Project Controls | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 124; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 132.2813; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 135.3237; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 138.4362; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 141.6202; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 144.8775; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 148.2097; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 151.6185; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 155.1057; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 158.6731; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 162.3226; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 162.3226; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 169.8753; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 173.7825; NEED TO ADD P6 SUFFIX FY33: 177.7795; NEED TO ADD P6 SUFFIX FY34: 181.8684; NEED TO ADD P6 SUFFIX FY35: 186.0514; Insert Notes About Rate Set - Date, Origin, Etc FY19: 156.42; Insert Notes About Rate Set - Date, Origin, Etc FY20: 162.68; Insert Notes About Rate Set - Date, Origin, Etc FY21: 169.19; Insert Notes About Rate Set - Date, Origin, Etc FY22: 175.96; Insert Notes About Rate Set - Date, Origin, Etc FY23: 183; Insert Notes About Rate Set - Date, Origin, Etc FY24: 190.32; Insert Notes About Rate Set - Date, Origin, Etc FY25: 197.93; Insert Notes About Rate Set - Date, Origin, Etc FY26: 205.85; Insert Notes About Rate Set - Date, Origin, Etc FY27: 214.08; Insert Notes About Rate Set - Date, Origin, Etc FY28: 222.64; Insert Notes About Rate Set - Date, Origin, Etc FY29: 231.55; Insert Notes About Rate Set - Date, Origin, Etc FY30: 240.81; Insert Notes About Rate Set - Date, Origin, Etc FY31: 250.44; Insert Notes About Rate Set - Date, Origin, Etc FY32: 260.46; RESOURCE ID SUFFIX FY33: 270.88; RESOURCE ID SUFFIX FY34: 281.72; RESOURCE ID SUFFIX FY35: 292.99
FY19_21133 | ADMIN6, LTS MGR | Labor | ADMIN6, LTS MGR | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 138.1072; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 138.9827; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 143.2912; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 147.7332; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 152.313; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 157.0347; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 161.9027; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 166.9217; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 172.0963; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 177.4313; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 182.9316; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 182.9316; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 194.4492; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 200.4771; NEED TO ADD P6 SUFFIX FY33: 206.6919; NEED TO ADD P6 SUFFIX FY34: 213.0994; NEED TO ADD P6 SUFFIX FY35: 219.7055; Insert Notes About Rate Set - Date, Origin, Etc FY19: 204.24; Insert Notes About Rate Set - Date, Origin, Etc FY20: 212.41; Insert Notes About Rate Set - Date, Origin, Etc FY21: 220.91; Insert Notes About Rate Set - Date, Origin, Etc FY22: 229.75; Insert Notes About Rate Set - Date, Origin, Etc FY23: 238.94; Insert Notes About Rate Set - Date, Origin, Etc FY24: 248.5; Insert Notes About Rate Set - Date, Origin, Etc FY25: 258.44; Insert Notes About Rate Set - Date, Origin, Etc FY26: 268.78; Insert Notes About Rate Set - Date, Origin, Etc FY27: 279.53; Insert Notes About Rate Set - Date, Origin, Etc FY28: 290.71; Insert Notes About Rate Set - Date, Origin, Etc FY29: 302.34; Insert Notes About Rate Set - Date, Origin, Etc FY30: 314.43; Insert Notes About Rate Set - Date, Origin, Etc FY31: 327.01; Insert Notes About Rate Set - Date, Origin, Etc FY32: 340.09; RESOURCE ID SUFFIX FY33: 353.69; RESOURCE ID SUFFIX FY34: 367.84; RESOURCE ID SUFFIX FY35: 382.55
FY19_609 | Copy Services | Nonlabor | Copy Services | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.023; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.0465; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.0706; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.0952; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.1204; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.1462; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.1725; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.1995; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.2271; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.3137; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.344; NEED TO ADD P6 SUFFIX FY33: 1.3749; NEED TO ADD P6 SUFFIX FY34: 1.4065; NEED TO ADD P6 SUFFIX FY35: 1.4388; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.5; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.54; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.58; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.62; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.66; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.7; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.74; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.78; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.82; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.87; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.92; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.97; Insert Notes About Rate Set - Date, Origin, Etc FY31: 2.02; Insert Notes About Rate Set - Date, Origin, Etc FY32: 2.07; RESOURCE ID SUFFIX FY33: 2.12; RESOURCE ID SUFFIX FY34: 2.17; RESOURCE ID SUFFIX FY35: 2.22
FY19_ECR_PROF2 | ECR PROF2 | Labor | ECR PROF2 | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 79.3438; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 81.8035; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 84.3394; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 86.9539; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 89.6495; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 92.4286; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 95.2939; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 98.248; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 101.2937; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 104.4338; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 107.6713; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 107.6713; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 114.4504; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 117.9983; NEED TO ADD P6 SUFFIX FY33: 121.6563; NEED TO ADD P6 SUFFIX FY34: 125.4276; NEED TO ADD P6 SUFFIX FY35: 129.3159; Insert Notes About Rate Set - Date, Origin, Etc FY19: 79.3438; Insert Notes About Rate Set - Date, Origin, Etc FY20: 81.8035; Insert Notes About Rate Set - Date, Origin, Etc FY21: 84.3394; Insert Notes About Rate Set - Date, Origin, Etc FY22: 86.9539; Insert Notes About Rate Set - Date, Origin, Etc FY23: 89.6495; Insert Notes About Rate Set - Date, Origin, Etc FY24: 92.4286; Insert Notes About Rate Set - Date, Origin, Etc FY25: 95.2939; Insert Notes About Rate Set - Date, Origin, Etc FY26: 98.248; Insert Notes About Rate Set - Date, Origin, Etc FY27: 101.2937; Insert Notes About Rate Set - Date, Origin, Etc FY28: 104.4338; Insert Notes About Rate Set - Date, Origin, Etc FY29: 107.6713; Insert Notes About Rate Set - Date, Origin, Etc FY30: 107.6713; Insert Notes About Rate Set - Date, Origin, Etc FY31: 114.4504; Insert Notes About Rate Set - Date, Origin, Etc FY32: 117.9983; RESOURCE ID SUFFIX FY33: 121.6563; RESOURCE ID SUFFIX FY34: 125.4276; RESOURCE ID SUFFIX FY35: 129.3159
FY19_17382 | ESD, ES&H Coordinator | Labor | ESD, ES&H Coordinator | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 90.37; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 83.08; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 86.45; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 89.95; NEED TO ADD P6 SUFFIX FY33: 89.95; NEED TO ADD P6 SUFFIX FY34: 89.95; NEED TO ADD P6 SUFFIX FY35: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY19: 120.34; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.15; Insert Notes About Rate Set - Date, Origin, Etc FY21: 130.16; Insert Notes About Rate Set - Date, Origin, Etc FY22: 135.37; Insert Notes About Rate Set - Date, Origin, Etc FY23: 140.78; Insert Notes About Rate Set - Date, Origin, Etc FY24: 146.41; Insert Notes About Rate Set - Date, Origin, Etc FY25: 152.27; Insert Notes About Rate Set - Date, Origin, Etc FY26: 158.36; Insert Notes About Rate Set - Date, Origin, Etc FY27: 164.69; Insert Notes About Rate Set - Date, Origin, Etc FY28: 171.28; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.13; Insert Notes About Rate Set - Date, Origin, Etc FY30: 185.26; Insert Notes About Rate Set - Date, Origin, Etc FY31: 192.67; Insert Notes About Rate Set - Date, Origin, Etc FY32: 200.38; RESOURCE ID SUFFIX FY33: 208.4; RESOURCE ID SUFFIX FY34: 216.74; RESOURCE ID SUFFIX FY35: 225.41
FY19_23494 | ESHR/SHR | Labor | ESHR/SHR | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 79.85; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 83.08; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 86.45; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 89.95; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 89.95; NEED TO ADD P6 SUFFIX FY33: 89.95; NEED TO ADD P6 SUFFIX FY34: 89.95; NEED TO ADD P6 SUFFIX FY35: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY19: 79.85; Insert Notes About Rate Set - Date, Origin, Etc FY20: 83.08; Insert Notes About Rate Set - Date, Origin, Etc FY21: 86.45; Insert Notes About Rate Set - Date, Origin, Etc FY22: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY23: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY24: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY25: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY26: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY27: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY28: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY29: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY30: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY31: 89.95; Insert Notes About Rate Set - Date, Origin, Etc FY32: 89.95; RESOURCE ID SUFFIX FY33: 89.95; RESOURCE ID SUFFIX FY34: 89.95; RESOURCE ID SUFFIX FY35: 89.95
FY19_ESHR_SHR_PROF2 | ESHR/SHR PROF2 | Labor | ESHR/SHR PROF2 | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 79.3438; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 81.8035; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 84.3394; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 86.9539; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 89.6495; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 92.4286; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 95.2939; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 98.248; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 101.2937; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 104.4338; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 107.6713; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 107.6713; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 114.4504; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 117.9983; NEED TO ADD P6 SUFFIX FY33: 121.6563; NEED TO ADD P6 SUFFIX FY34: 125.4276; NEED TO ADD P6 SUFFIX FY35: 129.3159; Insert Notes About Rate Set - Date, Origin, Etc FY19: 79.3438; Insert Notes About Rate Set - Date, Origin, Etc FY20: 81.8035; Insert Notes About Rate Set - Date, Origin, Etc FY21: 84.3394; Insert Notes About Rate Set - Date, Origin, Etc FY22: 86.9539; Insert Notes About Rate Set - Date, Origin, Etc FY23: 89.6495; Insert Notes About Rate Set - Date, Origin, Etc FY24: 92.4286; Insert Notes About Rate Set - Date, Origin, Etc FY25: 95.2939; Insert Notes About Rate Set - Date, Origin, Etc FY26: 98.248; Insert Notes About Rate Set - Date, Origin, Etc FY27: 101.2937; Insert Notes About Rate Set - Date, Origin, Etc FY28: 104.4338; Insert Notes About Rate Set - Date, Origin, Etc FY29: 107.6713; Insert Notes About Rate Set - Date, Origin, Etc FY30: 107.6713; Insert Notes About Rate Set - Date, Origin, Etc FY31: 114.4504; Insert Notes About Rate Set - Date, Origin, Etc FY32: 117.9983; RESOURCE ID SUFFIX FY33: 121.6563; RESOURCE ID SUFFIX FY34: 125.4276; RESOURCE ID SUFFIX FY35: 129.3159
FY19_22746 | Field Engineer, PROF2, LTYS DATA | Labor | Field Engineer, PROF2, LTYS DATA | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 100.176; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 101.9355; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 105.0955; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 108.3534; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 111.7124; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 115.1755; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 118.7459; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 122.427; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 126.2223; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 130.1352; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 134.1693; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 134.1693; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 142.6168; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 147.0379; NEED TO ADD P6 SUFFIX FY33: 151.5961; NEED TO ADD P6 SUFFIX FY34: 156.2955; NEED TO ADD P6 SUFFIX FY35: 161.1407; Insert Notes About Rate Set - Date, Origin, Etc FY19: 120.34; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.15; Insert Notes About Rate Set - Date, Origin, Etc FY21: 130.16; Insert Notes About Rate Set - Date, Origin, Etc FY22: 135.37; Insert Notes About Rate Set - Date, Origin, Etc FY23: 140.78; Insert Notes About Rate Set - Date, Origin, Etc FY24: 146.41; Insert Notes About Rate Set - Date, Origin, Etc FY25: 152.27; Insert Notes About Rate Set - Date, Origin, Etc FY26: 158.36; Insert Notes About Rate Set - Date, Origin, Etc FY27: 164.69; Insert Notes About Rate Set - Date, Origin, Etc FY28: 171.28; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.13; Insert Notes About Rate Set - Date, Origin, Etc FY30: 185.26; Insert Notes About Rate Set - Date, Origin, Etc FY31: 192.67; Insert Notes About Rate Set - Date, Origin, Etc FY32: 200.38; RESOURCE ID SUFFIX FY33: 208.4; RESOURCE ID SUFFIX FY34: 216.74; RESOURCE ID SUFFIX FY35: 225.41
FY19_614 | Field Sampling Team | Labor | Field Sampling Team | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 93.4306; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 95.5795; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 97.7778; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 100.0267; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 102.3273; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 104.6809; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 107.0885; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 109.5516; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 112.0712; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 114.6489; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 117.2858; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 117.2858; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 122.743; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 125.5661; NEED TO ADD P6 SUFFIX FY33: 128.4541; NEED TO ADD P6 SUFFIX FY34: 131.4085; NEED TO ADD P6 SUFFIX FY35: 134.4309; Insert Notes About Rate Set - Date, Origin, Etc FY19: 144.55; Insert Notes About Rate Set - Date, Origin, Etc FY20: 148.16; Insert Notes About Rate Set - Date, Origin, Etc FY21: 151.86; Insert Notes About Rate Set - Date, Origin, Etc FY22: 155.66; Insert Notes About Rate Set - Date, Origin, Etc FY23: 159.55; Insert Notes About Rate Set - Date, Origin, Etc FY24: 163.54; Insert Notes About Rate Set - Date, Origin, Etc FY25: 167.63; Insert Notes About Rate Set - Date, Origin, Etc FY26: 171.82; Insert Notes About Rate Set - Date, Origin, Etc FY27: 176.12; Insert Notes About Rate Set - Date, Origin, Etc FY28: 180.52; Insert Notes About Rate Set - Date, Origin, Etc FY29: 185.03; Insert Notes About Rate Set - Date, Origin, Etc FY30: 189.66; Insert Notes About Rate Set - Date, Origin, Etc FY31: 194.4; Insert Notes About Rate Set - Date, Origin, Etc FY32: 199.26; RESOURCE ID SUFFIX FY33: 204.24; RESOURCE ID SUFFIX FY34: 209.35; RESOURCE ID SUFFIX FY35: 214.58
FY19_637 | FSS Professional | Labor | FSS Professional | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 114.85; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 118.3624; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 121.0848; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 123.8697; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 126.7187; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 129.6332; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 132.6148; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 135.665; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 138.7852; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 141.9773; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 145.2428; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 145.2428; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 152.0008; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 155.4968; NEED TO ADD P6 SUFFIX FY33: 159.0732; NEED TO ADD P6 SUFFIX FY34: 162.7319; NEED TO ADD P6 SUFFIX FY35: 166.4748; Insert Notes About Rate Set - Date, Origin, Etc FY19: 170.02; Insert Notes About Rate Set - Date, Origin, Etc FY20: 174.27; Insert Notes About Rate Set - Date, Origin, Etc FY21: 178.63; Insert Notes About Rate Set - Date, Origin, Etc FY22: 183.1; Insert Notes About Rate Set - Date, Origin, Etc FY23: 187.68; Insert Notes About Rate Set - Date, Origin, Etc FY24: 192.37; Insert Notes About Rate Set - Date, Origin, Etc FY25: 197.18; Insert Notes About Rate Set - Date, Origin, Etc FY26: 202.11; Insert Notes About Rate Set - Date, Origin, Etc FY27: 207.16; Insert Notes About Rate Set - Date, Origin, Etc FY28: 212.34; Insert Notes About Rate Set - Date, Origin, Etc FY29: 217.65; Insert Notes About Rate Set - Date, Origin, Etc FY30: 223.09; Insert Notes About Rate Set - Date, Origin, Etc FY31: 228.67; Insert Notes About Rate Set - Date, Origin, Etc FY32: 234.39; RESOURCE ID SUFFIX FY33: 240.25; RESOURCE ID SUFFIX FY34: 246.26; RESOURCE ID SUFFIX FY35: 252.42
FY19_638 | FSS Technical | Labor | FSS Technical | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 83.5; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 85.7631; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 87.7356; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 89.7535; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 91.8179; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 93.9297; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 96.09; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 98.3001; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 100.561; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 102.8739; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 105.24; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 105.24; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 110.1367; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 112.6699; NEED TO ADD P6 SUFFIX FY33: 115.2613; NEED TO ADD P6 SUFFIX FY34: 117.9123; NEED TO ADD P6 SUFFIX FY35: 120.6243; Insert Notes About Rate Set - Date, Origin, Etc FY19: 123.8; Insert Notes About Rate Set - Date, Origin, Etc FY20: 126.9; Insert Notes About Rate Set - Date, Origin, Etc FY21: 130.07; Insert Notes About Rate Set - Date, Origin, Etc FY22: 133.32; Insert Notes About Rate Set - Date, Origin, Etc FY23: 136.65; Insert Notes About Rate Set - Date, Origin, Etc FY24: 140.07; Insert Notes About Rate Set - Date, Origin, Etc FY25: 143.57; Insert Notes About Rate Set - Date, Origin, Etc FY26: 147.16; Insert Notes About Rate Set - Date, Origin, Etc FY27: 150.84; Insert Notes About Rate Set - Date, Origin, Etc FY28: 154.61; Insert Notes About Rate Set - Date, Origin, Etc FY29: 158.48; Insert Notes About Rate Set - Date, Origin, Etc FY30: 162.44; Insert Notes About Rate Set - Date, Origin, Etc FY31: 166.5; Insert Notes About Rate Set - Date, Origin, Etc FY32: 170.66; RESOURCE ID SUFFIX FY33: 174.93; RESOURCE ID SUFFIX FY34: 179.3; RESOURCE ID SUFFIX FY35: 183.78
FY19_SINS | Insurance | Nonlabor | Insurance | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.0997; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.125; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.1509; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.1774; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.2044; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.2321; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.2605; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.2895; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.3191; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.3495; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.3495; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.4123; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.4447; NEED TO ADD P6 SUFFIX FY33: 1.478; NEED TO ADD P6 SUFFIX FY34: 1.512; NEED TO ADD P6 SUFFIX FY35: 1.5467; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.71; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.75; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.79; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.83; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.88; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.93; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.98; Insert Notes About Rate Set - Date, Origin, Etc FY26: 2.03; Insert Notes About Rate Set - Date, Origin, Etc FY27: 2.08; Insert Notes About Rate Set - Date, Origin, Etc FY28: 2.13; Insert Notes About Rate Set - Date, Origin, Etc FY29: 2.18; Insert Notes About Rate Set - Date, Origin, Etc FY30: 2.23; Insert Notes About Rate Set - Date, Origin, Etc FY31: 2.29; Insert Notes About Rate Set - Date, Origin, Etc FY32: 2.35; RESOURCE ID SUFFIX FY33: 2.41; RESOURCE ID SUFFIX FY34: 2.47; RESOURCE ID SUFFIX FY35: 2.53
FY19_SACCESS | Land Access Cost | Nonlabor | Land Access Cost | bar: Created by Jaclyn from P6 Rates on 2/14/19 FY19 to NEED TO ADD P6 SUFFIX FY35; Insert Notes About Rate Set - Date, Origin, Etc FY19 to RESOURCE ID SUFFIX FY35
FY19_300 | Materials & Supplies Low Value <$25K | Nonlabor | Materials & Supplies Low Value <$25K | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1.075; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.0997; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.125; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.1509; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.1774; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.2044; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.2321; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.2605; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.2895; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.3191; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.3495; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.3495; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.4123; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.4447; NEED TO ADD P6 SUFFIX FY33: 1.478; NEED TO ADD P6 SUFFIX FY34: 1.512; NEED TO ADD P6 SUFFIX FY35: 1.5467; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.71; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.75; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.79; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.83; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.88; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.93; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.98; Insert Notes About Rate Set - Date, Origin, Etc FY26: 2.03; Insert Notes About Rate Set - Date, Origin, Etc FY27: 2.08; Insert Notes About Rate Set - Date, Origin, Etc FY28: 2.13; Insert Notes About Rate Set - Date, Origin, Etc FY29: 2.18; Insert Notes About Rate Set - Date, Origin, Etc FY30: 2.23; Insert Notes About Rate Set - Date, Origin, Etc FY31: 2.29; Insert Notes About Rate Set - Date, Origin, Etc FY32: 2.35; RESOURCE ID SUFFIX FY33: 2.41; RESOURCE ID SUFFIX FY34: 2.47; RESOURCE ID SUFFIX FY35: 2.53
FY19_633 | Motor Vehicles | Nonlabor | Motor Vehicles | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.023; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.0465; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.0706; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.0952; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.1204; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.1462; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.1725; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.1995; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.2271; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.3137; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.344; NEED TO ADD P6 SUFFIX FY33: 1.3749; NEED TO ADD P6 SUFFIX FY34: 1.4065; NEED TO ADD P6 SUFFIX FY35: 1.4388; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.5; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.54; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.58; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.62; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.66; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.7; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.74; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.78; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.82; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.87; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.92; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.97; Insert Notes About Rate Set - Date, Origin, Etc FY31: 2.02; Insert Notes About Rate Set - Date, Origin, Etc FY32: 2.07; RESOURCE ID SUFFIX FY33: 2.12; RESOURCE ID SUFFIX FY34: 2.17; RESOURCE ID SUFFIX FY35: 2.22
FY19_NYSDEC | NYSDEC Oversight Grant | Nonlabor | NYSDEC Oversight Grant | bar: Created by Jaclyn from P6 Rates on 2/14/19 FY19 to NEED TO ADD P6 SUFFIX FY35; Insert Notes About Rate Set - Date, Origin, Etc FY19 to RESOURCE ID SUFFIX FY35
FY19_1_26_1 | Other Electric | Nonlabor | Other Electric | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.023; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.0465; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.0706; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.0952; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.1204; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.1462; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.1725; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.1995; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.2271; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.3137; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.344; NEED TO ADD P6 SUFFIX FY33: 1.3749; NEED TO ADD P6 SUFFIX FY34: 1.4065; NEED TO ADD P6 SUFFIX FY35: 1.4388; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.12; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.15; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.18; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.21; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.24; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.27; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.3; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.33; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.36; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.39; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.42; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.46; Insert Notes About Rate Set - Date, Origin, Etc FY31: 1.5; Insert Notes About Rate Set - Date, Origin, Etc FY32: 1.54; RESOURCE ID SUFFIX FY33: 1.58; RESOURCE ID SUFFIX FY34: 1.62; RESOURCE ID SUFFIX FY35: 1.66
FY19_480 | Other Space Charge Recharge | Nonlabor | Other Space Charge Recharge | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.023; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.0465; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.0706; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.0952; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.1204; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.1462; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.1725; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.1995; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.2271; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.3137; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.344; NEED TO ADD P6 SUFFIX FY33: 1.3749; NEED TO ADD P6 SUFFIX FY34: 1.4065; NEED TO ADD P6 SUFFIX FY35: 1.4388; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.6; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.64; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.68; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.72; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.76; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.8; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.85; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.9; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.95; Insert Notes About Rate Set - Date, Origin, Etc FY28: 2; Insert Notes About Rate Set - Date, Origin, Etc FY29: 2.05; Insert Notes About Rate Set - Date, Origin, Etc FY30: 2.1; Insert Notes About Rate Set - Date, Origin, Etc FY31: 2.15; Insert Notes About Rate Set - Date, Origin, Etc FY32: 2.2; RESOURCE ID SUFFIX FY33: 2.26; RESOURCE ID SUFFIX FY34: 2.32; RESOURCE ID SUFFIX FY35: 2.38
FY19_604 | PE Professional | Labor | PE Professional | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 147.58; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 146.6396; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 150.0124; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 153.4626; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 156.9923; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 160.6031; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 164.297; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 168.0758; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 171.9415; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 175.8962; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 179.9418; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 179.9418; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 188.3143; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 192.6456; NEED TO ADD P6 SUFFIX FY33: 197.0764; NEED TO ADD P6 SUFFIX FY34: 201.6092; NEED TO ADD P6 SUFFIX FY35: 206.2462; Insert Notes About Rate Set - Date, Origin, Etc FY19: 209.87; Insert Notes About Rate Set - Date, Origin, Etc FY20: 215.12; Insert Notes About Rate Set - Date, Origin, Etc FY21: 220.5; Insert Notes About Rate Set - Date, Origin, Etc FY22: 226.01; Insert Notes About Rate Set - Date, Origin, Etc FY23: 231.66; Insert Notes About Rate Set - Date, Origin, Etc FY24: 237.45; Insert Notes About Rate Set - Date, Origin, Etc FY25: 243.39; Insert Notes About Rate Set - Date, Origin, Etc FY26: 249.47; Insert Notes About Rate Set - Date, Origin, Etc FY27: 255.71; Insert Notes About Rate Set - Date, Origin, Etc FY28: 262.1; Insert Notes About Rate Set - Date, Origin, Etc FY29: 268.65; Insert Notes About Rate Set - Date, Origin, Etc FY30: 275.37; Insert Notes About Rate Set - Date, Origin, Etc FY31: 282.25; Insert Notes About Rate Set - Date, Origin, Etc FY32: 289.31; RESOURCE ID SUFFIX FY33: 296.54; RESOURCE ID SUFFIX FY34: 303.95; RESOURCE ID SUFFIX FY35: 311.55
FY19_600 | PE Trades | Labor | PE Trades | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 115.19; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 118.7706; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 121.5023; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 124.2969; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 127.1557; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 130.0803; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 133.0721; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 136.1328; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 139.2638; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 142.4669; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 145.7436; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 145.7436; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 152.5249; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 156.033; NEED TO ADD P6 SUFFIX FY33: 159.6218; NEED TO ADD P6 SUFFIX FY34: 163.2931; NEED TO ADD P6 SUFFIX FY35: 167.0488; Insert Notes About Rate Set - Date, Origin, Etc FY19: 170.01; Insert Notes About Rate Set - Date, Origin, Etc FY20: 174.26; Insert Notes About Rate Set - Date, Origin, Etc FY21: 178.62; Insert Notes About Rate Set - Date, Origin, Etc FY22: 183.09; Insert Notes About Rate Set - Date, Origin, Etc FY23: 187.67; Insert Notes About Rate Set - Date, Origin, Etc FY24: 192.36; Insert Notes About Rate Set - Date, Origin, Etc FY25: 197.17; Insert Notes About Rate Set - Date, Origin, Etc FY26: 202.1; Insert Notes About Rate Set - Date, Origin, Etc FY27: 207.15; Insert Notes About Rate Set - Date, Origin, Etc FY28: 212.33; Insert Notes About Rate Set - Date, Origin, Etc FY29: 217.64; Insert Notes About Rate Set - Date, Origin, Etc FY30: 223.08; Insert Notes About Rate Set - Date, Origin, Etc FY31: 228.66; Insert Notes About Rate Set - Date, Origin, Etc FY32: 234.38; RESOURCE ID SUFFIX FY33: 240.24; RESOURCE ID SUFFIX FY34: 246.25; RESOURCE ID SUFFIX FY35: 252.41
FY19_20867 | PROF2, LTS FIELD ENGR | Labor | PROF2, LTS FIELD ENGR | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 79.3582; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 81.8035; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 84.3394; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 86.9539; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 89.6495; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 92.4286; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 95.2939; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 98.248; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 101.2937; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 104.4338; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 107.6713; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 107.6713; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 114.4504; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 117.9983; NEED TO ADD P6 SUFFIX FY33: 121.6563; NEED TO ADD P6 SUFFIX FY34: 125.4276; NEED TO ADD P6 SUFFIX FY35: 129.3159; Insert Notes About Rate Set - Date, Origin, Etc FY19: 120.34; Insert Notes About Rate Set - Date, Origin, Etc FY20: 125.55; Insert Notes About Rate Set - Date, Origin, Etc FY21: 130.16; Insert Notes About Rate Set - Date, Origin, Etc FY22: 135.37; Insert Notes About Rate Set - Date, Origin, Etc FY23: 140.78; Insert Notes About Rate Set - Date, Origin, Etc FY24: 146.41; Insert Notes About Rate Set - Date, Origin, Etc FY25: 152.27; Insert Notes About Rate Set - Date, Origin, Etc FY26: 158.36; Insert Notes About Rate Set - Date, Origin, Etc FY27: 164.69; Insert Notes About Rate Set - Date, Origin, Etc FY28: 171.28; Insert Notes About Rate Set - Date, Origin, Etc FY29: 178.13; Insert Notes About Rate Set - Date, Origin, Etc FY30: 185.26; Insert Notes About Rate Set - Date, Origin, Etc FY31: 192.67; Insert Notes About Rate Set - Date, Origin, Etc FY32: 200.38; RESOURCE ID SUFFIX FY33: 208.4; RESOURCE ID SUFFIX FY34: 216.74; RESOURCE ID SUFFIX FY35: 225.41
FY19_20222 | PROF5 EPD MGR | Labor | PROF5 EPD MGR | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 138.1072; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 138.9827; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 143.2912; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 147.7332; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 152.313; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 157.0347; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 161.9027; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 166.9217; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 172.0963; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 177.4313; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 182.9316; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 182.9316; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 194.4492; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 200.4771; NEED TO ADD P6 SUFFIX FY33: 206.6919; NEED TO ADD P6 SUFFIX FY34: 213.0994; NEED TO ADD P6 SUFFIX FY35: 219.7055; Insert Notes About Rate Set - Date, Origin, Etc FY19: 202.77; Insert Notes About Rate Set - Date, Origin, Etc FY20: 210.88; Insert Notes About Rate Set - Date, Origin, Etc FY21: 219.32; Insert Notes About Rate Set - Date, Origin, Etc FY22: 228.09; Insert Notes About Rate Set - Date, Origin, Etc FY23: 237.21; Insert Notes About Rate Set - Date, Origin, Etc FY24: 246.7; Insert Notes About Rate Set - Date, Origin, Etc FY25: 256.57; Insert Notes About Rate Set - Date, Origin, Etc FY26: 266.83; Insert Notes About Rate Set - Date, Origin, Etc FY27: 277.5; Insert Notes About Rate Set - Date, Origin, Etc FY28: 288.6; Insert Notes About Rate Set - Date, Origin, Etc FY29: 300.14; Insert Notes About Rate Set - Date, Origin, Etc FY30: 312.15; Insert Notes About Rate Set - Date, Origin, Etc FY31: 324.64; Insert Notes About Rate Set - Date, Origin, Etc FY32: 337.63; RESOURCE ID SUFFIX FY33: 351.14; RESOURCE ID SUFFIX FY34: 365.19; RESOURCE ID SUFFIX FY35: 379.8
FY19_21478 | Project Manager - PROF4 , LTS PM | Labor | Project Manager - PROF4 , LTS PM | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 116.6111; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 118.2962; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 121.9633; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 125.7442; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 129.6423; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 133.6612; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 137.8047; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 142.0766; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 146.481; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 151.0219; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 155.7036; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 155.7036; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 165.5068; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 170.6376; NEED TO ADD P6 SUFFIX FY33: 175.9273; NEED TO ADD P6 SUFFIX FY34: 181.3811; NEED TO ADD P6 SUFFIX FY35: 187.0039; Insert Notes About Rate Set - Date, Origin, Etc FY19: 173.72; Insert Notes About Rate Set - Date, Origin, Etc FY20: 180.67; Insert Notes About Rate Set - Date, Origin, Etc FY21: 187.9; Insert Notes About Rate Set - Date, Origin, Etc FY22: 195.42; Insert Notes About Rate Set - Date, Origin, Etc FY23: 203.24; Insert Notes About Rate Set - Date, Origin, Etc FY24: 211.37; Insert Notes About Rate Set - Date, Origin, Etc FY25: 219.82; Insert Notes About Rate Set - Date, Origin, Etc FY26: 228.61; Insert Notes About Rate Set - Date, Origin, Etc FY27: 237.75; Insert Notes About Rate Set - Date, Origin, Etc FY28: 247.26; Insert Notes About Rate Set - Date, Origin, Etc FY29: 257.15; Insert Notes About Rate Set - Date, Origin, Etc FY30: 267.44; Insert Notes About Rate Set - Date, Origin, Etc FY31: 278.14; Insert Notes About Rate Set - Date, Origin, Etc FY32: 289.27; RESOURCE ID SUFFIX FY33: 300.84; RESOURCE ID SUFFIX FY34: 312.87; RESOURCE ID SUFFIX FY35: 325.38
FY19_19515 | Project Manager, PROF4, LTS PM | Labor | Project Manager, PROF4, LTS PM | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 116.6111; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 118.2962; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 121.9633; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 125.7442; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 129.6423; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 133.6612; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 137.8047; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 142.0766; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 146.481; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 151.0219; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 155.7036; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 155.7036; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 165.5068; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 170.6376; NEED TO ADD P6 SUFFIX FY33: 175.9273; NEED TO ADD P6 SUFFIX FY34: 181.3811; NEED TO ADD P6 SUFFIX FY35: 187.0039; Insert Notes About Rate Set - Date, Origin, Etc FY19: 173.72; Insert Notes About Rate Set - Date, Origin, Etc FY20: 180.67; Insert Notes About Rate Set - Date, Origin, Etc FY21: 187.9; Insert Notes About Rate Set - Date, Origin, Etc FY22: 195.42; Insert Notes About Rate Set - Date, Origin, Etc FY23: 203.24; Insert Notes About Rate Set - Date, Origin, Etc FY24: 211.37; Insert Notes About Rate Set - Date, Origin, Etc FY25: 219.82; Insert Notes About Rate Set - Date, Origin, Etc FY26: 228.61; Insert Notes About Rate Set - Date, Origin, Etc FY27: 237.75; Insert Notes About Rate Set - Date, Origin, Etc FY28: 247.26; Insert Notes About Rate Set - Date, Origin, Etc FY29: 257.15; Insert Notes About Rate Set - Date, Origin, Etc FY30: 267.44; Insert Notes About Rate Set - Date, Origin, Etc FY31: 278.14; Insert Notes About Rate Set - Date, Origin, Etc FY32: 289.27; RESOURCE ID SUFFIX FY33: 300.84; RESOURCE ID SUFFIX FY34: 312.87; RESOURCE ID SUFFIX FY35: 325.38
FY19_TECH3 | Sampling Team Lead | Labor | Sampling Team Lead | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 89.672; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 92.4518; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 95.3178; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 98.2727; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 101.3191; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 104.46; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 107.6983; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 111.0369; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 114.4791; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 118.0279; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 121.6868; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 121.6868; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 129.3483; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 133.3581; NEED TO ADD P6 SUFFIX FY33: 137.4922; NEED TO ADD P6 SUFFIX FY34: 141.7545; NEED TO ADD P6 SUFFIX FY35: 146.1488; Insert Notes About Rate Set - Date, Origin, Etc FY19: 89.672; Insert Notes About Rate Set - Date, Origin, Etc FY20: 92.4518; Insert Notes About Rate Set - Date, Origin, Etc FY21: 95.3178; Insert Notes About Rate Set - Date, Origin, Etc FY22: 98.2727; Insert Notes About Rate Set - Date, Origin, Etc FY23: 101.3191; Insert Notes About Rate Set - Date, Origin, Etc FY24: 104.46; Insert Notes About Rate Set - Date, Origin, Etc FY25: 107.6983; Insert Notes About Rate Set - Date, Origin, Etc FY26: 111.0369; Insert Notes About Rate Set - Date, Origin, Etc FY27: 114.4791; Insert Notes About Rate Set - Date, Origin, Etc FY28: 118.0279; Insert Notes About Rate Set - Date, Origin, Etc FY29: 121.6868; Insert Notes About Rate Set - Date, Origin, Etc FY30: 121.6868; Insert Notes About Rate Set - Date, Origin, Etc FY31: 129.3483; Insert Notes About Rate Set - Date, Origin, Etc FY32: 133.3581; RESOURCE ID SUFFIX FY33: 137.4922; RESOURCE ID SUFFIX FY34: 141.7545; RESOURCE ID SUFFIX FY35: 146.1488
FY19_23718 | Sr. Applications Engineer PROF3, LTS Programmer | Labor | Sr. Applications Engineer PROF3, LTS Programmer | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 100.176; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 101.9355; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 105.0955; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 108.3534; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 111.7124; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 115.1755; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 118.7459; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 122.427; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 126.2223; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 130.1352; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 134.1693; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 134.1693; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 142.6168; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 147.0379; NEED TO ADD P6 SUFFIX FY33: 151.5961; NEED TO ADD P6 SUFFIX FY34: 156.2955; NEED TO ADD P6 SUFFIX FY35: 161.1407; Insert Notes About Rate Set - Date, Origin, Etc FY19: 149.73; Insert Notes About Rate Set - Date, Origin, Etc FY20: 155.72; Insert Notes About Rate Set - Date, Origin, Etc FY21: 161.95; Insert Notes About Rate Set - Date, Origin, Etc FY22: 168.43; Insert Notes About Rate Set - Date, Origin, Etc FY23: 175.17; Insert Notes About Rate Set - Date, Origin, Etc FY24: 182.18; Insert Notes About Rate Set - Date, Origin, Etc FY25: 189.47; Insert Notes About Rate Set - Date, Origin, Etc FY26: 197.05; Insert Notes About Rate Set - Date, Origin, Etc FY27: 204.93; Insert Notes About Rate Set - Date, Origin, Etc FY28: 213.13; Insert Notes About Rate Set - Date, Origin, Etc FY29: 221.66; Insert Notes About Rate Set - Date, Origin, Etc FY30: 230.53; Insert Notes About Rate Set - Date, Origin, Etc FY31: 239.75; Insert Notes About Rate Set - Date, Origin, Etc FY32: 249.34; RESOURCE ID SUFFIX FY33: 259.31; RESOURCE ID SUFFIX FY34: 269.68; RESOURCE ID SUFFIX FY35: 280.47
FY19_1_26 | Subcontract - Over 25K Under 2M | Nonlabor | Subcontract - Over 25K Under 2M | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1.075; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.0997; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.125; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.1509; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.1774; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.2044; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.2321; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.2605; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.2895; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.3191; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.3495; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.3495; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.4123; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.4447; NEED TO ADD P6 SUFFIX FY33: 1.478; NEED TO ADD P6 SUFFIX FY34: 1.512; NEED TO ADD P6 SUFFIX FY35: 1.5467; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.31; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.34; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.37; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.4; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.44; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.48; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.52; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.56; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.6; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.64; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.68; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.72; Insert Notes About Rate Set - Date, Origin, Etc FY31: 1.76; Insert Notes About Rate Set - Date, Origin, Etc FY32: 1.8; RESOURCE ID SUFFIX FY33: 1.85; RESOURCE ID SUFFIX FY34: 1.9; RESOURCE ID SUFFIX FY35: 1.95
FY19_1_26_2 | Telephone Charges | Nonlabor | Telephone Charges | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.023; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.0465; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.0706; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.0952; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.1204; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.1462; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.1725; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.1995; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.2271; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.3137; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.344; NEED TO ADD P6 SUFFIX FY33: 1.3749; NEED TO ADD P6 SUFFIX FY34: 1.4065; NEED TO ADD P6 SUFFIX FY35: 1.4388; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1.6; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.64; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.68; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.72; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.76; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.8; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.85; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.9; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.95; Insert Notes About Rate Set - Date, Origin, Etc FY28: 2; Insert Notes About Rate Set - Date, Origin, Etc FY29: 2.05; Insert Notes About Rate Set - Date, Origin, Etc FY30: 2.1; Insert Notes About Rate Set - Date, Origin, Etc FY31: 2.15; Insert Notes About Rate Set - Date, Origin, Etc FY32: 2.2; RESOURCE ID SUFFIX FY33: 2.26; RESOURCE ID SUFFIX FY34: 2.32; RESOURCE ID SUFFIX FY35: 2.38
FY19_507 | Waste Management Allocation | Nonlabor | Waste Management Allocation | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 1; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 1.023; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 1.0465; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 1.0706; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 1.0952; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 1.1204; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 1.1462; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 1.1725; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 1.1995; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 1.2271; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 1.2553; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 1.3137; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 1.344; NEED TO ADD P6 SUFFIX FY33: 1.3749; NEED TO ADD P6 SUFFIX FY34: 1.4065; NEED TO ADD P6 SUFFIX FY35: 1.4388; Insert Notes About Rate Set - Date, Origin, Etc FY19: 1; Insert Notes About Rate Set - Date, Origin, Etc FY20: 1.023; Insert Notes About Rate Set - Date, Origin, Etc FY21: 1.0465; Insert Notes About Rate Set - Date, Origin, Etc FY22: 1.0706; Insert Notes About Rate Set - Date, Origin, Etc FY23: 1.0952; Insert Notes About Rate Set - Date, Origin, Etc FY24: 1.1204; Insert Notes About Rate Set - Date, Origin, Etc FY25: 1.1462; Insert Notes About Rate Set - Date, Origin, Etc FY26: 1.1725; Insert Notes About Rate Set - Date, Origin, Etc FY27: 1.1995; Insert Notes About Rate Set - Date, Origin, Etc FY28: 1.2271; Insert Notes About Rate Set - Date, Origin, Etc FY29: 1.2553; Insert Notes About Rate Set - Date, Origin, Etc FY30: 1.2553; Insert Notes About Rate Set - Date, Origin, Etc FY31: 1.3137; Insert Notes About Rate Set - Date, Origin, Etc FY32: 1.344; RESOURCE ID SUFFIX FY33: 1.3749; RESOURCE ID SUFFIX FY34: 1.4065; RESOURCE ID SUFFIX FY35: 1.4388
FY19_652 | WMD Professional | Labor | WMD Professional | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 125.9; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 131.465; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 134.4887; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 137.5819; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 140.7463; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 143.9835; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 147.2951; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 150.6829; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 154.1486; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 157.694; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 161.3209; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 161.3209; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 168.827; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 172.7101; NEED TO ADD P6 SUFFIX FY33: 176.6824; NEED TO ADD P6 SUFFIX FY34: 180.7461; NEED TO ADD P6 SUFFIX FY35: 184.9033; Insert Notes About Rate Set - Date, Origin, Etc FY19: 180.95; Insert Notes About Rate Set - Date, Origin, Etc FY20: 185.47; Insert Notes About Rate Set - Date, Origin, Etc FY21: 190.11; Insert Notes About Rate Set - Date, Origin, Etc FY22: 194.86; Insert Notes About Rate Set - Date, Origin, Etc FY23: 199.73; Insert Notes About Rate Set - Date, Origin, Etc FY24: 204.72; Insert Notes About Rate Set - Date, Origin, Etc FY25: 209.84; Insert Notes About Rate Set - Date, Origin, Etc FY26: 215.09; Insert Notes About Rate Set - Date, Origin, Etc FY27: 220.47; Insert Notes About Rate Set - Date, Origin, Etc FY28: 225.98; Insert Notes About Rate Set - Date, Origin, Etc FY29: 231.63; Insert Notes About Rate Set - Date, Origin, Etc FY30: 237.42; Insert Notes About Rate Set - Date, Origin, Etc FY31: 243.36; Insert Notes About Rate Set - Date, Origin, Etc FY32: 249.44; RESOURCE ID SUFFIX FY33: 255.68; RESOURCE ID SUFFIX FY34: 262.07; RESOURCE ID SUFFIX FY35: 268.62
FY19_653 | WMD Technical | Labor | WMD Technical | Created by Jaclyn from P6 Rates on 2/14/19 FY19: 87.35; Created by Jaclyn from P6 Rates on 2/14/19 FY20: 91.0585; Created by Jaclyn from P6 Rates on 2/14/19 FY21: 93.1528; Created by Jaclyn from P6 Rates on 2/14/19 FY22: 95.2953; Created by Jaclyn from P6 Rates on 2/14/19 FY23: 97.4871; Created by Jaclyn from P6 Rates on 2/14/19 FY24: 99.7293; Created by Jaclyn from P6 Rates on 2/14/19 FY25: 102.0231; Created by Jaclyn from P6 Rates on 2/14/19 FY26: 104.3697; Created by Jaclyn from P6 Rates on 2/14/19 FY27: 106.7702; Created by Jaclyn from P6 Rates on 2/14/19 FY28: 109.2259; Created by Jaclyn from P6 Rates on 2/14/19 FY29: 111.7381; Created by Jaclyn from P6 Rates on 2/14/19 FY30: 111.7381; Created by Jaclyn from P6 Rates on 2/14/19 FY31: 116.9371; Created by Jaclyn from P6 Rates on 2/14/19 FY32: 119.6267; NEED TO ADD P6 SUFFIX FY33: 122.3781; NEED TO ADD P6 SUFFIX FY34: 125.1928; NEED TO ADD P6 SUFFIX FY35: 128.0722; Insert Notes About Rate Set - Date, Origin, Etc FY19: 130.45; Insert Notes About Rate Set - Date, Origin, Etc FY20: 133.71; Insert Notes About Rate Set - Date, Origin, Etc FY21: 137.05; Insert Notes About Rate Set - Date, Origin, Etc FY22: 140.48; Insert Notes About Rate Set - Date, Origin, Etc FY23: 143.99; Insert Notes About Rate Set - Date, Origin, Etc FY24: 147.59; Insert Notes About Rate Set - Date, Origin, Etc FY25: 151.28; Insert Notes About Rate Set - Date, Origin, Etc FY26: 155.06; Insert Notes About Rate Set - Date, Origin, Etc FY27: 158.94; Insert Notes About Rate Set - Date, Origin, Etc FY28: 162.91; Insert Notes About Rate Set - Date, Origin, Etc FY29: 166.98; Insert Notes About Rate Set - Date, Origin, Etc FY30: 171.15; Insert Notes About Rate Set - Date, Origin, Etc FY31: 175.43; Insert Notes About Rate Set - Date, Origin, Etc FY32: 179.82; RESOURCE ID SUFFIX FY33: 184.32; RESOURCE ID SUFFIX FY34: 188.93; RESOURCE ID SUFFIX FY35: 193.65

## Resource Structure 4 (hidden)
RESOURCE STRUCTURE: | NEXO |  |  | NEXO_RATE1 | [16 empty] | NEXO
Resource ID | Description | Resource Type | Combined Name | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35
(ASIC Designer #1) |  | Labor |  | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
Marcin |  | Labor |  | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
MGMT1 | MGMT1 - TBD | Labor | MGMT1 - TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
Non Labor | Non Labor | Nonlabor | Non Labor | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
PMC | Project Controls Recharge | Labor | Project Controls Recharge | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
PROF1 EE | PROF1 EE- TBD | Labor | PROF1 EE- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
PROF1 ME | PROF1 ME- TBD | Labor | PROF1 ME- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
PROF2 EE | PROF2 EE- TBD | Labor | PROF2 EE- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
PROF2 ME | PROF2 ME- TBD | Labor | PROF2 ME- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
PROF4 EE | PROF4 EE- TBD | Labor | PROF4 EE- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
SCI1 | (New Resource) | Labor | (New Resource) | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
SCI2 | SCI2- TBD | Labor | SCI2- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
SCI3 | SCI3- TBD | Labor | SCI3- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
SCI4 | SCI4- TBD | Labor | SCI4- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
SCI5 | SCI5- TBD | Labor | SCI5- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
Student/EE | (New Resource) | Labor | (New Resource) | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
TECH1 | TECH1- TBD | Labor | TECH1- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
TECH2 | TECH2- TBD | Labor | TECH2- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
TECH3 | TECH3- TBD | Labor | TECH3- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10
TECH4 | TECH4- TBD | Labor | TECH4- TBD | NEXO_RATE1 FY16: 10; NEXO_RATE1 FY17: 10; NEXO_RATE1 FY18: 10; NEXO_RATE1 FY19: 10; NEXO_RATE1 FY20: 10; NEXO_RATE1 FY21: 10; NEXO_RATE1 FY22: 10; NEXO_RATE1 FY23: 10; NEXO_RATE1 FY24: 10; NEXO_RATE1 FY25: 10; NEXO_RATE1 FY26: 10; NEXO_RATE1 FY27: 10; NEXO_RATE1 FY28: 10; NEXO_RATE1 FY29: 10; NEXO_RATE1 FY30: 10; NEXO_RATE1 FY31: 10; NEXO_RATE1 FY32: 10; NEXO FY33: 10; NEXO FY34: 10; NEXO FY35: 10

## Resource Structure 5 (hidden)
RESOURCE STRUCTURE: | EIC |  |  | EIC FY20 LDRD | [16 empty] | FY20_EIC |  |  | EIC FY20 | [16 empty] | FY20_EICnoLDRD
Resource ID | Description | Resource Type | Combined Name | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35
TRAVEL_FY20_EIC | Travel_NonLabor | Nonlabor | TRAVEL_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.2437; EIC FY20 LDRD FY20: 1.2723; EIC FY20 LDRD FY21: 1.3173; EIC FY20 LDRD FY22: 1.3418; EIC FY20 LDRD FY23: 1.3727; EIC FY20 LDRD FY24: 1.4042; EIC FY20 LDRD FY25: 1.4365; EIC FY20 LDRD FY26: 1.4696; EIC FY20 LDRD FY27: 1.5034; EIC FY20 LDRD FY28: 1.538; EIC FY20 LDRD FY29: 1.5733; EIC FY20 LDRD FY30: 1.6095; EIC FY20 LDRD FY31: 1.6465; EIC FY20 LDRD FY32: 1.6844; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1.2122; EIC FY20 FY20: 1.24; EIC FY20 FY21: 1.2839; EIC FY20 FY22: 1.3078; EIC FY20 FY23: 1.3379; EIC FY20 FY24: 1.3687; EIC FY20 FY25: 1.4001; EIC FY20 FY26: 1.4323; EIC FY20 FY27: 1.4653; EIC FY20 FY28: 1.499; EIC FY20 FY29: 1.5335; EIC FY20 FY30: 1.5687; EIC FY20 FY31: 1.6048; EIC FY20 FY32: 1.6417
Purch_Const_FY20_EIC | Purchases_Construction Contract_NonLabor | Nonlabor | Purch_Const_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 0.99612; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.0568; EIC FY20 LDRD FY22: 1.0885; EIC FY20 LDRD FY23: 1.1211; EIC FY20 LDRD FY24: 1.1548; EIC FY20 LDRD FY25: 1.1894; EIC FY20 LDRD FY26: 1.2251; EIC FY20 LDRD FY27: 1.2619; EIC FY20 LDRD FY28: 1.2997; EIC FY20 LDRD FY29: 1.3387; EIC FY20 LDRD FY30: 1.3789; EIC FY20 LDRD FY31: 1.4202; EIC FY20 LDRD FY32: 1.4628; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.97087; EIC FY20 FY20: 1; EIC FY20 FY21: 1.03; EIC FY20 FY22: 1.0609; EIC FY20 FY23: 1.0927; EIC FY20 FY24: 1.1255; EIC FY20 FY25: 1.1593; EIC FY20 FY26: 1.1941; EIC FY20 FY27: 1.2299; EIC FY20 FY28: 1.2668; EIC FY20 FY29: 1.3048; EIC FY20 FY30: 1.3439; EIC FY20 FY31: 1.3842; EIC FY20 FY32: 1.4258
Purch<$2M_FY20_EIC | Purchases<$2M_NonLabor | Nonlabor | Purch<$2M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.0029; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.0496; EIC FY20 LDRD FY22: 1.0737; EIC FY20 LDRD FY23: 1.0984; EIC FY20 LDRD FY24: 1.1237; EIC FY20 LDRD FY25: 1.1495; EIC FY20 LDRD FY26: 1.176; EIC FY20 LDRD FY27: 1.203; EIC FY20 LDRD FY28: 1.2307; EIC FY20 LDRD FY29: 1.259; EIC FY20 LDRD FY30: 1.288; EIC FY20 LDRD FY31: 1.3176; EIC FY20 LDRD FY32: 1.3479; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.97752; EIC FY20 FY20: 1; EIC FY20 FY21: 1.023; EIC FY20 FY22: 1.0465; EIC FY20 FY23: 1.0706; EIC FY20 FY24: 1.0952; EIC FY20 FY25: 1.1204; EIC FY20 FY26: 1.1462; EIC FY20 FY27: 1.1725; EIC FY20 FY28: 1.1995; EIC FY20 FY29: 1.2271; EIC FY20 FY30: 1.2553; EIC FY20 FY31: 1.2842; EIC FY20 FY32: 1.3137
Purch>$2M_FY20_EIC | Purchases>$2M (Portion Over)_NonLabor | Nonlabor | Purch>$2M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.0029; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.0496; EIC FY20 LDRD FY22: 1.0737; EIC FY20 LDRD FY23: 1.0984; EIC FY20 LDRD FY24: 1.1237; EIC FY20 LDRD FY25: 1.1495; EIC FY20 LDRD FY26: 1.176; EIC FY20 LDRD FY27: 1.203; EIC FY20 LDRD FY28: 1.2307; EIC FY20 LDRD FY29: 1.259; EIC FY20 LDRD FY30: 1.288; EIC FY20 LDRD FY31: 1.3176; EIC FY20 LDRD FY32: 1.3479; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.97752; EIC FY20 FY20: 1; EIC FY20 FY21: 1.023; EIC FY20 FY22: 1.0465; EIC FY20 FY23: 1.0706; EIC FY20 FY24: 1.0952; EIC FY20 FY25: 1.1204; EIC FY20 FY26: 1.1462; EIC FY20 FY27: 1.1725; EIC FY20 FY28: 1.1995; EIC FY20 FY29: 1.2271; EIC FY20 FY30: 1.2553; EIC FY20 FY31: 1.2842; EIC FY20 FY32: 1.3137
SPACE_FY20_EIC | Space_NonLabor | Nonlabor | SPACE_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.2437; EIC FY20 LDRD FY20: 1.2723; EIC FY20 LDRD FY21: 1.3173; EIC FY20 LDRD FY22: 1.3418; EIC FY20 LDRD FY23: 1.3727; EIC FY20 LDRD FY24: 1.4042; EIC FY20 LDRD FY25: 1.4365; EIC FY20 LDRD FY26: 1.4696; EIC FY20 LDRD FY27: 1.5034; EIC FY20 LDRD FY28: 1.538; EIC FY20 LDRD FY29: 1.5733; EIC FY20 LDRD FY30: 1.6095; EIC FY20 LDRD FY31: 1.6465; EIC FY20 LDRD FY32: 1.6844; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1.2122; EIC FY20 FY20: 1.24; EIC FY20 FY21: 1.2839; EIC FY20 FY22: 1.3078; EIC FY20 FY23: 1.3379; EIC FY20 FY24: 1.3687; EIC FY20 FY25: 1.4001; EIC FY20 FY26: 1.4323; EIC FY20 FY27: 1.4653; EIC FY20 FY28: 1.499; EIC FY20 FY29: 1.5335; EIC FY20 FY30: 1.5687; EIC FY20 FY31: 1.6048; EIC FY20 FY32: 1.6417
ELECT_FY20_EIC | Electric_NonLabor | Nonlabor | ELECT_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.0029; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.0496; EIC FY20 LDRD FY22: 1.0737; EIC FY20 LDRD FY23: 1.0984; EIC FY20 LDRD FY24: 1.1237; EIC FY20 LDRD FY25: 1.1495; EIC FY20 LDRD FY26: 1.176; EIC FY20 LDRD FY27: 1.203; EIC FY20 LDRD FY28: 1.2307; EIC FY20 LDRD FY29: 1.259; EIC FY20 LDRD FY30: 1.288; EIC FY20 LDRD FY31: 1.3176; EIC FY20 LDRD FY32: 1.3479; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.97752; EIC FY20 FY20: 1; EIC FY20 FY21: 1.023; EIC FY20 FY22: 1.0465; EIC FY20 FY23: 1.0706; EIC FY20 FY24: 1.0952; EIC FY20 FY25: 1.1204; EIC FY20 FY26: 1.1462; EIC FY20 FY27: 1.1725; EIC FY20 FY28: 1.1995; EIC FY20 FY29: 1.2271; EIC FY20 FY30: 1.2553; EIC FY20 FY31: 1.2842; EIC FY20 FY32: 1.3137
ELECTne_FY20_EIC | Electric_No Escalation_NonLabor | Nonlabor | ELECTne_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.026; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.026; EIC FY20 LDRD FY22: 1.026; EIC FY20 LDRD FY23: 1.026; EIC FY20 LDRD FY24: 1.026; EIC FY20 LDRD FY25: 1.026; EIC FY20 LDRD FY26: 1.026; EIC FY20 LDRD FY27: 1.026; EIC FY20 LDRD FY28: 1.026; EIC FY20 LDRD FY29: 1.026; EIC FY20 LDRD FY30: 1.026; EIC FY20 LDRD FY31: 1.026; EIC FY20 LDRD FY32: 1.026; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1; EIC FY20 FY20: 1; EIC FY20 FY21: 1; EIC FY20 FY22: 1; EIC FY20 FY23: 1; EIC FY20 FY24: 1; EIC FY20 FY25: 1; EIC FY20 FY26: 1; EIC FY20 FY27: 1; EIC FY20 FY28: 1; EIC FY20 FY29: 1; EIC FY20 FY30: 1; EIC FY20 FY31: 1; EIC FY20 FY32: 1
MISC01_FY20_EIC | TLD Badges, Vehicles_NonLabor | Nonlabor | MISC01_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.2437; EIC FY20 LDRD FY20: 1.2723; EIC FY20 LDRD FY21: 1.3173; EIC FY20 LDRD FY22: 1.3418; EIC FY20 LDRD FY23: 1.3727; EIC FY20 LDRD FY24: 1.4042; EIC FY20 LDRD FY25: 1.4365; EIC FY20 LDRD FY26: 1.4696; EIC FY20 LDRD FY27: 1.5034; EIC FY20 LDRD FY28: 1.538; EIC FY20 LDRD FY29: 1.5733; EIC FY20 LDRD FY30: 1.6095; EIC FY20 LDRD FY31: 1.6465; EIC FY20 LDRD FY32: 1.6844; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1.2122; EIC FY20 FY20: 1.24; EIC FY20 FY21: 1.2839; EIC FY20 FY22: 1.3078; EIC FY20 FY23: 1.3379; EIC FY20 FY24: 1.3687; EIC FY20 FY25: 1.4001; EIC FY20 FY26: 1.4323; EIC FY20 FY27: 1.4653; EIC FY20 FY28: 1.499; EIC FY20 FY29: 1.5335; EIC FY20 FY30: 1.5687; EIC FY20 FY31: 1.6048; EIC FY20 FY32: 1.6417
SCIENT_L_FY20_EIC | Scientist_Low | Labor | SCIENT_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 117.3851; EIC FY20 LDRD FY20: 121.4936; EIC FY20 LDRD FY21: 128.2471; EIC FY20 LDRD FY22: 132.1704; EIC FY20 LDRD FY23: 136.7964; EIC FY20 LDRD FY24: 141.5843; EIC FY20 LDRD FY25: 146.5397; EIC FY20 LDRD FY26: 151.6686; EIC FY20 LDRD FY27: 156.977; EIC FY20 LDRD FY28: 162.4712; EIC FY20 LDRD FY29: 168.1577; EIC FY20 LDRD FY30: 174.0432; EIC FY20 LDRD FY31: 180.1348; EIC FY20 LDRD FY32: 186.4395; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 114.4104; EIC FY20 FY20: 118.4148; EIC FY20 FY21: 124.9972; EIC FY20 FY22: 128.8211; EIC FY20 FY23: 133.3299; EIC FY20 FY24: 137.9964; EIC FY20 FY25: 142.8263; EIC FY20 FY26: 147.8252; EIC FY20 FY27: 152.9991; EIC FY20 FY28: 158.354; EIC FY20 FY29: 163.8964; EIC FY20 FY30: 169.6328; EIC FY20 FY31: 175.57; EIC FY20 FY32: 181.7149
SCIENT_M_FY20_EIC | Scientist_Med | Labor | SCIENT_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 144.6977; EIC FY20 LDRD FY20: 149.7621; EIC FY20 LDRD FY21: 158.087; EIC FY20 LDRD FY22: 162.9232; EIC FY20 LDRD FY23: 168.6256; EIC FY20 LDRD FY24: 174.5274; EIC FY20 LDRD FY25: 180.6359; EIC FY20 LDRD FY26: 186.9582; EIC FY20 LDRD FY27: 193.5017; EIC FY20 LDRD FY28: 200.2743; EIC FY20 LDRD FY29: 207.2839; EIC FY20 LDRD FY30: 214.5388; EIC FY20 LDRD FY31: 222.0477; EIC FY20 LDRD FY32: 229.8193; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 141.0309; EIC FY20 FY20: 145.967; EIC FY20 FY21: 154.081; EIC FY20 FY22: 158.7946; EIC FY20 FY23: 164.3524; EIC FY20 FY24: 170.1047; EIC FY20 FY25: 176.0584; EIC FY20 FY26: 182.2205; EIC FY20 FY27: 188.5982; EIC FY20 FY28: 195.1991; EIC FY20 FY29: 202.0311; EIC FY20 FY30: 209.1022; EIC FY20 FY31: 216.4207; EIC FY20 FY32: 223.9955
SCIENT_H_FY20_EIC | Scientist_High | Labor | SCIENT_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 200.719; EIC FY20 LDRD FY20: 207.7442; EIC FY20 LDRD FY21: 219.2922; EIC FY20 LDRD FY22: 226.0008; EIC FY20 LDRD FY23: 233.9108; EIC FY20 LDRD FY24: 242.0977; EIC FY20 LDRD FY25: 250.5711; EIC FY20 LDRD FY26: 259.3411; EIC FY20 LDRD FY27: 268.4181; EIC FY20 LDRD FY28: 277.8127; EIC FY20 LDRD FY29: 287.5361; EIC FY20 LDRD FY30: 297.5999; EIC FY20 LDRD FY31: 308.0159; EIC FY20 LDRD FY32: 318.7965; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 195.6326; EIC FY20 FY20: 202.4797; EIC FY20 FY21: 213.7351; EIC FY20 FY22: 220.2737; EIC FY20 FY23: 227.9833; EIC FY20 FY24: 235.9627; EIC FY20 FY25: 244.2214; EIC FY20 FY26: 252.7692; EIC FY20 FY27: 261.6161; EIC FY20 FY28: 270.7726; EIC FY20 FY29: 280.2497; EIC FY20 FY30: 290.0584; EIC FY20 FY31: 300.2105; EIC FY20 FY32: 310.7178
PHYSIC_L_FY20_EIC | Physicist_Low | Labor | PHYSIC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 144.6977; EIC FY20 LDRD FY20: 149.7621; EIC FY20 LDRD FY21: 158.087; EIC FY20 LDRD FY22: 162.9232; EIC FY20 LDRD FY23: 168.6256; EIC FY20 LDRD FY24: 174.5274; EIC FY20 LDRD FY25: 180.6359; EIC FY20 LDRD FY26: 186.9582; EIC FY20 LDRD FY27: 193.5017; EIC FY20 LDRD FY28: 200.2743; EIC FY20 LDRD FY29: 207.2839; EIC FY20 LDRD FY30: 214.5388; EIC FY20 LDRD FY31: 222.0477; EIC FY20 LDRD FY32: 229.8193; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 141.0309; EIC FY20 FY20: 145.967; EIC FY20 FY21: 154.081; EIC FY20 FY22: 158.7946; EIC FY20 FY23: 164.3524; EIC FY20 FY24: 170.1047; EIC FY20 FY25: 176.0584; EIC FY20 FY26: 182.2205; EIC FY20 FY27: 188.5982; EIC FY20 FY28: 195.1991; EIC FY20 FY29: 202.0311; EIC FY20 FY30: 209.1022; EIC FY20 FY31: 216.4207; EIC FY20 FY32: 223.9955
PHYSIC_M_FY20_EIC | Physicist_Med | Labor | PHYSIC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 166.5261; EIC FY20 LDRD FY20: 172.3546; EIC FY20 LDRD FY21: 181.9354; EIC FY20 LDRD FY22: 187.5011; EIC FY20 LDRD FY23: 194.0637; EIC FY20 LDRD FY24: 200.8559; EIC FY20 LDRD FY25: 207.8859; EIC FY20 LDRD FY26: 215.1619; EIC FY20 LDRD FY27: 222.6925; EIC FY20 LDRD FY28: 230.4868; EIC FY20 LDRD FY29: 238.5538; EIC FY20 LDRD FY30: 246.9032; EIC FY20 LDRD FY31: 255.5448; EIC FY20 LDRD FY32: 264.4889; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 162.3062; EIC FY20 FY20: 167.9869; EIC FY20 FY21: 177.325; EIC FY20 FY22: 182.7497; EIC FY20 FY23: 189.1459; EIC FY20 FY24: 195.766; EIC FY20 FY25: 202.6178; EIC FY20 FY26: 209.7095; EIC FY20 FY27: 217.0493; EIC FY20 FY28: 224.646; EIC FY20 FY29: 232.5086; EIC FY20 FY30: 240.6464; EIC FY20 FY31: 249.069; EIC FY20 FY32: 257.7865
PHYSIC_H_FY20_EIC | Physicist_High | Labor | PHYSIC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 200.719; EIC FY20 LDRD FY20: 207.7442; EIC FY20 LDRD FY21: 219.2922; EIC FY20 LDRD FY22: 226.0008; EIC FY20 LDRD FY23: 233.9108; EIC FY20 LDRD FY24: 242.0977; EIC FY20 LDRD FY25: 250.5711; EIC FY20 LDRD FY26: 259.3411; EIC FY20 LDRD FY27: 268.4181; EIC FY20 LDRD FY28: 277.8127; EIC FY20 LDRD FY29: 287.5361; EIC FY20 LDRD FY30: 297.5999; EIC FY20 LDRD FY31: 308.0159; EIC FY20 LDRD FY32: 318.7965; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 195.6326; EIC FY20 FY20: 202.4797; EIC FY20 FY21: 213.7351; EIC FY20 FY22: 220.2737; EIC FY20 FY23: 227.9833; EIC FY20 FY24: 235.9627; EIC FY20 FY25: 244.2214; EIC FY20 FY26: 252.7692; EIC FY20 FY27: 261.6161; EIC FY20 FY28: 270.7726; EIC FY20 FY29: 280.2497; EIC FY20 FY30: 290.0584; EIC FY20 FY31: 300.2105; EIC FY20 FY32: 310.7178
OPTR_L_FY20_EIC | Operators_Low | Labor | OPTR_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
OPTR_M_FY20_EIC | Operators_Med | Labor | OPTR_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
OPTR_H_FY20_EIC | Operators_High | Labor | OPTR_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 122.6182; EIC FY20 LDRD FY20: 126.9098; EIC FY20 LDRD FY21: 133.9645; EIC FY20 LDRD FY22: 138.0627; EIC FY20 LDRD FY23: 142.8949; EIC FY20 LDRD FY24: 147.8962; EIC FY20 LDRD FY25: 153.0726; EIC FY20 LDRD FY26: 158.4301; EIC FY20 LDRD FY27: 163.9752; EIC FY20 LDRD FY28: 169.7143; EIC FY20 LDRD FY29: 175.6543; EIC FY20 LDRD FY30: 181.8022; EIC FY20 LDRD FY31: 188.1653; EIC FY20 LDRD FY32: 194.7511; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 119.5109; EIC FY20 FY20: 123.6938; EIC FY20 FY21: 130.5697; EIC FY20 FY22: 134.5641; EIC FY20 FY23: 139.2738; EIC FY20 FY24: 144.1484; EIC FY20 FY25: 149.1936; EIC FY20 FY26: 154.4154; EIC FY20 FY27: 159.8199; EIC FY20 FY28: 165.4136; EIC FY20 FY29: 171.2031; EIC FY20 FY30: 177.1952; EIC FY20 FY31: 183.397; EIC FY20 FY32: 189.8159
POSTDocBNL_FY20_EIC | Post Doc (BNL) | Labor | POSTDocBNL_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 65.3593; EIC FY20 LDRD FY20: 67.6469; EIC FY20 LDRD FY21: 71.4072; EIC FY20 LDRD FY22: 73.5917; EIC FY20 LDRD FY23: 76.1674; EIC FY20 LDRD FY24: 78.8332; EIC FY20 LDRD FY25: 81.5924; EIC FY20 LDRD FY26: 84.4481; EIC FY20 LDRD FY27: 87.4038; EIC FY20 LDRD FY28: 90.463; EIC FY20 LDRD FY29: 93.6292; EIC FY20 LDRD FY30: 96.9062; EIC FY20 LDRD FY31: 100.2979; EIC FY20 LDRD FY32: 103.8083; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 63.703; EIC FY20 FY20: 65.9326; EIC FY20 FY21: 69.5977; EIC FY20 FY22: 71.7268; EIC FY20 FY23: 74.2372; EIC FY20 FY24: 76.8355; EIC FY20 FY25: 79.5248; EIC FY20 FY26: 82.3081; EIC FY20 FY27: 85.1889; EIC FY20 FY28: 88.1705; EIC FY20 FY29: 91.2565; EIC FY20 FY30: 94.4505; EIC FY20 FY31: 97.7563; EIC FY20 FY32: 101.1777
POSTDocNonBNL_FY20_EIC | Post Doc (nonBNL) | Labor | POSTDocNonBNL_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 0.9913; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.0701; EIC FY20 LDRD FY22: 1.1076; EIC FY20 LDRD FY23: 1.1463; EIC FY20 LDRD FY24: 1.1865; EIC FY20 LDRD FY25: 1.228; EIC FY20 LDRD FY26: 1.271; EIC FY20 LDRD FY27: 1.3154; EIC FY20 LDRD FY28: 1.3615; EIC FY20 LDRD FY29: 1.4091; EIC FY20 LDRD FY30: 1.4585; EIC FY20 LDRD FY31: 1.5095; EIC FY20 LDRD FY32: 1.5623; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.96618; EIC FY20 FY20: 1; EIC FY20 FY21: 1.043; EIC FY20 FY22: 1.0795; EIC FY20 FY23: 1.1173; EIC FY20 FY24: 1.1564; EIC FY20 FY25: 1.1969; EIC FY20 FY26: 1.2388; EIC FY20 FY27: 1.2821; EIC FY20 FY28: 1.327; EIC FY20 FY29: 1.3734; EIC FY20 FY30: 1.4215; EIC FY20 FY31: 1.4713; EIC FY20 FY32: 1.5227
RASCIEN_L_FY20_EIC | Research Associate_Low | Labor | RASCIEN_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 60.3479; EIC FY20 LDRD FY20: 62.46; EIC FY20 LDRD FY21: 65.932; EIC FY20 LDRD FY22: 67.949; EIC FY20 LDRD FY23: 70.3273; EIC FY20 LDRD FY24: 72.7887; EIC FY20 LDRD FY25: 75.3363; EIC FY20 LDRD FY26: 77.9731; EIC FY20 LDRD FY27: 80.7021; EIC FY20 LDRD FY28: 83.5267; EIC FY20 LDRD FY29: 86.4501; EIC FY20 LDRD FY30: 89.4759; EIC FY20 LDRD FY31: 92.6076; EIC FY20 LDRD FY32: 95.8488; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 58.8186; EIC FY20 FY20: 60.8772; EIC FY20 FY21: 64.2613; EIC FY20 FY22: 66.2271; EIC FY20 FY23: 68.5451; EIC FY20 FY24: 70.9442; EIC FY20 FY25: 73.4272; EIC FY20 FY26: 75.9972; EIC FY20 FY27: 78.6571; EIC FY20 FY28: 81.4101; EIC FY20 FY29: 84.2594; EIC FY20 FY30: 87.2085; EIC FY20 FY31: 90.2608; EIC FY20 FY32: 93.4199
RASCIEN_M_FY20_EIC | Research Associate_Med | Labor | RASCIEN_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 65.3593; EIC FY20 LDRD FY20: 67.6469; EIC FY20 LDRD FY21: 71.4072; EIC FY20 LDRD FY22: 73.5917; EIC FY20 LDRD FY23: 76.1674; EIC FY20 LDRD FY24: 78.8332; EIC FY20 LDRD FY25: 81.5924; EIC FY20 LDRD FY26: 84.4481; EIC FY20 LDRD FY27: 87.4038; EIC FY20 LDRD FY28: 90.463; EIC FY20 LDRD FY29: 93.6292; EIC FY20 LDRD FY30: 96.9062; EIC FY20 LDRD FY31: 100.2979; EIC FY20 LDRD FY32: 103.8083; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 63.703; EIC FY20 FY20: 65.9326; EIC FY20 FY21: 69.5977; EIC FY20 FY22: 71.7268; EIC FY20 FY23: 74.2372; EIC FY20 FY24: 76.8355; EIC FY20 FY25: 79.5248; EIC FY20 FY26: 82.3081; EIC FY20 FY27: 85.1889; EIC FY20 FY28: 88.1705; EIC FY20 FY29: 91.2565; EIC FY20 FY30: 94.4505; EIC FY20 FY31: 97.7563; EIC FY20 FY32: 101.1777
RASCIEN_H_FY20_EIC | Research Associate_High | Labor | RASCIEN_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 74.0127; EIC FY20 LDRD FY20: 76.6032; EIC FY20 LDRD FY21: 80.8614; EIC FY20 LDRD FY22: 83.3351; EIC FY20 LDRD FY23: 86.2518; EIC FY20 LDRD FY24: 89.2706; EIC FY20 LDRD FY25: 92.3951; EIC FY20 LDRD FY26: 95.6289; EIC FY20 LDRD FY27: 98.976; EIC FY20 LDRD FY28: 102.4401; EIC FY20 LDRD FY29: 106.0255; EIC FY20 LDRD FY30: 109.7364; EIC FY20 LDRD FY31: 113.5772; EIC FY20 LDRD FY32: 117.5524; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 72.1372; EIC FY20 FY20: 74.662; EIC FY20 FY21: 78.8123; EIC FY20 FY22: 81.2233; EIC FY20 FY23: 84.0661; EIC FY20 FY24: 87.0084; EIC FY20 FY25: 90.0537; EIC FY20 FY26: 93.2056; EIC FY20 FY27: 96.4678; EIC FY20 FY28: 99.8442; EIC FY20 FY29: 103.3387; EIC FY20 FY30: 106.9556; EIC FY20 FY31: 110.699; EIC FY20 FY32: 114.5735
STUDENTBNL_FY20_EIC | Graduate Student (BNL) | Labor | STUDENTBNL_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 0.9913; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.0701; EIC FY20 LDRD FY22: 1.1076; EIC FY20 LDRD FY23: 1.1463; EIC FY20 LDRD FY24: 1.1865; EIC FY20 LDRD FY25: 1.228; EIC FY20 LDRD FY26: 1.271; EIC FY20 LDRD FY27: 1.3154; EIC FY20 LDRD FY28: 1.3615; EIC FY20 LDRD FY29: 1.4091; EIC FY20 LDRD FY30: 1.4585; EIC FY20 LDRD FY31: 1.5095; EIC FY20 LDRD FY32: 1.5623; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.96618; EIC FY20 FY20: 1; EIC FY20 FY21: 1.043; EIC FY20 FY22: 1.0795; EIC FY20 FY23: 1.1173; EIC FY20 FY24: 1.1564; EIC FY20 FY25: 1.1969; EIC FY20 FY26: 1.2388; EIC FY20 FY27: 1.2821; EIC FY20 FY28: 1.327; EIC FY20 FY29: 1.3734; EIC FY20 FY30: 1.4215; EIC FY20 FY31: 1.4713; EIC FY20 FY32: 1.5227
STUDENTnonBNL_FY20_EIC | Graduate Student (nonBNL) | Labor | STUDENTnonBNL_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 0.9913; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.0701; EIC FY20 LDRD FY22: 1.1076; EIC FY20 LDRD FY23: 1.1463; EIC FY20 LDRD FY24: 1.1865; EIC FY20 LDRD FY25: 1.228; EIC FY20 LDRD FY26: 1.271; EIC FY20 LDRD FY27: 1.3154; EIC FY20 LDRD FY28: 1.3615; EIC FY20 LDRD FY29: 1.4091; EIC FY20 LDRD FY30: 1.4585; EIC FY20 LDRD FY31: 1.5095; EIC FY20 LDRD FY32: 1.5623; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.96618; EIC FY20 FY20: 1; EIC FY20 FY21: 1.043; EIC FY20 FY22: 1.0795; EIC FY20 FY23: 1.1173; EIC FY20 FY24: 1.1564; EIC FY20 FY25: 1.1969; EIC FY20 FY26: 1.2388; EIC FY20 FY27: 1.2821; EIC FY20 FY28: 1.327; EIC FY20 FY29: 1.3734; EIC FY20 FY30: 1.4215; EIC FY20 FY31: 1.4713; EIC FY20 FY32: 1.5227
DOEPNR_FY20_EIC | DOE Partner Laboratories | Labor | DOEPNR_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 0.96618; EIC FY20 LDRD FY20: 1; EIC FY20 LDRD FY21: 1.043; EIC FY20 LDRD FY22: 1.0795; EIC FY20 LDRD FY23: 1.1173; EIC FY20 LDRD FY24: 1.1564; EIC FY20 LDRD FY25: 1.1969; EIC FY20 LDRD FY26: 1.2388; EIC FY20 LDRD FY27: 1.2821; EIC FY20 LDRD FY28: 1.327; EIC FY20 LDRD FY29: 1.3734; EIC FY20 LDRD FY30: 1.4215; EIC FY20 LDRD FY31: 1.4713; EIC FY20 LDRD FY32: 1.5227; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.96618; EIC FY20 FY20: 1; EIC FY20 FY21: 1.043; EIC FY20 FY22: 1.0795; EIC FY20 FY23: 1.1173; EIC FY20 FY24: 1.1564; EIC FY20 FY25: 1.1969; EIC FY20 FY26: 1.2388; EIC FY20 FY27: 1.2821; EIC FY20 FY28: 1.327; EIC FY20 FY29: 1.3734; EIC FY20 FY30: 1.4215; EIC FY20 FY31: 1.4713; EIC FY20 FY32: 1.5227
EDUCINST_FY20_EIC | Educational Institutions | Labor | EDUCINST_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 0.9913; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.0701; EIC FY20 LDRD FY22: 1.1076; EIC FY20 LDRD FY23: 1.1463; EIC FY20 LDRD FY24: 1.1865; EIC FY20 LDRD FY25: 1.228; EIC FY20 LDRD FY26: 1.271; EIC FY20 LDRD FY27: 1.3154; EIC FY20 LDRD FY28: 1.3615; EIC FY20 LDRD FY29: 1.4091; EIC FY20 LDRD FY30: 1.4585; EIC FY20 LDRD FY31: 1.5095; EIC FY20 LDRD FY32: 1.5623; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 0.96618; EIC FY20 FY20: 1; EIC FY20 FY21: 1.043; EIC FY20 FY22: 1.0795; EIC FY20 FY23: 1.1173; EIC FY20 FY24: 1.1564; EIC FY20 FY25: 1.1969; EIC FY20 FY26: 1.2388; EIC FY20 FY27: 1.2821; EIC FY20 FY28: 1.327; EIC FY20 FY29: 1.3734; EIC FY20 FY30: 1.4215; EIC FY20 FY31: 1.4713; EIC FY20 FY32: 1.5227
DESEL_L_FY20_EIC | Designer Electrical_Low | Labor | DESEL_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
DESEL_M_FY20_EIC | Designer Electrical_Med | Labor | DESEL_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
DESEL_H_FY20_EIC | Designer Electrical_High | Labor | DESEL_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 122.6182; EIC FY20 LDRD FY20: 126.9098; EIC FY20 LDRD FY21: 133.9645; EIC FY20 LDRD FY22: 138.0627; EIC FY20 LDRD FY23: 142.8949; EIC FY20 LDRD FY24: 147.8962; EIC FY20 LDRD FY25: 153.0726; EIC FY20 LDRD FY26: 158.4301; EIC FY20 LDRD FY27: 163.9752; EIC FY20 LDRD FY28: 169.7143; EIC FY20 LDRD FY29: 175.6543; EIC FY20 LDRD FY30: 181.8022; EIC FY20 LDRD FY31: 188.1653; EIC FY20 LDRD FY32: 194.7511; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 119.5109; EIC FY20 FY20: 123.6938; EIC FY20 FY21: 130.5697; EIC FY20 FY22: 134.5641; EIC FY20 FY23: 139.2738; EIC FY20 FY24: 144.1484; EIC FY20 FY25: 149.1936; EIC FY20 FY26: 154.4154; EIC FY20 FY27: 159.8199; EIC FY20 FY28: 165.4136; EIC FY20 FY29: 171.2031; EIC FY20 FY30: 177.1952; EIC FY20 FY31: 183.397; EIC FY20 FY32: 189.8159
DES_L_FY20_EIC | Designer General_Low | Labor | DES_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
DES_M_FY20_EIC | Designer General_Med | Labor | DES_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
DES_H_FY20_EIC | Designer General_High | Labor | DES_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 122.6182; EIC FY20 LDRD FY20: 126.9098; EIC FY20 LDRD FY21: 133.9645; EIC FY20 LDRD FY22: 138.0627; EIC FY20 LDRD FY23: 142.8949; EIC FY20 LDRD FY24: 147.8962; EIC FY20 LDRD FY25: 153.0726; EIC FY20 LDRD FY26: 158.4301; EIC FY20 LDRD FY27: 163.9752; EIC FY20 LDRD FY28: 169.7143; EIC FY20 LDRD FY29: 175.6543; EIC FY20 LDRD FY30: 181.8022; EIC FY20 LDRD FY31: 188.1653; EIC FY20 LDRD FY32: 194.7511; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 119.5109; EIC FY20 FY20: 123.6938; EIC FY20 FY21: 130.5697; EIC FY20 FY22: 134.5641; EIC FY20 FY23: 139.2738; EIC FY20 FY24: 144.1484; EIC FY20 FY25: 149.1936; EIC FY20 FY26: 154.4154; EIC FY20 FY27: 159.8199; EIC FY20 FY28: 165.4136; EIC FY20 FY29: 171.2031; EIC FY20 FY30: 177.1952; EIC FY20 FY31: 183.397; EIC FY20 FY32: 189.8159
DESMC_L_FY20_EIC | Designer Mechanical_Low | Labor | DESMC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
DESMC_M_FY20_EIC | Designer Mechanical_Med | Labor | DESMC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
DESMC_H_FY20_EIC | Designer Mechanical_High | Labor | DESMC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 122.6182; EIC FY20 LDRD FY20: 126.9098; EIC FY20 LDRD FY21: 133.9645; EIC FY20 LDRD FY22: 138.0627; EIC FY20 LDRD FY23: 142.8949; EIC FY20 LDRD FY24: 147.8962; EIC FY20 LDRD FY25: 153.0726; EIC FY20 LDRD FY26: 158.4301; EIC FY20 LDRD FY27: 163.9752; EIC FY20 LDRD FY28: 169.7143; EIC FY20 LDRD FY29: 175.6543; EIC FY20 LDRD FY30: 181.8022; EIC FY20 LDRD FY31: 188.1653; EIC FY20 LDRD FY32: 194.7511; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 119.5109; EIC FY20 FY20: 123.6938; EIC FY20 FY21: 130.5697; EIC FY20 FY22: 134.5641; EIC FY20 FY23: 139.2738; EIC FY20 FY24: 144.1484; EIC FY20 FY25: 149.1936; EIC FY20 FY26: 154.4154; EIC FY20 FY27: 159.8199; EIC FY20 FY28: 165.4136; EIC FY20 FY29: 171.2031; EIC FY20 FY30: 177.1952; EIC FY20 FY31: 183.397; EIC FY20 FY32: 189.8159
ESH_L_FY20_EIC | ES&H Engineer_Low | Labor | ESH_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
ESH_M_FY20_EIC | ES&H Engineer_Med | Labor | ESH_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
ESH_H_FY20_EIC | ES&H Engineer_High | Labor | ESH_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 189.0297; EIC FY20 LDRD FY20: 195.6457; EIC FY20 LDRD FY21: 206.5212; EIC FY20 LDRD FY22: 212.8391; EIC FY20 LDRD FY23: 220.2885; EIC FY20 LDRD FY24: 227.9986; EIC FY20 LDRD FY25: 235.9785; EIC FY20 LDRD FY26: 244.2378; EIC FY20 LDRD FY27: 252.7861; EIC FY20 LDRD FY28: 261.6336; EIC FY20 LDRD FY29: 270.7908; EIC FY20 LDRD FY30: 280.2685; EIC FY20 LDRD FY31: 290.0779; EIC FY20 LDRD FY32: 300.2306; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 184.2395; EIC FY20 FY20: 190.6878; EIC FY20 FY21: 201.2878; EIC FY20 FY22: 207.4456; EIC FY20 FY23: 214.7062; EIC FY20 FY24: 222.2209; EIC FY20 FY25: 229.9986; EIC FY20 FY26: 238.0486; EIC FY20 FY27: 246.3803; EIC FY20 FY28: 255.0036; EIC FY20 FY29: 263.9287; EIC FY20 FY30: 273.1662; EIC FY20 FY31: 282.727; EIC FY20 FY32: 292.6225
QA_L_FY20_EIC | QA Professional_Low | Labor | QA_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 85.078; EIC FY20 LDRD FY20: 88.0557; EIC FY20 LDRD FY21: 92.9505; EIC FY20 LDRD FY22: 95.794; EIC FY20 LDRD FY23: 99.1468; EIC FY20 LDRD FY24: 102.617; EIC FY20 LDRD FY25: 106.2086; EIC FY20 LDRD FY26: 109.9259; EIC FY20 LDRD FY27: 113.7733; EIC FY20 LDRD FY28: 117.7553; EIC FY20 LDRD FY29: 121.8768; EIC FY20 LDRD FY30: 126.1425; EIC FY20 LDRD FY31: 130.5574; EIC FY20 LDRD FY32: 135.127; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 82.922; EIC FY20 FY20: 85.8243; EIC FY20 FY21: 90.595; EIC FY20 FY22: 93.3665; EIC FY20 FY23: 96.6344; EIC FY20 FY24: 100.0166; EIC FY20 FY25: 103.5171; EIC FY20 FY26: 107.1402; EIC FY20 FY27: 110.8901; EIC FY20 FY28: 114.7713; EIC FY20 FY29: 118.7883; EIC FY20 FY30: 122.9459; EIC FY20 FY31: 127.249; EIC FY20 FY32: 131.7027
QA_M_FY20_EIC | QA Professional_Med | Labor | QA_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 125.5077; EIC FY20 LDRD FY20: 129.9005; EIC FY20 LDRD FY21: 137.1213; EIC FY20 LDRD FY22: 141.3162; EIC FY20 LDRD FY23: 146.2622; EIC FY20 LDRD FY24: 151.3814; EIC FY20 LDRD FY25: 156.6797; EIC FY20 LDRD FY26: 162.1635; EIC FY20 LDRD FY27: 167.8393; EIC FY20 LDRD FY28: 173.7136; EIC FY20 LDRD FY29: 179.7936; EIC FY20 LDRD FY30: 186.0864; EIC FY20 LDRD FY31: 192.5994; EIC FY20 LDRD FY32: 199.3404; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 122.3272; EIC FY20 FY20: 126.6086; EIC FY20 FY21: 133.6465; EIC FY20 FY22: 137.7351; EIC FY20 FY23: 142.5558; EIC FY20 FY24: 147.5452; EIC FY20 FY25: 152.7093; EIC FY20 FY26: 158.0541; EIC FY20 FY27: 163.586; EIC FY20 FY28: 169.3116; EIC FY20 FY29: 175.2375; EIC FY20 FY30: 181.3708; EIC FY20 FY31: 187.7187; EIC FY20 FY32: 194.2889
QA_H_FY20_EIC | QA Professional_High | Labor | QA_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 166.0196; EIC FY20 LDRD FY20: 171.8303; EIC FY20 LDRD FY21: 181.382; EIC FY20 LDRD FY22: 186.9308; EIC FY20 LDRD FY23: 193.4734; EIC FY20 LDRD FY24: 200.245; EIC FY20 LDRD FY25: 207.2536; EIC FY20 LDRD FY26: 214.5074; EIC FY20 LDRD FY27: 222.0152; EIC FY20 LDRD FY28: 229.7857; EIC FY20 LDRD FY29: 237.8282; EIC FY20 LDRD FY30: 246.1522; EIC FY20 LDRD FY31: 254.7675; EIC FY20 LDRD FY32: 263.6844; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 161.8125; EIC FY20 FY20: 167.476; EIC FY20 FY21: 176.7856; EIC FY20 FY22: 182.1938; EIC FY20 FY23: 188.5706; EIC FY20 FY24: 195.1706; EIC FY20 FY25: 202.0015; EIC FY20 FY26: 209.0716; EIC FY20 FY27: 216.3891; EIC FY20 FY28: 223.9627; EIC FY20 FY29: 231.8014; EIC FY20 FY30: 239.9145; EIC FY20 FY31: 248.3115; EIC FY20 FY32: 257.0024
TRAD_L_FY20_EIC | Tech Rad_Low | Labor | TRAD_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TRAD_M_FY20_EIC | Tech Rad_Med | Labor | TRAD_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TRAD_H_FY20_EIC | Tech Rad_High | Labor | TRAD_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
CS_R_FY20_EIC | Central Shops_RC | Labor | CS_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 150.8651; EIC FY20 LDRD FY20: 153.8824; EIC FY20 LDRD FY21: 160.4118; EIC FY20 LDRD FY22: 162.9231; EIC FY20 LDRD FY23: 166.1816; EIC FY20 LDRD FY24: 169.5052; EIC FY20 LDRD FY25: 172.8953; EIC FY20 LDRD FY26: 176.3533; EIC FY20 LDRD FY27: 179.8803; EIC FY20 LDRD FY28: 183.4779; EIC FY20 LDRD FY29: 187.1475; EIC FY20 LDRD FY30: 190.8904; EIC FY20 LDRD FY31: 194.7082; EIC FY20 LDRD FY32: 198.6024; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 147.042; EIC FY20 FY20: 149.9828; EIC FY20 FY21: 156.3468; EIC FY20 FY22: 158.7945; EIC FY20 FY23: 161.9704; EIC FY20 FY24: 165.2098; EIC FY20 FY25: 168.514; EIC FY20 FY26: 171.8843; EIC FY20 FY27: 175.322; EIC FY20 FY28: 178.8284; EIC FY20 FY29: 182.405; EIC FY20 FY30: 186.0531; EIC FY20 FY31: 189.7741; EIC FY20 FY32: 193.5696
BTAC_R_FY20_EIC | Building Trades Assigned - Carpenters_RC | Labor | BTAC_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 124.3842; EIC FY20 LDRD FY20: 126.8719; EIC FY20 LDRD FY21: 132.2552; EIC FY20 LDRD FY22: 134.3257; EIC FY20 LDRD FY23: 137.0122; EIC FY20 LDRD FY24: 139.7525; EIC FY20 LDRD FY25: 142.5475; EIC FY20 LDRD FY26: 145.3985; EIC FY20 LDRD FY27: 148.3065; EIC FY20 LDRD FY28: 151.2726; EIC FY20 LDRD FY29: 154.298; EIC FY20 LDRD FY30: 157.384; EIC FY20 LDRD FY31: 160.5317; EIC FY20 LDRD FY32: 163.7423; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 121.2321; EIC FY20 FY20: 123.6568; EIC FY20 FY21: 128.9037; EIC FY20 FY22: 130.9218; EIC FY20 FY23: 133.5402; EIC FY20 FY24: 136.211; EIC FY20 FY25: 138.9352; EIC FY20 FY26: 141.7139; EIC FY20 FY27: 144.5482; EIC FY20 FY28: 147.4392; EIC FY20 FY29: 150.388; EIC FY20 FY30: 153.3957; EIC FY20 FY31: 156.4636; EIC FY20 FY32: 159.5929
BTUC_R_FY20_EIC | Building Trades Unassigned - Carpenters_RC | Labor | BTUC_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 150.8651; EIC FY20 LDRD FY20: 153.8824; EIC FY20 LDRD FY21: 160.4118; EIC FY20 LDRD FY22: 162.9231; EIC FY20 LDRD FY23: 166.1816; EIC FY20 LDRD FY24: 169.5052; EIC FY20 LDRD FY25: 172.8953; EIC FY20 LDRD FY26: 176.3533; EIC FY20 LDRD FY27: 179.8803; EIC FY20 LDRD FY28: 183.4779; EIC FY20 LDRD FY29: 187.1475; EIC FY20 LDRD FY30: 190.8904; EIC FY20 LDRD FY31: 194.7082; EIC FY20 LDRD FY32: 198.6024; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 147.042; EIC FY20 FY20: 149.9828; EIC FY20 FY21: 156.3468; EIC FY20 FY22: 158.7945; EIC FY20 FY23: 161.9704; EIC FY20 FY24: 165.2098; EIC FY20 FY25: 168.514; EIC FY20 FY26: 171.8843; EIC FY20 FY27: 175.322; EIC FY20 FY28: 178.8284; EIC FY20 FY29: 182.405; EIC FY20 FY30: 186.0531; EIC FY20 FY31: 189.7741; EIC FY20 FY32: 193.5696
BTAE_R_FY20_EIC | Building Trades Assigned - Electricians_RC | Labor | BTAE_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 124.3842; EIC FY20 LDRD FY20: 126.8719; EIC FY20 LDRD FY21: 132.2552; EIC FY20 LDRD FY22: 134.3257; EIC FY20 LDRD FY23: 137.0122; EIC FY20 LDRD FY24: 139.7525; EIC FY20 LDRD FY25: 142.5475; EIC FY20 LDRD FY26: 145.3985; EIC FY20 LDRD FY27: 148.3065; EIC FY20 LDRD FY28: 151.2726; EIC FY20 LDRD FY29: 154.298; EIC FY20 LDRD FY30: 157.384; EIC FY20 LDRD FY31: 160.5317; EIC FY20 LDRD FY32: 163.7423; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 121.2321; EIC FY20 FY20: 123.6568; EIC FY20 FY21: 128.9037; EIC FY20 FY22: 130.9218; EIC FY20 FY23: 133.5402; EIC FY20 FY24: 136.211; EIC FY20 FY25: 138.9352; EIC FY20 FY26: 141.7139; EIC FY20 FY27: 144.5482; EIC FY20 FY28: 147.4392; EIC FY20 FY29: 150.388; EIC FY20 FY30: 153.3957; EIC FY20 FY31: 156.4636; EIC FY20 FY32: 159.5929
BTUE_R_FY20_EIC | Building Trades Unassigned - Electricians_RC | Labor | BTUE_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 150.8651; EIC FY20 LDRD FY20: 153.8824; EIC FY20 LDRD FY21: 160.4118; EIC FY20 LDRD FY22: 162.9231; EIC FY20 LDRD FY23: 166.1816; EIC FY20 LDRD FY24: 169.5052; EIC FY20 LDRD FY25: 172.8953; EIC FY20 LDRD FY26: 176.3533; EIC FY20 LDRD FY27: 179.8803; EIC FY20 LDRD FY28: 183.4779; EIC FY20 LDRD FY29: 187.1475; EIC FY20 LDRD FY30: 190.8904; EIC FY20 LDRD FY31: 194.7082; EIC FY20 LDRD FY32: 198.6024; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 147.042; EIC FY20 FY20: 149.9828; EIC FY20 FY21: 156.3468; EIC FY20 FY22: 158.7945; EIC FY20 FY23: 161.9704; EIC FY20 FY24: 165.2098; EIC FY20 FY25: 168.514; EIC FY20 FY26: 171.8843; EIC FY20 FY27: 175.322; EIC FY20 FY28: 178.8284; EIC FY20 FY29: 182.405; EIC FY20 FY30: 186.0531; EIC FY20 FY31: 189.7741; EIC FY20 FY32: 193.5696
BTAP_R_FY20_EIC | Building Trades Assigned - Plumbers_RC | Labor | BTAP_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 124.3842; EIC FY20 LDRD FY20: 126.8719; EIC FY20 LDRD FY21: 132.2552; EIC FY20 LDRD FY22: 134.3257; EIC FY20 LDRD FY23: 137.0122; EIC FY20 LDRD FY24: 139.7525; EIC FY20 LDRD FY25: 142.5475; EIC FY20 LDRD FY26: 145.3985; EIC FY20 LDRD FY27: 148.3065; EIC FY20 LDRD FY28: 151.2726; EIC FY20 LDRD FY29: 154.298; EIC FY20 LDRD FY30: 157.384; EIC FY20 LDRD FY31: 160.5317; EIC FY20 LDRD FY32: 163.7423; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 121.2321; EIC FY20 FY20: 123.6568; EIC FY20 FY21: 128.9037; EIC FY20 FY22: 130.9218; EIC FY20 FY23: 133.5402; EIC FY20 FY24: 136.211; EIC FY20 FY25: 138.9352; EIC FY20 FY26: 141.7139; EIC FY20 FY27: 144.5482; EIC FY20 FY28: 147.4392; EIC FY20 FY29: 150.388; EIC FY20 FY30: 153.3957; EIC FY20 FY31: 156.4636; EIC FY20 FY32: 159.5929
BTUP_R_FY20_EIC | Building Trades Unassigned - Plumbers_RC | Labor | BTUP_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 150.8651; EIC FY20 LDRD FY20: 153.8824; EIC FY20 LDRD FY21: 160.4118; EIC FY20 LDRD FY22: 162.9231; EIC FY20 LDRD FY23: 166.1816; EIC FY20 LDRD FY24: 169.5052; EIC FY20 LDRD FY25: 172.8953; EIC FY20 LDRD FY26: 176.3533; EIC FY20 LDRD FY27: 179.8803; EIC FY20 LDRD FY28: 183.4779; EIC FY20 LDRD FY29: 187.1475; EIC FY20 LDRD FY30: 190.8904; EIC FY20 LDRD FY31: 194.7082; EIC FY20 LDRD FY32: 198.6024; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 147.042; EIC FY20 FY20: 149.9828; EIC FY20 FY21: 156.3468; EIC FY20 FY22: 158.7945; EIC FY20 FY23: 161.9704; EIC FY20 FY24: 165.2098; EIC FY20 FY25: 168.514; EIC FY20 FY26: 171.8843; EIC FY20 FY27: 175.322; EIC FY20 FY28: 178.8284; EIC FY20 FY29: 182.405; EIC FY20 FY30: 186.0531; EIC FY20 FY31: 189.7741; EIC FY20 FY32: 193.5696
BTAR_R_FY20_EIC | Building Trades Assigned - Riggers_RC | Labor | BTAR_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 124.3842; EIC FY20 LDRD FY20: 126.8719; EIC FY20 LDRD FY21: 132.2552; EIC FY20 LDRD FY22: 134.3257; EIC FY20 LDRD FY23: 137.0122; EIC FY20 LDRD FY24: 139.7525; EIC FY20 LDRD FY25: 142.5475; EIC FY20 LDRD FY26: 145.3985; EIC FY20 LDRD FY27: 148.3065; EIC FY20 LDRD FY28: 151.2726; EIC FY20 LDRD FY29: 154.298; EIC FY20 LDRD FY30: 157.384; EIC FY20 LDRD FY31: 160.5317; EIC FY20 LDRD FY32: 163.7423; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 121.2321; EIC FY20 FY20: 123.6568; EIC FY20 FY21: 128.9037; EIC FY20 FY22: 130.9218; EIC FY20 FY23: 133.5402; EIC FY20 FY24: 136.211; EIC FY20 FY25: 138.9352; EIC FY20 FY26: 141.7139; EIC FY20 FY27: 144.5482; EIC FY20 FY28: 147.4392; EIC FY20 FY29: 150.388; EIC FY20 FY30: 153.3957; EIC FY20 FY31: 156.4636; EIC FY20 FY32: 159.5929
BTUR_R_FY20_EIC | Building Trades Unassigned - Riggers_RC | Labor | BTUR_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 150.8651; EIC FY20 LDRD FY20: 153.8824; EIC FY20 LDRD FY21: 160.4118; EIC FY20 LDRD FY22: 162.9231; EIC FY20 LDRD FY23: 166.1816; EIC FY20 LDRD FY24: 169.5052; EIC FY20 LDRD FY25: 172.8953; EIC FY20 LDRD FY26: 176.3533; EIC FY20 LDRD FY27: 179.8803; EIC FY20 LDRD FY28: 183.4779; EIC FY20 LDRD FY29: 187.1475; EIC FY20 LDRD FY30: 190.8904; EIC FY20 LDRD FY31: 194.7082; EIC FY20 LDRD FY32: 198.6024; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 147.042; EIC FY20 FY20: 149.9828; EIC FY20 FY21: 156.3468; EIC FY20 FY22: 158.7945; EIC FY20 FY23: 161.9704; EIC FY20 FY24: 165.2098; EIC FY20 FY25: 168.514; EIC FY20 FY26: 171.8843; EIC FY20 FY27: 175.322; EIC FY20 FY28: 178.8284; EIC FY20 FY29: 182.405; EIC FY20 FY30: 186.0531; EIC FY20 FY31: 189.7741; EIC FY20 FY32: 193.5696
BTGG_R_FY20_EIC | Building Trades - General_RC | Labor | BTGG_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 87.2136; EIC FY20 LDRD FY20: 88.9579; EIC FY20 LDRD FY21: 92.7325; EIC FY20 LDRD FY22: 94.1843; EIC FY20 LDRD FY23: 96.0679; EIC FY20 LDRD FY24: 97.9893; EIC FY20 LDRD FY25: 99.9491; EIC FY20 LDRD FY26: 101.9481; EIC FY20 LDRD FY27: 103.987; EIC FY20 LDRD FY28: 106.0668; EIC FY20 LDRD FY29: 108.1881; EIC FY20 LDRD FY30: 110.3519; EIC FY20 LDRD FY31: 112.5589; EIC FY20 LDRD FY32: 114.8101; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 85.0035; EIC FY20 FY20: 86.7036; EIC FY20 FY21: 90.3825; EIC FY20 FY22: 91.7975; EIC FY20 FY23: 93.6335; EIC FY20 FY24: 95.5062; EIC FY20 FY25: 97.4163; EIC FY20 FY26: 99.3646; EIC FY20 FY27: 101.3519; EIC FY20 FY28: 103.3789; EIC FY20 FY29: 105.4465; EIC FY20 FY30: 107.5554; EIC FY20 FY31: 109.7066; EIC FY20 FY32: 111.9007
BTAW_R_FY20_EIC | Building Trades Assigned - Welders_RC | Labor | BTAW_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 124.3842; EIC FY20 LDRD FY20: 126.8719; EIC FY20 LDRD FY21: 132.2552; EIC FY20 LDRD FY22: 134.3257; EIC FY20 LDRD FY23: 137.0122; EIC FY20 LDRD FY24: 139.7525; EIC FY20 LDRD FY25: 142.5475; EIC FY20 LDRD FY26: 145.3985; EIC FY20 LDRD FY27: 148.3065; EIC FY20 LDRD FY28: 151.2726; EIC FY20 LDRD FY29: 154.298; EIC FY20 LDRD FY30: 157.384; EIC FY20 LDRD FY31: 160.5317; EIC FY20 LDRD FY32: 163.7423; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 121.2321; EIC FY20 FY20: 123.6568; EIC FY20 FY21: 128.9037; EIC FY20 FY22: 130.9218; EIC FY20 FY23: 133.5402; EIC FY20 FY24: 136.211; EIC FY20 FY25: 138.9352; EIC FY20 FY26: 141.7139; EIC FY20 FY27: 144.5482; EIC FY20 FY28: 147.4392; EIC FY20 FY29: 150.388; EIC FY20 FY30: 153.3957; EIC FY20 FY31: 156.4636; EIC FY20 FY32: 159.5929
BTUW_R_FY20_EIC | Building Trades Unassigned - Welders_RC | Labor | BTUW_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 150.8651; EIC FY20 LDRD FY20: 153.8824; EIC FY20 LDRD FY21: 160.4118; EIC FY20 LDRD FY22: 162.9231; EIC FY20 LDRD FY23: 166.1816; EIC FY20 LDRD FY24: 169.5052; EIC FY20 LDRD FY25: 172.8953; EIC FY20 LDRD FY26: 176.3533; EIC FY20 LDRD FY27: 179.8803; EIC FY20 LDRD FY28: 183.4779; EIC FY20 LDRD FY29: 187.1475; EIC FY20 LDRD FY30: 190.8904; EIC FY20 LDRD FY31: 194.7082; EIC FY20 LDRD FY32: 198.6024; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 147.042; EIC FY20 FY20: 149.9828; EIC FY20 FY21: 156.3468; EIC FY20 FY22: 158.7945; EIC FY20 FY23: 161.9704; EIC FY20 FY24: 165.2098; EIC FY20 FY25: 168.514; EIC FY20 FY26: 171.8843; EIC FY20 FY27: 175.322; EIC FY20 FY28: 178.8284; EIC FY20 FY29: 182.405; EIC FY20 FY30: 186.0531; EIC FY20 FY31: 189.7741; EIC FY20 FY32: 193.5696
APPLIC_L_FY20_EIC | Applications Engineer (Programmer)_Low | Labor | APPLIC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
APPLIC_M_FY20_EIC | Applications Engineer (Programmer)_Med | Labor | APPLIC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
APPLIC_H_FY20_EIC | Applications Engineer (Programmer)_High | Labor | APPLIC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TECHE_L_FY20_EIC | Technology Engineer (Controls)_Low | Labor | TECHE_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
TECHE_M_FY20_EIC | Technology Engineer (Controls)_Med | Labor | TECHE_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
TECHE_H_FY20_EIC | Technology Engineer (Controls)_High | Labor | TECHE_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TG_L_FY20_EIC | Engineer Digital_Low | Labor | TG_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
TG_M_FY20_EIC | Engineer Digital_Med | Labor | TG_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
TG_H_FY20_EIC | Engineer Digital_High | Labor | TG_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TCT_L_FY20_EIC | Tech Controls_Low | Labor | TCT_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TCT_M_FY20_EIC | Tech Controls_Med | Labor | TCT_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TCT_H_FY20_EIC | Tech Controls_High | Labor | TCT_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
SYS_L_FY20_EIC | Engineer Systems/ Systems Architect_Low | Labor | SYS_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
SYS_M_FY20_EIC | Engineer Systems/ Systems Architect_Med | Labor | SYS_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
SYS_H_FY20_EIC | Engineer Systems/ Systems Architect_High | Labor | SYS_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 189.0297; EIC FY20 LDRD FY20: 195.6457; EIC FY20 LDRD FY21: 206.5212; EIC FY20 LDRD FY22: 212.8391; EIC FY20 LDRD FY23: 220.2885; EIC FY20 LDRD FY24: 227.9986; EIC FY20 LDRD FY25: 235.9785; EIC FY20 LDRD FY26: 244.2378; EIC FY20 LDRD FY27: 252.7861; EIC FY20 LDRD FY28: 261.6336; EIC FY20 LDRD FY29: 270.7908; EIC FY20 LDRD FY30: 280.2685; EIC FY20 LDRD FY31: 290.0779; EIC FY20 LDRD FY32: 300.2306; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 184.2395; EIC FY20 FY20: 190.6878; EIC FY20 FY21: 201.2878; EIC FY20 FY22: 207.4456; EIC FY20 FY23: 214.7062; EIC FY20 FY24: 222.2209; EIC FY20 FY25: 229.9986; EIC FY20 FY26: 238.0486; EIC FY20 FY27: 246.3803; EIC FY20 FY28: 255.0036; EIC FY20 FY29: 263.9287; EIC FY20 FY30: 273.1662; EIC FY20 FY31: 282.727; EIC FY20 FY32: 292.6225
EECY_L_FY20_EIC | Engineer Cryo Elec_Low | Labor | EECY_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
EECY_M_FY20_EIC | Engineer Cryo Elec_Med | Labor | EECY_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EECY_H_FY20_EIC | Engineer Cryo Elec_High | Labor | EECY_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
EMCY_L_FY20_EIC | Engineer Cryo Mech_Low | Labor | EMCY_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
EMCY_M_FY20_EIC | Engineer Cryo Mech_Med | Labor | EMCY_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EMCY_H_FY20_EIC | Engineer Cryo Mech_High | Labor | EMCY_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TECY_L_FY20_EIC | Tech Cryo Elec_Low | Labor | TECY_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TECY_M_FY20_EIC | Tech Cryo Elec_Med | Labor | TECY_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TECY_H_FY20_EIC | Tech Cryo Elec_High | Labor | TECY_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
TMCY_L_FY20_EIC | Tech Cryo Mech_Low | Labor | TMCY_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TMCY_M_FY20_EIC | Tech Cryo Mech_Med | Labor | TMCY_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TMCY_H_FY20_EIC | Tech Cryo Mech_High | Labor | TMCY_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
EEIN_L_FY20_EIC | Engineer Instrum Elec_Low | Labor | EEIN_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EEIN_M_FY20_EIC | Engineer Instrum Elec_Med | Labor | EEIN_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
EEIN_H_FY20_EIC | Engineer Instrum Elec_High | Labor | EEIN_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TEIN_L_FY20_EIC | Tech Instrum Elec_Low | Labor | TEIN_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TEIN_M_FY20_EIC | Tech Instrum Elec_Med | Labor | TEIN_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TEIN_H_FY20_EIC | Tech Instrum Elec_High | Labor | TEIN_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
EMIN_L_FY20_EIC | Engineer Instrum Mech_Low | Labor | EMIN_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EMIN_M_FY20_EIC | Engineer Instrum Mech_Med | Labor | EMIN_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
EMIN_H_FY20_EIC | Engineer Instrum Mech_High | Labor | EMIN_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TMIN_L_FY20_EIC | Tech Instrum Mech_Low | Labor | TMIN_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TMIN_M_FY20_EIC | Tech Instrum Mech_Med | Labor | TMIN_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TMIN_H_FY20_EIC | Tech Instrum Mech_High | Labor | TMIN_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
FE_L_FY20_EIC | Engineer Facility_Low | Labor | FE_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
FE_M_FY20_EIC | Engineer Facility_Med | Labor | FE_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
FE_H_FY20_EIC | Engineer Facility_High | Labor | FE_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
FT_L_FY20_EIC | Tech Facility_Low | Labor | FT_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
FT_M_FY20_EIC | Tech Facility_Med | Labor | FT_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
FT_H_FY20_EIC | Tech Facility_High | Labor | FT_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 122.6182; EIC FY20 LDRD FY20: 126.9098; EIC FY20 LDRD FY21: 133.9645; EIC FY20 LDRD FY22: 138.0627; EIC FY20 LDRD FY23: 142.8949; EIC FY20 LDRD FY24: 147.8962; EIC FY20 LDRD FY25: 153.0726; EIC FY20 LDRD FY26: 158.4301; EIC FY20 LDRD FY27: 163.9752; EIC FY20 LDRD FY28: 169.7143; EIC FY20 LDRD FY29: 175.6543; EIC FY20 LDRD FY30: 181.8022; EIC FY20 LDRD FY31: 188.1653; EIC FY20 LDRD FY32: 194.7511; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 119.5109; EIC FY20 FY20: 123.6938; EIC FY20 FY21: 130.5697; EIC FY20 FY22: 134.5641; EIC FY20 FY23: 139.2738; EIC FY20 FY24: 144.1484; EIC FY20 FY25: 149.1936; EIC FY20 FY26: 154.4154; EIC FY20 FY27: 159.8199; EIC FY20 FY28: 165.4136; EIC FY20 FY29: 171.2031; EIC FY20 FY30: 177.1952; EIC FY20 FY31: 183.397; EIC FY20 FY32: 189.8159
ECS_R_FY20_EIC | Engineering Construction Services _RC | Labor | ECS_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 184.659; EIC FY20 LDRD FY20: 191.1221; EIC FY20 LDRD FY21: 201.7461; EIC FY20 LDRD FY22: 207.9179; EIC FY20 LDRD FY23: 215.1951; EIC FY20 LDRD FY24: 222.7269; EIC FY20 LDRD FY25: 230.5223; EIC FY20 LDRD FY26: 238.5906; EIC FY20 LDRD FY27: 246.9413; EIC FY20 LDRD FY28: 255.5842; EIC FY20 LDRD FY29: 264.5297; EIC FY20 LDRD FY30: 273.7882; EIC FY20 LDRD FY31: 283.3708; EIC FY20 LDRD FY32: 293.2888; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 179.9795; EIC FY20 FY20: 186.2788; EIC FY20 FY21: 196.6337; EIC FY20 FY22: 202.6491; EIC FY20 FY23: 209.7418; EIC FY20 FY24: 217.0828; EIC FY20 FY25: 224.6807; EIC FY20 FY26: 232.5445; EIC FY20 FY27: 240.6835; EIC FY20 FY28: 249.1075; EIC FY20 FY29: 257.8262; EIC FY20 FY30: 266.8501; EIC FY20 FY31: 276.1899; EIC FY20 FY32: 285.8565
EMAG_L_FY20_EIC | Engineer Magnet_Low | Labor | EMAG_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EMAG_M_FY20_EIC | Engineer Magnet_Med | Labor | EMAG_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
EMAG_H_FY20_EIC | Engineer Magnet_High | Labor | EMAG_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TMAG_L_FY20_EIC | Tech Magnet_Low | Labor | TMAG_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TMAG_M_FY20_EIC | Tech Magnet_Med | Labor | TMAG_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TMAG_H_FY20_EIC | Tech Magnet_High | Labor | TMAG_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
EPS_L_FY20_EIC | Engineer Power Supply_Low | Labor | EPS_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EPS_M_FY20_EIC | Engineer Power Supply_Med | Labor | EPS_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
EPS_H_FY20_EIC | Engineer Power Supply_High | Labor | EPS_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TPS_L_FY20_EIC | Tech Power Supply_Low | Labor | TPS_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TPS_M_FY20_EIC | Tech Power Supply_Med | Labor | TPS_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TPS_H_FY20_EIC | Tech Power Supply_High | Labor | TPS_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
ERF_L_FY20_EIC | Engineer RF-SRF_Low | Labor | ERF_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
ERF_M_FY20_EIC | Engineer RF-SRF_Med | Labor | ERF_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
ERF_H_FY20_EIC | Engineer RF-SRF_High | Labor | ERF_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TRF_L_FY20_EIC | Tech RF-SRF_Low | Labor | TRF_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TRF_M_FY20_EIC | Tech RF-SRF_Med | Labor | TRF_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TRF_H_FY20_EIC | Tech RF-SRF_High | Labor | TRF_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
SE_L_FY20_EIC | Engineer Survey_Low | Labor | SE_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
SE_M_FY20_EIC | Engineer Survey_Med | Labor | SE_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
SE_H_FY20_EIC | Engineer Survey_High | Labor | SE_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
ST_L_FY20_EIC | Tech Survey_Low | Labor | ST_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
ST_M_FY20_EIC | Tech Survey_Med | Labor | ST_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
ST_H_FY20_EIC | Tech Survey_High | Labor | ST_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 122.6182; EIC FY20 LDRD FY20: 126.9098; EIC FY20 LDRD FY21: 133.9645; EIC FY20 LDRD FY22: 138.0627; EIC FY20 LDRD FY23: 142.8949; EIC FY20 LDRD FY24: 147.8962; EIC FY20 LDRD FY25: 153.0726; EIC FY20 LDRD FY26: 158.4301; EIC FY20 LDRD FY27: 163.9752; EIC FY20 LDRD FY28: 169.7143; EIC FY20 LDRD FY29: 175.6543; EIC FY20 LDRD FY30: 181.8022; EIC FY20 LDRD FY31: 188.1653; EIC FY20 LDRD FY32: 194.7511; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 119.5109; EIC FY20 FY20: 123.6938; EIC FY20 FY21: 130.5697; EIC FY20 FY22: 134.5641; EIC FY20 FY23: 139.2738; EIC FY20 FY24: 144.1484; EIC FY20 FY25: 149.1936; EIC FY20 FY26: 154.4154; EIC FY20 FY27: 159.8199; EIC FY20 FY28: 165.4136; EIC FY20 FY29: 171.2031; EIC FY20 FY30: 177.1952; EIC FY20 FY31: 183.397; EIC FY20 FY32: 189.8159
CBLPULL_FY20_EIC | Cable Pullers | Labor | CBLPULL_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
EEVC_L_FY20_EIC | Engineer Vacuum Elec_Low | Labor | EEVC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EEVC_M_FY20_EIC | Engineer Vacuum Elec_Med | Labor | EEVC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
EEVC_H_FY20_EIC | Engineer Vacuum Elec_High | Labor | EEVC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TEVC_L_FY20_EIC | Tech Vacuum Elec_Low | Labor | TEVC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TEVC_M_FY20_EIC | Tech Vacuum Elec_Med | Labor | TEVC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TEVC_H_FY20_EIC | Tech Vacuum Elec_High | Labor | TEVC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
EMVC_L_FY20_EIC | Engineer Vacuum Mech_Low | Labor | EMVC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EMVC_M_FY20_EIC | Engineer Vacuum Mech_Med | Labor | EMVC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
EMVC_H_FY20_EIC | Engineer Vacuum Mech_High | Labor | EMVC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
TMVC_L_FY20_EIC | Tech Vacuum Mech_Low | Labor | TMVC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
TMVC_M_FY20_EIC | Tech Vacuum Mech_Med | Labor | TMVC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
TMVC_H_FY20_EIC | Tech Vacuum Mech_High | Labor | TMVC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
EE_L_FY20_EIC | Engineer Electrical_Low | Labor | EE_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EE_M_FY20_EIC | Engineer Electrical_Med | Labor | EE_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
EE_H_FY20_EIC | Engineer Electrical_High | Labor | EE_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
ET_L_FY20_EIC | Tech Electrical_Low | Labor | ET_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
ET_M_FY20_EIC | Tech Electrical_Med | Labor | ET_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
ET_H_FY20_EIC | Tech Electrical_High | Labor | ET_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
ME_L_FY20_EIC | Engineer Mechanical_Low | Labor | ME_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
ME_M_FY20_EIC | Engineer Mechanical_Med | Labor | ME_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
ME_H_FY20_EIC | Engineer Mechanical_High | Labor | ME_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
MT_L_FY20_EIC | Tech Mechanical_Low | Labor | MT_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
MT_M_FY20_EIC | Tech Mechanical_Med | Labor | MT_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
MT_H_FY20_EIC | Tech Mechanical_High | Labor | MT_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
DMGMT_L_FY20_EIC | Division Manager_Low | Labor | DMGMT_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 320.4298; EIC FY20 LDRD FY20: 331.6448; EIC FY20 LDRD FY21: 350.0803; EIC FY20 LDRD FY22: 360.7899; EIC FY20 LDRD FY23: 373.4176; EIC FY20 LDRD FY24: 386.4872; EIC FY20 LDRD FY25: 400.0142; EIC FY20 LDRD FY26: 414.0147; EIC FY20 LDRD FY27: 428.5052; EIC FY20 LDRD FY28: 443.5029; EIC FY20 LDRD FY29: 459.0255; EIC FY20 LDRD FY30: 475.0914; EIC FY20 LDRD FY31: 491.7196; EIC FY20 LDRD FY32: 508.9298; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 312.3098; EIC FY20 FY20: 323.2406; EIC FY20 FY21: 341.2089; EIC FY20 FY22: 351.6471; EIC FY20 FY23: 363.9548; EIC FY20 FY24: 376.6932; EIC FY20 FY25: 389.8775; EIC FY20 FY26: 403.5232; EIC FY20 FY27: 417.6465; EIC FY20 FY28: 432.2641; EIC FY20 FY29: 447.3934; EIC FY20 FY30: 463.0521; EIC FY20 FY31: 479.2589; EIC FY20 FY32: 496.033
DMGMT_M_FY20_EIC | Division Manager_Med | Labor | DMGMT_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 372.0514; EIC FY20 LDRD FY20: 385.0732; EIC FY20 LDRD FY21: 406.4786; EIC FY20 LDRD FY22: 418.9136; EIC FY20 LDRD FY23: 433.5755; EIC FY20 LDRD FY24: 448.7507; EIC FY20 LDRD FY25: 464.457; EIC FY20 LDRD FY26: 480.7129; EIC FY20 LDRD FY27: 497.5379; EIC FY20 LDRD FY28: 514.9517; EIC FY20 LDRD FY29: 532.975; EIC FY20 LDRD FY30: 551.6292; EIC FY20 LDRD FY31: 570.9362; EIC FY20 LDRD FY32: 590.9189; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 362.6232; EIC FY20 FY20: 375.315; EIC FY20 FY21: 396.178; EIC FY20 FY22: 408.2979; EIC FY20 FY23: 422.5883; EIC FY20 FY24: 437.3789; EIC FY20 FY25: 452.6872; EIC FY20 FY26: 468.5312; EIC FY20 FY27: 484.9298; EIC FY20 FY28: 501.9023; EIC FY20 FY29: 519.4689; EIC FY20 FY30: 537.6503; EIC FY20 FY31: 556.4681; EIC FY20 FY32: 575.9445
DMGMT_H_FY20_EIC | Division Manager_High | Labor | DMGMT_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 466.8723; EIC FY20 LDRD FY20: 483.2129; EIC FY20 LDRD FY21: 510.0736; EIC FY20 LDRD FY22: 525.6778; EIC FY20 LDRD FY23: 544.0765; EIC FY20 LDRD FY24: 563.1192; EIC FY20 LDRD FY25: 582.8283; EIC FY20 LDRD FY26: 603.2273; EIC FY20 LDRD FY27: 624.3403; EIC FY20 LDRD FY28: 646.1922; EIC FY20 LDRD FY29: 668.8089; EIC FY20 LDRD FY30: 692.2172; EIC FY20 LDRD FY31: 716.4449; EIC FY20 LDRD FY32: 741.5204; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 455.0413; EIC FY20 FY20: 470.9677; EIC FY20 FY21: 497.1478; EIC FY20 FY22: 512.3566; EIC FY20 FY23: 530.2891; EIC FY20 FY24: 548.8492; EIC FY20 FY25: 568.0589; EIC FY20 FY26: 587.941; EIC FY20 FY27: 608.5189; EIC FY20 FY28: 629.8171; EIC FY20 FY29: 651.8607; EIC FY20 FY30: 674.6758; EIC FY20 FY31: 698.2894; EIC FY20 FY32: 722.7296
MGMT_L_FY20_EIC | Group Manager_Low | Labor | MGMT_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
MGMT_M_FY20_EIC | Group Manager_Med | Labor | MGMT_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
MGMT_H_FY20_EIC | Group Manager_High | Labor | MGMT_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 189.0297; EIC FY20 LDRD FY20: 195.6457; EIC FY20 LDRD FY21: 206.5212; EIC FY20 LDRD FY22: 212.8391; EIC FY20 LDRD FY23: 220.2885; EIC FY20 LDRD FY24: 227.9986; EIC FY20 LDRD FY25: 235.9785; EIC FY20 LDRD FY26: 244.2378; EIC FY20 LDRD FY27: 252.7861; EIC FY20 LDRD FY28: 261.6336; EIC FY20 LDRD FY29: 270.7908; EIC FY20 LDRD FY30: 280.2685; EIC FY20 LDRD FY31: 290.0779; EIC FY20 LDRD FY32: 300.2306; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 184.2395; EIC FY20 FY20: 190.6878; EIC FY20 FY21: 201.2878; EIC FY20 FY22: 207.4456; EIC FY20 FY23: 214.7062; EIC FY20 FY24: 222.2209; EIC FY20 FY25: 229.9986; EIC FY20 FY26: 238.0486; EIC FY20 FY27: 246.3803; EIC FY20 FY28: 255.0036; EIC FY20 FY29: 263.9287; EIC FY20 FY30: 273.1662; EIC FY20 FY31: 282.727; EIC FY20 FY32: 292.6225
MGMTSCI_H_FY20_EIC | Manager-Scientist_High | Labor | MGMTSCI_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 255.5751; EIC FY20 LDRD FY20: 264.5202; EIC FY20 LDRD FY21: 279.2244; EIC FY20 LDRD FY22: 287.7664; EIC FY20 LDRD FY23: 297.8382; EIC FY20 LDRD FY24: 308.2625; EIC FY20 LDRD FY25: 319.0517; EIC FY20 LDRD FY26: 330.2185; EIC FY20 LDRD FY27: 341.7762; EIC FY20 LDRD FY28: 353.7384; EIC FY20 LDRD FY29: 366.1192; EIC FY20 LDRD FY30: 378.9334; EIC FY20 LDRD FY31: 392.196; EIC FY20 LDRD FY32: 405.9229; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 249.0986; EIC FY20 FY20: 257.817; EIC FY20 FY21: 272.1485; EIC FY20 FY22: 280.4741; EIC FY20 FY23: 290.2907; EIC FY20 FY24: 300.4509; EIC FY20 FY25: 310.9666; EIC FY20 FY26: 321.8505; EIC FY20 FY27: 333.1152; EIC FY20 FY28: 344.7743; EIC FY20 FY29: 356.8414; EIC FY20 FY30: 369.3308; EIC FY20 FY31: 382.2574; EIC FY20 FY32: 395.6364
PHYMGR_H_FY20_EIC | Physicist Manager_High | Labor | PHYMGR_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 255.5751; EIC FY20 LDRD FY20: 264.5202; EIC FY20 LDRD FY21: 279.2244; EIC FY20 LDRD FY22: 287.7664; EIC FY20 LDRD FY23: 297.8382; EIC FY20 LDRD FY24: 308.2625; EIC FY20 LDRD FY25: 319.0517; EIC FY20 LDRD FY26: 330.2185; EIC FY20 LDRD FY27: 341.7762; EIC FY20 LDRD FY28: 353.7384; EIC FY20 LDRD FY29: 366.1192; EIC FY20 LDRD FY30: 378.9334; EIC FY20 LDRD FY31: 392.196; EIC FY20 LDRD FY32: 405.9229; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 249.0986; EIC FY20 FY20: 257.817; EIC FY20 FY21: 272.1485; EIC FY20 FY22: 280.4741; EIC FY20 FY23: 290.2907; EIC FY20 FY24: 300.4509; EIC FY20 FY25: 310.9666; EIC FY20 FY26: 321.8505; EIC FY20 FY27: 333.1152; EIC FY20 FY28: 344.7743; EIC FY20 FY29: 356.8414; EIC FY20 FY30: 369.3308; EIC FY20 FY31: 382.2574; EIC FY20 FY32: 395.6364
ADMN_L_FY20_EIC | Administrative_Low | Labor | ADMN_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 70.8946; EIC FY20 LDRD FY20: 73.3759; EIC FY20 LDRD FY21: 77.4548; EIC FY20 LDRD FY22: 79.8242; EIC FY20 LDRD FY23: 82.6181; EIC FY20 LDRD FY24: 85.5097; EIC FY20 LDRD FY25: 88.5026; EIC FY20 LDRD FY26: 91.6002; EIC FY20 LDRD FY27: 94.8062; EIC FY20 LDRD FY28: 98.1244; EIC FY20 LDRD FY29: 101.5587; EIC FY20 LDRD FY30: 105.1133; EIC FY20 LDRD FY31: 108.7923; EIC FY20 LDRD FY32: 112.6; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 69.0981; EIC FY20 FY20: 71.5165; EIC FY20 FY21: 75.492; EIC FY20 FY22: 77.8014; EIC FY20 FY23: 80.5245; EIC FY20 FY24: 83.3428; EIC FY20 FY25: 86.2598; EIC FY20 FY26: 89.2789; EIC FY20 FY27: 92.4037; EIC FY20 FY28: 95.6378; EIC FY20 FY29: 98.9851; EIC FY20 FY30: 102.4496; EIC FY20 FY31: 106.0354; EIC FY20 FY32: 109.7466
ADMN_M_FY20_EIC | Administrative_Med | Labor | ADMN_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 85.078; EIC FY20 LDRD FY20: 88.0557; EIC FY20 LDRD FY21: 92.9505; EIC FY20 LDRD FY22: 95.794; EIC FY20 LDRD FY23: 99.1468; EIC FY20 LDRD FY24: 102.617; EIC FY20 LDRD FY25: 106.2086; EIC FY20 LDRD FY26: 109.9259; EIC FY20 LDRD FY27: 113.7733; EIC FY20 LDRD FY28: 117.7553; EIC FY20 LDRD FY29: 121.8768; EIC FY20 LDRD FY30: 126.1425; EIC FY20 LDRD FY31: 130.5574; EIC FY20 LDRD FY32: 135.127; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 82.922; EIC FY20 FY20: 85.8243; EIC FY20 FY21: 90.595; EIC FY20 FY22: 93.3665; EIC FY20 FY23: 96.6344; EIC FY20 FY24: 100.0166; EIC FY20 FY25: 103.5171; EIC FY20 FY26: 107.1402; EIC FY20 FY27: 110.8901; EIC FY20 FY28: 114.7713; EIC FY20 FY29: 118.7883; EIC FY20 FY30: 122.9459; EIC FY20 FY31: 127.249; EIC FY20 FY32: 131.7027
ADMN_H_FY20_EIC | Administrative_High | Labor | ADMN_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 125.5077; EIC FY20 LDRD FY20: 129.9005; EIC FY20 LDRD FY21: 137.1213; EIC FY20 LDRD FY22: 141.3162; EIC FY20 LDRD FY23: 146.2622; EIC FY20 LDRD FY24: 151.3814; EIC FY20 LDRD FY25: 156.6797; EIC FY20 LDRD FY26: 162.1635; EIC FY20 LDRD FY27: 167.8393; EIC FY20 LDRD FY28: 173.7136; EIC FY20 LDRD FY29: 179.7936; EIC FY20 LDRD FY30: 186.0864; EIC FY20 LDRD FY31: 192.5994; EIC FY20 LDRD FY32: 199.3404; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 122.3272; EIC FY20 FY20: 126.6086; EIC FY20 FY21: 133.6465; EIC FY20 FY22: 137.7351; EIC FY20 FY23: 142.5558; EIC FY20 FY24: 147.5452; EIC FY20 FY25: 152.7093; EIC FY20 FY26: 158.0541; EIC FY20 FY27: 163.586; EIC FY20 FY28: 169.3116; EIC FY20 FY29: 175.2375; EIC FY20 FY30: 181.3708; EIC FY20 FY31: 187.7187; EIC FY20 FY32: 194.2889
BUSOP_L_FY20_EIC | Business Ops_Low | Labor | BUSOP_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 85.078; EIC FY20 LDRD FY20: 88.0557; EIC FY20 LDRD FY21: 92.9505; EIC FY20 LDRD FY22: 95.794; EIC FY20 LDRD FY23: 99.1468; EIC FY20 LDRD FY24: 102.617; EIC FY20 LDRD FY25: 106.2086; EIC FY20 LDRD FY26: 109.9259; EIC FY20 LDRD FY27: 113.7733; EIC FY20 LDRD FY28: 117.7553; EIC FY20 LDRD FY29: 121.8768; EIC FY20 LDRD FY30: 126.1425; EIC FY20 LDRD FY31: 130.5574; EIC FY20 LDRD FY32: 135.127; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 82.922; EIC FY20 FY20: 85.8243; EIC FY20 FY21: 90.595; EIC FY20 FY22: 93.3665; EIC FY20 FY23: 96.6344; EIC FY20 FY24: 100.0166; EIC FY20 FY25: 103.5171; EIC FY20 FY26: 107.1402; EIC FY20 FY27: 110.8901; EIC FY20 FY28: 114.7713; EIC FY20 FY29: 118.7883; EIC FY20 FY30: 122.9459; EIC FY20 FY31: 127.249; EIC FY20 FY32: 131.7027
BUSOP_M_FY20_EIC | Business Ops_Med | Labor | BUSOP_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 125.5077; EIC FY20 LDRD FY20: 129.9005; EIC FY20 LDRD FY21: 137.1213; EIC FY20 LDRD FY22: 141.3162; EIC FY20 LDRD FY23: 146.2622; EIC FY20 LDRD FY24: 151.3814; EIC FY20 LDRD FY25: 156.6797; EIC FY20 LDRD FY26: 162.1635; EIC FY20 LDRD FY27: 167.8393; EIC FY20 LDRD FY28: 173.7136; EIC FY20 LDRD FY29: 179.7936; EIC FY20 LDRD FY30: 186.0864; EIC FY20 LDRD FY31: 192.5994; EIC FY20 LDRD FY32: 199.3404; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 122.3272; EIC FY20 FY20: 126.6086; EIC FY20 FY21: 133.6465; EIC FY20 FY22: 137.7351; EIC FY20 FY23: 142.5558; EIC FY20 FY24: 147.5452; EIC FY20 FY25: 152.7093; EIC FY20 FY26: 158.0541; EIC FY20 FY27: 163.586; EIC FY20 FY28: 169.3116; EIC FY20 FY29: 175.2375; EIC FY20 FY30: 181.3708; EIC FY20 FY31: 187.7187; EIC FY20 FY32: 194.2889
BUSOP_H_FY20_EIC | Business Ops_High | Labor | BUSOP_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 221.6939; EIC FY20 LDRD FY20: 229.4532; EIC FY20 LDRD FY21: 242.208; EIC FY20 LDRD FY22: 249.6176; EIC FY20 LDRD FY23: 258.3543; EIC FY20 LDRD FY24: 267.3967; EIC FY20 LDRD FY25: 276.7555; EIC FY20 LDRD FY26: 286.442; EIC FY20 LDRD FY27: 296.4674; EIC FY20 LDRD FY28: 306.8438; EIC FY20 LDRD FY29: 317.5833; EIC FY20 LDRD FY30: 328.6988; EIC FY20 LDRD FY31: 340.2032; EIC FY20 LDRD FY32: 352.1103; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 216.076; EIC FY20 FY20: 223.6386; EIC FY20 FY21: 236.0702; EIC FY20 FY22: 243.2921; EIC FY20 FY23: 251.8073; EIC FY20 FY24: 260.6206; EIC FY20 FY25: 269.7423; EIC FY20 FY26: 279.1833; EIC FY20 FY27: 288.9547; EIC FY20 FY28: 299.0681; EIC FY20 FY29: 309.5355; EIC FY20 FY30: 320.3692; EIC FY20 FY31: 331.5821; EIC FY20 FY32: 343.1875
HR_L_FY20_EIC | Human Resources_Low | Labor | HR_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 85.078; EIC FY20 LDRD FY20: 88.0557; EIC FY20 LDRD FY21: 92.9505; EIC FY20 LDRD FY22: 95.794; EIC FY20 LDRD FY23: 99.1468; EIC FY20 LDRD FY24: 102.617; EIC FY20 LDRD FY25: 106.2086; EIC FY20 LDRD FY26: 109.9259; EIC FY20 LDRD FY27: 113.7733; EIC FY20 LDRD FY28: 117.7553; EIC FY20 LDRD FY29: 121.8768; EIC FY20 LDRD FY30: 126.1425; EIC FY20 LDRD FY31: 130.5574; EIC FY20 LDRD FY32: 135.127; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 82.922; EIC FY20 FY20: 85.8243; EIC FY20 FY21: 90.595; EIC FY20 FY22: 93.3665; EIC FY20 FY23: 96.6344; EIC FY20 FY24: 100.0166; EIC FY20 FY25: 103.5171; EIC FY20 FY26: 107.1402; EIC FY20 FY27: 110.8901; EIC FY20 FY28: 114.7713; EIC FY20 FY29: 118.7883; EIC FY20 FY30: 122.9459; EIC FY20 FY31: 127.249; EIC FY20 FY32: 131.7027
HR_M_FY20_EIC | Human Resources_Med | Labor | HR_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 125.5077; EIC FY20 LDRD FY20: 129.9005; EIC FY20 LDRD FY21: 137.1213; EIC FY20 LDRD FY22: 141.3162; EIC FY20 LDRD FY23: 146.2622; EIC FY20 LDRD FY24: 151.3814; EIC FY20 LDRD FY25: 156.6797; EIC FY20 LDRD FY26: 162.1635; EIC FY20 LDRD FY27: 167.8393; EIC FY20 LDRD FY28: 173.7136; EIC FY20 LDRD FY29: 179.7936; EIC FY20 LDRD FY30: 186.0864; EIC FY20 LDRD FY31: 192.5994; EIC FY20 LDRD FY32: 199.3404; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 122.3272; EIC FY20 FY20: 126.6086; EIC FY20 FY21: 133.6465; EIC FY20 FY22: 137.7351; EIC FY20 FY23: 142.5558; EIC FY20 FY24: 147.5452; EIC FY20 FY25: 152.7093; EIC FY20 FY26: 158.0541; EIC FY20 FY27: 163.586; EIC FY20 FY28: 169.3116; EIC FY20 FY29: 175.2375; EIC FY20 FY30: 181.3708; EIC FY20 FY31: 187.7187; EIC FY20 FY32: 194.2889
HR_H_FY20_EIC | Human Resources_High | Labor | HR_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 221.6939; EIC FY20 LDRD FY20: 229.4532; EIC FY20 LDRD FY21: 242.208; EIC FY20 LDRD FY22: 249.6176; EIC FY20 LDRD FY23: 258.3543; EIC FY20 LDRD FY24: 267.3967; EIC FY20 LDRD FY25: 276.7555; EIC FY20 LDRD FY26: 286.442; EIC FY20 LDRD FY27: 296.4674; EIC FY20 LDRD FY28: 306.8438; EIC FY20 LDRD FY29: 317.5833; EIC FY20 LDRD FY30: 328.6988; EIC FY20 LDRD FY31: 340.2032; EIC FY20 LDRD FY32: 352.1103; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 216.076; EIC FY20 FY20: 223.6386; EIC FY20 FY21: 236.0702; EIC FY20 FY22: 243.2921; EIC FY20 FY23: 251.8073; EIC FY20 FY24: 260.6206; EIC FY20 FY25: 269.7423; EIC FY20 FY26: 279.1833; EIC FY20 FY27: 288.9547; EIC FY20 FY28: 299.0681; EIC FY20 FY29: 309.5355; EIC FY20 FY30: 320.3692; EIC FY20 FY31: 331.5821; EIC FY20 FY32: 343.1875
ITNET_L_FY20_EIC | IT Professional (Network-Bus Support)_Low | Labor | ITNET_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
ITNET_M_FY20_EIC | IT Professional (Network-Bus Support)_Med | Labor | ITNET_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
ITNET_H_FY20_EIC | IT Professional (Network-Bus Support)_High | Labor | ITNET_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 189.0297; EIC FY20 LDRD FY20: 195.6457; EIC FY20 LDRD FY21: 206.5212; EIC FY20 LDRD FY22: 212.8391; EIC FY20 LDRD FY23: 220.2885; EIC FY20 LDRD FY24: 227.9986; EIC FY20 LDRD FY25: 235.9785; EIC FY20 LDRD FY26: 244.2378; EIC FY20 LDRD FY27: 252.7861; EIC FY20 LDRD FY28: 261.6336; EIC FY20 LDRD FY29: 270.7908; EIC FY20 LDRD FY30: 280.2685; EIC FY20 LDRD FY31: 290.0779; EIC FY20 LDRD FY32: 300.2306; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 184.2395; EIC FY20 FY20: 190.6878; EIC FY20 FY21: 201.2878; EIC FY20 FY22: 207.4456; EIC FY20 FY23: 214.7062; EIC FY20 FY24: 222.2209; EIC FY20 FY25: 229.9986; EIC FY20 FY26: 238.0486; EIC FY20 FY27: 246.3803; EIC FY20 FY28: 255.0036; EIC FY20 FY29: 263.9287; EIC FY20 FY30: 273.1662; EIC FY20 FY31: 282.727; EIC FY20 FY32: 292.6225
PROC_L_FY20_EIC | Procurement_Low | Labor | PROC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 85.078; EIC FY20 LDRD FY20: 88.0557; EIC FY20 LDRD FY21: 92.9505; EIC FY20 LDRD FY22: 95.794; EIC FY20 LDRD FY23: 99.1468; EIC FY20 LDRD FY24: 102.617; EIC FY20 LDRD FY25: 106.2086; EIC FY20 LDRD FY26: 109.9259; EIC FY20 LDRD FY27: 113.7733; EIC FY20 LDRD FY28: 117.7553; EIC FY20 LDRD FY29: 121.8768; EIC FY20 LDRD FY30: 126.1425; EIC FY20 LDRD FY31: 130.5574; EIC FY20 LDRD FY32: 135.127; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 82.922; EIC FY20 FY20: 85.8243; EIC FY20 FY21: 90.595; EIC FY20 FY22: 93.3665; EIC FY20 FY23: 96.6344; EIC FY20 FY24: 100.0166; EIC FY20 FY25: 103.5171; EIC FY20 FY26: 107.1402; EIC FY20 FY27: 110.8901; EIC FY20 FY28: 114.7713; EIC FY20 FY29: 118.7883; EIC FY20 FY30: 122.9459; EIC FY20 FY31: 127.249; EIC FY20 FY32: 131.7027
PROC_M_FY20_EIC | Procurement_Med | Labor | PROC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 125.5077; EIC FY20 LDRD FY20: 129.9005; EIC FY20 LDRD FY21: 137.1213; EIC FY20 LDRD FY22: 141.3162; EIC FY20 LDRD FY23: 146.2622; EIC FY20 LDRD FY24: 151.3814; EIC FY20 LDRD FY25: 156.6797; EIC FY20 LDRD FY26: 162.1635; EIC FY20 LDRD FY27: 167.8393; EIC FY20 LDRD FY28: 173.7136; EIC FY20 LDRD FY29: 179.7936; EIC FY20 LDRD FY30: 186.0864; EIC FY20 LDRD FY31: 192.5994; EIC FY20 LDRD FY32: 199.3404; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 122.3272; EIC FY20 FY20: 126.6086; EIC FY20 FY21: 133.6465; EIC FY20 FY22: 137.7351; EIC FY20 FY23: 142.5558; EIC FY20 FY24: 147.5452; EIC FY20 FY25: 152.7093; EIC FY20 FY26: 158.0541; EIC FY20 FY27: 163.586; EIC FY20 FY28: 169.3116; EIC FY20 FY29: 175.2375; EIC FY20 FY30: 181.3708; EIC FY20 FY31: 187.7187; EIC FY20 FY32: 194.2889
PROC_H_FY20_EIC | Procurement_High | Labor | PROC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 166.0196; EIC FY20 LDRD FY20: 171.8303; EIC FY20 LDRD FY21: 181.382; EIC FY20 LDRD FY22: 186.9308; EIC FY20 LDRD FY23: 193.4734; EIC FY20 LDRD FY24: 200.245; EIC FY20 LDRD FY25: 207.2536; EIC FY20 LDRD FY26: 214.5074; EIC FY20 LDRD FY27: 222.0152; EIC FY20 LDRD FY28: 229.7857; EIC FY20 LDRD FY29: 237.8282; EIC FY20 LDRD FY30: 246.1522; EIC FY20 LDRD FY31: 254.7675; EIC FY20 LDRD FY32: 263.6844; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 161.8125; EIC FY20 FY20: 167.476; EIC FY20 FY21: 176.7856; EIC FY20 FY22: 182.1938; EIC FY20 FY23: 188.5706; EIC FY20 FY24: 195.1706; EIC FY20 FY25: 202.0015; EIC FY20 FY26: 209.0716; EIC FY20 FY27: 216.3891; EIC FY20 FY28: 223.9627; EIC FY20 FY29: 231.8014; EIC FY20 FY30: 239.9145; EIC FY20 FY31: 248.3115; EIC FY20 FY32: 257.0024
PC_L_FY20_EIC | Project Controls_Low | Labor | PC_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 85.078; EIC FY20 LDRD FY20: 88.0557; EIC FY20 LDRD FY21: 92.9505; EIC FY20 LDRD FY22: 95.794; EIC FY20 LDRD FY23: 99.1468; EIC FY20 LDRD FY24: 102.617; EIC FY20 LDRD FY25: 106.2086; EIC FY20 LDRD FY26: 109.9259; EIC FY20 LDRD FY27: 113.7733; EIC FY20 LDRD FY28: 117.7553; EIC FY20 LDRD FY29: 121.8768; EIC FY20 LDRD FY30: 126.1425; EIC FY20 LDRD FY31: 130.5574; EIC FY20 LDRD FY32: 135.127; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 82.922; EIC FY20 FY20: 85.8243; EIC FY20 FY21: 90.595; EIC FY20 FY22: 93.3665; EIC FY20 FY23: 96.6344; EIC FY20 FY24: 100.0166; EIC FY20 FY25: 103.5171; EIC FY20 FY26: 107.1402; EIC FY20 FY27: 110.8901; EIC FY20 FY28: 114.7713; EIC FY20 FY29: 118.7883; EIC FY20 FY30: 122.9459; EIC FY20 FY31: 127.249; EIC FY20 FY32: 131.7027
PC_M_FY20_EIC | Project Controls_Med | Labor | PC_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 125.5077; EIC FY20 LDRD FY20: 129.9005; EIC FY20 LDRD FY21: 137.1213; EIC FY20 LDRD FY22: 141.3162; EIC FY20 LDRD FY23: 146.2622; EIC FY20 LDRD FY24: 151.3814; EIC FY20 LDRD FY25: 156.6797; EIC FY20 LDRD FY26: 162.1635; EIC FY20 LDRD FY27: 167.8393; EIC FY20 LDRD FY28: 173.7136; EIC FY20 LDRD FY29: 179.7936; EIC FY20 LDRD FY30: 186.0864; EIC FY20 LDRD FY31: 192.5994; EIC FY20 LDRD FY32: 199.3404; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 122.3272; EIC FY20 FY20: 126.6086; EIC FY20 FY21: 133.6465; EIC FY20 FY22: 137.7351; EIC FY20 FY23: 142.5558; EIC FY20 FY24: 147.5452; EIC FY20 FY25: 152.7093; EIC FY20 FY26: 158.0541; EIC FY20 FY27: 163.586; EIC FY20 FY28: 169.3116; EIC FY20 FY29: 175.2375; EIC FY20 FY30: 181.3708; EIC FY20 FY31: 187.7187; EIC FY20 FY32: 194.2889
PC_H_FY20_EIC | Project Controls_High | Labor | PC_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 166.0196; EIC FY20 LDRD FY20: 171.8303; EIC FY20 LDRD FY21: 181.382; EIC FY20 LDRD FY22: 186.9308; EIC FY20 LDRD FY23: 193.4734; EIC FY20 LDRD FY24: 200.245; EIC FY20 LDRD FY25: 207.2536; EIC FY20 LDRD FY26: 214.5074; EIC FY20 LDRD FY27: 222.0152; EIC FY20 LDRD FY28: 229.7857; EIC FY20 LDRD FY29: 237.8282; EIC FY20 LDRD FY30: 246.1522; EIC FY20 LDRD FY31: 254.7675; EIC FY20 LDRD FY32: 263.6844; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 161.8125; EIC FY20 FY20: 167.476; EIC FY20 FY21: 176.7856; EIC FY20 FY22: 182.1938; EIC FY20 FY23: 188.5706; EIC FY20 FY24: 195.1706; EIC FY20 FY25: 202.0015; EIC FY20 FY26: 209.0716; EIC FY20 FY27: 216.3891; EIC FY20 FY28: 223.9627; EIC FY20 FY29: 231.8014; EIC FY20 FY30: 239.9145; EIC FY20 FY31: 248.3115; EIC FY20 FY32: 257.0024
PROJ_R_FY20_EIC | Project Management Specialist_RC | Labor | PROJ_R_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 159.6805; EIC FY20 LDRD FY20: 165.2693; EIC FY20 LDRD FY21: 174.4563; EIC FY20 LDRD FY22: 179.7932; EIC FY20 LDRD FY23: 186.086; EIC FY20 LDRD FY24: 192.599; EIC FY20 LDRD FY25: 199.34; EIC FY20 LDRD FY26: 206.3169; EIC FY20 LDRD FY27: 213.538; EIC FY20 LDRD FY28: 221.0118; EIC FY20 LDRD FY29: 228.7472; EIC FY20 LDRD FY30: 236.7533; EIC FY20 LDRD FY31: 245.0397; EIC FY20 LDRD FY32: 253.6161; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 155.634; EIC FY20 FY20: 161.0812; EIC FY20 FY21: 170.0354; EIC FY20 FY22: 175.2371; EIC FY20 FY23: 181.3704; EIC FY20 FY24: 187.7183; EIC FY20 FY25: 194.2885; EIC FY20 FY26: 201.0886; EIC FY20 FY27: 208.1267; EIC FY20 FY28: 215.4111; EIC FY20 FY29: 222.9505; EIC FY20 FY30: 230.7538; EIC FY20 FY31: 238.8302; EIC FY20 FY32: 247.1892
Budget_Act_Labor_$_FY20_EIC | Budgeted_Actual_Labor_Dollars | Labor | Budget_Act_Labor_$_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1; EIC FY20 LDRD FY20: 1; EIC FY20 LDRD FY21: 1; EIC FY20 LDRD FY22: 1; EIC FY20 LDRD FY23: 1; EIC FY20 LDRD FY24: 1; EIC FY20 LDRD FY25: 1; EIC FY20 LDRD FY26: 1; EIC FY20 LDRD FY27: 1; EIC FY20 LDRD FY28: 1; EIC FY20 LDRD FY29: 1; EIC FY20 LDRD FY30: 1; EIC FY20 LDRD FY31: 1; EIC FY20 LDRD FY32: 1; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1; EIC FY20 FY20: 1; EIC FY20 FY21: 1; EIC FY20 FY22: 1; EIC FY20 FY23: 1; EIC FY20 FY24: 1; EIC FY20 FY25: 1; EIC FY20 FY26: 1; EIC FY20 FY27: 1; EIC FY20 FY28: 1; EIC FY20 FY29: 1; EIC FY20 FY30: 1; EIC FY20 FY31: 1; EIC FY20 FY32: 1
Budget_Act_Labor_Hrs_FY20_EIC | Budgeted_Actual_Labor_Hours | Labor | Budget_Act_Labor_Hrs_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1; EIC FY20 LDRD FY20: 1; EIC FY20 LDRD FY21: 1; EIC FY20 LDRD FY22: 1; EIC FY20 LDRD FY23: 1; EIC FY20 LDRD FY24: 1; EIC FY20 LDRD FY25: 1; EIC FY20 LDRD FY26: 1; EIC FY20 LDRD FY27: 1; EIC FY20 LDRD FY28: 1; EIC FY20 LDRD FY29: 1; EIC FY20 LDRD FY30: 1; EIC FY20 LDRD FY31: 1; EIC FY20 LDRD FY32: 1; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1; EIC FY20 FY20: 1; EIC FY20 FY21: 1; EIC FY20 FY22: 1; EIC FY20 FY23: 1; EIC FY20 FY24: 1; EIC FY20 FY25: 1; EIC FY20 FY26: 1; EIC FY20 FY27: 1; EIC FY20 FY28: 1; EIC FY20 FY29: 1; EIC FY20 FY30: 1; EIC FY20 FY31: 1; EIC FY20 FY32: 1
Budget_Act_NonLabor_$_FY20_EIC | Budgeted_Actual_NonLabor_Dollars | Nonlabor | Budget_Act_NonLabor_$_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1; EIC FY20 LDRD FY20: 1; EIC FY20 LDRD FY21: 1; EIC FY20 LDRD FY22: 1; EIC FY20 LDRD FY23: 1; EIC FY20 LDRD FY24: 1; EIC FY20 LDRD FY25: 1; EIC FY20 LDRD FY26: 1; EIC FY20 LDRD FY27: 1; EIC FY20 LDRD FY28: 1; EIC FY20 LDRD FY29: 1; EIC FY20 LDRD FY30: 1; EIC FY20 LDRD FY31: 1; EIC FY20 LDRD FY32: 1; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1; EIC FY20 FY20: 1; EIC FY20 FY21: 1; EIC FY20 FY22: 1; EIC FY20 FY23: 1; EIC FY20 FY24: 1; EIC FY20 FY25: 1; EIC FY20 FY26: 1; EIC FY20 FY27: 1; EIC FY20 FY28: 1; EIC FY20 FY29: 1; EIC FY20 FY30: 1; EIC FY20 FY31: 1; EIC FY20 FY32: 1
Purch_Indirects_FY20_EIC | Purchases_Burdens for ne resources_NonLabor | Nonlabor | Purch_Indirects_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1; EIC FY20 LDRD FY20: 1; EIC FY20 LDRD FY21: 1; EIC FY20 LDRD FY22: 1; EIC FY20 LDRD FY23: 1; EIC FY20 LDRD FY24: 1; EIC FY20 LDRD FY25: 1; EIC FY20 LDRD FY26: 1; EIC FY20 LDRD FY27: 1; EIC FY20 LDRD FY28: 1; EIC FY20 LDRD FY29: 1; EIC FY20 LDRD FY30: 1; EIC FY20 LDRD FY31: 1; EIC FY20 LDRD FY32: 1; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1; EIC FY20 FY20: 1; EIC FY20 FY21: 1; EIC FY20 FY22: 1; EIC FY20 FY23: 1; EIC FY20 FY24: 1; EIC FY20 FY25: 1; EIC FY20 FY26: 1; EIC FY20 FY27: 1; EIC FY20 FY28: 1; EIC FY20 FY29: 1; EIC FY20 FY30: 1; EIC FY20 FY31: 1; EIC FY20 FY32: 1
Purch<$2Mne_FY20_EIC | Purchases<$2M_NonLabor No Escalation | Nonlabor | Purch<$2Mne_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.026; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.026; EIC FY20 LDRD FY22: 1.026; EIC FY20 LDRD FY23: 1.026; EIC FY20 LDRD FY24: 1.026; EIC FY20 LDRD FY25: 1.026; EIC FY20 LDRD FY26: 1.026; EIC FY20 LDRD FY27: 1.026; EIC FY20 LDRD FY28: 1.026; EIC FY20 LDRD FY29: 1.026; EIC FY20 LDRD FY30: 1.026; EIC FY20 LDRD FY31: 1.026; EIC FY20 LDRD FY32: 1.026; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1; EIC FY20 FY20: 1; EIC FY20 FY21: 1; EIC FY20 FY22: 1; EIC FY20 FY23: 1; EIC FY20 FY24: 1; EIC FY20 FY25: 1; EIC FY20 FY26: 1; EIC FY20 FY27: 1; EIC FY20 FY28: 1; EIC FY20 FY29: 1; EIC FY20 FY30: 1; EIC FY20 FY31: 1; EIC FY20 FY32: 1
Purch>$2Mne_FY20_EIC | Purchases>$2M (Portion Over)_NonLabor No Escalation | Nonlabor | Purch>$2Mne_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 1.026; EIC FY20 LDRD FY20: 1.026; EIC FY20 LDRD FY21: 1.026; EIC FY20 LDRD FY22: 1.026; EIC FY20 LDRD FY23: 1.026; EIC FY20 LDRD FY24: 1.026; EIC FY20 LDRD FY25: 1.026; EIC FY20 LDRD FY26: 1.026; EIC FY20 LDRD FY27: 1.026; EIC FY20 LDRD FY28: 1.026; EIC FY20 LDRD FY29: 1.026; EIC FY20 LDRD FY30: 1.026; EIC FY20 LDRD FY31: 1.026; EIC FY20 LDRD FY32: 1.026; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 1; EIC FY20 FY20: 1; EIC FY20 FY21: 1; EIC FY20 FY22: 1; EIC FY20 FY23: 1; EIC FY20 FY24: 1; EIC FY20 FY25: 1; EIC FY20 FY26: 1; EIC FY20 FY27: 1; EIC FY20 FY28: 1; EIC FY20 FY29: 1; EIC FY20 FY30: 1; EIC FY20 FY31: 1; EIC FY20 FY32: 1
RAPHYS_L_FY20_EIC | Research Associate Physics_Low | Labor | RAPHYS_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 60.3479; EIC FY20 LDRD FY20: 62.46; EIC FY20 LDRD FY21: 65.932; EIC FY20 LDRD FY22: 67.949; EIC FY20 LDRD FY23: 70.3273; EIC FY20 LDRD FY24: 72.7887; EIC FY20 LDRD FY25: 75.3363; EIC FY20 LDRD FY26: 77.9731; EIC FY20 LDRD FY27: 80.7021; EIC FY20 LDRD FY28: 83.5267; EIC FY20 LDRD FY29: 86.4501; EIC FY20 LDRD FY30: 89.4759; EIC FY20 LDRD FY31: 92.6076; EIC FY20 LDRD FY32: 95.8488; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 58.8186; EIC FY20 FY20: 60.8772; EIC FY20 FY21: 64.2613; EIC FY20 FY22: 66.2271; EIC FY20 FY23: 68.5451; EIC FY20 FY24: 70.9442; EIC FY20 FY25: 73.4272; EIC FY20 FY26: 75.9972; EIC FY20 FY27: 78.6571; EIC FY20 FY28: 81.4101; EIC FY20 FY29: 84.2594; EIC FY20 FY30: 87.2085; EIC FY20 FY31: 90.2608; EIC FY20 FY32: 93.4199
RAPHYS_M_FY20_EIC | Research Associate Physics_Med | Labor | RAPHYS_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 65.3593; EIC FY20 LDRD FY20: 67.6469; EIC FY20 LDRD FY21: 71.4072; EIC FY20 LDRD FY22: 73.5917; EIC FY20 LDRD FY23: 76.1674; EIC FY20 LDRD FY24: 78.8332; EIC FY20 LDRD FY25: 81.5924; EIC FY20 LDRD FY26: 84.4481; EIC FY20 LDRD FY27: 87.4038; EIC FY20 LDRD FY28: 90.463; EIC FY20 LDRD FY29: 93.6292; EIC FY20 LDRD FY30: 96.9062; EIC FY20 LDRD FY31: 100.2979; EIC FY20 LDRD FY32: 103.8083; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 63.703; EIC FY20 FY20: 65.9326; EIC FY20 FY21: 69.5977; EIC FY20 FY22: 71.7268; EIC FY20 FY23: 74.2372; EIC FY20 FY24: 76.8355; EIC FY20 FY25: 79.5248; EIC FY20 FY26: 82.3081; EIC FY20 FY27: 85.1889; EIC FY20 FY28: 88.1705; EIC FY20 FY29: 91.2565; EIC FY20 FY30: 94.4505; EIC FY20 FY31: 97.7563; EIC FY20 FY32: 101.1777
RAPHYS_H_FY20_EIC | Research Associate Physics_High | Labor | RAPHYS_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 74.0127; EIC FY20 LDRD FY20: 76.6032; EIC FY20 LDRD FY21: 80.8614; EIC FY20 LDRD FY22: 83.3351; EIC FY20 LDRD FY23: 86.2518; EIC FY20 LDRD FY24: 89.2706; EIC FY20 LDRD FY25: 92.3951; EIC FY20 LDRD FY26: 95.6289; EIC FY20 LDRD FY27: 98.976; EIC FY20 LDRD FY28: 102.4401; EIC FY20 LDRD FY29: 106.0255; EIC FY20 LDRD FY30: 109.7364; EIC FY20 LDRD FY31: 113.5772; EIC FY20 LDRD FY32: 117.5524; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 72.1372; EIC FY20 FY20: 74.662; EIC FY20 FY21: 78.8123; EIC FY20 FY22: 81.2233; EIC FY20 FY23: 84.0661; EIC FY20 FY24: 87.0084; EIC FY20 FY25: 90.0537; EIC FY20 FY26: 93.2056; EIC FY20 FY27: 96.4678; EIC FY20 FY28: 99.8442; EIC FY20 FY29: 103.3387; EIC FY20 FY30: 106.9556; EIC FY20 FY31: 110.699; EIC FY20 FY32: 114.5735
SCIAS_L_FY20_EIC | Scientist Associate_Low | Labor | SCIAS_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
SCIAS_M_FY20_EIC | Scientist Associate_Med | Labor | SCIAS_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
SCIAS_H_FY20_EIC | Scientist Associate_High | Labor | SCIAS_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
ASPHY_FY20_EIC | Associate Physicist | Labor | ASPHY_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 117.3851; EIC FY20 LDRD FY20: 121.4936; EIC FY20 LDRD FY21: 128.2471; EIC FY20 LDRD FY22: 132.1704; EIC FY20 LDRD FY23: 136.7964; EIC FY20 LDRD FY24: 141.5843; EIC FY20 LDRD FY25: 146.5397; EIC FY20 LDRD FY26: 151.6686; EIC FY20 LDRD FY27: 156.977; EIC FY20 LDRD FY28: 162.4712; EIC FY20 LDRD FY29: 168.1577; EIC FY20 LDRD FY30: 174.0432; EIC FY20 LDRD FY31: 180.1348; EIC FY20 LDRD FY32: 186.4395; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 114.4104; EIC FY20 FY20: 118.4148; EIC FY20 FY21: 124.9972; EIC FY20 FY22: 128.8211; EIC FY20 FY23: 133.3299; EIC FY20 FY24: 137.9964; EIC FY20 FY25: 142.8263; EIC FY20 FY26: 147.8252; EIC FY20 FY27: 152.9991; EIC FY20 FY28: 158.354; EIC FY20 FY29: 163.8964; EIC FY20 FY30: 169.6328; EIC FY20 FY31: 175.57; EIC FY20 FY32: 181.7149
PHYAS_L_FY20_EIC | Physics Associate_Low | Labor | PHYAS_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 67.4383; EIC FY20 LDRD FY20: 69.7986; EIC FY20 LDRD FY21: 73.6786; EIC FY20 LDRD FY22: 75.9326; EIC FY20 LDRD FY23: 78.5902; EIC FY20 LDRD FY24: 81.3408; EIC FY20 LDRD FY25: 84.1878; EIC FY20 LDRD FY26: 87.1344; EIC FY20 LDRD FY27: 90.1841; EIC FY20 LDRD FY28: 93.3405; EIC FY20 LDRD FY29: 96.6074; EIC FY20 LDRD FY30: 99.9887; EIC FY20 LDRD FY31: 103.4883; EIC FY20 LDRD FY32: 107.1104; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 65.7293; EIC FY20 FY20: 68.0299; EIC FY20 FY21: 71.8115; EIC FY20 FY22: 74.0083; EIC FY20 FY23: 76.5986; EIC FY20 FY24: 79.2796; EIC FY20 FY25: 82.0544; EIC FY20 FY26: 84.9263; EIC FY20 FY27: 87.8987; EIC FY20 FY28: 90.9752; EIC FY20 FY29: 94.1593; EIC FY20 FY30: 97.4549; EIC FY20 FY31: 100.8658; EIC FY20 FY32: 104.3961
PHYAS_M_FY20_EIC | Physics Associate_Med | Labor | PHYAS_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
PHYAS_H_FY20_EIC | Physics Associate_High | Labor | PHYAS_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 121.5781; EIC FY20 LDRD FY20: 125.8333; EIC FY20 LDRD FY21: 132.8281; EIC FY20 LDRD FY22: 136.8916; EIC FY20 LDRD FY23: 141.6828; EIC FY20 LDRD FY24: 146.6417; EIC FY20 LDRD FY25: 151.7742; EIC FY20 LDRD FY26: 157.0863; EIC FY20 LDRD FY27: 162.5843; EIC FY20 LDRD FY28: 168.2748; EIC FY20 LDRD FY29: 174.1644; EIC FY20 LDRD FY30: 180.2601; EIC FY20 LDRD FY31: 186.5692; EIC FY20 LDRD FY32: 193.0992; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 118.4972; EIC FY20 FY20: 122.6446; EIC FY20 FY21: 129.4621; EIC FY20 FY22: 133.4227; EIC FY20 FY23: 138.0924; EIC FY20 FY24: 142.9257; EIC FY20 FY25: 147.9281; EIC FY20 FY26: 153.1056; EIC FY20 FY27: 158.4643; EIC FY20 FY28: 164.0105; EIC FY20 FY29: 169.7509; EIC FY20 FY30: 175.6922; EIC FY20 FY31: 181.8414; EIC FY20 FY32: 188.2058
EMT_L_FY20_EIC | Electro-Mechanical Tech_Low | Labor | EMT_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
EMT_M_FY20_EIC | Electro-Mechanical Tech_Med | Labor | EMT_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 93.7586; EIC FY20 LDRD FY20: 97.0401; EIC FY20 LDRD FY21: 102.4344; EIC FY20 LDRD FY22: 105.568; EIC FY20 LDRD FY23: 109.2629; EIC FY20 LDRD FY24: 113.0871; EIC FY20 LDRD FY25: 117.0452; EIC FY20 LDRD FY26: 121.1417; EIC FY20 LDRD FY27: 125.3817; EIC FY20 LDRD FY28: 129.7701; EIC FY20 LDRD FY29: 134.312; EIC FY20 LDRD FY30: 139.0129; EIC FY20 LDRD FY31: 143.8784; EIC FY20 LDRD FY32: 148.9141; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 91.3826; EIC FY20 FY20: 94.581; EIC FY20 FY21: 99.8386; EIC FY20 FY22: 102.8928; EIC FY20 FY23: 106.4941; EIC FY20 FY24: 110.2214; EIC FY20 FY25: 114.0791; EIC FY20 FY26: 118.0719; EIC FY20 FY27: 122.2044; EIC FY20 FY28: 126.4816; EIC FY20 FY29: 130.9084; EIC FY20 FY30: 135.4902; EIC FY20 FY31: 140.2324; EIC FY20 FY32: 145.1405
EMT_H_FY20_EIC | Electro-Mechanical Tech_High | Labor | EMT_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
E_L_FY20_EIC | Engineer_Low | Labor | E_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 97.9207; EIC FY20 LDRD FY20: 101.3479; EIC FY20 LDRD FY21: 106.9816; EIC FY20 LDRD FY22: 110.2544; EIC FY20 LDRD FY23: 114.1133; EIC FY20 LDRD FY24: 118.1073; EIC FY20 LDRD FY25: 122.241; EIC FY20 LDRD FY26: 126.5194; EIC FY20 LDRD FY27: 130.9476; EIC FY20 LDRD FY28: 135.5308; EIC FY20 LDRD FY29: 140.2744; EIC FY20 LDRD FY30: 145.184; EIC FY20 LDRD FY31: 150.2654; EIC FY20 LDRD FY32: 155.5247; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 95.4393; EIC FY20 FY20: 98.7796; EIC FY20 FY21: 104.2706; EIC FY20 FY22: 107.4604; EIC FY20 FY23: 111.2215; EIC FY20 FY24: 115.1143; EIC FY20 FY25: 119.1433; EIC FY20 FY26: 123.3133; EIC FY20 FY27: 127.6293; EIC FY20 FY28: 132.0963; EIC FY20 FY29: 136.7197; EIC FY20 FY30: 141.5049; EIC FY20 FY31: 146.4575; EIC FY20 FY32: 151.5835
E_M_FY20_EIC | Engineer_Med | Labor | E_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 140.9107; EIC FY20 LDRD FY20: 145.8426; EIC FY20 LDRD FY21: 153.9497; EIC FY20 LDRD FY22: 158.6593; EIC FY20 LDRD FY23: 164.2124; EIC FY20 LDRD FY24: 169.9598; EIC FY20 LDRD FY25: 175.9084; EIC FY20 LDRD FY26: 182.0652; EIC FY20 LDRD FY27: 188.4375; EIC FY20 LDRD FY28: 195.0328; EIC FY20 LDRD FY29: 201.859; EIC FY20 LDRD FY30: 208.924; EIC FY20 LDRD FY31: 216.2364; EIC FY20 LDRD FY32: 223.8046; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 137.3399; EIC FY20 FY20: 142.1468; EIC FY20 FY21: 150.0485; EIC FY20 FY22: 154.6387; EIC FY20 FY23: 160.0511; EIC FY20 FY24: 165.6529; EIC FY20 FY25: 171.4507; EIC FY20 FY26: 177.4515; EIC FY20 FY27: 183.6623; EIC FY20 FY28: 190.0905; EIC FY20 FY29: 196.7437; EIC FY20 FY30: 203.6297; EIC FY20 FY31: 210.7567; EIC FY20 FY32: 218.1332
E_H_FY20_EIC | Engineer_High | Labor | E_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 163.5084; EIC FY20 LDRD FY20: 169.2312; EIC FY20 LDRD FY21: 178.6384; EIC FY20 LDRD FY22: 184.1033; EIC FY20 LDRD FY23: 190.5469; EIC FY20 LDRD FY24: 197.2161; EIC FY20 LDRD FY25: 204.1186; EIC FY20 LDRD FY26: 211.2628; EIC FY20 LDRD FY27: 218.657; EIC FY20 LDRD FY28: 226.31; EIC FY20 LDRD FY29: 234.2308; EIC FY20 LDRD FY30: 242.4289; EIC FY20 LDRD FY31: 250.9139; EIC FY20 LDRD FY32: 259.6959; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 159.3649; EIC FY20 FY20: 164.9427; EIC FY20 FY21: 174.1115; EIC FY20 FY22: 179.438; EIC FY20 FY23: 185.7183; EIC FY20 FY24: 192.2184; EIC FY20 FY25: 198.9461; EIC FY20 FY26: 205.9092; EIC FY20 FY27: 213.116; EIC FY20 FY28: 220.5751; EIC FY20 FY29: 228.2952; EIC FY20 FY30: 236.2855; EIC FY20 FY31: 244.5555; EIC FY20 FY32: 253.115
T_L_FY20_EIC | Tech_Low | Labor | T_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 73.0586; EIC FY20 LDRD FY20: 75.6156; EIC FY20 LDRD FY21: 79.819; EIC FY20 LDRD FY22: 82.2608; EIC FY20 LDRD FY23: 85.1399; EIC FY20 LDRD FY24: 88.1198; EIC FY20 LDRD FY25: 91.204; EIC FY20 LDRD FY26: 94.3961; EIC FY20 LDRD FY27: 97.7; EIC FY20 LDRD FY28: 101.1195; EIC FY20 LDRD FY29: 104.6587; EIC FY20 LDRD FY30: 108.3217; EIC FY20 LDRD FY31: 112.113; EIC FY20 LDRD FY32: 116.0369; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 71.2072; EIC FY20 FY20: 73.6995; EIC FY20 FY21: 77.7963; EIC FY20 FY22: 80.1762; EIC FY20 FY23: 82.9824; EIC FY20 FY24: 85.8868; EIC FY20 FY25: 88.8928; EIC FY20 FY26: 92.004; EIC FY20 FY27: 95.2242; EIC FY20 FY28: 98.557; EIC FY20 FY29: 102.0065; EIC FY20 FY30: 105.5768; EIC FY20 FY31: 109.2719; EIC FY20 FY32: 113.0965
T_M_FY20_EIC | Tech_Med | Labor | T_M_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 107.3865; EIC FY20 LDRD FY20: 111.145; EIC FY20 LDRD FY21: 117.3233; EIC FY20 LDRD FY22: 120.9125; EIC FY20 LDRD FY23: 125.1444; EIC FY20 LDRD FY24: 129.5244; EIC FY20 LDRD FY25: 134.0578; EIC FY20 LDRD FY26: 138.7498; EIC FY20 LDRD FY27: 143.6061; EIC FY20 LDRD FY28: 148.6323; EIC FY20 LDRD FY29: 153.8344; EIC FY20 LDRD FY30: 159.2186; EIC FY20 LDRD FY31: 164.7913; EIC FY20 LDRD FY32: 170.559; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 104.6652; EIC FY20 FY20: 108.3285; EIC FY20 FY21: 114.3502; EIC FY20 FY22: 117.8484; EIC FY20 FY23: 121.9731; EIC FY20 FY24: 126.2422; EIC FY20 FY25: 130.6606; EIC FY20 FY26: 135.2338; EIC FY20 FY27: 139.9669; EIC FY20 FY28: 144.8658; EIC FY20 FY29: 149.9361; EIC FY20 FY30: 155.1839; EIC FY20 FY31: 160.6153; EIC FY20 FY32: 166.2368
T_H_FY20_EIC | Tech_High | Labor | T_H_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 122.6182; EIC FY20 LDRD FY20: 126.9098; EIC FY20 LDRD FY21: 133.9645; EIC FY20 LDRD FY22: 138.0627; EIC FY20 LDRD FY23: 142.8949; EIC FY20 LDRD FY24: 147.8962; EIC FY20 LDRD FY25: 153.0726; EIC FY20 LDRD FY26: 158.4301; EIC FY20 LDRD FY27: 163.9752; EIC FY20 LDRD FY28: 169.7143; EIC FY20 LDRD FY29: 175.6543; EIC FY20 LDRD FY30: 181.8022; EIC FY20 LDRD FY31: 188.1653; EIC FY20 LDRD FY32: 194.7511; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 119.5109; EIC FY20 FY20: 123.6938; EIC FY20 FY21: 130.5697; EIC FY20 FY22: 134.5641; EIC FY20 FY23: 139.2738; EIC FY20 FY24: 144.1484; EIC FY20 FY25: 149.1936; EIC FY20 FY26: 154.4154; EIC FY20 FY27: 159.8199; EIC FY20 FY28: 165.4136; EIC FY20 FY29: 171.2031; EIC FY20 FY30: 177.1952; EIC FY20 FY31: 183.397; EIC FY20 FY32: 189.8159
CONTP_L_FY20_EIC | Contracted Labor (Proc)_Low | Labor | CONTP_L_FY20_EIC | EIC FY20 LDRD FY16: 0; EIC FY20 LDRD FY17: 0; EIC FY20 LDRD FY18: 0; EIC FY20 LDRD FY19: 131.8574; EIC FY20 LDRD FY20: 136.4724; EIC FY20 LDRD FY21: 142.3407; EIC FY20 LDRD FY22: 147.3226; EIC FY20 LDRD FY23: 152.4789; EIC FY20 LDRD FY24: 157.8157; EIC FY20 LDRD FY25: 163.3392; EIC FY20 LDRD FY26: 169.0561; EIC FY20 LDRD FY27: 174.9731; EIC FY20 LDRD FY28: 181.0971; EIC FY20 LDRD FY29: 187.4355; EIC FY20 LDRD FY30: 193.9958; EIC FY20 LDRD FY31: 200.7856; EIC FY20 LDRD FY32: 207.8131; EIC FY20 FY16: 0; EIC FY20 FY17: 0; EIC FY20 FY18: 0; EIC FY20 FY19: 128.516; EIC FY20 FY20: 133.014; EIC FY20 FY21: 138.7336; EIC FY20 FY22: 143.5893; EIC FY20 FY23: 148.6149; EIC FY20 FY24: 153.8165; EIC FY20 FY25: 159.2; EIC FY20 FY26: 164.772; EIC FY20 FY27: 170.5391; EIC FY20 FY28: 176.5079; EIC FY20 FY29: 182.6857; EIC FY20 FY30: 189.0797; EIC FY20 FY31: 195.6975; EIC FY20 FY32: 202.5469

## Holidays (hidden)
FY Year Equals | Start | Finish | Holidays | YEAR | DATE
FY16 | 2015-10-01 | 2016-09-30 | New Years Day Observed | 2015 | 2015-01-01
FY17 | 2016-10-01 | 2017-09-30 | Martin Luther King Day | 2015 | 2015-01-19
FY18 | 2017-10-01 | 2018-09-30 | Presidents' Day | 2015 | 2015-02-16
FY19 | 2018-10-01 | 2019-09-30 | Memorial Day | 2015 | 2015-05-25
FY20 | 2019-10-01 | 2020-09-30 | Independence Day Observed | 2015 | 2015-07-03
FY21 | 2020-10-01 | 2021-09-30 | Labor Day | 2015 | 2015-09-07
FY22 | 2021-10-01 | 2022-09-30 | Columbus Day | 2015 | 2015-10-12
FY23 | 2022-10-01 | 2023-09-30 | Veterans Day Observed | 2015 | 2015-11-11
FY24 | 2023-10-01 | 2024-09-30 | Thanksgiving Day | 2015 | 2015-11-26
FY25 | 2024-10-01 | 2025-09-30 | Day After Thanksgiving Day | 2015 | 2015-11-27
FY26 | 2025-10-01 | 2026-09-30 | Christmas Day Observed | 2015 | 2015-12-25
FY27 | 2026-10-01 | 2027-09-30 | New Years Day Observed | 2016 | 2016-01-01
FY28 | 2027-10-01 | 2028-09-30 | Martin Luther King Day | 2016 | 2016-01-18
FY29 | 2028-10-01 | 2029-09-30 | Presidents' Day | 2016 | 2016-02-15
FY30 | 2029-10-01 | 2030-09-30 | Memorial Day | 2016 | 2016-05-30
FY31 | 2030-10-01 | 2031-09-30 | Independence Day Observed | 2016 | 2016-07-04
FY32 | 2031-10-01 | 2032-09-30 | Labor Day | 2016 | 2016-09-05
FY33 | 2032-10-01 | 2033-09-30 | Columbus Day | 2016 | 2016-10-10
FY34 | 2033-10-01 | 2034-09-30 | Veterans Day Observed | 2016 | 2016-11-11
FY35 | 2034-10-01 | 2035-09-30 | Thanksgiving Day | 2016 | 2016-11-24
|  |  | Day After Thanksgiving Day | 2016 | 2016-11-25
|  |  | Christmas Day Observed | 2016 | 2016-12-26
|  |  | New Years Day Observed | 2017 | 2017-01-02
|  |  | Martin Luther King Day | 2017 | 2017-01-16
|  |  | Presidents' Day | 2017 | 2017-02-20
|  |  | Memorial Day | 2017 | 2017-05-29
|  |  | Independence Day Observed | 2017 | 2017-07-04
|  |  | Labor Day | 2017 | 2017-09-04
|  |  | Columbus Day | 2017 | 2017-10-09
|  |  | Veterans Day Observed | 2017 | 2017-11-10
|  |  | Thanksgiving Day | 2017 | 2017-11-23
|  |  | Day After Thanksgiving Day | 2017 | 2017-11-24
|  |  | Christmas Day Observed | 2017 | 2017-12-25
|  |  | New Years Day Observed | 2018 | 2018-01-01
|  |  | Martin Luther King Day | 2018 | 2018-01-15
|  |  | Presidents' Day | 2018 | 2018-02-19
|  |  | Memorial Day | 2018 | 2018-05-28
|  |  | Independence Day Observed | 2018 | 2018-07-04
|  |  | Labor Day | 2018 | 2018-09-03
|  |  | Columbus Day | 2018 | 2018-10-08
|  |  | Veterans Day Observed | 2018 | 2018-11-12
|  |  | Thanksgiving Day | 2018 | 2018-11-22
|  |  | Day After Thanksgiving Day | 2018 | 2018-11-23
|  |  | Christmas Day Observed | 2018 | 2018-12-25
|  |  | New Years Day Observed | 2019 | 2019-01-01
|  |  | Martin Luther King Day | 2019 | 2019-01-21
|  |  | Presidents' Day | 2019 | 2019-02-18
|  |  | Memorial Day | 2019 | 2019-05-27
|  |  | Independence Day Observed | 2019 | 2019-07-04
|  |  | Labor Day | 2019 | 2019-09-02
|  |  | Columbus Day | 2019 | 2019-10-14
|  |  | Veterans Day Observed | 2019 | 2019-11-11
|  |  | Thanksgiving Day | 2019 | 2019-11-28
|  |  | Day After Thanksgiving Day | 2019 | 2019-11-29
|  |  | Christmas Day Observed | 2019 | 2019-12-25
|  |  | New Years Day Observed | 2020 | 2020-01-01
|  |  | Martin Luther King Day | 2020 | 2020-01-20
|  |  | Presidents' Day | 2020 | 2020-02-17
|  |  | Memorial Day | 2020 | 2020-05-25
|  |  | Independence Day Observed | 2020 | 2020-07-03
|  |  | Labor Day | 2020 | 2020-09-07
|  |  | Columbus Day | 2020 | 2020-10-12
|  |  | Veterans Day Observed | 2020 | 2020-11-11
|  |  | Thanksgiving Day | 2020 | 2020-11-26
|  |  | Day After Thanksgiving Day | 2020 | 2020-11-27
|  |  | Christmas Day Observed | 2020 | 2020-12-25
|  |  | New Years Day Observed | 2021 | 2021-01-01
|  |  | Martin Luther King Day | 2021 | 2021-01-18
|  |  | Presidents' Day | 2021 | 2021-02-15
|  |  | Memorial Day | 2021 | 2021-05-31
|  |  | Independence Day Observed | 2021 | 2021-07-05
|  |  | Labor Day | 2021 | 2021-09-06
|  |  | Columbus Day | 2021 | 2021-10-11
|  |  | Veterans Day Observed | 2021 | 2021-11-11
|  |  | Thanksgiving Day | 2021 | 2021-11-25
|  |  | Day After Thanksgiving Day | 2021 | 2021-11-26
|  |  | Christmas Day Observed | 2021 | 2021-12-24
|  |  | New Years Day Observed | 2021 | 2021-12-31
|  |  | Martin Luther King Day | 2022 | 2022-01-17
|  |  | Presidents' Day | 2022 | 2022-02-21
|  |  | Memorial Day | 2022 | 2022-05-30
|  |  | Independence Day Observed | 2022 | 2022-07-04
|  |  | Labor Day | 2022 | 2022-09-05
|  |  | Columbus Day | 2022 | 2022-10-10
|  |  | Veterans Day Observed | 2022 | 2022-11-11
|  |  | Thanksgiving Day | 2022 | 2022-11-24
|  |  | Day After Thanksgiving Day | 2022 | 2022-11-25
|  |  | Christmas Day Observed | 2022 | 2022-12-26
|  |  | New Years Day Observed | 2023 | 2023-01-02
|  |  | Martin Luther King Day | 2023 | 2023-01-16
|  |  | Presidents' Day | 2023 | 2023-02-20
|  |  | Memorial Day | 2023 | 2023-05-29
|  |  | Independence Day Observed | 2023 | 2023-07-04
|  |  | Labor Day | 2023 | 2023-09-04
|  |  | Columbus Day | 2023 | 2023-10-09
|  |  | Veterans Day Observed | 2023 | 2023-11-10
|  |  | Thanksgiving Day | 2023 | 2023-11-23
|  |  | Day After Thanksgiving Day | 2023 | 2023-11-24
|  |  | Christmas Day Observed | 2023 | 2023-12-25
|  |  | New Years Day Observed | 2024 | 2024-01-01
|  |  | Martin Luther King Day | 2024 | 2024-01-15
|  |  | Presidents' Day | 2024 | 2024-02-19
|  |  | Memorial Day | 2024 | 2024-05-27
|  |  | Independence Day Observed | 2024 | 2024-07-04
|  |  | Labor Day | 2024 | 2024-09-02
|  |  | Columbus Day | 2024 | 2024-10-14
|  |  | Veterans Day Observed | 2024 | 2024-11-11
|  |  | Thanksgiving Day | 2024 | 2024-11-28
|  |  | Day After Thanksgiving Day | 2024 | 2024-11-29
|  |  | Christmas Day Observed | 2024 | 2024-12-25
|  |  | New Years Day Observed | 2025 | 2025-01-01
|  |  | Martin Luther King Day | 2025 | 2025-01-20
|  |  | Presidents' Day | 2025 | 2025-02-17
|  |  | Memorial Day | 2025 | 2025-05-26
|  |  | Independence Day Observed | 2025 | 2025-07-04
|  |  | Labor Day | 2025 | 2025-09-01
|  |  | Columbus Day | 2025 | 2025-10-13
|  |  | Veterans Day Observed | 2025 | 2025-11-11
|  |  | Thanksgiving Day | 2025 | 2025-11-27
|  |  | Day After Thanksgiving Day | 2025 | 2025-11-28
|  |  | Christmas Day Observed | 2025 | 2025-12-25
|  |  | New Years Day Observed | 2026 | 2026-01-01
|  |  | Martin Luther King Day | 2026 | 2026-01-19
|  |  | Presidents' Day | 2026 | 2026-02-16
|  |  | Memorial Day | 2026 | 2026-05-25
|  |  | Independence Day Observed | 2026 | 2026-07-03
|  |  | Labor Day | 2026 | 2026-09-07
|  |  | Columbus Day | 2026 | 2026-10-12
|  |  | Veterans Day Observed | 2026 | 2026-11-11
|  |  | Thanksgiving Day | 2026 | 2026-11-26
|  |  | Day After Thanksgiving Day | 2026 | 2026-11-27
|  |  | Christmas Day Observed | 2026 | 2026-12-25
|  |  | New Years Day Observed | 2027 | 2027-01-01
|  |  | Martin Luther King Day | 2027 | 2027-01-18
|  |  | Presidents' Day | 2027 | 2027-02-15
|  |  | Memorial Day | 2027 | 2027-05-31
|  |  | Independence Day Observed | 2027 | 2027-07-05
|  |  | Labor Day | 2027 | 2027-09-06
|  |  | Columbus Day | 2027 | 2027-10-11
|  |  | Veterans Day Observed | 2027 | 2027-11-11
|  |  | Thanksgiving Day | 2027 | 2027-11-25
|  |  | Day After Thanksgiving Day | 2027 | 2027-11-26
|  |  | Christmas Day Observed | 2027 | 2027-12-24
|  |  | New Years Day Observed | 2027 | 2027-12-31
|  |  | Martin Luther King Day | 2028 | 2028-01-17
|  |  | Presidents' Day | 2028 | 2028-02-21
|  |  | Memorial Day | 2028 | 2028-05-29
|  |  | Independence Day Observed | 2028 | 2028-07-04
|  |  | Labor Day | 2028 | 2028-09-04
|  |  | Columbus Day | 2028 | 2028-10-09
|  |  | Veterans Day Observed | 2028 | 2028-11-10
|  |  | Thanksgiving Day | 2028 | 2028-11-23
|  |  | Day After Thanksgiving Day | 2028 | 2028-11-24
|  |  | Christmas Day Observed | 2028 | 2028-12-25
|  |  | New Years Day Observed | 2029 | 2029-01-01
|  |  | Martin Luther King Day | 2029 | 2029-01-15
|  |  | Presidents' Day | 2029 | 2029-02-19
|  |  | Memorial Day | 2029 | 2029-05-28
|  |  | Independence Day Observed | 2029 | 2029-07-04
|  |  | Labor Day | 2029 | 2029-09-03
|  |  | Columbus Day | 2029 | 2029-10-08
|  |  | Veterans Day Observed | 2029 | 2029-11-12
|  |  | Thanksgiving Day | 2029 | 2029-11-22
|  |  | Day After Thanksgiving Day | 2029 | 2029-11-23
|  |  | Christmas Day Observed | 2029 | 2029-12-25
|  |  | New Years Day Observed | 2030 | 2030-01-01
|  |  | Martin Luther King Day | 2030 | 2030-01-21
|  |  | Presidents' Day | 2030 | 2030-02-18
|  |  | Memorial Day | 2030 | 2030-05-27
|  |  | Independence Day Observed | 2030 | 2030-07-04
|  |  | Labor Day | 2030 | 2030-09-02
|  |  | Columbus Day | 2030 | 2030-10-14
|  |  | Veterans Day Observed | 2030 | 2030-11-11
|  |  | Thanksgiving Day | 2030 | 2030-11-28
|  |  | Day After Thanksgiving Day | 2030 | 2030-11-29
|  |  | Christmas Day Observed | 2030 | 2030-12-25
|  |  | New Years Day Observed | 2031 | 2031-01-01
|  |  | Martin Luther King Day | 2031 | 2031-01-20
|  |  | Presidents' Day | 2031 | 2031-02-17
|  |  | Memorial Day | 2031 | 2031-05-26
|  |  | Independence Day Observed | 2031 | 2031-07-04
|  |  | Labor Day | 2031 | 2031-09-01
|  |  | Columbus Day | 2031 | 2031-10-13
|  |  | Veterans Day Observed | 2031 | 2031-11-11
|  |  | Thanksgiving Day | 2031 | 2031-11-27
|  |  | Day After Thanksgiving Day | 2031 | 2031-11-28
|  |  | Christmas Day Observed | 2031 | 2031-12-25
|  |  | New Years Day Observed | 2032 | 2032-01-01
|  |  | Martin Luther King Day | 2032 | 2032-01-19
|  |  | Presidents' Day | 2032 | 2032-02-16
|  |  | Memorial Day | 2032 | 2032-05-31
|  |  | Independence Day Observed | 2032 | 2032-07-05
|  |  | Labor Day | 2032 | 2032-09-06
|  |  | Columbus Day | 2032 | 2032-10-11
|  |  | Veterans Day Observed | 2032 | 2032-11-11
|  |  | Thanksgiving Day | 2032 | 2032-11-25
|  |  | Day After Thanksgiving Day | 2032 | 2032-11-26
|  |  | Christmas Day Observed | 2032 | 2032-12-24
|  |  | New Years Day Observed | 2032 | 2032-12-31
|  |  | Martin Luther King Day | 2033 | 2033-01-17
|  |  | Presidents' Day | 2033 | 2033-02-21
|  |  | Memorial Day | 2033 | 2033-05-30
|  |  | Independence Day Observed | 2033 | 2033-07-04
|  |  | Labor Day | 2033 | 2033-09-05
|  |  | Columbus Day | 2033 | 2033-10-10
|  |  | Veterans Day Observed | 2033 | 2033-11-11
|  |  | Thanksgiving Day | 2033 | 2033-11-24
|  |  | Day After Thanksgiving Day | 2033 | 2033-11-25
|  |  | Christmas Day Observed | 2033 | 2033-12-26
|  |  | New Years Day Observed | 2034 | 2034-01-02
|  |  | Martin Luther King Day | 2034 | 2034-01-16
|  |  | Presidents' Day | 2034 | 2034-02-20
|  |  | Memorial Day | 2034 | 2034-05-29
|  |  | Independence Day Observed | 2034 | 2034-07-04
|  |  | Labor Day | 2034 | 2034-09-04
|  |  | Columbus Day | 2034 | 2034-10-09
|  |  | Veterans Day Observed | 2034 | 2034-11-10
|  |  | Thanksgiving Day | 2034 | 2034-11-23
|  |  | Day After Thanksgiving Day | 2034 | 2034-11-24
|  |  | Christmas Day Observed | 2034 | 2034-12-25
|  |  | New Years Day Observed | 2035 | 2035-01-01
|  |  | Martin Luther King Day | 2035 | 2035-01-15
|  |  | Presidents' Day | 2035 | 2035-02-19
|  |  | Memorial Day | 2035 | 2035-05-28
|  |  | Independence Day Observed | 2035 | 2035-07-04
|  |  | Labor Day | 2035 | 2035-09-03
|  |  | Columbus Day | 2035 | 2035-10-08
|  |  | Veterans Day Observed | 2035 | 2035-11-12
|  |  | Thanksgiving Day | 2035 | 2035-11-22
|  |  | Day After Thanksgiving Day | 2035 | 2035-11-23
|  |  | Christmas Day Observed | 2035 | 2035-12-25
|  |  | New Years Day Observed | 2036 | 2036-01-01
|  |  | Martin Luther King Day | 2036 | 2036-01-21
|  |  | Presidents' Day | 2036 | 2036-02-18
|  |  | Memorial Day | 2036 | 2036-05-26
|  |  | Independence Day Observed | 2036 | 2036-07-04
|  |  | Labor Day | 2036 | 2036-09-01
|  |  | Columbus Day | 2036 | 2036-10-13
|  |  | Veterans Day Observed | 2036 | 2036-11-11
|  |  | Thanksgiving Day | 2036 | 2036-11-27
|  |  | Day After Thanksgiving Day | 2036 | 2036-11-28
|  |  | Christmas Day Observed | 2036 | 2036-12-25
|  |  | New Years Day Observed | 2037 | 2037-01-01
|  |  | Martin Luther King Day | 2037 | 2037-01-19
|  |  | Presidents' Day | 2037 | 2037-02-16
|  |  | Memorial Day | 2037 | 2037-05-25
|  |  | Independence Day Observed | 2037 | 2037-07-03
|  |  | Labor Day | 2037 | 2037-09-07
|  |  | Columbus Day | 2037 | 2037-10-12
|  |  | Veterans Day Observed | 2037 | 2037-11-11
|  |  | Thanksgiving Day | 2037 | 2037-11-26
|  |  | Day After Thanksgiving Day | 2037 | 2037-11-27
|  |  | Christmas Day Observed | 2037 | 2037-12-25
|  |  | New Years Day Observed | 2038 | 2038-01-01
|  |  | Martin Luther King Day | 2038 | 2038-01-18
|  |  | Presidents' Day | 2038 | 2038-02-15
|  |  | Memorial Day | 2038 | 2038-05-31
|  |  | Independence Day Observed | 2038 | 2038-07-05
|  |  | Labor Day | 2038 | 2038-09-06
|  |  | Columbus Day | 2038 | 2038-10-11
|  |  | Veterans Day Observed | 2038 | 2038-11-11
|  |  | Thanksgiving Day | 2038 | 2038-11-25
|  |  | Day After Thanksgiving Day | 2038 | 2038-11-26
|  |  | Christmas Day Observed | 2038 | 2038-12-24
|  |  | New Years Day Observed | 2038 | 2038-12-31
|  |  | Martin Luther King Day | 2039 | 2039-01-17
|  |  | Presidents' Day | 2039 | 2039-02-21
|  |  | Memorial Day | 2039 | 2039-05-30
|  |  | Independence Day Observed | 2039 | 2039-07-04
|  |  | Labor Day | 2039 | 2039-09-05
|  |  | Columbus Day | 2039 | 2039-10-10
|  |  | Veterans Day Observed | 2039 | 2039-11-11
|  |  | Thanksgiving Day | 2039 | 2039-11-24
|  |  | Day After Thanksgiving Day | 2039 | 2039-11-25
|  |  | Christmas Day Observed | 2039 | 2039-12-26
|  |  | New Years Day Observed | 2040 | 2040-01-02
|  |  | Martin Luther King Day | 2040 | 2040-01-16
|  |  | Presidents' Day | 2040 | 2040-02-20
|  |  | Memorial Day | 2040 | 2040-05-28
|  |  | Independence Day Observed | 2040 | 2040-07-04
|  |  | Labor Day | 2040 | 2040-09-03
|  |  | Columbus Day | 2040 | 2040-10-08
|  |  | Veterans Day Observed | 2040 | 2040-11-12
|  |  | Thanksgiving Day | 2040 | 2040-11-22
|  |  | Day After Thanksgiving Day | 2040 | 2040-11-23
|  |  | Christmas Day Observed | 2040 | 2040-12-25
|  |  | New Years Day Observed | 2041 | 2041-01-01
|  |  | Martin Luther King Day | 2041 | 2041-01-21
|  |  | Presidents' Day | 2041 | 2041-02-18
|  |  | Memorial Day | 2041 | 2041-05-27
|  |  | Independence Day Observed | 2041 | 2041-07-04
|  |  | Labor Day | 2041 | 2041-09-02
|  |  | Columbus Day | 2041 | 2041-10-14
|  |  | Veterans Day Observed | 2041 | 2041-11-11
|  |  | Thanksgiving Day | 2041 | 2041-11-28
|  |  | Day After Thanksgiving Day | 2041 | 2041-11-29
|  |  | Christmas Day Observed | 2041 | 2041-12-25
|  |  | New Years Day Observed | 2042 | 2042-01-01
|  |  | Martin Luther King Day | 2042 | 2042-01-20
|  |  | Presidents' Day | 2042 | 2042-02-17
|  |  | Memorial Day | 2042 | 2042-05-26
|  |  | Independence Day Observed | 2042 | 2042-07-04
|  |  | Labor Day | 2042 | 2042-09-01
|  |  | Columbus Day | 2042 | 2042-10-13
|  |  | Veterans Day Observed | 2042 | 2042-11-11
|  |  | Thanksgiving Day | 2042 | 2042-11-27
|  |  | Day After Thanksgiving Day | 2042 | 2042-11-28
|  |  | Christmas Day Observed | 2042 | 2042-12-25
|  |  | New Years Day Observed | 2043 | 2043-01-01
|  |  | Martin Luther King Day | 2043 | 2043-01-19
|  |  | Presidents' Day | 2043 | 2043-02-16
|  |  | Memorial Day | 2043 | 2043-05-25
|  |  | Independence Day Observed | 2043 | 2043-07-03
|  |  | Labor Day | 2043 | 2043-09-07
|  |  | Columbus Day | 2043 | 2043-10-12
|  |  | Veterans Day Observed | 2043 | 2043-11-11
|  |  | Thanksgiving Day | 2043 | 2043-11-26
|  |  | Day After Thanksgiving Day | 2043 | 2043-11-27
|  |  | Christmas Day Observed | 2043 | 2043-12-25
|  |  | New Years Day Observed | 2044 | 2044-01-01
|  |  | Martin Luther King Day | 2044 | 2044-01-18
|  |  | Presidents' Day | 2044 | 2044-02-15
|  |  | Memorial Day | 2044 | 2044-05-30
|  |  | Independence Day Observed | 2044 | 2044-07-04
|  |  | Labor Day | 2044 | 2044-09-05
|  |  | Columbus Day | 2044 | 2044-10-10
|  |  | Veterans Day Observed | 2044 | 2044-11-11
|  |  | Thanksgiving Day | 2044 | 2044-11-24
|  |  | Day After Thanksgiving Day | 2044 | 2044-11-25
|  |  | Christmas Day Observed | 2044 | 2044-12-26
|  |  | New Years Day Observed | 2045 | 2045-01-02
|  |  | Martin Luther King Day | 2045 | 2045-01-16
|  |  | Presidents' Day | 2045 | 2045-02-20
|  |  | Memorial Day | 2045 | 2045-05-29
|  |  | Independence Day Observed | 2045 | 2045-07-04
|  |  | Labor Day | 2045 | 2045-09-04
|  |  | Columbus Day | 2045 | 2045-10-09
|  |  | Veterans Day Observed | 2045 | 2045-11-10
|  |  | Thanksgiving Day | 2045 | 2045-11-23
|  |  | Day After Thanksgiving Day | 2045 | 2045-11-24
|  |  | Christmas Day Observed | 2045 | 2045-12-25
|  |  | New Years Day Observed | 2046 | 2046-01-01
|  |  | Martin Luther King Day | 2046 | 2046-01-15
|  |  | Presidents' Day | 2046 | 2046-02-19
|  |  | Memorial Day | 2046 | 2046-05-28
|  |  | Independence Day Observed | 2046 | 2046-07-04
|  |  | Labor Day | 2046 | 2046-09-03
|  |  | Columbus Day | 2046 | 2046-10-08
|  |  | Veterans Day Observed | 2046 | 2046-11-12
|  |  | Thanksgiving Day | 2046 | 2046-11-22
|  |  | Day After Thanksgiving Day | 2046 | 2046-11-23
|  |  | Christmas Day Observed | 2046 | 2046-12-25
|  |  | New Years Day Observed | 2047 | 2047-01-01
|  |  | Martin Luther King Day | 2047 | 2047-01-21
|  |  | Presidents' Day | 2047 | 2047-02-18
|  |  | Memorial Day | 2047 | 2047-05-27
|  |  | Independence Day Observed | 2047 | 2047-07-04
|  |  | Labor Day | 2047 | 2047-09-02
|  |  | Columbus Day | 2047 | 2047-10-14
|  |  | Veterans Day Observed | 2047 | 2047-11-11
|  |  | Thanksgiving Day | 2047 | 2047-11-28
|  |  | Day After Thanksgiving Day | 2047 | 2047-11-29
|  |  | Christmas Day Observed | 2047 | 2047-12-25
|  |  | New Years Day Observed | 2048 | 2048-01-01
|  |  | Martin Luther King Day | 2048 | 2048-01-20
|  |  | Presidents' Day | 2048 | 2048-02-17
|  |  | Memorial Day | 2048 | 2048-05-25
|  |  | Independence Day Observed | 2048 | 2048-07-03
|  |  | Labor Day | 2048 | 2048-09-07
|  |  | Columbus Day | 2048 | 2048-10-12
|  |  | Veterans Day Observed | 2048 | 2048-11-11
|  |  | Thanksgiving Day | 2048 | 2048-11-26
|  |  | Day After Thanksgiving Day | 2048 | 2048-11-27
|  |  | Christmas Day Observed | 2048 | 2048-12-25
|  |  | New Years Day Observed | 2049 | 2049-01-01
|  |  | Martin Luther King Day | 2049 | 2049-01-18
|  |  | Presidents' Day | 2049 | 2049-02-15
|  |  | Memorial Day | 2049 | 2049-05-31
|  |  | Independence Day Observed | 2049 | 2049-07-05
|  |  | Labor Day | 2049 | 2049-09-06
|  |  | Columbus Day | 2049 | 2049-10-11
|  |  | Veterans Day Observed | 2049 | 2049-11-11
|  |  | Thanksgiving Day | 2049 | 2049-11-25
|  |  | Day After Thanksgiving Day | 2049 | 2049-11-26
|  |  | Christmas Day Observed | 2049 | 2049-12-24
|  |  | New Years Day Observed | 2049 | 2049-12-31
|  |  | Martin Luther King Day | 2050 | 2050-01-17
|  |  | Presidents' Day | 2050 | 2050-02-21
|  |  | Memorial Day | 2050 | 2050-05-30
|  |  | Independence Day Observed | 2050 | 2050-07-04
|  |  | Labor Day | 2050 | 2050-09-05
|  |  | Columbus Day | 2050 | 2050-10-10
|  |  | Veterans Day Observed | 2050 | 2050-11-11
|  |  | Thanksgiving Day | 2050 | 2050-11-24
|  |  | Day After Thanksgiving Day | 2050 | 2050-11-25
|  |  | Christmas Day Observed | 2050 | 2050-12-26
|  |  | New Years Day Observed | 2051 | 2051-01-02
|  |  | Martin Luther King Day | 2051 | 2051-01-16
|  |  | Presidents' Day | 2051 | 2051-02-20
|  |  | Memorial Day | 2051 | 2051-05-29
|  |  | Independence Day Observed | 2051 | 2051-07-04
|  |  | Labor Day | 2051 | 2051-09-04
|  |  | Columbus Day | 2051 | 2051-10-09
|  |  | Veterans Day Observed | 2051 | 2051-11-10
|  |  | Thanksgiving Day | 2051 | 2051-11-23
|  |  | Day After Thanksgiving Day | 2051 | 2051-11-24
|  |  | Christmas Day Observed | 2051 | 2051-12-25
|  |  | New Years Day Observed | 2052 | 2052-01-01
|  |  | Martin Luther King Day | 2052 | 2052-01-15
|  |  | Presidents' Day | 2052 | 2052-02-19
|  |  | Memorial Day | 2052 | 2052-05-27
|  |  | Independence Day Observed | 2052 | 2052-07-04
|  |  | Labor Day | 2052 | 2052-09-02
|  |  | Columbus Day | 2052 | 2052-10-14
|  |  | Veterans Day Observed | 2052 | 2052-11-11
|  |  | Thanksgiving Day | 2052 | 2052-11-28
|  |  | Day After Thanksgiving Day | 2052 | 2052-11-29
|  |  | Christmas Day Observed | 2052 | 2052-12-25
|  |  | New Years Day Observed | 2053 | 2053-01-01
|  |  | Martin Luther King Day | 2053 | 2053-01-20
|  |  | Presidents' Day | 2053 | 2053-02-17
|  |  | Memorial Day | 2053 | 2053-05-26
|  |  | Independence Day Observed | 2053 | 2053-07-04
|  |  | Labor Day | 2053 | 2053-09-01
|  |  | Columbus Day | 2053 | 2053-10-13
|  |  | Veterans Day Observed | 2053 | 2053-11-11
|  |  | Thanksgiving Day | 2053 | 2053-11-27
|  |  | Day After Thanksgiving Day | 2053 | 2053-11-28
|  |  | Christmas Day Observed | 2053 | 2053-12-25
|  |  | New Years Day Observed | 2054 | 2054-01-01
|  |  | Martin Luther King Day | 2054 | 2054-01-19
|  |  | Presidents' Day | 2054 | 2054-02-16
|  |  | Memorial Day | 2054 | 2054-05-25
|  |  | Independence Day Observed | 2054 | 2054-07-03
|  |  | Labor Day | 2054 | 2054-09-07
|  |  | Columbus Day | 2054 | 2054-10-12
|  |  | Veterans Day Observed | 2054 | 2054-11-11
|  |  | Thanksgiving Day | 2054 | 2054-11-26
|  |  | Day After Thanksgiving Day | 2054 | 2054-11-27
|  |  | Christmas Day Observed | 2054 | 2054-12-25
|  |  | New Years Day Observed | 2055 | 2055-01-01
|  |  | Martin Luther King Day | 2055 | 2055-01-18
|  |  | Presidents' Day | 2055 | 2055-02-15
|  |  | Memorial Day | 2055 | 2055-05-31
|  |  | Independence Day Observed | 2055 | 2055-07-05
|  |  | Labor Day | 2055 | 2055-09-06
|  |  | Columbus Day | 2055 | 2055-10-11
|  |  | Veterans Day Observed | 2055 | 2055-11-11
|  |  | Thanksgiving Day | 2055 | 2055-11-25
|  |  | Day After Thanksgiving Day | 2055 | 2055-11-26
|  |  | Christmas Day Observed | 2055 | 2055-12-24
|  |  | New Years Day Observed | 2055 | 2055-12-31
|  |  | Martin Luther King Day | 2056 | 2056-01-17
|  |  | Presidents' Day | 2056 | 2056-02-21
|  |  | Memorial Day | 2056 | 2056-05-29
|  |  | Independence Day Observed | 2056 | 2056-07-04
|  |  | Labor Day | 2056 | 2056-09-04
|  |  | Columbus Day | 2056 | 2056-10-09
|  |  | Veterans Day Observed | 2056 | 2056-11-10
|  |  | Thanksgiving Day | 2056 | 2056-11-23
|  |  | Day After Thanksgiving Day | 2056 | 2056-11-24
|  |  | Christmas Day Observed | 2056 | 2056-12-25
|  |  | New Years Day Observed | 2057 | 2057-01-01
|  |  | Martin Luther King Day | 2057 | 2057-01-15
|  |  | Presidents' Day | 2057 | 2057-02-19
|  |  | Memorial Day | 2057 | 2057-05-28
|  |  | Independence Day Observed | 2057 | 2057-07-04
|  |  | Labor Day | 2057 | 2057-09-03
|  |  | Columbus Day | 2057 | 2057-10-08
|  |  | Veterans Day Observed | 2057 | 2057-11-12
|  |  | Thanksgiving Day | 2057 | 2057-11-22
|  |  | Day After Thanksgiving Day | 2057 | 2057-11-23
|  |  | Christmas Day Observed | 2057 | 2057-12-25
|  |  | New Years Day Observed | 2058 | 2058-01-01
|  |  | Martin Luther King Day | 2058 | 2058-01-21
|  |  | Presidents' Day | 2058 | 2058-02-18
|  |  | Memorial Day | 2058 | 2058-05-27
|  |  | Independence Day Observed | 2058 | 2058-07-04
|  |  | Labor Day | 2058 | 2058-09-02
|  |  | Columbus Day | 2058 | 2058-10-14
|  |  | Veterans Day Observed | 2058 | 2058-11-11
|  |  | Thanksgiving Day | 2058 | 2058-11-28
|  |  | Day After Thanksgiving Day | 2058 | 2058-11-29
|  |  | Christmas Day Observed | 2058 | 2058-12-25
|  |  | New Years Day Observed | 2059 | 2059-01-01
|  |  | Martin Luther King Day | 2059 | 2059-01-20
|  |  | Presidents' Day | 2059 | 2059-02-17
|  |  | Memorial Day | 2059 | 2059-05-26
|  |  | Independence Day Observed | 2059 | 2059-07-04
|  |  | Labor Day | 2059 | 2059-09-01
|  |  | Columbus Day | 2059 | 2059-10-13
|  |  | Veterans Day Observed | 2059 | 2059-11-11
|  |  | Thanksgiving Day | 2059 | 2059-11-27
|  |  | Day After Thanksgiving Day | 2059 | 2059-11-28
|  |  | Christmas Day Observed | 2059 | 2059-12-25
|  |  | New Years Day Observed | 2060 | 2060-01-01
|  |  | Martin Luther King Day | 2060 | 2060-01-19
|  |  | Presidents' Day | 2060 | 2060-02-16
|  |  | Memorial Day | 2060 | 2060-05-31
|  |  | Independence Day Observed | 2060 | 2060-07-05
|  |  | Labor Day | 2060 | 2060-09-06
|  |  | Columbus Day | 2060 | 2060-10-11
|  |  | Veterans Day Observed | 2060 | 2060-11-11
|  |  | Thanksgiving Day | 2060 | 2060-11-25
|  |  | Day After Thanksgiving Day | 2060 | 2060-11-26
|  |  | Christmas Day Observed | 2060 | 2060-12-24
|  |  | New Years Day Observed | 2060 | 2060-12-31
|  |  | Martin Luther King Day | 2061 | 2061-01-17
|  |  | Presidents' Day | 2061 | 2061-02-21
|  |  | Memorial Day | 2061 | 2061-05-30
|  |  | Independence Day Observed | 2061 | 2061-07-04
|  |  | Labor Day | 2061 | 2061-09-05
|  |  | Columbus Day | 2061 | 2061-10-10
|  |  | Veterans Day Observed | 2061 | 2061-11-11
|  |  | Thanksgiving Day | 2061 | 2061-11-24
|  |  | Day After Thanksgiving Day | 2061 | 2061-11-25
|  |  | Christmas Day Observed | 2061 | 2061-12-26
|  |  | New Years Day Observed | 2062 | 2062-01-02
|  |  | Martin Luther King Day | 2062 | 2062-01-16
|  |  | Presidents' Day | 2062 | 2062-02-20
|  |  | Memorial Day | 2062 | 2062-05-29
|  |  | Independence Day Observed | 2062 | 2062-07-04
|  |  | Labor Day | 2062 | 2062-09-04
|  |  | Columbus Day | 2062 | 2062-10-09
|  |  | Veterans Day Observed | 2062 | 2062-11-10
|  |  | Thanksgiving Day | 2062 | 2062-11-23
|  |  | Day After Thanksgiving Day | 2062 | 2062-11-24
|  |  | Christmas Day Observed | 2062 | 2062-12-25
|  |  | New Years Day Observed | 2063 | 2063-01-01
|  |  | Martin Luther King Day | 2063 | 2063-01-15
|  |  | Presidents' Day | 2063 | 2063-02-19
|  |  | Memorial Day | 2063 | 2063-05-28
|  |  | Independence Day Observed | 2063 | 2063-07-04
|  |  | Labor Day | 2063 | 2063-09-03
|  |  | Columbus Day | 2063 | 2063-10-08
|  |  | Veterans Day Observed | 2063 | 2063-11-12
|  |  | Thanksgiving Day | 2063 | 2063-11-22
|  |  | Day After Thanksgiving Day | 2063 | 2063-11-23
|  |  | Christmas Day Observed | 2063 | 2063-12-25
|  |  | New Years Day Observed | 2064 | 2064-01-01
|  |  | Martin Luther King Day | 2064 | 2064-01-21
|  |  | Presidents' Day | 2064 | 2064-02-18
|  |  | Memorial Day | 2064 | 2064-05-26
|  |  | Independence Day Observed | 2064 | 2064-07-04
|  |  | Labor Day | 2064 | 2064-09-01
|  |  | Columbus Day | 2064 | 2064-10-13
|  |  | Veterans Day Observed | 2064 | 2064-11-11
|  |  | Thanksgiving Day | 2064 | 2064-11-27
|  |  | Day After Thanksgiving Day | 2064 | 2064-11-28
|  |  | Christmas Day Observed | 2064 | 2064-12-25
|  |  | New Years Day Observed | 2065 | 2065-01-01
|  |  | Martin Luther King Day | 2065 | 2065-01-19
|  |  | Presidents' Day | 2065 | 2065-02-16
|  |  | Memorial Day | 2065 | 2065-05-25
|  |  | Independence Day Observed | 2065 | 2065-07-03
|  |  | Labor Day | 2065 | 2065-09-07
|  |  | Columbus Day | 2065 | 2065-10-12
|  |  | Veterans Day Observed | 2065 | 2065-11-11
|  |  | Thanksgiving Day | 2065 | 2065-11-26
|  |  | Day After Thanksgiving Day | 2065 | 2065-11-27
|  |  | Christmas Day Observed | 2065 | 2065-12-25
|  |  | New Years Day Observed | 2066 | 2066-01-01
|  |  | Martin Luther King Day | 2066 | 2066-01-18
|  |  | Presidents' Day | 2066 | 2066-02-15
|  |  | Memorial Day | 2066 | 2066-05-31
|  |  | Independence Day Observed | 2066 | 2066-07-05
|  |  | Labor Day | 2066 | 2066-09-06
|  |  | Columbus Day | 2066 | 2066-10-11
|  |  | Veterans Day Observed | 2066 | 2066-11-11
|  |  | Thanksgiving Day | 2066 | 2066-11-25
|  |  | Day After Thanksgiving Day | 2066 | 2066-11-26
|  |  | Christmas Day Observed | 2066 | 2066-12-24
|  |  | New Years Day Observed | 2066 | 2066-12-31
|  |  | Martin Luther King Day | 2067 | 2067-01-17
|  |  | Presidents' Day | 2067 | 2067-02-21
|  |  | Memorial Day | 2067 | 2067-05-30
|  |  | Independence Day Observed | 2067 | 2067-07-04
|  |  | Labor Day | 2067 | 2067-09-05
|  |  | Columbus Day | 2067 | 2067-10-10
|  |  | Veterans Day Observed | 2067 | 2067-11-11
|  |  | Thanksgiving Day | 2067 | 2067-11-24
|  |  | Day After Thanksgiving Day | 2067 | 2067-11-25
|  |  | Christmas Day Observed | 2067 | 2067-12-26
|  |  | New Years Day Observed | 2068 | 2068-01-02
|  |  | Martin Luther King Day | 2068 | 2068-01-16
|  |  | Presidents' Day | 2068 | 2068-02-20
|  |  | Memorial Day | 2068 | 2068-05-28
|  |  | Independence Day Observed | 2068 | 2068-07-04
|  |  | Labor Day | 2068 | 2068-09-03
|  |  | Columbus Day | 2068 | 2068-10-08
|  |  | Veterans Day Observed | 2068 | 2068-11-12
|  |  | Thanksgiving Day | 2068 | 2068-11-22
|  |  | Day After Thanksgiving Day | 2068 | 2068-11-23
|  |  | Christmas Day Observed | 2068 | 2068-12-25
|  |  | New Years Day Observed | 2069 | 2069-01-01
|  |  | Martin Luther King Day | 2069 | 2069-01-21
|  |  | Presidents' Day | 2069 | 2069-02-18
|  |  | Memorial Day | 2069 | 2069-05-27
|  |  | Independence Day Observed | 2069 | 2069-07-04
|  |  | Labor Day | 2069 | 2069-09-02
|  |  | Columbus Day | 2069 | 2069-10-14
|  |  | Veterans Day Observed | 2069 | 2069-11-11
|  |  | Thanksgiving Day | 2069 | 2069-11-28
|  |  | Day After Thanksgiving Day | 2069 | 2069-11-29
|  |  | Christmas Day Observed | 2069 | 2069-12-25
|  |  | New Years Day Observed | 2070 | 2070-01-01
|  |  | Martin Luther King Day | 2070 | 2070-01-20
|  |  | Presidents' Day | 2070 | 2070-02-17
|  |  | Memorial Day | 2070 | 2070-05-26
|  |  | Independence Day Observed | 2070 | 2070-07-04
|  |  | Labor Day | 2070 | 2070-09-01
|  |  | Columbus Day | 2070 | 2070-10-13
|  |  | Veterans Day Observed | 2070 | 2070-11-11
|  |  | Thanksgiving Day | 2070 | 2070-11-27
|  |  | Day After Thanksgiving Day | 2070 | 2070-11-28
|  |  | Christmas Day Observed | 2070 | 2070-12-25
|  |  | New Years Day Observed | 2071 | 2071-01-01
|  |  | Martin Luther King Day | 2071 | 2071-01-19
|  |  | Presidents' Day | 2071 | 2071-02-16
|  |  | Memorial Day | 2071 | 2071-05-25
|  |  | Independence Day Observed | 2071 | 2071-07-03
|  |  | Labor Day | 2071 | 2071-09-07
|  |  | Columbus Day | 2071 | 2071-10-12
|  |  | Veterans Day Observed | 2071 | 2071-11-11
|  |  | Thanksgiving Day | 2071 | 2071-11-26
|  |  | Day After Thanksgiving Day | 2071 | 2071-11-27
|  |  | Christmas Day Observed | 2071 | 2071-12-25
|  |  | New Years Day Observed | 2072 | 2072-01-01
|  |  | Martin Luther King Day | 2072 | 2072-01-18
|  |  | Presidents' Day | 2072 | 2072-02-15
|  |  | Memorial Day | 2072 | 2072-05-30
|  |  | Independence Day Observed | 2072 | 2072-07-04
|  |  | Labor Day | 2072 | 2072-09-05
|  |  | Columbus Day | 2072 | 2072-10-10
|  |  | Veterans Day Observed | 2072 | 2072-11-11
|  |  | Thanksgiving Day | 2072 | 2072-11-24
|  |  | Day After Thanksgiving Day | 2072 | 2072-11-25
|  |  | Christmas Day Observed | 2072 | 2072-12-26
|  |  | New Years Day Observed | 2073 | 2073-01-02
|  |  | Martin Luther King Day | 2073 | 2073-01-16
|  |  | Presidents' Day | 2073 | 2073-02-20
|  |  | Memorial Day | 2073 | 2073-05-29
|  |  | Independence Day Observed | 2073 | 2073-07-04
|  |  | Labor Day | 2073 | 2073-09-04
|  |  | Columbus Day | 2073 | 2073-10-09
|  |  | Veterans Day Observed | 2073 | 2073-11-10
|  |  | Thanksgiving Day | 2073 | 2073-11-23
|  |  | Day After Thanksgiving Day | 2073 | 2073-11-24
|  |  | Christmas Day Observed | 2073 | 2073-12-25
|  |  | New Years Day Observed | 2074 | 2074-01-01
|  |  | Martin Luther King Day | 2074 | 2074-01-15
|  |  | Presidents' Day | 2074 | 2074-02-19
|  |  | Memorial Day | 2074 | 2074-05-28
|  |  | Independence Day Observed | 2074 | 2074-07-04
|  |  | Labor Day | 2074 | 2074-09-03
|  |  | Columbus Day | 2074 | 2074-10-08
|  |  | Veterans Day Observed | 2074 | 2074-11-12
|  |  | Thanksgiving Day | 2074 | 2074-11-22
|  |  | Day After Thanksgiving Day | 2074 | 2074-11-23
|  |  | Christmas Day Observed | 2074 | 2074-12-25
|  |  | New Years Day Observed | 2075 | 2075-01-01
|  |  | Martin Luther King Day | 2075 | 2075-01-21
|  |  | Presidents' Day | 2075 | 2075-02-18
|  |  | Memorial Day | 2075 | 2075-05-27
|  |  | Independence Day Observed | 2075 | 2075-07-04
|  |  | Labor Day | 2075 | 2075-09-02
|  |  | Columbus Day | 2075 | 2075-10-14
|  |  | Veterans Day Observed | 2075 | 2075-11-11
|  |  | Thanksgiving Day | 2075 | 2075-11-28
|  |  | Day After Thanksgiving Day | 2075 | 2075-11-29
|  |  | Christmas Day Observed | 2075 | 2075-12-25
|  |  | New Years Day Observed | 2076 | 2076-01-01
|  |  | Martin Luther King Day | 2076 | 2076-01-20
|  |  | Presidents' Day | 2076 | 2076-02-17
|  |  | Memorial Day | 2076 | 2076-05-25
|  |  | Independence Day Observed | 2076 | 2076-07-03
|  |  | Labor Day | 2076 | 2076-09-07
|  |  | Columbus Day | 2076 | 2076-10-12
|  |  | Veterans Day Observed | 2076 | 2076-11-11
|  |  | Thanksgiving Day | 2076 | 2076-11-26
|  |  | Day After Thanksgiving Day | 2076 | 2076-11-27
|  |  | Christmas Day Observed | 2076 | 2076-12-25
|  |  | New Years Day Observed | 2077 | 2077-01-01
|  |  | Martin Luther King Day | 2077 | 2077-01-18
|  |  | Presidents' Day | 2077 | 2077-02-15
|  |  | Memorial Day | 2077 | 2077-05-31
|  |  | Independence Day Observed | 2077 | 2077-07-05
|  |  | Labor Day | 2077 | 2077-09-06
|  |  | Columbus Day | 2077 | 2077-10-11
|  |  | Veterans Day Observed | 2077 | 2077-11-11
|  |  | Thanksgiving Day | 2077 | 2077-11-25
|  |  | Day After Thanksgiving Day | 2077 | 2077-11-26
|  |  | Christmas Day Observed | 2077 | 2077-12-24
|  |  | New Years Day Observed | 2077 | 2077-12-31
|  |  | Martin Luther King Day | 2078 | 2078-01-17
|  |  | Presidents' Day | 2078 | 2078-02-21
|  |  | Memorial Day | 2078 | 2078-05-30
|  |  | Independence Day Observed | 2078 | 2078-07-04
|  |  | Labor Day | 2078 | 2078-09-05
|  |  | Columbus Day | 2078 | 2078-10-10
|  |  | Veterans Day Observed | 2078 | 2078-11-11
|  |  | Thanksgiving Day | 2078 | 2078-11-24
|  |  | Day After Thanksgiving Day | 2078 | 2078-11-25
|  |  | Christmas Day Observed | 2078 | 2078-12-26
|  |  | New Years Day Observed | 2079 | 2079-01-02
|  |  | Martin Luther King Day | 2079 | 2079-01-16
|  |  | Presidents' Day | 2079 | 2079-02-20
|  |  | Memorial Day | 2079 | 2079-05-29
|  |  | Independence Day Observed | 2079 | 2079-07-04
|  |  | Labor Day | 2079 | 2079-09-04
|  |  | Columbus Day | 2079 | 2079-10-09
|  |  | Veterans Day Observed | 2079 | 2079-11-10
|  |  | Thanksgiving Day | 2079 | 2079-11-23
|  |  | Day After Thanksgiving Day | 2079 | 2079-11-24
|  |  | Christmas Day Observed | 2079 | 2079-12-25
|  |  | New Years Day Observed | 2080 | 2080-01-01
|  |  | Martin Luther King Day | 2080 | 2080-01-15
|  |  | Presidents' Day | 2080 | 2080-02-19
|  |  | Memorial Day | 2080 | 2080-05-27
|  |  | Independence Day Observed | 2080 | 2080-07-04
|  |  | Labor Day | 2080 | 2080-09-02
|  |  | Columbus Day | 2080 | 2080-10-14
|  |  | Veterans Day Observed | 2080 | 2080-11-11
|  |  | Thanksgiving Day | 2080 | 2080-11-28
|  |  | Day After Thanksgiving Day | 2080 | 2080-11-29
|  |  | Christmas Day Observed | 2080 | 2080-12-25
|  |  | New Years Day Observed | 2081 | 2081-01-01
|  |  | Martin Luther King Day | 2081 | 2081-01-20
|  |  | Presidents' Day | 2081 | 2081-02-17
|  |  | Memorial Day | 2081 | 2081-05-26
|  |  | Independence Day Observed | 2081 | 2081-07-04
|  |  | Labor Day | 2081 | 2081-09-01
|  |  | Columbus Day | 2081 | 2081-10-13
|  |  | Veterans Day Observed | 2081 | 2081-11-11
|  |  | Thanksgiving Day | 2081 | 2081-11-27
|  |  | Day After Thanksgiving Day | 2081 | 2081-11-28
|  |  | Christmas Day Observed | 2081 | 2081-12-25
|  |  | New Years Day Observed | 2082 | 2082-01-01
|  |  | Martin Luther King Day | 2082 | 2082-01-19
|  |  | Presidents' Day | 2082 | 2082-02-16
|  |  | Memorial Day | 2082 | 2082-05-25
|  |  | Independence Day Observed | 2082 | 2082-07-03
|  |  | Labor Day | 2082 | 2082-09-07
|  |  | Columbus Day | 2082 | 2082-10-12
|  |  | Veterans Day Observed | 2082 | 2082-11-11
|  |  | Thanksgiving Day | 2082 | 2082-11-26
|  |  | Day After Thanksgiving Day | 2082 | 2082-11-27
|  |  | Christmas Day Observed | 2082 | 2082-12-25
|  |  | New Years Day Observed | 2083 | 2083-01-01
|  |  | Martin Luther King Day | 2083 | 2083-01-18
|  |  | Presidents' Day | 2083 | 2083-02-15
|  |  | Memorial Day | 2083 | 2083-05-31
|  |  | Independence Day Observed | 2083 | 2083-07-05
|  |  | Labor Day | 2083 | 2083-09-06
|  |  | Columbus Day | 2083 | 2083-10-11
|  |  | Veterans Day Observed | 2083 | 2083-11-11
|  |  | Thanksgiving Day | 2083 | 2083-11-25
|  |  | Day After Thanksgiving Day | 2083 | 2083-11-26
|  |  | Christmas Day Observed | 2083 | 2083-12-24
|  |  | New Years Day Observed | 2083 | 2083-12-31
|  |  | Martin Luther King Day | 2084 | 2084-01-17
|  |  | Presidents' Day | 2084 | 2084-02-21
|  |  | Memorial Day | 2084 | 2084-05-29
|  |  | Independence Day Observed | 2084 | 2084-07-04
|  |  | Labor Day | 2084 | 2084-09-04
|  |  | Columbus Day | 2084 | 2084-10-09
|  |  | Veterans Day Observed | 2084 | 2084-11-10
|  |  | Thanksgiving Day | 2084 | 2084-11-23
|  |  | Day After Thanksgiving Day | 2084 | 2084-11-24
|  |  | Christmas Day Observed | 2084 | 2084-12-25
|  |  | New Years Day Observed | 2085 | 2085-01-01
|  |  | Martin Luther King Day | 2085 | 2085-01-15
|  |  | Presidents' Day | 2085 | 2085-02-19
|  |  | Memorial Day | 2085 | 2085-05-28
|  |  | Independence Day Observed | 2085 | 2085-07-04
|  |  | Labor Day | 2085 | 2085-09-03
|  |  | Columbus Day | 2085 | 2085-10-08
|  |  | Veterans Day Observed | 2085 | 2085-11-12
|  |  | Thanksgiving Day | 2085 | 2085-11-22
|  |  | Day After Thanksgiving Day | 2085 | 2085-11-23
|  |  | Christmas Day Observed | 2085 | 2085-12-25
|  |  | New Years Day Observed | 2086 | 2086-01-01
|  |  | Martin Luther King Day | 2086 | 2086-01-21
|  |  | Presidents' Day | 2086 | 2086-02-18
|  |  | Memorial Day | 2086 | 2086-05-27
|  |  | Independence Day Observed | 2086 | 2086-07-04
|  |  | Labor Day | 2086 | 2086-09-02
|  |  | Columbus Day | 2086 | 2086-10-14
|  |  | Veterans Day Observed | 2086 | 2086-11-11
|  |  | Thanksgiving Day | 2086 | 2086-11-28
|  |  | Day After Thanksgiving Day | 2086 | 2086-11-29
|  |  | Christmas Day Observed | 2086 | 2086-12-25
|  |  | New Years Day Observed | 2087 | 2087-01-01
|  |  | Martin Luther King Day | 2087 | 2087-01-20
|  |  | Presidents' Day | 2087 | 2087-02-17
|  |  | Memorial Day | 2087 | 2087-05-26
|  |  | Independence Day Observed | 2087 | 2087-07-04
|  |  | Labor Day | 2087 | 2087-09-01
|  |  | Columbus Day | 2087 | 2087-10-13
|  |  | Veterans Day Observed | 2087 | 2087-11-11
|  |  | Thanksgiving Day | 2087 | 2087-11-27
|  |  | Day After Thanksgiving Day | 2087 | 2087-11-28
|  |  | Christmas Day Observed | 2087 | 2087-12-25
|  |  | New Years Day Observed | 2088 | 2088-01-01
|  |  | Martin Luther King Day | 2088 | 2088-01-19
|  |  | Presidents' Day | 2088 | 2088-02-16
|  |  | Memorial Day | 2088 | 2088-05-31
|  |  | Independence Day Observed | 2088 | 2088-07-05
|  |  | Labor Day | 2088 | 2088-09-06
|  |  | Columbus Day | 2088 | 2088-10-11
|  |  | Veterans Day Observed | 2088 | 2088-11-11
|  |  | Thanksgiving Day | 2088 | 2088-11-25
|  |  | Day After Thanksgiving Day | 2088 | 2088-11-26
|  |  | Christmas Day Observed | 2088 | 2088-12-24
|  |  | New Years Day Observed | 2088 | 2088-12-31
|  |  | Martin Luther King Day | 2089 | 2089-01-17
|  |  | Presidents' Day | 2089 | 2089-02-21
|  |  | Memorial Day | 2089 | 2089-05-30
|  |  | Independence Day Observed | 2089 | 2089-07-04
|  |  | Labor Day | 2089 | 2089-09-05
|  |  | Columbus Day | 2089 | 2089-10-10
|  |  | Veterans Day Observed | 2089 | 2089-11-11
|  |  | Thanksgiving Day | 2089 | 2089-11-24
|  |  | Day After Thanksgiving Day | 2089 | 2089-11-25
|  |  | Christmas Day Observed | 2089 | 2089-12-26
|  |  | New Years Day Observed | 2090 | 2090-01-02
|  |  | Martin Luther King Day | 2090 | 2090-01-16
|  |  | Presidents' Day | 2090 | 2090-02-20
|  |  | Memorial Day | 2090 | 2090-05-29
|  |  | Independence Day Observed | 2090 | 2090-07-04
|  |  | Labor Day | 2090 | 2090-09-04
|  |  | Columbus Day | 2090 | 2090-10-09
|  |  | Veterans Day Observed | 2090 | 2090-11-10
|  |  | Thanksgiving Day | 2090 | 2090-11-23
|  |  | Day After Thanksgiving Day | 2090 | 2090-11-24
|  |  | Christmas Day Observed | 2090 | 2090-12-25
|  |  | New Years Day Observed | 2091 | 2091-01-01
|  |  | Martin Luther King Day | 2091 | 2091-01-15
|  |  | Presidents' Day | 2091 | 2091-02-19
|  |  | Memorial Day | 2091 | 2091-05-28
|  |  | Independence Day Observed | 2091 | 2091-07-04
|  |  | Labor Day | 2091 | 2091-09-03
|  |  | Columbus Day | 2091 | 2091-10-08
|  |  | Veterans Day Observed | 2091 | 2091-11-12
|  |  | Thanksgiving Day | 2091 | 2091-11-22
|  |  | Day After Thanksgiving Day | 2091 | 2091-11-23
|  |  | Christmas Day Observed | 2091 | 2091-12-25
|  |  | New Years Day Observed | 2092 | 2092-01-01
|  |  | Martin Luther King Day | 2092 | 2092-01-21
|  |  | Presidents' Day | 2092 | 2092-02-18
|  |  | Memorial Day | 2092 | 2092-05-26
|  |  | Independence Day Observed | 2092 | 2092-07-04
|  |  | Labor Day | 2092 | 2092-09-01
|  |  | Columbus Day | 2092 | 2092-10-13
|  |  | Veterans Day Observed | 2092 | 2092-11-11
|  |  | Thanksgiving Day | 2092 | 2092-11-27
|  |  | Day After Thanksgiving Day | 2092 | 2092-11-28
|  |  | Christmas Day Observed | 2092 | 2092-12-25
|  |  | New Years Day Observed | 2093 | 2093-01-01
|  |  | Martin Luther King Day | 2093 | 2093-01-19
|  |  | Presidents' Day | 2093 | 2093-02-16
|  |  | Memorial Day | 2093 | 2093-05-25
|  |  | Independence Day Observed | 2093 | 2093-07-03
|  |  | Labor Day | 2093 | 2093-09-07
|  |  | Columbus Day | 2093 | 2093-10-12
|  |  | Veterans Day Observed | 2093 | 2093-11-11
|  |  | Thanksgiving Day | 2093 | 2093-11-26
|  |  | Day After Thanksgiving Day | 2093 | 2093-11-27
|  |  | Christmas Day Observed | 2093 | 2093-12-25
|  |  | New Years Day Observed | 2094 | 2094-01-01
|  |  | Martin Luther King Day | 2094 | 2094-01-18
|  |  | Presidents' Day | 2094 | 2094-02-15
|  |  | Memorial Day | 2094 | 2094-05-31
|  |  | Independence Day Observed | 2094 | 2094-07-05
|  |  | Labor Day | 2094 | 2094-09-06
|  |  | Columbus Day | 2094 | 2094-10-11
|  |  | Veterans Day Observed | 2094 | 2094-11-11
|  |  | Thanksgiving Day | 2094 | 2094-11-25
|  |  | Day After Thanksgiving Day | 2094 | 2094-11-26
|  |  | Christmas Day Observed | 2094 | 2094-12-24
|  |  | New Years Day Observed | 2094 | 2094-12-31
|  |  | Martin Luther King Day | 2095 | 2095-01-17
|  |  | Presidents' Day | 2095 | 2095-02-21
|  |  | Memorial Day | 2095 | 2095-05-30
|  |  | Independence Day Observed | 2095 | 2095-07-04
|  |  | Labor Day | 2095 | 2095-09-05
|  |  | Columbus Day | 2095 | 2095-10-10
|  |  | Veterans Day Observed | 2095 | 2095-11-11
|  |  | Thanksgiving Day | 2095 | 2095-11-24
|  |  | Day After Thanksgiving Day | 2095 | 2095-11-25
|  |  | Christmas Day Observed | 2095 | 2095-12-26
|  |  | New Years Day Observed | 2096 | 2096-01-02
|  |  | Martin Luther King Day | 2096 | 2096-01-16
|  |  | Presidents' Day | 2096 | 2096-02-20
|  |  | Memorial Day | 2096 | 2096-05-28
|  |  | Independence Day Observed | 2096 | 2096-07-04
|  |  | Labor Day | 2096 | 2096-09-03
|  |  | Columbus Day | 2096 | 2096-10-08
|  |  | Veterans Day Observed | 2096 | 2096-11-12
|  |  | Thanksgiving Day | 2096 | 2096-11-22
|  |  | Day After Thanksgiving Day | 2096 | 2096-11-23
|  |  | Christmas Day Observed | 2096 | 2096-12-25
|  |  | New Years Day Observed | 2097 | 2097-01-01
|  |  | Martin Luther King Day | 2097 | 2097-01-21
|  |  | Presidents' Day | 2097 | 2097-02-18
|  |  | Memorial Day | 2097 | 2097-05-27
|  |  | Independence Day Observed | 2097 | 2097-07-04
|  |  | Labor Day | 2097 | 2097-09-02
|  |  | Columbus Day | 2097 | 2097-10-14
|  |  | Veterans Day Observed | 2097 | 2097-11-11
|  |  | Thanksgiving Day | 2097 | 2097-11-28
|  |  | Day After Thanksgiving Day | 2097 | 2097-11-29
|  |  | Christmas Day Observed | 2097 | 2097-12-25
|  |  | New Years Day Observed | 2098 | 2098-01-01
|  |  | Martin Luther King Day | 2098 | 2098-01-20
|  |  | Presidents' Day | 2098 | 2098-02-17
|  |  | Memorial Day | 2098 | 2098-05-26
|  |  | Independence Day Observed | 2098 | 2098-07-04
|  |  | Labor Day | 2098 | 2098-09-01
|  |  | Columbus Day | 2098 | 2098-10-13
|  |  | Veterans Day Observed | 2098 | 2098-11-11
|  |  | Thanksgiving Day | 2098 | 2098-11-27
|  |  | Day After Thanksgiving Day | 2098 | 2098-11-28
|  |  | Christmas Day Observed | 2098 | 2098-12-25
|  |  | New Years Day Observed | 2099 | 2099-01-01
|  |  | Martin Luther King Day | 2099 | 2099-01-19
|  |  | Presidents' Day | 2099 | 2099-02-16
|  |  | Memorial Day | 2099 | 2099-05-25
|  |  | Independence Day Observed | 2099 | 2099-07-03
|  |  | Labor Day | 2099 | 2099-09-07
|  |  | Columbus Day | 2099 | 2099-10-12
|  |  | Veterans Day Observed | 2099 | 2099-11-11
|  |  | Thanksgiving Day | 2099 | 2099-11-26
|  |  | Day After Thanksgiving Day | 2099 | 2099-11-27
|  |  | Christmas Day Observed | 2099 | 2099-12-25
Formulas:
Start = [Finish, row above]+1