## High Level expanded
EIC EXPERIMENTAL EQUIPMENT | [6 empty] | References
PRELIMINARY MILESTONES | [6 empty] | 1. JLab Hall B: 5T Superconducting solenoid (approx. 5 years to construct)
Version No. | 3
Date | 06.24.2021
Engineer | Renuka Rajput-Ghoshal
|  |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33
Conceptual design
Design Down-select
Material Down-select
Preliminary Design
Request for Information (RFI) to vendors
Detailed Design
Request for Quotation (RFQ)
Magnet Procurement
Magnet Final Design and Build
Installation in Assembly Hall
CD-0
Dec-2019
CD-1
June 2021
CD-2/3A
April 2023
CD-3
July 2024
Early CD-4a
Q3FY30
Early CD-4
Q3FY31
CD-4a
Q3FY31
CD-4
Q3FY33
15 mths
60 mths
17 mths
15 mths
15 mths

## Solenoid installation
EIC Detector Solenoid
Preliminary Installation Schedule
Version No. | 2
Date | 12.17.20
Engineer | Renuka Rajput-Ghoshal
Reviewers | Ruben Fair, Rolf Ent, Elke-Caroline Aschenauer
Task Number | Task Details | Before magnet arrives | week 1-4 | week 5-8 | week 9-12 | week 13-16 | week 17-20 | week 21-24 | week 25-28 | week 29-32 | week 33-36 | week 37-40 | week 41-44 | week 45-48 | week 49-52 | week 53-56 | week 57-60 | week 61-64 | week 65-68 | week 69-72
1 | Install Cradle (3 month)
2 | Install lower half of the Barrel Hcal (2.5 month)
3 | Solenoid arrival check
4 | Installation
4.1 | Install Solenoid
4.2 | Install upper half of the Barrel Hcal
5 | Cryocan
5.1 | Cryocan Fabrication | Cryocan Fabrication can be done before installation starts
5.2 | Cryocan Installation in the Hall
5.3 | Cryocan Pressure system Review
5.4 | Magnet Pressure system reviw
6 | Electrical
6.1 | Power supply and I&C procurmeent and Installation | Power supply and I&C Fabrication can be done before installation starts
6.2 | Power supply and I&C checks
7 | Pre-installation checks and connections
7.1 | Solenoid pre-installation for cryo and INC checks
7.2 | Connecting Cryocan to the magnet
7.3 | Connecting power supply and I&C to the magnet
7.4 | Low power test
8 | Hcal endcap installation | This can start any time as soon as one has access to the IR, but ideally after low power test
9 | Cryogenic operation set up
10 | Solenoid pump down
11 | Cool Down Review
11 | Solenoid cool down (from Room temp. to He-temp)
12 | Final checks
13 | Readiness/Power up review
14 | Low power cryogenic and magnet test
15 | High power test
16 | Roll in to Collision Hall
17 | Field mapping
18 | Roll into Assmbley Hall
19 | Install Barrel Ecal, DIRC, TPC
20 | Install electron and hadron endcap detectors
21 | Install Muvertex detector (3.5 month) | but to install the mu-vertex, at least one half of the endcap detectors need to be removed to install the mu-vertex
21.1 | Roll Detector in the assemlby Hall
21.2 | De-install lepton endcap detectors
21.3 | Install mu-vertex dectector
21.4 | Install hadron-endcap or electron endcap detectors
21.5 | Roll back into IR

## High Level
EIC EXPERIMENTAL EQUIPMENT | [5 empty] | References
PRELIMINARY MILESTONES | [5 empty] | 1. JLab Hall B: 5T Superconducting solenoid (approx. 5 years to construct)
| Version No. | 2
| Date | 06.15.2021
| Engineer | Renuka Rajput-Ghoshal
|  |  |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33
NEW SOLENOID
Conceptual design
Preliminary Design
Final Design
Construction (includes procurements)
Installation in Assembly Hall
REFURBISHED BABAR SOLENOID
Conceptual design
Preliminary Design
Final Design
Construction (includes procurements and cryo can)
|  |  | Deinstall detector components inside barrel (5 mths) | FY27: If the outer Hcal needs to be removed it will add 5m
|  |  | Construction (Refurbishment + Trim Coil + Iron Mods) | FY26: 30 mths + 6 mths + 6 mths = 42 mths
Installation in Assembly Hall
Commissioning and Pre-Ops
Note on F16: Renuka Rajput-Ghoshal: I think we should add some time for the procurement process here! Probably 6 months or so?
Early CD-4a
Q3FY30
Early CD-4
Q3FY31
15 mths
60 mths
17 mths
15 mths
15 mths
15 mths
18 mths
12 mths
24 mths
5 mths
17 mths
6 m
BABAR Magnet
Available FY26
CD-4a
Q3FY31
CD-4
Q3FY33
42 mths
CD-0
Dec-2019
CD-1
June 2021
CD-2/3A
April 2023
CD-3
July 2024