## Slide 1
Cost and Schedule estimates
In support of the EICSC silicon tracking detector models
The document images provided In these slides are obviously too small to read easily. The full original files can be found at: https://drive.google.com/drive/folders/1FnKxdKmx12GPCRavtxmuQLwkLokao9Qp?usp=sharing

## Slide 2
What has been generated – Cost estimates
Four DRAFT cost estimates for detector construction
All-silicon model as per YR
Hybrid base (all-silicon with the outer layers removed and the appropriate changes propagated through the rest of the estimate) to be used as a basis for hybrid configurations.
All silicon model with 3 vertexing layers (27cm active length).
Hybrid base as above but with 3 vertexing layers (27cm active length).
Attributes
These are full bottom-up cost estimates in excel format broken out into simple labor categories and materials.
Caveats, explanations and assumptions are shown in the comments and introductory table cells.
These estimates are being provided as input for the proto-collaboration internal cost estimation process.
These estimated are not fully “scrubbed”, but as our state of knowledge about the final configuration is not yet well developed, they are, in my opinion, the best level of estimation appropriate to this stage of the project. Please use the appropriate version with the latest date (currently 2021_10_19) in the cost estimates folder as we are “scrubbing” the cost estimates continuously and making improvements.

## Slide 3
Cost estimates - Structure
These are large documents (all-silicon is 448 lines)
The upper level WBS elements are chosen to be localized detector elements to facilitate the easy removal or increase in numbers to match a configuration requested by a proto-collaboration.
Each of the major subsystem task (red) has a rollup row (blue) that gives a total for the tasks in that category (bold)
It is intended that these sub-task rollups be used as a set of task summaries to represent the full estimate if desired.
These rollups are summed at the end of the table to provide the full cost estimate.
All estimates in todays dollars (no escalation) and todays exchange rates.

## Slide 4
Cost estimates – Summary, Comments and questions
Some items listed in the cost estimates may belong in other WBS. E.g. power supplies and travel may be covered in an integration WBS. These items may be deducted from the cost estimate as presented.
The design of the spreadsheet is intended to make the scaling (in quantity) and addition/removal of components as easy as possible within a reasonable creation time.
Scaling up or down with disc or stave sizes in not recommended without a reanalysis of the feasibility, mechanics and propagation of material changes into the simulations. As one can see from the difference between the hybrid and the all-silicon estimates, simple scaling by area for silicon tracking detector costs is not accurate.
It appears that this met the needs of the proto-collaborations, we have made individualized changes as requests have come in.

## Slide 5
Schedule estimates
The rollup task lines of the all-silicon cost estimate were transferred into a MS project document as tasks.
The durations of these tasks were estimated by me. They are not a simple convolution of the hours in the task lines but rather an experience based estimation.
Simple dependencies are added to give a reasonable approximation of what can be expected.
This is NOT a resource loaded schedule, which is the only real way to answer questions about labor force needs in a timeframe or assess true in-rollup task dependencies.
This technically driven schedule represents a best estimate minimum time possible for construction without resource constraints. The actual construction time will be longer.
The results are consistent with previous experience.
This estimate is available as an .mpp file.
If the hybrid design is selected, it can likely be fabricated in less time, but this is not explicitly explored.

## Slide 6
Start time is arbitrary, but listed as October 1, 2024 in this estimate.
The unconstrained construction project completes in ~2.5 years.
This is roughly consistent with other construction projects of this complexity and technology.
There is, of course, no slack estimates or contingency in this formulation.
Future exercises with a resource loaded schedule doing resource leveling will extend the timeframe, but this is outside of the scope of this estimate.
Schedule estimates

## Slide 7
R&D cost estimation
The previous estimates cover the construction phase, which may be of different amounts depending on the detector configuration shown.
The R&D needed to develop sensors and detector components are common for all configurations and have been estimated in draft form to bring the silicon development to CD-3 level of readiness.
This estimate is available at the linked folder shown before.
However, as the estimate is the same for all proto-collaborations, the entry of this information into the project spreadsheets will be common.
It is suggested that this be done once and used by all proto-collaborations as a common element of the proposals.