## BCWR - Cat A
Baseline data |  |  |  | Forecast Data (July status file - path June by hand)
Activity ID | Activity Name | Budgeted Units | Budgeted Cost | Forecast Start | Forecast Finish | % Complete | Resource ID Name | Calc ETC Units | Updated ETC Units | Potential PCR? | Calc ETC Cost | Updated ETC Cost | EAC Growth | Fraction Under Contract | Fraction Pay-as-you-go | Fraction To-Be-Contracted | Updated ETC Under Contract | Updated ETC Pay-as-you-go | Updated ETC To-Be-Contracted | P6 Sums to Compare to B&E/Kelly Carroll Values - only include things ordered and/or with Webreq; No pay-as-you-go labor
A-TEC TEC
POM02.01.01.02 Labor by FY |  |  |  | 01-Oct-21 A | 2022-01-05
S103400 | Mgmt labor - A - MIE - FY22 | 68 | 11360.99 | 01-Oct-21 A | 2022-01-05 | 61.9% | PM Spec - PS | 25.908 |  |  | 4328.5372 | 4328.5372 | 0 |  | 1 |  | 0 | 4328.5372 | 0
POM02.01.02.01.08 TPC Assembly |  |  |  | 01-Feb-21 A | 2022-01-20 | [14 empty] | 0
S121605 | TPC Assembly Mechanical Engineering Support | 1500 | 156597.44 | 01-Feb-21 A | 2022-01-20 | 86.01% | PROF2 | 209.85 |  |  | 21907.9819 | 21907.9819 | 0 |  | 1 |  | 0 | 21907.9819 | 0 | TPC Assembly work
S121950 | TPC Assembly technical Support | 20000 | 23333.76 | 01-Jun-21 A | 2021-12-15 | 90.52% | Purch 1st $2M | 1896 |  |  | 2212.0404 | 2212.0404 | 0 |  | 1 |  | 0 | 2212.0404 | 0
POM02.01.02.05.04 TPC FEE Production |  |  |  | 02-Nov-20 A | 2021-12-29 | [14 empty] | 206405.8061
S141800 | Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | 266694 | 309547.54 | 02-Nov-20 A | 2021-12-15 | 97% | Purch 1st $2M | 8000.82 |  |  | 9286.4262 | 9286.4262 | 0 | 1 |  |  | 9286.4262 | 0 | 0 | TPC FEE work
S142500 | Procure TPC FEE LV Power Supplies - Delivery Acceptance | 190056 | 220595.02 | 25-Jan-21 A | 2021-12-15 | 86% | Purch 1st $2M | 26607.84 |  |  | 30883.3028 | 30883.3028 | 0 | 1 |  |  | 30883.3028 | 0 | 0
S143200 | Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | 150983 | 178748.47 | 11-Oct-21 A | 2021-12-22 | 7% | Purch 1st $2M | 140414.19 |  |  | 166236.0771 | 166236.0771 | 0 | 1 |  |  | 166236.0771 | 0 | 0
S143270 | TPC FEE Electrical Engineering Support 1 | 1500 | 120025.52 | 01-Feb-21 A | 2021-12-29 | 91.3% | TECH1 | 130.5 |  |  | 10442.2202 | 10442.2202 | 0 |  | 1 |  | 0 | 10442.2202 | 0
POM02.01.02.06.03 TPC DAM Production |  |  |  | 01-Feb-21 A | 2022-03-29 | [14 empty] | 0
S147370 | Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Delivery Acceptance | 80745 | 95593.84 | 2022-03-23 | 2022-03-29 | 0% | Purch 1st $2M | 80745 |  |  | 95593.84 | 95593.84 | 0 |  |  | 1 | 0 | 0 | 95593.84 | TPC DAM work
S147380 | TPC DAM Electrical Engineering Support | 368 | 48446.29 | 01-Feb-21 A | 2022-01-14 | 90% | PROF3 | 36.8 |  |  | 4844.629 | 4844.629 | 0 |  | 1 |  | 0 | 4844.629 | 0
POM02.01.02.07.01 TPC Laser System |  |  |  | 06-Oct-20 A | 2021-12-30 | [14 empty] | 243534.78
S149600 | Procure TPC Lasers - Delivery Acceptance | 145840 | 169274.2 | 06-Oct-20 A | 2021-12-30 | 50% | Purch 1st $2M | 72920 |  |  | 84637.1 | 84637.1 | 0 | 1 |  |  | 84637.1 | 0 | 0 | TPC laser, gas, cooling all
S149650 | TPC Diffuse Lasers | 200000 | 232136.86 | 04-Jan-21 A | 2021-12-30 | 50% | Purch 1st $2M | 100000 |  |  | 116068.43 | 116068.43 | 0 | 1 |  |  | 116068.43 | 0 | 0 | rolled up into this line
S150300 | Procure TPC Optics with Mirrors - Delivery Acceptance | 58800 | 68248.24 | 13-Oct-20 A | 2021-12-30 | 50% | Purch 1st $2M | 29400 |  |  | 34124.12 | 34124.12 | 0 | 1 |  |  | 34124.12 | 0 | 0
S150500 | Procure TPC mirror bundles with supports M&S | 15000 | 17410.26 | 13-Jan-21 A | 2021-12-30 | 50% | Purch 1st $2M | 7500 |  |  | 8705.13 | 8705.13 | 0 | 1 |  |  | 8705.13 | 0 | 0
POM02.01.02.07.02 TPC Gas System |  |  |  | 12-Jan-21 A | 2022-03-21
S152300 | Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | 33035 | 38343.21 | 12-Jan-21 A | 2021-12-30 | 80% | Purch 1st $2M | 6607 |  |  | 7668.642 | 7668.642 | 0 |  |  | 1 | 0 | 0 | 7668.642
S153000 | Procure TPC Gas System Computer Controller M&S | 18401 | 21784.91 | 2022-01-03 | 2022-02-22 | 0% | Purch 1st $2M | 18401 |  |  | 21784.91 | 21784.91 | 0 |  |  | 1 | 0 | 0 | 21784.91
S153700 | Procure TPC Gas System Components for Installation - Delivery Acceptance | 34086 | 40354.35 | 08-Mar-21 A | 2022-03-21 | 80% | Purch 1st $2M | 6817.2 |  |  | 8070.87 | 8070.87 | 0 |  |  | 1 | 0 | 0 | 8070.87
POM02.01.03.01.03.01 Order Material for EMCAL Final Block Production |  |  |  | 03-Aug-20 A | 2021-12-14 | [14 empty] | 30382.0791
S171800 | Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | 90653 | 104858.47 | 03-Aug-20 A | 2021-12-14 | 87% | UIUC Contracted Purchase | 11784.89 |  |  | 13631.6011 | 13631.6011 | 0 | 1 |  |  | 13631.6011 | 0 | 0 | EMCal block work
POM02.01.03.01.03.02 Fabricate final blocks |  |  |  | 29-Nov-21 A | 2021-12-17
S177900 | Fabricate final blocks sector 62 | 50 | 2742.89 | 29-Nov-21 A | 2021-12-03 | 80% | TECH3 UIUC - PS | 10 |  |  | 548.578 | 548.578 | 0 | 1 |  |  | 548.578 | 0 | 0
S177900 | Fabricate final blocks sector 62 | 75 | 1377.57 | 29-Nov-21 A | 2021-12-03 | 80% | STUDENT UIUC - PS | 15 |  |  | 275.514 | 275.514 | 0 | 1 |  |  | 275.514 | 0 | 0
S177900 | Fabricate final blocks sector 62 | 10 | 1197.12 | 29-Nov-21 A | 2021-12-03 | 80% | TECH3 Senior UIUC - PS | 2 |  |  | 239.424 | 239.424 | 0 | 1 |  |  | 239.424 | 0 | 0
S178000 | Fabricate final blocks sector 63 | 50 | 2742.89 | 2021-12-06 | 2021-12-10 | 0% | TECH3 UIUC - PS | 50 |  |  | 2742.89 | 2742.89 | 0 | 1 |  |  | 2742.89 | 0 | 0
S178000 | Fabricate final blocks sector 63 | 75 | 1377.57 | 2021-12-06 | 2021-12-10 | 0% | STUDENT UIUC - PS | 75 |  |  | 1377.57 | 1377.57 | 0 | 1 |  |  | 1377.57 | 0 | 0
S178000 | Fabricate final blocks sector 63 | 10 | 1197.12 | 2021-12-06 | 2021-12-10 | 0% | TECH3 Senior UIUC - PS | 10 |  |  | 1197.12 | 1197.12 | 0 | 1 |  |  | 1197.12 | 0 | 0
S178100 | Fabricate final blocks sector 64 | 50 | 2742.89 | 2021-12-13 | 2021-12-17 | 0% | TECH3 UIUC - PS | 50 |  |  | 2742.89 | 2742.89 | 0 | 1 |  |  | 2742.89 | 0 | 0
S178100 | Fabricate final blocks sector 64 | 75 | 1377.57 | 2021-12-13 | 2021-12-17 | 0% | STUDENT UIUC - PS | 75 |  |  | 1377.57 | 1377.57 | 0 | 1 |  |  | 1377.57 | 0 | 0
S178100 | Fabricate final blocks sector 64 | 10 | 1197.12 | 2021-12-13 | 2021-12-17 | 0% | TECH3 Senior UIUC - PS | 10 |  |  | 1197.12 | 1197.12 | 0 | 1 |  |  | 1197.12 | 0 | 0
POM02.01.03.01.03.03 Pack and ship final blocks to BNL |  |  |  | 26-Oct-21 A | 2021-12-20
S176010 | Pack and ship final blocks for sectors 57-64 to BNL - M&S | 6480 | 7671.66 | 26-Oct-21 A | 2021-12-20 | 51% | UIUC Contracted Purchase | 3175.2 |  |  | 3759.1134 | 3759.1134 | 0 | 1 |  |  | 3759.1134 | 0 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 16 | 293.88 | 26-Oct-21 A | 2021-12-20 | 51% | STUDENT UIUC - PS | 7.84 |  |  | 144.0012 | 144.0012 | 0 | 1 |  |  | 144.0012 | 0 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 10 | 548.58 | 26-Oct-21 A | 2021-12-20 | 51% | TECH3 UIUC - PS | 4.9 |  |  | 268.8042 | 268.8042 | 0 | 1 |  |  | 268.8042 | 0 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 15 | 1795.68 | 26-Oct-21 A | 2021-12-20 | 51% | TECH3 Senior UIUC - PS | 7.35 |  |  | 879.8832 | 879.8832 | 0 | 1 |  |  | 879.8832 | 0 | 0
POM02.01.03.02.02.03 EMCAL Final Module Fabrication |  |  |  | 22-Dec-20 A | 2022-02-03 | [14 empty] | 5534.5907
S187400 | Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | 215244 | 240129.12 | 22-Dec-20 A | 2021-12-15 | 98% | Purch 1st $2M Fixed | 4304.88 |  |  | 4802.5824 | 4802.5824 | 0 | 1 |  |  | 4802.5824 | 0 | 0 | EMCal module & sector work
S187700 | Install light guides on final blocks M&S | 1650 | 1926.31 | 21-Jan-21 A | 2022-01-31 | 68% | Purch 1st $2M | 528 |  |  | 616.4192 | 616.4192 | 0 | 1 |  |  | 616.4192 | 0 | 0
S188100 | Install SiPMs daughterboards on final blocks M&S | 300 | 350.27 | 22-Jan-21 A | 2022-02-03 | 67% | Purch 1st $2M | 99 |  |  | 115.5891 | 115.5891 | 0 | 1 |  |  | 115.5891 | 0 | 0
POM02.01.03.02.03.03 EMCAL Final Production Sector Assembly |  |  |  | 04-Jan-21 A | 2022-03-25
S196910 | Technical support labor for EMCal assembly | 3520 | 281618.43 | 04-Jan-21 A | 2022-03-25 | 80% | TECH1 | 704 |  |  | 56323.686 | 56323.686 | 0 |  | 1 |  | 0 | 56323.686 | 0
POM02.01.05.02.02 EMCal Electronics: Production |  |  |  | 20-Jul-21 A | 2022-01-28 | [14 empty] | 898898.7025
S233200 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Delivery Acceptance | 177356 | 209971.41 | 20-Jul-21 A | 2022-01-03 | 75% | Purch 1st $2M | 44339 |  |  | 52492.8525 | 52492.8525 | 0 | 1 |  |  | 52492.8525 | 0 | 0
S233250 | Trunk Signal Cables - EMCal | 670160 | 790134.13 | 31-Aug-21 A | 2022-01-28 | 15% | Purch 1st $2M | 569636 |  |  | 671614.0105 | 671614.0105 | 0 | 1 |  |  | 671614.0105 | 0 | 0
S244450 | Trunk Signal Cables - OuterHCal | 128640 | 151669.53 | 31-Aug-21 A | 2022-01-28 | 15% | Purch 1st $2M | 109344 |  |  | 128919.1005 | 128919.1005 | 0 | 1 |  |  | 128919.1005 | 0 | 0
POM02.01.05.02.04 HCal Electronics: Production |  |  |  | 14-Dec-20 A | 2021-12-23
S244400 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | 87827 | 101939.42 | 14-Dec-20 A | 2021-12-23 | 55% | Purch 1st $2M | 39522.15 |  |  | 45872.739 | 45872.739 | 0 | 1 |  |  | 45872.739 | 0 | 0
POM02.01.05.03.02 Calorimeter Digitizers: Production |  |  |  | 30-Apr-21 A | 2022-02-28 | [14 empty] | 260020.0605
S252700 | Procure Production Digitizer (Parts) - Delivery Acceptance | 584602 | 678538.37 | 30-Apr-21 A | 2021-12-10 | 95% | Purch 1st $2M | 29230.1 |  |  | 33926.9185 | 33926.9185 | 0 | 1 |  |  | 33926.9185 | 0 | 0 | Digitizers
S252800 | Procure Production Digitizer (Boards) - Delivery Acceptance | 129049 | 152780.85 | 16-Aug-21 A | 2022-01-28 | 60% | Purch 1st $2M | 51619.6 |  |  | 61112.34 | 61112.34 | 0 | 1 |  |  | 61112.34 | 0 | 0
S252900 | Procure Production Digitizer (Assembly & Tests) - Delivery Acceptance | 199077 | 235686.86 | 16-Aug-21 A | 2022-02-28 | 30% | Purch 1st $2M | 139353.9 |  |  | 164980.802 | 164980.802 | 0 | 1 |  |  | 164980.802 | 0 | 0
POM02.01.06.01.03 DAQ Production |  |  |  | 2022-01-03 | 2022-04-04 | [14 empty] | 219658.06
S255900 | Procure DAQ Production Boards DCM2 - Delivery Acceptance | 104682 | 123932.81 | 2022-03-29 | 2022-04-04 | 0% | Purch 1st $2M | 104682 |  |  | 123932.81 | 123932.81 | 0 | 1 |  |  | 123932.81 | 0 | 0 | Remaining DAQ items
S256700 | Procure DAQ Production Crates - Delivery Acceptance | 64000 | 75769.47 | 2022-03-08 | 2022-03-14 | 0% | Purch 1st $2M | 64000 |  |  | 75769.47 | 75769.47 | 0 | 1 |  |  | 75769.47 | 0 | 0
S258700 | Procure DAQ Production jackboard Slow control computers - Delivery Acceptance | 16856 | 19955.78 | 2022-01-03 | 2022-01-07 | 0% | Purch 1st $2M | 16856 |  |  | 19955.78 | 19955.78 | 0 | 1 |  |  | 19955.78 | 0 | 0
POM02.01.06.02.03 LL1 Trigger Preproduction Prototype |  |  |  | 2021-12-20 | 2021-12-27 | [14 empty] | 209549.94
S263600 | Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance | 60000 | 71033.88 | 2021-12-20 | 2021-12-27 | 0% | Purch 1st $2M | 60000 |  |  | 71033.88 | 71033.88 | 0 | 1 |  |  | 71033.88 | 0 | 0 | LL-1 work (Nevis)
POM02.01.06.02.04 LL1 Trigger Production |  |  |  | 2022-03-03 | 2022-03-09
S264900 | Procure Production LL1 System - Delivery Acceptance | 117000 | 138516.06 | 2022-03-03 | 2022-03-09 | 0% | Purch 1st $2M | 117000 |  |  | 138516.06 | 138516.06 | 0 | 1 |  |  | 138516.06 | 0 | 0
POM02.01.06.03.03 GL1 Trigger Production |  |  |  | 15-Nov-21 A | 2022-02-01 | [14 empty] | 0
S267600 | Procure Production GL1 Components - final hardware - Delivery Acceptance | 28150 | 33326.73 | 15-Nov-21 A | 2022-02-01 | 20% | Purch 1st $2M | 22520 |  |  | 26661.384 | 26661.384 | 0 |  |  | 1 | 0 | 0 | 26661.384 | GL-1 and Timing
POM02.01.06.04.03 Timing System Production |  |  |  | 15-Nov-21 A | 2022-02-22
S270300 | Timing System Production (FPGA Boards) - Delivery Acceptance | 41600 | 49250.16 | 15-Nov-21 A | 2022-02-22 | 20% | Purch 1st $2M | 33280 |  |  | 39400.128 | 39400.128 | 0 |  |  | 1 | 0 | 0 | 39400.128
POM02.01.07 Min Bias Trigger Detector |  |  |  | 23-Aug-21 A | 2021-12-23 | [14 empty] | 61951.008
S273500 | Procure Min/Bias Electronics (sPHENIX Production Digitizers) - Delivery Acceptance | 14770 | 17486.17 | 23-Aug-21 A | 2021-12-23 | 60% | Purch 1st $2M | 5908 |  |  | 6994.468 | 6994.468 | 0 | 1 |  |  | 6994.468 | 0 | 0 | MBD work (Nevis)
S273600 | Procure MBD Shaper/Disc Board 128 Channels - Delivery Acceptance | 46420 | 54956.54 | 2021-12-16 | 2021-12-22 | 0% | Purch 1st $2M | 46420 |  |  | 54956.54 | 54956.54 | 0 | 1 |  |  | 54956.54 | 0 | 0
|  | 4005558 | 5311894.21 |  |  |  | 0 | 1974335.918 |  |  | 2435173.8956 | 2435173.8956 |  |  |  |  | 2135935.0269 | 100059.0947 | 199179.774
[17 empty] | P6 BCWR CHECKSUM | 2435173.8956
| JACK board for TPC FEE (verbal estimate)(reduce by $40K for AVNET FPGAs that will be in hand and $20K for parts on order) |  | 140000 | [8 empty] | 140000 |  |  |  | 1 | 0 | 0 | 140000
| Laser Motors/controls ($130K) -$40K in P6 |  | 90000 | [8 empty] | 90000 |  |  |  | 1 | 0 | 0 | 90000
| Sum of adjustments above |  | 230000
| TOTAL BCWR+Known Additions | [10 empty] | 2665173.8956 |  |  | TOTALs for "Fractions" |  | 2135935.0269 | 100059.0947 | 429179.774
Contracting Categories
Above
[17 empty] | Revised CHECKSUM with known additions | 2665173.8956

## BCWR - Cat C
Baseline data |  |  |  | Forecast Data (June status file)
Activity ID | Activity Name | Baseline Units | Baseline Cost | Forecast Start | Forecast Finish | % Complete | Resource ID Name | Calc ETC Units | Updated ETC Units | Potential PCR? | Calc ETC Cost | Updated ETC Cost | EAC Growth | M&S Fraction Under Contract | M&S Fraction Pay-as-you-go | M&S Fraction To-Be-Contracted | Labor Fraction Underway | Labor Fraction Pay-as-you-go (e.g. LOE) | Labor Fraction To-Be-Started | Updated ETC M&S Under Contract | Updated ETC M&S Pay-as-you-go | Updated ETC M&S To-Be-Contracted | Updated ETC Labor Underway | Updated ETC Labor Pay-as-you-go (e.g. LOE) | Updated ETC Labor To-Be-Started
C Infrastructure / Facility Upgrade
POM02.02.01.02 Magnet Management and Technical Oversight |  | 1232 | 224569.92 | 01-Oct-21 A | 2022-09-30
S274800 | 2022 Magnet Project Management | 880 | 161062.11 | 01-Oct-21 A | 2022-09-30 | 15.6% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 135936.4208 | 135936.4208 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 135936.4208 | 0
S275900 | 2022 PS & Quench Protection L3 Project Management | 352 | 63507.81 | 01-Oct-21 A | 2022-09-30 | 15.6% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 53600.5916 | 53600.5916 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 53600.5916 | 0
POM02.02.01.04 Infrastructure Management |  | 1305 | 162791.06 | 01-Oct-21 A | 2022-10-07
S276400 | 2022 Infrastructure Project Management | 800 | 107371.17 | 01-Oct-21 A | 2022-09-30 | 15.6% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 90621.2675 | 90621.2675 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 90621.2675 | 0
S276500 | 2023 Infrastructure Project Management | 40 | 5529.62 | 2022-10-03 | 2022-10-07 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 5529.62 | 5529.62 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 5529.62 | 0
S277000 | 2022 Facility Support Systems L3 Project Management | 352 | 37515.39 | 01-Oct-21 A | 2022-09-30 | 15.6% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 31662.9892 | 31662.9892 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 31662.9892 | 0
S277100 | 2023 Facility Support Systems L3 Project Management | 113 | 12374.89 | 2022-10-03 | 2022-10-07 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 12374.89 | 12374.89 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 12374.89 | 0
POM02.02.01.05 Installation Management |  | 1162 | 211555.35 | 01-Oct-21 A | 2022-10-05
S278200 | 2022 Integration & Installation Project Management | 880 | 159150.58 | 01-Oct-21 A | 2022-09-30 | 15.6% | PROF5 PO M | Labor Hr/M&S Direct$ |  |  | 134323.0895 | 134323.0895 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 134323.0895 | 0
S278300 | 2023 Integration & Installation Project Management | 282 | 52404.77 | 2022-10-03 | 2022-10-05 | 0% | PROF5 PO M | Labor Hr/M&S Direct$ |  |  | 52404.77 | 52404.77 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 52404.77 | 0
POM02.02.02.01.01 Safety Reviews |  | 112 | 21091.72 | 08-Mar-21 A | 2022-05-25
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 16 | 2921.39 | 08-Mar-21 A | 2022-05-23 | 58% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 1226.9838 | 1226.9838 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 1226.9838 | 0
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 8 | 1249.87 | 08-Mar-21 A | 2022-05-23 | 58% | PROF4 AM | Labor Hr/M&S Direct$ |  |  | 524.9454 | 524.9454 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 524.9454 | 0
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 16 | 3275.94 | 08-Mar-21 A | 2022-05-23 | 58% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 1375.8948 | 1375.8948 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 1375.8948 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | 16 | 2921.39 | 2022-05-24 | 2022-05-24 | 0% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 2921.39 | 2921.39 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 2921.39 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | 8 | 1249.87 | 2022-05-24 | 2022-05-24 | 0% | PROF4 AM | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 1249.87 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | 16 | 3275.94 | 2022-05-24 | 2022-05-24 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 3275.94 | 3275.94 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 3275.94 | 0
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 2921.39 | 2022-05-25 | 2022-05-25 | 0% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 2921.39 | 2921.39 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 2921.39 | 0
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 3275.94 | 2022-05-25 | 2022-05-25 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 3275.94 | 3275.94 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 3275.94 | 0
POM02.02.02.01.02 Cooldown & Power Tests |  | 724 |  | 2022-05-26 | 2022-07-05
S279100 | Cooldown | 60 | 8052.84 | 2022-05-26 | 2022-06-16 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 8052.84 | 8052.84 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8052.84
S279100 | Cooldown | 60 | 7264.33 | 2022-05-26 | 2022-06-16 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S279100 | Cooldown | 60 | 12284.77 | 2022-05-26 | 2022-06-16 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 12284.77 | 12284.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12284.77
S279200 | 4.5K Static Heat Load test | 8 | 1073.71 | 2022-06-17 | 2022-06-20 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 1073.71 | 1073.71 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1073.71
S279200 | 4.5K Static Heat Load test | 8 | 968.58 | 2022-06-17 | 2022-06-20 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S279200 | 4.5K Static Heat Load test | 8 | 1637.97 | 2022-06-17 | 2022-06-20 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 1637.97 | 1637.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1637.97
S279300 | 4.5K Low power test | 20 | 2684.28 | 2022-06-21 | 2022-06-27 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S279300 | 4.5K Low power test | 80 | 14606.95 | 2022-06-21 | 2022-06-27 | 0% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 14606.95 | 14606.95 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14606.95
S279300 | 4.5K Low power test | 80 | 9685.77 | 2022-06-21 | 2022-06-27 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S279300 | 4.5K Low power test | 80 | 16379.7 | 2022-06-21 | 2022-06-27 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 16379.7 | 16379.7 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 16379.7
S279400 | 4.5K High Power Test | 20 | 2684.28 | 2022-06-28 | 2022-07-05 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S279400 | 4.5K High Power Test | 80 | 14606.95 | 2022-06-28 | 2022-07-05 | 0% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 14606.95 | 14606.95 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14606.95
S279400 | 4.5K High Power Test | 80 | 9685.77 | 2022-06-28 | 2022-07-05 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S279400 | 4.5K High Power Test | 80 | 16379.7 | 2022-06-28 | 2022-07-05 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 16379.7 | 16379.7 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 16379.7
POM02.02.02.02 Magnet Transport & Assembly |  | 616 |  | 2022-02-25 | 2022-04-14
S281400 | Magnet and Solenoid Valvebox - Reinstall | 400 | 48428.87 | 2022-02-25 | 2022-03-31 | 0% | TECH3 AM | Labor Hr/M&S Direct$ |  |  | 48428.87 | 48428.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 48428.87
S281400 | Magnet and Solenoid Valvebox - Reinstall | 40 | 6249.34 | 2022-02-25 | 2022-03-31 | 0% | PROF4 AM | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | 160 | 19371.55 | 2022-04-01 | 2022-04-14 | 0% | TECH3 AM | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | 16 | 2499.74 | 2022-04-01 | 2022-04-14 | 0% | PROF4 AM | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
POM02.02.02.03.01.04.02.01 IP8 Cold Box |  | 125253 |  | 2021-12-01 | 2021-12-07 | [20 empty] | 782433.94
S1006440 | AET submits FDR report to BNL for approval | 125253 | 139733.75 | 2021-12-01 | 2021-12-07 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 139733.75 | 139733.75 | 0 | 1 | [5 empty] | 139733.75 | 0 | 0 | 0 | 0 | 0
POM02.02.02.03.01.04.02.02 Three Manifold Jumper Transfer Lines |  | 140909 |  | 2021-12-30 | 2022-02-04
S1006680 | BNL review for PDR approval | 23485 | 26200.08 | 2021-12-30 | 2022-01-06 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 26200.08 | 26200.08 | 0 | 1 | [5 empty] | 26200.08 | 0 | 0 | 0 | 0 | 0
S1006760 | BNL review for IDR approval | 23485 | 26200.08 | 2022-01-14 | 2022-01-21 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 26200.08 | 26200.08 | 0 | 1 | [5 empty] | 26200.08 | 0 | 0 | 0 | 0 | 0
S1006800 | AET submits FDR report to BNL for approval | 93940 | 104800.31 | 2022-01-24 | 2022-02-04 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 104800.31 | 104800.31 | 0 | 1 | [5 empty] | 104800.31 | 0 | 0 | 0 | 0 | 0
POM02.02.02.03.01.04.02.03 Three Solenoid Valve Box Transfer Lines |  | 422728 |  | 2021-12-30 | 2022-04-04
S1007000 | BNL review for PDR approval | 23485 | 26200.08 | 2021-12-30 | 2022-01-06 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 26200.08 | 26200.08 | 0 | 1 | [5 empty] | 26200.08 | 0 | 0 | 0 | 0 | 0
S1007080 | BNL review for IDR approval | 23485 | 26200.08 | 2022-01-14 | 2022-01-21 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 26200.08 | 26200.08 | 0 | 1 | [5 empty] | 26200.08 | 0 | 0 | 0 | 0 | 0
S1007120 | AET submits FDR report to BNL for approval | 93940 | 104800.31 | 2022-01-24 | 2022-01-28 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 104800.31 | 104800.31 | 0 | 1 | [5 empty] | 104800.31 | 0 | 0 | 0 | 0 | 0
S1007240 | Delivery of all three Solenoid Valve Box Transfer Lines and two 4" & 5" NPS Field Joint Sleeves | 203536 | 240965.68 | 2022-03-08 | 2022-03-14 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 240965.68 | 240965.68 | 0 | 1 | [5 empty] | 240965.68 | 0 | 0 | 0 | 0 | 0
S1007280 | Approval of all Data/Documentation/ Reports | 78283 | 87333.57 | 2022-03-29 | 2022-04-04 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 87333.57 | 87333.57 | 0 | 1 | [5 empty] | 87333.57 | 0 | 0 | 0 | 0 | 0
POM02.02.02.03.01.04.04 Vendor Engineering and Design |  | 501 |  | 02-Dec-19 A | 2022-02-25
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 240 | 30362.29 | 02-Dec-19 A | 2022-02-25 | 87% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 3947.0977 | 3947.0977 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3947.0977 | 0 | 0
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 54 | 6162.6 | 02-Dec-19 A | 2022-02-25 | 87% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 801.138 | 801.138 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 801.138 | 0 | 0
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 207 | 39949.54 | 02-Dec-19 A | 2022-02-25 | 87% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 5193.4402 | 5193.4402 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 5193.4402 | 0 | 0
POM02.02.02.03.02.04.01 Vendor Engineering and Design |  | 36 |  | 02-Dec-20 A | 2021-12-30
S289500 | Engineering Support for Procure LN2 supply transfer line system | 36 | 7156.18 | 02-Dec-20 A | 2021-12-30 | 92% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 572.4944 | 572.4944 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 572.4944 | 0 | 0
POM02.02.02.03.02.04.02 Vendor Fabrication |  | 107261 |  | 13-Jul-21 A | 2022-02-04 | [20 empty] | 35898.546
S291500 | Procure LN2 supply transfer line system - Phase 5 - Shipping - Delivery Acceptance | 107261 | 119661.82 | 13-Jul-21 A | 2022-02-04 | 70% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 35898.546 | 35898.546 | 0 | 1 | [5 empty] | 35898.546 | 0 | 0 | 0 | 0 | 0 | All Ability N2 system
POM02.02.02.03.02.05 Delivery and receiving, LN2 Supply Transfer Line System |  | 21 |  | 13-Jul-21 A | 2022-02-07
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | 5 | 671.07 | 13-Jul-21 A | 2022-02-07 | 55% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 301.9815 | 301.9815 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 301.9815 | 0 | 0
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | 16 | 2123.01 | 13-Jul-21 A | 2022-02-07 | 55% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 955.3545 | 955.3545 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 955.3545 | 0 | 0
POM02.02.02.03.02.06 Installation, LN2 Supply Transfer Line System |  | 644 |  | 17-May-21 A | 2022-04-07
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | 48 | 6254.63 | 17-May-21 A | 2022-02-25 | 85% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 938.1945 | 938.1945 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 938.1945 | 0 | 0
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | 40 | 4701.83 | 17-May-21 A | 2022-02-25 | 85% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 705.2745 | 705.2745 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 705.2745 | 0 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 16 | 2147.42 | 20-Jul-21 A | 2022-03-10 | 30% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 1503.194 | 1503.194 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1503.194 | 0 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 240 | 29057.32 | 20-Jul-21 A | 2022-03-10 | 30% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 20340.124 | 20340.124 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 20340.124 | 0 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 16 | 2123.01 | 20-Jul-21 A | 2022-03-10 | 30% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 1486.107 | 1486.107 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1486.107 | 0 | 0
S292120 | Welding LN2 Segment #1 to LN2 Dewar | 80 | 10615.05 | 2022-03-11 | 2022-03-24 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10615.05 | 10615.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10615.05
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | 24 | 3221.14 | 21-Jul-21 A | 2022-03-16 | 35% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 2093.741 | 2093.741 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 2093.741 | 0 | 0
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | 96 | 11622.93 | 21-Jul-21 A | 2022-03-16 | 35% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7554.9045 | 7554.9045 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 7554.9045 | 0 | 0
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | 20 | 2684.28 | 2022-03-25 | 2022-04-07 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | 64 | 7748.62 | 2022-03-25 | 2022-04-07 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7748.62 | 7748.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7748.62
POM02.02.02.03.03.01 Engineering and Design, Warm Piping System |  | 57 |  | 02-Dec-19 A | 2021-12-30
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | 19 | 2403.68 | 02-Dec-19 A | 2021-12-30 | 93% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 168.2576 | 168.2576 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 168.2576 | 0 | 0
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | 38 | 7333.73 | 02-Dec-19 A | 2021-12-30 | 93% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 513.3611 | 513.3611 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 513.3611 | 0 | 0
POM02.02.02.03.03.04 Installation: Warm Piping Systems |  | 514 |  | 2022-02-25 | 2022-05-23 | [20 empty] | 0
S294860 | (Warm Piping System) Assembly hall work on Platform | 18 | 2415.85 | 2022-02-25 | 2022-03-17 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 2415.85 | 2415.85 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2415.85
S294860 | (Warm Piping System) Assembly hall work on Platform | 90 | 10896.5 | 2022-02-25 | 2022-03-17 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 10896.5 | 10896.5 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10896.5
S294860 | (Warm Piping System) Assembly hall work on Platform | 20 | 2653.76 | 2022-02-25 | 2022-03-17 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 2653.76 | 2653.76 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2653.76
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 18 | 2415.85 | 2022-04-26 | 2022-05-16 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 2415.85 | 2415.85 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2415.85
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 90 | 10896.5 | 2022-04-26 | 2022-05-16 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 10896.5 | 10896.5 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10896.5
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 20 | 2653.76 | 2022-04-26 | 2022-05-16 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 2653.76 | 2653.76 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2653.76
S295000 | (Warm Piping System) Pressure and leak check | 32 | 4294.85 | 2022-05-10 | 2022-05-16 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 4294.85 | 4294.85 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4294.85
S295000 | (Warm Piping System) Pressure and leak check | 32 | 3874.31 | 2022-05-10 | 2022-05-16 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | 20 | 2684.28 | 2022-03-18 | 2022-03-31 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | 64 | 7748.62 | 2022-03-18 | 2022-03-31 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7748.62 | 7748.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7748.62
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | 32 | 4294.85 | 2022-05-17 | 2022-05-23 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 4294.85 | 4294.85 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4294.85
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | 32 | 3874.31 | 2022-05-17 | 2022-05-23 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S295300 | (Warm Piping System) Vacuum Pumping System installation | 8 | 1073.71 | 2022-03-18 | 2022-03-24 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 1073.71 | 1073.71 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1073.71
S295300 | (Warm Piping System) Vacuum Pumping System installation | 38 | 4600.74 | 2022-03-18 | 2022-03-24 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 4600.74 | 4600.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4600.74
POM02.02.02.03.04.02 Procurement |  | 3012 |  | 01-Oct-20 A | 2021-12-30 | [20 empty] | 696.41
S296600 | (Cryo Controls Hardware procurement) SC level probes Labor | 12 | 1563.66 | 01-Oct-20 A | 2021-12-30 | 80% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 312.732 | 312.732 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 312.732 | 0 | 0 | All Cryo Controls M&S
S296700 | (Cryo Controls Hardware procurement) SC level probes M&S | 3000 | 3482.05 | 01-Oct-20 A | 2021-12-30 | 80% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 696.41 | 696.41 | 0 | 1 | [5 empty] | 696.41 | 0 | 0 | 0 | 0 | 0 | in-progress
POM02.02.02.03.04.03 Installation: Cryo Controls Hardware |  | 1330 |  | 15-Jun-21 A | 2022-05-06
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | 48 | 6254.63 | 19-Jul-21 A | 2022-01-19 | 85% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 938.1945 | 938.1945 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 938.1945 | 0 | 0
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | 280 | 32912.83 | 19-Jul-21 A | 2022-01-19 | 85% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 4936.9245 | 4936.9245 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 4936.9245 | 0 | 0
S299800 | (Cryo Controls Hardware) Cable pulling | 52 | 6295.75 | 19-Jul-21 A | 2022-03-15 | 35% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 4092.2375 | 4092.2375 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 4092.2375 | 0 | 0
S299800 | (Cryo Controls Hardware) Cable pulling | 150 | 19903.22 | 19-Jul-21 A | 2022-03-15 | 35% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 12937.093 | 12937.093 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 12937.093 | 0 | 0
S299900 | (Cryo Controls Hardware) Cable termination | 160 | 19371.55 | 20-Jul-21 A | 2022-04-01 | 30% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 13560.085 | 13560.085 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 13560.085 | 0 | 0
S300000 | (Cryo Controls Hardware) Check out continuity | 40 | 4842.89 | 2022-04-25 | 2022-05-06 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S300200 | (Cryo Controls Hardware) Heater 480VAC wiring | 480 | 63690.31 | 18-Oct-21 A | 2022-03-30 | 50% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 31845.155 | 31845.155 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 31845.155 | 0 | 0
S300300 | (Cryo Controls Hardware) Insulating vacuum roughing pumps 480VAC Breaker install and 480V wiring to roughing pumps | 8 | 1061.51 | 15-Jun-21 A | 2022-03-30 | 80% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 212.302 | 212.302 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 212.302 | 0 | 0
S300400 | (Cryo Controls Hardware) Heater I/O wiring, temp sensors | 16 | 1937.15 | 2022-03-31 | 2022-04-06 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S300500 | (Cryo Controls Hardware) Wire up instruments and control valves | 96 | 11622.93 | 2022-04-04 | 2022-04-22 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 11622.93 | 11622.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11622.93
POM02.02.02.03.05 Cryo Controls Software |  | 1576 |  | 13-Jul-20 A | 2022-05-20
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | 8 | 1012.08 | 03-Aug-20 A | 2022-01-28 | 75% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 253.02 | 253.02 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 253.02 | 0 | 0
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | 8 | 1178.12 | 03-Aug-20 A | 2022-01-28 | 75% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 294.53 | 294.53 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 294.53 | 0 | 0
S300900 | (Cryo Controls Hardware) Built HMI operator screens | 576 | 75055.58 | 08-Mar-21 A | 2022-01-28 | 85% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 11258.337 | 11258.337 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 11258.337 | 0 | 0
S300900 | (Cryo Controls Hardware) Built HMI operator screens | 72 | 10921.17 | 08-Mar-21 A | 2022-01-28 | 85% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1638.1755 | 1638.1755 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1638.1755 | 0 | 0
S301000 | (Cryo Controls Hardware) PLC programming | 576 | 74042.51 | 13-Jul-20 A | 2021-12-30 | 95% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 3702.1255 | 3702.1255 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3702.1255 | 0 | 0
S301000 | (Cryo Controls Hardware) PLC programming | 72 | 10773.76 | 13-Jul-20 A | 2021-12-30 | 95% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 538.688 | 538.688 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 538.688 | 0 | 0
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 120 | 16105.68 | 2022-05-09 | 2022-05-20 | 0% | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 16105.68 | 16105.68 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 16105.68
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 120 | 14528.66 | 2022-05-09 | 2022-05-20 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 14528.66 | 14528.66 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14528.66
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 24 | 3749.6 | 2022-05-09 | 2022-05-20 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
POM02.02.02.04.01.01 Design AC/DC Power Distribution |  | 5 |  | 2021-12-01 | 2021-12-28 | [20 empty] | 0
S302101 | Magnet: Design DC Flags 50% | 5 | 781.17 | 2021-12-01 | 2021-12-28 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 781.17 | 781.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 781.17 | All magnet PSU
POM02.02.02.04.01.03 Install PS AC/DC Cabling |  | 1320 |  | 2021-12-01 | 2022-03-10 | [20 empty] | M&S in-progress
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | 240 | 31845.16 | 2021-12-01 | 2021-12-21 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 31845.16 | 31845.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 31845.16
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | 60 | 9374.01 | 2021-12-01 | 2021-12-21 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 9374.01 | 9374.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9374.01
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 60 | 9374.01 | 2021-12-01 | 2021-12-21 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 9374.01 | 9374.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9374.01
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 240 | 29057.32 | 2021-12-01 | 2021-12-21 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 29057.32 | 29057.32 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 29057.32
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 300 | 39806.44 | 2021-12-01 | 2021-12-21 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 39806.44 | 39806.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 39806.44
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 40 | 6249.34 | 2022-02-25 | 2022-03-10 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 160 | 19371.55 | 2022-02-25 | 2022-03-10 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 220 | 29191.39 | 2022-02-25 | 2022-03-10 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 29191.39 | 29191.39 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 29191.39
POM02.02.02.04.02.01 Install Power Supply |  | 3406 |  | 24-May-21 A | 2022-05-16
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | 7 | 1061.78 | 24-May-21 A | 2021-12-15 | 30% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 743.246 | 743.246 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 743.246 | 0 | 0
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | 32 | 3761.47 | 24-May-21 A | 2021-12-15 | 30% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2633.029 | 2633.029 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 2633.029 | 0 | 0
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 70 | 8475.05 | 2022-04-26 | 2022-05-02 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 8475.05 | 8475.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8475.05
S304800 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR M&S | 3137 | 3499.68 | 2022-04-26 | 2022-05-02 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 3499.68 | 3499.68 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3499.68
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 12498.68 | 2022-05-03 | 2022-05-16 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 12498.68 | 12498.68 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12498.68
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 9685.77 | 2022-05-03 | 2022-05-16 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
POM02.02.02.04.03.02.01 Install Quench Detector |  | 322 |  | 01-Oct-19 A | 2022-05-09
S307100 | Magnet: Connect Signal Interconnections | 80 | 9403.66 | 08-Mar-21 A | 2022-04-12 | 30% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 6582.562 | 6582.562 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 6582.562 | 0 | 0
S307200 | Magnet: Quench Detector Testing | 80 | 9685.77 | 20-Jul-21 A | 2022-05-09 | 15% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 8232.9045 | 8232.9045 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 8232.9045 | 0 | 0
S307200 | Magnet: Quench Detector Testing | 80 | 14433.59 | 20-Jul-21 A | 2022-05-09 | 15% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 12268.5515 | 12268.5515 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 12268.5515 | 0 | 0
S307311 | Magnet: Quench Detector Documentation Split_85% | 54 | 6227.23 | 01-Oct-19 A | 2022-01-14 | 90% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 622.723 | 622.723 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 622.723 | 0 | 0
S307311 | Magnet: Quench Detector Documentation Split_85% | 27 | 4639.86 | 01-Oct-19 A | 2022-01-14 | 90% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 463.986 | 463.986 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 463.986 | 0 | 0
POM02.02.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication |  | 202 |  | 30-Oct-20 A | 2022-05-09 | [20 empty] | 0
S308615 | Develop readout electronics | 90 | 13651.47 | 30-Oct-20 A | 2022-01-28 | 90% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1365.147 | 1365.147 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1365.147 | 0 | 0 | All field-measurement
S308617 | Calibrate probes | 24 | 5242.73 | 2022-01-31 | 2022-04-25 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 5242.73 | 5242.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5242.73 | M&S in-progress
S308617 | Calibrate probes | 24 | 3749.6 | 2022-01-31 | 2022-04-25 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S308617 | Calibrate probes | 24 | 2905.73 | 2022-01-31 | 2022-04-25 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S308619 | Install probes and readout on TPC | 40 | 4842.89 | 2022-04-26 | 2022-05-09 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
POM02.02.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis |  | 64880 |  | 01-Oct-20 A | 2022-08-26
S308621 | Conceptual design of mapping campaign | 32 | 6786.71 | 01-Oct-20 A | 2021-12-29 | 80% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 1357.342 | 1357.342 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1357.342 | 0 | 0
S308623 | Develop mapping plan with Vendor | 100 | 21208.47 | 30-Oct-20 A | 2021-12-30 | 50% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 10604.235 | 10604.235 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 10604.235 | 0 | 0
S308625 | Complete MOU with Vendor | 8 | 1747.58 | 22-Feb-21 A | 2022-01-05 | 30% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 1223.306 | 1223.306 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1223.306 | 0 | 0
S308627 | Place contract with Vendor (Procurement string, $70K obligated at Contract award, paid when mapped?) | 63000 | 74585.57 | 2021-12-30 | 2022-02-28 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 74585.57 | 74585.57 | 0 |  |  | 1 |  |  |  | 0 | 0 | 74585.57 | 0 | 0 | 0
S308629 | Complete mechanical and electrical design for mapping | 60 | 9114.63 | 23-Nov-20 A | 2022-01-27 | 40% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 5468.778 | 5468.778 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 5468.778 | 0 | 0
S308629 | Complete mechanical and electrical design for mapping | 30 | 3531.66 | 23-Nov-20 A | 2022-01-27 | 40% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2118.996 | 2118.996 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 2118.996 | 0 | 0
S308631 | Review mapping plan | 16 | 2499.74 | 2021-12-30 | 2022-01-06 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S308631 | Review mapping plan | 16 | 1937.15 | 2021-12-30 | 2022-01-06 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S308631 | Review mapping plan | 10 | 2184.47 | 2021-12-30 | 2022-01-06 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 2184.47 | 2184.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2184.47
S308633 | Construct mapping support (mechanical and electrical) | 32 | 3874.31 | 08-Mar-21 A | 2022-01-21 | 5% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 3680.5945 | 3680.5945 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3680.5945 | 0 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 9685.77 | 2022-06-17 | 2022-06-30 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 19371.55 | 2022-06-17 | 2022-06-30 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 10737.12 | 2022-06-17 | 2022-06-30 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 10737.12 | 10737.12 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10737.12
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 34951.55 | 2022-06-17 | 2022-06-30 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 34951.55 | 34951.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 34951.55
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9685.77 | 2022-07-06 | 2022-07-26 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 34951.55 | 2022-07-06 | 2022-07-26 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 34951.55 | 34951.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 34951.55
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 10737.12 | 2022-07-06 | 2022-07-26 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 10737.12 | 10737.12 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10737.12
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 19371.55 | 2022-07-06 | 2022-07-26 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9685.77 | 2022-07-06 | 2022-07-26 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 34951.55 | 2022-07-06 | 2022-07-26 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 34951.55 | 34951.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 34951.55
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 10737.12 | 2022-07-06 | 2022-07-26 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 10737.12 | 10737.12 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10737.12
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 19371.55 | 2022-07-06 | 2022-07-26 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 40 | 4842.89 | 2022-07-27 | 2022-07-29 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 80 | 9685.77 | 2022-07-27 | 2022-07-29 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S309110 | Receive report from CERN, incorporate into analysis | 16 | 3495.16 | 2022-08-01 | 2022-08-26 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 3495.16 | 3495.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3495.16
POM02.02.03.01 Cradle Carriage |  | 126986 |  | 17-Dec-19 A | 2022-07-15 | [20 empty] | 0
S313400 | CC Seismic Restraints - Assembly & Detail Drawings - Physics Resource(s) | 120 | 13694.66 | 17-Dec-19 A | 2021-12-30 | 95% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 684.733 | 684.733 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 684.733 | 0 | 0 | All cradle-carriage
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 80 | 11781.2 | 17-Dec-19 A | 2021-12-30 | 95% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 589.06 | 589.06 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 589.06 | 0 | 0 | M&S in-progress
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 40 | 6802.52 | 17-Dec-19 A | 2021-12-30 | 95% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 340.126 | 340.126 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 340.126 | 0 | 0
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 120 | 13694.66 | 17-Dec-19 A | 2021-12-30 | 95% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 684.733 | 684.733 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 684.733 | 0 | 0
S313500 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - Physics Resource(s) | 20 | 2421.44 | 2022-01-03 | 2022-01-07 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 40 | 6249.34 | 2022-01-03 | 2022-01-07 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 20 | 2421.44 | 2022-01-03 | 2022-01-07 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S313600 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 20 | 2421.44 | 2022-01-10 | 2022-01-14 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 40 | 6249.34 | 2022-01-10 | 2022-01-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 20 | 3608.4 | 2022-01-10 | 2022-01-14 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 3608.4 | 3608.4 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3608.4
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 20 | 2421.44 | 2022-01-10 | 2022-01-14 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S313700 | CC Seismic Restraints - Prepare Procurement Package - Physics Resource(s) | 20 | 2421.44 | 2022-01-18 | 2022-01-24 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 20 | 3124.67 | 2022-01-18 | 2022-01-24 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 8 | 1443.36 | 2022-01-18 | 2022-01-24 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 1443.36 | 1443.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1443.36
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 20 | 2421.44 | 2022-01-18 | 2022-01-24 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S313800 | CC Seismic Restraints - Procurement Readiness Review - Physics Resource(s) | 20 | 2421.44 | 2022-01-25 | 2022-01-31 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 20 | 3124.67 | 2022-01-25 | 2022-01-31 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 8 | 1443.36 | 2022-01-25 | 2022-01-31 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 1443.36 | 1443.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1443.36
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 20 | 2421.44 | 2022-01-25 | 2022-01-31 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S313900 | CC Seismic Restraints - Provide Requirement to Procurement | 8 | 1443.36 | 2022-02-01 | 2022-02-07 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 1443.36 | 1443.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1443.36
S314100 | CC Seismic Restraints - Vendor Responses - Physics Resource(s) | 18 | 2179.3 | 2022-02-15 | 2022-03-15 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2179.3 | 2179.3 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2179.3
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 18 | 2812.2 | 2022-02-15 | 2022-03-15 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 2812.2 | 2812.2 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2812.2
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 8 | 1443.36 | 2022-02-15 | 2022-03-15 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 1443.36 | 1443.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1443.36
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 18 | 2179.3 | 2022-02-15 | 2022-03-15 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2179.3 | 2179.3 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2179.3
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | 18 | 2179.3 | 2022-03-16 | 2022-04-12 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2179.3 | 2179.3 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2179.3
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | 36 | 4358.6 | 2022-03-16 | 2022-04-12 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4358.6 | 4358.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4358.6
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 18 | 2812.2 | 2022-03-16 | 2022-04-12 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 2812.2 | 2812.2 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2812.2
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 8 | 1443.36 | 2022-03-16 | 2022-04-12 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 1443.36 | 1443.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1443.36
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 18 | 2179.3 | 2022-03-16 | 2022-04-12 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2179.3 | 2179.3 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2179.3
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | 10 | 1210.72 | 2022-04-14 | 2022-07-08 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1210.72 | 1210.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1210.72
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | 40 | 4842.89 | 2022-04-14 | 2022-07-08 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 24 | 3749.6 | 2022-04-14 | 2022-07-08 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 24 | 4330.08 | 2022-04-14 | 2022-07-08 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 4330.08 | 4330.08 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4330.08
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 10 | 1210.72 | 2022-04-14 | 2022-07-08 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 1210.72 | 1210.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1210.72
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | 4 | 484.29 | 2022-07-11 | 2022-07-15 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | 20 | 2421.44 | 2022-07-11 | 2022-07-15 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 2 | 312.47 | 2022-07-11 | 2022-07-15 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.47 | 312.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 312.47
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 4 | 721.68 | 2022-07-11 | 2022-07-15 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 721.68 | 721.68 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 721.68
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 4 | 484.29 | 2022-07-11 | 2022-07-15 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
S314650 | CC Seismic Restraints - Delivery Acceptance - M&S | 126000 | 149171.15 | 2022-07-11 | 2022-07-15 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 149171.15 | 149171.15 | 0 |  |  | 1 |  |  |  | 0 | 0 | 149171.15 | 0 | 0 | 0
POM02.02.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports |  | 186846 |  | 12-Mar-20 A | 2022-05-26 | [20 empty] | 0
S317040 | Create TPC Supports Detailed Design Drawings | 80 | 10424.39 | 17-Nov-20 A | 2021-12-30 | 95% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 521.2195 | 521.2195 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 521.2195 | 0 | 0 | All support items
S317040 | Create TPC Supports Detailed Design Drawings | 160 | 20848.77 | 17-Nov-20 A | 2021-12-30 | 95% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 1042.4385 | 1042.4385 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1042.4385 | 0 | 0 | M&S in progress
S317041 | Review Design and Safety TPC Supports | 8 | 1073.71 | 22-Sep-21 A | 2022-01-14 | 50% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 536.855 | 536.855 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 536.855 | 0 | 0
S317041 | Review Design and Safety TPC Supports | 8 | 1073.71 | 22-Sep-21 A | 2022-01-14 | 50% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 536.855 | 536.855 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 536.855 | 0 | 0
S317042 | Address Action Items for TPC Supports | 8 | 1073.71 | 2022-01-18 | 2022-01-19 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1073.71 | 1073.71 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1073.71
S317042 | Address Action Items for TPC Supports | 8 | 1073.71 | 2022-01-18 | 2022-01-19 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 1073.71 | 1073.71 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1073.71
S317070 | Create MBD Supports Detailed Design Drawings | 60 | 7818.29 | 18-May-20 A | 2022-01-14 | 75% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1954.5725 | 1954.5725 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1954.5725 | 0 | 0
S317070 | Create MBD Supports Detailed Design Drawings | 80 | 10424.39 | 18-May-20 A | 2022-01-14 | 75% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2606.0975 | 2606.0975 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 2606.0975 | 0 | 0
S317071 | Review Design and Safety MBD Supports | 4 | 536.86 | 2022-01-18 | 2022-01-19 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 536.86 | 536.86 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 536.86
S317071 | Review Design and Safety MBD Supports | 4 | 536.86 | 2022-01-18 | 2022-01-19 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 536.86 | 536.86 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 536.86
S317072 | Address Action Items for MBD Supports | 4 | 536.86 | 2022-01-20 | 2022-01-21 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 536.86 | 536.86 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 536.86
S317072 | Address Action Items for MBD Supports | 4 | 536.86 | 2022-01-20 | 2022-01-21 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 536.86 | 536.86 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 536.86
S317090 | Create Beampipe Supports and Beampipe Detailed Design Drawings | 240 | 31273.16 | 12-Mar-20 A | 2021-12-03 | 90% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 3127.316 | 3127.316 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3127.316 | 0 | 0
S317090 | Create Beampipe Supports and Beampipe Detailed Design Drawings | 300 | 39091.45 | 12-Mar-20 A | 2021-12-03 | 90% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 3909.145 | 3909.145 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3909.145 | 0 | 0
S317091 | Review Design and Safety Beampipe Supports | 20 | 2684.28 | 2021-12-06 | 2021-12-10 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317091 | Review Design and Safety Beampipe Supports | 20 | 2684.28 | 2021-12-06 | 2021-12-10 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317092 | Address Action Items for Beampipe Supports | 4 | 536.86 | 2021-12-13 | 2021-12-14 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 536.86 | 536.86 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 536.86
S317092 | Address Action Items for Beampipe Supports | 4 | 536.86 | 2021-12-13 | 2021-12-14 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 536.86 | 536.86 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 536.86
S317140 | Prepare Procurement Package for TPC Supports | 40 | 4842.89 | 2022-01-20 | 2022-02-16 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S317140 | Prepare Procurement Package for TPC Supports | 40 | 5368.56 | 2022-01-20 | 2022-02-16 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 5368.56 | 5368.56 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5368.56
S317140 | Prepare Procurement Package for TPC Supports | 40 | 5368.56 | 2022-01-20 | 2022-02-16 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 5368.56 | 5368.56 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5368.56
S317150 | Prepare Procurement Package for INTT Supports | 20 | 2421.44 | 2022-01-03 | 2022-01-14 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S317150 | Prepare Procurement Package for INTT Supports | 20 | 2684.28 | 2022-01-03 | 2022-01-14 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317150 | Prepare Procurement Package for INTT Supports | 20 | 2684.28 | 2022-01-03 | 2022-01-14 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317160 | Prepare Procurement Package for MVTX Supports | 20 | 2421.44 | 2022-01-03 | 2022-01-14 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S317160 | Prepare Procurement Package for MVTX Supports | 20 | 2684.28 | 2022-01-03 | 2022-01-14 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317160 | Prepare Procurement Package for MVTX Supports | 20 | 2684.28 | 2022-01-03 | 2022-01-14 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317170 | Prepare Procurement Package for MBD Supports | 10 | 1210.72 | 2022-01-24 | 2022-02-04 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1210.72 | 1210.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1210.72
S317170 | Prepare Procurement Package for MBD Supports | 10 | 1342.14 | 2022-01-24 | 2022-02-04 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 1342.14 | 1342.14 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1342.14
S317170 | Prepare Procurement Package for MBD Supports | 10 | 1342.14 | 2022-01-24 | 2022-02-04 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1342.14 | 1342.14 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1342.14
S317190 | Prepare Procurement Package for Beampipe Supports | 40 | 4842.89 | 2021-12-15 | 2021-12-29 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S317190 | Prepare Procurement Package for Beampipe Supports | 40 | 5368.56 | 2021-12-15 | 2021-12-29 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 5368.56 | 5368.56 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5368.56
S317190 | Prepare Procurement Package for Beampipe Supports | 40 | 5368.56 | 2021-12-15 | 2021-12-29 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 5368.56 | 5368.56 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5368.56
S317240 | Evaluate and Process Bid for TPC Supports | 20 | 2684.28 | 2022-02-17 | 2022-03-17 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317240 | Evaluate and Process Bid for TPC Supports | 20 | 2684.28 | 2022-02-17 | 2022-03-17 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317250 | Evaluate and Process Bid for INTT Supports | 20 | 2684.28 | 2022-01-18 | 2022-02-14 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317250 | Evaluate and Process Bid for INTT Supports | 20 | 2684.28 | 2022-01-18 | 2022-02-14 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317260 | Evaluate and Process Bid for MVTX Supports | 20 | 2684.28 | 2022-01-18 | 2022-02-14 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317260 | Evaluate and Process Bid for MVTX Supports | 20 | 2684.28 | 2022-01-18 | 2022-02-14 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317270 | Evaluate and Process Bid for MBD Supports | 10 | 1342.14 | 2022-02-07 | 2022-03-07 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 1342.14 | 1342.14 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1342.14
S317270 | Evaluate and Process Bid for MBD Supports | 10 | 1342.14 | 2022-02-07 | 2022-03-07 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1342.14 | 1342.14 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1342.14
S317290 | Evaluate and Process Bid for Beampipe Supports | 20 | 2684.28 | 2021-12-30 | 2022-01-28 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317290 | Evaluate and Process Bid for Beampipe Supports | 20 | 2684.28 | 2021-12-30 | 2022-01-28 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S317940 | Procure TPC Supports - M&S | 50000 | 59194.9 | 2022-03-18 | 2022-05-12 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 59194.9 | 59194.9 | 0 |  |  | 1 |  |  |  | 0 | 0 | 59194.9 | 0 | 0 | 0
S317950 | Procure INTT Supports - M&S | 50000 | 59194.9 | 2022-02-15 | 2022-04-12 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 59194.9 | 59194.9 | 0 |  |  | 1 |  |  |  | 0 | 0 | 59194.9 | 0 | 0 | 0
S317960 | Procure MVTX Supports - M&S | 50000 | 59194.9 | 2022-02-15 | 2022-04-12 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 59194.9 | 59194.9 | 0 |  |  | 1 |  |  |  | 0 | 0 | 59194.9 | 0 | 0 | 0
S317970 | Procure MBD Supports - M&S | 10000 | 11838.98 | 2022-03-08 | 2022-04-04 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 11838.98 | 11838.98 | 0 |  |  | 1 |  |  |  | 0 | 0 | 11838.98 | 0 | 0 | 0
S317990 | Procure Beampipe Supports - M&S | 25000 | 29597.45 | 2022-01-31 | 2022-02-28 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 29597.45 | 29597.45 | 0 |  |  | 1 |  |  |  | 0 | 0 | 29597.45 | 0 | 0 | 0
S318140 | Perform TPC Supports Acceptance | 40 | 4842.89 | 2022-05-13 | 2022-05-26 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S318140 | Perform TPC Supports Acceptance | 40 | 5368.56 | 2022-05-13 | 2022-05-26 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 5368.56 | 5368.56 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5368.56
S318150 | Perform INTT Supports Acceptance | 20 | 2421.44 | 2022-04-13 | 2022-04-26 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S318150 | Perform INTT Supports Acceptance | 20 | 2684.28 | 2022-04-13 | 2022-04-26 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S318160 | Perform MVTX Supports Acceptance | 20 | 2421.44 | 2022-04-13 | 2022-04-26 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S318160 | Perform MVTX Supports Acceptance | 20 | 2684.28 | 2022-04-13 | 2022-04-26 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2684.28 | 2684.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2684.28
S318170 | Perform MBD Supports Acceptance | 10 | 1210.72 | 2022-04-05 | 2022-04-18 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1210.72 | 1210.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1210.72
S318170 | Perform MBD Supports Acceptance | 10 | 1342.14 | 2022-04-05 | 2022-04-18 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1342.14 | 1342.14 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1342.14
S318190 | Perform Beampipe Supports Acceptance | 40 | 4842.89 | 2022-03-01 | 2022-03-14 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S318190 | Perform Beampipe Supports Acceptance | 40 | 5368.56 | 2022-03-01 | 2022-03-14 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 5368.56 | 5368.56 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5368.56
POM02.02.03.04 End Caps/ Pole Tips |  | 890478 |  | 2022-01-18 | 2022-01-31 | [20 empty] | 993188.32
S325400 | End Caps/ Pole Tips - Delivery Acceptance | 890262 | 993188.32 | 2022-01-18 | 2022-01-18 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 993188.32 | 993188.32 | 0 | 1 | [5 empty] | 993188.32 | 0 | 0 | 0 | 0 | 0 | All Pole-tips M&S
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | 40 | 4842.89 | 2022-01-18 | 2022-01-31 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89 | in-progress
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | 44 | 5327.18 | 2022-01-18 | 2022-01-31 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 5327.18 | 5327.18 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5327.18
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 36 | 6495.12 | 2022-01-18 | 2022-01-31 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 6495.12 | 6495.12 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6495.12
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 44 | 5327.18 | 2022-01-18 | 2022-01-31 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 5327.18 | 5327.18 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5327.18
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 52 | 8124.14 | 2022-01-18 | 2022-01-31 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 8124.14 | 8124.14 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8124.14
POM02.02.03.05 CC Bridge, Mid Platforms and Access |  | 399912 |  | 16-Aug-21 A | 2022-01-25 | [20 empty] | 469603.1539
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | 36 | 4327.23 | 16-Aug-21 A | 2022-01-10 | 25% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 3245.4225 | 3245.4225 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3245.4225 | 0 | 0 | All Bridge/platform
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | 72 | 8654.47 | 16-Aug-21 A | 2022-01-10 | 25% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 6490.8525 | 6490.8525 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 6490.8525 | 0 | 0 | M&S in-progress
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 60 | 9306.55 | 16-Aug-21 A | 2022-01-10 | 25% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 6979.9125 | 6979.9125 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 6979.9125 | 0 | 0
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 30 | 5373.65 | 16-Aug-21 A | 2022-01-10 | 25% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 4030.2375 | 4030.2375 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 4030.2375 | 0 | 0
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 36 | 4327.23 | 16-Aug-21 A | 2022-01-10 | 25% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 3245.4225 | 3245.4225 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3245.4225 | 0 | 0
S327100 | CC Bridge, Mid Platforms & Access - Delivery Acceptance | 354678 | 419902.57 | 2022-01-11 | 2022-01-25 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 419902.57 | 419902.57 | 0 | 1 | [5 empty] | 419902.57 | 0 | 0 | 0 | 0 | 0
S327150 | Access stairs for upper platforms | 45000 | 50202.61 | 23-Aug-21 A | 2021-12-30 | 1% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 49700.5839 | 49700.5839 | 0 | 1 | [5 empty] | 49700.5839 | 0 | 0 | 0 | 0 | 0
POM02.02.04.01.01 Line Electric Power Distribution |  | 50472 |  | 01-Oct-21 A | 2022-09-30 | [20 empty] | 75295.918
S277600 | 2022 Detector Support Systems L3 Project Management | 352 | 63660.23 | 01-Oct-21 A | 2022-09-30 | 15.6% | PROF5 PO M | Labor Hr/M&S Direct$ |  |  | 53729.2341 | 53729.2341 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 53729.2341 | 0 | Infrastructure
S329100 | Procure Line Electric Power Distribution Components - Delivery Acceptance | 50000 | 59194.9 | 2021-12-01 | 2021-12-29 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 59194.9 | 59194.9 | 0 | 0.6 |  | 0.4 |  |  |  | 35516.94 | 0 | 23677.96 | 0 | 0 | 0 | Detector M&S in-progress
S329200 | Perform Line Electric Power Distribution Components Acceptance | 40 | 5368.56 | 2021-12-01 | 2021-12-29 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 5368.56 | 5368.56 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5368.56
S329200 | Perform Line Electric Power Distribution Components Acceptance | 80 | 9685.77 | 2021-12-01 | 2021-12-29 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
POM02.02.04.01.02 Detector Support Services Systems (including Cables, Fibers, Cable Trays) |  | 54780 |  | 15-Jul-20 A | 2022-09-02
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | 40 | 6249.34 | 23-Aug-21 A | 2022-06-02 | 90% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 624.934 | 624.934 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 624.934 | 0 | 0
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | 40 | 4842.89 | 23-Aug-21 A | 2022-06-02 | 90% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 484.289 | 484.289 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 484.289 | 0 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 4 | 624.93 | 01-Sep-21 A | 2022-06-09 | 90% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 62.493 | 62.493 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 62.493 | 0 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 20 | 2421.44 | 01-Sep-21 A | 2022-06-09 | 90% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 242.144 | 242.144 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 242.144 | 0 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 4 | 484.29 | 01-Sep-21 A | 2022-06-09 | 90% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 48.429 | 48.429 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 48.429 | 0 | 0
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | 80 | 14606.95 | 2022-06-10 | 2022-09-02 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 14606.95 | 14606.95 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14606.95
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | 80 | 10737.12 | 2022-06-10 | 2022-09-02 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 10737.12 | 10737.12 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10737.12
S329440 | Conceptual Design for Routing Rack Cooling System | 104 | 13551.7 | 23-Oct-20 A | 2021-12-29 | 75% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 3387.925 | 3387.925 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3387.925 | 0 | 0
S329440 | Conceptual Design for Routing Rack Cooling System | 104 | 12224.76 | 23-Oct-20 A | 2021-12-29 | 75% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 3056.19 | 3056.19 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3056.19 | 0 | 0
S329450 | Conceptual Design for Routing Detector Cooling System | 100 | 13030.48 | 15-Jul-20 A | 2021-12-30 | 75% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 3257.62 | 3257.62 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3257.62 | 0 | 0
S329450 | Conceptual Design for Routing Detector Cooling System | 200 | 23509.16 | 15-Jul-20 A | 2021-12-30 | 75% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 5877.29 | 5877.29 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 5877.29 | 0 | 0
S330200 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) M&S | 32000 | 37884.74 | 23-Aug-21 A | 2022-06-01 | 90% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 3788.474 | 3788.474 | 0 | 1 | [5 empty] | 3788.474 | 0 | 0 | 0 | 0 | 0
S330350 | Procure Fiber Optics Trunk Cables and Accessories - Labor - CA-D Resource(s) | 4 | 624.93 | 2022-06-10 | 2022-09-02 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S330355 | Procure Fiber Optics Trunk Cables and Accessories - M&S | 22000 | 26045.76 | 2022-06-10 | 2022-09-02 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 26045.76 | 26045.76 | 0 |  |  | 1 |  |  |  | 0 | 0 | 26045.76 | 0 | 0 | 0
POM02.02.04.01.03 Detector Electronics Racks and Rack generic support systems |  | 93032 |  | 05-Jul-21 A | 2022-07-12
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 48 | 7499.21 | 05-Jul-21 A | 2021-12-06 | 80% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1499.842 | 1499.842 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1499.842 | 0 | 0
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 144 | 17434.39 | 05-Jul-21 A | 2021-12-06 | 80% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 3486.878 | 3486.878 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3486.878 | 0 | 0
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 48 | 6442.27 | 05-Jul-21 A | 2021-12-06 | 80% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1288.454 | 1288.454 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1288.454 | 0 | 0
S331400 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - M&S | 92000 | 108918.62 | 05-Jul-21 A | 2021-12-06 | 80% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 21783.724 | 21783.724 | 0 | 1 | [5 empty] | 21783.724 | 0 | 0 | 0 | 0 | 0
S331450 | Assemble Racks for Lower West Platform | 80 | 9685.77 | 13-Sep-21 A | 2022-03-18 | 63% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 3583.7349 | 3583.7349 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3583.7349 | 0 | 0
S331460 | Assemble Racks for Middle West Platform | 80 | 9685.77 | 13-Sep-21 A | 2022-03-18 | 91% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 871.7193 | 871.7193 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 871.7193 | 0 | 0
S331470 | Assemble Racks for Lower East Platform | 80 | 9685.77 | 15-Nov-21 A | 2022-02-18 | 70% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 2905.731 | 2905.731 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 2905.731 | 0 | 0
S331480 | Assemble Racks for Middle East Platform | 80 | 9685.77 | 13-Sep-21 A | 2022-03-18 | 32% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 6586.3236 | 6586.3236 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 6586.3236 | 0 | 0
S331490 | Assemble Racks for Main Upper Platform | 200 | 24214.44 | 13-Sep-21 A | 2021-12-30 | 23% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 18645.1188 | 18645.1188 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 18645.1188 | 0 | 0
S331495 | Assemble Racks for Rack Room | 200 | 24214.44 | 13-Sep-21 A | 2022-07-12 | 10% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 21792.996 | 21792.996 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 21792.996 | 0 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 8 | 1249.87 | 2021-12-07 | 2021-12-20 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 40 | 4842.89 | 2021-12-07 | 2021-12-20 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 16 | 1937.15 | 2021-12-07 | 2021-12-20 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 8 | 1073.71 | 2021-12-07 | 2021-12-20 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1073.71 | 1073.71 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1073.71
POM02.02.04.01.04 Detector Gas and Cooling Services Systems |  | 108132 |  | 18-Mar-20 A | 2023-01-13
S331710 | Design Cooling Manifolds for EMCal | 8 | 1178.12 | 18-Mar-20 A | 2021-12-13 | 85% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 176.718 | 176.718 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 176.718 | 0 | 0
S331710 | Design Cooling Manifolds for EMCal | 24 | 2738.93 | 18-Mar-20 A | 2021-12-13 | 85% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 410.8395 | 410.8395 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 410.8395 | 0 | 0
S331730 | Design Coolin Manifolds for INTT | 8 | 1213.46 | 08-Dec-20 A | 2021-12-13 | 85% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 182.019 | 182.019 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 182.019 | 0 | 0
S331730 | Design Coolin Manifolds for INTT | 24 | 2821.1 | 08-Dec-20 A | 2021-12-13 | 85% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 423.165 | 423.165 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 423.165 | 0 | 0
S332200 | Prepare Detector Cooling Services Systems Components Procurement Package(s) | 32 | 4999.47 | 2021-12-01 | 2022-01-13 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 4999.47 | 4999.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4999.47
S332200 | Prepare Detector Cooling Services Systems Components Procurement Package(s) | 72 | 8717.2 | 2021-12-01 | 2022-01-13 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8717.2 | 8717.2 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8717.2
S332300 | Evaluate & Process Detector Cooling Services Systems Components Bids | 24 | 3749.6 | 2022-01-14 | 2022-02-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S332300 | Evaluate & Process Detector Cooling Services Systems Components Bids | 24 | 2905.73 | 2022-01-14 | 2022-02-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S332400 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) L | 96 | 14998.41 | 2022-03-01 | 2022-07-06 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 14998.41 | 14998.41 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14998.41
S332400 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) L | 96 | 11622.93 | 2022-03-01 | 2022-07-06 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 11622.93 | 11622.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11622.93
S332500 | Procure & Deliver Detector CoolingServices Systems Components (leadtime and fabrication included) M&S | 53000 | 62746.59 | 2022-03-01 | 2022-07-06 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 62746.59 | 62746.59 | 0 |  |  | 1 |  |  |  | 0 | 0 | 62746.59 | 0 | 0 | 0
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 16 | 2499.74 | 2022-07-07 | 2022-08-03 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 16 | 1937.15 | 2022-07-07 | 2022-08-03 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 8 | 968.58 | 2022-07-07 | 2022-08-03 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | 8 | 1213.46 | 18-Dec-20 A | 2021-12-29 | 75% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 303.365 | 303.365 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 303.365 | 0 | 0
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | 16 | 1880.73 | 18-Dec-20 A | 2021-12-29 | 75% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 470.1825 | 470.1825 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 470.1825 | 0 | 0
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | 8 | 1213.46 | 18-Dec-20 A | 2021-12-29 | 90% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 121.346 | 121.346 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 121.346 | 0 | 0
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | 16 | 1880.73 | 18-Dec-20 A | 2021-12-29 | 90% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 188.073 | 188.073 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 188.073 | 0 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 96 | 14561.56 | 15-Feb-21 A | 2021-12-29 | 50% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 7280.78 | 7280.78 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 7280.78 | 0 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642.2 | 15-Feb-21 A | 2021-12-29 | 50% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2821.1 | 2821.1 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 2821.1 | 0 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642.2 | 15-Feb-21 A | 2021-12-29 | 50% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2821.1 | 2821.1 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 2821.1 | 0 | 0
S332740 | Review Detector Gas Service Systems Design/Safety | 8 | 1249.87 | 2021-12-01 | 2021-12-14 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S332740 | Review Detector Gas Service Systems Design/Safety | 16 | 1937.15 | 2021-12-01 | 2021-12-14 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 20 | 3124.67 | 2021-12-15 | 2021-12-29 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 8 | 968.58 | 2021-12-15 | 2021-12-29 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 8 | 968.58 | 2021-12-15 | 2021-12-29 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 32 | 4999.47 | 2021-12-30 | 2022-05-09 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 4999.47 | 4999.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4999.47
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 72 | 8717.2 | 2021-12-30 | 2022-05-09 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8717.2 | 8717.2 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8717.2
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 3749.6 | 2022-05-10 | 2022-06-21 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 2905.73 | 2022-05-10 | 2022-06-21 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 15182.14 | 2022-06-22 | 2022-12-14 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 15182.14 | 15182.14 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 15182.14
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 11765.31 | 2022-06-22 | 2022-12-14 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 11765.31 | 11765.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11765.31
S332770 | Procure & Deliver Detector Gas Services Systems Components - M&S | 54000 | 64452.59 | 2022-06-22 | 2022-12-14 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 64452.59 | 64452.59 | 0 |  |  | 1 |  |  |  | 0 | 0 | 64452.59 | 0 | 0 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 2574.73 | 2022-12-15 | 2023-01-13 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2574.73 | 2574.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2574.73
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 1995.27 | 2022-12-15 | 2023-01-13 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 8 | 997.63 | 2022-12-15 | 2023-01-13 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
POM02.02.04.01.05 Detector Safety Subsystems |  | 12320 |  | 05-Jul-21 A | 2022-06-16
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | 24 | 2905.73 | 05-Jul-21 A | 2021-12-09 | 80% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 581.146 | 581.146 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 581.146 | 0 | 0
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | 48 | 7499.21 | 05-Jul-21 A | 2021-12-09 | 80% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1499.842 | 1499.842 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1499.842 | 0 | 0
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | 8 | 968.58 | 2021-12-10 | 2021-12-23 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | 16 | 2499.74 | 2021-12-10 | 2021-12-23 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S332900 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - CA-D Resource(s) | 12 | 1874.8 | 05-Jul-21 A | 2021-12-09 | 80% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 374.96 | 374.96 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 374.96 | 0 | 0
S333000 | Review Detector Safety Subsystems Design/Safety - CA-D Resource(s) | 8 | 1249.87 | 2021-12-10 | 2021-12-23 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | 8 | 968.58 | 2021-12-27 | 2022-01-10 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | 16 | 2499.74 | 2021-12-27 | 2022-01-10 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | 8 | 968.58 | 2022-01-11 | 2022-01-25 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | 8 | 1249.87 | 2022-01-11 | 2022-01-25 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | 24 | 2905.73 | 2022-01-26 | 2022-03-09 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | 24 | 3749.6 | 2022-01-26 | 2022-03-09 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | 48 | 5811.46 | 2022-03-10 | 2022-06-02 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 5811.46 | 5811.46 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5811.46
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | 48 | 7499.21 | 2022-03-10 | 2022-06-02 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 7499.21 | 7499.21 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7499.21
S333600 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) - M&S | 12000 | 14206.78 | 2022-03-10 | 2022-06-02 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 14206.78 | 14206.78 | 0 | 1 | [5 empty] | 14206.78 | 0 | 0 | 0 | 0 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | 4 | 484.29 | 2022-06-03 | 2022-06-16 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
S333700 | Perform Detector Safety Subsystems Components Acceptance | 4 | 484.29 | 2022-06-03 | 2022-06-16 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
S333700 | Perform Detector Safety Subsystems Components Acceptance | 8 | 1249.87 | 2022-06-03 | 2022-06-16 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S333700 | Perform Detector Safety Subsystems Components Acceptance | 4 | 484.29 | 2022-06-03 | 2022-06-16 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
POM02.02.04.01.07 Rack Room Modifications |  | 20438 |  | 02-Jul-21 A | 2022-08-17
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 2905.73 | 2022-01-31 | 2022-03-14 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 3749.6 | 2022-01-31 | 2022-03-14 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 2905.73 | 2022-01-31 | 2022-03-14 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | 8 | 940.37 | 02-Jul-21 A | 2021-12-29 | 85% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 141.0555 | 141.0555 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 141.0555
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | 32 | 4853.85 | 02-Jul-21 A | 2021-12-29 | 85% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 728.0775 | 728.0775 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 728.0775 | 0 | 0
S335200 | Review Rack Room Modifications Components Design/Safety | 8 | 1460.7 | 2021-12-30 | 2022-01-13 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 1460.7 | 1460.7 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1460.7
S335200 | Review Rack Room Modifications Components Design/Safety | 8 | 1249.87 | 2021-12-30 | 2022-01-13 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 8 | 1460.7 | 2022-01-14 | 2022-01-28 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 1460.7 | 1460.7 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1460.7
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 16 | 1937.15 | 2022-01-14 | 2022-01-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 8 | 968.58 | 2022-01-14 | 2022-01-28 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 8 | 1249.87 | 2022-01-14 | 2022-01-28 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 8 | 968.58 | 2022-01-14 | 2022-01-28 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S335500 | Prepare Rack Room Modifications Components Procurement Package(s) - CA-D Resource(s) | 2 | 312.47 | 2022-01-31 | 2022-03-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.47 | 312.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 312.47
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 8 | 968.58 | 2022-03-15 | 2022-04-11 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 16 | 1937.15 | 2022-03-15 | 2022-04-11 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 16 | 2499.74 | 2022-03-15 | 2022-04-11 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 16 | 1937.15 | 2022-03-15 | 2022-04-11 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 24 | 2905.73 | 2022-04-12 | 2022-07-06 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 48 | 5811.46 | 2022-04-12 | 2022-07-06 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 5811.46 | 5811.46 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5811.46
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 48 | 7499.21 | 2022-04-12 | 2022-07-06 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 7499.21 | 7499.21 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7499.21
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 48 | 5811.46 | 2022-04-12 | 2022-07-06 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 5811.46 | 5811.46 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5811.46
S335800 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - M&S | 20000 | 23677.96 | 2022-04-12 | 2022-07-06 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 23677.96 | 23677.96 | 0 |  |  | 1 |  |  |  | 0 | 0 | 23677.96 | 0 | 0 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | 8 | 1460.7 | 2022-08-04 | 2022-08-17 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 1460.7 | 1460.7 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1460.7
S335900 | Perform Rack Room Modifications Components Acceptance | 4 | 484.29 | 2022-08-04 | 2022-08-17 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
S335900 | Perform Rack Room Modifications Components Acceptance | 8 | 968.58 | 2022-08-04 | 2022-08-17 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S335900 | Perform Rack Room Modifications Components Acceptance | 8 | 1249.87 | 2022-08-04 | 2022-08-17 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S335900 | Perform Rack Room Modifications Components Acceptance | 8 | 968.58 | 2022-08-04 | 2022-08-17 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
POM02.02.04.01.08 Control Room and Offices Modifications |  | 50324 |  | 06-Sep-21 A | 2022-06-20
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | 8 | 968.58 | 06-Sep-21 A | 2022-02-02 | 85% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 145.287 | 145.287 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 145.287 | 0 | 0
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | 4 | 624.93 | 06-Sep-21 A | 2022-02-02 | 85% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 93.7395 | 93.7395 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 93.7395 | 0 | 0
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 2905.73 | 2022-02-25 | 2022-04-07 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 3749.6 | 2022-02-25 | 2022-04-07 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 2905.73 | 2022-02-25 | 2022-04-07 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 8 | 1460.7 | 2022-06-07 | 2022-06-20 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 1460.7 | 1460.7 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1460.7
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 4 | 484.29 | 2022-06-07 | 2022-06-20 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 8 | 968.58 | 2022-06-07 | 2022-06-20 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 8 | 1249.87 | 2022-06-07 | 2022-06-20 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 8 | 968.58 | 2022-06-07 | 2022-06-20 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S336300 | Review Control Room and Offices Modifications Design/Safety | 4 | 730.35 | 2022-02-03 | 2022-02-09 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 730.35 | 730.35 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 730.35
S336300 | Review Control Room and Offices Modifications Design/Safety | 4 | 624.93 | 2022-02-03 | 2022-02-09 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 1460.7 | 2022-02-10 | 2022-02-24 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 1460.7 | 1460.7 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1460.7
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 968.58 | 2022-02-10 | 2022-02-24 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 968.58 | 2022-02-10 | 2022-02-24 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 1249.87 | 2022-02-10 | 2022-02-24 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 968.58 | 2022-02-10 | 2022-02-24 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S336600 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - CA-D Resource(s) | 2 | 312.47 | 2022-02-25 | 2022-04-07 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.47 | 312.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 312.47
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 8 | 968.58 | 2022-04-08 | 2022-04-21 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 8 | 968.58 | 2022-04-08 | 2022-04-21 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 8 | 1249.87 | 2022-04-08 | 2022-04-21 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 8 | 968.58 | 2022-04-08 | 2022-04-21 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 48 | 5811.46 | 2022-04-22 | 2022-06-03 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 5811.46 | 5811.46 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5811.46
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 24 | 2905.73 | 2022-04-22 | 2022-06-03 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 24 | 3749.6 | 2022-04-22 | 2022-06-03 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 24 | 2905.73 | 2022-04-22 | 2022-06-03 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S336900 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - M&S | 50000 | 59194.9 | 2022-04-25 | 2022-06-06 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 59194.9 | 59194.9 | 0 |  |  | 1 |  |  |  | 0 | 0 | 59194.9 | 0 | 0 | 0
S337000 | Perform Control Room and Offices Modifications Components Acceptance - CA-D Resource(s) | 2 | 312.47 | 2022-06-07 | 2022-06-20 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.47 | 312.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 312.47
POM02.02.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR |  | 113 |  | 2022-10-03 | 2022-10-04 | [20 empty] | 166612.609
S277700 | 2023 Detector Support Systems L3 Project Management | 113 | 20999.07 | 2022-10-03 | 2022-10-04 | 0% | PROF5 PO M | Labor Hr/M&S Direct$ |  |  | 20999.07 | 20999.07 | 0 |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 20999.07 | 0 | All Infrasructure Facility
POM02.02.04.02.02 Beampipe/Vacuum |  | 100072 |  | 01-Oct-21 A | 2022-07-20 | [20 empty] | M&S in-progress
S339300 | Perform Beampipe/vacuum Acceptance - Physics Resource(s) NEG coating | 36 | 4358.6 | 2021-12-01 | 2022-07-20 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 4358.6 | 4358.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4358.6
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) NEG coating | 26 | 3113.28 | 2021-12-01 | 2022-07-20 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 3113.28 | 3113.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3113.28
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) NEG coating | 10 | 1606.97 | 2021-12-01 | 2022-07-20 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1606.97 | 1606.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1606.97
S339350 | NEG Re-coating of beryllium beampipe | 100000 | 111561.35 | 01-Oct-21 A | 2022-06-30 | 0% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 111561.35 | 111561.35 | 0 | 1 | [5 empty] | 111561.35 | 0 | 0 | 0 | 0 | 0
POM02.02.04.02.03 IR HVAC |  | 35262 |  | 02-Sep-21 A | 2022-04-27
S339500 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - M&S | 35000 | 41436.43 | 16-Nov-21 A | 2022-04-13 | 50% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 20718.215 | 20718.215 | 0 | 1 | [5 empty] | 20718.215 | 0 | 0 | 0 | 0 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | 16 | 2216.77 | 02-Sep-21 A | 2022-01-18 | 50% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1108.385 | 1108.385 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1108.385 | 0 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | 32 | 3402.32 | 02-Sep-21 A | 2022-01-18 | 50% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 1701.16 | 1701.16 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1701.16 | 0 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | 4 | 624.93 | 02-Sep-21 A | 2022-01-18 | 50% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.465 | 312.465 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 312.465 | 0 | 0
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | 48 | 6650.3 | 16-Nov-21 A | 2022-04-13 | 50% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 3325.15 | 3325.15 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3325.15 | 0 | 0
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | 96 | 10206.97 | 16-Nov-21 A | 2022-04-13 | 50% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 5103.485 | 5103.485 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 5103.485 | 0 | 0
S340400 | Perform IR HVAC Components Acceptance | 40 | 4842.89 | 2022-04-14 | 2022-04-27 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S340400 | Perform IR HVAC Components Acceptance | 8 | 1108.38 | 2022-04-14 | 2022-04-27 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1108.38 | 1108.38 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1108.38
S340400 | Perform IR HVAC Components Acceptance | 16 | 1701.16 | 2022-04-14 | 2022-04-27 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 1701.16 | 1701.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1701.16
S340400 | Perform IR HVAC Components Acceptance | 2 | 312.47 | 2022-04-14 | 2022-04-27 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.47 | 312.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 312.47
POM02.02.04.02.04 IR Electronics Cooling Water Distribution System |  | 65316 |  | 26-Apr-21 A | 2022-04-14
S340600 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - M&S | 65000 | 76953.37 | 26-Apr-21 A | 2022-04-07 | 80% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 15390.674 | 15390.674 | 0 | 1 | [5 empty] | 15390.674 | 0 | 0 | 0 | 0 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | 8 | 1108.38 | 2021-12-01 | 2021-12-14 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1108.38 | 1108.38 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1108.38
S340900 | Review IR Electronics cooling water System Design/Safety | 16 | 1701.16 | 2021-12-01 | 2021-12-14 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 1701.16 | 1701.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1701.16
S340900 | Review IR Electronics cooling water System Design/Safety | 4 | 624.93 | 2021-12-01 | 2021-12-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 8 | 1108.38 | 2021-12-15 | 2021-12-29 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1108.38 | 1108.38 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1108.38
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 16 | 1701.16 | 2021-12-15 | 2021-12-29 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 1701.16 | 1701.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1701.16
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 2 | 312.47 | 2021-12-15 | 2021-12-29 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.47 | 312.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 312.47
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 16 | 2216.77 | 2021-12-30 | 2022-01-28 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 2216.77 | 2216.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2216.77
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 32 | 3402.32 | 2021-12-30 | 2022-01-28 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 3402.32 | 3402.32 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3402.32
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 4 | 624.93 | 2021-12-30 | 2022-01-28 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 16 | 2216.77 | 2022-01-31 | 2022-02-28 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 2216.77 | 2216.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2216.77
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 32 | 3402.32 | 2022-01-31 | 2022-02-28 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 3402.32 | 3402.32 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3402.32
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 4 | 624.93 | 2022-01-31 | 2022-02-28 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 40 | 5435.38 | 26-Apr-21 A | 2022-03-11 | 70% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1630.614 | 1630.614 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 1630.614 | 0 | 0
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 80 | 8342.3 | 26-Apr-21 A | 2022-03-11 | 70% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 2502.69 | 2502.69 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 2502.69 | 0 | 0
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 2 | 306.46 | 26-Apr-21 A | 2022-03-11 | 70% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 91.938 | 91.938 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 91.938 | 0 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 20 | 2421.44 | 2022-04-08 | 2022-04-14 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 4 | 554.19 | 2022-04-08 | 2022-04-14 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 554.19 | 554.19 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 554.19
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 8 | 850.58 | 2022-04-08 | 2022-04-14 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 850.58 | 850.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 850.58
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 4 | 624.93 | 2022-04-08 | 2022-04-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
POM02.02.04.02.05 IR/AH Safety Subsystems |  | 32795 |  | 14-Dec-20 A | 2022-08-17
S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - M&S | 32000 | 37884.74 | 2022-05-10 | 2022-08-03 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 37884.74 | 37884.74 | 0 | 0.5 |  | 0.5 |  |  |  | 18942.37 | 0 | 18942.37 | 0 | 0 | 0
S341800 | Analyze IR/AH Safety Subsystems Requirements - Physics Resource(s) | 3 | 531.81 | 14-Dec-20 A | 2021-12-29 | 45% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 292.4955 | 292.4955 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 292.4955 | 0 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 72 | 9684.91 | 14-Dec-20 A | 2021-12-29 | 45% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 5326.7005 | 5326.7005 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 5326.7005 | 0 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 96 | 9909.68 | 14-Dec-20 A | 2021-12-29 | 45% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 5450.324 | 5450.324 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 5450.324 | 0 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 10 | 1516.83 | 14-Dec-20 A | 2021-12-29 | 45% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 834.2565 | 834.2565 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 834.2565 | 0 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 60 | 8312.88 | 2021-12-30 | 2022-02-11 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 8312.88 | 8312.88 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8312.88
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 96 | 10206.97 | 2021-12-30 | 2022-02-11 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 10206.97 | 10206.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10206.97
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 8 | 1249.87 | 2021-12-30 | 2022-02-11 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S342000 | Review IR/AH Safety Subsystems Design/Safety | 8 | 1108.38 | 2022-02-14 | 2022-02-28 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1108.38 | 1108.38 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1108.38
S342000 | Review IR/AH Safety Subsystems Design/Safety | 32 | 3402.32 | 2022-02-14 | 2022-02-28 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 3402.32 | 3402.32 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3402.32
S342000 | Review IR/AH Safety Subsystems Design/Safety | 8 | 1249.87 | 2022-02-14 | 2022-02-28 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 8 | 1108.38 | 2022-03-01 | 2022-03-14 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1108.38 | 1108.38 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1108.38
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 32 | 3402.32 | 2022-03-01 | 2022-03-14 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 3402.32 | 3402.32 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3402.32
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 4 | 624.93 | 2022-03-01 | 2022-03-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 8 | 1108.38 | 2022-03-15 | 2022-03-28 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1108.38 | 1108.38 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1108.38
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 16 | 1701.16 | 2022-03-15 | 2022-03-28 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 1701.16 | 1701.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1701.16
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 4 | 624.93 | 2022-03-15 | 2022-03-28 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 24 | 3325.15 | 2022-03-29 | 2022-05-09 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 3325.15 | 3325.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3325.15
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 48 | 5103.49 | 2022-03-29 | 2022-05-09 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 5103.49 | 5103.49 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5103.49
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 4 | 624.93 | 2022-03-29 | 2022-05-09 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 48 | 6650.3 | 2022-05-10 | 2022-08-03 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 6650.3 | 6650.3 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6650.3
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 96 | 10206.97 | 2022-05-10 | 2022-08-03 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 10206.97 | 10206.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10206.97
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 2 | 312.47 | 2022-05-10 | 2022-08-03 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.47 | 312.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 312.47
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 88 | 12192.22 | 2022-08-04 | 2022-08-17 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 12192.22 | 12192.22 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12192.22
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 16 | 1701.16 | 2022-08-04 | 2022-08-17 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 1701.16 | 1701.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1701.16
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 4 | 624.93 | 2022-08-04 | 2022-08-17 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
POM02.02.04.02.06 Assembly Hall and Interaction Region Modifications |  | 10539 |  | 2021-12-01 | 2022-08-03
S342800 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - M&S | 10000 | 11838.98 | 2022-03-15 | 2022-07-20 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 11838.98 | 11838.98 | 0 |  |  | 1 |  |  |  | 0 | 0 | 11838.98 | 0 | 0 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 8 | 1108.38 | 2021-12-01 | 2021-12-14 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 1108.38 | 1108.38 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1108.38
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 16 | 1701.16 | 2021-12-01 | 2021-12-14 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 1701.16 | 1701.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1701.16
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 5 | 781.17 | 2021-12-01 | 2021-12-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 781.17 | 781.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 781.17
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 72 | 9975.45 | 2021-12-15 | 2022-01-28 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 9975.45 | 9975.45 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9975.45
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 48 | 5103.49 | 2021-12-15 | 2022-01-28 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 5103.49 | 5103.49 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5103.49
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 4 | 624.93 | 2021-12-15 | 2022-01-28 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 72 | 9975.45 | 2022-01-31 | 2022-03-14 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 9975.45 | 9975.45 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9975.45
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 48 | 5103.49 | 2022-01-31 | 2022-03-14 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 5103.49 | 5103.49 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5103.49
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 2 | 312.47 | 2022-01-31 | 2022-03-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 312.47 | 312.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 312.47
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 72 | 9975.45 | 2022-03-15 | 2022-07-20 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 9975.45 | 9975.45 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9975.45
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 144 | 15310.46 | 2022-03-15 | 2022-07-20 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 15310.46 | 15310.46 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 15310.46
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 8 | 1249.87 | 2022-03-15 | 2022-07-20 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S343700 | Perform Assembly Hall Modifications Components Acceptance | 24 | 3325.15 | 2022-07-21 | 2022-08-03 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 3325.15 | 3325.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3325.15
S343700 | Perform Assembly Hall Modifications Components Acceptance | 16 | 1701.16 | 2022-07-21 | 2022-08-03 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 1701.16 | 1701.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1701.16
POM02.02.05.02 Infrastructure Installation |  | 13314 |  | 09-Sep-21 A | 2022-10-19 | [20 empty] | 302506.664
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 32 | 3880.12 | 2022-09-06 | 2022-10-03 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 3880.12 | 3880.12 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3880.12 | All Installation
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 200 | 26577.44 | 2022-09-06 | 2022-10-03 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 26577.44 | 26577.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 26577.44 | M&S in-progress
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 80 | 12517.42 | 2022-09-06 | 2022-10-03 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 12517.42 | 12517.42 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12517.42
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 200 | 24250.76 | 2022-09-06 | 2022-10-03 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 24250.76 | 24250.76 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 24250.76
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 200 | 24250.76 | 2022-09-06 | 2022-10-03 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 24250.76 | 24250.76 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 24250.76
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 160 | 21230.1 | 09-Sep-21 A | 2022-01-25 | 20% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 16984.08 | 16984.08 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 16984.08 | 0 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 40 | 6249.34 | 09-Sep-21 A | 2022-01-25 | 20% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 4999.472 | 4999.472 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 4999.472 | 0 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 4 | 818.98 | 09-Sep-21 A | 2022-01-25 | 20% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 655.184 | 655.184 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 655.184 | 0 | 0
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 80 | 10615.05 | 2022-01-26 | 2022-02-23 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10615.05 | 10615.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10615.05
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 40 | 6249.34 | 2022-01-26 | 2022-02-23 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4842.89 | 2022-04-28 | 2022-05-11 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S345500 | Install IR HVAC - Labor - C-AD Resources | 64 | 8492.04 | 2022-04-28 | 2022-05-11 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 8492.04 | 8492.04 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8492.04
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4252.91 | 2022-04-28 | 2022-05-11 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 4252.91 | 4252.91 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4252.91
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 6249.34 | 2022-04-28 | 2022-05-11 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S345600 | Install IR HVAC - M&S | 500 | 591.95 | 2022-04-28 | 2022-05-11 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 80 | 9685.77 | 2022-08-18 | 2022-09-15 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 16 | 2499.74 | 2022-08-18 | 2022-09-15 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 24 | 3184.52 | 2022-08-18 | 2022-09-15 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 3184.52 | 3184.52 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3184.52
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 40 | 4252.91 | 2022-08-18 | 2022-09-15 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 4252.91 | 4252.91 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4252.91
S345800 | Install On Detector Safety Subsystems - Labor | 80 | 9685.77 | 2022-06-17 | 2022-07-15 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S345800 | Install On Detector Safety Subsystems - Labor | 40 | 4842.89 | 2022-06-17 | 2022-07-15 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3124.67 | 2022-06-17 | 2022-07-15 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3124.67 | 2022-06-17 | 2022-07-15 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S345900 | Install On Detector Safety Subsystems - M&S | 500 | 591.95 | 2022-06-17 | 2022-07-15 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S345910 | Install Off Detector Safety Subsystems - M&S | 500 | 591.95 | 2022-08-18 | 2022-09-15 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 32 | 4999.47 | 09-Sep-21 A | 2022-01-25 | 20% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 3999.576 | 3999.576 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3999.576
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 32 | 4999.47 | 2022-01-26 | 2022-02-23 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 4999.47 | 4999.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4999.47
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 4 | 818.98 | 2022-01-26 | 2022-02-23 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 818.98 | 818.98 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 818.98
S346200 | Install Line Electric Power Distribution Off Detector - M&S | 500 | 591.95 | 09-Sep-21 A | 2022-01-25 | 20% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 473.56 | 473.56 | 0 | 1 | [5 empty] | 473.56 | 0 | 0 | 0 | 0 | 0
S346210 | Install Line Electric Power Distribution On Detector - M&S | 500 | 591.95 | 2022-01-26 | 2022-02-23 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S346298 | Build North and South work platforms | 30 | 3632.17 | 2022-08-23 | 2022-08-24 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 3632.17 | 3632.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3632.17
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 20 | 3124.67 | 2022-08-25 | 2022-08-25 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 40 | 4842.89 | 2022-08-25 | 2022-08-25 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 16 | 1937.15 | 2022-08-25 | 2022-08-25 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 104 | 12591.51 | 2022-08-25 | 2022-08-25 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 12591.51 | 12591.51 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12591.51
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 80 | 8505.81 | 2022-08-25 | 2022-08-25 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 8505.81 | 8505.81 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8505.81
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 40 | 6249.34 | 2022-08-25 | 2022-08-25 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S346400 | Install Beampipe Temp Support M&S | 500 | 591.95 | 2022-08-25 | 2022-08-25 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S346402 | Beampipe bakeout | 500 | 591.95 | 2022-08-26 | 2022-08-29 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S346404 | Install permanent Beampipe support | 500 | 603.79 | 2022-09-21 | 2022-09-21 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 12541.53 | 2022-08-18 | 2022-10-06 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 12541.53 | 12541.53 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12541.53
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 160 | 19437.97 | 2022-08-18 | 2022-10-06 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 19437.97 | 19437.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19437.97
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 160 | 19437.97 | 2022-08-18 | 2022-10-06 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 19437.97 | 19437.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19437.97
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 40 | 4859.49 | 2022-08-18 | 2022-10-06 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 4859.49 | 4859.49 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4859.49
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 12541.53 | 2022-08-18 | 2022-10-06 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 12541.53 | 12541.53 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12541.53
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 160 | 19437.97 | 2022-08-18 | 2022-10-06 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 19437.97 | 19437.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19437.97
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 160 | 21302.89 | 2022-08-18 | 2022-10-06 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 21302.89 | 21302.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 21302.89
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 20 | 2133.74 | 2022-08-18 | 2022-10-06 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 2133.74 | 2133.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2133.74
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 8 | 1254.15 | 2022-08-18 | 2022-10-06 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1254.15 | 1254.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1254.15
S346800 | Install Non-IR Infrastructure - M&S | 500 | 593.3 | 2022-08-18 | 2022-10-06 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 593.3 | 593.3 | 0 |  |  | 1 |  |  |  | 0 | 0 | 593.3 | 0 | 0 | 0
S346900 | Install Detector Support Services Systems - Labor - CA-D Resource(s) | 40 | 4259.28 | 2022-09-06 | 2022-10-03 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 4259.28 | 4259.28 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4259.28
S347000 | Install Detector Support Services Systems - M&S | 500 | 592.54 | 2022-09-06 | 2022-10-03 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 592.54 | 592.54 | 0 |  |  | 1 |  |  |  | 0 | 0 | 592.54 | 0 | 0 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 120 | 18748.01 | 13-Sep-21 A | 2022-07-25 | 20% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 14998.408 | 14998.408 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 14998.408 | 0 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 280 | 33900.21 | 13-Sep-21 A | 2022-07-25 | 20% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 27120.168 | 27120.168 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 27120.168 | 0 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 280 | 33900.21 | 13-Sep-21 A | 2022-07-25 | 20% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 27120.168 | 27120.168 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 27120.168 | 0 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 48 | 5811.46 | 13-Sep-21 A | 2022-07-25 | 20% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 4649.168 | 4649.168 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 4649.168 | 0 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 120 | 18748.01 | 13-Sep-21 A | 2022-07-25 | 20% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 14998.408 | 14998.408 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 14998.408 | 0 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18860.5 | 2022-07-26 | 2022-10-19 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 18860.5 | 18860.5 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 18860.5
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 34103.61 | 2022-07-26 | 2022-10-19 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 34103.61 | 34103.61 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 34103.61
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 34103.61 | 2022-07-26 | 2022-10-19 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 34103.61 | 34103.61 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 34103.61
S347200 | Install Electronics Racks On Carriage - Labor | 48 | 5846.33 | 2022-07-26 | 2022-10-19 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 5846.33 | 5846.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5846.33
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18860.5 | 2022-07-26 | 2022-10-19 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 18860.5 | 18860.5 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 18860.5
S347300 | Install Electronics Racks Rackroom - M&S | 500 | 591.95 | 13-Sep-21 A | 2022-07-25 | 20% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 473.56 | 473.56 | 0 | 1 | [5 empty] | 473.56 | 0 | 0 | 0 | 0 | 0
S347310 | Install Electronics Racks On Carriage - M&S | 500 | 594.32 | 2022-07-26 | 2022-10-19 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 594.32 | 594.32 | 0 |  |  | 1 |  |  |  | 0 | 0 | 594.32 | 0 | 0 | 0
S347400 | Install Gas and Cooling System Services - Labor | 120 | 18748.01 | 2022-08-04 | 2022-09-29 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 18748.01 | 18748.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 18748.01
S347400 | Install Gas and Cooling System Services - Labor | 720 | 87171.97 | 2022-08-04 | 2022-09-29 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 87171.97 | 87171.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 87171.97
S347400 | Install Gas and Cooling System Services - Labor | 96 | 11622.93 | 2022-08-04 | 2022-09-29 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 11622.93 | 11622.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11622.93
S347500 | Install Gas and Cooling System Services - M&S | 500 | 591.95 | 2022-08-04 | 2022-09-29 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 80 | 9685.77 | 2022-04-15 | 2022-05-12 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 80 | 10615.05 | 2022-04-15 | 2022-05-12 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10615.05 | 10615.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10615.05
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 20 | 2126.45 | 2022-04-15 | 2022-05-12 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 2126.45 | 2126.45 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2126.45
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 8 | 1249.87 | 2022-04-15 | 2022-05-12 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 80 | 9685.77 | 2022-02-25 | 2022-03-24 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 16 | 1937.15 | 2022-02-25 | 2022-03-24 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 32 | 4246.02 | 2022-02-25 | 2022-03-24 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 4246.02 | 4246.02 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4246.02
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 20 | 3124.67 | 2022-02-25 | 2022-03-24 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S347800 | Install IR Electronics Cooling Water Off Detector - M&S | 500 | 591.95 | 2022-04-15 | 2022-05-12 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S347810 | Install IR Electronics Cooling Water On Detector - M&S | 500 | 591.95 | 2022-02-25 | 2022-03-24 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
POM02.02.05.03 Cradle Carriage Assembly/Installation |  | 5016 |  | 2022-01-27 | 2022-02-24
S349300 | Install platforms & access - Labor - Physics Resource(s) | 16 | 2499.74 | 2022-01-27 | 2022-02-24 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S349300 | Install platforms & access - Labor - Physics Resource(s) | 240 | 29057.32 | 2022-01-27 | 2022-02-24 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 29057.32 | 29057.32 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 29057.32
S349300 | Install platforms & access - Labor - Physics Resource(s) | 16 | 1937.15 | 2022-01-27 | 2022-02-24 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 176 | 27497.09 | 2022-01-27 | 2022-02-24 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 27497.09 | 27497.09 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 27497.09
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 72 | 8717.2 | 2022-01-27 | 2022-02-24 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 8717.2 | 8717.2 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8717.2
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 80 | 11083.84 | 2022-01-27 | 2022-02-24 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 11083.84 | 11083.84 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11083.84
S349400 | Install platforms & access - M&S | 1000 | 1183.9 | 2022-01-27 | 2022-02-24 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 1183.9 | 1183.9 | 0 |  |  | 1 |  |  |  | 0 | 0 | 1183.9 | 0 | 0 | 0
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 8 | 1249.87 | 2022-02-01 | 2022-02-14 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 64 | 7748.62 | 2022-02-01 | 2022-02-14 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 7748.62 | 7748.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7748.62
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 8 | 968.58 | 2022-02-01 | 2022-02-14 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 136 | 21247.75 | 2022-02-01 | 2022-02-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 21247.75 | 21247.75 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 21247.75
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 120 | 15922.58 | 2022-02-01 | 2022-02-14 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 15922.58 | 15922.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 15922.58
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 80 | 11083.84 | 2022-02-01 | 2022-02-14 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 11083.84 | 11083.84 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11083.84
S349600 | Install Pole Tips - M&S | 3000 | 3551.69 | 2022-02-01 | 2022-02-14 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 3551.69 | 3551.69 | 0 |  |  | 1 |  |  |  | 0 | 0 | 3551.69 | 0 | 0 | 0
POM02.02.05.04 Outer Hcal Installation |  | 6188 |  | 22-Nov-21 A | 2022-04-28
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 8 | 1249.87 | 2021-12-06 | 2021-12-17 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 256 | 33968.17 | 2021-12-06 | 2021-12-17 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 33968.17 | 33968.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 33968.17
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 8 | 968.58 | 2021-12-06 | 2021-12-17 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 128 | 15497.24 | 2021-12-06 | 2021-12-17 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 15497.24 | 15497.24 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 15497.24
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 64 | 9998.94 | 2021-12-13 | 2022-01-11 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 9998.94 | 9998.94 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9998.94
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 64 | 7748.62 | 2021-12-13 | 2022-01-11 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 7748.62 | 7748.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7748.62
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 512 | 61988.96 | 2021-12-13 | 2022-01-11 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 61988.96 | 61988.96 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 61988.96
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 480 | 63690.31 | 2021-12-13 | 2022-01-11 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 63690.31 | 63690.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 63690.31
S350950 | Install Large Support Rings and Cross Braces | 40 | 4842.89 | 22-Nov-21 A | 2021-12-03 | 50% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.445 | 2421.445 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.445
S350950 | Install Large Support Rings and Cross Braces | 40 | 6249.34 | 22-Nov-21 A | 2021-12-03 | 50% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S351000 | Transport Remainder of Outer Hcal Sectors to AH - Labor - CA-D Resource(s) | 8 | 850.58 | 2021-12-06 | 2021-12-17 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 850.58 | 850.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 850.58
S351100 | Transport Remainder of Outer Hcal Sectors to AH - M&S | 500 | 591.95 | 2021-12-06 | 2021-12-17 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 20 | 2126.45 | 2021-12-13 | 2022-01-26 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 2126.45 | 2126.45 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2126.45
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 8 | 1249.87 | 2021-12-13 | 2022-01-26 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 480 | 66503.02 | 2021-12-13 | 2022-01-26 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 66503.02 | 66503.02 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 66503.02
S351300 | Install Remainder of Outer HCal Sectors - M&S | 500 | 591.95 | 2021-12-13 | 2022-01-26 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | 4 | 484.29 | 2022-01-27 | 2022-02-02 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | 20 | 2421.44 | 2022-01-27 | 2022-02-02 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | 80 | 10615.05 | 2022-01-27 | 2022-02-02 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10615.05 | 10615.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10615.05
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | 60 | 7264.33 | 2022-01-27 | 2022-02-02 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S351500 | Align/Survey Outer Hcal to Centerline - M&S | 500 | 591.95 | 2022-01-27 | 2022-02-02 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 9685.77 | 2022-02-03 | 2022-03-03 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S351600 | Install Outer HCal Cables and Services - Labor | 160 | 19371.55 | 2022-02-03 | 2022-03-03 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 12498.68 | 2022-02-03 | 2022-03-03 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 12498.68 | 12498.68 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12498.68
S351700 | Install Outer HCal Cables and Services - M&S | 500 | 591.95 | 2022-02-03 | 2022-03-03 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | 8 | 1249.87 | 2022-03-04 | 2022-03-17 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S351800 | Review Outer HCal for Operational Readiness (ORR) | 8 | 968.58 | 2022-03-04 | 2022-03-17 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S351800 | Review Outer HCal for Operational Readiness (ORR) | 8 | 968.58 | 2022-03-04 | 2022-03-17 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S351800 | Review Outer HCal for Operational Readiness (ORR) | 8 | 968.58 | 2022-03-04 | 2022-03-17 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S351900 | Address Action Items from Outer Hcal ORR | 8 | 1249.87 | 2022-03-18 | 2022-03-31 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S351900 | Address Action Items from Outer Hcal ORR | 8 | 968.58 | 2022-03-18 | 2022-03-31 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S351900 | Address Action Items from Outer Hcal ORR | 8 | 968.58 | 2022-03-18 | 2022-03-31 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S351900 | Address Action Items from Outer Hcal ORR | 8 | 968.58 | 2022-03-18 | 2022-03-31 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S352000 | Commission Outer HCal - Labor | 32 | 4999.47 | 2022-04-01 | 2022-04-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 4999.47 | 4999.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4999.47
S352000 | Commission Outer HCal - Labor | 160 | 29213.91 | 2022-04-01 | 2022-04-28 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 29213.91 | 29213.91 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 29213.91
S352000 | Commission Outer HCal - Labor | 32 | 3874.31 | 2022-04-01 | 2022-04-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S352000 | Commission Outer HCal - Labor | 320 | 38743.1 | 2022-04-01 | 2022-04-28 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 38743.1 | 38743.1 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 38743.1
S352000 | Commission Outer HCal - Labor | 160 | 24997.35 | 2022-04-01 | 2022-04-28 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 24997.35 | 24997.35 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 24997.35
S352000 | Commission Outer HCal - Labor | 320 | 38743.1 | 2022-04-01 | 2022-04-28 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 38743.1 | 38743.1 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 38743.1
S352200 | Commission Outer HCal - M&S | 500 | 591.95 | 2022-04-01 | 2022-04-28 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
POM02.02.05.05 SC Magnet Installation |  | 96 |  | 2021-12-01 | 2021-12-29
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 8 | 1249.87 | 2021-12-01 | 2021-12-14 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 8 | 968.58 | 2021-12-01 | 2021-12-14 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 8 | 968.58 | 2021-12-01 | 2021-12-14 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 8 | 968.58 | 2021-12-01 | 2021-12-14 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 8 | 1637.97 | 2021-12-01 | 2021-12-14 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 1637.97 | 1637.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1637.97
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 8 | 1249.87 | 2021-12-01 | 2021-12-14 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 8 | 1249.87 | 2021-12-15 | 2021-12-29 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 8 | 968.58 | 2021-12-15 | 2021-12-29 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 8 | 968.58 | 2021-12-15 | 2021-12-29 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 8 | 968.58 | 2021-12-15 | 2021-12-29 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 8 | 1637.97 | 2021-12-15 | 2021-12-29 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 1637.97 | 1637.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1637.97
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 8 | 1249.87 | 2021-12-15 | 2021-12-29 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
POM02.02.05.06 Inner Hcal Installation |  | 272912 |  | 15-Nov-21 A | 2022-04-21
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | 8 | 1249.87 | 2022-01-27 | 2022-01-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | 2 | 242.14 | 2022-01-27 | 2022-01-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 242.14 | 242.14 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 242.14
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | 32 | 3874.31 | 2022-01-27 | 2022-01-28 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S354600 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures (North slider) - M&S | 80000 | 94711.84 | 19-Nov-21 A | 2021-12-10 | 1% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 93764.7216 | 93764.7216 | 0 | 1 | [5 empty] | 93764.7216 | 0 | 0 | 0 | 0 | 0
S354610 | IHCal Fixture South Slider Beam | 80805 | 90147.15 | 19-Nov-21 A | 2022-01-10 | 1% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 89245.6785 | 89245.6785 | 0 | 1 | [5 empty] | 89245.6785 | 0 | 0 | 0 | 0 | 0
S354620 | IHCal A-Frame stand | 44894 | 50084.35 | 19-Nov-21 A | 2022-01-10 | 1% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 49583.5065 | 49583.5065 | 0 | 1 | [5 empty] | 49583.5065 | 0 | 0 | 0 | 0 | 0
S354630 | IHCal Barrel Fabrication Sled | 47818 | 53346.41 | 19-Nov-21 A | 2022-01-14 | 1% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 52812.9459 | 52812.9459 | 0 | 1 | [5 empty] | 52812.9459 | 0 | 0 | 0 | 0 | 0
S354670 | IHCal motor and gearbox for rings | 14625 | 16315.85 | 19-Nov-21 A | 2022-01-20 | 1% | Purch 1st $2M Fixed | Labor Hr/M&S Direct$ |  |  | 16152.6915 | 16152.6915 | 0 | 1 | [5 empty] | 16152.6915 | 0 | 0 | 0 | 0 | 0
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 15-Nov-21 A | 2022-03-14 | 10% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1124.883 | 1124.883 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1124.883
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 15-Nov-21 A | 2022-03-14 | 10% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 871.722 | 871.722 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 871.722
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 15-Nov-21 A | 2022-03-14 | 10% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 871.722 | 871.722 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 871.722
S355338 | Move third 8 IHCal sectors to assembly area | 16 | 1937.15 | 2021-12-10 | 2021-12-30 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S355348 | Move fourth 8 IHCal sectors to assembly area | 16 | 1937.15 | 2021-12-20 | 2022-01-10 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S355350 | Assemble first 8 IHCal sectors into barrel on fixture | 16 | 1937.15 | 2021-12-13 | 2021-12-17 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S355352 | Assemble second 8 IHCal sectors into barrel on fixture | 32 | 3874.31 | 2021-12-20 | 2021-12-27 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S355354 | Assemble third 8 IHCal sectors into barrel on fixture | 32 | 3874.31 | 2022-01-04 | 2022-01-10 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S355356 | Assemble fourth/last 8 IHCal sectors into barrel on fixture | 32 | 3874.31 | 2022-01-12 | 2022-01-19 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | 64 | 9998.94 | 2022-01-20 | 2022-01-26 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 9998.94 | 9998.94 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9998.94
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | 64 | 7748.62 | 2022-01-20 | 2022-01-26 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 7748.62 | 7748.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7748.62
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | 512 | 61988.96 | 2022-01-20 | 2022-01-26 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 61988.96 | 61988.96 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 61988.96
S355700 | Install Inner HCal assembly on Insertion Fixture - M&S | 500 | 591.95 | 2022-01-20 | 2022-01-26 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S356000 | Install Inner HCal - Labor - CA-D Resource(s) | 4 | 624.93 | 2022-01-27 | 2022-01-28 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S356000 | Install Inner HCal - Labor - CA-D Resource(s) | 120 | 16625.75 | 2022-01-27 | 2022-01-28 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 16625.75 | 16625.75 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 16625.75
S356100 | Install Inner HCal - M&S | 500 | 591.95 | 2022-01-31 | 2022-02-01 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S356400 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - Physics Resource(s) | 4 | 484.29 | 2022-02-02 | 2022-02-08 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 484.29 | 484.29 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 484.29
S356400 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421.44 | 2022-02-02 | 2022-02-08 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615.05 | 2022-02-02 | 2022-02-08 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10615.05 | 10615.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10615.05
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264.33 | 2022-02-02 | 2022-02-08 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8312.88 | 2022-02-02 | 2022-02-08 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 8312.88 | 8312.88 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8312.88
S356500 | Align/Survey Inner HCal to SC Magnet Centerline - M&S | 500 | 591.95 | 2022-02-02 | 2022-02-08 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 9685.77 | 2022-01-20 | 2022-02-16 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 160 | 19371.55 | 2022-01-20 | 2022-02-16 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 12498.68 | 2022-01-20 | 2022-02-16 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 12498.68 | 12498.68 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12498.68
S356700 | Install Inner HCal Cables and Services (if instrumented) - M&S | 500 | 591.95 | 2022-02-17 | 2022-03-17 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 1249.87 | 2022-03-18 | 2022-03-31 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 1249.87 | 2022-03-18 | 2022-03-31 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 968.58 | 2022-03-18 | 2022-03-31 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 968.58 | 2022-03-18 | 2022-03-31 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 968.58 | 2022-03-18 | 2022-03-31 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S356900 | Address Action Items from Inner Hcal ORR | 8 | 1249.87 | 2022-04-01 | 2022-04-14 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S356900 | Address Action Items from Inner Hcal ORR | 8 | 1249.87 | 2022-04-01 | 2022-04-14 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S356900 | Address Action Items from Inner Hcal ORR | 8 | 968.58 | 2022-04-01 | 2022-04-14 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S356900 | Address Action Items from Inner Hcal ORR | 8 | 968.58 | 2022-04-01 | 2022-04-14 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S356900 | Address Action Items from Inner Hcal ORR | 8 | 968.58 | 2022-04-01 | 2022-04-14 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 320 | 58427.81 | 2022-04-15 | 2022-04-21 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 58427.81 | 58427.81 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 58427.81
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 160 | 24997.35 | 2022-04-15 | 2022-04-21 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 24997.35 | 24997.35 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 24997.35
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 160 | 19371.55 | 2022-04-15 | 2022-04-21 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 32 | 3874.31 | 2022-04-15 | 2022-04-21 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S357200 | Commission Inner HCal - M&S | 500 | 591.95 | 2022-04-15 | 2022-04-21 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
POM02.02.05.07 EMCal Installation |  | 4824 |  | 2022-03-04 | 2022-07-08
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 120 | 15922.58 | 2022-03-04 | 2022-03-25 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 15922.58 | 15922.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 15922.58
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 64 | 7748.62 | 2022-03-04 | 2022-03-25 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 7748.62 | 7748.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7748.62
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 8 | 1249.87 | 2022-03-04 | 2022-03-25 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S358300 | Transport Assembled EMCal Sectors to AH - M&S | 500 | 591.95 | 2022-03-04 | 2022-03-25 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S358400 | Install EMCal Sectors - Labor | 64 | 9998.94 | 2022-03-07 | 2022-03-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 9998.94 | 9998.94 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9998.94
S358400 | Install EMCal Sectors - Labor | 64 | 7748.62 | 2022-03-07 | 2022-03-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 7748.62 | 7748.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7748.62
S358400 | Install EMCal Sectors - Labor | 512 | 61988.96 | 2022-03-07 | 2022-03-28 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 61988.96 | 61988.96 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 61988.96
S358500 | Install EMCal Sectors - M&S | 500 | 591.95 | 2022-03-07 | 2022-03-28 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421.44 | 2022-03-29 | 2022-04-19 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615.05 | 2022-03-29 | 2022-04-19 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10615.05 | 10615.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10615.05
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264.33 | 2022-03-29 | 2022-04-19 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8312.88 | 2022-03-29 | 2022-04-19 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 8312.88 | 8312.88 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8312.88
S358700 | Align/Survey EMCal to SC Magnet Centerline - M&S | 500 | 591.95 | 2022-03-29 | 2022-04-19 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S358800 | Install EMCal Cables and Services - Labor | 160 | 19371.55 | 2022-04-20 | 2022-05-11 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 19371.55 | 19371.55 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 19371.55
S358800 | Install EMCal Cables and Services - Labor | 64 | 7748.62 | 2022-04-20 | 2022-05-11 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 7748.62 | 7748.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7748.62
S358800 | Install EMCal Cables and Services - Labor | 32 | 4999.47 | 2022-04-20 | 2022-05-11 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 4999.47 | 4999.47 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4999.47
S358800 | Install EMCal Cables and Services - Labor | 32 | 3874.31 | 2022-04-20 | 2022-05-11 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 3874.31 | 3874.31 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3874.31
S358800 | Install EMCal Cables and Services - Labor | 320 | 42460.21 | 2022-04-20 | 2022-05-11 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 42460.21 | 42460.21 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 42460.21
S358900 | Install EMCal Cables and Services - M&S | 500 | 591.95 | 2022-04-20 | 2022-05-11 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | 8 | 1249.87 | 2022-05-12 | 2022-05-18 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S359000 | EMCal - Operational Readiness Review (ORR) | 8 | 968.58 | 2022-05-12 | 2022-05-18 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S359000 | EMCal - Operational Readiness Review (ORR) | 8 | 968.58 | 2022-05-12 | 2022-05-18 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S359000 | EMCal - Operational Readiness Review (ORR) | 8 | 968.58 | 2022-05-12 | 2022-05-18 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S359100 | Address Action Items from EMCal ORR | 8 | 1249.87 | 2022-05-19 | 2022-06-02 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S359100 | Address Action Items from EMCal ORR | 8 | 968.58 | 2022-05-19 | 2022-06-02 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S359100 | Address Action Items from EMCal ORR | 8 | 968.58 | 2022-05-19 | 2022-06-02 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S359100 | Address Action Items from EMCal ORR | 8 | 968.58 | 2022-05-19 | 2022-06-02 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S359200 | Commission EMCal - Labor | 400 | 73034.77 | 2022-06-03 | 2022-07-08 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 73034.77 | 73034.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 73034.77
S359200 | Commission EMCal - Labor | 40 | 6249.34 | 2022-06-03 | 2022-07-08 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S359200 | Commission EMCal - Labor | 40 | 4842.89 | 2022-06-03 | 2022-07-08 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S359200 | Commission EMCal - Labor | 40 | 6249.34 | 2022-06-03 | 2022-07-08 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S359200 | Commission EMCal - Labor | 40 | 4842.89 | 2022-06-03 | 2022-07-08 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S359200 | Commission EMCal - Labor | 40 | 4842.89 | 2022-06-03 | 2022-07-08 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S359400 | Commission EMCal - M&S | 500 | 591.95 | 2022-06-03 | 2022-07-08 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
POM02.02.05.08 TPC Installation |  | 34840 |  | 10-Feb-21 A | 2022-10-24
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 4 | 624.93 | 2022-08-08 | 2022-08-12 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 16 | 1937.15 | 2022-08-08 | 2022-08-12 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 60 | 7264.33 | 2022-08-08 | 2022-08-12 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 36 | 4776.77 | 2022-08-08 | 2022-08-12 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 4776.77 | 4776.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4776.77
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 60 | 9374.01 | 2021-12-01 | 2022-04-11 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 9374.01 | 9374.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9374.01
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 20 | 2421.44 | 2021-12-01 | 2022-04-11 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S359800 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - M&S | 30000 | 35516.94 | 2021-12-01 | 2022-04-11 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 35516.94 | 35516.94 | 0 |  |  | 1 |  |  |  | 0 | 0 | 35516.94 | 0 | 0 | 0
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 10-Feb-21 A | 2022-04-25 | 90% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 606.732 | 606.732 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 606.732
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 8 | 940.37 | 10-Feb-21 A | 2022-04-25 | 90% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 94.037 | 94.037 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 94.037
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 20 | 2350.92 | 10-Feb-21 A | 2022-04-25 | 90% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 235.092 | 235.092 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 235.092
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-04-26 | 2022-05-09 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-04-26 | 2022-05-09 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-04-26 | 2022-05-09 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-05-10 | 2022-05-23 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-05-10 | 2022-05-23 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-05-10 | 2022-05-23 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 1249.87 | 2022-05-27 | 2022-06-03 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 24 | 2905.73 | 2022-05-27 | 2022-06-03 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 968.58 | 2022-05-27 | 2022-06-03 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 8 | 1249.87 | 2022-05-27 | 2022-06-03 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S360500 | Transport Assembled TPC Sections to AH - M&S | 500 | 591.95 | 2022-05-27 | 2022-06-03 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S360600 | Open SC Magnet Pole Tip Doors | 4 | 624.93 | 2022-06-06 | 2022-06-06 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S360600 | Open SC Magnet Pole Tip Doors | 16 | 1937.15 | 2022-06-06 | 2022-06-06 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S360700 | Install TPC Support - Labor | 4 | 624.93 | 2022-08-01 | 2022-08-05 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 624.93 | 624.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 624.93
S360700 | Install TPC Support - Labor | 16 | 1937.15 | 2022-08-01 | 2022-08-05 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S360700 | Install TPC Support - Labor | 80 | 9685.77 | 2022-08-01 | 2022-08-05 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9685.77 | 9685.77 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9685.77
S360800 | Install TPC Support - M&S | 500 | 591.95 | 2022-08-01 | 2022-08-05 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 8 | 850.58 | 2022-08-08 | 2022-08-15 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 850.58 | 850.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 850.58
S361000 | Install TPC (Mechanical) - M&S | 500 | 591.95 | 2022-08-08 | 2022-08-15 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421.44 | 2022-08-16 | 2022-08-22 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615.05 | 2022-08-16 | 2022-08-22 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10615.05 | 10615.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10615.05
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264.33 | 2022-08-16 | 2022-08-22 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8312.88 | 2022-08-16 | 2022-08-22 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 8312.88 | 8312.88 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8312.88
S361200 | Align/Survey TPC to SC Magnet Centerline - M&S | 500 | 591.95 | 2022-08-16 | 2022-08-22 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S361300 | Install TPC Cables and Services - Labor | 120 | 14528.66 | 2022-08-26 | 2022-09-16 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 14528.66 | 14528.66 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14528.66
S361300 | Install TPC Cables and Services - Labor | 60 | 7264.33 | 2022-08-26 | 2022-09-16 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S361300 | Install TPC Cables and Services - Labor | 24 | 3749.6 | 2022-08-26 | 2022-09-16 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S361300 | Install TPC Cables and Services - Labor | 24 | 2905.73 | 2022-08-26 | 2022-09-16 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S361300 | Install TPC Cables and Services - Labor | 240 | 31845.16 | 2022-08-26 | 2022-09-16 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 31845.16 | 31845.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 31845.16
S361400 | Install TPC Cables and Services - M&S | 500 | 591.95 | 2022-08-26 | 2022-09-16 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S361500 | TPC - Operational Readiness Review (ORR) | 8 | 1287.36 | 2022-09-19 | 2022-09-23 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S361500 | TPC - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-09-19 | 2022-09-23 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S361500 | TPC - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-09-19 | 2022-09-23 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S361500 | TPC - Operational Readiness Review (ORR) | 8 | 1105.92 | 2022-09-19 | 2022-09-23 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1105.92 | 1105.92 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1105.92
S361600 | Address Action Items from TPC ORR | 8 | 1287.36 | 2022-09-26 | 2022-09-30 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S361600 | Address Action Items from TPC ORR | 8 | 997.63 | 2022-09-26 | 2022-09-30 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S361600 | Address Action Items from TPC ORR | 8 | 1105.92 | 2022-09-26 | 2022-09-30 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 1105.92 | 1105.92 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1105.92
S361600 | Address Action Items from TPC ORR | 8 | 997.63 | 2022-09-26 | 2022-09-30 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S361700 | Commission TPC - Labor Phys | 40 | 6436.82 | 2022-10-03 | 2022-10-24 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 6436.82 | 6436.82 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6436.82
S361700 | Commission TPC - Labor Phys | 40 | 4988.17 | 2022-10-03 | 2022-10-24 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S361700 | Commission TPC - Labor Phys | 400 | 75225.81 | 2022-10-03 | 2022-10-24 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 75225.81 | 75225.81 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 75225.81
S361700 | Commission TPC - Labor Phys | 40 | 4988.17 | 2022-10-03 | 2022-10-24 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S361700 | Commission TPC - Labor Phys | 40 | 6436.82 | 2022-10-03 | 2022-10-24 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 6436.82 | 6436.82 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6436.82
S361700 | Commission TPC - Labor Phys | 40 | 4988.17 | 2022-10-03 | 2022-10-24 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S361900 | Commission TPC - M&S | 500 | 603.79 | 2022-10-03 | 2022-10-24 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
POM02.02.05.09 INTT Installation |  | 34846 |  | 01-Oct-19 A | 2022-10-19
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 30 | 4550.49 | 01-Oct-19 A | 2021-12-29 | 95% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 227.5245 | 227.5245 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 227.5245
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 60 | 7052.75 | 01-Oct-19 A | 2021-12-29 | 95% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 352.6375 | 352.6375 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 352.6375
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | 60 | 9374.01 | 2021-12-30 | 2022-03-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 9374.01 | 9374.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9374.01
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | 20 | 2421.44 | 2021-12-30 | 2022-03-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S362200 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - M&S | 30000 | 35516.94 | 2021-12-30 | 2022-03-28 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 35516.94 | 35516.94 | 0 |  |  | 1 |  |  |  | 0 | 0 | 35516.94 | 0 | 0 | 0
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 40 | 6249.34 | 2022-03-29 | 2022-04-11 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 20 | 2421.44 | 2022-03-29 | 2022-04-11 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-04-12 | 2022-04-25 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-04-12 | 2022-04-25 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-04-12 | 2022-04-25 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 1249.87 | 2022-04-26 | 2022-05-09 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 968.58 | 2022-04-26 | 2022-05-09 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 968.58 | 2022-04-26 | 2022-05-09 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 1249.87 | 2022-08-26 | 2022-08-29 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S362800 | Transport Assembled INTT Sections to AH - Labor | 24 | 2905.73 | 2022-08-26 | 2022-08-29 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 968.58 | 2022-08-26 | 2022-08-29 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S362900 | Transport Assembled INTT Sections to AH - M&S | 500 | 591.95 | 2022-08-26 | 2022-08-29 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S363000 | Install INTT Support - Labor | 8 | 1249.87 | 2022-08-30 | 2022-08-31 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S363000 | Install INTT Support - Labor | 8 | 968.58 | 2022-08-30 | 2022-08-31 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S363000 | Install INTT Support - Labor | 60 | 7264.33 | 2022-08-30 | 2022-08-31 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S363100 | Install INTT Support - M&S | 500 | 591.95 | 2022-08-30 | 2022-08-31 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S363200 | Install INTT (mechanical) - Labor | 8 | 1249.87 | 2022-09-01 | 2022-09-06 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S363200 | Install INTT (mechanical) - Labor | 8 | 968.58 | 2022-09-01 | 2022-09-06 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S363200 | Install INTT (mechanical) - Labor | 60 | 7264.33 | 2022-09-01 | 2022-09-06 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S363300 | Install INTT (mechanical) - M&S | 500 | 591.95 | 2022-09-01 | 2022-09-02 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421.44 | 2022-09-07 | 2022-09-13 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615.05 | 2022-09-07 | 2022-09-13 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10615.05 | 10615.05 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10615.05
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264.33 | 2022-09-07 | 2022-09-13 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7264.33 | 7264.33 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7264.33
S363500 | Align/Survey INTT to SC Magnet Centerline - M&S | 500 | 591.95 | 2022-09-07 | 2022-09-13 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S363600 | Install INTT Cables and Services - Labor | 120 | 14703.01 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 14703.01 | 14703.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14703.01
S363600 | Install INTT Cables and Services - Labor | 120 | 14703.01 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 14703.01 | 14703.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14703.01
S363600 | Install INTT Cables and Services - Labor | 24 | 3794.6 | 2022-09-14 | 2022-09-20 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3794.6 | 3794.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3794.6
S363600 | Install INTT Cables and Services - Labor | 24 | 3794.6 | 2022-09-14 | 2022-09-20 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3794.6 | 3794.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3794.6
S363600 | Install INTT Cables and Services - Labor | 24 | 2940.6 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2940.6 | 2940.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2940.6
S363600 | Install INTT Cables and Services - Labor | 240 | 32227.3 | 2022-09-14 | 2022-09-20 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 32227.3 | 32227.3 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 32227.3
S363700 | Install INTT Cables and Services - M&S | 500 | 596.68 | 2022-09-14 | 2022-09-20 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 596.68 | 596.68 | 0 |  |  | 1 |  |  |  | 0 | 0 | 596.68 | 0 | 0 | 0
S363800 | INTT - Operational Readiness Review (ORR) | 8 | 1287.36 | 2022-09-21 | 2022-09-27 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S363800 | INTT - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-09-21 | 2022-09-27 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S363800 | INTT - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-09-21 | 2022-09-27 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S363800 | INTT - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-09-21 | 2022-09-27 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S363900 | Address Action Items from INTT ORR | 8 | 1287.36 | 2022-09-28 | 2022-10-04 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S363900 | Address Action Items from INTT ORR | 8 | 997.63 | 2022-09-28 | 2022-10-04 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S363900 | Address Action Items from INTT ORR | 8 | 997.63 | 2022-09-28 | 2022-10-04 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S363900 | Address Action Items from INTT ORR | 8 | 997.63 | 2022-09-28 | 2022-10-04 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S364000 | Commission INTT - Labor | 40 | 6436.82 | 2022-10-05 | 2022-10-19 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 6436.82 | 6436.82 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6436.82
S364000 | Commission INTT - Labor | 400 | 75225.81 | 2022-10-05 | 2022-10-19 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 75225.81 | 75225.81 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 75225.81
S364000 | Commission INTT - Labor | 40 | 4988.17 | 2022-10-05 | 2022-10-19 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S364000 | Commission INTT - Labor | 40 | 4988.17 | 2022-10-05 | 2022-10-19 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S364000 | Commission INTT - Labor | 40 | 6436.82 | 2022-10-05 | 2022-10-19 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 6436.82 | 6436.82 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6436.82
S364000 | Commission INTT - Labor | 40 | 4988.17 | 2022-10-05 | 2022-10-19 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S364200 | Commission INTT - M&S | 500 | 603.79 | 2022-10-05 | 2022-10-19 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
POM02.02.05.10 MVTX Installation |  | 33976 |  | 01-Oct-19 A | 2022-11-14
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | 30 | 4550.49 | 01-Oct-19 A | 2021-12-29 | 95% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 227.5245 | 227.5245 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 227.5245 | 0 | 0
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | 60 | 7052.75 | 01-Oct-19 A | 2021-12-29 | 95% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 352.6375 | 352.6375 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 352.6375 | 0 | 0
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 60 | 9374.01 | 2021-12-30 | 2022-03-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 9374.01 | 9374.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9374.01
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 20 | 2421.44 | 2021-12-30 | 2022-03-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 20 | 2421.44 | 2021-12-30 | 2022-03-28 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2421.44 | 2421.44 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2421.44
S364500 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - M&S | 30000 | 35516.94 | 2021-12-30 | 2022-03-28 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 35516.94 | 35516.94 | 0 |  |  | 1 |  |  |  | 0 | 0 | 35516.94 | 0 | 0 | 0
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 29-Apr-21 A | 2022-03-30 | 50% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3033.66 | 3033.66 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 3033.66 | 0 | 0
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 10 | 1175.46 | 29-Apr-21 A | 2022-03-30 | 50% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 587.73 | 587.73 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 587.73 | 0 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-03-31 | 2022-04-13 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-03-31 | 2022-04-13 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-03-31 | 2022-04-13 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-04-14 | 2022-04-27 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-04-14 | 2022-04-27 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-04-14 | 2022-04-27 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 1249.87 | 2022-05-06 | 2022-05-12 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S365300 | Transport Assembled MVTX Sections to IR - Labor | 24 | 2905.73 | 2022-05-06 | 2022-05-12 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 968.58 | 2022-05-06 | 2022-05-12 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S365400 | Transport Assembled MVTX Sections to IR - M&S | 500 | 591.95 | 2022-05-06 | 2022-05-12 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 591.95 | 591.95 | 0 |  |  | 1 |  |  |  | 0 | 0 | 591.95 | 0 | 0 | 0
S365500 | Install MVTX Support - Labor | 8 | 1287.36 | 2022-09-22 | 2022-09-26 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S365500 | Install MVTX Support - Labor | 8 | 997.63 | 2022-09-22 | 2022-09-26 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S365500 | Install MVTX Support - Labor | 60 | 7482.26 | 2022-09-22 | 2022-09-26 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 7482.26 | 7482.26 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7482.26
S365600 | Install MVTX Support - M&S | 500 | 603.79 | 2022-09-22 | 2022-09-26 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S365700 | Install FELIX | 16 | 2211.85 | 2022-09-27 | 2022-09-28 | 0% | PROF3 IO E | Labor Hr/M&S Direct$ |  |  | 2211.85 | 2211.85 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2211.85
S365900 | Install Optical fibers | 40 | 4988.17 | 2022-09-27 | 2022-09-28 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S366000 | Install RU | 40 | 5529.62 | 2022-09-27 | 2022-09-28 | 0% | PROF3 IO E | Labor Hr/M&S Direct$ |  |  | 5529.62 | 5529.62 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5529.62
S366200 | Install Samtec Cables | 40 | 4988.17 | 2022-09-27 | 2022-09-28 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S366300 | Install Half-Barrel 1 | 80 | 11059.23 | 2022-09-29 | 2022-10-06 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 11059.23 | 11059.23 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11059.23
S366300 | Install Half-Barrel 1 | 80 | 9976.35 | 2022-09-29 | 2022-10-06 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9976.35 | 9976.35 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9976.35
S366500 | Install Half-Barrel 2 | 80 | 9976.35 | 2022-10-07 | 2022-10-14 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9976.35 | 9976.35 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9976.35
S366500 | Install Half-Barrel 2 | 80 | 11059.23 | 2022-10-07 | 2022-10-14 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 11059.23 | 11059.23 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11059.23
S366700 | Align/Survey MVTX to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2022-10-17 | 2022-10-18 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 2494.09 | 2494.09 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2494.09
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10933.5 | 2022-10-17 | 2022-10-18 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 10933.5 | 10933.5 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10933.5
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 2022-10-17 | 2022-10-18 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 7482.26 | 7482.26 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7482.26
S366800 | Align/Survey MVTX to SC Magnet Centerline - M&S | 500 | 603.79 | 2022-10-17 | 2022-10-18 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9976.35 | 2022-10-19 | 2022-10-21 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 9976.35 | 9976.35 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9976.35
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3862.09 | 2022-10-19 | 2022-10-21 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3862.09 | 3862.09 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3862.09
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9976.35 | 2022-10-19 | 2022-10-21 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 9976.35 | 9976.35 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9976.35
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 2992.9 | 2022-10-19 | 2022-10-21 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2992.9 | 2992.9 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2992.9
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3862.09 | 2022-10-19 | 2022-10-21 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3862.09 | 3862.09 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3862.09
S366900 | Install MVTX Remaining Cables and Services - Labor | 160 | 21867.01 | 2022-10-19 | 2022-10-21 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 21867.01 | 21867.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 21867.01
S367000 | Install MVTX Remaining Cables and Services - M&S | 500 | 603.79 | 2022-10-19 | 2022-10-21 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | 8 | 1287.36 | 2022-10-24 | 2022-10-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S367100 | MVTX - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-10-24 | 2022-10-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S367100 | MVTX - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-10-24 | 2022-10-28 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S367100 | MVTX - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-10-24 | 2022-10-28 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S367300 | Address Action Items from MVTX ORR | 8 | 1287.36 | 2022-10-31 | 2022-11-04 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S367300 | Address Action Items from MVTX ORR | 8 | 997.63 | 2022-10-31 | 2022-11-04 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S367300 | Address Action Items from MVTX ORR | 8 | 997.63 | 2022-10-31 | 2022-11-04 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S367300 | Address Action Items from MVTX ORR | 8 | 997.63 | 2022-10-31 | 2022-11-04 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S367600 | Commission MVTX - M&S | 500 | 603.79 | 2022-11-07 | 2022-11-14 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
POM02.02.05.11 Min Bias Installation |  | 14576 |  | 13-May-20 A | 2022-11-09
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | 16 | 2426.93 | 13-May-20 A | 2021-12-29 | 75% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 606.7325 | 606.7325 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 606.7325 | 0 | 0
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | 30 | 3526.37 | 13-May-20 A | 2021-12-29 | 75% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 881.5925 | 881.5925 | 0 |  |  |  | 1 |  |  | 0 | 0 | 0 | 881.5925 | 0 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 30 | 4687 | 2021-12-30 | 2022-03-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 4687 | 4687 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4687
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1210.72 | 2021-12-30 | 2022-03-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1210.72 | 1210.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1210.72
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1210.72 | 2021-12-30 | 2022-03-28 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1210.72 | 1210.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1210.72
S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - M&S | 10000 | 11838.98 | 2021-12-30 | 2022-03-28 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 11838.98 | 11838.98 | 0 |  |  | 1 |  |  |  | 0 | 0 | 11838.98 | 0 | 0 | 0
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 29-Apr-21 A | 2022-04-13 | 50% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3033.66 | 3033.66 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3033.66
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 20 | 2350.92 | 29-Apr-21 A | 2022-04-13 | 50% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1175.46 | 1175.46 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1175.46
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-04-14 | 2022-04-27 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-04-14 | 2022-04-27 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-04-14 | 2022-04-27 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-04-28 | 2022-05-11 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-04-28 | 2022-05-11 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-04-28 | 2022-05-11 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 1287.36 | 2022-09-22 | 2022-09-22 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 997.63 | 2022-09-22 | 2022-09-22 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S368600 | Transport Assembled Min Bias Sections to AH - M&S | 500 | 603.79 | 2022-09-22 | 2022-09-22 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S368700 | Install Min Bias Support - Labor | 8 | 1287.36 | 2022-09-23 | 2022-09-27 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S368700 | Install Min Bias Support - Labor | 8 | 997.63 | 2022-09-23 | 2022-09-27 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S368700 | Install Min Bias Support - Labor | 16 | 1995.27 | 2022-09-23 | 2022-09-27 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S368800 | Install Min Bias Support - M&S | 500 | 603.79 | 2022-09-23 | 2022-09-27 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S368900 | Install Min Bias (mechanical) - Labor | 8 | 1287.36 | 2022-09-28 | 2022-10-04 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S368900 | Install Min Bias (mechanical) - Labor | 8 | 997.63 | 2022-09-28 | 2022-10-04 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S368900 | Install Min Bias (mechanical) - Labor | 16 | 1995.27 | 2022-09-28 | 2022-10-04 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S369000 | Install Min Bias (mechanical) - M&S | 500 | 603.79 | 2022-09-28 | 2022-10-04 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 8 | 997.63 | 2022-10-05 | 2022-10-12 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 20 | 2733.38 | 2022-10-05 | 2022-10-12 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 2733.38 | 2733.38 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2733.38
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 24 | 2992.9 | 2022-10-05 | 2022-10-12 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 2992.9 | 2992.9 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2992.9
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 24 | 3424.91 | 2022-10-05 | 2022-10-12 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 3424.91 | 3424.91 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3424.91
S369200 | Align/Survey Min Bias to SC Magnet Centerline - M&S | 500 | 603.79 | 2022-10-05 | 2022-10-12 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S369300 | Install Min Bias Cables and Services - Labor | 120 | 14964.52 | 2022-10-13 | 2022-10-19 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 14964.52 | 14964.52 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14964.52
S369300 | Install Min Bias Cables and Services - Labor | 24 | 3862.09 | 2022-10-13 | 2022-10-19 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3862.09 | 3862.09 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3862.09
S369300 | Install Min Bias Cables and Services - Labor | 120 | 14964.52 | 2022-10-13 | 2022-10-19 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 14964.52 | 14964.52 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 14964.52
S369300 | Install Min Bias Cables and Services - Labor | 24 | 2992.9 | 2022-10-13 | 2022-10-19 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 2992.9 | 2992.9 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2992.9
S369300 | Install Min Bias Cables and Services - Labor | 24 | 3862.09 | 2022-10-13 | 2022-10-19 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 3862.09 | 3862.09 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3862.09
S369300 | Install Min Bias Cables and Services - Labor | 240 | 32800.51 | 2022-10-13 | 2022-10-19 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 32800.51 | 32800.51 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 32800.51
S369400 | Install Min Bias Cables and Services - M&S | 500 | 603.79 | 2022-10-13 | 2022-10-19 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | 8 | 1287.36 | 2022-10-20 | 2022-10-26 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S369500 | Min Bias - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-10-20 | 2022-10-26 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S369500 | Min Bias - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-10-20 | 2022-10-26 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S369500 | Min Bias - Operational Readiness Review (ORR) | 8 | 997.63 | 2022-10-20 | 2022-10-26 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S369600 | Address Action Items from Min Bias ORR | 8 | 1287.36 | 2022-10-27 | 2022-11-02 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1287.36 | 1287.36 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1287.36
S369600 | Address Action Items from Min Bias ORR | 8 | 997.63 | 2022-10-27 | 2022-11-02 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S369600 | Address Action Items from Min Bias ORR | 8 | 997.63 | 2022-10-27 | 2022-11-02 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S369600 | Address Action Items from Min Bias ORR | 8 | 997.63 | 2022-10-27 | 2022-11-02 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 997.63 | 997.63 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 997.63
S369700 | Commission Min Bias - Labor | 400 | 75225.81 | 2022-11-03 | 2022-11-09 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 75225.81 | 75225.81 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 75225.81
S369700 | Commission Min Bias - Labor | 40 | 4988.17 | 2022-11-03 | 2022-11-09 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S369700 | Commission Min Bias - Labor | 40 | 6436.82 | 2022-11-03 | 2022-11-09 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 6436.82 | 6436.82 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6436.82
S369700 | Commission Min Bias - Labor | 40 | 4988.17 | 2022-11-03 | 2022-11-09 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S369700 | Commission Min Bias - Labor | 40 | 6436.82 | 2022-11-03 | 2022-11-09 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 6436.82 | 6436.82 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6436.82
S369700 | Commission Min Bias - Labor | 40 | 4988.17 | 2022-11-03 | 2022-11-09 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 4988.17 | 4988.17 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4988.17
S369900 | Commission Min Bias - M&S | 500 | 603.79 | 2022-11-03 | 2022-11-09 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 603.79 | 603.79 | 0 |  |  | 1 |  |  |  | 0 | 0 | 603.79 | 0 | 0 | 0
POM02.02.05.12 Full System Integration and ORR |  | 3608 |  | 2022-04-05 | 2022-11-21
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 8 | 1249.87 | 2022-04-05 | 2022-04-25 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 24 | 2905.73 | 2022-04-05 | 2022-04-25 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 96 | 11622.93 | 2022-04-05 | 2022-04-25 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 11622.93 | 11622.93 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 11622.93
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 8 | 968.58 | 2022-04-05 | 2022-04-25 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 968.58 | 968.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 968.58
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 40 | 4842.89 | 2022-04-05 | 2022-04-25 | 0% | TECH3 AM | Labor Hr/M&S Direct$ |  |  | 4842.89 | 4842.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4842.89
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 8 | 850.58 | 2022-04-05 | 2022-04-25 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 850.58 | 850.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 850.58
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 8 | 1249.87 | 2022-04-05 | 2022-04-25 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 40 | 5541.92 | 2022-04-05 | 2022-04-25 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 5541.92 | 5541.92 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5541.92
S370100 | Move Full sPHENIX to IR - M&S | 1000 | 1183.9 | 2022-04-05 | 2022-04-25 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 1183.9 | 1183.9 | 0 |  |  | 1 |  |  |  | 0 | 0 | 1183.9 | 0 | 0 | 0
S370200 | Align Full sPHENIX to Nominal Beamline and IP - Labor - Physics Resource(s) | 16 | 1937.15 | 2022-07-18 | 2022-07-22 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 40 | 5307.53 | 2022-07-18 | 2022-07-22 | 0% | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 5307.53 | 5307.53 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5307.53
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 48 | 5811.46 | 2022-07-18 | 2022-07-22 | 0% | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 5811.46 | 5811.46 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5811.46
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 8 | 850.58 | 2022-07-18 | 2022-07-22 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 850.58 | 850.58 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 850.58
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 8 | 1249.87 | 2022-07-18 | 2022-07-22 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 48 | 6650.3 | 2022-07-18 | 2022-07-22 | 0% | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 6650.3 | 6650.3 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6650.3
S370300 | Align Full sPHENIX to Nominal Beamline and IP - M&S | 1000 | 1183.9 | 2022-07-18 | 2022-07-22 | 0% | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 1183.9 | 1183.9 | 0 |  |  | 1 |  |  |  | 0 | 0 | 1183.9 | 0 | 0 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249.34 | 2022-05-09 | 2022-06-06 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249.34 | 2022-05-09 | 2022-06-06 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 7303.48 | 2022-05-09 | 2022-06-06 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 7303.48 | 7303.48 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7303.48
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 8737.89 | 2022-05-09 | 2022-06-06 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 8737.89 | 8737.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8737.89
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1249.87 | 2022-06-07 | 2022-06-09 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1249.87 | 2022-06-07 | 2022-06-09 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S370510 | Review of Safety System Design by CAD ESRC | 24 | 5242.73 | 2022-06-07 | 2022-06-09 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 5242.73 | 5242.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5242.73
S370510 | Review of Safety System Design by CAD ESRC | 24 | 4382.09 | 2022-06-07 | 2022-06-09 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 4382.09 | 4382.09 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4382.09
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249.34 | 2022-06-10 | 2022-07-08 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249.34 | 2022-06-10 | 2022-07-08 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 6249.34 | 6249.34 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6249.34
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 7303.48 | 2022-06-10 | 2022-07-08 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 7303.48 | 7303.48 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 7303.48
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 8737.89 | 2022-06-10 | 2022-07-08 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 8737.89 | 8737.89 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8737.89
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3608.4 | 2022-06-10 | 2022-07-08 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 3608.4 | 3608.4 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3608.4
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 4094.92 | 2022-06-10 | 2022-07-08 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 4094.92 | 4094.92 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4094.92
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 2126.45 | 2022-06-10 | 2022-07-08 | 0% | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 2126.45 | 2126.45 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2126.45
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3124.67 | 2022-06-10 | 2022-07-08 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 3124.67 | 3124.67 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3124.67
S370530 | Review and approve procedures | 16 | 2499.74 | 2022-07-11 | 2022-07-12 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S370530 | Review and approve procedures | 16 | 2499.74 | 2022-07-11 | 2022-07-12 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S370530 | Review and approve procedures | 16 | 2921.39 | 2022-07-11 | 2022-07-12 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 2921.39 | 2921.39 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2921.39
S370530 | Review and approve procedures | 16 | 3495.16 | 2022-07-11 | 2022-07-12 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 3495.16 | 3495.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3495.16
S370530 | Review and approve procedures | 16 | 2886.72 | 2022-07-11 | 2022-07-12 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 2886.72 | 2886.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2886.72
S370530 | Review and approve procedures | 16 | 3275.94 | 2022-07-11 | 2022-07-12 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 3275.94 | 3275.94 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3275.94
S370540 | Magnet Checkout After Power Testing | 16 | 2921.39 | 2022-07-13 | 2022-07-19 | 0% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 2921.39 | 2921.39 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2921.39
S370540 | Magnet Checkout After Power Testing | 16 | 3275.94 | 2022-07-13 | 2022-07-19 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 3275.94 | 3275.94 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3275.94
S370540 | Magnet Checkout After Power Testing | 16 | 2886.72 | 2022-07-13 | 2022-07-19 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 2886.72 | 2886.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2886.72
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 2905.73 | 2022-07-20 | 2022-07-26 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 2905.73 | 2905.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2905.73
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 3749.6 | 2022-07-20 | 2022-07-26 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 3749.6 | 3749.6 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3749.6
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 5242.73 | 2022-07-20 | 2022-07-26 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 5242.73 | 5242.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 5242.73
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2921.39 | 2022-07-27 | 2022-08-09 | 0% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 2921.39 | 2921.39 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2921.39
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2886.72 | 2022-07-27 | 2022-08-09 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 2886.72 | 2886.72 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2886.72
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 3275.94 | 2022-07-27 | 2022-08-09 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 3275.94 | 3275.94 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3275.94
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2499.74 | 2022-08-10 | 2022-08-16 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937.15 | 2022-08-10 | 2022-08-16 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937.15 | 2022-08-10 | 2022-08-16 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2499.74 | 2022-08-10 | 2022-08-16 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 3495.16 | 2022-08-10 | 2022-08-16 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 3495.16 | 3495.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3495.16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2499.74 | 2022-08-17 | 2022-08-23 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937.15 | 2022-08-17 | 2022-08-23 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937.15 | 2022-08-17 | 2022-08-23 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1937.15 | 1937.15 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1937.15
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2499.74 | 2022-08-17 | 2022-08-23 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 2499.74 | 2499.74 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2499.74
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 3495.16 | 2022-08-17 | 2022-08-23 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 3495.16 | 3495.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3495.16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2921.39 | 2022-08-17 | 2022-08-23 | 0% | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 2921.39 | 2921.39 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2921.39
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1460.7 | 2022-08-17 | 2022-08-23 | 0% | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 1460.7 | 1460.7 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1460.7
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1249.87 | 2022-08-17 | 2022-08-23 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1249.87 | 2022-08-17 | 2022-08-23 | 0% | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 1249.87 | 1249.87 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1249.87
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1637.97 | 2022-08-17 | 2022-08-23 | 0% | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 1637.97 | 1637.97 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1637.97
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 16 | 3495.16 | 2022-08-24 | 2022-08-30 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 3495.16 | 3495.16 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3495.16
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 2574.73 | 2022-10-24 | 2022-10-28 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2574.73 | 2574.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2574.73
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 1995.27 | 2022-10-24 | 2022-10-28 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 1995.27 | 2022-10-24 | 2022-10-28 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 1995.27 | 2022-10-24 | 2022-10-28 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 2574.73 | 2022-10-24 | 2022-10-28 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 2574.73 | 2574.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2574.73
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 2211.85 | 2022-10-24 | 2022-10-28 | 0% | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 2211.85 | 2211.85 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2211.85
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 2973.32 | 2022-10-24 | 2022-10-28 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 2973.32 | 2973.32 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2973.32
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 3600.01 | 2022-10-24 | 2022-10-28 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 3600.01 | 3600.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3600.01
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 2574.73 | 2022-10-31 | 2022-11-21 | 0% | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 2574.73 | 2574.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2574.73
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 1995.27 | 2022-10-31 | 2022-11-21 | 0% | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 1995.27 | 2022-10-31 | 2022-11-21 | 0% | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 1995.27 | 2022-10-31 | 2022-11-21 | 0% | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 1995.27 | 1995.27 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1995.27
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 2574.73 | 2022-10-31 | 2022-11-21 | 0% | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 2574.73 | 2574.73 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2574.73
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 2211.85 | 2022-10-31 | 2022-11-21 | 0% | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 2211.85 | 2211.85 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2211.85
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 3600.01 | 2022-10-31 | 2022-11-21 | 0% | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 3600.01 | 3600.01 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3600.01
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 2973.32 | 2022-10-31 | 2022-11-21 | 0% | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 2973.32 | 2973.32 | 0 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2973.32
[11 empty] | 9363567.1953 | 9363567.1953 | [7 empty] | 2826235.5609 | 0 | 889200.56 | 472703.1111 | 607954.2968 | 4567473.6665
[20 empty] | SUM M&S |  | 3715436.1209
[20 empty] | SUM LABOR |  | 5648131.0744
[20 empty] | CHECKSUM |  | 9363567.1953

## Open Commitments Cat A
WBS number | WBS Name | Account | PO Number | PO Date | PO? | REQ ? | Description | Requestor | Vendor | Total | Open Commitment on B&E Monthly Summary | On Physics Monthly Summary List from KellyCarroll? (I.e. this sum appears to match) | REMARKS | Sum of Likely "Real" Commitments from Kelly's List + 11.7% Overhead | Corresponding P6 Sum, both placed and trying-to-place | Notes on Commitments vs P6 | Correction for the ETC/EAC Estimate (Commitment - P6) | Amount of likely late Invoicing | Amount of Cost Growth
1.2.1 | TPC Mechanics | 59702 | 392774 | 2020-12-16 |  | 1 | SMD TPC Cart Cantilever | Holland | Streck's Inc | 5000 | 5000 |  | never placed | 2852.818 | 0 |  | 2852.818 | 2852.818
|  | 59702 | 376464 | 2019-12-20 | 1 |  | sPHENIX TPC Fab | O'Brien | SUNY Stony Brook | 30901 | 2554 | 2554
1.2.2, 1.2.3, 1.2.4 | TPC R1, R2, R3 Modules | 59703 | 376464 | 2019-12-20 | 1 |  | sPHENIX TPC Fab | O'Brien | SUNY Stony Brook | 749434 | 61945 | 61945 |  | 69192.565 | 0 |  | 69192.565 | 69192.565
1.2.5 | TPC FEE | 59704 | 388253 | 2020-09-09 |  | 1 | LV Bulk Supplies | Mannel | Vicor Corp | 83687 | 83687 |  | never placed | 239386.504 | 206405.8061 |  | 32980.6979 |  | 32980.6979
|  | 59704 | 390055 | 2020-11-20 | 1 |  | LV Supplies for sPHENIX | Mannel | Vicor Corp | 91690 | 2 | 2
|  | 59704 | 383443 | 2021-04-23 | 1 |  | sPHENIX TPC FEE electronics (boards & stuffing) | O'Brien | PARPRO Technologies Inc | 35973 | 65146 | 32519 | price increase OKed; split part to Account 59728
|  | 59728 | 383443 | 2021-04-23 | 1 |  | sPHENIX TPC FEE electronics (boards & stuffing) | O'Brien | PARPRO Technologies Inc | 32627 | 32627 | 32627 | 53:47 split btw 59704, 58728
|  | 59728 | 399995 | 2021-07-13 | 1 |  | sPHENIX TPC FEE FPGA | Sakaguchi | Avnet In | 88872 | 88872 | 88872
|  | 59728 | 402061 | 2021-07-14 |  | 1 | sPHENIX TPC LV 12AWG cable | Sakaguchi | Allied Wire & Cable | 18300 | 24931 | 24931
|  | 59728 | 402224 | 2021-07-16 |  | 1 | sPHENIX TPC LV 18AWG cable | Sakaguchi | Mouser Electronics Inc | 8286 | 6026 | 6026
|  | 59728 | 403596 | 2021-08-12 |  | 1 | sPHENIX TPC LV cable harness | Sakaguchi | Becker Electronics Inc | 17280 | 17280 | 17280
|  | 59728 | 405332 | 2021-09-20 |  | 1 | sPHENIX TPC LV cable strain | Sakaguchi | MSC Industrial Supply | 5202 | 4001 | 4001
|  | 59728 | 405424 | 2021-09-29 | 1 |  | sPHENIX M-JACK SFP TxRx | Sakaguchi | FS Com | 4900 | 42
|  | 59728 | 405548 | 2021-09-24 |  | 1 | Mighty_J_Resistors | Dellapenna | DigiKey Corp | 4259 | 2618 | 2618
|  | 59728 | 405558 | 2021-09-24 |  | 1 | Mighty_First_IC_Order | Dellapenna | DigiKey Corp | 2881 | 2881 | 2881
|  | 59728 | 405777 | 2021-09-30 |  | 1 | sPHENIX TPC M-Jack Tx/Rx | Sakaguchi | Mouser Electronics Inc | 1461 | 1461 | 1461
|  | 59728 | 405823 | 2021-10-01 |  | 1 | sPHENIX Mjack Parts 3 | Sakaguchi | DigiKey Corp | 1094 | 1094 | 1094
|  | 59728 | 408284 | 12/?/2021 |  | 1 | more FPGAs for might-Jack | Sakaguchi | Avnet Inc | 18000
1.2.6 | TPC DAM | 59729 | 395126 | 2021-03-15 | 1 |  | FELIX Production 56BD_A | DellaPenna | AA Technology Inc | 13598 | 1970 | 1970 |  | 2200.49 | 0 |  | 2200.49 | 2200.49
1.2.7 | TPC Support | 59706 | 390374 | 2020-10-26 | 1 |  | TPC Line Laser Primary | Azmoun | Edmund Optics Inc | 3240 | 360 | 360 |  | 705643.527 | 243534.78 |  | 462108.747 |  | 462108.747
|  | 59706 | 391026 | 2020-11-12 | 1 |  | TPC Laser Sys Compound | Azmoun | Eksma-Optics-Altos Photonics Inc | 2436 | 243 | 243
|  | 59730 | 394400 | 2021-02-05 |  | 1 | Non-Magnetic R&D + PZT | Cacace | (any vendor) | 30775 | 30775 |  | Not placed yet
|  | 59730 | 401625 | 2021-07-21 | 1 |  | Light Diffuser | Azmoun | Luminit LLC | 8000 | 8000 | 8000
|  | 59730 | 405991 | 2021-10-06 |  | 1 | Beam Energy Mon for ONDA | Azmoun | RPMC Lasers Inc | 1240 | 1240 | 1240
|  | 59730 | 397664 | 2021-05-18 | 1 |  | 7 QLI Line Lasers for T | Azmoun | RPMC Lasers Inc | 165900 | 165900 | 165900
|  | 59730 | 404242 | 2021-09-21 | 1 |  | TPC SCADA | Vasquez, Joel | H.H. Benfield Electric dba | 21175 | 21175 | 21175
r |  | 59730 | 405031 | 2021-10-11 | 1 |  | 1+5 BrightSolutions Lasers | Azmoun | RPMC Lasers Inc | 284898 | 284898 | 284898
|  | 59730 | 407180 | 2021-11-02 |  | 1 | TPC Light pipes - Knight | Azmoun | Knight Optical (UK) Ltd | 70475 | 70475 |  | not awarded 11/30/2021
|  | 59730 | 407507 | 2021-11-09 |  | 1 | TPC Laser fiber splitter ArtPh | Azmoun | Art Photonics | 79440 | 79440 |  | not awarded 11/30/2021
1.3.1 | EMCal Blocks | 59708 | 393173 | 2021-01-12 | 1 |  | GE RTV-615 Kit | M Lenz | Newark Corp DBA Newark Element | 205 | 28 | 28 |  | 77005.98 | 30382.0791 |  | 46623.9009 | 46623.9009
|  | 59708 | 362913 | 2019-03-13 |  | 1 | sPHENIX EM Calorimeter | O'Brien | U Illinois UC | 475410 | 9509 | 9509
|  | 59708 | 375848 | 2019-12-04 | 1 |  | sPHENIX EMCal Production | O'Brien | U Illinois UC | 1051513 | 59403 | 59403
|  | 59731 | 408487 | 2021-11-30 |  | 1 | sPHENIX Block final work (Caroline R) | O'Brien | U Illinois UC | 55602
1.3.2 | EMCal Sectors | 59709 | 359249 | 2019-02-04 | 1 |  | Acrylic Light Guides | Stoll | Matrix 1, LLC, d/b/a microPEP | 215244 | 5919 | 5919 |  | 101765.402 | 5534.5907 |  | 96230.8113 | 61791.8113 | 34439
|  | 59709 | 390162 | 2020-10-30 | 1 |  | EMCal SiPM Copper cooling | Stoll | Nicholas Duda, LLC | 61600 | 1400 | 1400
|  | 59709 | 394393 | 2021-01-29 |  | 1 | Therm Conductive Epoxy | Pisani | Mouser Electronics Inc | 254 | 254 |  | still only a Req
|  | 59709 | 383091 | 2020-05-22 |  | 1 | EMCal Sector Assembly (sawteeth) | O'Brien | SUNY Stony Brook | 271469 | 27588 | 27588 | Spent money but appears as REQ
|  | 59732 | 383091 | 2020-06-23 | 1 |  | EMCal Sector Assembly (cooling loops) | O'Brien | SUNY Stony Brook | 90620 | 21760 | 21760
|  | 59732 | 383462 | 2020-06-22 | 1 |  | Job Shopper Nicholas Se… | Wahl, W | United Global Technologies | 16019 | 16019 | 16019
|  | 59732 | 398317 | 2021-05-10 | 1 |  | Job Shopper Gregory Lan | Sharma, Rahul | United Global Technologies | 10920 | 10920 | 10920
|  | 59732 | 406841 | 2021-11-24 | 1 |  | Assembly of Light Guide | Lenz, Michael | Nicholas Duda LLC | 7500 | 7500 | 7500
1.4.1 | InnerHCal | 59710 | 389547 | 2020-10-02 |  | 1 | Detector component for (IHCal sectors) | O'Brien | Iowa State U | 950000 | 266345 | 266345 | Spent money but appears as REQ | 323991.435 | 0 | 4th invoice | 323991.435 | 323991.435
|  | 59710 | 392879 | 2020-12-18 |  | 1 | sPHENIX IHCal sector as | O'Brien | Rutgers U | 53431 | 23710 | 23710 |  |  |  | late
|  | 59733 | 402364 | 2021-07-21 |  | 1 | Hydraulic Equipment | Pontieri | Airoyal Company | 1374 | 1374
1.4.3 | OuterHCal Scint | 59712 | 361122 | 2019-03-08 | 1 |  | Scintillating Tiles | O'Brien | Geogia State U | 1488294 | 9752 | 9752 | de-commit? | 10892.984 | 0 |  | 0
1.4.4 | OuterHCal Sector | 59713 | 381347 | 2020-03-26 | 1 |  | sPHENIX Calorimeter com | O'Brien | Iowa State U | 105517 | 13380 | 13380 | de-commit? | 14945.46 | 0 |  | 0
1.5.2 | Calorimeter FEE | 59715 | 373822 | 2019-10-17 | 1 |  | EMCal Interface Assy Sc | Boose | East End Assemblies | 52228 | 1651 | 1651 | de-commit? | 1271100.203 | 898898.7025 |  | 372201.5005 |  | 372201.5005
|  | 59715 | 381490 | 2020-04-12 | 1 |  | EMCal Interior Signal Cables | Mannel | East End Assemblies | 149338 | 1425 |  | not on Kelly's summary???
|  | 59715 | 381567 | 2020-03-31 |  | 1 | Connectors | Mannel | East End Assemblies | 475 | 475 |  | Never placed
|  | 59715 | 388253 | 2020-09-09 |  | 1 | LV Bulk Supplies | Mannel | Vicor Corporation | 10035 | 10035 |  | Never placed
|  | 59715 | 377727 | 2020-02-14 | 1 |  | EMCal SiPM board Assembly | Mannel | CEM Ltd | 46865 | 29484 |  | Should be gone?
|  | 59738 | 401658 | 2021-07-21 | 1 |  | Power Cables for HCal | Mannel | Becker Electronics Inc | 2176 | 2176 | 2176 | de-commit?
|  | 59738 | 401868 | 2021-07-21 |  | 1 | Power Cables for EMCal | Mannel | Becker Electronics Inc | 23046 | 23046 | 23046
|  | 59738 | 397235 | 2021-04-01 |  | 1 | Calorimeter Signal Cables | Boose | Meritec | 1085342 | 1094121 | 1094121 | WHERE IN NOVEMBER LISTS ??
|  | 59738 | 407605 | 2021-11-12 |  | 1 | EMCal/Hcal SC/TP cables | Mannel | Becker Electronics Inc | 16965 | 16965
1.5.3 | Cal Digitizers | 59716 | 388253 | 2020-09-09 |  | 1 | LV Bulk Supplies | Mannel | Vicor Corporation | 63337 | 63337 |  | Never placed | 302287.008 | 260020.0605 |  | 42266.9475 |  | 42266.9475
|  | 59716 | 382403 | 2020-04-29 |  | 1 | sPHENIX Digitzer System | Mannel | Nevis Columbia | 763438 | 270617 | 270617 | Spent money but appears as REQ
|  | 59739 | 407605 | 2021-11-12 |  | 1 | EMCal/Hcal SC/TP cables | Mannel | Becker Electronics Inc | 107 | 107
|  | 59739 | 390055 | 2020-11-20 | 1 |  | LV Supplies for sPHENIX | Mannel | Vicor Corporation | 70303 | 7 | 7 | de-commit?
1.6.1 | DAQ | 59718 | 380992 | 2020-03-19 |  | 1 | Arista Network Switch | Purschke | ThunderCat Technology LLC | 50500 | 50500 |  | returned; REMOVE | 156380 | 219658.06 |  | -63278.06 |  | -63278.06
|  | 59740 | 396499 | 2021-08-19 | 1 |  | DCM-II crates etc | O'Brien | Nevis Columbia | 140000 | 140000 | 140000
1.6.2 | LL-1 | 59741 | 396499 | 2021-08-19 | 1 |  | sPHENIX Electronics (LL1 production) | O'Brien | Nevis Columbia | 230923 | 188306 |  | Placed in late August | 210337.802 | 209549.94 |  | 787.862 |  | 787.862
1.6.4 | Timing | 59742 | [11 empty] | 0 | 0 |  | 0
1.7 | MBD | 59722 | 388253 | 2020-09-09 |  | 1 | LV Bulk Supplies | Mannel | Vicor Corporation | 3570 | 3570 |  | Never placed | 78526.217 | 61951.008 |  | 16575.209 |  | 16575.209
|  | 59722 | 382403 | 2020-05-27 | 1 |  | sPHENIX Digitizer System | Mannel | Nevis Columbia | 16129 | 6764 | 6764
|  | 59743 | 405337 | 2021-09-20 | 1 |  | Meritec HM 2mm Cables | CHIU | Meritec | 7290 | 7290
|  | 59743 | 396499 | 2021-08-19 | 1 |  | sPHENIX Electronics (MBD Production) | O'Brien | Nevis Columbia | 68977 | 56247 |  | Placed in late August
[18 empty] | 506653.0202 | 898081.9039
[16 empty] | TOTAL CORRECTION MIE | 1404734.9241

## Open Commitments Cat C
WBS number | WBS Name | Account | PO Number | PO Date | PO? | REQ ? | Description | Requestor | Vendor | Total | Open Commitment | On Physics Monthly Summary List from KellyCarroll? | REMARKS | Sum of Likely "Real" Commitments from Kelly's List + 11.7% Overhead | Corresponding P6 Sum, both placed and trying-to-place | Notes on Commitments vs P6 | Correction for the ETC/EAC Estimate (Commit - P6) | Amount of likely late Invoicing | Amount of Cost Growth
2.2.3 | Cryogenics | 16718 | 384315 | 2020-11-12 | 1 |  | sPHENIX LN2 System | Orfin | Ability | 247261 | 109704 | 109704 |  | 997113.507 | 819028.896 | late invoice from Abiility? | 178084.611 | 178084.611
|  | 16718 | 397827 | 2021-06-03 | 1 |  | sPHENIX 20kW heaters | Tallerico | Chromalox Inc c/o Faber Associates | 31550 | 31150 | 31150 |  |  |  | heaters claimed; late invoice?
|  | 16718 | 404025 | 2021-08-20 |  | 1 | brady labels for 1008 u | Tallerico | K C Electronic Distributors Inc | 2852 | 300 | 300
|  | 16718 | 362765 | 2019-05-28 | 1 |  | Cryogenics system sPHENIX (Helium) | Than, Yatming | Bennu Group Inc DBA (Ability Engineering) | 1565660 | 751517 | 751517
2.2.4 | Power Supply/QD | 16719 | 400512 | 2021-06-23 | 1 |  | standard 14 days (??) | Schultheiss | Holman's USA LLC | 2037 | 2037 | 2037 |  | 2275.329 | 0 |  | 2275.329 | 2275.329
2.3.3 | Barrel Steel | 16722 | 364436 | 2019-10-01 | 1 |  | Wire Pendant EEA | Streckenbach | Mass Crane & Hoist Services Inc | 11878 | 14254 | 14254 |  | 15921.718 | 0 |  | 15921.718 |  | 15921.718
2.4.1 | Infrastructure - Detector | 16723 | 389021 | 2020-10-06 | 1 |  | Job Shopper-Joseph Curr | Feder, Russell | ION Computer Systems Inc | 151555 | 42124 | 42124 |  | 139993.61 | 75295.918 | Labor is in addition to P6 | 64697.692 |  | 64697.692
|  | 16723 | 389300 | 2020-10-06 | 1 |  | Job Shopper-Jermaine Jo | Feder, Russell | United Global Technologies | 144403 | 40611 | 40611
|  | 16723 | 398619 | 2021-05-07 | 1 |  | Electrical Connection B | Vasquez | H.H.Benfield Electric dba | 5000 | 5000 | 5000
|  | 16723 | 403753 | 2021-10-14 | 1 |  | Carriage Cable Tray Sys | Vasquez | Kelly&Hayes Electrical Supply Inc | 9261 | 3202 | 3202
|  | 16723 | 404029 | 2021-09-10 | 1 |  | oHCal Channel System | Vasquez | Kelly&Hayes Electrical Supply Inc | 2979 | 2979 | 2979
|  | 16723 | 405770 | 2021-10-04 | 1 |  | Rack Interlock Puch Button | Vasquez | Grainger | 4739 | 4739 | 4739
|  | 16723 | 405846 | 2021-10-12 | 1 |  | UPS Batteries | Vasquez | K C Electronics Distributors | 1766 | 1766 | 1766
|  | 16723 | 406331 | 2021-10-14 |  | 1 | E-Stops | Vasquez | Power Resources International | 551 | 50 | 50
|  | 16723 | 407887 | 2021-11-24 | 1 |  | Vesda Net Interface Card | Vasquez | Johnsonn Controls Fire Protection LP | 1106 | 1106 | 1106
|  | 16723 | 408174 | 2021-11-30 | 1 |  | Light Fixture | Vasquez | Turtle & Hughes Inc | 725 | 725 | 725
|  | 16723 | 108182 | 2021-12-01 | 1 |  | Rack Room Interlock System | Vasquez | H.H.Benfield Electric dba | 528 | 528 | 528
|  | 16723 | 398624 | 2021-05-07 | 1 |  | Power Distribution Panel | Vasquez | H.H.Benfield Electric dba | 22500 | 22500 | 22500
2.4.2 | Infrastructure - Facilities | 16724 | 396236 | 2021-03-18 | 1 |  | Welding inspection for | Mills | Quality Control Laboratories LLC | 8250 | 1500 | 1500 |  | 486841.099 | 166612.609 |  | 320228.49 | 232857 | 87371.49
|  | 16724 | 401169 | 2021-07-13 | 1 |  | sPHENIX Inspection and | Mills | Quality Control Laboratories LLC | 20000 | 6425 | 6425 |  |  |  | outstanding
|  | 16724 | 405632 | 2021-10-29 | 1 |  | Vesda system for 1008 | Chan | Johnson Controls Fire Protection LP | 19819 | 19819 | 19819
|  | 16724 | 383876 | 2020-11-04 | 1 |  | Al-Be beampipe for sPHENIX | Nayak, Sumanta | Materion Brush Inc | 284828 | 143354 | 143354
|  | 16724 | 397246 | 2021-06-09 | 1 |  | EP1128654 C1008311VKVK | Kearney | Ferguson Enterprises | 6112 | 1004 | 1004
|  | 16724 | 405999 | 2021-10-06 |  | 1 | Rack Interlock Water Le | Vasquez | Faber Associates | 24129 | 24129 | 24129
|  | 16724 | 406080 | 2021-10-07 |  | 1 | Global Interlocks System | Vasquez | Turtle & Hughes Inc | 11574 | 6759 | 6759
|  | 16724 | 389925 | 2021-01-29 | 1 |  | (concrete track work) | Mills | G&M Earth Moving Inc | 1137078 | 232857 | 232857
2.5 | Installation | 16727 | 401725 | 2021-08-12 | 1 |  | sPHENIX InnerHCAl slider beam | Feder | Streck's Inc | 160805 | 160805 | 160805 |  | 400435.564 | 302506.664 | Large jump for Ihcal items | 97928.9 | 34812 | 63116.9
|  | 16727 | 401901 | 2021-08-31 | 1 |  | IHCal assy A-Frame stand | Feder | Streck's Inc | 44894 | 44894 | 44894
|  | 16727 | 399894 | 2021-07-01 | 1 |  | Motor, gearbox and Cont for IHCal | Demino, Leo | H.H.Benfield Electric dba | 14625 | 14625 | 14625 |  |  |  | of $34,812 late invoice
|  | 16727 | 380126 | 2020-03-02 | 1 |  | Design & fab, silicon det (MVTX | O'Brien | MIT (LNS) | 30500 | 30500 | 30500 |  |  |  | from Stony Brook
|  | 16727 | 395973 | 2021-06-15 | 1 | 1 | sPHENIX EMCal fixture ($72,218) and IHCal barrel fab sled components, hardware, fabrication and assembly ($47,818 for IHCal) | O'Brien | SUNY Stony Brook | 120036 | 107668 | 107668
|  | 16727 | 407234 | 2021-11-03 |  | 1 | IHCal stanchion - I | Feder | Xometry Inc | 70635 | 70635 |  | Not awarded yet 11/19/2021
|  | 16727 | 406772 | 2021-10-24 |  | 1 | IHCal Stanchion - II Weldment | Feder | Streck's Inc | 155420 | 155420 |  | Not awarded yet 11/19/2021
2.3.1 | Carriage/Cradle | 16729 | 406778 | 2021-11-10 | 1 |  | sPHENIX Track Clamp | Holland, Robert | Streck's Inc | 56202 | 56202 | 56202 |  | 79957.094 | 0 | None in P6 | 79957.094 |  | 79957.094
|  | 16729 | EP1139611 | 2021-10-05 | 1 |  | Matl Est - EP1139611 |  |  | 0 | 500 | 500
|  | 16729 | 388730 | 2021-02-09 | 1 |  | sPHENIX Magnet endcap | Hock, Jon | Streck's Inc | 14880 | 14880 | 14880
2.3.2 | LSR, Inner Rings etc | 16731 | 400958 | 2021-07-13 | 1 |  | sPHENIX Magnet Support | Holland, Robert | Centerline Precision IN | 9919 | 2259 | 2259 |  | 2523.303 | 0 |  | 2523.303 | 2523.303
2.3.4 | Pole Tips | 16732 | 405503 | 2021-10-15 | 1 |  | sPHENIX Endcap tracks | Hock | Stecks's Inc | 24984 | 24984 | 24984 |  | 1022329.782 | 993188.32 | Bracket not in P6 | 29141.462 |  | 29141.462
|  | 16732 | 388730 | 2021-02-09 | 1 |  | sPHENIX Magnet Endcap d | Hock, Jon | Streck's Inc | 890262 | 890262 | 890262
2.3.5 | Bridge, Platforms | 16733 | 405740 | 2021-09-30 |  | 1 | Ladder for sPHENIX Plat | Hock | any vendor | 1321 | 1321 |  | not placed yet | 470054.823 | 469603.1539 | keep the commit for | 451.6691 |  | 451.6691
|  | 16733 | 391837 | 2021-03-03 | 1 |  | sPHENIX Platform parts | Hock, Jon | Streck's Inc | 354679 | 354679 | 354679 |  |  |  | stairs until Dec when P6
|  | 16733 | 397180 | 2021-08-02 | 1 |  | Stairs for sPHENIX platform | Hock, Jon | Panel Built | 66140 | 66140 |  | delivered in November |  |  | will claim them
[18 empty] | 450552.243 | 340658.0251
[16 empty] | TOTAL Correction I&F | 791210.2681

## EAC for Cat A
|  | BCWR from P6 from November 2021 |  | 2435173.8956
Additions
| JACK board for TPC FEE (verbal estimate)(reduce by $40K for AVNET FPGAs that will be in hand and $20K for parts on order) |  | 140000
| Laser Motors/controls ($130K) -$40K in P6 |  | 90000
| Sum of known additions above |  |  | 230000
|  | BCWR + Additions |  | 2665173.8956
Adjustments | Adjust for Risk Events Expected Value (updated from May MIE review total) |  |  | 425000
| Adjust for Estimate Uncertainty (use Glenn's November MIE total) |  |  | 155465
| Adjust for unpaid invoices and known cost growth(comparison of P6 incomplete with B&E commitments and Kelly Carroll's summary) |  |  | 1404734.9241 | This is derived from the Open Commitments Cat A tab
Adjust for other anticipated but not-yet-realized overruns
|  | ETC = BCWR+Additions+Adjustments |  | 4650373.8197
|  | ACWP from November 2021 |  | 21661911
|  | EAC = ETC + ACWP |  | 26312284.8197
|  | TOTAL Budget |  | 27000000
|  | As-Yet unassigned Cat A Contingency |  | 687715.1803
|  | As-Yet unassigned Cat A Contingency w/o Risk or EU |  | 1268180.1803 | i.e. take ETC+ACWP+ (unpaid invoices & known cost growth) only

## EAC for Cat C
|  | BCWR from P6 from November 2021 | 9363567.1953
Additions
| Sum of known additions above |  | 0
|  | BCWR + Additions | 9363567.1953
Adjustments | Adjust for Risk Events Expected Value (use Irina's April I&F Review Average Expected Value total) |  | 107012
| Adjust for Estimate Uncertainty (use Glenn's November total) |  | 397794 | this is for the M&S items in Cat C ONLY
| Adjust for unpaid invoices and known cost growth(comparison of P6 incomplete with B&E commitments and Kelly Carroll's summary) |  | 791210.2681 | This is derived from the Open Commitments Cat C tab | UPDATE
Adjust for other anticipated but not-yet-realized overruns
|  | ETC = BCWR+Additions+Adjustments | 10659583.4634
|  | ACWP from November 2021 | 22804556
|  | EAC = ETC + ACWP | 33464139.4634
|  | TOTAL Budget | 33400000
|  | As-Yet unassigned Cat C Contingency | -64139.4634
|  | As-Yet unassigned Cat C Contingency w/o Risk or EU | 440666.5366 | i.e. take ETC+ACWP+ (unpaid invoices & known cost growth) only

## Remaining Cat C M&S ToBeOrdered
Baseline data |  |  |  | Forecast Data (June status file)
Activity ID | Activity Name | Baseline Units | Baseline Cost | Forecast Start | Forecast Finish | % Complete | Resource ID Name | Calc ETC Units | Updated ETC Units | Potential PCR? | Calc ETC Cost | Updated ETC Cost | EAC Growth | M&S Fraction Under Contract | M&S Fraction To-Be-Contracted | Updated ETC M&S Under Contract | Updated ETC M&S To-Be-Contracted
C Infrastructure / Facility Upgrade
2.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis
S308627 | Place contract with Vendor (Procurement string, $70K obligated at Contract award, paid when mapped?) | 63000 | 73123 | 2021-09-30 | 2022-02-28 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 63000 |  |  | 73123 | 73123 | 0 |  | 1 | 0 | 73123
2.03.01 Cradle Carriage
S314650 | CC Seismic Restraints - Delivery Acceptance - M&S | 126000 | 146246 | 2022-04-15 | 2022-04-21 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 126000 |  |  | 146246 | 146246 | 0 |  | 1 | 0 | 146246
2.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports
S317940 | Procure TPC Supports - M&S | 50000 | 58034 | 2022-02-10 | 2022-04-07 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 58034 | 58034 | 0 |  | 1 | 0 | 58034
S317950 | Procure INTT Supports - M&S | 50000 | 58034 | 2022-02-02 | 2022-03-30 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 58034 | 58034 | 0 |  | 1 | 0 | 58034
S317960 | Procure MVTX Supports - M&S | 50000 | 58034 | 2022-01-24 | 2022-03-21 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 58034 | 58034 | 0 |  | 1 | 0 | 58034
S317970 | Procure MBD Supports - M&S | 10000 | 11607 | 2022-02-11 | 2022-03-11 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 |  |  | 11607 | 11607 | 0 |  | 1 | 0 | 11607
S317990 | Procure Beampipe Supports - M&S | 25000 | 29017 | 2022-01-31 | 2022-02-28 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 25000 |  |  | 29017 | 29017 | 0 |  | 1 | 0 | 29017
2.04.01.02 Detector Support Services Systems (including Cables, Fibers, Cable Trays)
S330355 | Procure Fiber Optics Trunk Cables and Accessories - M&S | 22000 | 26046 | 2022-06-09 | 2022-09-01 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 22000 |  |  | 26046 | 26046 | 0 |  | 1 | 0 | 26046
2.04.01.04 Detector Gas and Cooling Services Systems
S332500 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) M&S | 53000 | 62419 | 2022-02-15 | 2022-06-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 53000 |  |  | 62419 | 62419 | 0 |  | 1 | 0 | 62419
S332770 | Procure & Deliver Detector Gas Services Systems Components - M&S | 54000 | 63930 | 2022-03-29 | 2022-09-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 54000 |  |  | 63930 | 63930 | 0 |  | 1 | 0 | 63930
2.04.01.05 Detector Safety Subsystems
S333600 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) - M&S | 12000 | 14156 | 2022-02-10 | 2022-05-05 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 12000 |  |  | 14156 | 14156 | 0 |  | 1 | 0 | 14156
2.04.01.07 Rack Room Modifications
S335800 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - M&S | 20000 | 23678 | 2022-01-12 | 2022-04-07 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 20000 |  |  | 23678 | 23678 | 0 |  | 1 | 0 | 23678
2.04.01.08 Control Room and Offices Modifications
S336900 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - M&S | 50000 | 59195 | 2022-02-11 | 2022-03-25 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 59195 | 59195 | 0 |  | 1 | 0 | 59195
2.04.02.03 IR HVAC
S339500 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - M&S | 35000 | 40624 | 2021-12-16 | 2022-03-15 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 17500 |  |  | 20312 | 20312 | 0 |  | 1 | 0 | 20312
2.04.02.05 IR/AH Safety Subsystems
S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - M&S | 32000 | 37142 | 2022-02-15 | 2022-05-10 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 32000 |  |  | 37142 | 37142 | 0 |  | 1 | 0 | 37142
2.04.02.06 Assembly Hall and Interaction Region Modifications
S342800 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - M&S | 10000 | 11607 | 2022-02-14 | 2022-06-21 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 |  |  | 11607 | 11607 | 0 |  | 1 | 0 | 11607
2.05.02 Infrastructure Installation
S346400 | Install Beampipe Temp Support - M&S | 500 | 592 | 2022-08-25 | 2022-08-25 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S345600 | Install IR HVAC - M&S | 500 | 580 | 2022-03-30 | 2022-04-12 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 580 | 580 | 0 |  | 1 | 0 | 580
S347800 | Install IR Electronics Cooling Water Off Detector - M&S | 500 | 592 | 2022-01-21 | 2022-02-17 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S345900 | Install On Detector Safety Subsystems - M&S | 500 | 592 | 2022-05-20 | 2022-06-17 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S347000 | Install Detector Support Services Systems - M&S | 500 | 592 | 2022-09-02 | 2022-09-30 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S347500 | Install Gas and Cooling System Services - M&S | 500 | 592 | 2022-07-22 | 2022-09-16 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S346800 | Install Non-IR Infrastructure - M&S | 500 | 592 | 2022-07-21 | 2022-09-08 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S345910 | Install Off Detector Safety Subsystems - M&S | 500 | 580 | 2022-05-25 | 2022-06-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 580 | 580 | 0 |  | 1 | 0 | 580
S346210 | Install Line Electric Power Distribution On Detector - M&S | 500 | 592 | 2021-12-28 | 2022-01-26 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S347810 | Install IR Electronics Cooling Water On Detector - M&S | 500 | 592 | 2022-02-09 | 2022-03-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S347310 | Install Electronics Racks On Carriage - M&S | 500 | 592 | 2022-07-26 | 2022-10-19 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
2.05.03 Cradle Carriage Assembly/Installation
S349400 | Install platforms & access - M&S | 1000 | 1184 | 2022-01-11 | 2022-02-08 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 |  |  | 1184 | 1184 | 0 |  | 1 | 0 | 1184
S349600 | Install Pole Tips - M&S | 3000 | 3552 | 2022-01-11 | 2022-01-25 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 3000 |  |  | 3552 | 3552 | 0 |  | 1 | 0 | 3552
2.05.04 Outer Hcal Installation
S351100 | Transport Remainder of Outer Hcal Sectors to AH - M&S | 500 | 592 | 2021-11-17 | 2021-12-02 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S351300 | Install Remainder of Outer HCal Sectors - M&S | 500 | 592 | 2021-11-24 | 2022-01-10 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S351500 | Align/Survey Outer Hcal to Centerline - M&S | 500 | 592 | 2022-01-11 | 2022-01-18 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S351700 | Install Outer HCal Cables and Services - M&S | 500 | 592 | 2022-01-19 | 2022-02-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S352200 | Commission Outer HCal - M&S | 500 | 592 | 2022-03-17 | 2022-04-13 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
2.05.06 Inner Hcal Installation
S355700 | Install Inner HCAL Assembly on insertion fixture - M&S | 500 | 592 | 2022-02-01 | 2022-02-07 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S356100 | Install Inner HCal - M&S | 500 | 592 | 2022-02-10 | 2022-02-11 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S356500 | Align/Survey Inner HCal to SC Magnet Centerline - M&S | 500 | 592 | 2022-02-14 | 2022-02-18 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S356700 | Install Inner HCal Cables and Services - M&S | 500 | 592 | 2022-03-02 | 2022-03-29 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S357200 | Commission Inner HCal - M&S | 500 | 592 | 2022-04-27 | 2022-05-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
2.05.07 EMCal Installation
S358300 | Transport Assembled EMCal Sectors to AH - M&S | 500 | 592 | 2022-02-22 | 2022-03-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S358500 | Install EMCal Sectors - M&S | 500 | 592 | 2022-02-23 | 2022-03-16 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S358700 | Align/Survey EMCal to SC Magnet Centerline - M&S | 500 | 592 | 2022-03-17 | 2022-04-07 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S358900 | Install EMCal Cables and Services - M&S | 500 | 592 | 2022-04-08 | 2022-04-29 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S359400 | Commission EMCal - M&S | 500 | 592 | 2022-05-23 | 2022-06-27 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
2.05.08 TPC Installation
S359800 | (Planning Package) Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - M&S | 30000 | 34821 | 2021-10-01 | 2022-02-14 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 |  |  | 34821 | 34821 | 0 |  | 1 | 0 | 34821
S360500 | Transport Assembled TPC Sections to AH - M&S | 500 | 592 | 2022-04-22 | 2022-04-28 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S360800 | Install TPC Support - M&S | 500 | 592 | 2022-08-01 | 2022-08-05 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S361000 | Install TPC (Mechanical) - M&S | 500 | 592 | 2022-08-08 | 2022-08-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S361200 | Align/Survey TPC to SC Magnet Centerline - M&S | 500 | 592 | 2022-08-16 | 2022-08-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S361400 | Install TPC Cables and Services - M&S | 500 | 592 | 2022-08-26 | 2022-09-16 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S361900 | Commission TPC - M&S | 500 | 601 | 2022-10-03 | 2022-10-24 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 601 | 601 | 0 |  | 1 | 0 | 601
2.05.09 INTT Installation
S362200 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - M&S | 30000 | 34821 | 2021-10-01 | 2021-12-30 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 |  |  | 34821 | 34821 | 0 |  | 1 | 0 | 34821
S362900 | Transport Assembled INTT Sections to AH - M&S | 500 | 592 | 2022-08-26 | 2022-08-29 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S363100 | Install INTT Support - M&S | 500 | 592 | 2022-08-30 | 2022-08-31 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S363300 | Install INTT (mechanical) - M&S | 500 | 592 | 2022-09-01 | 2022-09-02 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S363500 | Align/Survey INTT to SC Magnet Centerline - M&S | 500 | 592 | 2022-09-07 | 2022-09-13 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S363700 | Install INTT Cables and Services - M&S | 500 | 592 | 2022-09-14 | 2022-09-20 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S364200 | Commission INTT - M&S | 500 | 599 | 2022-10-05 | 2022-10-19 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 599 | 599 | 0 |  | 1 | 0 | 599
2.05.10 MVTX Installation
S364500 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - M&S | 30000 | 35517 | 2021-11-01 | 2022-01-31 | 0% | Purch 1st $2M | 30000 |  |  | 35517 | 35517 | 0 |  | 1 | 0 | 35517
S365400 | Transport Assembled MVTX Sections to IR - M&S | 500 | 592 | 2022-04-13 | 2022-04-19 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S365600 | Install MVTX Support - M&S | 500 | 592 | 2022-09-22 | 2022-09-26 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S366800 | Align/Survey MVTX to SC Magnet Centerline - M&S | 500 | 604 | 2022-10-17 | 2022-10-18 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 604 | 604 | 0 |  | 1 | 0 | 604
S367000 | Install MVTX Remaining Cables and Services - M&S | 500 | 604 | 2022-10-19 | 2022-10-21 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 604 | 604 | 0 |  | 1 | 0 | 604
S367600 | Commission MVTX - M&S | 500 | 604 | 2022-11-07 | 2022-11-14 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 604 | 604 | 0 |  | 1 | 0 | 604
2.05.11 Min Bias Installation
S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - M&S | 10000 | 11607 | 2021-10-01 | 2021-12-30 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 |  |  | 11607 | 11607 | 0 |  | 1 | 0 | 11607
S368600 | Transport Assembled Min Bias Sections to AH - M&S | 500 | 592 | 2022-09-22 | 2022-09-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S368800 | Install Min Bias Support - M&S | 500 | 592 | 2022-09-23 | 2022-09-27 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S369000 | Install Min Bias (mechanical) - M&S | 500 | 592 | 2022-09-28 | 2022-10-04 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0 |  | 1 | 0 | 592
S369200 | Align/Survey Min Bias to SC Magnet Centerline - M&S | 500 | 594 | 2022-10-05 | 2022-10-12 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 594 | 594 | 0 |  | 1 | 0 | 594
S369400 | Install Min Bias Cables and Services - M&S | 500 | 604 | 2022-10-13 | 2022-10-19 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 604 | 604 | 0 |  | 1 | 0 | 604
S369900 | Commission Min Bias - M&S | 500 | 604 | 2022-11-03 | 2022-11-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 604 | 604 | 0 |  | 1 | 0 | 604
2.05.12 Full System Integration and ORR
S370100 | Move Full sPHENIX to IR - M&S | 1000 | 1184 | 2022-04-05 | 2022-04-25 | 0% | Purch 1st $2M | 1000 |  |  | 1184 | 1184 | 0 |  | 1 | 0 | 1184
S370300 | Align Full sPHENIX to Nominal Beamline and IP - M&S | 1000 | 1184 | 2022-06-16 | 2022-06-22 | 0% | Purch 1st $2M | 1000 |  |  | 1184 | 1184 | 0 |  | 1 | 0 | 1184
923456
[11 empty] | 905512 | 905512 |  |  |  | 0 | 905512
[16 empty] | SUM M&S | 905512
[16 empty] | CHECKSUM | 905512
[12 empty] | Amount above for installation incidentals (i.e. pay-as-you-go) |  |  |  |  | 37359
[12 empty] | Amount for orders to be placed with outside vendors |  |  |  |  | 868153
Formulas:
Forecast Start = VLOOKUP([Activity ID],'[1]forecast data dump'!$A1:H3483,4,FALSE)
Forecast Finish = VLOOKUP([Activity ID],'[1]forecast data dump'!$A1:H3483,5,FALSE)

## ETC sheet-Cat T_BT (hidden)
Baseline data |  |  |  | Forecast Data (June status file)
Activity ID | Activity Name | Baseline Units | Baseline Cost | Forecast Start | Forecast Finish | % Complete | Resource ID Name | Calc ETC Units | Updated ETC Units | Potential PCR? | Calc ETC Cost | Updated ETC Cost | EAC Growth
T Non BNL Contributions
1.02.01.02 TPC v2 Field Cage
S110400 | Assemble TPC v2 Outer Field Cage | 480 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 9.6 |  |  | 0 | 0 | 0
S110400 | Assemble TPC v2 Outer Field Cage | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 1.6 |  |  | 0 | 0 | 0
S110400 | Assemble TPC v2 Outer Field Cage | 160 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 3.2 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 8 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 8 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 8 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 136 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 136 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 136 |  |  | 0 | 0 | 0
1.02.01.08 TPC Assembly
S121610 | Install TPC Modules into Field Cage | 576 | 0 | 25-Aug-21* | 2021-10-15 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 576 |  |  | 0 | 0 | 0
S121610 | Install TPC Modules into Field Cage | 4800 | 0 | 25-Aug-21* | 2021-10-15 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 4800 |  |  | 0 | 0 | 0
S121610 | Install TPC Modules into Field Cage | 1920 | 0 | 25-Aug-21* | 2021-10-15 | 0% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 1920 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | 2600 | 0 | 2021-11-01 | 2022-02-02 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 2600 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | 312 | 0 | 2021-11-01 | 2022-02-02 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 312 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | 520 | 0 | 2021-11-01 | 2022-02-02 | 0% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 520 |  |  | 0 | 0 | 0
S121600 | Production Readiness Review for TPC Final Assembly | 8 | 0 | 2021-08-24 | 2021-08-24 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 8 |  |  | 0 | 0 | 0
S121600 | Production Readiness Review for TPC Final Assembly | 8 | 0 | 2021-08-24 | 2021-08-24 | 0% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 8 |  |  | 0 | 0 | 0
1.02.02.03 TPC R1 Module Production
S125505 | Build TPC R1 Modules - Contributed Labor | 288 | 0 | 11-Jan-21 A | 2021-09-03 | 85% | SCI3 Wayne - Unpaid.SCI3 Wayne - Unpaid | 43.2 |  |  | 0 | 0 | 0
S125505 | Build TPC R1 Modules - Contributed Labor | 2400 | 0 | 11-Jan-21 A | 2021-09-03 | 85% | STUDENT Wayne - Unpaid.STUDENT Wayne - Unpaid | 360 |  |  | 0 | 0 | 0
S125605 | Test TPC R1 Modules - Contributed Labor | 288 | 0 | 11-Jan-21 A | 2021-09-20 | 85% | SCI3 Wayne - Unpaid.SCI3 Wayne - Unpaid | 43.2 |  |  | 0 | 0 | 0
S125605 | Test TPC R1 Modules - Contributed Labor | 2400 | 0 | 11-Jan-21 A | 2021-09-20 | 85% | STUDENT Wayne - Unpaid.STUDENT Wayne - Unpaid | 360 |  |  | 0 | 0 | 0
1.02.03.03 TPC R2 Module Production
S129500 | Build TPC R2 Modules | 288 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | SCI3 Vanderbilt - Unpaid.SCI3 Vanderbilt - Unpaid | 43.2 |  |  | 0 | 0 | 0
S129500 | Build TPC R2 Modules | 960 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | TECH3 Vanderbilt - Unpaid.TECH3 Vanderbilt - Unpaid | 144 |  |  | 0 | 0 | 0
S129500 | Build TPC R2 Modules | 2400 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 360 |  |  | 0 | 0 | 0
S129600 | Test TPC R2 Modules | 288 | 0 | 17-Nov-20 A | 2021-07-22 | 85% | SCI3 Vanderbilt - Unpaid.SCI3 Vanderbilt - Unpaid | 43.2 |  |  | 0 | 0 | 0
S129600 | Test TPC R2 Modules | 2400 | 0 | 17-Nov-20 A | 2021-07-22 | 85% | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 360 |  |  | 0 | 0 | 0
1.02.04.03 TPC R3 Module Production
S133700 | Build TPC R3a Modules | 288 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 43.2 |  |  | 0 | 0 | 0
S133700 | Build TPC R3a Modules | 960 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | TECH3 WIS - Unpaid.TECH3 WIS - Unpaid | 144 |  |  | 0 | 0 | 0
S133700 | Build TPC R3a Modules | 2400 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 360 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | 288 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 43.2 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | 960 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | TECH3 WIS - Unpaid.TECH3 WIS - Unpaid | 144 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | 2400 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 360 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | 288 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 43.2 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | 960 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | TECH3 Temple - Unpaid.TECH3 Temple - Unpaid | 144 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | 2400 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 360 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | 288 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 43.2 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | 2400 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 360 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | 960 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | TECH3 Temple - Unpaid.TECH3 Temple - Unpaid | 144 |  |  | 0 | 0 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S263700 | Trigger LL1 Preproduction Prototype: Test trigger systems | 280 | 0 | 2021-08-09 | 2021-08-27 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 280 |  |  | 0 | 0 | 0
1.06.02.04 LL1 Trigger Production
S264000 | Trigger LL1 Production: Updates to trigger board: Production | 136 | 0 | 2021-09-03 | 2021-09-28 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 136 |  |  | 0 | 0 | 0
S264100 | Trigger LL1 Production: final updates to trigger crate requirements | 20 | 0 | 2021-09-29 | 2021-10-13 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 20 |  |  | 0 | 0 | 0
S265000 | Trigger LL1 Production: Program and commission trigger boards | 60 | 0 | 2021-11-12 | 2021-12-06 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 60 |  |  | 0 | 0 | 0
S265100 | Trigger LL1 Production: Assemble trigger system | 120 | 0 | 2021-12-07 | 2021-12-13 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 120 |  |  | 0 | 0 | 0
S265200 | Trigger LL1 Production: Commission trigger systems | 120 | 0 | 2021-12-14 | 2021-12-20 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 120 |  |  | 0 | 0 | 0
2.05.06 Inner Hcal Installation
S357100 | Commission Inner HCal (labor - if instrumented) - Labor | 640 | 0 | 2022-03-14 | 2022-03-18 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 640 |  |  | 0 | 0 | 0
2.05.07 EMCal Installation
S359300 | Commission EMCal - Labor | 1600 | 0 | 2022-03-30 | 2022-05-03 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 |  |  | 0 | 0 | 0
2.05.08 TPC Installation
S361800 | Commission TPC - Labor Students | 1600 | 0 | 2022-09-15 | 2022-10-05 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 |  |  | 0 | 0 | 0
2.05.09 INTT Installation
S364100 | Commission INTT - Student Labor | 1600 | 0 | 2022-09-19 | 2022-09-30 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 |  |  | 0 | 0 | 0
2.05.10 MVTX Installation
S367500 | Commission MVTX - Labor | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | POSTD LBNL.POSTD LBNL | 480 |  |  | 0 | 0 | 0
S367500 | Commission MVTX - Labor | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 480 |  |  | 0 | 0 | 0
S367500 | Commission MVTX - Labor | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | SCI3 LANL.SCI3 LANL | 480 |  |  | 0 | 0 | 0
S365100 | Installation Prep | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | SCI3 LANL.SCI3 LANL | 80 |  |  | 0 | 0 | 0
S365100 | Installation Prep | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 80 |  |  | 0 | 0 | 0
S365100 | Installation Prep | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | POSTD LBNL.POSTD LBNL | 80 |  |  | 0 | 0 | 0
S365200 | Installation Review | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 8 |  |  | 0 | 0 | 0
S365200 | Installation Review | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | POSTD LBNL.POSTD LBNL | 8 |  |  | 0 | 0 | 0
S365200 | Installation Review | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | SCI3 LANL.SCI3 LANL | 8 |  |  | 0 | 0 | 0
S365800 | Install FELIX | 16 | 0 | 2022-08-17 | 2022-08-18 | 0% | SCI3 LANL.SCI3 LANL | 16 |  |  | 0 | 0 | 0
S366100 | Install RU | 40 | 0 | 2022-08-17 | 2022-08-18 | 0% | SCI3 LANL.SCI3 LANL | 40 |  |  | 0 | 0 | 0
S366400 | Install Half-Barrel 1 | 30 | 0 | 2022-08-19 | 2022-08-26 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 30 |  |  | 0 | 0 | 0
S366400 | Install Half-Barrel 1 | 30 | 0 | 2022-08-19 | 2022-08-26 | 0% | POSTD LBNL.POSTD LBNL | 30 |  |  | 0 | 0 | 0
S366600 | Install Half-Barrel 2 | 30 | 0 | 2022-08-29 | 2022-09-02 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 30 |  |  | 0 | 0 | 0
S366600 | Install Half-Barrel 2 | 30 | 0 | 2022-08-29 | 2022-09-02 | 0% | POSTD LBNL.POSTD LBNL | 30 |  |  | 0 | 0 | 0
S367400 | Address Action Items from MVTX ORR | 16 | 0 | 2022-09-20 | 2022-09-26 | 0% | SCI3 LANL.SCI3 LANL | 16 |  |  | 0 | 0 | 0
S367400 | Address Action Items from MVTX ORR | 16 | 0 | 2022-09-20 | 2022-09-26 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 16 |  |  | 0 | 0 | 0
S367200 | MVTX - Operational Readiness Review (ORR) | 16 | 0 | 2022-09-13 | 2022-09-19 | 0% | SCI3 LANL.SCI3 LANL | 16 |  |  | 0 | 0 | 0
S367200 | MVTX - Operational Readiness Review (ORR) | 16 | 0 | 2022-09-13 | 2022-09-19 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 16 |  |  | 0 | 0 | 0
2.05.11 Min Bias Installation
S369800 | Commission Min Bias - Labor | 1600 | 0 | 2022-09-28 | 2022-10-04 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 |  |  | 0 | 0 | 0
B_T Multiple B_T
1.02.01.08 TPC Assembly
S121700 | Install TPC Electronics | 400 | 0 | 2021-10-18 | 2021-10-29 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 400 |  |  | 0 | 0 | 0
S121700 | Install TPC Electronics | 160 | 18807 | 2021-10-18 | 2021-10-29 | 0% | TECH3 PO M.TECH3 PO M | 160 |  |  | 18807 | 18807 | 0
S121700 | Install TPC Electronics | 48 | 0 | 2021-10-18 | 2021-10-29 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 48 |  |  | 0 | 0 | 0
1.02.05.04 TPC FEE Production
S143300 | Perform QA Testing on TPC FEE | 56 | 8494 | 2021-10-06 | 2022-01-19 | 0% | PROF4 PO E.PROF4 PO E | 56 |  |  | 8494 | 8494 | 0
S143300 | Perform QA Testing on TPC FEE | 56 | 0 | 2021-10-06 | 2022-01-19 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 56 |  |  | 0 | 0 | 0
S143300 | Perform QA Testing on TPC FEE | 280 | 0 | 2021-10-06 | 2022-01-19 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 280 |  |  | 0 | 0 | 0
S143300 | Perform QA Testing on TPC FEE | 168 | 19748 | 2021-10-06 | 2022-01-19 | 0% | TECH3 PO E.TECH3 PO E | 168 |  |  | 19748 | 19748 | 0
S143300 | Perform QA Testing on TPC FEE | 323 | 57258 | 2021-10-06 | 2022-01-19 | 0% | SCI3 PO.SCI3 PO | 323 |  |  | 57258 | 57258 | 0
1.02.06.03 TPC DAM Production
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 44 | 6674 | 08-Mar-21 A | 2021-08-03 | 10% | PROF4 PO E.PROF4 PO E | 39.6 |  |  | 6006.6 | 6006.6 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 264 | 31032 | 08-Mar-21 A | 2021-08-03 | 10% | TECH3 PO E.TECH3 PO E | 237.6 |  |  | 27928.8 | 27928.8 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 44 | 0 | 08-Mar-21 A | 2021-08-03 | 10% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 39.6 |  |  | 0 | 0 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 220 | 0 | 08-Mar-21 A | 2021-08-03 | 10% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 198 |  |  | 0 | 0 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 183 | 32440 | 08-Mar-21 A | 2021-08-03 | 10% | SCI3 PO.SCI3 PO | 164.7 |  |  | 29196 | 29196 | 0
S148500 | Test Full TPC DAM System | 960 | 145959 | 2021-08-04 | 2021-12-14 | 0% | PROF4 PO E.PROF4 PO E | 960 |  |  | 145959 | 145959 | 0
S148500 | Test Full TPC DAM System | 440 | 0 | 2021-08-04 | 2021-12-14 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 440 |  |  | 0 | 0 | 0
S148500 | Test Full TPC DAM System | 440 | 78182 | 2021-08-04 | 2021-12-14 | 0% | SCI3 PO.SCI3 PO | 440 |  |  | 78182 | 78182 | 0
1.02.07.01 TPC Laser System
S150400 | Procure TPC mirror bundles with supports Labor | 24 | 0 | 13-Jan-21 A | 2021-08-31 | 50% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 12 |  |  | 0 | 0 | 0
S150400 | Procure TPC mirror bundles with supports Labor | 24 | 3533 | 13-Jan-21 A | 2021-08-31 | 50% | PROF4 PO M.PROF4 PO M | 12 |  |  | 1766.5 | 1766.5 | 0
1.02.07.02 TPC Gas System
S152800 | Assemble TPC Gas System controls | 48 | 7069 | 22-Mar-21 A | 2021-08-24 | 10% | PROF4 PO M.PROF4 PO M | 43.2 |  |  | 6362.1 | 6362.1 | 0
S152800 | Assemble TPC Gas System controls | 1920 | 0 | 22-Mar-21 A | 2021-08-24 | 10% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 1728 |  |  | 0 | 0 | 0
S152800 | Assemble TPC Gas System controls | 480 | 54779 | 22-Mar-21 A | 2021-08-24 | 10% | TECH3 PO M.TECH3 PO M | 432 |  |  | 49301.1 | 49301.1 | 0
S152900 | Set up TPC Gas System computer control Labor | 24 | 3543 | 15-Mar-21 A | 2021-10-14 | 25% | PROF4 PO M.PROF4 PO M | 18 |  |  | 2657.25 | 2657.25 | 0
S152900 | Set up TPC Gas System computer control Labor | 480 | 0 | 15-Mar-21 A | 2021-10-14 | 25% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 360 |  |  | 0 | 0 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S196900 | Test final sectors with LEDs & cosmic rays | 462 | 70218 | 23-Feb-21 A | 2022-02-04 | 10% | PROF4 PO E.PROF4 PO E | 415.8 |  |  | 63196.2 | 63196.2 | 0
S196900 | Test final sectors with LEDs & cosmic rays | 462 | 54415 | 23-Feb-21 A | 2022-02-04 | 10% | TECH3 PO E.TECH3 PO E | 415.8 |  |  | 48973.5 | 48973.5 | 0
S196900 | Test final sectors with LEDs & cosmic rays | 4608 | 0 | 23-Feb-21 A | 2022-02-04 | 10% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 4147.2 |  |  | 0 | 0 | 0
S197000 | Repair or rework any sectors as required | 231 | 35114 | 16-Mar-21 A | 2022-02-04 | 31% | PROF4 PO M.PROF4 PO M | 159.39 |  |  | 24228.66 | 24228.66 | 0
S197000 | Repair or rework any sectors as required | 462 | 54423 | 16-Mar-21 A | 2022-02-04 | 31% | TECH3 PO M.TECH3 PO M | 318.78 |  |  | 37551.87 | 37551.87 | 0
S197000 | Repair or rework any sectors as required | 2304 | 0 | 16-Mar-21 A | 2022-02-04 | 31% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1589.76 |  |  | 0 | 0 | 0
S197000 | Repair or rework any sectors as required | 462 | 98193 | 16-Mar-21 A | 2022-02-04 | 31% | SCI4 PO.SCI 4 PO | 318.78 |  |  | 67753.17 | 67753.17 | 0
S197000 | Repair or rework any sectors as required | 231 | 35114 | 16-Mar-21 A | 2022-02-04 | 31% | PROF4 PO E.PROF4 PO E | 159.39 |  |  | 24228.66 | 24228.66 | 0
S197000 | Repair or rework any sectors as required | 231 | 27211 | 16-Mar-21 A | 2022-02-04 | 31% | TECH3 PO E.TECH3 PO E | 159.39 |  |  | 18775.59 | 18775.59 | 0
1.05.02.02 EMCal Electronics: Production
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 321 | 41744 | 01-Dec-20 A | 2021-07-20 | 60% | PROF3 PO E.PROF3 PO E | 128.4 |  |  | 16697.6 | 16697.6 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 80 | 14153 | 01-Dec-20 A | 2021-07-20 | 60% | SCI3 PO.SCI3 PO | 32 |  |  | 5661.2 | 5661.2 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 80 | 9385 | 01-Dec-20 A | 2021-07-20 | 60% | TECH3 PO E.TECH3 PO E | 32 |  |  | 3754 | 3754 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 176 | 0 | 01-Dec-20 A | 2021-07-20 | 60% | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 70.4 |  |  | 0 | 0 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 176 | 0 | 01-Dec-20 A | 2021-07-20 | 60% | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 70.4 |  |  | 0 | 0 | 0
1.06.01.03 DAQ Production
S256000 | DAQ Production Boards: Firmware updates | 64 | 11345 | 2021-11-02 | 2022-01-18 | 0% | SCI3 PO.SCI3 PO | 64 |  |  | 11345 | 11345 | 0
S256000 | DAQ Production Boards: Firmware updates | 240 | 0 | 2021-11-02 | 2022-01-18 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 240 |  |  | 0 | 0 | 0
S256000 | DAQ Production Boards: Firmware updates | 960 | 125093 | 2021-11-02 | 2022-01-18 | 0% | PROF3 PO E.PROF3 PO E | 960 |  |  | 125093 | 125093 | 0
S260600 | DAQ Production: DAQ Software development | 880 | 130060 | 16-Nov-20 A | 2021-11-30 | 90% | PROF4 PO M.PROF4 PO M | 88 |  |  | 13006 | 13006 | 0
S260600 | DAQ Production: DAQ Software development | 880 | 151998 | 16-Nov-20 A | 2021-11-30 | 90% | SCI3 PO.SCI3 PO | 88 |  |  | 15199.8 | 15199.8 | 0
S260600 | DAQ Production: DAQ Software development | 1760 | 0 | 16-Nov-20 A | 2021-11-30 | 90% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 176 |  |  | 0 | 0 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S263800 | Final Design Review - DAQ Local Level-1 | 32 | 0 | 2021-08-30 | 2021-09-02 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 32 |  |  | 0 | 0 | 0
S263800 | Final Design Review - DAQ Local Level-1 | 32 | 5673 | 2021-08-30 | 2021-09-02 | 0% | SCI3 PO.SCI3 PO | 32 |  |  | 5673 | 5673 | 0
1.06.02.04 LL1 Trigger Production
S264200 | Production Readiness Review - DAQ Local Level-1 | 32 | 0 | 2021-10-14 | 2021-10-27 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 32 |  |  | 0 | 0 | 0
S264200 | Production Readiness Review - DAQ Local Level-1 | 32 | 5673 | 2021-10-14 | 2021-10-27 | 0% | SCI3 PO.SCI3 PO | 32 |  |  | 5673 | 5673 | 0
1.06.03.02 GL1 Trigger Prototype
S266600 | GL1 Prototype: test prototype | 80 | 13768 | 17-Dec-19 A | 2021-07-30 | 95% | SCI3 PO.SCI3 PO | 4 |  |  | 688.4 | 688.4 | 0
S266600 | GL1 Prototype: test prototype | 240 | 0 | 17-Dec-19 A | 2021-07-30 | 95% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 12 |  |  | 0 | 0 | 0
S266600 | GL1 Prototype: test prototype | 240 | 30362 | 17-Dec-19 A | 2021-07-30 | 95% | PROF3 PO E.PROF3 PO E | 12 |  |  | 1518.1 | 1518.1 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 80 | 13768 | 03-Nov-20 A | 2021-08-30 | 60% | SCI3 PO.SCI3 PO | 32 |  |  | 5507.2 | 5507.2 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 100 | 0 | 03-Nov-20 A | 2021-08-30 | 60% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 40 |  |  | 0 | 0 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 200 | 0 | 03-Nov-20 A | 2021-08-30 | 60% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 80 |  |  | 0 | 0 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 80 | 10121 | 03-Nov-20 A | 2021-08-30 | 60% | PROF3 PO E.PROF3 PO E | 32 |  |  | 4048.4 | 4048.4 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | 64 | 11015 | 2021-07-02 | 2021-07-30 | 0% | SCI3 PO.SCI3 PO | 64 |  |  | 11015 | 11015 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | 60 | 0 | 2021-07-02 | 2021-07-30 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 60 |  |  | 0 | 0 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | 80 | 10121 | 2021-07-02 | 2021-07-30 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10121 | 10121 | 0
1.06.03.03 GL1 Trigger Production
S266900 | GL1 Production: final firmware updates | 64 | 0 | 2021-08-02 | 2021-10-26 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 64 |  |  | 0 | 0 | 0
S266900 | GL1 Production: final firmware updates | 64 | 11015 | 2021-08-02 | 2021-10-26 | 0% | SCI3 PO.SCI3 PO | 64 |  |  | 11015 | 11015 | 0
S266900 | GL1 Production: final firmware updates | 406 | 51363 | 2021-08-02 | 2021-10-26 | 0% | PROF3 PO E.PROF3 PO E | 406 |  |  | 51363 | 51363 | 0
S267900 | GL1 Production: install GL1 system | 80 | 10424 | 2021-10-27 | 2021-12-03 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10424 | 10424 | 0
S267900 | GL1 Production: install GL1 system | 320 | 37615 | 2021-10-27 | 2021-12-03 | 0% | TECH3 PO E.TECH3 PO E | 320 |  |  | 37615 | 37615 | 0
S267900 | GL1 Production: install GL1 system | 160 | 0 | 2021-10-27 | 2021-12-03 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 160 |  |  | 0 | 0 | 0
S268000 | GL1 Production: commission GL1 system | 72 | 12763 | 2021-12-06 | 2022-01-19 | 0% | SCI3 PO.SCI3 PO | 72 |  |  | 12763 | 12763 | 0
S268000 | GL1 Production: commission GL1 system | 108 | 0 | 2021-12-06 | 2022-01-19 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 108 |  |  | 0 | 0 | 0
S268000 | GL1 Production: commission GL1 system | 108 | 14073 | 2021-12-06 | 2022-01-19 | 0% | PROF3 PO E.PROF3 PO E | 108 |  |  | 14073 | 14073 | 0
1.06.04.02 Timing System Prototype
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | 16 | 2754 | 24-Feb-20 A | 2021-07-30 | 95% | SCI3 PO.SCI3 PO | 0.8 |  |  | 137.7 | 137.7 | 0
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | 80 | 0 | 24-Feb-20 A | 2021-07-30 | 95% | STUDENT UCol - Unpaid.STUDENT UCol - Unpaid | 4 |  |  | 0 | 0 | 0
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | 40 | 0 | 24-Feb-20 A | 2021-07-30 | 95% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 2 |  |  | 0 | 0 | 0
S269600 | Update design specifications; incorporate final design choice | 12 | 2065 | 2021-08-02 | 2021-08-13 | 0% | SCI3 PO.SCI3 PO | 12 |  |  | 2065 | 2065 | 0
S269600 | Update design specifications; incorporate final design choice | 30 | 0 | 2021-08-02 | 2021-08-13 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 30 |  |  | 0 | 0 | 0
1.06.04.03 Timing System Production
S270500 | Timing System Production: final firmware updates | 64 | 11015 | 15-Mar-21 A | 2021-08-16 | 60% | SCI3 PO.SCI3 PO | 25.6 |  |  | 4406 | 4406 | 0
S270500 | Timing System Production: final firmware updates | 64 | 0 | 15-Mar-21 A | 2021-08-16 | 60% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 25.6 |  |  | 0 | 0 | 0
S270500 | Timing System Production: final firmware updates | 560 | 70845 | 15-Mar-21 A | 2021-08-16 | 60% | PROF3 PO E.PROF3 PO E | 224 |  |  | 28338 | 28338 | 0
S270700 | Timing System Production: commission timing system | 128 | 22690 | 2021-12-13 | 2022-01-11 | 0% | SCI3 PO.SCI3 PO | 128 |  |  | 22690 | 22690 | 0
S270700 | Timing System Production: commission timing system | 192 | 0 | 2021-12-13 | 2022-01-11 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 192 |  |  | 0 | 0 | 0
S270700 | Timing System Production: commission timing system | 320 | 41698 | 2021-12-13 | 2022-01-11 | 0% | PROF3 PO E.PROF3 PO E | 320 |  |  | 41698 | 41698 | 0
S270800 | Timing System Production: additional firmware updates | 144 | 18764 | 2022-01-12 | 2022-02-04 | 0% | PROF3 PO E.PROF3 PO E | 144 |  |  | 18764 | 18764 | 0
1.07 Min Bias Trigger Detector
S273800 | Test Full Min/Bias Electronics | 16 | 2085 | 2021-12-10 | 2022-01-18 | 0% | PROF3 PO M.PROF3 PO M | 16 |  |  | 2085 | 2085 | 0
S273800 | Test Full Min/Bias Electronics | 48 | 8509 | 2021-12-10 | 2022-01-18 | 0% | SCI3 PO.SCI3 PO | 48 |  |  | 8509 | 8509 | 0
S273800 | Test Full Min/Bias Electronics | 48 | 0 | 2021-12-10 | 2022-01-18 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 48 |  |  | 0 | 0 | 0
S274000 | Bench Test Min/Bias Detector | 80 | 14182 | 2022-01-19 | 2022-01-25 | 0% | SCI3 PO.SCI3 PO | 80 |  |  | 14182 | 14182 | 0
S274000 | Bench Test Min/Bias Detector | 80 | 0 | 2022-01-19 | 2022-01-25 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 80 |  |  | 0 | 0 | 0
A-TEC TEC
1.01.02 Labor by FY
S103200 | Mgmt Labor - A - MIE - FY21 | 1050 | 170568 | 01-Oct-20 A | 30-Sep-21* | 74.4% | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 268.8 |  |  | 43665.408 | 43665.408 | 0
S103400 | Mgmt labor - A - MIE - FY22 | 68 | 11361 | 01-Oct-21* | 2022-01-05 | 0% | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 68 |  |  | 11361 | 11361 | 0
1.01.03 Management Travel
S104200 | Travel FY21 | 5000 | 6905 | 01-Oct-20 A | 2021-09-30 | 74.4% | Travel.Travel Cost | 1280 |  |  | 1767.68 | 1767.68 | 0
1.02.01.08 TPC Assembly
S121650 | Procure Piping Fittings | 1102 | 1279 | 17-May-21 A | 2021-09-09 | 50% | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 551 |  |  | 639.5 | 639.5 | 0
S121950 | TPC Assembly technical Support | 20000 | 23254 | 01-Jun-21 A | 2021-09-20 | 33% | Purch 1st $2M.Material (Purchase (1st $2M) | 13400 |  |  | 15580.18 | 15580.18 | 0
S121605 | TPC Assembly Mechanical Engineering Support | 1500 | 156234 | 01-Feb-21 A | 2022-01-20 | 43.62% | PROF2.PROF2 | 845.7 |  |  | 88084.7292 | 88084.7292 | 0
1.02.02.03 TPC R1 Module Production
S125500 | Build TPC R1 Modules | 960 | 63130 | 11-Jan-21 A | 2021-09-03 | 85% | TECH3 Wayne - PS.TECH3 Wayne - Purchased Services | 144 |  |  | 9469.5 | 9469.5 | 0
S125600 | Test TPC R1 Modules | 960 | 63173 | 11-Jan-21 A | 2021-09-20 | 85% | TECH3 Wayne - PS.TECH3 Wayne - Purchased Services | 144 |  |  | 9475.95 | 9475.95 | 0
1.02.05.04 TPC FEE Production
S136500 | Procure TPC FEE Cooling System - Delivery Acceptance | 60155 | 69821 | 15-Mar-21 A | 2021-07-30 | 17.8% | Purch 1st $2M.Material (Purchase (1st $2M) | 49447.41 |  |  | 57392.862 | 57392.862 | 0
S141500 | Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Delivery Acceptance | 29663 | 34429 | 15-Mar-21 A | 2021-07-30 | 33.2% | Purch 1st $2M.Material (Purchase (1st $2M) | 19814.884 |  |  | 22998.572 | 22998.572 | 0
S142500 | Procure TPC FEE LV Power Supplies - Delivery Acceptance | 190056 | 220595 | 25-Jan-21 A | 2021-07-30 | 80.2% | Purch 1st $2M.Material (Purchase (1st $2M) | 37631.088 |  |  | 43677.81 | 43677.81 | 0
S143200 | Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | 150983 | 175244 | 2021-09-29 | 2021-10-05 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 150983 |  |  | 175244 | 175244 | 0
S141800 | Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | 266694 | 309548 | 02-Nov-20 A | 2021-07-30 | 85% | Purch 1st $2M.Material (Purchase (1st $2M) | 40004.1 |  |  | 46432.2 | 46432.2 | 0
S143250 | TPC Front End Electronics | 150000 | 174103 | 15-Feb-21 A | 2021-07-30 | 33.2% | Purch 1st $2M.Material (Purchase (1st $2M) | 100200 |  |  | 116300.804 | 116300.804 | 0
S143270 | TPC FEE Electrical Engineering Support 1 | 1500 | 119731 | 01-Feb-21 A | 2021-12-29 | 46.52% | TECH1.TECH1 | 802.2 |  |  | 64032.1388 | 64032.1388 | 0
S143271 | TPC FEE Electrical Engineering Support 2 | 0 | 0 | 01-Feb-21 A | 2021-12-29 | 46.52% | PROF3.PROF3 | 0 |  |  | 0 | 0 | 0
1.02.06.03 TPC DAM Production
S147300 | Procure TPC DAM Felix 2.0 Boards - Delivery Acceptance | 130362 | 151309 | 02-Dec-20 A | 2021-07-29 | 80% | Purch 1st $2M.Material (Purchase (1st $2M) | 26072.4 |  |  | 30261.8 | 30261.8 | 0
S147370 | Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Delivery Acceptance | 80745 | 93719 | 2021-10-20 | 2021-10-26 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 80745 |  |  | 93719 | 93719 | 0
S147380 | TPC DAM Electrical Engineering Support | 368 | 48327 | 01-Feb-21 A | 2021-12-30 | 45% | PROF3.PROF3 | 202.4 |  |  | 26579.85 | 26579.85 | 0
1.02.07.01 TPC Laser System
S149600 | Procure TPC Lasers - Delivery Acceptance | 145840 | 165955 | 06-Oct-20 A | 2021-08-16 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 72920 |  |  | 82977.5 | 82977.5 | 0
S150300 | Procure TPC Optics with Mirrors - Delivery Acceptance | 58800 | 66910 | 13-Oct-20 A | 2021-08-12 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 29400 |  |  | 33455 | 33455 | 0
S150500 | Procure TPC mirror bundles with supports M&S | 15000 | 17060 | 13-Jan-21 A | 2021-08-31 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 7500 |  |  | 8530 | 8530 | 0
S150800 | Install &Test TPC Laser safety interlocks M&S | 2000 | 2276 | 2021-08-20 | 2021-08-31 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 2000 |  |  | 2276 | 2276 | 0
S149650 | TPC Diffuse Lasers | 200000 | 232137 | 04-Jan-21 A | 2021-08-02 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 100000 |  |  | 116068.5 | 116068.5 | 0
1.02.07.02 TPC Gas System
S152300 | Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | 33035 | 37591 | 12-Jan-21 A | 2021-07-29 | 70% | Purch 1st $2M.Material (Purchase (1st $2M) | 9910.5 |  |  | 11277.3 | 11277.3 | 0
S153000 | Procure TPC Gas System Computer Controller M&S | 18401 | 20975 | 2021-08-25 | 2021-10-14 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 18401 |  |  | 20975 | 20975 | 0
S153700 | Procure TPC Gas System Components for Installation - Delivery Acceptance | 34086 | 39563 | 08-Mar-21 A | 2021-08-31 | 70% | Purch 1st $2M.Material (Purchase (1st $2M) | 10225.8 |  |  | 11868.9 | 11868.9 | 0
1.02.07.03 TPC Cooling System
S155700 | Procure TPC Plumbing - Contract/PO M&S | 11667 | 13542 | 2021-09-15 | 2021-10-13 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 11667 |  |  | 13542 | 13542 | 0
S155900 | Set up TPC Cooling System computer controls M&S | 10493 | 12179 | 2021-10-14 | 2021-10-20 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10493 |  |  | 12179 | 12179 | 0
1.03.01.03.01 Order Material for EMCAL Final Block Production
S172800 | Prepare fiber assemblies for final blocks | 0 | 0 | 21-Jun-19 A | 2021-08-02 | 96% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 0 |  |  | 0 | 0 | 0
S172800 | Prepare fiber assemblies for final blocks | 9360 | 163757 | 21-Jun-19 A | 2021-08-02 | 96% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 374.4 |  |  | 6550.28 | 6550.28 | 0
S172800 | Prepare fiber assemblies for final blocks | 0 | 0 | 21-Jun-19 A | 2021-08-02 | 96% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 0 |  |  | 0 | 0 | 0
S171800 | Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | 90653 | 104592 | 03-Aug-20 A | 2021-07-19 | 55% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 40793.85 |  |  | 47066.4 | 47066.4 | 0
S172500 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | 26230 | 30218 | 03-Aug-20 A | 2021-07-19 | 75% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6557.5 |  |  | 7554.5 | 7554.5 | 0
S172850 | Supervise EMCal Final Block Production | 52800 | 60868 | 01-May-20 A | 2021-11-30 | 65% | Purch 1st $2M.Material (Purchase (1st $2M) | 18480 |  |  | 21303.8 | 21303.8 | 0
S172870 | EMCal Block Production QA | 460000 | 533915 | 01-Dec-20 A | 2021-09-27 | 70% | Purch 1st $2M.Material (Purchase (1st $2M) | 138000 |  |  | 160174.5 | 160174.5 | 0
1.03.01.03.02 Fabricate final blocks
S175900 | Fabricate final blocks sector 42 | 50 | 2663 | 30-Jun-21 A | 2021-07-08 | 88% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 6 |  |  | 319.56 | 319.56 | 0
S175900 | Fabricate final blocks sector 42 | 75 | 1337 | 30-Jun-21 A | 2021-07-08 | 88% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 9 |  |  | 160.44 | 160.44 | 0
S175900 | Fabricate final blocks sector 42 | 10 | 1162 | 30-Jun-21 A | 2021-07-08 | 88% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 1.2 |  |  | 139.44 | 139.44 | 0
S176000 | Fabricate final blocks sector 43 | 50 | 2663 | 2021-07-09 | 2021-07-16 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176000 | Fabricate final blocks sector 43 | 75 | 1337 | 2021-07-09 | 2021-07-16 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176000 | Fabricate final blocks sector 43 | 10 | 1162 | 2021-07-09 | 2021-07-16 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176100 | Fabricate final blocks sector 44 | 50 | 2663 | 2021-07-19 | 2021-07-26 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176100 | Fabricate final blocks sector 44 | 75 | 1337 | 2021-07-19 | 2021-07-26 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176100 | Fabricate final blocks sector 44 | 10 | 1162 | 2021-07-19 | 2021-07-26 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176200 | Fabricate final blocks sector 45 | 50 | 2663 | 2021-07-27 | 2021-08-03 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176200 | Fabricate final blocks sector 45 | 75 | 1337 | 2021-07-27 | 2021-08-03 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176200 | Fabricate final blocks sector 45 | 10 | 1162 | 2021-07-27 | 2021-08-03 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176300 | Fabricate final blocks sector 46 | 50 | 2663 | 2021-08-04 | 2021-08-11 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176300 | Fabricate final blocks sector 46 | 75 | 1337 | 2021-08-04 | 2021-08-11 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176300 | Fabricate final blocks sector 46 | 10 | 1162 | 2021-08-04 | 2021-08-11 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176400 | Fabricate final blocks sector 47 | 50 | 2663 | 2021-08-12 | 2021-08-19 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176400 | Fabricate final blocks sector 47 | 75 | 1337 | 2021-08-12 | 2021-08-19 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176400 | Fabricate final blocks sector 47 | 10 | 1162 | 2021-08-12 | 2021-08-19 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176500 | Fabricate final blocks sector 48 | 50 | 2663 | 2021-08-20 | 2021-08-27 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176500 | Fabricate final blocks sector 48 | 75 | 1337 | 2021-08-20 | 2021-08-27 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176500 | Fabricate final blocks sector 48 | 10 | 1162 | 2021-08-20 | 2021-08-27 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176600 | Fabricate final blocks sector 49 | 50 | 2663 | 2021-08-30 | 2021-09-07 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176600 | Fabricate final blocks sector 49 | 75 | 1337 | 2021-08-30 | 2021-09-07 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176600 | Fabricate final blocks sector 49 | 10 | 1162 | 2021-08-30 | 2021-09-07 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176700 | Fabricate final blocks sector 50 | 50 | 2663 | 2021-09-08 | 2021-09-15 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176700 | Fabricate final blocks sector 50 | 75 | 1337 | 2021-09-08 | 2021-09-15 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176700 | Fabricate final blocks sector 50 | 10 | 1162 | 2021-09-08 | 2021-09-15 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176800 | Fabricate final blocks sector 51 | 50 | 2663 | 2021-09-16 | 2021-09-23 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176800 | Fabricate final blocks sector 51 | 75 | 1337 | 2021-09-16 | 2021-09-23 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176800 | Fabricate final blocks sector 51 | 10 | 1162 | 2021-09-16 | 2021-09-23 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176900 | Fabricate final blocks sector 52 | 50 | 2663 | 2021-09-24 | 2021-10-01 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176900 | Fabricate final blocks sector 52 | 75 | 1337 | 2021-09-24 | 2021-10-01 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176900 | Fabricate final blocks sector 52 | 10 | 1162 | 2021-09-24 | 2021-10-01 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177000 | Fabricate final blocks sector 53 | 50 | 2663 | 2021-10-04 | 2021-10-12 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177000 | Fabricate final blocks sector 53 | 75 | 1337 | 2021-10-04 | 2021-10-12 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177000 | Fabricate final blocks sector 53 | 10 | 1162 | 2021-10-04 | 2021-10-12 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177100 | Fabricate final blocks sector 54 | 50 | 2663 | 2021-10-13 | 2021-10-20 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177100 | Fabricate final blocks sector 54 | 75 | 1337 | 2021-10-13 | 2021-10-20 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177100 | Fabricate final blocks sector 54 | 10 | 1162 | 2021-10-13 | 2021-10-20 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177200 | Fabricate final blocks sector 55 | 50 | 2663 | 2021-10-21 | 2021-10-28 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177200 | Fabricate final blocks sector 55 | 75 | 1337 | 2021-10-21 | 2021-10-28 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177200 | Fabricate final blocks sector 55 | 10 | 1162 | 2021-10-21 | 2021-10-28 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177300 | Fabricate final blocks sector 56 | 50 | 2663 | 2021-10-29 | 2021-11-04 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177300 | Fabricate final blocks sector 56 | 75 | 1337 | 2021-10-29 | 2021-11-04 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177300 | Fabricate final blocks sector 56 | 10 | 1162 | 2021-10-29 | 2021-11-04 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177400 | Fabricate final blocks sector 57 | 50 | 2663 | 2021-11-05 | 2021-11-12 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177400 | Fabricate final blocks sector 57 | 75 | 1337 | 2021-11-05 | 2021-11-12 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177400 | Fabricate final blocks sector 57 | 10 | 1162 | 2021-11-05 | 2021-11-12 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177500 | Fabricate final blocks sector 58 | 50 | 2663 | 2021-11-15 | 2021-11-19 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177500 | Fabricate final blocks sector 58 | 75 | 1337 | 2021-11-15 | 2021-11-19 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177500 | Fabricate final blocks sector 58 | 10 | 1162 | 2021-11-15 | 2021-11-19 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177600 | Fabricate final blocks sector 59 | 50 | 2663 | 2021-11-22 | 2021-11-30 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177600 | Fabricate final blocks sector 59 | 75 | 1337 | 2021-11-22 | 2021-11-30 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177600 | Fabricate final blocks sector 59 | 10 | 1162 | 2021-11-22 | 2021-11-30 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177700 | Fabricate final blocks sector 60 | 50 | 2663 | 2021-12-01 | 2021-12-07 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177700 | Fabricate final blocks sector 60 | 75 | 1337 | 2021-12-01 | 2021-12-07 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177700 | Fabricate final blocks sector 60 | 10 | 1162 | 2021-12-01 | 2021-12-07 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177800 | Fabricate final blocks sector 61 | 50 | 2663 | 2021-12-08 | 2021-12-14 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177800 | Fabricate final blocks sector 61 | 75 | 1337 | 2021-12-08 | 2021-12-14 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177800 | Fabricate final blocks sector 61 | 10 | 1162 | 2021-12-08 | 2021-12-14 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177900 | Fabricate final blocks sector 62 | 50 | 2663 | 2021-12-15 | 2021-12-21 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177900 | Fabricate final blocks sector 62 | 75 | 1337 | 2021-12-15 | 2021-12-21 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177900 | Fabricate final blocks sector 62 | 10 | 1162 | 2021-12-15 | 2021-12-21 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S178000 | Fabricate final blocks sector 63 | 50 | 2663 | 2021-12-22 | 2021-12-29 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S178000 | Fabricate final blocks sector 63 | 75 | 1337 | 2021-12-22 | 2021-12-29 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S178000 | Fabricate final blocks sector 63 | 10 | 1162 | 2021-12-22 | 2021-12-29 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S178100 | Fabricate final blocks sector 64 | 50 | 2663 | 2021-12-30 | 2022-01-06 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S178100 | Fabricate final blocks sector 64 | 75 | 1337 | 2021-12-30 | 2022-01-06 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S178100 | Fabricate final blocks sector 64 | 10 | 1162 | 2021-12-30 | 2022-01-06 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
1.03.01.03.03 Pack and ship final blocks to BNL
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | 16 | 285 | 15-Jun-21 A | 2021-09-03 | 5% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 15.2 |  |  | 270.75 | 270.75 | 0
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | 10 | 533 | 15-Jun-21 A | 2021-09-03 | 5% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 9.5 |  |  | 506.35 | 506.35 | 0
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | 15 | 1743 | 15-Jun-21 A | 2021-09-03 | 5% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 14.25 |  |  | 1655.85 | 1655.85 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | 16 | 285 | 2021-11-05 | 2021-11-12 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 |  |  | 285 | 285 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | 10 | 533 | 2021-11-05 | 2021-11-12 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 |  |  | 533 | 533 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | 15 | 1743 | 2021-11-05 | 2021-11-12 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 |  |  | 1743 | 1743 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 16 | 285 | 2022-01-07 | 2022-01-07 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 |  |  | 285 | 285 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 10 | 533 | 2022-01-07 | 2022-01-07 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 |  |  | 533 | 533 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 15 | 1743 | 2022-01-07 | 2022-01-07 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 |  |  | 1743 | 1743 | 0
S178710 | Pack and ship final blocks for sectors 40-48 to BNL - M&S | 6480 | 7521 | 15-Jun-21 A | 2021-09-03 | 5% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6156 |  |  | 7144.95 | 7144.95 | 0
S178910 | Pack and ship final blocks for sectors 49-56 to BNL - M&S | 6480 | 7521 | 2021-11-05 | 2021-11-12 | 0% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 |  |  | 7521 | 7521 | 0
S176010 | Pack and ship final blocks for sectors 57-64 to BNL - M&S | 6480 | 7521 | 2022-01-07 | 2022-01-07 | 0% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 |  |  | 7521 | 7521 | 0
1.03.02.02.03 EMCAL Final Module Fabrication
S187700 | Install light guides on final blocks M&S | 1650 | 1912 | 21-Jan-21 A | 2022-01-31 | 35% | Purch 1st $2M.Material (Purchase (1st $2M) | 1072.5 |  |  | 1242.8 | 1242.8 | 0
S188100 | Install SiPMs daughterboards on final blocks M&S | 300 | 348 | 22-Jan-21 A | 2022-02-03 | 35% | Purch 1st $2M.Material (Purchase (1st $2M) | 195 |  |  | 226.2 | 226.2 | 0
S187400 | Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | 215244 | 240129 | 22-Dec-20 A | 2021-07-30 | 74% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 55963.44 |  |  | 62433.54 | 62433.54 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S196100 | Procure EMCAL Cooling System for Final Sectors - Delivery Acceptance | 70893 | 82284 | 18-Jan-21 A | 2021-07-14 | 42% | Purch 1st $2M.Material (Purchase (1st $2M) | 41117.94 |  |  | 47724.72 | 47724.72 | 0
S196910 | Technical support labor for EMCal assembly | 3520 | 281000 | 04-Jan-21 A | 2022-01-12 | 50% | TECH1.TECH1 | 1760 |  |  | 140500 | 140500 | 0
1.04.01 Inner HCAL Support Structure & Support Rings
S199310 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 2 | 237500 | 264958 | 16-Aug-21* | 2021-08-20 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 |  |  | 264958 | 264958 | 0
S199320 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 3 | 237500 | 264958 | 24-Sep-21* | 2021-09-30 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 |  |  | 264958 | 264958 | 0
S199330 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 4 | 237500 | 264958 | 15-Nov-21* | 2021-11-19 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 |  |  | 264958 | 264958 | 0
1.05.02.02 EMCal Electronics: Production
S228100 | Test SiPM Daughter Boards Production Sectors 13-64 | 176 | 2888 | 01-Dec-20 A | 2021-07-20 | 60% | STUDENT UM - PS.STUDENT UM - Purchased Services | 70.4 |  |  | 1155.2 | 1155.2 | 0
S229400 | Test EMCal Preamp Boards: Production Sectors 13-64 | 384 | 6313 | 26-Feb-21 A | 2021-07-14 | 40% | STUDENT UM - PS.STUDENT UM - Purchased Services | 230.4 |  |  | 3787.8 | 3787.8 | 0
S233200 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Delivery Acceptance | 177356 | 205854 | 2021-12-27 | 2022-01-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 177356 |  |  | 205854 | 205854 | 0
S233250 | Trunk Signal Cables - EMCal | 670160 | 777844 | 2021-07-30 | 2021-12-23 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 670160 |  |  | 777844 | 777844 | 0
1.05.02.04 HCal Electronics: Production
S244400 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | 87827 | 101939 | 14-Dec-20 A | 2021-08-27 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 43913.5 |  |  | 50969.5 | 50969.5 | 0
S244450 | Trunk Signal Cables - OuterHCal | 128640 | 149310 | 2021-07-30 | 2021-12-23 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 128640 |  |  | 149310 | 149310 | 0
1.05.03.02 Calorimeter Digitizers: Production
S252800 | Procure Production Digitizer (Boards) - Delivery Acceptance | 129049 | 149785 | 2021-08-03 | 2021-08-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 129049 |  |  | 149785 | 149785 | 0
S252900 | Procure Production Digitizer (Assembly & Tests) - Delivery Acceptance | 199077 | 231066 | 2021-10-28 | 2021-11-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 199077 |  |  | 231066 | 231066 | 0
S252700 | Procure Production Digitizer (Parts) - Delivery Acceptance | 584602 | 678538 | 30-Apr-21 A | 2021-08-09 | 37% | Purch 1st $2M.Material (Purchase (1st $2M) | 368299.26 |  |  | 427478.94 | 427478.94 | 0
1.06.01.03 DAQ Production
S255900 | Procure DAQ Production Boards - Delivery Acceptance | 104682 | 121503 | 2021-10-26 | 2021-11-01 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 104682 |  |  | 121503 | 121503 | 0
S256700 | Procure DAQ Production Crates - Delivery Acceptance | 64000 | 74284 | 2021-11-24 | 2021-12-02 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 64000 |  |  | 74284 | 74284 | 0
S258700 | Procure DAQ Production jSEB Slow control computers - Delivery Acceptance | 16856 | 19181 | 2021-08-02 | 2021-08-06 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 16856 |  |  | 19181 | 19181 | 0
S259500 | Procure DAQ Production Buffer Boxes - Delivery Acceptance | 223540 | 259459 | 23-Nov-20 A | 2021-10-29 | 18% | Purch 1st $2M.Material (Purchase (1st $2M) | 183302.8 |  |  | 212756.38 | 212756.38 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S263600 | Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance | 60000 | 69641 | 2021-08-02 | 2021-08-06 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 60000 |  |  | 69641 | 69641 | 0
1.06.02.04 LL1 Trigger Production
S264900 | Procure Production LL1 System - Delivery Acceptance | 117000 | 135800 | 2021-11-04 | 2021-11-10 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 117000 |  |  | 135800 | 135800 | 0
1.06.03.03 GL1 Trigger Production
S267600 | Procure Production GL1 Components - final hardware - Delivery Acceptance | 28150 | 32673 | 2021-09-14 | 2021-09-20 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 28150 |  |  | 32673 | 32673 | 0
1.06.04.03 Timing System Production
S270300 | Timing System Production (FPGA Boards) - Delivery Acceptance | 41600 | 48284 | 2021-10-27 | 2021-11-02 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 41600 |  |  | 48284 | 48284 | 0
1.07 Min Bias Trigger Detector
S273500 | Procure Min/Bias Electronics (sPHENIX Production Digitizers) - Delivery Acceptance | 14770 | 17143 | 2021-12-03 | 2021-12-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 14770 |  |  | 17143 | 17143 | 0
S273600 | Procure MBD Shaper/Disc Board 128 Channels - Delivery Acceptance | 46420 | 53879 | 2021-12-03 | 2021-12-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 46420 |  |  | 53879 | 53879 | 0
Formulas:
Forecast Finish = VLOOKUP([Activity ID],'forecast data dump'!$A1:H3450,5,FALSE)
Forecast Start = VLOOKUP([Activity ID],'forecast data dump'!$A1:H3450,4,FALSE)

## ETC sheet-Cat B (hidden)
Baseline data |  |  |  | Forecast Data (June status file)
Activity ID | Activity Name | Baseline Units | Baseline Cost | Forecast Start | Forecast Finish | % Complete | Resource ID Name | Calc ETC Units | Updated ETC Units | Potential PCR? | Calc ETC Cost | Updated ETC Cost | EAC Growth
B BNL Contributed Labor
1.01.02 Labor by FY
S103310 | Mgmt labor - B - BNL Contributed Labor - FY21 - CA-D Resource(s) | 880 | 154145 | 01-Oct-20 A | 30-Sep-21* | 74.3% | PROF5 AD.PROF5 AD | 226.16 |  |  | 39615.265 | 39615.265 | 0
S103510 | Mgmt labor - B - BNL Contributed Labor - FY22 - CA-D Resource(s) | 35 | 6351 | 01-Oct-21* | 2022-01-05 | 0% | PROF5 AD.PROF5 AD | 35 |  |  | 6351 | 6351 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 2965 | 628831 | 01-Oct-20 A | 30-Sep-21* | 74.3% | SCI4 PO.SCI 4 PO | 762.005 |  |  | 161609.567 | 161609.567 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 1896 | 291837 | 01-Oct-20 A | 30-Sep-21* | 74.3% | SCI2 PO.SCI2 PO | 487.272 |  |  | 75002.109 | 75002.109 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 100 | 15199 | 01-Oct-20 A | 30-Sep-21* | 74.3% | PROF4 PO M.PROF4 PO M | 25.7 |  |  | 3906.143 | 3906.143 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 468 | 81977 | 01-Oct-20 A | 30-Sep-21* | 74.3% | PROF5 PO M.PROF5 PO M | 120.276 |  |  | 21068.089 | 21068.089 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 1632 | 168465 | 01-Oct-20 A | 30-Sep-21* | 74.3% | PROF2 PO PC.PROF2 PO PC | 419.424 |  |  | 43295.505 | 43295.505 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 426 | 26656 | 01-Oct-20 A | 30-Sep-21* | 74.3% | ADMIN1 PO.ADMIN1 PO | 109.482 |  |  | 6850.592 | 6850.592 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 1613 | 376091 | 01-Oct-20 A | 30-Sep-21* | 74.3% | ADMIN7 PO.ADMIN7 PO | 414.541 |  |  | 96655.387 | 96655.387 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 4 | 626 | 01-Oct-21* | 2022-01-05 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 626 | 626 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 19 | 3377 | 01-Oct-21* | 2022-01-05 | 0% | PROF5 PO M.PROF5 PO M | 19 |  |  | 3377 | 3377 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 75 | 11891 | 01-Oct-21* | 2022-01-05 | 0% | SCI2 PO.SCI2 PO | 75 |  |  | 11891 | 11891 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 65 | 6941 | 01-Oct-21* | 2022-01-05 | 0% | PROF2 PO PC.PROF2 PO PC | 65 |  |  | 6941 | 6941 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 17 | 1098 | 01-Oct-21* | 2022-01-05 | 0% | ADMIN1 PO.ADMIN1 PO | 17 |  |  | 1098 | 1098 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 65 | 15494 | 01-Oct-21* | 2022-01-05 | 0% | ADMIN7 PO.ADMIN7 PO | 65 |  |  | 15494 | 15494 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 118 | 25777 | 01-Oct-21* | 2022-01-05 | 0% | SCI4 PO.SCI 4 PO | 118 |  |  | 25777 | 25777 | 0
1.02.01.02 TPC v2 Field Cage
S112200 | TPC Field Cage Safety Review | 4 | 688 | 2021-08-16 | 2021-08-18 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S112200 | TPC Field Cage Safety Review | 4 | 589 | 2021-08-16 | 2021-08-18 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 589 | 589 | 0
S112300 | Final Design Review - TPC Field Cage | 4 | 688 | 2021-08-19 | 2021-08-23 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S112300 | Final Design Review - TPC Field Cage | 4 | 589 | 2021-08-19 | 2021-08-23 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 589 | 589 | 0
S112100 | Benchtest TPC v2 Field Cage | 4 | 688 | 2021-08-02 | 2021-08-06 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S112100 | Benchtest TPC v2 Field Cage | 4 | 589 | 2021-08-02 | 2021-08-06 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 589 | 589 | 0
1.02.05.02 TPC FEE Prototype v2 (Pre-Production)
S137700 | Final Design Review, Production Readiness Review - TPC FEE | 4 | 589 | 13-Apr-20 A | 2021-07-28 | 95% | PROF4 PO M.PROF4 PO M | 0.2 |  |  | 29.45 | 29.45 | 0
S137700 | Final Design Review, Production Readiness Review - TPC FEE | 4 | 688 | 13-Apr-20 A | 2021-07-28 | 95% | SCI3 PO.SCI3 PO | 0.2 |  |  | 34.4 | 34.4 | 0
1.02.05.03 SAMPA chip 80 nsec
S140701 | Production Readiness Review for TPC FEE full production | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | PROF3 IO E.PROF3 IO E | 8 |  |  | 1012 | 1012 | 0
S140701 | Production Readiness Review for TPC FEE full production | 8 | 1178 | 2021-07-01 | 2021-07-01 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1178 | 1178 | 0
S140701 | Production Readiness Review for TPC FEE full production | 8 | 1377 | 2021-07-01 | 2021-07-01 | 0% | SCI3 PO.SCI3 PO | 8 |  |  | 1377 | 1377 | 0
1.02.06.03 TPC DAM Production
S147500 | TPC DAM Felix 2.0 Bandwidth test in 1008 | 320 | 48539 | 15-Mar-21 A | 2021-08-31 | 40% | PROF4 PO E.PROF4 PO E | 192 |  |  | 29123.4 | 29123.4 | 0
S147500 | TPC DAM Felix 2.0 Bandwidth test in 1008 | 67 | 11877 | 15-Mar-21 A | 2021-08-31 | 40% | SCI3 PO.SCI3 PO | 40.2 |  |  | 7126.2 | 7126.2 | 0
1.02.07.01 TPC Laser System
S148800 | TPC Laser System Safety Review | 4 | 572 | 22-Mar-21 A | 2021-07-22 | 20% | PROF4 PO M.PROF4 PO M | 3.2 |  |  | 457.6 | 457.6 | 0
S148800 | TPC Laser System Safety Review | 4 | 668 | 22-Mar-21 A | 2021-07-22 | 20% | SCI3 PO.SCI3 PO | 3.2 |  |  | 534.4 | 534.4 | 0
S148900 | Procurement Readiness Review - TPC Laser System | 4 | 572 | 22-Mar-21 A | 2021-07-30 | 50% | PROF4 PO M.PROF4 PO M | 2 |  |  | 286 | 286 | 0
S148900 | Procurement Readiness Review - TPC Laser System | 4 | 668 | 22-Mar-21 A | 2021-07-30 | 50% | SCI3 PO.SCI3 PO | 2 |  |  | 334 | 334 | 0
S150600 | Install & Test TPC lasers | 24 | 2739 | 2021-08-17 | 2021-08-19 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S150700 | Install &Test TPC Laser safety interlocks Labor | 64 | 11015 | 2021-08-20 | 2021-08-31 | 0% | SCI3 PO.SCI3 PO | 64 |  |  | 11015 | 11015 | 0
S150700 | Install &Test TPC Laser safety interlocks Labor | 64 | 9425 | 2021-08-20 | 2021-08-31 | 0% | PROF4 PO M.PROF4 PO M | 64 |  |  | 9425 | 9425 | 0
S150900 | Install &Test TPC Laser optics with mounts | 64 | 7304 | 2021-08-20 | 2021-08-31 | 0% | TECH3 PO M.TECH3 PO M | 64 |  |  | 7304 | 7304 | 0
S151000 | Install &Test TPC mirror bundles and supports | 24 | 2739 | 2021-09-01 | 2021-09-03 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
1.02.07.02 TPC Gas System
S153900 | Install and Test TPC Gas System Interlocks | 40 | 6067 | 2021-12-01 | 2021-12-07 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6067 | 6067 | 0
S153800 | Assemble and Plumb TPC Gas System | 440 | 51720 | 16-Mar-21 A | 2021-11-30 | 30% | TECH3 PO M.TECH3 PO M | 308 |  |  | 36204 | 36204 | 0
1.02.07.03 TPC Cooling System
S155100 | Install TPC Cooling System pumps | 24 | 2739 | 2021-07-01 | 2021-07-06 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S155200 | Install TPC Cooling System heat exchanger | 24 | 2739 | 2021-07-07 | 2021-07-09 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S155300 | Install TPC Cooling System PH control | 24 | 2739 | 2021-07-12 | 2021-07-14 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S155400 | Install TPC Cooling System end cap manifolds | 80 | 9130 | 2021-07-15 | 2021-07-28 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9130 | 9130 | 0
S155500 | Install TPC Cooling System tanks | 24 | 2739 | 2021-07-29 | 2021-08-02 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S155600 | Install TPC Cooling System plumbing Labor | 240 | 27453 | 2021-08-03 | 2021-09-14 | 0% | TECH3 PO M.TECH3 PO M | 240 |  |  | 27453 | 27453 | 0
S155800 | Set up TPC Cooling System computer controls Labor | 40 | 4702 | 2021-10-14 | 2021-10-20 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
S156000 | Set up and Test TPC Cooling System & Interlocks | 40 | 4702 | 2021-10-21 | 2021-10-27 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
1.03.02.02.03 EMCAL Final Module Fabrication
S187500 | Receive, unpack, log & inspect final blocks | 462 | 69911 | 23-Nov-20 A | 2022-01-31 | 58% | PROF4 PO E.PROF4 PO E | 194.04 |  |  | 29362.62 | 29362.62 | 0
S187500 | Receive, unpack, log & inspect final blocks | 922 | 108120 | 23-Nov-20 A | 2022-01-31 | 58% | TECH3 PO M.TECH3 PO M | 387.24 |  |  | 45410.4 | 45410.4 | 0
S187600 | Install light guides on final blocks Labor | 462 | 69926 | 21-Jan-21 A | 2022-01-31 | 35% | PROF4 PO E.PROF4 PO E | 300.3 |  |  | 45451.9 | 45451.9 | 0
S187600 | Install light guides on final blocks Labor | 922 | 108143 | 21-Jan-21 A | 2022-01-31 | 35% | TECH3 PO M.TECH3 PO M | 599.3 |  |  | 70292.95 | 70292.95 | 0
S187800 | Install reflectors on final blocks Labor | 462 | 69957 | 23-Nov-20 A | 2022-01-31 | 38% | PROF4 PO E.PROF4 PO E | 286.44 |  |  | 43373.34 | 43373.34 | 0
S187800 | Install reflectors on final blocks Labor | 922 | 108191 | 23-Nov-20 A | 2022-01-31 | 38% | TECH3 PO M.TECH3 PO M | 571.64 |  |  | 67078.42 | 67078.42 | 0
S188000 | Install SiPMs daughterboards on final blocks Labor | 462 | 70018 | 22-Jan-21 A | 2022-02-03 | 35% | PROF4 PO E.PROF4 PO E | 300.3 |  |  | 45511.7 | 45511.7 | 0
S188000 | Install SiPMs daughterboards on final blocks Labor | 922 | 108286 | 22-Jan-21 A | 2022-02-03 | 35% | TECH3 PO M.TECH3 PO M | 599.3 |  |  | 70385.9 | 70385.9 | 0
S188200 | Glue final blocks together into modules | 462 | 70049 | 22-Jan-21 A | 2022-02-03 | 33% | PROF4 PO E.PROF4 PO E | 309.54 |  |  | 46932.83 | 46932.83 | 0
S188200 | Glue final blocks together into modules | 922 | 108333 | 22-Jan-21 A | 2022-02-03 | 33% | TECH3 PO M.TECH3 PO M | 617.74 |  |  | 72583.11 | 72583.11 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S196200 | Build mechanical enclosures for final sectors | 720 | 84633 | 12-Jan-21 A | 2021-07-14 | 33% | TECH3 PO M.TECH3 PO M | 482.4 |  |  | 56704.11 | 56704.11 | 0
S196300 | Build mechanical fixtures for final sectors | 720 | 84017 | 12-Jan-21 A | 2021-07-14 | 45% | TECH3 PO M.TECH3 PO M | 396 |  |  | 46209.35 | 46209.35 | 0
S196400 | Build cooling system for final sectors | 180 | 27303 | 12-Jan-21 A | 2021-07-14 | 33% | PROF4 PO M.PROF4 PO M | 120.6 |  |  | 18293.01 | 18293.01 | 0
S196500 | Install modules in final sectors | 462 | 70145 | 26-Jan-21 A | 2022-02-03 | 33% | PROF4 PO E.PROF4 PO E | 309.54 |  |  | 46997.15 | 46997.15 | 0
S196500 | Install modules in final sectors | 1383 | 162722 | 26-Jan-21 A | 2022-02-03 | 33% | TECH3 PO M.TECH3 PO M | 926.61 |  |  | 109023.74 | 109023.74 | 0
S196700 | Install readout electronics on final sectors | 1383 | 162798 | 22-Feb-21 A | 2022-02-04 | 31% | TECH3 PO M.TECH3 PO M | 954.27 |  |  | 112330.62 | 112330.62 | 0
S196700 | Install readout electronics on final sectors | 462 | 70178 | 22-Feb-21 A | 2022-02-04 | 31% | PROF4 PO E.PROF4 PO E | 318.78 |  |  | 48422.82 | 48422.82 | 0
S196800 | Install cables & cooling system on final sectors | 462 | 70198 | 22-Feb-21 A | 2022-02-04 | 31% | PROF4 PO E.PROF4 PO E | 318.78 |  |  | 48436.62 | 48436.62 | 0
S196800 | Install cables & cooling system on final sectors | 1728 | 262557 | 22-Feb-21 A | 2022-02-04 | 31% | PROF4 PO M.PROF4 PO M | 1192.32 |  |  | 181164.33 | 181164.33 | 0
S196800 | Install cables & cooling system on final sectors | 1383 | 162845 | 22-Feb-21 A | 2022-02-04 | 31% | TECH3 PO M.TECH3 PO M | 954.27 |  |  | 112363.05 | 112363.05 | 0
1.05.02.02 EMCal Electronics: Production
S229405 | Test EMCal Preamp Boards: Production Sectors 13-64 - Contributed Labor | 96 | 11284 | 29-Mar-21 A | 2021-07-14 | 40% | TECH3 PO E.TECH3 PO E | 57.6 |  |  | 6770.4 | 6770.4 | 0
S229405 | Test EMCal Preamp Boards: Production Sectors 13-64 - Contributed Labor | 153 | 19937 | 29-Mar-21 A | 2021-07-14 | 40% | PROF3 PO E.PROF3 PO E | 91.8 |  |  | 11962.2 | 11962.2 | 0
1.06.01.03 DAQ Production
S256800 | DAQ Production: Crate installation | 32 | 4854 | 07-Dec-20 A | 2021-12-17 | 30% | PROF4 PO M.PROF4 PO M | 22.4 |  |  | 3397.8 | 3397.8 | 0
S256800 | DAQ Production: Crate installation | 32 | 5673 | 07-Dec-20 A | 2021-12-17 | 30% | SCI3 PO.SCI3 PO | 22.4 |  |  | 3971.1 | 3971.1 | 0
S256800 | DAQ Production: Crate installation | 512 | 60183 | 07-Dec-20 A | 2021-12-17 | 30% | TECH3 PO M.TECH3 PO M | 358.4 |  |  | 42128.1 | 42128.1 | 0
S256800 | DAQ Production: Crate installation | 32 | 4122 | 07-Dec-20 A | 2021-12-17 | 30% | CRAFT3.CRAFT3 | 22.4 |  |  | 2885.4 | 2885.4 | 0
S258600 | DAQ Production: Procure jSEB Slow control computers | 80 | 11781 | 20-Jul-20 A | 2021-07-30 | 50% | PROF4 PO M.PROF4 PO M | 40 |  |  | 5890.5 | 5890.5 | 0
S258600 | DAQ Production: Procure jSEB Slow control computers | 80 | 13768 | 20-Jul-20 A | 2021-07-30 | 50% | SCI3 PO.SCI3 PO | 40 |  |  | 6884 | 6884 | 0
S260500 | DAQ Production: Modify and Debug event builder software | 320 | 48539 | 26-Apr-21 A | 2021-08-25 | 90% | PROF4 PO M.PROF4 PO M | 32 |  |  | 4853.9 | 4853.9 | 0
S260500 | DAQ Production: Modify and Debug event builder software | 320 | 56726 | 26-Apr-21 A | 2021-08-25 | 90% | SCI3 PO.SCI3 PO | 32 |  |  | 5672.6 | 5672.6 | 0
S260400 | DAQ Production: Setting up the switches | 56 | 8494 | 12-Feb-21 A | 2021-07-30 | 80% | PROF4 PO M.PROF4 PO M | 11.2 |  |  | 1698.8 | 1698.8 | 0
S260400 | DAQ Production: Setting up the switches | 88 | 15600 | 12-Feb-21 A | 2021-07-30 | 80% | SCI3 PO.SCI3 PO | 17.6 |  |  | 3120 | 3120 | 0
S260400 | DAQ Production: Setting up the switches | 44 | 5172 | 12-Feb-21 A | 2021-07-30 | 80% | TECH3 PO M.TECH3 PO M | 8.8 |  |  | 1034.4 | 1034.4 | 0
S260700 | DAQ Production: Internal Readiness Review | 80 | 12135 | 2022-01-19 | 2022-02-01 | 0% | PROF4 PO M.PROF4 PO M | 80 |  |  | 12135 | 12135 | 0
S260700 | DAQ Production: Internal Readiness Review | 240 | 42545 | 2022-01-19 | 2022-02-01 | 0% | SCI3 PO.SCI3 PO | 240 |  |  | 42545 | 42545 | 0
S258800 | Production jSEB Slow control computers - Setup Machines | 40 | 6884 | 2021-08-09 | 2021-08-13 | 0% | SCI3 PO.SCI3 PO | 40 |  |  | 6884 | 6884 | 0
S259600 | Production Buffer Boxes - Setup Machines | 40 | 7091 | 23-Nov-20 A | 2021-11-05 | 16% | SCI3 PO.SCI3 PO | 33.6 |  |  | 5956.44 | 5956.44 | 0
1.06.03.02 GL1 Trigger Prototype
S266701 | Final Design Review - DAQ Global Level-1 | 4 | 506 | 2021-07-01 | 2021-07-01 | 0% | PROF3 IO E.PROF3 IO E | 4 |  |  | 506 | 506 | 0
S266701 | Final Design Review - DAQ Global Level-1 | 4 | 688 | 2021-07-01 | 2021-07-01 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S266701 | Final Design Review - DAQ Global Level-1 | 4 | 0 | 2021-07-01 | 2021-07-01 | 0% | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 |  |  | 0 | 0 | 0
S266701 | Final Design Review - DAQ Global Level-1 | 4 | 824 | 2021-07-01 | 2021-07-01 | 0% | SCI4 PO.SCI 4 PO | 4 |  |  | 824 | 824 | 0
S266701 | Final Design Review - DAQ Global Level-1 | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1012 | 1012 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 4 | 506 | 2021-07-01 | 2021-07-01 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 506 | 506 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | PROF3 IO E.PROF3 IO E | 8 |  |  | 1012 | 1012 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 4 | 688 | 2021-07-01 | 2021-07-01 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 4 | 0 | 2021-07-01 | 2021-07-01 | 0% | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 |  |  | 0 | 0 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 4 | 824 | 2021-07-01 | 2021-07-01 | 0% | SCI4 PO.SCI 4 PO | 4 |  |  | 824 | 824 | 0
1.06.03.03 GL1 Trigger Production
S268100 | GL1 Production: additional firmware improvements | 156 | 20328 | 2022-01-20 | 2022-02-04 | 0% | PROF3 PO E.PROF3 PO E | 156 |  |  | 20328 | 20328 | 0
S268010 | GL1 Production: commission GL1 system | 108 | 14073 | 2021-12-06 | 2022-01-19 | 0% | PROF3 IO E.PROF3 IO E | 108 |  |  | 14073 | 14073 | 0
1.06.04.02 Timing System Prototype
S269501 | Final Design Review - DAQ Timing System | 8 | 1012 | 2021-08-02 | 2021-08-02 | 0% | PROF3 IO E.PROF3 IO E | 8 |  |  | 1012 | 1012 | 0
S269501 | Final Design Review - DAQ Timing System | 4 | 506 | 2021-08-02 | 2021-08-02 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 506 | 506 | 0
S269501 | Final Design Review - DAQ Timing System | 4 | 688 | 2021-08-02 | 2021-08-02 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S269501 | Final Design Review - DAQ Timing System | 4 | 0 | 2021-08-02 | 2021-08-02 | 0% | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 |  |  | 0 | 0 | 0
S269501 | Final Design Review - DAQ Timing System | 4 | 824 | 2021-08-02 | 2021-08-02 | 0% | SCI4 PO.SCI 4 PO | 4 |  |  | 824 | 824 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 4 | 824 | 2021-07-30 | 2021-07-30 | 0% | SCI4 PO.SCI 4 PO | 4 |  |  | 824 | 824 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 4 | 688 | 2021-07-30 | 2021-07-30 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 4 | 0 | 2021-07-30 | 2021-07-30 | 0% | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 |  |  | 0 | 0 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 4 | 506 | 2021-07-30 | 2021-07-30 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 506 | 506 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 8 | 1012 | 2021-07-30 | 2021-07-30 | 0% | PROF3 IO E.PROF3 IO E | 8 |  |  | 1012 | 1012 | 0
1.06.04.03 Timing System Production
S270600 | Timing System Production: install timing system | 80 | 10424 | 2021-11-03 | 2021-12-10 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10424 | 10424 | 0
S270600 | Timing System Production: install timing system | 40 | 7091 | 2021-11-03 | 2021-12-10 | 0% | SCI3 PO.SCI3 PO | 40 |  |  | 7091 | 7091 | 0
S270600 | Timing System Production: install timing system | 320 | 37615 | 2021-11-03 | 2021-12-10 | 0% | TECH3 PO E.TECH3 PO E | 320 |  |  | 37615 | 37615 | 0
S270510 | Timing System Production: final firmware updates | 322 | 40736 | 15-Mar-21 A | 2021-08-16 | 60% | PROF3 IO E.PROF3 IO E | 128.8 |  |  | 16294.4 | 16294.4 | 0
S270610 | Timing System Production: install timing system | 160 | 20849 | 2021-11-03 | 2021-12-10 | 0% | PROF3 IO E.PROF3 IO E | 160 |  |  | 20849 | 20849 | 0
S270710 | Timing System Production: commission timing system | 192 | 25019 | 2021-12-13 | 2022-01-11 | 0% | PROF3 IO E.PROF3 IO E | 192 |  |  | 25019 | 25019 | 0
1.07 Min Bias Trigger Detector
S273700 | Oversight of sPHENIX MBD Digitizers Procurement | 16 | 2762 | 2021-07-01 | 2021-12-02 | 0% | SCI3 PO.SCI3 PO | 16 |  |  | 2762 | 2762 | 0
Formulas:
Forecast Finish = VLOOKUP([Activity ID],'forecast data dump'!$A1:H3450,5,FALSE)
Forecast Start = VLOOKUP([Activity ID],'forecast data dump'!$A1:H3450,4,FALSE)

## ETC sheet-All incomplete (hidden)
Baseline data |  |  |  | Forecast Data (June status file)
Activity ID | Activity Name | Baseline Units | Baseline Cost | Forecast Start | Forecast Finish | % Complete | Resource ID Name | Calc ETC Units | Updated ETC Units | Potential PCR? | Calc ETC Cost | Updated ETC Cost | EAC Growth
B BNL Contributed Labor
1.01.02 Labor by FY
S103310 | Mgmt labor - B - BNL Contributed Labor - FY21 - CA-D Resource(s) | 880 | 154145 | 01-Oct-20 A | 30-Sep-21* | 74.3% | PROF5 AD.PROF5 AD | 226.16 |  |  | 39615.265 | 39615.265 | 0
S103510 | Mgmt labor - B - BNL Contributed Labor - FY22 - CA-D Resource(s) | 35 | 6351 | 01-Oct-21* | 2022-01-05 | 0% | PROF5 AD.PROF5 AD | 35 |  |  | 6351 | 6351 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 2965 | 628831 | 01-Oct-20 A | 30-Sep-21* | 74.3% | SCI4 PO.SCI 4 PO | 762.005 |  |  | 161609.567 | 161609.567 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 1896 | 291837 | 01-Oct-20 A | 30-Sep-21* | 74.3% | SCI2 PO.SCI2 PO | 487.272 |  |  | 75002.109 | 75002.109 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 100 | 15199 | 01-Oct-20 A | 30-Sep-21* | 74.3% | PROF4 PO M.PROF4 PO M | 25.7 |  |  | 3906.143 | 3906.143 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 468 | 81977 | 01-Oct-20 A | 30-Sep-21* | 74.3% | PROF5 PO M.PROF5 PO M | 120.276 |  |  | 21068.089 | 21068.089 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 1632 | 168465 | 01-Oct-20 A | 30-Sep-21* | 74.3% | PROF2 PO PC.PROF2 PO PC | 419.424 |  |  | 43295.505 | 43295.505 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 426 | 26656 | 01-Oct-20 A | 30-Sep-21* | 74.3% | ADMIN1 PO.ADMIN1 PO | 109.482 |  |  | 6850.592 | 6850.592 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 1613 | 376091 | 01-Oct-20 A | 30-Sep-21* | 74.3% | ADMIN7 PO.ADMIN7 PO | 414.541 |  |  | 96655.387 | 96655.387 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 4 | 626 | 01-Oct-21* | 2022-01-05 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 626 | 626 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 19 | 3377 | 01-Oct-21* | 2022-01-05 | 0% | PROF5 PO M.PROF5 PO M | 19 |  |  | 3377 | 3377 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 75 | 11891 | 01-Oct-21* | 2022-01-05 | 0% | SCI2 PO.SCI2 PO | 75 |  |  | 11891 | 11891 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 65 | 6941 | 01-Oct-21* | 2022-01-05 | 0% | PROF2 PO PC.PROF2 PO PC | 65 |  |  | 6941 | 6941 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 17 | 1098 | 01-Oct-21* | 2022-01-05 | 0% | ADMIN1 PO.ADMIN1 PO | 17 |  |  | 1098 | 1098 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 65 | 15494 | 01-Oct-21* | 2022-01-05 | 0% | ADMIN7 PO.ADMIN7 PO | 65 |  |  | 15494 | 15494 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 118 | 25777 | 01-Oct-21* | 2022-01-05 | 0% | SCI4 PO.SCI 4 PO | 118 |  |  | 25777 | 25777 | 0
1.02.01.02 TPC v2 Field Cage
S112200 | TPC Field Cage Safety Review | 4 | 688 | 2021-08-16 | 2021-08-18 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S112200 | TPC Field Cage Safety Review | 4 | 589 | 2021-08-16 | 2021-08-18 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 589 | 589 | 0
S112300 | Final Design Review - TPC Field Cage | 4 | 688 | 2021-08-19 | 2021-08-23 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S112300 | Final Design Review - TPC Field Cage | 4 | 589 | 2021-08-19 | 2021-08-23 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 589 | 589 | 0
S112100 | Benchtest TPC v2 Field Cage | 4 | 688 | 2021-08-02 | 2021-08-06 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S112100 | Benchtest TPC v2 Field Cage | 4 | 589 | 2021-08-02 | 2021-08-06 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 589 | 589 | 0
1.02.05.02 TPC FEE Prototype v2 (Pre-Production)
S137700 | Final Design Review, Production Readiness Review - TPC FEE | 4 | 589 | 13-Apr-20 A | 2021-07-28 | 95% | PROF4 PO M.PROF4 PO M | 0.2 |  |  | 29.45 | 29.45 | 0
S137700 | Final Design Review, Production Readiness Review - TPC FEE | 4 | 688 | 13-Apr-20 A | 2021-07-28 | 95% | SCI3 PO.SCI3 PO | 0.2 |  |  | 34.4 | 34.4 | 0
1.02.05.03 SAMPA chip 80 nsec
S140701 | Production Readiness Review for TPC FEE full production | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | PROF3 IO E.PROF3 IO E | 8 |  |  | 1012 | 1012 | 0
S140701 | Production Readiness Review for TPC FEE full production | 8 | 1178 | 2021-07-01 | 2021-07-01 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1178 | 1178 | 0
S140701 | Production Readiness Review for TPC FEE full production | 8 | 1377 | 2021-07-01 | 2021-07-01 | 0% | SCI3 PO.SCI3 PO | 8 |  |  | 1377 | 1377 | 0
1.02.06.03 TPC DAM Production
S147500 | TPC DAM Felix 2.0 Bandwidth test in 1008 | 320 | 48539 | 15-Mar-21 A | 2021-08-31 | 40% | PROF4 PO E.PROF4 PO E | 192 |  |  | 29123.4 | 29123.4 | 0
S147500 | TPC DAM Felix 2.0 Bandwidth test in 1008 | 67 | 11877 | 15-Mar-21 A | 2021-08-31 | 40% | SCI3 PO.SCI3 PO | 40.2 |  |  | 7126.2 | 7126.2 | 0
1.02.07.01 TPC Laser System
S148800 | TPC Laser System Safety Review | 4 | 572 | 22-Mar-21 A | 2021-07-22 | 20% | PROF4 PO M.PROF4 PO M | 3.2 |  |  | 457.6 | 457.6 | 0
S148800 | TPC Laser System Safety Review | 4 | 668 | 22-Mar-21 A | 2021-07-22 | 20% | SCI3 PO.SCI3 PO | 3.2 |  |  | 534.4 | 534.4 | 0
S148900 | Procurement Readiness Review - TPC Laser System | 4 | 572 | 22-Mar-21 A | 2021-07-30 | 50% | PROF4 PO M.PROF4 PO M | 2 |  |  | 286 | 286 | 0
S148900 | Procurement Readiness Review - TPC Laser System | 4 | 668 | 22-Mar-21 A | 2021-07-30 | 50% | SCI3 PO.SCI3 PO | 2 |  |  | 334 | 334 | 0
S150600 | Install & Test TPC lasers | 24 | 2739 | 2021-08-17 | 2021-08-19 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S150700 | Install &Test TPC Laser safety interlocks Labor | 64 | 11015 | 2021-08-20 | 2021-08-31 | 0% | SCI3 PO.SCI3 PO | 64 |  |  | 11015 | 11015 | 0
S150700 | Install &Test TPC Laser safety interlocks Labor | 64 | 9425 | 2021-08-20 | 2021-08-31 | 0% | PROF4 PO M.PROF4 PO M | 64 |  |  | 9425 | 9425 | 0
S150900 | Install &Test TPC Laser optics with mounts | 64 | 7304 | 2021-08-20 | 2021-08-31 | 0% | TECH3 PO M.TECH3 PO M | 64 |  |  | 7304 | 7304 | 0
S151000 | Install &Test TPC mirror bundles and supports | 24 | 2739 | 2021-09-01 | 2021-09-03 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
1.02.07.02 TPC Gas System
S153900 | Install and Test TPC Gas System Interlocks | 40 | 6067 | 2021-12-01 | 2021-12-07 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6067 | 6067 | 0
S153800 | Assemble and Plumb TPC Gas System | 440 | 51720 | 16-Mar-21 A | 2021-11-30 | 30% | TECH3 PO M.TECH3 PO M | 308 |  |  | 36204 | 36204 | 0
1.02.07.03 TPC Cooling System
S155100 | Install TPC Cooling System pumps | 24 | 2739 | 2021-07-01 | 2021-07-06 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S155200 | Install TPC Cooling System heat exchanger | 24 | 2739 | 2021-07-07 | 2021-07-09 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S155300 | Install TPC Cooling System PH control | 24 | 2739 | 2021-07-12 | 2021-07-14 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S155400 | Install TPC Cooling System end cap manifolds | 80 | 9130 | 2021-07-15 | 2021-07-28 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9130 | 9130 | 0
S155500 | Install TPC Cooling System tanks | 24 | 2739 | 2021-07-29 | 2021-08-02 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2739 | 2739 | 0
S155600 | Install TPC Cooling System plumbing Labor | 240 | 27453 | 2021-08-03 | 2021-09-14 | 0% | TECH3 PO M.TECH3 PO M | 240 |  |  | 27453 | 27453 | 0
S155800 | Set up TPC Cooling System computer controls Labor | 40 | 4702 | 2021-10-14 | 2021-10-20 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
S156000 | Set up and Test TPC Cooling System & Interlocks | 40 | 4702 | 2021-10-21 | 2021-10-27 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
1.03.02.02.03 EMCAL Final Module Fabrication
S187500 | Receive, unpack, log & inspect final blocks | 462 | 69911 | 23-Nov-20 A | 2022-01-31 | 58% | PROF4 PO E.PROF4 PO E | 194.04 |  |  | 29362.62 | 29362.62 | 0
S187500 | Receive, unpack, log & inspect final blocks | 922 | 108120 | 23-Nov-20 A | 2022-01-31 | 58% | TECH3 PO M.TECH3 PO M | 387.24 |  |  | 45410.4 | 45410.4 | 0
S187600 | Install light guides on final blocks Labor | 462 | 69926 | 21-Jan-21 A | 2022-01-31 | 35% | PROF4 PO E.PROF4 PO E | 300.3 |  |  | 45451.9 | 45451.9 | 0
S187600 | Install light guides on final blocks Labor | 922 | 108143 | 21-Jan-21 A | 2022-01-31 | 35% | TECH3 PO M.TECH3 PO M | 599.3 |  |  | 70292.95 | 70292.95 | 0
S187800 | Install reflectors on final blocks Labor | 462 | 69957 | 23-Nov-20 A | 2022-01-31 | 38% | PROF4 PO E.PROF4 PO E | 286.44 |  |  | 43373.34 | 43373.34 | 0
S187800 | Install reflectors on final blocks Labor | 922 | 108191 | 23-Nov-20 A | 2022-01-31 | 38% | TECH3 PO M.TECH3 PO M | 571.64 |  |  | 67078.42 | 67078.42 | 0
S188000 | Install SiPMs daughterboards on final blocks Labor | 462 | 70018 | 22-Jan-21 A | 2022-02-03 | 35% | PROF4 PO E.PROF4 PO E | 300.3 |  |  | 45511.7 | 45511.7 | 0
S188000 | Install SiPMs daughterboards on final blocks Labor | 922 | 108286 | 22-Jan-21 A | 2022-02-03 | 35% | TECH3 PO M.TECH3 PO M | 599.3 |  |  | 70385.9 | 70385.9 | 0
S188200 | Glue final blocks together into modules | 462 | 70049 | 22-Jan-21 A | 2022-02-03 | 33% | PROF4 PO E.PROF4 PO E | 309.54 |  |  | 46932.83 | 46932.83 | 0
S188200 | Glue final blocks together into modules | 922 | 108333 | 22-Jan-21 A | 2022-02-03 | 33% | TECH3 PO M.TECH3 PO M | 617.74 |  |  | 72583.11 | 72583.11 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S196200 | Build mechanical enclosures for final sectors | 720 | 84633 | 12-Jan-21 A | 2021-07-14 | 33% | TECH3 PO M.TECH3 PO M | 482.4 |  |  | 56704.11 | 56704.11 | 0
S196300 | Build mechanical fixtures for final sectors | 720 | 84017 | 12-Jan-21 A | 2021-07-14 | 45% | TECH3 PO M.TECH3 PO M | 396 |  |  | 46209.35 | 46209.35 | 0
S196400 | Build cooling system for final sectors | 180 | 27303 | 12-Jan-21 A | 2021-07-14 | 33% | PROF4 PO M.PROF4 PO M | 120.6 |  |  | 18293.01 | 18293.01 | 0
S196500 | Install modules in final sectors | 462 | 70145 | 26-Jan-21 A | 2022-02-03 | 33% | PROF4 PO E.PROF4 PO E | 309.54 |  |  | 46997.15 | 46997.15 | 0
S196500 | Install modules in final sectors | 1383 | 162722 | 26-Jan-21 A | 2022-02-03 | 33% | TECH3 PO M.TECH3 PO M | 926.61 |  |  | 109023.74 | 109023.74 | 0
S196700 | Install readout electronics on final sectors | 1383 | 162798 | 22-Feb-21 A | 2022-02-04 | 31% | TECH3 PO M.TECH3 PO M | 954.27 |  |  | 112330.62 | 112330.62 | 0
S196700 | Install readout electronics on final sectors | 462 | 70178 | 22-Feb-21 A | 2022-02-04 | 31% | PROF4 PO E.PROF4 PO E | 318.78 |  |  | 48422.82 | 48422.82 | 0
S196800 | Install cables & cooling system on final sectors | 462 | 70198 | 22-Feb-21 A | 2022-02-04 | 31% | PROF4 PO E.PROF4 PO E | 318.78 |  |  | 48436.62 | 48436.62 | 0
S196800 | Install cables & cooling system on final sectors | 1728 | 262557 | 22-Feb-21 A | 2022-02-04 | 31% | PROF4 PO M.PROF4 PO M | 1192.32 |  |  | 181164.33 | 181164.33 | 0
S196800 | Install cables & cooling system on final sectors | 1383 | 162845 | 22-Feb-21 A | 2022-02-04 | 31% | TECH3 PO M.TECH3 PO M | 954.27 |  |  | 112363.05 | 112363.05 | 0
1.05.02.02 EMCal Electronics: Production
S229405 | Test EMCal Preamp Boards: Production Sectors 13-64 - Contributed Labor | 96 | 11284 | 29-Mar-21 A | 2021-07-14 | 40% | TECH3 PO E.TECH3 PO E | 57.6 |  |  | 6770.4 | 6770.4 | 0
S229405 | Test EMCal Preamp Boards: Production Sectors 13-64 - Contributed Labor | 153 | 19937 | 29-Mar-21 A | 2021-07-14 | 40% | PROF3 PO E.PROF3 PO E | 91.8 |  |  | 11962.2 | 11962.2 | 0
1.06.01.03 DAQ Production
S256800 | DAQ Production: Crate installation | 32 | 4854 | 07-Dec-20 A | 2021-12-17 | 30% | PROF4 PO M.PROF4 PO M | 22.4 |  |  | 3397.8 | 3397.8 | 0
S256800 | DAQ Production: Crate installation | 32 | 5673 | 07-Dec-20 A | 2021-12-17 | 30% | SCI3 PO.SCI3 PO | 22.4 |  |  | 3971.1 | 3971.1 | 0
S256800 | DAQ Production: Crate installation | 512 | 60183 | 07-Dec-20 A | 2021-12-17 | 30% | TECH3 PO M.TECH3 PO M | 358.4 |  |  | 42128.1 | 42128.1 | 0
S256800 | DAQ Production: Crate installation | 32 | 4122 | 07-Dec-20 A | 2021-12-17 | 30% | CRAFT3.CRAFT3 | 22.4 |  |  | 2885.4 | 2885.4 | 0
S258600 | DAQ Production: Procure jSEB Slow control computers | 80 | 11781 | 20-Jul-20 A | 2021-07-30 | 50% | PROF4 PO M.PROF4 PO M | 40 |  |  | 5890.5 | 5890.5 | 0
S258600 | DAQ Production: Procure jSEB Slow control computers | 80 | 13768 | 20-Jul-20 A | 2021-07-30 | 50% | SCI3 PO.SCI3 PO | 40 |  |  | 6884 | 6884 | 0
S260500 | DAQ Production: Modify and Debug event builder software | 320 | 48539 | 26-Apr-21 A | 2021-08-25 | 90% | PROF4 PO M.PROF4 PO M | 32 |  |  | 4853.9 | 4853.9 | 0
S260500 | DAQ Production: Modify and Debug event builder software | 320 | 56726 | 26-Apr-21 A | 2021-08-25 | 90% | SCI3 PO.SCI3 PO | 32 |  |  | 5672.6 | 5672.6 | 0
S260400 | DAQ Production: Setting up the switches | 56 | 8494 | 12-Feb-21 A | 2021-07-30 | 80% | PROF4 PO M.PROF4 PO M | 11.2 |  |  | 1698.8 | 1698.8 | 0
S260400 | DAQ Production: Setting up the switches | 88 | 15600 | 12-Feb-21 A | 2021-07-30 | 80% | SCI3 PO.SCI3 PO | 17.6 |  |  | 3120 | 3120 | 0
S260400 | DAQ Production: Setting up the switches | 44 | 5172 | 12-Feb-21 A | 2021-07-30 | 80% | TECH3 PO M.TECH3 PO M | 8.8 |  |  | 1034.4 | 1034.4 | 0
S260700 | DAQ Production: Internal Readiness Review | 80 | 12135 | 2022-01-19 | 2022-02-01 | 0% | PROF4 PO M.PROF4 PO M | 80 |  |  | 12135 | 12135 | 0
S260700 | DAQ Production: Internal Readiness Review | 240 | 42545 | 2022-01-19 | 2022-02-01 | 0% | SCI3 PO.SCI3 PO | 240 |  |  | 42545 | 42545 | 0
S258800 | Production jSEB Slow control computers - Setup Machines | 40 | 6884 | 2021-08-09 | 2021-08-13 | 0% | SCI3 PO.SCI3 PO | 40 |  |  | 6884 | 6884 | 0
S259600 | Production Buffer Boxes - Setup Machines | 40 | 7091 | 23-Nov-20 A | 2021-11-05 | 16% | SCI3 PO.SCI3 PO | 33.6 |  |  | 5956.44 | 5956.44 | 0
1.06.03.02 GL1 Trigger Prototype
S266701 | Final Design Review - DAQ Global Level-1 | 4 | 506 | 2021-07-01 | 2021-07-01 | 0% | PROF3 IO E.PROF3 IO E | 4 |  |  | 506 | 506 | 0
S266701 | Final Design Review - DAQ Global Level-1 | 4 | 688 | 2021-07-01 | 2021-07-01 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S266701 | Final Design Review - DAQ Global Level-1 | 4 | 0 | 2021-07-01 | 2021-07-01 | 0% | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 |  |  | 0 | 0 | 0
S266701 | Final Design Review - DAQ Global Level-1 | 4 | 824 | 2021-07-01 | 2021-07-01 | 0% | SCI4 PO.SCI 4 PO | 4 |  |  | 824 | 824 | 0
S266701 | Final Design Review - DAQ Global Level-1 | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1012 | 1012 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 4 | 506 | 2021-07-01 | 2021-07-01 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 506 | 506 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | PROF3 IO E.PROF3 IO E | 8 |  |  | 1012 | 1012 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 4 | 688 | 2021-07-01 | 2021-07-01 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 4 | 0 | 2021-07-01 | 2021-07-01 | 0% | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 |  |  | 0 | 0 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 4 | 824 | 2021-07-01 | 2021-07-01 | 0% | SCI4 PO.SCI 4 PO | 4 |  |  | 824 | 824 | 0
1.06.03.03 GL1 Trigger Production
S268100 | GL1 Production: additional firmware improvements | 156 | 20328 | 2022-01-20 | 2022-02-04 | 0% | PROF3 PO E.PROF3 PO E | 156 |  |  | 20328 | 20328 | 0
S268010 | GL1 Production: commission GL1 system | 108 | 14073 | 2021-12-06 | 2022-01-19 | 0% | PROF3 IO E.PROF3 IO E | 108 |  |  | 14073 | 14073 | 0
1.06.04.02 Timing System Prototype
S269501 | Final Design Review - DAQ Timing System | 8 | 1012 | 2021-08-02 | 2021-08-02 | 0% | PROF3 IO E.PROF3 IO E | 8 |  |  | 1012 | 1012 | 0
S269501 | Final Design Review - DAQ Timing System | 4 | 506 | 2021-08-02 | 2021-08-02 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 506 | 506 | 0
S269501 | Final Design Review - DAQ Timing System | 4 | 688 | 2021-08-02 | 2021-08-02 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S269501 | Final Design Review - DAQ Timing System | 4 | 0 | 2021-08-02 | 2021-08-02 | 0% | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 |  |  | 0 | 0 | 0
S269501 | Final Design Review - DAQ Timing System | 4 | 824 | 2021-08-02 | 2021-08-02 | 0% | SCI4 PO.SCI 4 PO | 4 |  |  | 824 | 824 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 4 | 824 | 2021-07-30 | 2021-07-30 | 0% | SCI4 PO.SCI 4 PO | 4 |  |  | 824 | 824 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 4 | 688 | 2021-07-30 | 2021-07-30 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 688 | 688 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 4 | 0 | 2021-07-30 | 2021-07-30 | 0% | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 |  |  | 0 | 0 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 4 | 506 | 2021-07-30 | 2021-07-30 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 506 | 506 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | 8 | 1012 | 2021-07-30 | 2021-07-30 | 0% | PROF3 IO E.PROF3 IO E | 8 |  |  | 1012 | 1012 | 0
1.06.04.03 Timing System Production
S270600 | Timing System Production: install timing system | 80 | 10424 | 2021-11-03 | 2021-12-10 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10424 | 10424 | 0
S270600 | Timing System Production: install timing system | 40 | 7091 | 2021-11-03 | 2021-12-10 | 0% | SCI3 PO.SCI3 PO | 40 |  |  | 7091 | 7091 | 0
S270600 | Timing System Production: install timing system | 320 | 37615 | 2021-11-03 | 2021-12-10 | 0% | TECH3 PO E.TECH3 PO E | 320 |  |  | 37615 | 37615 | 0
S270510 | Timing System Production: final firmware updates | 322 | 40736 | 15-Mar-21 A | 2021-08-16 | 60% | PROF3 IO E.PROF3 IO E | 128.8 |  |  | 16294.4 | 16294.4 | 0
S270610 | Timing System Production: install timing system | 160 | 20849 | 2021-11-03 | 2021-12-10 | 0% | PROF3 IO E.PROF3 IO E | 160 |  |  | 20849 | 20849 | 0
S270710 | Timing System Production: commission timing system | 192 | 25019 | 2021-12-13 | 2022-01-11 | 0% | PROF3 IO E.PROF3 IO E | 192 |  |  | 25019 | 25019 | 0
1.07 Min Bias Trigger Detector
S273700 | Oversight of sPHENIX MBD Digitizers Procurement | 16 | 2762 | 2021-07-01 | 2021-12-02 | 0% | SCI3 PO.SCI3 PO | 16 |  |  | 2762 | 2762 | 0
C Infrastructure / Facility Upgrade
2.01.02 Magnet Management and Technical Oversight
S274700 | 2021 Magnet Project Management | 880 | 155997 | 01-Oct-20 A | 2021-09-30 | 74.4% | SCI3 AD.SCI3 AD | 225.28 |  |  | 39935.232 | 39935.232 | 0
S274800 | 2022 Magnet Project Management | 880 | 160676 | 2021-10-01 | 2022-09-30 | 0% | SCI3 AD.SCI3 AD | 880 |  |  | 160676 | 160676 | 0
S275800 | 2021 PS & Quench Protection L3 Project Management | 352 | 61658 | 01-Oct-20 A | 2021-09-30 | 74.4% | PROF5 AD.PROF5 AD | 90.112 |  |  | 15784.448 | 15784.448 | 0
S275900 | 2022 PS & Quench Protection L3 Project Management | 352 | 63508 | 2021-10-01 | 2022-09-30 | 0% | PROF5 AD.PROF5 AD | 352 |  |  | 63508 | 63508 | 0
2.01.04 Infrastructure Management
S276300 | 2021 Infrastructure Project Management | 890 | 144577 | 01-Oct-20 A | 2021-09-30 | 74.4% | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 227.84 |  |  | 37011.712 | 37011.712 | 0
S276300 | 2021 Infrastructure Project Management | 860 | 112062 | 01-Oct-20 A | 2021-09-30 | 74.4% | PROF3 PO E.PROF3 PO E | 220.16 |  |  | 28687.872 | 28687.872 | 0
S276400 | 2022 Infrastructure Project Management | 800 | 107371 | 2021-10-01 | 2022-09-30 | 0% | PROF3 PO E.PROF3 PO E | 800 |  |  | 107371 | 107371 | 0
S276900 | 2021 Facility Support Systems L3 Project Management | 352 | 36335 | 01-Oct-20 A | 2021-09-30 | 74.4% | PROF2 AD.PROF2 AD | 90.112 |  |  | 9301.76 | 9301.76 | 0
S277500 | 2021 Detector Support Systems L3 Project Management | 440 | 66741 | 01-Oct-20 A | 2021-09-30 | 74.4% | PROF4 PO E.PROF4 PO E | 112.64 |  |  | 17085.696 | 17085.696 | 0
S277500 | 2021 Detector Support Systems L3 Project Management | 352 | 45867 | 01-Oct-20 A | 2021-09-30 | 74.4% | PROF3 PO E.PROF3 PO E | 90.112 |  |  | 11741.952 | 11741.952 | 0
S276500 | 2023 Infrastructure Project Management | 40 | 5530 | 2022-10-03 | 2022-10-07 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5530 | 5530 | 0
2.01.05 Installation Management
S278100 | 2021 Integration & Installation Project Management | 880 | 154145 | 02-Oct-20 A | 2021-09-30 | 74.4% | PROF5 PO M.PROF5 PO M | 225.28 |  |  | 39461.12 | 39461.12 | 0
S278100 | 2021 Integration & Installation Project Management | 440 | 57334 | 02-Oct-20 A | 2021-09-30 | 74.4% | PROF3 PO E.PROF3 PO E | 112.64 |  |  | 14677.504 | 14677.504 | 0
S278100 | 2021 Integration & Installation Project Management | 440 | 77998 | 02-Oct-20 A | 2021-09-30 | 74.4% | SCI3 PO.SCI3 PO | 112.64 |  |  | 19967.488 | 19967.488 | 0
S278200 | 2022 Integration & Installation Project Management | 880 | 158770 | 2021-10-01 | 2022-09-30 | 0% | PROF5 PO M.PROF5 PO M | 880 |  |  | 158770 | 158770 | 0
S278300 | 2023 Integration & Installation Project Management | 282 | 52405 | 2022-10-03 | 2022-10-05 | 0% | PROF5 PO M.PROF5 PO M | 282 |  |  | 52405 | 52405 | 0
2.02.01.01 Safety Reviews
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 16 | 2921 | 08-Mar-21 A | 2022-05-04 | 50% | SCI3 AD.SCI3 AD | 8 |  |  | 1460.5 | 1460.5 | 0
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 8 | 1250 | 08-Mar-21 A | 2022-05-04 | 50% | PROF4 AM.PROF4 AM | 4 |  |  | 625 | 625 | 0
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 16 | 3276 | 08-Mar-21 A | 2022-05-04 | 50% | PROF6 AD.PROF6 AD | 8 |  |  | 1638 | 1638 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | 16 | 2921 | 2022-04-28 | 2022-04-28 | 0% | SCI3 AD.SCI3 AD | 16 |  |  | 2921 | 2921 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | 8 | 1250 | 2022-04-28 | 2022-04-28 | 0% | PROF4 AM.PROF4 AM | 8 |  |  | 1250 | 1250 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | 16 | 3276 | 2022-04-28 | 2022-04-28 | 0% | PROF6 AD.PROF6 AD | 16 |  |  | 3276 | 3276 | 0
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 2921 | 2022-04-29 | 2022-04-29 | 0% | SCI3 AD.SCI3 AD | 16 |  |  | 2921 | 2921 | 0
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 3276 | 2022-04-29 | 2022-04-29 | 0% | PROF6 AD.PROF6 AD | 16 |  |  | 3276 | 3276 | 0
2.02.01.02 Cooldown & Power Tests
S279100 | Cooldown | 60 | 8053 | 2022-05-05 | 2022-05-25 | 0% | PROF3 AD.PROF3 AD | 60 |  |  | 8053 | 8053 | 0
S279100 | Cooldown | 60 | 7264 | 2022-05-05 | 2022-05-25 | 0% | TECH3 AD.TECH3 AD | 60 |  |  | 7264 | 7264 | 0
S279100 | Cooldown | 60 | 12285 | 2022-05-05 | 2022-05-25 | 0% | PROF6 AD.PROF6 AD | 60 |  |  | 12285 | 12285 | 0
S279200 | 4.5K Static Heat Load test | 8 | 1074 | 2022-05-26 | 2022-05-27 | 0% | PROF3 AD.PROF3 AD | 8 |  |  | 1074 | 1074 | 0
S279200 | 4.5K Static Heat Load test | 8 | 969 | 2022-05-26 | 2022-05-27 | 0% | TECH3 AD.TECH3 AD | 8 |  |  | 969 | 969 | 0
S279200 | 4.5K Static Heat Load test | 8 | 1638 | 2022-05-26 | 2022-05-27 | 0% | PROF6 AD.PROF6 AD | 8 |  |  | 1638 | 1638 | 0
S279300 | 4.5K Low power test | 20 | 2684 | 2022-05-31 | 2022-06-06 | 0% | PROF3 AD.PROF3 AD | 20 |  |  | 2684 | 2684 | 0
S279300 | 4.5K Low power test | 80 | 14607 | 2022-05-31 | 2022-06-06 | 0% | SCI3 AD.SCI3 AD | 80 |  |  | 14607 | 14607 | 0
S279300 | 4.5K Low power test | 80 | 9686 | 2022-05-31 | 2022-06-06 | 0% | TECH3 AD.TECH3 AD | 80 |  |  | 9686 | 9686 | 0
S279300 | 4.5K Low power test | 80 | 16380 | 2022-05-31 | 2022-06-06 | 0% | PROF6 AD.PROF6 AD | 80 |  |  | 16380 | 16380 | 0
S279400 | 4.5K High Power Test | 20 | 2684 | 2022-06-07 | 2022-06-13 | 0% | PROF3 AD.PROF3 AD | 20 |  |  | 2684 | 2684 | 0
S279400 | 4.5K High Power Test | 80 | 14607 | 2022-06-07 | 2022-06-13 | 0% | SCI3 AD.SCI3 AD | 80 |  |  | 14607 | 14607 | 0
S279400 | 4.5K High Power Test | 80 | 9686 | 2022-06-07 | 2022-06-13 | 0% | TECH3 AD.TECH3 AD | 80 |  |  | 9686 | 9686 | 0
S279400 | 4.5K High Power Test | 80 | 16380 | 2022-06-07 | 2022-06-13 | 0% | PROF6 AD.PROF6 AD | 80 |  |  | 16380 | 16380 | 0
2.02.02 Magnet Transport & Assembly
S281400 | Magnet and Solenoid Valvebox - Reinstall | 400 | 48260 | 2021-10-12 | 2021-11-16 | 0% | TECH3 AM.TECH3 AM | 400 |  |  | 48260 | 48260 | 0
S281400 | Magnet and Solenoid Valvebox - Reinstall | 40 | 6227 | 2021-10-12 | 2021-11-16 | 0% | PROF4 AM.PROF4 AM | 40 |  |  | 6227 | 6227 | 0
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | 160 | 19372 | 2021-11-17 | 2021-12-02 | 0% | TECH3 AM.TECH3 AM | 160 |  |  | 19372 | 19372 | 0
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | 16 | 2500 | 2021-11-17 | 2021-12-02 | 0% | PROF4 AM.PROF4 AM | 16 |  |  | 2500 | 2500 | 0
2.02.03.01.04.02.01 IP8 Cold Box
S1006280 | BNL review for PDR approval | 31313 | 34933 | 2021-07-16 | 2021-07-29 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 31313 |  |  | 34933 | 34933 | 0
S1006440 | AET submits FDR report to BNL for approval | 125253 | 139734 | 2021-08-20 | 2021-09-17 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 125253 |  |  | 139734 | 139734 | 0
S1006400 | BNL review for IDR approval | 31313 | 34933 | 2021-08-13 | 2021-08-19 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 31313 |  |  | 34933 | 34933 | 0
2.02.03.01.04.02.02 Three Manifold Jumper Transfer Lines
S1006680 | BNL review for PDR approval | 23485 | 26200 | 2021-07-30 | 2021-08-05 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 |  |  | 26200 | 26200 | 0
S1006800 | AET submits FDR report to BNL for approval | 93940 | 104800 | 2021-08-20 | 2021-09-02 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 93940 |  |  | 104800 | 104800 | 0
S1006760 | BNL review for IDR approval | 23485 | 26200 | 2021-08-13 | 2021-08-19 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 |  |  | 26200 | 26200 | 0
2.02.03.01.04.02.03 Three Solenoid Valve Box Transfer Lines
S1007000 | BNL review for PDR approval | 23485 | 26200 | 2021-11-24 | 2021-12-02 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 |  |  | 26200 | 26200 | 0
S1007120 | AET submits FDR report to BNL for approval | 93940 | 104800 | 2021-12-17 | 2021-12-23 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 93940 |  |  | 104800 | 104800 | 0
S1007080 | BNL review for IDR approval | 23485 | 26200 | 2021-12-10 | 2021-12-16 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 |  |  | 26200 | 26200 | 0
S1007240 | Delivery of all three Solenoid Valve Box Transfer Lines and two 4" & 5" NPS Field Joint Sleeves | 203536 | 240966 | 2022-02-02 | 2022-02-08 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 203536 |  |  | 240966 | 240966 | 0
S1007280 | Approval of all Data/Documentation/ Reports | 78283 | 87334 | 2022-02-09 | 2022-02-15 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 78283 |  |  | 87334 | 87334 | 0
2.02.03.01.04.04 Vendor Engineering and Design
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 240 | 30692 | 02-Dec-19 A | 2021-11-30 | 76% | PROF3 AD.PROF3 AD | 57.6 |  |  | 7366.08 | 7366.08 | 0
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 54 | 6230 | 02-Dec-19 A | 2021-11-30 | 76% | TECH3 AD.TECH3 AD | 12.96 |  |  | 1495.2 | 1495.2 | 0
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 207 | 40384 | 02-Dec-19 A | 2021-11-30 | 76% | PROF6 AD.PROF6 AD | 49.68 |  |  | 9692.16 | 9692.16 | 0
2.02.03.01.06 Installation
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 20 | 2606 | 2021-07-01 | 2021-07-08 | 0% | PROF3 AD.PROF3 AD | 20 |  |  | 2606 | 2606 | 0
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 20 | 2351 | 2021-07-01 | 2021-07-08 | 0% | TECH3 AD.TECH3 AD | 20 |  |  | 2351 | 2351 | 0
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 40 | 5153 | 2021-07-01 | 2021-07-08 | 0% | CRAFT3.CRAFT3 | 40 |  |  | 5153 | 5153 | 0
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 8 | 1590 | 2021-07-01 | 2021-07-08 | 0% | PROF6 AD.PROF6 AD | 8 |  |  | 1590 | 1590 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 24 | 3127 | 2021-07-09 | 2021-08-19 | 0% | PROF3 AD.PROF3 AD | 24 |  |  | 3127 | 3127 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 360 | 42316 | 2021-07-09 | 2021-08-19 | 0% | TECH3 AD.TECH3 AD | 360 |  |  | 42316 | 42316 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 180 | 23188 | 2021-07-09 | 2021-08-19 | 0% | CRAFT3.CRAFT3 | 180 |  |  | 23188 | 23188 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 40 | 4702 | 2021-07-09 | 2021-08-19 | 0% | TECH3 AD.TECH3 AD | 40 |  |  | 4702 | 4702 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 24 | 4771 | 2021-07-09 | 2021-08-19 | 0% | PROF6 AD.PROF6 AD | 24 |  |  | 4771 | 4771 | 0
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | 12 | 1611 | 2022-01-11 | 2022-02-08 | 0% | PROF3 AD.PROF3 AD | 12 |  |  | 1611 | 1611 | 0
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | 40 | 4843 | 2022-01-11 | 2022-02-08 | 0% | TECH3 AD.TECH3 AD | 40 |  |  | 4843 | 4843 | 0
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | 12 | 2457 | 2022-01-11 | 2022-02-08 | 0% | PROF6 AD.PROF6 AD | 12 |  |  | 2457 | 2457 | 0
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | 80 | 10737 | 2022-03-30 | 2022-04-12 | 0% | PROF3 AD.PROF3 AD | 80 |  |  | 10737 | 10737 | 0
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | 120 | 14529 | 2022-03-30 | 2022-04-12 | 0% | TECH3 AD.TECH3 AD | 120 |  |  | 14529 | 14529 | 0
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | 80 | 16380 | 2022-03-30 | 2022-04-12 | 0% | PROF6 AD.PROF6 AD | 80 |  |  | 16380 | 16380 | 0
S287600 | RHIC Helium Interface - Final pump and purge | 24 | 3221 | 2022-04-13 | 2022-04-26 | 0% | PROF3 AD.PROF3 AD | 24 |  |  | 3221 | 3221 | 0
S287600 | RHIC Helium Interface - Final pump and purge | 120 | 14529 | 2022-04-13 | 2022-04-26 | 0% | TECH3 AD.TECH3 AD | 120 |  |  | 14529 | 14529 | 0
S287600 | RHIC Helium Interface - Final pump and purge | 4 | 819 | 2022-04-13 | 2022-04-26 | 0% | PROF6 AD.PROF6 AD | 4 |  |  | 819 | 819 | 0
2.02.03.02.04.01 Vendor Engineering and Design
S289500 | Engineering Support for Procure LN2 supply transfer line system | 36 | 6948 | 02-Dec-20 A | 2021-08-16 | 88% | PROF6 AD.PROF6 AD | 4.32 |  |  | 833.76 | 833.76 | 0
2.02.03.02.04.02 Vendor Fabrication
S291100 | (LN2 supply transfer line system) Final assemblies | 0 | 0 | 2021-08-17 | 2021-09-28 | 0% | PROF6 AD.PROF6 AD | 0 |  |  | 0 | 0 | 0
S291200 | (LN2 supply transfer line system) BNL Holdpoint witness | 0 | 0 | 2021-09-29 | 2021-09-29 | 0% | PROF6 AD.PROF6 AD | 0 |  |  | 0 | 0 | 0
S291300 | (LN2 supply transfer line system) Shipping Labor | 0 | 0 | 2021-09-30 | 2021-10-19 | 0% | PROF6 AD.PROF6 AD | 0 |  |  | 0 | 0 | 0
S291500 | Procure LN2 supply transfer line system - Final Docs Package | 107261 | 119662 | 20-Oct-21* | 2021-10-20 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 107261 |  |  | 119662 | 119662 | 0
2.02.03.02.05 Delivery and receiving, LN2 Supply Transfer Line System
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | 5 | 652 | 2021-10-20 | 2021-10-20 | 0% | PROF3 AD.PROF3 AD | 5 |  |  | 652 | 652 | 0
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | 16 | 2061 | 2021-10-20 | 2021-10-20 | 0% | CRAFT3.CRAFT3 | 16 |  |  | 2061 | 2061 | 0
S291700 | (LN2 supply transfer line system) Inspection | 1 | 199 | 2021-10-21 | 2021-10-21 | 0% | PROF6 AD.PROF6 AD | 1 |  |  | 199 | 199 | 0
2.02.03.02.06 Installation, LN2 Supply Transfer Line System
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | 48 | 6072 | 17-May-21 A | 2021-07-20 | 3% | PROF3 AD.PROF3 AD | 46.56 |  |  | 5889.84 | 5889.84 | 0
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | 40 | 4565 | 17-May-21 A | 2021-07-20 | 3% | TECH3 AD.TECH3 AD | 38.8 |  |  | 4428.05 | 4428.05 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 16 | 2085 | 2021-10-22 | 2021-11-04 | 0% | PROF3 AD.PROF3 AD | 16 |  |  | 2085 | 2085 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 240 | 28211 | 2021-10-22 | 2021-11-04 | 0% | TECH3 AD.TECH3 AD | 240 |  |  | 28211 | 28211 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 16 | 2061 | 2021-10-22 | 2021-11-04 | 0% | CRAFT3.CRAFT3 | 16 |  |  | 2061 | 2061 | 0
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | 24 | 3127 | 2021-11-05 | 2021-11-30 | 0% | PROF3 AD.PROF3 AD | 24 |  |  | 3127 | 3127 | 0
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | 96 | 11284 | 2021-11-05 | 2021-11-30 | 0% | TECH3 AD.TECH3 AD | 96 |  |  | 11284 | 11284 | 0
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | 20 | 2606 | 2021-12-01 | 2021-12-14 | 0% | PROF3 AD.PROF3 AD | 20 |  |  | 2606 | 2606 | 0
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | 64 | 7523 | 2021-12-01 | 2021-12-14 | 0% | TECH3 AD.TECH3 AD | 64 |  |  | 7523 | 7523 | 0
S292120 | Welding LN2 Segment #1 to LN2 Dewar | 80 | 10306 | 2021-11-05 | 2021-11-19 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10306 | 10306 | 0
2.02.03.03.01 Engineering and Design, Warm Piping System
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | 19 | 2404 | 02-Dec-19 A | 2021-08-30 | 85% | PROF3 AD.PROF3 AD | 2.85 |  |  | 360.6 | 360.6 | 0
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | 38 | 7334 | 02-Dec-19 A | 2021-08-30 | 85% | PROF6 AD.PROF6 AD | 5.7 |  |  | 1100.1 | 1100.1 | 0
2.02.03.03.02.01 Warm Piping tie in to WR header
S292800 | (Warm Piping tie in to WR header) General Arrangement Layout | 20 | 2530 | 03-Aug-20 A | 2021-07-20 | 97% | PROF3 AD.PROF3 AD | 0.6 |  |  | 75.9 | 75.9 | 0
S292800 | (Warm Piping tie in to WR header) General Arrangement Layout | 80 | 15439 | 03-Aug-20 A | 2021-07-20 | 97% | PROF6 AD.PROF6 AD | 2.4 |  |  | 463.17 | 463.17 | 0
S292900 | (Warm Piping tie in to WR header) Detailed drawing package with weld map | 16 | 2024 | 17-Nov-20 A | 2021-07-22 | 82% | PROF3 AD.PROF3 AD | 2.88 |  |  | 364.32 | 364.32 | 0
S292900 | (Warm Piping tie in to WR header) Detailed drawing package with weld map | 16 | 3088 | 17-Nov-20 A | 2021-07-22 | 82% | PROF6 AD.PROF6 AD | 2.88 |  |  | 555.84 | 555.84 | 0
2.02.03.03.02.04 Warm Piping for Summer 80K Hold Helium Compressor Loop
S293500 | (Current Leads Warm Piping) Detailed drawing package with weld map | 26 | 3289 | 16-Dec-19 A | 2021-07-30 | 85% | PROF3 AD.PROF3 AD | 3.9 |  |  | 493.35 | 493.35 | 0
S293500 | (Current Leads Warm Piping) Detailed drawing package with weld map | 128 | 24703 | 16-Dec-19 A | 2021-07-30 | 85% | PROF6 AD.PROF6 AD | 19.2 |  |  | 3705.45 | 3705.45 | 0
2.02.03.03.03 Procurement of Materials, Warm Piping System
S294500 | Procure Warm Piping and fittings - Delivery acceptance | 32000 | 37142 | 14-Jun-21 A | 2021-08-04 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 16000 |  |  | 18571 | 18571 | 0
2.02.03.03.04 Installation: Warm Piping Systems
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | 144 | 18764 | 2021-08-31 | 2022-01-12 | 0% | PROF3 AD.PROF3 AD | 144 |  |  | 18764 | 18764 | 0
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | 360 | 42316 | 2021-08-31 | 2022-01-12 | 0% | TECH3 AD.TECH3 AD | 360 |  |  | 42316 | 42316 | 0
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | 240 | 30918 | 2021-08-31 | 2022-01-12 | 0% | CRAFT3.CRAFT3 | 240 |  |  | 30918 | 30918 | 0
S294840 | (Warm Piping System) Remaining outside /1008B/Westwall work (between run21 and run22) | 36 | 4691 | 2021-07-09 | 2021-08-19 | 0% | PROF3 AD.PROF3 AD | 36 |  |  | 4691 | 4691 | 0
S294840 | (Warm Piping System) Remaining outside /1008B/Westwall work (between run21 and run22) | 180 | 21158 | 2021-07-09 | 2021-08-19 | 0% | TECH3 AD.TECH3 AD | 180 |  |  | 21158 | 21158 | 0
S294840 | (Warm Piping System) Remaining outside /1008B/Westwall work (between run21 and run22) | 40 | 5153 | 2021-07-09 | 2021-08-19 | 0% | CRAFT3.CRAFT3 | 40 |  |  | 5153 | 5153 | 0
S295000 | (Warm Piping System) Pressure and leak check | 32 | 4295 | 2022-04-13 | 2022-04-19 | 0% | PROF3 AD.PROF3 AD | 32 |  |  | 4295 | 4295 | 0
S295000 | (Warm Piping System) Pressure and leak check | 32 | 3874 | 2022-04-13 | 2022-04-19 | 0% | TECH3 AD.TECH3 AD | 32 |  |  | 3874 | 3874 | 0
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | 20 | 2684 | 2022-01-26 | 2022-02-08 | 0% | PROF3 AD.PROF3 AD | 20 |  |  | 2684 | 2684 | 0
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | 64 | 7749 | 2022-01-26 | 2022-02-08 | 0% | TECH3 AD.TECH3 AD | 64 |  |  | 7749 | 7749 | 0
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | 32 | 4295 | 2022-04-20 | 2022-04-26 | 0% | PROF3 AD.PROF3 AD | 32 |  |  | 4295 | 4295 | 0
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | 32 | 3874 | 2022-04-20 | 2022-04-26 | 0% | TECH3 AD.TECH3 AD | 32 |  |  | 3874 | 3874 | 0
S295300 | (Warm Piping System) Vacuum Pumping System installation | 8 | 1074 | 2022-01-26 | 2022-02-01 | 0% | PROF3 AD.PROF3 AD | 8 |  |  | 1074 | 1074 | 0
S295300 | (Warm Piping System) Vacuum Pumping System installation | 38 | 4601 | 2022-01-26 | 2022-02-01 | 0% | TECH3 AD.TECH3 AD | 38 |  |  | 4601 | 4601 | 0
S294860 | (Warm Piping System) Assembly hall work on Platform | 18 | 2416 | 2022-01-04 | 2022-01-25 | 0% | PROF3 AD.PROF3 AD | 18 |  |  | 2416 | 2416 | 0
S294860 | (Warm Piping System) Assembly hall work on Platform | 90 | 10896 | 2022-01-04 | 2022-01-25 | 0% | TECH3 AD.TECH3 AD | 90 |  |  | 10896 | 10896 | 0
S294860 | (Warm Piping System) Assembly hall work on Platform | 20 | 2654 | 2022-01-04 | 2022-01-25 | 0% | CRAFT3.CRAFT3 | 20 |  |  | 2654 | 2654 | 0
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 18 | 2416 | 2022-03-30 | 2022-04-19 | 0% | PROF3 AD.PROF3 AD | 18 |  |  | 2416 | 2416 | 0
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 90 | 10896 | 2022-03-30 | 2022-04-19 | 0% | TECH3 AD.TECH3 AD | 90 |  |  | 10896 | 10896 | 0
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 20 | 2654 | 2022-03-30 | 2022-04-19 | 0% | CRAFT3.CRAFT3 | 20 |  |  | 2654 | 2654 | 0
2.02.03.04.01 Engineering and Design
S295500 | (Controls Hardware) Wire diagram drawings | 128 | 14608 | 19-Apr-21 A | 2021-09-28 | 25% | TECH3 AD.TECH3 AD | 96 |  |  | 10956 | 10956 | 0
S295600 | (Controls Hardware) Power distribution drawings | 40 | 4565 | 15-Feb-21 A | 2021-10-27 | 25% | TECH3 AD.TECH3 AD | 30 |  |  | 3423.75 | 3423.75 | 0
S295700 | (Controls Hardware) I/O list table | 48 | 6072 | 07-Aug-20 A | 2021-07-23 | 90% | PROF3 AD.PROF3 AD | 4.8 |  |  | 607.2 | 607.2 | 0
S295700 | (Controls Hardware) I/O list table | 48 | 5478 | 07-Aug-20 A | 2021-07-23 | 90% | TECH3 AD.TECH3 AD | 4.8 |  |  | 547.8 | 547.8 | 0
S295401 | (Controls Hardware) Cryo instrument and equipment specifications 70% | 84 | 10627 | 01-Oct-19 A | 2021-07-28 | 91% | PROF3 AD.PROF3 AD | 7.56 |  |  | 956.43 | 956.43 | 0
S295401 | (Controls Hardware) Cryo instrument and equipment specifications 70% | 84 | 12370 | 01-Oct-19 A | 2021-07-28 | 91% | PROF4 AD.PROF4 AD | 7.56 |  |  | 1113.3 | 1113.3 | 0
2.02.03.04.02 Procurement
S296600 | (Cryo Controls Hardware procurement) SC level probes Labor | 12 | 1518 | 01-Oct-20 A | 2021-08-27 | 50% | PROF3 AD.PROF3 AD | 6 |  |  | 759 | 759 | 0
S298200 | (Cryo Controls Hardware procurement) Switch, 480 VAC Labor | 5 | 633 | 2021-07-26 | 2021-08-27 | 0% | PROF3 AD.PROF3 AD | 5 |  |  | 633 | 633 | 0
S296700 | (Cryo Controls Hardware procurement) SC level probes M&S | 3000 | 3414 | 01-Oct-20 A | 2021-08-27 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 1500 |  |  | 1707 | 1707 | 0
S298300 | (Cryo Controls Hardware procurement) Switch, 480 VAC M&S | 1220 | 1388 | 2021-07-26 | 2021-08-27 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 1220 |  |  | 1388 | 1388 | 0
2.02.03.04.03 Installation: Cryo Controls Hardware
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | 48 | 6072 | 2021-08-30 | 2021-09-27 | 0% | PROF3 AD.PROF3 AD | 48 |  |  | 6072 | 6072 | 0
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | 280 | 31954 | 2021-08-30 | 2021-09-27 | 0% | TECH3 AD.TECH3 AD | 280 |  |  | 31954 | 31954 | 0
S299700 | (Cryo Controls Hardware) Rack install | 4 | 506 | 2021-09-28 | 2021-10-04 | 0% | PROF3 AD.PROF3 AD | 4 |  |  | 506 | 506 | 0
S299700 | (Cryo Controls Hardware) Rack install | 13 | 1484 | 2021-09-28 | 2021-10-04 | 0% | TECH3 AD.TECH3 AD | 13 |  |  | 1484 | 1484 | 0
S299800 | (Cryo Controls Hardware) Cable pulling | 52 | 6087 | 2021-10-05 | 2021-12-17 | 0% | TECH3 AD.TECH3 AD | 52 |  |  | 6087 | 6087 | 0
S299800 | (Cryo Controls Hardware) Cable pulling | 150 | 19245 | 2021-10-05 | 2021-12-17 | 0% | CRAFT3.CRAFT3 | 150 |  |  | 19245 | 19245 | 0
S299900 | (Cryo Controls Hardware) Cable termination | 160 | 19372 | 2022-02-09 | 2022-03-09 | 0% | TECH3 AD.TECH3 AD | 160 |  |  | 19372 | 19372 | 0
S300000 | (Cryo Controls Hardware) Check out continuity | 40 | 4843 | 2022-03-31 | 2022-04-13 | 0% | TECH3 AD.TECH3 AD | 40 |  |  | 4843 | 4843 | 0
S300100 | (Cryo Controls Hardware) Heater Control Panel Install | 32 | 4122 | 15-Jun-21 A | 2022-01-13 | 50% | CRAFT3.CRAFT3 | 16 |  |  | 2061 | 2061 | 0
S300200 | (Cryo Controls Hardware) Heater 480VAC wiring | 480 | 63690 | 2022-02-09 | 2022-02-15 | 0% | CRAFT3.CRAFT3 | 480 |  |  | 63690 | 63690 | 0
S300400 | (Cryo Controls Hardware) Heater I/O wiring, temp sensors | 16 | 1937 | 2022-03-03 | 2022-03-09 | 0% | TECH3 AD.TECH3 AD | 16 |  |  | 1937 | 1937 | 0
S300500 | (Cryo Controls Hardware) Wire up instruments and control valves | 96 | 11623 | 2022-03-10 | 2022-03-30 | 0% | TECH3 AD.TECH3 AD | 96 |  |  | 11623 | 11623 | 0
S300300 | (Cryo Controls Hardware) Insulating vacuum roughing pumps 480VAC Breaker install and 480V wiring to roughing pumps | 8 | 1062 | 15-Jun-21 A | 2022-03-21 | 50% | CRAFT3.CRAFT3 | 4 |  |  | 531 | 531 | 0
2.02.03.05 Cryo Controls Software
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | 8 | 1012 | 03-Aug-20 A | 2021-08-27 | 60% | PROF3 AD.PROF3 AD | 3.2 |  |  | 404.8 | 404.8 | 0
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | 8 | 1178 | 03-Aug-20 A | 2021-08-27 | 60% | PROF4 AD.PROF4 AD | 3.2 |  |  | 471.2 | 471.2 | 0
S300900 | (Cryo Controls Hardware) Built HMI operator screens | 576 | 75056 | 08-Mar-21 A | 2021-09-20 | 45% | PROF3 AD.PROF3 AD | 316.8 |  |  | 41280.8 | 41280.8 | 0
S300900 | (Cryo Controls Hardware) Built HMI operator screens | 72 | 10921 | 08-Mar-21 A | 2021-09-20 | 45% | PROF4 AD.PROF4 AD | 39.6 |  |  | 6006.55 | 6006.55 | 0
S301000 | (Cryo Controls Hardware) PLC programming | 576 | 77132 | 13-Jul-20 A | 2021-08-27 | 92% | PROF3 AD.PROF3 AD | 46.08 |  |  | 6170.56 | 6170.56 | 0
S301000 | (Cryo Controls Hardware) PLC programming | 72 | 11223 | 13-Jul-20 A | 2021-08-27 | 92% | PROF4 AD.PROF4 AD | 5.76 |  |  | 897.84 | 897.84 | 0
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 120 | 16106 | 2022-04-14 | 2022-04-27 | 0% | PROF3 AD.PROF3 AD | 120 |  |  | 16106 | 16106 | 0
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 120 | 14529 | 2022-04-14 | 2022-04-27 | 0% | TECH3 AD.TECH3 AD | 120 |  |  | 14529 | 14529 | 0
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 24 | 3750 | 2022-04-14 | 2022-04-27 | 0% | PROF4 AD.PROF4 AD | 24 |  |  | 3750 | 3750 | 0
2.02.04.01.01 Design AC/DC Power Distribution
S302101 | Magnet: Design DC Flags 50% | 5 | 736 | 01-Jul-21* | 2021-07-28 | 0% | PROF4 AD.PROF4 AD | 5 |  |  | 736 | 736 | 0
2.02.04.01.03 Install PS AC/DC Cabling
S303200 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution in 1008B to 1008IR | 60 | 8836 | 16-Sep-20 A | 2021-09-08 | 30% | PROF4 AD.PROF4 AD | 42 |  |  | 6185.2 | 6185.2 | 0
S303200 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution in 1008B to 1008IR | 240 | 30017 | 16-Sep-20 A | 2021-09-08 | 30% | CRAFT3.CRAFT3 | 168 |  |  | 21011.9 | 21011.9 | 0
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 60 | 8836 | 2021-09-09 | 2021-09-29 | 0% | PROF4 AD.PROF4 AD | 60 |  |  | 8836 | 8836 | 0
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 240 | 27389 | 2021-09-09 | 2021-09-29 | 0% | TECH3 AD.TECH3 AD | 240 |  |  | 27389 | 27389 | 0
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 300 | 37521 | 2021-09-09 | 2021-09-29 | 0% | CRAFT3.CRAFT3 | 300 |  |  | 37521 | 37521 | 0
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | 240 | 30017 | 2021-09-09 | 2021-09-29 | 0% | CRAFT3.CRAFT3 | 240 |  |  | 30017 | 30017 | 0
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | 60 | 8836 | 2021-09-09 | 2021-09-29 | 0% | PROF4 AD.PROF4 AD | 60 |  |  | 8836 | 8836 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 40 | 6249 | 2022-01-04 | 2022-01-18 | 0% | PROF4 AD.PROF4 AD | 40 |  |  | 6249 | 6249 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 160 | 19372 | 2022-01-04 | 2022-01-18 | 0% | TECH3 AD.TECH3 AD | 160 |  |  | 19372 | 19372 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 220 | 29191 | 2022-01-04 | 2022-01-18 | 0% | CRAFT3.CRAFT3 | 220 |  |  | 29191 | 29191 | 0
2.02.04.02.01 Install Power Supply
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | 7 | 1031 | 24-May-21 A | 2021-08-31 | 10% | PROF4 AD.PROF4 AD | 6.3 |  |  | 927.9 | 927.9 | 0
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | 32 | 3652 | 24-May-21 A | 2021-08-31 | 10% | TECH3 AD.TECH3 AD | 28.8 |  |  | 3286.8 | 3286.8 | 0
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 12499 | 2022-04-06 | 2022-04-19 | 0% | PROF4 AD.PROF4 AD | 80 |  |  | 12499 | 12499 | 0
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 9686 | 2022-04-06 | 2022-04-19 | 0% | TECH3 AD.TECH3 AD | 80 |  |  | 9686 | 9686 | 0
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 70 | 8475 | 2022-03-30 | 2022-04-05 | 0% | TECH3 AD.TECH3 AD | 70 |  |  | 8475 | 8475 | 0
S304800 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR M&S | 3137 | 3500 | 2022-03-30 | 2022-04-05 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 3137 |  |  | 3500 | 3500 | 0
2.02.04.03.02.01 Install Quench Detector
S307100 | Magnet: Connect Signal Interconnections | 80 | 9130 | 08-Mar-21 A | 2021-08-31 | 30% | TECH3 AD.TECH3 AD | 56 |  |  | 6391 | 6391 | 0
S307200 | Magnet: Quench Detector Testing | 80 | 9404 | 2022-04-13 | 2022-04-19 | 0% | TECH3 AD.TECH3 AD | 80 |  |  | 9404 | 9404 | 0
S307200 | Magnet: Quench Detector Testing | 80 | 14013 | 2022-04-13 | 2022-04-19 | 0% | PROF5 AD.PROF5 AD | 80 |  |  | 14013 | 14013 | 0
S307311 | Magnet: Quench Detector Documentation Split_85% | 54 | 6226 | 01-Oct-19 A | 2021-10-29 | 90% | TECH3 AD.TECH3 AD | 5.4 |  |  | 622.6 | 622.6 | 0
S307311 | Magnet: Quench Detector Documentation Split_85% | 27 | 4639 | 01-Oct-19 A | 2021-10-29 | 90% | PROF5 AD.PROF5 AD | 2.7 |  |  | 463.9 | 463.9 | 0
2.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication
S308615 | Develop readout electronics | 90 | 13651 | 30-Oct-20 A | 2021-09-01 | 90% | PROF4 PO E.PROF4 PO E | 9 |  |  | 1365.1 | 1365.1 | 0
S308617 | Calibrate probes | 24 | 5090 | 2021-09-02 | 2021-12-01 | 0% | SCI4 PO.SCI 4 PO | 24 |  |  | 5090 | 5090 | 0
S308617 | Calibrate probes | 24 | 3640 | 2021-09-02 | 2021-12-01 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3640 | 3640 | 0
S308617 | Calibrate probes | 24 | 2821 | 2021-09-02 | 2021-12-01 | 0% | TECH3 PO E.TECH3 PO E | 24 |  |  | 2821 | 2821 | 0
S308619 | Install probes and readout on TPC | 40 | 4843 | 2022-02-03 | 2022-02-16 | 0% | TECH3 PO E.TECH3 PO E | 40 |  |  | 4843 | 4843 | 0
2.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 9686 | 2022-05-26 | 2022-06-09 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 19372 | 2022-05-26 | 2022-06-09 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 10737 | 2022-05-26 | 2022-06-09 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10737 | 10737 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 34952 | 2022-05-26 | 2022-06-09 | 0% | SCI4 PO.SCI 4 PO | 160 |  |  | 34952 | 34952 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9686 | 2022-06-14 | 2022-07-05 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 34952 | 2022-06-14 | 2022-07-05 | 0% | SCI4 PO.SCI 4 PO | 160 |  |  | 34952 | 34952 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 10737 | 2022-06-14 | 2022-07-05 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10737 | 10737 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 19372 | 2022-06-14 | 2022-07-05 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S309100 | Magnet Field Measurements: Remove Field Mapping Equipment | 40 | 4843 | 2022-07-06 | 2022-07-07 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4843 | 4843 | 0
S309100 | Magnet Field Measurements: Remove Field Mapping Equipment | 80 | 9686 | 2022-07-06 | 2022-07-07 | 0% | TECH3 PO E.TECH3 PO E | 80 |  |  | 9686 | 9686 | 0
S309005 | Magnet Field Measurements: Perform Magnetic Survey of as-build structure in IR | 80 | 9686 | 2022-06-14 | 2022-07-05 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S309005 | Magnet Field Measurements: Perform Magnetic Survey of as-build structure in IR | 160 | 34952 | 2022-06-14 | 2022-07-05 | 0% | SCI4 PO.SCI 4 PO | 160 |  |  | 34952 | 34952 | 0
S309005 | Magnet Field Measurements: Perform Magnetic Survey of as-build structure in IR | 80 | 10737 | 2022-06-14 | 2022-07-05 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10737 | 10737 | 0
S309005 | Magnet Field Measurements: Perform Magnetic Survey of as-build structure in IR | 160 | 19372 | 2022-06-14 | 2022-07-05 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S308625 | Complete MOU with Vendor | 8 | 1697 | 22-Feb-21 A | 2021-10-05 | 20% | SCI4 PO.SCI 4 PO | 6.4 |  |  | 1357.6 | 1357.6 | 0
S308621 | Conceptual design of mapping campaign | 32 | 6787 | 01-Oct-20 A | 2021-09-29 | 60% | SCI4 PO.SCI 4 PO | 12.8 |  |  | 2714.8 | 2714.8 | 0
S308623 | Develop mapping plan with Vendor | 100 | 21208 | 30-Oct-20 A | 2021-11-30 | 50% | SCI4 PO.SCI 4 PO | 50 |  |  | 10604 | 10604 | 0
S308627 | Place contract with Vendor (Procurement string, $70K obligated at Contract award, paid when mapped?) | 63000 | 73123 | 2021-09-30 | 2022-02-28 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 63000 |  |  | 73123 | 73123 | 0
S308629 | Complete mechanical and electrical design for mapping | 60 | 9101 | 23-Nov-20 A | 2021-10-01 | 35% | PROF4 PO M.PROF4 PO M | 39 |  |  | 5915.65 | 5915.65 | 0
S308629 | Complete mechanical and electrical design for mapping | 30 | 3526 | 23-Nov-20 A | 2021-10-01 | 35% | TECH3 PO D.TECH3 PO D | 19.5 |  |  | 2291.9 | 2291.9 | 0
S308631 | Review mapping plan | 16 | 2427 | 2021-09-30 | 2021-10-06 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2427 | 2427 | 0
S308631 | Review mapping plan | 16 | 1881 | 2021-09-30 | 2021-10-06 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1881 | 1881 | 0
S308631 | Review mapping plan | 10 | 2121 | 2021-09-30 | 2021-10-06 | 0% | SCI4 PO.SCI 4 PO | 10 |  |  | 2121 | 2121 | 0
S308633 | Construct mapping support (mechanical and electrical) | 32 | 3761 | 08-Mar-21 A | 2021-10-21 | 5% | TECH3 PO M.TECH3 PO M | 30.4 |  |  | 3572.95 | 3572.95 | 0
S309110 | Receive report from CERN, incorporate into analysis | 16 | 3495 | 08-Jul-22* | 2022-08-04 | 0% | SCI4 PO.SCI 4 PO | 16 |  |  | 3495 | 3495 | 0
2.03.01 Cradle Carriage
S313400 | CC Seismic Restraints - Assembly & Detail Drawings - Physics Resource(s) | 120 | 13695 | 17-Dec-19 A | 2021-07-16 | 95% | TECH3 PO D.TECH3 PO D | 6 |  |  | 684.75 | 684.75 | 0
S313500 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - Physics Resource(s) | 20 | 2282 | 2021-07-19 | 2021-07-23 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2282 | 2282 | 0
S313600 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 20 | 2282 | 2021-07-26 | 2021-07-30 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2282 | 2282 | 0
S313700 | CC Seismic Restraints - Prepare Procurement Package - Physics Resource(s) | 20 | 2282 | 2021-08-02 | 2021-08-06 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2282 | 2282 | 0
S313800 | CC Seismic Restraints - Procurement Readiness Review - Physics Resource(s) | 20 | 2282 | 2021-08-09 | 2021-08-13 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2282 | 2282 | 0
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | 18 | 2054 | 2021-10-13 | 2021-11-24 | 0% | TECH3 PO D.TECH3 PO D | 18 |  |  | 2054 | 2054 | 0
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | 36 | 4108 | 2021-10-13 | 2021-11-24 | 0% | TECH3 PO M.TECH3 PO M | 36 |  |  | 4108 | 4108 | 0
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | 10 | 1160 | 2021-11-30 | 2022-08-16 | 0% | TECH3 PO D.TECH3 PO D | 10 |  |  | 1160 | 1160 | 0
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | 40 | 4642 | 2021-11-30 | 2022-08-16 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4642 | 4642 | 0
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | 4 | 470 | 2022-08-17 | 2022-08-23 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 470 | 470 | 0
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | 20 | 2351 | 2022-08-17 | 2022-08-23 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2351 | 2351 | 0
S313900 | CC Seismic Restraints - Provide Requirement to Procurement | 8 | 1361 | 2021-08-16 | 2021-08-20 | 0% | PROF5 AD.PROF5 AD | 8 |  |  | 1361 | 1361 | 0
S314100 | CC Seismic Restraints - Vendor Responses - Physics Resource(s) | 18 | 2054 | 2021-08-30 | 2021-10-12 | 0% | TECH3 PO D.TECH3 PO D | 18 |  |  | 2054 | 2054 | 0
S316000 | Steel Track Modifications - Finish Track Work M&S | 20000 | 23214 | 15-Oct-20 A | 2021-08-30 | 95% | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 |  |  | 1160.7 | 1160.7 | 0
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 80 | 11781 | 17-Dec-19 A | 2021-07-16 | 95% | PROF4 AD.PROF4 AD | 4 |  |  | 589.05 | 589.05 | 0
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 40 | 6803 | 17-Dec-19 A | 2021-07-16 | 95% | PROF5 AD.PROF5 AD | 2 |  |  | 340.15 | 340.15 | 0
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 120 | 13695 | 17-Dec-19 A | 2021-07-16 | 95% | TECH3 AD.TECH3 AD | 6 |  |  | 684.75 | 684.75 | 0
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 40 | 5891 | 2021-07-19 | 2021-07-23 | 0% | PROF4 AD.PROF4 AD | 40 |  |  | 5891 | 5891 | 0
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 20 | 2282 | 2021-07-19 | 2021-07-23 | 0% | TECH3 AD.TECH3 AD | 20 |  |  | 2282 | 2282 | 0
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 40 | 5891 | 2021-07-26 | 2021-07-30 | 0% | PROF4 AD.PROF4 AD | 40 |  |  | 5891 | 5891 | 0
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 20 | 3401 | 2021-07-26 | 2021-07-30 | 0% | PROF5 AD.PROF5 AD | 20 |  |  | 3401 | 3401 | 0
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 20 | 2282 | 2021-07-26 | 2021-07-30 | 0% | TECH3 AD.TECH3 AD | 20 |  |  | 2282 | 2282 | 0
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 20 | 2945 | 2021-08-02 | 2021-08-06 | 0% | PROF4 AD.PROF4 AD | 20 |  |  | 2945 | 2945 | 0
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 8 | 1361 | 2021-08-02 | 2021-08-06 | 0% | PROF5 AD.PROF5 AD | 8 |  |  | 1361 | 1361 | 0
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 20 | 2282 | 2021-08-02 | 2021-08-06 | 0% | TECH3 AD.TECH3 AD | 20 |  |  | 2282 | 2282 | 0
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 20 | 2945 | 2021-08-09 | 2021-08-13 | 0% | PROF4 AD.PROF4 AD | 20 |  |  | 2945 | 2945 | 0
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 8 | 1361 | 2021-08-09 | 2021-08-13 | 0% | PROF5 AD.PROF5 AD | 8 |  |  | 1361 | 1361 | 0
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 20 | 2282 | 2021-08-09 | 2021-08-13 | 0% | TECH3 AD.TECH3 AD | 20 |  |  | 2282 | 2282 | 0
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 18 | 2651 | 2021-10-13 | 2021-11-24 | 0% | PROF4 AD.PROF4 AD | 18 |  |  | 2651 | 2651 | 0
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 8 | 1361 | 2021-10-13 | 2021-11-24 | 0% | PROF5 AD.PROF5 AD | 8 |  |  | 1361 | 1361 | 0
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 18 | 2054 | 2021-10-13 | 2021-11-24 | 0% | TECH3 AD.TECH3 AD | 18 |  |  | 2054 | 2054 | 0
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 24 | 3594 | 2021-11-30 | 2022-08-16 | 0% | PROF4 AD.PROF4 AD | 24 |  |  | 3594 | 3594 | 0
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 24 | 4150 | 2021-11-30 | 2022-08-16 | 0% | PROF5 AD.PROF5 AD | 24 |  |  | 4150 | 4150 | 0
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 10 | 1160 | 2021-11-30 | 2022-08-16 | 0% | TECH3 AD.TECH3 AD | 10 |  |  | 1160 | 1160 | 0
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 2 | 303 | 2022-08-17 | 2022-08-23 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 303 | 303 | 0
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 4 | 701 | 2022-08-17 | 2022-08-23 | 0% | PROF5 AD.PROF5 AD | 4 |  |  | 701 | 701 | 0
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 4 | 470 | 2022-08-17 | 2022-08-23 | 0% | TECH3 AD.TECH3 AD | 4 |  |  | 470 | 470 | 0
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 18 | 2651 | 2021-08-30 | 2021-10-12 | 0% | PROF4 AD.PROF4 AD | 18 |  |  | 2651 | 2651 | 0
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 8 | 1361 | 2021-08-30 | 2021-10-12 | 0% | PROF5 AD.PROF5 AD | 8 |  |  | 1361 | 1361 | 0
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 18 | 2054 | 2021-08-30 | 2021-10-12 | 0% | TECH3 AD.TECH3 AD | 18 |  |  | 2054 | 2054 | 0
S314650 | CC Seismic Restraints - Delivery Acceptance - M&S | 126000 | 146246 | 2022-08-17 | 2022-08-23 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 126000 |  |  | 146246 | 146246 | 0
S316005 | Steel Track Modifications - Finish Track Work Labor | 24 | 3036 | 15-Oct-20 A | 2021-08-30 | 95% | PROF3 AD.PROF3 AD | 1.2 |  |  | 151.8 | 151.8 | 0
S316005 | Steel Track Modifications - Finish Track Work Labor | 40 | 5003 | 15-Oct-20 A | 2021-08-30 | 95% | CRAFT3.CRAFT3 | 2 |  |  | 250.15 | 250.15 | 0
2.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports
S317200 | Evaluate & Process Bid for Inner HCal Support Tabs - Physics Resource(s) | 16 | 1826 | 2021-07-01 | 2021-07-29 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1826 | 1826 | 0
S317200 | Evaluate & Process Bid for Inner HCal Support Tabs - Physics Resource(s) | 16 | 1826 | 2021-07-01 | 2021-07-29 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1826 | 1826 | 0
S318000 | Perform Inner HCal Support Tabs Acceptance - Physics Resource(s) | 20 | 2351 | 2021-11-05 | 2021-12-14 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2351 | 2351 | 0
S318000 | Perform Inner HCal Support Tabs Acceptance - Physics Resource(s) | 8 | 940 | 2021-11-05 | 2021-12-14 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S317400 | Procure IHCal Structural Support - Provide Requirements to Procurement | 32 | 4048 | 2021-07-30 | 2021-08-05 | 0% | PROF3 PO M.PROF3 PO M | 32 |  |  | 4048 | 4048 | 0
S317600 | Procure IHCal Structural Support - Vendor Response and Selection | 32 | 4048 | 2021-08-13 | 2021-08-19 | 0% | PROF3 PO M.PROF3 PO M | 32 |  |  | 4048 | 4048 | 0
S317900 | Procure IHCal Structural Support - Delivery Acceptance | 45850 | 53217 | 2021-10-29 | 2021-11-04 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 45850 |  |  | 53217 | 53217 | 0
S317210 | Evaluate & Process Bid for Inner HCal Support Tabs - CA-D Resource(s) | 32 | 4712 | 2021-07-01 | 2021-07-29 | 0% | PROF4 AD.PROF4 AD | 32 |  |  | 4712 | 4712 | 0
S318010 | Perform Inner HCal Support Tabs Acceptance - CA-D Resource(s) | 16 | 2427 | 2021-11-05 | 2021-12-14 | 0% | PROF4 AD.PROF4 AD | 16 |  |  | 2427 | 2427 | 0
S317040 | Create TPC Supports Detailed Design Drawings | 80 | 10424 | 17-Nov-20 A | 2021-08-06 | 95% | PROF3 PO M.PROF3 PO M | 4 |  |  | 521.2 | 521.2 | 0
S317040 | Create TPC Supports Detailed Design Drawings | 160 | 18807 | 17-Nov-20 A | 2021-08-06 | 95% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940.35 | 940.35 | 0
S317041 | Review Design and Safety TPC Supports | 8 | 1042 | 2021-08-09 | 2021-08-13 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1042 | 1042 | 0
S317041 | Review Design and Safety TPC Supports | 8 | 1042 | 2021-08-09 | 2021-08-13 | 0% | PROF3 PO M.PROF3 PO M | 8 |  |  | 1042 | 1042 | 0
S317042 | Address Action Items for TPC Supports | 8 | 1042 | 2021-08-16 | 2021-08-17 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1042 | 1042 | 0
S317042 | Address Action Items for TPC Supports | 8 | 1042 | 2021-08-16 | 2021-08-17 | 0% | PROF3 PO M.PROF3 PO M | 8 |  |  | 1042 | 1042 | 0
S317050 | Create INTT Supports Detailed Design Drawings | 40 | 5212 | 13-May-20 A | 2021-08-12 | 65% | PROF3 PO M.PROF3 PO M | 14 |  |  | 1824.2 | 1824.2 | 0
S317050 | Create INTT Supports Detailed Design Drawings | 160 | 18807 | 13-May-20 A | 2021-08-12 | 65% | TECH3 PO D.TECH3 PO D | 56 |  |  | 6582.45 | 6582.45 | 0
S317051 | Review Design and Safety INTT Supports | 8 | 1042 | 2021-08-13 | 2021-08-19 | 0% | PROF3 PO M.PROF3 PO M | 8 |  |  | 1042 | 1042 | 0
S317051 | Review Design and Safety INTT Supports | 40 | 4702 | 2021-08-13 | 2021-08-19 | 0% | TECH3 PO D.TECH3 PO D | 40 |  |  | 4702 | 4702 | 0
S317052 | Address Action Items for INTT Supports | 8 | 1042 | 2021-08-20 | 2021-08-23 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1042 | 1042 | 0
S317052 | Address Action Items for INTT Supports | 8 | 1042 | 2021-08-20 | 2021-08-23 | 0% | PROF3 PO M.PROF3 PO M | 8 |  |  | 1042 | 1042 | 0
S317062 | Address Action Items for MVTX Supports | 8 | 1042 | 2021-08-13 | 2021-08-16 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1042 | 1042 | 0
S317062 | Address Action Items for MVTX Supports | 8 | 1042 | 2021-08-13 | 2021-08-16 | 0% | PROF3 PO M.PROF3 PO M | 8 |  |  | 1042 | 1042 | 0
S317070 | Create MBD Supports Detailed Design Drawings | 60 | 7818 | 18-May-20 A | 2021-08-26 | 70% | PROF3 PO M.PROF3 PO M | 18 |  |  | 2345.4 | 2345.4 | 0
S317070 | Create MBD Supports Detailed Design Drawings | 80 | 9404 | 18-May-20 A | 2021-08-26 | 70% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821.2 | 2821.2 | 0
S317071 | Review Design and Safety MBD Supports | 4 | 521 | 2021-08-27 | 2021-08-30 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 521 | 521 | 0
S317071 | Review Design and Safety MBD Supports | 4 | 521 | 2021-08-27 | 2021-08-30 | 0% | PROF3 PO M.PROF3 PO M | 4 |  |  | 521 | 521 | 0
S317072 | Address Action Items for MBD Supports | 4 | 521 | 2021-08-31 | 2021-09-01 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 521 | 521 | 0
S317072 | Address Action Items for MBD Supports | 4 | 521 | 2021-08-31 | 2021-09-01 | 0% | PROF3 PO M.PROF3 PO M | 4 |  |  | 521 | 521 | 0
S317090 | Create Beampipe Supports Detailed Design Drawings | 240 | 30362 | 12-Mar-20 A | 2021-07-28 | 90% | PROF3 PO M.PROF3 PO M | 24 |  |  | 3036.2 | 3036.2 | 0
S317090 | Create Beampipe Supports Detailed Design Drawings | 300 | 34237 | 12-Mar-20 A | 2021-07-28 | 90% | TECH3 PO D.TECH3 PO D | 30 |  |  | 3423.7 | 3423.7 | 0
S317091 | Review Design and Safety Beampipe Supports | 20 | 2530 | 2021-07-29 | 2021-08-04 | 0% | PROF3 PO M.PROF3 PO M | 20 |  |  | 2530 | 2530 | 0
S317091 | Review Design and Safety Beampipe Supports | 20 | 2282 | 2021-07-29 | 2021-08-04 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2282 | 2282 | 0
S317092 | Address Action Items for Beampipe Supports | 4 | 521 | 2021-08-05 | 2021-08-06 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 521 | 521 | 0
S317092 | Address Action Items for Beampipe Supports | 4 | 521 | 2021-08-05 | 2021-08-06 | 0% | PROF3 PO M.PROF3 PO M | 4 |  |  | 521 | 521 | 0
S317140 | Prepare Procurement Package for TPC Supports | 40 | 4702 | 2021-08-18 | 2021-09-15 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
S317140 | Prepare Procurement Package for TPC Supports | 40 | 5212 | 2021-08-18 | 2021-09-15 | 0% | PROF3 PO M.PROF3 PO M | 40 |  |  | 5212 | 5212 | 0
S317140 | Prepare Procurement Package for TPC Supports | 40 | 5212 | 2021-08-18 | 2021-09-15 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S317150 | Prepare Procurement Package for INTT Supports | 20 | 2351 | 2021-08-24 | 2021-09-07 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2351 | 2351 | 0
S317150 | Prepare Procurement Package for INTT Supports | 20 | 2606 | 2021-08-24 | 2021-09-07 | 0% | PROF3 PO M.PROF3 PO M | 20 |  |  | 2606 | 2606 | 0
S317150 | Prepare Procurement Package for INTT Supports | 20 | 2606 | 2021-08-24 | 2021-09-07 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S317160 | Prepare Procurement Package for MVTX Supports | 20 | 2351 | 2021-08-17 | 2021-08-30 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2351 | 2351 | 0
S317160 | Prepare Procurement Package for MVTX Supports | 20 | 2606 | 2021-08-17 | 2021-08-30 | 0% | PROF3 PO M.PROF3 PO M | 20 |  |  | 2606 | 2606 | 0
S317160 | Prepare Procurement Package for MVTX Supports | 20 | 2606 | 2021-08-17 | 2021-08-30 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S317170 | Prepare Procurement Package for MBD Supports | 10 | 1175 | 2021-09-02 | 2021-09-16 | 0% | TECH3 PO M.TECH3 PO M | 10 |  |  | 1175 | 1175 | 0
S317170 | Prepare Procurement Package for MBD Supports | 10 | 1303 | 2021-09-02 | 2021-09-16 | 0% | PROF3 PO M.PROF3 PO M | 10 |  |  | 1303 | 1303 | 0
S317170 | Prepare Procurement Package for MBD Supports | 10 | 1303 | 2021-09-02 | 2021-09-16 | 0% | PROF3 PO E.PROF3 PO E | 10 |  |  | 1303 | 1303 | 0
S317190 | Prepare Procurement Package for Beampipe Supports | 40 | 4702 | 2021-08-09 | 2021-08-20 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
S317190 | Prepare Procurement Package for Beampipe Supports | 40 | 5212 | 2021-08-09 | 2021-08-20 | 0% | PROF3 PO M.PROF3 PO M | 40 |  |  | 5212 | 5212 | 0
S317190 | Prepare Procurement Package for Beampipe Supports | 40 | 5212 | 2021-08-09 | 2021-08-20 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S317240 | Evaluate and Process Bid for TPC Supports | 20 | 2606 | 2021-09-16 | 2021-10-14 | 0% | PROF3 PO M.PROF3 PO M | 20 |  |  | 2606 | 2606 | 0
S317240 | Evaluate and Process Bid for TPC Supports | 20 | 2606 | 2021-09-16 | 2021-10-14 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S317250 | Evaluate and Process Bid for INTT Supports | 20 | 2606 | 2021-09-08 | 2021-10-05 | 0% | PROF3 PO M.PROF3 PO M | 20 |  |  | 2606 | 2606 | 0
S317250 | Evaluate and Process Bid for INTT Supports | 20 | 2606 | 2021-09-08 | 2021-10-05 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S317260 | Evaluate and Process Bid for MVTX Supports | 20 | 2606 | 2021-08-31 | 2021-09-28 | 0% | PROF3 PO M.PROF3 PO M | 20 |  |  | 2606 | 2606 | 0
S317260 | Evaluate and Process Bid for MVTX Supports | 20 | 2606 | 2021-08-31 | 2021-09-28 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S317270 | Evaluate and Process Bid for MBD Supports | 10 | 1303 | 2021-09-17 | 2021-10-15 | 0% | PROF3 PO M.PROF3 PO M | 10 |  |  | 1303 | 1303 | 0
S317270 | Evaluate and Process Bid for MBD Supports | 10 | 1303 | 2021-09-17 | 2021-10-15 | 0% | PROF3 PO E.PROF3 PO E | 10 |  |  | 1303 | 1303 | 0
S317290 | Evaluate and Process Bid for Beampipe Supports | 20 | 2606 | 2021-08-23 | 2021-09-20 | 0% | PROF3 PO M.PROF3 PO M | 20 |  |  | 2606 | 2606 | 0
S317290 | Evaluate and Process Bid for Beampipe Supports | 20 | 2606 | 2021-08-23 | 2021-09-20 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S317920 | Procure Magnet Supports - M&S | 50000 | 58034 | 10-May-21 A | 2021-08-05 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 25000 |  |  | 29017 | 29017 | 0
S317940 | Procure TPC Supports - M&S | 50000 | 58034 | 2021-10-18 | 2021-12-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 58034 | 58034 | 0
S317950 | Procure INTT Supports - M&S | 50000 | 58034 | 2021-10-07 | 2021-12-07 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 58034 | 58034 | 0
S317960 | Procure MVTX Supports - M&S | 50000 | 58034 | 2021-09-30 | 2021-11-30 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 58034 | 58034 | 0
S317970 | Procure MBD Supports - M&S | 10000 | 11607 | 2021-10-18 | 2021-11-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 |  |  | 11607 | 11607 | 0
S317980 | Procure Large Support Rings - M&S | 300000 | 348205 | 15-Apr-21 A | 2021-08-25 | 25% | Purch 1st $2M.Material (Purchase (1st $2M) | 225000 |  |  | 261153.75 | 261153.75 | 0
S317990 | Procure Beampipe Supports - M&S | 25000 | 29017 | 2021-09-21 | 2021-10-19 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 25000 |  |  | 29017 | 29017 | 0
S318120 | Perform Magnet Supports Acceptance | 20 | 2351 | 2021-08-06 | 2021-08-19 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2351 | 2351 | 0
S318120 | Perform Magnet Supports Acceptance | 20 | 2606 | 2021-08-06 | 2021-08-19 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S318140 | Perform TPC Supports Acceptance | 40 | 4702 | 2021-12-16 | 2021-12-30 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
S318140 | Perform TPC Supports Acceptance | 40 | 5212 | 2021-12-16 | 2021-12-30 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S318150 | Perform INTT Supports Acceptance | 20 | 2351 | 2021-12-08 | 2021-12-21 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2351 | 2351 | 0
S318150 | Perform INTT Supports Acceptance | 20 | 2606 | 2021-12-08 | 2021-12-21 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S318160 | Perform MVTX Supports Acceptance | 20 | 2351 | 2021-12-01 | 2021-12-14 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2351 | 2351 | 0
S318160 | Perform MVTX Supports Acceptance | 20 | 2606 | 2021-12-01 | 2021-12-14 | 0% | PROF3 PO E.PROF3 PO E | 20 |  |  | 2606 | 2606 | 0
S318170 | Perform MBD Supports Acceptance | 10 | 1175 | 2021-11-16 | 2021-12-01 | 0% | TECH3 PO M.TECH3 PO M | 10 |  |  | 1175 | 1175 | 0
S318170 | Perform MBD Supports Acceptance | 10 | 1303 | 2021-11-16 | 2021-12-01 | 0% | PROF3 PO E.PROF3 PO E | 10 |  |  | 1303 | 1303 | 0
S318180 | Perform Large Support Rings Acceptance | 80 | 9404 | 2021-08-26 | 2021-09-09 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9404 | 9404 | 0
S318180 | Perform Large Support Rings Acceptance | 40 | 5212 | 2021-08-26 | 2021-09-09 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S318190 | Perform Beampipe Supports Acceptance | 40 | 4702 | 2021-10-20 | 2021-11-02 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
S318190 | Perform Beampipe Supports Acceptance | 40 | 5212 | 2021-10-20 | 2021-11-02 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S318182 | Assemble Large Support Rings | 80 | 9404 | 2021-09-10 | 2021-09-30 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9404 | 9404 | 0
S318182 | Assemble Large Support Rings | 40 | 5212 | 2021-09-10 | 2021-09-30 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S318182 | Assemble Large Support Rings | 40 | 6067 | 2021-09-10 | 2021-09-30 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6067 | 6067 | 0
2.03.04 End Caps/ Pole Tips
S325400 | End Caps/ Pole Tips - Delivery Acceptance | 890262 | 993188 | 2021-08-26 | 2021-08-26 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 890262 |  |  | 993188 | 993188 | 0
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | 40 | 4702 | 2021-08-26 | 2021-09-09 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4702 | 4702 | 0
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | 44 | 5172 | 2021-08-26 | 2021-09-09 | 0% | TECH3 PO D.TECH3 PO D | 44 |  |  | 5172 | 5172 | 0
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 36 | 6306 | 2021-08-26 | 2021-09-09 | 0% | PROF5 AD.PROF5 AD | 36 |  |  | 6306 | 6306 | 0
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 44 | 5172 | 2021-08-26 | 2021-09-09 | 0% | TECH3 AD.TECH3 AD | 44 |  |  | 5172 | 5172 | 0
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 52 | 7888 | 2021-08-26 | 2021-09-09 | 0% | PROF4 AD.PROF4 AD | 52 |  |  | 7888 | 7888 | 0
2.03.05 CC Bridge, Mid Platforms and Access
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | 36 | 4232 | 2021-07-01 | 2021-11-01 | 0% | TECH3 PO D.TECH3 PO D | 36 |  |  | 4232 | 4232 | 0
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | 72 | 8463 | 2021-07-01 | 2021-11-01 | 0% | TECH3 PO M.TECH3 PO M | 72 |  |  | 8463 | 8463 | 0
S327100 | CC Bridge, Mid Platforms & Access - Delivery Acceptance | 320659 | 372184 | 01-Dec-21* | 2021-12-14 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 320659 |  |  | 372184 | 372184 | 0
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 60 | 9101 | 2021-07-01 | 2021-11-01 | 0% | PROF4 AD.PROF4 AD | 60 |  |  | 9101 | 9101 | 0
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 30 | 5255 | 2021-07-01 | 2021-11-01 | 0% | PROF5 AD.PROF5 AD | 30 |  |  | 5255 | 5255 | 0
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 36 | 4232 | 2021-07-01 | 2021-11-01 | 0% | TECH3 AD.TECH3 AD | 36 |  |  | 4232 | 4232 | 0
S327150 | Access stairs for upper platforms | 45000 | 50203 | 01-Jul-21* | 2022-01-31 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 45000 |  |  | 50203 | 50203 | 0
2.04.01.01 Line Electric Power Distribution
S328850 | Evaluate & Process Line Electric Power Distribution Components Bid | 40 | 5212 | 2021-07-29 | 2021-10-22 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S329200 | Perform Line Electric Power Distribution Components Acceptance | 80 | 9404 | 2022-01-25 | 2022-02-22 | 0% | TECH3 PO E.TECH3 PO E | 80 |  |  | 9404 | 9404 | 0
S329200 | Perform Line Electric Power Distribution Components Acceptance | 40 | 5212 | 2022-01-25 | 2022-02-22 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S329100 | Procure Line Electric Power Distribution Components - Delivery Acceptance | 50000 | 58034 | 2022-01-25 | 2022-02-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 58034 | 58034 | 0
S277600 | 2022 Detector Support Systems L3 Project Management | 352 | 47243 | 01-Oct-21* | 2022-09-30 | 0% | PROF3 PO E.PROF3 PO E | 352 |  |  | 47243 | 47243 | 0
S277700 | 2023 Detector Support Systems L3 Project Management | 113 | 15621 | 03-Oct-22* | 2022-10-04 | 0% | PROF3 PO E.PROF3 PO E | 113 |  |  | 15621 | 15621 | 0
2.04.01.02 Detector Support Services Systems (including Cables, Fibers, Cable Trays)
S329600 | Review Detector Support Services Systems Design/Safety - CA-D Resource(s) | 20 | 3034 | 2021-09-15 | 2021-10-01 | 0% | PROF4 AD.PROF4 AD | 20 |  |  | 3034 | 3034 | 0
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | 80 | 9404 | 2021-10-01 | 2021-10-20 | 0% | TECH3 PO D.TECH3 PO D | 80 |  |  | 9404 | 9404 | 0
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | 40 | 5212 | 2021-10-01 | 2021-10-20 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5212 | 5212 | 0
S329900 | Prepare Detector Support Services Systems Components Procurement Package(s) - CA-D Resource(s) | 20 | 3034 | 2021-10-20 | 2021-11-18 | 0% | PROF4 AD.PROF4 AD | 20 |  |  | 3034 | 3034 | 0
S330000 | Evaluate & Process Detector Support Services Systems Components Bids - CA-D Resource(s) | 10 | 1517 | 2021-11-18 | 2021-12-20 | 0% | PROF4 AD.PROF4 AD | 10 |  |  | 1517 | 1517 | 0
S330100 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor C | 2 | 308 | 2021-12-20 | 2022-03-04 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 308 | 308 | 0
S330300 | Perform Detector Support Services Systems Components Acceptance - CA-D Resource(s) | 4 | 625 | 2022-03-04 | 2022-03-11 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 625 | 625 | 0
S330200 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) M&S | 32000 | 37528 | 2021-12-20 | 2022-03-04 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 32000 |  |  | 37528 | 37528 | 0
S330350 | Procure Fiber Optics Trunk Cables and Accessories - Labor - CA-D Resource(s) | 4 | 625 | 2022-03-11 | 2022-06-06 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 625 | 625 | 0
S330355 | Procure Fiber Optics Trunk Cables and Accessories - M&S | 22000 | 26046 | 2022-03-11 | 2022-06-06 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 22000 |  |  | 26046 | 26046 | 0
S1002399 | Review Detector Support Services Systems Design/Safety - Physics Resource(s) | 8 | 940 | 2021-09-15 | 2021-10-01 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S1002399 | Review Detector Support Services Systems Design/Safety - Physics Resource(s) | 8 | 1042 | 2021-09-15 | 2021-10-01 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1042 | 1042 | 0
S1002479 | Prepare Detector Support Services Systems Components Procurement Package(s) - Physics Resource(s) | 80 | 9404 | 2021-10-20 | 2021-11-18 | 0% | TECH3 PO D.TECH3 PO D | 80 |  |  | 9404 | 9404 | 0
S1002479 | Prepare Detector Support Services Systems Components Procurement Package(s) - Physics Resource(s) | 80 | 10424 | 2021-10-20 | 2021-11-18 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10424 | 10424 | 0
S1002559 | Evaluate & Process Detector Support Services Systems Components Bids - Physics Resource(s) | 16 | 1881 | 2021-11-18 | 2021-12-20 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1881 | 1881 | 0
S1002559 | Evaluate & Process Detector Support Services Systems Components Bids - Physics Resource(s) | 16 | 2085 | 2021-11-18 | 2021-12-20 | 0% | PROF3 PO E.PROF3 PO E | 16 |  |  | 2085 | 2085 | 0
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | 40 | 4775 | 2021-12-20 | 2022-03-04 | 0% | TECH3 PO D.TECH3 PO D | 40 |  |  | 4775 | 4775 | 0
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | 40 | 5294 | 2021-12-20 | 2022-03-04 | 0% | PROF3 PO E.PROF3 PO E | 40 |  |  | 5294 | 5294 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 20 | 2421 | 2022-03-04 | 2022-03-11 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2421 | 2421 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 4 | 484 | 2022-03-04 | 2022-03-11 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 484 | 484 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 4 | 537 | 2022-03-04 | 2022-03-11 | 0% | PROF3 PO E.PROF3 PO E | 4 |  |  | 537 | 537 | 0
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | 80 | 14607 | 2022-03-11 | 2022-06-06 | 0% | SCI3 PO.SCI3 PO | 80 |  |  | 14607 | 14607 | 0
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | 80 | 10737 | 2022-03-11 | 2022-06-06 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10737 | 10737 | 0
S329440 | Conceptual Design for Routing Rack Cooling System | 104 | 13552 | 23-Oct-20 A | 2021-07-30 | 30% | PROF3 PO E.PROF3 PO E | 72.8 |  |  | 9486.4 | 9486.4 | 0
S329440 | Conceptual Design for Routing Rack Cooling System | 104 | 12225 | 23-Oct-20 A | 2021-07-30 | 30% | TECH3 PO D.TECH3 PO D | 72.8 |  |  | 8557.5 | 8557.5 | 0
S329450 | Conceptual Design for Routing Detector Cooling System | 100 | 13030 | 15-Jul-20 A | 2021-08-03 | 35% | PROF3 PO E.PROF3 PO E | 65 |  |  | 8469.5 | 8469.5 | 0
S329450 | Conceptual Design for Routing Detector Cooling System | 200 | 23509 | 15-Jul-20 A | 2021-08-03 | 35% | TECH3 PO D.TECH3 PO D | 130 |  |  | 15280.85 | 15280.85 | 0
S329460 | Design Package for Detector Cooling System | 120 | 15637 | 2021-08-03 | 2021-09-15 | 0% | PROF3 PO E.PROF3 PO E | 120 |  |  | 15637 | 15637 | 0
S329460 | Design Package for Detector Cooling System | 240 | 28211 | 2021-08-03 | 2021-09-15 | 0% | TECH3 PO D.TECH3 PO D | 240 |  |  | 28211 | 28211 | 0
2.04.01.03 Detector Electronics Racks and Rack generic support systems
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | 24 | 3640 | 23-Oct-20 A | 2021-07-14 | 40% | PROF4 PO M.PROF4 PO M | 14.4 |  |  | 2184 | 2184 | 0
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | 96 | 11284 | 23-Oct-20 A | 2021-07-14 | 40% | TECH3 PO D.TECH3 PO D | 57.6 |  |  | 6770.4 | 6770.4 | 0
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | 24 | 3127 | 23-Oct-20 A | 2021-07-14 | 40% | PROF3 PO E.PROF3 PO E | 14.4 |  |  | 1876.2 | 1876.2 | 0
S330800 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - CA-D Resource(s) | 8 | 1213 | 30-Apr-21 A | 2021-07-28 | 60% | PROF4 AD.PROF4 AD | 3.2 |  |  | 485.2 | 485.2 | 0
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | 8 | 1213 | 21-Jun-21 A | 2021-07-30 | 25% | PROF4 PO M.PROF4 PO M | 6 |  |  | 909.75 | 909.75 | 0
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | 32 | 3761 | 21-Jun-21 A | 2021-07-30 | 25% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2820.75 | 2820.75 | 0
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | 8 | 1042 | 21-Jun-21 A | 2021-07-30 | 25% | PROF3 PO E.PROF3 PO E | 6 |  |  | 781.5 | 781.5 | 0
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | 16 | 2427 | 2021-08-02 | 2021-09-27 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2427 | 2427 | 0
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | 72 | 8463 | 2021-08-02 | 2021-09-27 | 0% | TECH3 PO D.TECH3 PO D | 72 |  |  | 8463 | 8463 | 0
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | 16 | 2085 | 2021-08-02 | 2021-09-27 | 0% | PROF3 PO E.PROF3 PO E | 16 |  |  | 2085 | 2085 | 0
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | 48 | 7281 | 2021-09-28 | 2021-11-24 | 0% | PROF4 PO M.PROF4 PO M | 48 |  |  | 7281 | 7281 | 0
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | 144 | 16927 | 2021-09-28 | 2021-11-24 | 0% | TECH3 PO D.TECH3 PO D | 144 |  |  | 16927 | 16927 | 0
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | 48 | 6255 | 2021-09-28 | 2021-11-24 | 0% | PROF3 PO E.PROF3 PO E | 48 |  |  | 6255 | 6255 | 0
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 48 | 7496 | 2021-11-29 | 2022-02-09 | 0% | PROF4 PO M.PROF4 PO M | 48 |  |  | 7496 | 7496 | 0
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 144 | 17426 | 2021-11-29 | 2022-02-09 | 0% | TECH3 PO D.TECH3 PO D | 144 |  |  | 17426 | 17426 | 0
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 48 | 6439 | 2021-11-29 | 2022-02-09 | 0% | PROF3 PO E.PROF3 PO E | 48 |  |  | 6439 | 6439 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 8 | 1250 | 2022-02-10 | 2022-02-24 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 40 | 4843 | 2022-02-10 | 2022-02-24 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4843 | 4843 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 16 | 1937 | 2022-02-10 | 2022-02-24 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 8 | 1074 | 2022-02-10 | 2022-02-24 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1074 | 1074 | 0
S331400 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - M&S | 92000 | 108883 | 2021-11-29 | 2022-02-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 92000 |  |  | 108883 | 108883 | 0
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | 8 | 1213 | 30-Apr-21 A | 2021-07-28 | 85% | PROF4 PO M.PROF4 PO M | 1.2 |  |  | 181.95 | 181.95 | 0
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | 32 | 3761 | 30-Apr-21 A | 2021-07-28 | 85% | TECH3 PO D.TECH3 PO D | 4.8 |  |  | 564.15 | 564.15 | 0
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | 8 | 1042 | 30-Apr-21 A | 2021-07-28 | 85% | PROF3 PO E.PROF3 PO E | 1.2 |  |  | 156.3 | 156.3 | 0
2.04.01.04 Detector Gas and Cooling Services Systems
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Cooling | 96 | 14137 | 22-Feb-21 A | 2021-07-15 | 33% | PROF4 PO M.PROF4 PO M | 64.32 |  |  | 9471.79 | 9471.79 | 0
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Cooling | 48 | 5478 | 22-Feb-21 A | 2021-07-15 | 33% | TECH3 PO D.TECH3 PO D | 32.16 |  |  | 3670.26 | 3670.26 | 0
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Cooling | 48 | 5478 | 22-Feb-21 A | 2021-07-15 | 33% | TECH3 PO M.TECH3 PO M | 32.16 |  |  | 3670.26 | 3670.26 | 0
S331900 | Review Detector Gas and Cooling Services Systems Design/Safety - CA-D Resource(s) | 16 | 2356 | 08-Jun-21 A | 2021-08-31 | 50% | PROF4 AD.PROF4 AD | 8 |  |  | 1178 | 1178 | 0
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | 20 | 3034 | 2021-09-01 | 2021-09-15 | 0% | PROF4 PO M.PROF4 PO M | 20 |  |  | 3034 | 3034 | 0
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | 16 | 1881 | 2021-09-01 | 2021-09-15 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1881 | 1881 | 0
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | 16 | 1881 | 2021-09-01 | 2021-09-15 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1881 | 1881 | 0
S332200 | Prepare Detector Cooling Services Systems Components Procurement Package(s) | 32 | 4854 | 2021-09-16 | 2021-11-30 | 0% | PROF4 PO M.PROF4 PO M | 32 |  |  | 4854 | 4854 | 0
S332200 | Prepare Detector Cooling Services Systems Components Procurement Package(s) | 72 | 8463 | 2021-09-16 | 2021-11-30 | 0% | TECH3 PO D.TECH3 PO D | 72 |  |  | 8463 | 8463 | 0
S332300 | Evaluate & Process Detector Cooling Services Systems Components Bids | 24 | 3640 | 2021-12-01 | 2022-01-13 | 0% | PROF4 PO M.PROF4 PO M | 24 |  |  | 3640 | 3640 | 0
S332300 | Evaluate & Process Detector Cooling Services Systems Components Bids | 24 | 2821 | 2021-12-01 | 2022-01-13 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821 | 2821 | 0
S332400 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) L | 96 | 14882 | 2022-01-14 | 2022-05-23 | 0% | PROF4 PO M.PROF4 PO M | 96 |  |  | 14882 | 14882 | 0
S332400 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) L | 96 | 11533 | 2022-01-14 | 2022-05-23 | 0% | TECH3 PO D.TECH3 PO D | 96 |  |  | 11533 | 11533 | 0
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 16 | 2500 | 2022-05-24 | 2022-06-21 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2500 | 2500 | 0
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 16 | 1937 | 2022-05-24 | 2022-06-21 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 8 | 969 | 2022-05-24 | 2022-06-21 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S332500 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) M&S | 53000 | 62419 | 2022-01-14 | 2022-05-23 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 53000 |  |  | 62419 | 62419 | 0
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | 16 | 2356 | 15-Jun-21 A | 2021-08-31 | 50% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1178 | 1178 | 0
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | 20 | 2282 | 15-Jun-21 A | 2021-08-31 | 50% | TECH3 PO D.TECH3 PO D | 10 |  |  | 1141 | 1141 | 0
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | 8 | 913 | 15-Jun-21 A | 2021-08-31 | 50% | TECH3 PO M.TECH3 PO M | 4 |  |  | 456.5 | 456.5 | 0
S331710 | Design Coolin Manifolds for EMCal | 8 | 1178 | 18-Mar-20 A | 2021-07-15 | 40% | PROF4 PO E.PROF4 PO E | 4.8 |  |  | 706.8 | 706.8 | 0
S331710 | Design Coolin Manifolds for EMCal | 24 | 2739 | 18-Mar-20 A | 2021-07-15 | 40% | TECH3 PO D.TECH3 PO D | 14.4 |  |  | 1643.4 | 1643.4 | 0
S331730 | Design Coolin Manifolds for INTT | 8 | 1178 | 08-Dec-20 A | 2021-07-15 | 75% | PROF4 PO E.PROF4 PO E | 2 |  |  | 294.5 | 294.5 | 0
S331730 | Design Coolin Manifolds for INTT | 24 | 2739 | 08-Dec-20 A | 2021-07-15 | 75% | TECH3 PO D.TECH3 PO D | 6 |  |  | 684.75 | 684.75 | 0
S331750 | Conceptual Design for Routing Detector Cooling Chiller Systems to Det Manifolds | 8 | 1178 | 23-Feb-21 A | 2021-07-15 | 50% | PROF4 PO E.PROF4 PO E | 4 |  |  | 589 | 589 | 0
S331750 | Conceptual Design for Routing Detector Cooling Chiller Systems to Det Manifolds | 24 | 2739 | 23-Feb-21 A | 2021-07-15 | 50% | TECH3 PO D.TECH3 PO D | 12 |  |  | 1369.5 | 1369.5 | 0
S331760 | Conceptual Design for Cooling Tube Routing from Detector to IHCal manifold | 8 | 1178 | 2021-07-01 | 2021-07-08 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1178 | 1178 | 0
S331760 | Conceptual Design for Cooling Tube Routing from Detector to IHCal manifold | 24 | 2739 | 2021-07-01 | 2021-07-08 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2739 | 2739 | 0
S331770 | Conceptual Design for Cooling Tube Routing from Detector to EMCal manifold | 8 | 1199 | 08-Dec-20 A | 2021-07-15 | 20% | PROF4 PO E.PROF4 PO E | 6.4 |  |  | 959.2 | 959.2 | 0
S331770 | Conceptual Design for Cooling Tube Routing from Detector to EMCal manifold | 24 | 2788 | 08-Dec-20 A | 2021-07-15 | 20% | TECH3 PO D.TECH3 PO D | 19.2 |  |  | 2230.4 | 2230.4 | 0
S331780 | Conceptual Design for Cooling Tube Routing from Detector to TPC manifold | 8 | 1213 | 08-Dec-20 A | 2021-07-15 | 60% | PROF4 PO E.PROF4 PO E | 3.2 |  |  | 485.2 | 485.2 | 0
S331780 | Conceptual Design for Cooling Tube Routing from Detector to TPC manifold | 24 | 2821 | 08-Dec-20 A | 2021-07-15 | 60% | TECH3 PO D.TECH3 PO D | 9.6 |  |  | 1128.4 | 1128.4 | 0
S331790 | Conceptual Design for Cooling Tube Routing from Detector to INTT, MVTX manifold | 16 | 2427 | 14-Dec-20 A | 2021-07-15 | 5% | PROF4 PO E.PROF4 PO E | 15.2 |  |  | 2305.65 | 2305.65 | 0
S331790 | Conceptual Design for Cooling Tube Routing from Detector to INTT, MVTX manifold | 48 | 5642 | 14-Dec-20 A | 2021-07-15 | 5% | TECH3 PO D.TECH3 PO D | 45.6 |  |  | 5359.9 | 5359.9 | 0
S332710 | Conceptual Design for Routing N2 Line from Gas House to N2/Air Manifolds | 8 | 1213 | 18-Dec-20 A | 2021-07-19 | 80% | PROF4 PO M.PROF4 PO M | 1.6 |  |  | 242.6 | 242.6 | 0
S332710 | Conceptual Design for Routing N2 Line from Gas House to N2/Air Manifolds | 16 | 1881 | 18-Dec-20 A | 2021-07-19 | 80% | TECH3 PO D.TECH3 PO D | 3.2 |  |  | 376.2 | 376.2 | 0
S332715 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (MBD) | 8 | 1213 | 15-Feb-21 A | 2021-07-19 | 60% | PROF4 PO M.PROF4 PO M | 3.2 |  |  | 485.2 | 485.2 | 0
S332715 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (MBD) | 16 | 1881 | 15-Feb-21 A | 2021-07-19 | 60% | TECH3 PO D.TECH3 PO D | 6.4 |  |  | 752.4 | 752.4 | 0
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | 8 | 1213 | 18-Dec-20 A | 2021-07-19 | 30% | PROF4 PO M.PROF4 PO M | 5.6 |  |  | 849.1 | 849.1 | 0
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | 16 | 1881 | 18-Dec-20 A | 2021-07-19 | 30% | TECH3 PO D.TECH3 PO D | 11.2 |  |  | 1316.7 | 1316.7 | 0
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | 8 | 1213 | 18-Dec-20 A | 2021-07-19 | 30% | PROF4 PO M.PROF4 PO M | 5.6 |  |  | 849.1 | 849.1 | 0
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | 16 | 1881 | 18-Dec-20 A | 2021-07-19 | 30% | TECH3 PO D.TECH3 PO D | 11.2 |  |  | 1316.7 | 1316.7 | 0
S332730 | Conceptual Design for Gas Tube Routing from Det to Operating Gas Manifolds (TPC) | 8 | 1213 | 22-Dec-20 A | 2021-07-19 | 50% | PROF4 PO M.PROF4 PO M | 4 |  |  | 606.5 | 606.5 | 0
S332730 | Conceptual Design for Gas Tube Routing from Det to Operating Gas Manifolds (TPC) | 16 | 1881 | 22-Dec-20 A | 2021-07-19 | 50% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940.5 | 940.5 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 96 | 14562 | 15-Feb-21 A | 2021-09-24 | 30% | PROF4 PO M.PROF4 PO M | 67.2 |  |  | 10193.4 | 10193.4 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642 | 15-Feb-21 A | 2021-09-24 | 30% | TECH3 PO D.TECH3 PO D | 33.6 |  |  | 3949.4 | 3949.4 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642 | 15-Feb-21 A | 2021-09-24 | 30% | TECH3 PO M.TECH3 PO M | 33.6 |  |  | 3949.4 | 3949.4 | 0
S332740 | Review Detector Gas Service Systems Design/Safety | 8 | 1213 | 2021-07-09 | 2021-07-22 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S332740 | Review Detector Gas Service Systems Design/Safety | 16 | 1881 | 2021-07-09 | 2021-07-22 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1881 | 1881 | 0
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 20 | 3034 | 2021-07-23 | 2021-08-05 | 0% | PROF4 PO M.PROF4 PO M | 20 |  |  | 3034 | 3034 | 0
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 8 | 940 | 2021-07-23 | 2021-08-05 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 8 | 940 | 2021-07-23 | 2021-08-05 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 32 | 4854 | 2021-08-06 | 2021-12-16 | 0% | PROF4 PO M.PROF4 PO M | 32 |  |  | 4854 | 4854 | 0
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 72 | 8463 | 2021-08-06 | 2021-12-16 | 0% | TECH3 PO D.TECH3 PO D | 72 |  |  | 8463 | 8463 | 0
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 3648 | 2021-12-17 | 2022-02-01 | 0% | PROF4 PO M.PROF4 PO M | 24 |  |  | 3648 | 3648 | 0
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 2827 | 2021-12-17 | 2022-02-01 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2827 | 2827 | 0
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 14998 | 2022-02-02 | 2022-07-22 | 0% | PROF4 PO M.PROF4 PO M | 96 |  |  | 14998 | 14998 | 0
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 11623 | 2022-02-02 | 2022-07-22 | 0% | TECH3 PO D.TECH3 PO D | 96 |  |  | 11623 | 11623 | 0
S332770 | Procure & Deliver Detector Gas Services Systems Components - M&S | 54000 | 63930 | 2022-02-02 | 2022-07-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 54000 |  |  | 63930 | 63930 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 2500 | 2022-07-25 | 2022-08-19 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2500 | 2500 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 1937 | 2022-07-25 | 2022-08-19 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 8 | 969 | 2022-07-25 | 2022-08-19 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S332712 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (IHCal) | 8 | 1213 | 15-Feb-21 A | 2021-07-19 | 30% | PROF4 PO M.PROF4 PO M | 5.6 |  |  | 849.1 | 849.1 | 0
S332712 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (IHCal) | 16 | 1881 | 15-Feb-21 A | 2021-07-19 | 30% | TECH3 PO D.TECH3 PO D | 11.2 |  |  | 1316.7 | 1316.7 | 0
S331905 | Review Detector Cooling Services Systems Design/Safety | 16 | 2427 | 01-Jul-21* | 2021-07-15 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2427 | 2427 | 0
2.04.01.05 Detector Safety Subsystems
S332900 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - CA-D Resource(s) | 12 | 1820 | 2021-08-02 | 2021-09-03 | 0% | PROF4 AD.PROF4 AD | 12 |  |  | 1820 | 1820 | 0
S333000 | Review Detector Safety Subsystems Design/Safety - CA-D Resource(s) | 8 | 1213 | 2021-09-07 | 2021-09-20 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1213 | 1213 | 0
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | 8 | 940 | 2021-09-21 | 2021-10-04 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | 16 | 2427 | 2021-09-21 | 2021-10-04 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2427 | 2427 | 0
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | 8 | 940 | 2021-10-05 | 2021-10-19 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | 8 | 1213 | 2021-10-05 | 2021-10-19 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1213 | 1213 | 0
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | 24 | 2821 | 2021-10-20 | 2021-12-03 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821 | 2821 | 0
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | 24 | 3640 | 2021-10-20 | 2021-12-03 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3640 | 3640 | 0
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | 48 | 5780 | 2021-12-06 | 2022-03-03 | 0% | TECH3 PO D.TECH3 PO D | 48 |  |  | 5780 | 5780 | 0
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | 48 | 7459 | 2021-12-06 | 2022-03-03 | 0% | PROF4 PO E.PROF4 PO E | 48 |  |  | 7459 | 7459 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | 4 | 484 | 2022-03-04 | 2022-03-17 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 484 | 484 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | 4 | 484 | 2022-03-04 | 2022-03-17 | 0% | TECH3 PO M.TECH3 PO M | 4 |  |  | 484 | 484 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | 8 | 1250 | 2022-03-04 | 2022-03-17 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | 4 | 484 | 2022-03-04 | 2022-03-17 | 0% | TECH3 PO E.TECH3 PO E | 4 |  |  | 484 | 484 | 0
S333600 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) - M&S | 12000 | 14156 | 2021-12-06 | 2022-03-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 12000 |  |  | 14156 | 14156 | 0
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | 24 | 2821 | 2021-08-02 | 2021-09-03 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821 | 2821 | 0
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | 48 | 7281 | 2021-08-02 | 2021-09-03 | 0% | PROF4 PO E.PROF4 PO E | 48 |  |  | 7281 | 7281 | 0
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | 8 | 940 | 2021-09-07 | 2021-09-20 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | 16 | 2427 | 2021-09-07 | 2021-09-20 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2427 | 2427 | 0
2.04.01.06 Gas Mixing House & Gas Pad Components
S334000 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents C | 8 | 1213 | 01-Apr-21 A | 2021-10-28 | 60% | PROF4 AD.PROF4 AD | 3.2 |  |  | 485.2 | 485.2 | 0
S334100 | Review Gas Mixing House & Gas Pad Components Design/Safety - CA-D Resource(s) | 8 | 1213 | 2021-10-29 | 2021-11-12 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1213 | 1213 | 0
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | 8 | 1213 | 2021-11-15 | 2021-11-30 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S334400 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - CA-D Resource(s) | 2 | 303 | 2021-12-01 | 2022-01-13 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 303 | 303 | 0
S334500 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - CA-D Resource(s) | 2 | 303 | 2022-01-14 | 2022-02-28 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 303 | 303 | 0
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 72 | 11205 | 2022-03-01 | 2022-05-09 | 0% | PROF4 PO M.PROF4 PO M | 72 |  |  | 11205 | 11205 | 0
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 72 | 8683 | 2022-03-01 | 2022-05-09 | 0% | TECH3 PO D.TECH3 PO D | 72 |  |  | 8683 | 8683 | 0
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 72 | 8683 | 2022-03-01 | 2022-05-09 | 0% | TECH3 PO M.TECH3 PO M | 72 |  |  | 8683 | 8683 | 0
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 72 | 8683 | 2022-03-01 | 2022-05-09 | 0% | TECH3 PO E.TECH3 PO E | 72 |  |  | 8683 | 8683 | 0
S334800 | Perform Gas Mixing House & Gas Pad Components Acceptance - CA-D Resource(s) | 2 | 312 | 2022-05-10 | 2022-05-23 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 312 | 312 | 0
S334700 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - M&S | 10000 | 11808 | 2022-03-01 | 2022-05-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 |  |  | 11808 | 11808 | 0
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | 24 | 3640 | 01-Apr-21 A | 2021-10-28 | 60% | PROF4 PO M.PROF4 PO M | 9.6 |  |  | 1456 | 1456 | 0
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | 60 | 7053 | 01-Apr-21 A | 2021-10-28 | 60% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821.2 | 2821.2 | 0
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | 24 | 2821 | 01-Apr-21 A | 2021-10-28 | 60% | TECH3 PO M.TECH3 PO M | 9.6 |  |  | 1128.4 | 1128.4 | 0
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | 24 | 2821 | 01-Apr-21 A | 2021-10-28 | 60% | TECH3 PO E.TECH3 PO E | 9.6 |  |  | 1128.4 | 1128.4 | 0
S1003119 | Review Gas Mixing House & Gas Pad Components Design/Safety - Physics Resource(s) | 8 | 1213 | 2021-10-29 | 2021-11-12 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S1003119 | Review Gas Mixing House & Gas Pad Components Design/Safety - Physics Resource(s) | 8 | 940 | 2021-10-29 | 2021-11-12 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 24 | 3640 | 2021-12-01 | 2022-01-13 | 0% | PROF4 PO M.PROF4 PO M | 24 |  |  | 3640 | 3640 | 0
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 24 | 2821 | 2021-12-01 | 2022-01-13 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821 | 2821 | 0
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 24 | 2821 | 2021-12-01 | 2022-01-13 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2821 | 2821 | 0
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 24 | 2821 | 2021-12-01 | 2022-01-13 | 0% | TECH3 PO E.TECH3 PO E | 24 |  |  | 2821 | 2821 | 0
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 24 | 3640 | 2022-01-14 | 2022-02-28 | 0% | PROF4 PO M.PROF4 PO M | 24 |  |  | 3640 | 3640 | 0
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 24 | 2821 | 2022-01-14 | 2022-02-28 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821 | 2821 | 0
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 24 | 2821 | 2022-01-14 | 2022-02-28 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2821 | 2821 | 0
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 24 | 2821 | 2022-01-14 | 2022-02-28 | 0% | TECH3 PO E.TECH3 PO E | 24 |  |  | 2821 | 2821 | 0
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 8 | 1250 | 2022-05-10 | 2022-05-23 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 8 | 969 | 2022-05-10 | 2022-05-23 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 8 | 969 | 2022-05-10 | 2022-05-23 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 8 | 969 | 2022-05-10 | 2022-05-23 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
2.04.01.07 Rack Room Modifications
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | 8 | 961 | 2021-07-01 | 2021-08-26 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 961 | 961 | 0
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | 32 | 4959 | 2021-07-01 | 2021-08-26 | 0% | PROF4 PO E.PROF4 PO E | 32 |  |  | 4959 | 4959 | 0
S335200 | Review Rack Room Modifications Components Design/Safety | 8 | 1461 | 2021-08-27 | 2021-09-10 | 0% | SCI3 PO.SCI3 PO | 8 |  |  | 1461 | 1461 | 0
S335200 | Review Rack Room Modifications Components Design/Safety | 8 | 1250 | 2021-08-27 | 2021-09-10 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 8 | 1461 | 2021-09-13 | 2021-09-24 | 0% | SCI3 PO.SCI3 PO | 8 |  |  | 1461 | 1461 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 16 | 1937 | 2021-09-13 | 2021-09-24 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 8 | 969 | 2021-09-13 | 2021-09-24 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 8 | 1250 | 2021-09-13 | 2021-09-24 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 8 | 969 | 2021-09-13 | 2021-09-24 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S335500 | Prepare Rack Room Modifications Components Procurement Package(s) - CA-D Resource(s) | 2 | 312 | 2021-09-27 | 2021-11-08 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 312 | 312 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 8 | 969 | 2021-11-09 | 2021-12-09 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 16 | 1937 | 2021-11-09 | 2021-12-09 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1937 | 1937 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 16 | 2500 | 2021-11-09 | 2021-12-09 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2500 | 2500 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 16 | 1937 | 2021-11-09 | 2021-12-09 | 0% | TECH3 PO E.TECH3 PO E | 16 |  |  | 1937 | 1937 | 0
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 24 | 2906 | 2021-12-10 | 2022-03-09 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2906 | 2906 | 0
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 48 | 5811 | 2021-12-10 | 2022-03-09 | 0% | TECH3 PO M.TECH3 PO M | 48 |  |  | 5811 | 5811 | 0
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 48 | 7499 | 2021-12-10 | 2022-03-09 | 0% | PROF4 PO E.PROF4 PO E | 48 |  |  | 7499 | 7499 | 0
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 48 | 5811 | 2021-12-10 | 2022-03-09 | 0% | TECH3 PO E.TECH3 PO E | 48 |  |  | 5811 | 5811 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | 8 | 1461 | 2022-05-05 | 2022-05-18 | 0% | SCI3 PO.SCI3 PO | 8 |  |  | 1461 | 1461 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | 4 | 484 | 2022-05-05 | 2022-05-18 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 484 | 484 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | 8 | 969 | 2022-05-05 | 2022-05-18 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | 8 | 1250 | 2022-05-05 | 2022-05-18 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | 8 | 969 | 2022-05-05 | 2022-05-18 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S335800 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - M&S | 20000 | 23678 | 2021-12-10 | 2022-03-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 20000 |  |  | 23678 | 23678 | 0
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 2906 | 2021-09-27 | 2021-11-08 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2906 | 2906 | 0
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 3750 | 2021-09-27 | 2021-11-08 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3750 | 3750 | 0
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 2906 | 2021-09-27 | 2021-11-08 | 0% | TECH3 PO E.TECH3 PO E | 24 |  |  | 2906 | 2906 | 0
2.04.01.08 Control Room and Offices Modifications
S336100 | Analyze Control Room and Offices Modifications Requirements - CA-D Resource(s) | 4 | 625 | 2021-09-27 | 2021-10-08 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 625 | 625 | 0
S336200 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents C | 2 | 312 | 2021-10-12 | 2021-10-18 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 312 | 312 | 0
S336300 | Review Control Room and Offices Modifications Design/Safety | 4 | 730 | 2021-10-19 | 2021-10-25 | 0% | SCI3 PO.SCI3 PO | 4 |  |  | 730 | 730 | 0
S336300 | Review Control Room and Offices Modifications Design/Safety | 4 | 625 | 2021-10-19 | 2021-10-25 | 0% | PROF4 PO E.PROF4 PO E | 4 |  |  | 625 | 625 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 1461 | 2021-10-26 | 2021-11-08 | 0% | SCI3 PO.SCI3 PO | 8 |  |  | 1461 | 1461 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 969 | 2021-10-26 | 2021-11-08 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 969 | 2021-10-26 | 2021-11-08 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 1250 | 2021-10-26 | 2021-11-08 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 8 | 969 | 2021-10-26 | 2021-11-08 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S336600 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - CA-D Resource(s) | 2 | 312 | 2021-11-09 | 2021-12-23 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 312 | 312 | 0
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 8 | 1250 | 2021-12-27 | 2022-01-10 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 48 | 5811 | 2022-01-11 | 2022-02-23 | 0% | TECH3 PO D.TECH3 PO D | 48 |  |  | 5811 | 5811 | 0
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 24 | 2906 | 2022-01-11 | 2022-02-23 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2906 | 2906 | 0
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 24 | 3750 | 2022-01-11 | 2022-02-23 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3750 | 3750 | 0
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 24 | 2906 | 2022-01-11 | 2022-02-23 | 0% | TECH3 PO E.TECH3 PO E | 24 |  |  | 2906 | 2906 | 0
S337000 | Perform Control Room and Offices Modifications Components Acceptance - CA-D Resource(s) | 2 | 312 | 2022-02-25 | 2022-03-10 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 312 | 312 | 0
S336900 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - M&S | 50000 | 59195 | 2022-01-12 | 2022-02-24 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 |  |  | 59195 | 59195 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 8 | 1461 | 2021-09-27 | 2021-10-08 | 0% | SCI3 PO.SCI3 PO | 8 |  |  | 1461 | 1461 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 8 | 969 | 2021-09-27 | 2021-10-08 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 8 | 969 | 2021-09-27 | 2021-10-08 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 8 | 969 | 2021-09-27 | 2021-10-08 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 8 | 1250 | 2021-09-27 | 2021-10-08 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | 8 | 969 | 2021-10-12 | 2021-10-18 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | 4 | 625 | 2021-10-12 | 2021-10-18 | 0% | PROF4 PO E.PROF4 PO E | 4 |  |  | 625 | 625 | 0
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 2906 | 2021-11-09 | 2021-12-23 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2906 | 2906 | 0
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 3750 | 2021-11-09 | 2021-12-23 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3750 | 3750 | 0
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 24 | 2906 | 2021-11-09 | 2021-12-23 | 0% | TECH3 PO E.TECH3 PO E | 24 |  |  | 2906 | 2906 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 8 | 1461 | 2022-02-25 | 2022-03-10 | 0% | SCI3 PO.SCI3 PO | 8 |  |  | 1461 | 1461 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 4 | 484 | 2022-02-25 | 2022-03-10 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 484 | 484 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 8 | 969 | 2022-02-25 | 2022-03-10 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 8 | 1250 | 2022-02-25 | 2022-03-10 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 8 | 969 | 2022-02-25 | 2022-03-10 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
2.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR
S277000 | 2022 Facility Support Systems L3 Project Management | 352 | 37426 | 2021-10-01 | 2022-09-30 | 0% | PROF2 AD.PROF2 AD | 352 |  |  | 37426 | 37426 | 0
S277100 | 2023 Facility Support Systems L3 Project Management | 113 | 12375 | 2022-10-03 | 2022-10-07 | 0% | PROF2 AD.PROF2 AD | 113 |  |  | 12375 | 12375 | 0
2.04.02.02 Beampipe/Vacuum
S339300 | Perform Beampipe/vacuum Acceptance - Physics Resource(s) | 8 | 965 | 2021-07-01 | 2022-04-20 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 965 | 965 | 0
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) | 40 | 4824 | 2021-07-01 | 2022-04-20 | 0% | TECH3 AD.TECH3 AD | 40 |  |  | 4824 | 4824 | 0
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) | 16 | 2490 | 2021-07-01 | 2022-04-20 | 0% | PROF4 AD.PROF4 AD | 16 |  |  | 2490 | 2490 | 0
S339350 | NEG Re-coating of beryllium beampipe | 100000 | 111561 | 01-Jul-21* | 2022-07-15 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 100000 |  |  | 111561 | 111561 | 0
2.04.02.03 IR HVAC
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | 8 | 1076 | 21-Dec-20 A | 2021-07-19 | 50% | TECH4 AD.TECH4 AD | 4 |  |  | 538 | 538 | 0
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | 32 | 3303 | 21-Dec-20 A | 2021-07-19 | 50% | PROF2 AD.PROF2 AD | 16 |  |  | 1651.5 | 1651.5 | 0
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | 8 | 1213 | 21-Dec-20 A | 2021-07-19 | 50% | PROF4 AD.PROF4 AD | 4 |  |  | 606.5 | 606.5 | 0
S339800 | Review IR HVAC Design/Safety | 4 | 538 | 2021-07-20 | 2021-07-26 | 0% | TECH4 AD.TECH4 AD | 4 |  |  | 538 | 538 | 0
S339800 | Review IR HVAC Design/Safety | 8 | 826 | 2021-07-20 | 2021-07-26 | 0% | PROF2 AD.PROF2 AD | 8 |  |  | 826 | 826 | 0
S339800 | Review IR HVAC Design/Safety | 4 | 607 | 2021-07-20 | 2021-07-26 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | 8 | 1076 | 2021-07-27 | 2021-08-09 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | 16 | 1652 | 2021-07-27 | 2021-08-09 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | 8 | 1213 | 2021-07-27 | 2021-08-09 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1213 | 1213 | 0
S340100 | Prepare IR HVAC Components Procurement Package(s) | 16 | 2152 | 2021-08-10 | 2021-09-07 | 0% | TECH4 AD.TECH4 AD | 16 |  |  | 2152 | 2152 | 0
S340100 | Prepare IR HVAC Components Procurement Package(s) | 32 | 3303 | 2021-08-10 | 2021-09-07 | 0% | PROF2 AD.PROF2 AD | 32 |  |  | 3303 | 3303 | 0
S340100 | Prepare IR HVAC Components Procurement Package(s) | 4 | 607 | 2021-08-10 | 2021-09-07 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | 16 | 2152 | 2021-09-08 | 2021-10-05 | 0% | TECH4 AD.TECH4 AD | 16 |  |  | 2152 | 2152 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | 32 | 3303 | 2021-09-08 | 2021-10-05 | 0% | PROF2 AD.PROF2 AD | 32 |  |  | 3303 | 3303 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | 4 | 607 | 2021-09-08 | 2021-10-05 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | 48 | 6457 | 2021-10-06 | 2022-01-05 | 0% | TECH4 AD.TECH4 AD | 48 |  |  | 6457 | 6457 | 0
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | 96 | 9910 | 2021-10-06 | 2022-01-05 | 0% | PROF2 AD.PROF2 AD | 96 |  |  | 9910 | 9910 | 0
S340400 | Perform IR HVAC Components Acceptance | 40 | 4702 | 2022-01-06 | 2022-01-20 | 0% | TECH3 AD.TECH3 AD | 40 |  |  | 4702 | 4702 | 0
S340400 | Perform IR HVAC Components Acceptance | 8 | 1076 | 2022-01-06 | 2022-01-20 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S340400 | Perform IR HVAC Components Acceptance | 16 | 1652 | 2022-01-06 | 2022-01-20 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S340400 | Perform IR HVAC Components Acceptance | 2 | 303 | 2022-01-06 | 2022-01-20 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 303 | 303 | 0
S339500 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - M&S | 35000 | 40624 | 2021-10-06 | 2022-01-05 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 35000 |  |  | 40624 | 40624 | 0
2.04.02.04 IR Electronics Cooling Water Distribution System
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | 32 | 4304 | 21-Dec-20 A | 2021-07-19 | 80% | TECH4 AD.TECH4 AD | 6.4 |  |  | 860.8 | 860.8 | 0
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | 64 | 6606 | 21-Dec-20 A | 2021-07-19 | 80% | PROF2 AD.PROF2 AD | 12.8 |  |  | 1321.2 | 1321.2 | 0
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | 4 | 607 | 21-Dec-20 A | 2021-07-19 | 80% | PROF4 AD.PROF4 AD | 0.8 |  |  | 121.4 | 121.4 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | 8 | 1076 | 2021-07-20 | 2021-08-02 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | 16 | 1652 | 2021-07-20 | 2021-08-02 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | 4 | 607 | 2021-07-20 | 2021-08-02 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 8 | 1076 | 2021-08-03 | 2021-08-16 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 16 | 1652 | 2021-08-03 | 2021-08-16 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 2 | 303 | 2021-08-03 | 2021-08-16 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 303 | 303 | 0
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 16 | 2152 | 2021-08-17 | 2021-09-14 | 0% | TECH4 AD.TECH4 AD | 16 |  |  | 2152 | 2152 | 0
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 32 | 3303 | 2021-08-17 | 2021-09-14 | 0% | PROF2 AD.PROF2 AD | 32 |  |  | 3303 | 3303 | 0
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 4 | 607 | 2021-08-17 | 2021-09-14 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 16 | 2152 | 2021-09-15 | 2021-10-13 | 0% | TECH4 AD.TECH4 AD | 16 |  |  | 2152 | 2152 | 0
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 32 | 3303 | 2021-09-15 | 2021-10-13 | 0% | PROF2 AD.PROF2 AD | 32 |  |  | 3303 | 3303 | 0
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 4 | 607 | 2021-09-15 | 2021-10-13 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 40 | 5526 | 26-Apr-21 A | 2021-10-26 | 50% | TECH4 AD.TECH4 AD | 20 |  |  | 2763 | 2763 | 0
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 80 | 8481 | 26-Apr-21 A | 2021-10-26 | 50% | PROF2 AD.PROF2 AD | 40 |  |  | 4240.5 | 4240.5 | 0
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 2 | 312 | 26-Apr-21 A | 2021-10-26 | 50% | PROF4 AD.PROF4 AD | 1 |  |  | 156 | 156 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 20 | 2421 | 2022-01-13 | 2022-01-20 | 0% | TECH3 AD.TECH3 AD | 20 |  |  | 2421 | 2421 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 4 | 554 | 2022-01-13 | 2022-01-20 | 0% | TECH4 AD.TECH4 AD | 4 |  |  | 554 | 554 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 8 | 851 | 2022-01-13 | 2022-01-20 | 0% | PROF2 AD.PROF2 AD | 8 |  |  | 851 | 851 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 4 | 625 | 2022-01-13 | 2022-01-20 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 625 | 625 | 0
S340600 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - M&S | 65000 | 76953 | 26-Apr-21 A | 2022-01-12 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 32500 |  |  | 38476.5 | 38476.5 | 0
2.04.02.05 IR/AH Safety Subsystems
S341800 | Analyze IR/AH Safety Subsystems Requirements - Physics Resource(s) | 3 | 532 | 14-Dec-20 A | 2021-07-30 | 25% | SCI3 PO.SCI3 PO | 2.25 |  |  | 399 | 399 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 60 | 8071 | 2021-08-02 | 2021-09-13 | 0% | TECH4 AD.TECH4 AD | 60 |  |  | 8071 | 8071 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 96 | 9910 | 2021-08-02 | 2021-09-13 | 0% | PROF2 AD.PROF2 AD | 96 |  |  | 9910 | 9910 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 8 | 1213 | 2021-08-02 | 2021-09-13 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1213 | 1213 | 0
S342000 | Review IR/AH Safety Subsystems Design/Safety | 8 | 1076 | 2021-09-14 | 2021-09-27 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S342000 | Review IR/AH Safety Subsystems Design/Safety | 32 | 3303 | 2021-09-14 | 2021-09-27 | 0% | PROF2 AD.PROF2 AD | 32 |  |  | 3303 | 3303 | 0
S342000 | Review IR/AH Safety Subsystems Design/Safety | 8 | 1213 | 2021-09-14 | 2021-09-27 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1213 | 1213 | 0
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 8 | 1076 | 2021-09-28 | 2021-10-12 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 32 | 3303 | 2021-09-28 | 2021-10-12 | 0% | PROF2 AD.PROF2 AD | 32 |  |  | 3303 | 3303 | 0
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 4 | 607 | 2021-09-28 | 2021-10-12 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 8 | 1076 | 2021-10-13 | 2021-10-26 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 16 | 1652 | 2021-10-13 | 2021-10-26 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 4 | 607 | 2021-10-13 | 2021-10-26 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 24 | 3228 | 2021-10-27 | 2021-12-10 | 0% | TECH4 AD.TECH4 AD | 24 |  |  | 3228 | 3228 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 48 | 4955 | 2021-10-27 | 2021-12-10 | 0% | PROF2 AD.PROF2 AD | 48 |  |  | 4955 | 4955 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 4 | 607 | 2021-10-27 | 2021-12-10 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 48 | 6457 | 2021-12-13 | 2022-03-10 | 0% | TECH4 AD.TECH4 AD | 48 |  |  | 6457 | 6457 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 96 | 9910 | 2021-12-13 | 2022-03-10 | 0% | PROF2 AD.PROF2 AD | 96 |  |  | 9910 | 9910 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 2 | 303 | 2021-12-13 | 2022-03-10 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 303 | 303 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 88 | 11837 | 2022-03-11 | 2022-03-24 | 0% | TECH4 AD.TECH4 AD | 88 |  |  | 11837 | 11837 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 16 | 1652 | 2022-03-11 | 2022-03-24 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 4 | 607 | 2022-03-11 | 2022-03-24 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - M&S | 32000 | 37142 | 2021-12-13 | 2022-03-10 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 32000 |  |  | 37142 | 37142 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 72 | 9685 | 14-Dec-20 A | 2021-07-30 | 25% | TECH4 AD.TECH4 AD | 54 |  |  | 7263.75 | 7263.75 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 96 | 9910 | 14-Dec-20 A | 2021-07-30 | 25% | PROF2 AD.PROF2 AD | 72 |  |  | 7432.5 | 7432.5 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 10 | 1517 | 14-Dec-20 A | 2021-07-30 | 25% | PROF4 AD.PROF4 AD | 7.5 |  |  | 1137.75 | 1137.75 | 0
2.04.02.06 Assembly Hall and Interaction Region Modifications
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | 24 | 3228 | 2021-07-01 | 2021-08-12 | 0% | TECH4 AD.TECH4 AD | 24 |  |  | 3228 | 3228 | 0
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | 48 | 4955 | 2021-07-01 | 2021-08-12 | 0% | PROF2 AD.PROF2 AD | 48 |  |  | 4955 | 4955 | 0
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | 20 | 3034 | 2021-07-01 | 2021-08-12 | 0% | PROF4 AD.PROF4 AD | 20 |  |  | 3034 | 3034 | 0
S343100 | Review Assembly Hall Modifications Design/Safety | 8 | 1076 | 2021-08-13 | 2021-08-26 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S343100 | Review Assembly Hall Modifications Design/Safety | 16 | 1652 | 2021-08-13 | 2021-08-26 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S343100 | Review Assembly Hall Modifications Design/Safety | 5 | 758 | 2021-08-13 | 2021-08-26 | 0% | PROF4 AD.PROF4 AD | 5 |  |  | 758 | 758 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 8 | 1076 | 2021-08-27 | 2021-09-10 | 0% | TECH4 AD.TECH4 AD | 8 |  |  | 1076 | 1076 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 16 | 1652 | 2021-08-27 | 2021-09-10 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 5 | 758 | 2021-08-27 | 2021-09-10 | 0% | PROF4 AD.PROF4 AD | 5 |  |  | 758 | 758 | 0
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 72 | 9685 | 2021-09-13 | 2021-10-25 | 0% | TECH4 AD.TECH4 AD | 72 |  |  | 9685 | 9685 | 0
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 48 | 4955 | 2021-09-13 | 2021-10-25 | 0% | PROF2 AD.PROF2 AD | 48 |  |  | 4955 | 4955 | 0
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 4 | 607 | 2021-09-13 | 2021-10-25 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 72 | 9685 | 2021-10-26 | 2021-12-09 | 0% | TECH4 AD.TECH4 AD | 72 |  |  | 9685 | 9685 | 0
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 48 | 4955 | 2021-10-26 | 2021-12-09 | 0% | PROF2 AD.PROF2 AD | 48 |  |  | 4955 | 4955 | 0
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 2 | 303 | 2021-10-26 | 2021-12-09 | 0% | PROF4 AD.PROF4 AD | 2 |  |  | 303 | 303 | 0
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 72 | 9685 | 2021-12-10 | 2022-04-20 | 0% | TECH4 AD.TECH4 AD | 72 |  |  | 9685 | 9685 | 0
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 144 | 14865 | 2021-12-10 | 2022-04-20 | 0% | PROF2 AD.PROF2 AD | 144 |  |  | 14865 | 14865 | 0
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 8 | 1213 | 2021-12-10 | 2022-04-20 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1213 | 1213 | 0
S343700 | Perform Assembly Hall Modifications Components Acceptance | 24 | 3228 | 2022-04-21 | 2022-05-04 | 0% | TECH4 AD.TECH4 AD | 24 |  |  | 3228 | 3228 | 0
S343700 | Perform Assembly Hall Modifications Components Acceptance | 16 | 1652 | 2022-04-21 | 2022-05-04 | 0% | PROF2 AD.PROF2 AD | 16 |  |  | 1652 | 1652 | 0
S342800 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - M&S | 10000 | 11607 | 2021-12-10 | 2022-04-20 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 |  |  | 11607 | 11607 | 0
S343842 | Start Track Modification - IR BNL Oversight of Construction | 108 | 13663 | 2021-08-31 | 2021-10-12 | 0% | PROF3 AD.PROF3 AD | 108 |  |  | 13663 | 13663 | 0
S343842 | Start Track Modification - IR BNL Oversight of Construction | 24 | 3534 | 2021-08-31 | 2021-10-12 | 0% | PROF4 AD.PROF4 AD | 24 |  |  | 3534 | 3534 | 0
S343844 | Start Track Modification - IR Delivery Acceptance Labor | 16 | 2024 | 2021-10-13 | 2021-10-19 | 0% | PROF3 AD.PROF3 AD | 16 |  |  | 2024 | 2024 | 0
S343844 | Start Track Modification - IR Delivery Acceptance Labor | 8 | 1178 | 2021-10-13 | 2021-10-19 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1178 | 1178 | 0
S343845 | Start Track Modification - IR Delivery Acceptance M&S | 140000 | 162496 | 2021-10-13 | 2021-10-19 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 140000 |  |  | 162496 | 162496 | 0
S343849 | Addition of ReBar plus Concrete Forming and Placement for IR Tracks - Acceptance | 550000 | 613587 | 2021-12-21 | 2021-12-21 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 550000 |  |  | 613587 | 613587 | 0
2.05.02 Infrastructure Installation
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 32 | 4961 | 2022-02-23 | 2022-03-22 | 0% | PROF4 AD.PROF4 AD | 32 |  |  | 4961 | 4961 | 0
S346300 | Install Beampipe/Vacuum/Bakeout - Labor - Physics Resource(s) | 20 | 3125 | 2022-08-01 | 2022-08-09 | 0% | PROF4 PO M.PROF4 PO M | 20 |  |  | 3125 | 3125 | 0
S346300 | Install Beampipe/Vacuum/Bakeout - Labor - Physics Resource(s) | 40 | 4843 | 2022-08-01 | 2022-08-09 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4843 | 4843 | 0
S346300 | Install Beampipe/Vacuum/Bakeout - Labor - Physics Resource(s) | 16 | 1937 | 2022-08-01 | 2022-08-09 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4702 | 2022-01-21 | 2022-02-03 | 0% | TECH3 AD.TECH3 AD | 40 |  |  | 4702 | 4702 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 64 | 8245 | 2022-01-21 | 2022-02-03 | 0% | CRAFT3.CRAFT3 | 64 |  |  | 8245 | 8245 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4129 | 2022-01-21 | 2022-02-03 | 0% | PROF2 AD.PROF2 AD | 40 |  |  | 4129 | 4129 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 6067 | 2022-01-21 | 2022-02-03 | 0% | PROF4 AD.PROF4 AD | 40 |  |  | 6067 | 6067 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 80 | 9686 | 2022-01-21 | 2022-02-17 | 0% | TECH3 AD.TECH3 AD | 80 |  |  | 9686 | 9686 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 80 | 10615 | 2022-01-21 | 2022-02-17 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10615 | 10615 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 20 | 2126 | 2022-01-21 | 2022-02-17 | 0% | PROF2 AD.PROF2 AD | 20 |  |  | 2126 | 2126 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 8 | 1250 | 2022-01-21 | 2022-02-17 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S345800 | Install On Detector Safety Subsystems - Labor | 80 | 9686 | 2022-03-18 | 2022-04-14 | 0% | TECH3 PO E.TECH3 PO E | 80 |  |  | 9686 | 9686 | 0
S345800 | Install On Detector Safety Subsystems - Labor | 40 | 4843 | 2022-03-18 | 2022-04-14 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4843 | 4843 | 0
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3125 | 2022-03-18 | 2022-04-14 | 0% | PROF4 PO E.PROF4 PO E | 20 |  |  | 3125 | 3125 | 0
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3125 | 2022-03-18 | 2022-04-14 | 0% | PROF4 PO M.PROF4 PO M | 20 |  |  | 3125 | 3125 | 0
S346900 | Install Detector Support Services Systems - Labor - CA-D Resource(s) | 40 | 4253 | 2022-06-06 | 2022-07-05 | 0% | PROF2 AD.PROF2 AD | 40 |  |  | 4253 | 4253 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 120 | 18748 | 2022-02-25 | 2022-05-19 | 0% | PROF4 PO M.PROF4 PO M | 120 |  |  | 18748 | 18748 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 280 | 33900 | 2022-02-25 | 2022-05-19 | 0% | TECH3 PO E.TECH3 PO E | 280 |  |  | 33900 | 33900 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 280 | 33900 | 2022-02-25 | 2022-05-19 | 0% | TECH3 PO M.TECH3 PO M | 280 |  |  | 33900 | 33900 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 48 | 5811 | 2022-02-25 | 2022-05-19 | 0% | TECH3 PO D.TECH3 PO D | 48 |  |  | 5811 | 5811 | 0
S347100 | Install Electronics Racks Rackroom - Labor | 120 | 18748 | 2022-02-25 | 2022-05-19 | 0% | PROF4 PO E.PROF4 PO E | 120 |  |  | 18748 | 18748 | 0
S347400 | Install Gas and Cooling System Services - Labor | 120 | 18748 | 2022-06-22 | 2022-08-17 | 0% | PROF4 PO M.PROF4 PO M | 120 |  |  | 18748 | 18748 | 0
S347400 | Install Gas and Cooling System Services - Labor | 720 | 87172 | 2022-06-22 | 2022-08-17 | 0% | TECH3 PO M.TECH3 PO M | 720 |  |  | 87172 | 87172 | 0
S347400 | Install Gas and Cooling System Services - Labor | 96 | 11623 | 2022-06-22 | 2022-08-17 | 0% | TECH3 PO D.TECH3 PO D | 96 |  |  | 11623 | 11623 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 12499 | 2022-05-24 | 2022-07-13 | 0% | PROF4 PO M.PROF4 PO M | 80 |  |  | 12499 | 12499 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 160 | 19372 | 2022-05-24 | 2022-07-13 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 160 | 19372 | 2022-05-24 | 2022-07-13 | 0% | TECH3 PO M.TECH3 PO M | 160 |  |  | 19372 | 19372 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 40 | 4843 | 2022-05-24 | 2022-07-13 | 0% | TECH3 PO D.TECH3 PO D | 40 |  |  | 4843 | 4843 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 12499 | 2022-05-24 | 2022-07-13 | 0% | PROF4 PO E.PROF4 PO E | 80 |  |  | 12499 | 12499 | 0
S346200 | Install Line Electric Power Distribution Off Detector - M&S | 500 | 589 | 2022-02-23 | 2022-03-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 589 | 589 | 0
S346400 | Install Beampipe/Vacuum/Bakeout - M&S | 500 | 592 | 2022-08-01 | 2022-08-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S345600 | Install IR HVAC - M&S | 500 | 580 | 2022-01-21 | 2022-02-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 580 | 580 | 0
S347800 | Install IR Electronics Cooling Water Off Detector - M&S | 500 | 592 | 2022-01-21 | 2022-02-17 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S345900 | Install On Detector Safety Subsystems - M&S | 500 | 592 | 2022-03-18 | 2022-04-14 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S347000 | Install Detector Support Services Systems - M&S | 500 | 592 | 2022-06-06 | 2022-07-05 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S347300 | Install Electronics Racks Rackroom - M&S | 500 | 592 | 2022-02-25 | 2022-05-19 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S347500 | Install Gas and Cooling System Services - M&S | 500 | 592 | 2022-06-22 | 2022-08-17 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S346800 | Install Non-IR Infrastructure - M&S | 500 | 592 | 2022-05-24 | 2022-07-13 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 80 | 9404 | 2022-03-25 | 2022-04-21 | 0% | TECH3 AD.TECH3 AD | 80 |  |  | 9404 | 9404 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 16 | 2427 | 2022-03-25 | 2022-04-21 | 0% | PROF4 AD.PROF4 AD | 16 |  |  | 2427 | 2427 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 40 | 4129 | 2022-03-25 | 2022-04-21 | 0% | PROF2 AD.PROF2 AD | 40 |  |  | 4129 | 4129 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 24 | 3092 | 2022-03-25 | 2022-04-21 | 0% | CRAFT3.CRAFT3 | 24 |  |  | 3092 | 3092 | 0
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 32 | 4999 | 2022-03-23 | 2022-04-19 | 0% | PROF4 AD.PROF4 AD | 32 |  |  | 4999 | 4999 | 0
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 4 | 819 | 2022-03-23 | 2022-04-19 | 0% | PROF6 AD.PROF6 AD | 4 |  |  | 819 | 819 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18748 | 2022-05-20 | 2022-08-15 | 0% | PROF4 PO M.PROF4 PO M | 120 |  |  | 18748 | 18748 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 33900 | 2022-05-20 | 2022-08-15 | 0% | TECH3 PO E.TECH3 PO E | 280 |  |  | 33900 | 33900 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 33900 | 2022-05-20 | 2022-08-15 | 0% | TECH3 PO M.TECH3 PO M | 280 |  |  | 33900 | 33900 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 48 | 5811 | 2022-05-20 | 2022-08-15 | 0% | TECH3 PO D.TECH3 PO D | 48 |  |  | 5811 | 5811 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18748 | 2022-05-20 | 2022-08-15 | 0% | PROF4 PO E.PROF4 PO E | 120 |  |  | 18748 | 18748 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 80 | 9686 | 2022-01-04 | 2022-02-01 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 16 | 1937 | 2022-01-04 | 2022-02-01 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 32 | 4246 | 2022-01-04 | 2022-02-01 | 0% | CRAFT3.CRAFT3 | 32 |  |  | 4246 | 4246 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 20 | 3125 | 2022-01-04 | 2022-02-01 | 0% | PROF4 PO E.PROF4 PO E | 20 |  |  | 3125 | 3125 | 0
S345910 | Install Off Detector Safety Subsystems - M&S | 500 | 580 | 2022-03-25 | 2022-04-21 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 580 | 580 | 0
S346210 | Install Line Electric Power Distribution On Detector - M&S | 500 | 592 | 2022-03-23 | 2022-04-19 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S347810 | Install IR Electronics Cooling Water On Detector - M&S | 500 | 592 | 2022-01-04 | 2022-02-01 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S347310 | Install Electronics Racks On Carriage - M&S | 500 | 592 | 2022-05-20 | 2022-08-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | 80 | 9686 | 2022-08-01 | 2022-08-09 | 0% | TECH3 AD.TECH3 AD | 80 |  |  | 9686 | 9686 | 0
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | 80 | 8506 | 2022-08-01 | 2022-08-09 | 0% | PROF2 AD.PROF2 AD | 80 |  |  | 8506 | 8506 | 0
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | 24 | 2906 | 2022-08-01 | 2022-08-09 | 0% | TECH3 AD.TECH3 AD | 24 |  |  | 2906 | 2906 | 0
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | 40 | 6249 | 2022-08-01 | 2022-08-09 | 0% | PROF4 AD.PROF4 AD | 40 |  |  | 6249 | 6249 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 160 | 19372 | 2022-05-24 | 2022-07-13 | 0% | TECH3 AD.TECH3 AD | 160 |  |  | 19372 | 19372 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 160 | 21230 | 2022-05-24 | 2022-07-13 | 0% | CRAFT3.CRAFT3 | 160 |  |  | 21230 | 21230 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 20 | 2126 | 2022-05-24 | 2022-07-13 | 0% | PROF2 AD.PROF2 AD | 20 |  |  | 2126 | 2126 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 8 | 1250 | 2022-05-24 | 2022-07-13 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 32 | 3874 | 2022-06-06 | 2022-07-05 | 0% | TECH3 PO D.TECH3 PO D | 32 |  |  | 3874 | 3874 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 200 | 26538 | 2022-06-06 | 2022-07-05 | 0% | CRAFT3.CRAFT3 | 200 |  |  | 26538 | 26538 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 80 | 12499 | 2022-06-06 | 2022-07-05 | 0% | PROF4 PO E.PROF4 PO E | 80 |  |  | 12499 | 12499 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 200 | 24214 | 2022-06-06 | 2022-07-05 | 0% | TECH3 PO E.TECH3 PO E | 200 |  |  | 24214 | 24214 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 200 | 24214 | 2022-06-06 | 2022-07-05 | 0% | TECH3 PO M.TECH3 PO M | 200 |  |  | 24214 | 24214 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 160 | 21065 | 2022-02-23 | 2022-03-22 | 0% | CRAFT3.CRAFT3 | 160 |  |  | 21065 | 21065 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 40 | 6201 | 2022-02-23 | 2022-03-22 | 0% | PROF4 PO E.PROF4 PO E | 40 |  |  | 6201 | 6201 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 4 | 813 | 2022-02-23 | 2022-03-22 | 0% | PROF6 AD.PROF6 AD | 4 |  |  | 813 | 813 | 0
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 80 | 10615 | 2022-03-23 | 2022-04-19 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10615 | 10615 | 0
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 40 | 6249 | 2022-03-23 | 2022-04-19 | 0% | PROF4 PO E.PROF4 PO E | 40 |  |  | 6249 | 6249 | 0
2.05.03 Cradle Carriage Assembly/Installation
S349100 | Install magnet mounting feet - Labor - CA-D Resource(s) | 4 | 607 | 2021-09-07 | 2021-09-20 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 607 | 607 | 0
S349300 | Install platforms & access - Labor - Physics Resource(s) | 16 | 2500 | 2021-12-15 | 2022-01-03 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2500 | 2500 | 0
S349300 | Install platforms & access - Labor - Physics Resource(s) | 240 | 29057 | 2021-12-15 | 2022-01-03 | 0% | TECH3 PO M.TECH3 PO M | 240 |  |  | 29057 | 29057 | 0
S349300 | Install platforms & access - Labor - Physics Resource(s) | 16 | 1937 | 2021-12-15 | 2022-01-03 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 8 | 1250 | 2022-03-09 | 2022-03-22 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 64 | 7749 | 2022-03-09 | 2022-03-22 | 0% | TECH3 PO M.TECH3 PO M | 64 |  |  | 7749 | 7749 | 0
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 8 | 969 | 2022-03-09 | 2022-03-22 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S349200 | Install magnet mounting feet - M&S | 3000 | 3482 | 2021-09-07 | 2021-09-20 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 3000 |  |  | 3482 | 3482 | 0
S349400 | Install platforms & access - M&S | 1000 | 1184 | 2021-12-15 | 2022-01-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 |  |  | 1184 | 1184 | 0
S349600 | Install Pole Tips - M&S | 3000 | 3552 | 2022-03-09 | 2022-03-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 3000 |  |  | 3552 | 3552 | 0
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 176 | 27497 | 2021-12-15 | 2022-01-03 | 0% | PROF4 AD.PROF4 AD | 176 |  |  | 27497 | 27497 | 0
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 72 | 8717 | 2021-12-15 | 2022-01-03 | 0% | TECH3 AD.TECH3 AD | 72 |  |  | 8717 | 8717 | 0
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 80 | 11084 | 2021-12-15 | 2022-01-03 | 0% | TECH4 AD.TECH4 AD | 80 |  |  | 11084 | 11084 | 0
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 136 | 21248 | 2022-03-09 | 2022-03-22 | 0% | PROF4 AD.PROF4 AD | 136 |  |  | 21248 | 21248 | 0
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 120 | 15923 | 2022-03-09 | 2022-03-22 | 0% | CRAFT3.CRAFT3 | 120 |  |  | 15923 | 15923 | 0
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 80 | 11084 | 2022-03-09 | 2022-03-22 | 0% | TECH4 AD.TECH4 AD | 80 |  |  | 11084 | 11084 | 0
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | 10 | 1517 | 2021-09-07 | 2021-09-20 | 0% | PROF4 PO M.PROF4 PO M | 10 |  |  | 1517 | 1517 | 0
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | 160 | 18807 | 2021-09-07 | 2021-09-20 | 0% | TECH3 PO M.TECH3 PO M | 160 |  |  | 18807 | 18807 | 0
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | 8 | 940 | 2021-09-07 | 2021-09-20 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
2.05.04 Outer Hcal Installation
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | 600 | 80708 | 21-Jun-21 A | 2021-09-03 | 8% | TECH4 AD.TECH4 AD | 552 |  |  | 74251.36 | 74251.36 | 0
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | 20 | 2065 | 21-Jun-21 A | 2021-09-03 | 8% | PROF2 AD.PROF2 AD | 18.4 |  |  | 1899.8 | 1899.8 | 0
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | 8 | 1213 | 21-Jun-21 A | 2021-09-03 | 8% | PROF4 AD.PROF4 AD | 7.36 |  |  | 1115.96 | 1115.96 | 0
S351000 | Transport Remainder of Outer Hcal Sectors to AH - Labor - CA-D Resource(s) | 8 | 851 | 2021-10-19 | 2021-11-01 | 0% | PROF2 AD.PROF2 AD | 8 |  |  | 851 | 851 | 0
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 480 | 66503 | 2021-10-26 | 2021-11-23 | 0% | TECH4 AD.TECH4 AD | 480 |  |  | 66503 | 66503 | 0
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 20 | 2126 | 2021-10-26 | 2021-11-23 | 0% | PROF2 AD.PROF2 AD | 20 |  |  | 2126 | 2126 | 0
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 8 | 1250 | 2021-10-26 | 2021-11-23 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | 4 | 484 | 2021-11-24 | 2021-12-02 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 484 | 484 | 0
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | 20 | 2421 | 2021-11-24 | 2021-12-02 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2421 | 2421 | 0
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 9686 | 2021-12-03 | 2022-01-03 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S351600 | Install Outer HCal Cables and Services - Labor | 160 | 19372 | 2021-12-03 | 2022-01-03 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 12499 | 2021-12-03 | 2022-01-03 | 0% | PROF4 PO E.PROF4 PO E | 80 |  |  | 12499 | 12499 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | 8 | 1250 | 2022-01-04 | 2022-01-18 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | 8 | 969 | 2022-01-04 | 2022-01-18 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | 8 | 969 | 2022-01-04 | 2022-01-18 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | 8 | 969 | 2022-01-04 | 2022-01-18 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S351900 | Address Action Items from Outer Hcal ORR | 8 | 1250 | 2022-01-19 | 2022-02-01 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S351900 | Address Action Items from Outer Hcal ORR | 8 | 969 | 2022-01-19 | 2022-02-01 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S351900 | Address Action Items from Outer Hcal ORR | 8 | 969 | 2022-01-19 | 2022-02-01 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S351900 | Address Action Items from Outer Hcal ORR | 8 | 969 | 2022-01-19 | 2022-02-01 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S352000 | Commission Outer HCal - Labor | 32 | 4999 | 2022-02-02 | 2022-03-02 | 0% | PROF4 PO M.PROF4 PO M | 32 |  |  | 4999 | 4999 | 0
S352000 | Commission Outer HCal - Labor | 160 | 29214 | 2022-02-02 | 2022-03-02 | 0% | SCI3 PO.SCI3 PO | 160 |  |  | 29214 | 29214 | 0
S352000 | Commission Outer HCal - Labor | 32 | 3874 | 2022-02-02 | 2022-03-02 | 0% | TECH3 PO D.TECH3 PO D | 32 |  |  | 3874 | 3874 | 0
S352000 | Commission Outer HCal - Labor | 320 | 38743 | 2022-02-02 | 2022-03-02 | 0% | TECH3 PO M.TECH3 PO M | 320 |  |  | 38743 | 38743 | 0
S352000 | Commission Outer HCal - Labor | 160 | 24997 | 2022-02-02 | 2022-03-02 | 0% | PROF4 PO E.PROF4 PO E | 160 |  |  | 24997 | 24997 | 0
S352000 | Commission Outer HCal - Labor | 320 | 38743 | 2022-02-02 | 2022-03-02 | 0% | TECH3 PO E.TECH3 PO E | 320 |  |  | 38743 | 38743 | 0
S350900 | Install Partial Outer HCal (Prior to SC Magnet Install) - M&S | 500 | 580 | 21-Jun-21 A | 2021-09-03 | 8% | Purch 1st $2M.Material (Purchase (1st $2M) | 460 |  |  | 533.6 | 533.6 | 0
S351100 | Transport Remainder of Outer Hcal Sectors to AH - M&S | 500 | 592 | 2021-10-19 | 2021-11-01 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S351300 | Install Remainder of Outer HCal Sectors - M&S | 500 | 592 | 2021-10-26 | 2021-11-23 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S351500 | Align/Survey Outer Hcal to Centerline - M&S | 500 | 592 | 2021-11-24 | 2021-12-02 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S351700 | Install Outer HCal Cables and Services - M&S | 500 | 592 | 2021-12-03 | 2022-01-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S352200 | Commission Outer HCal - M&S | 500 | 592 | 2022-02-02 | 2022-03-02 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S352100 | Commission Outer HCal - Labor | 640 | 0 | 2022-02-02 | 2022-03-02 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 640 |  |  | 0 | 0 | 0
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | 80 | 10615 | 2021-11-24 | 2021-12-02 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10615 | 10615 | 0
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | 60 | 7264 | 2021-11-24 | 2021-12-02 | 0% | TECH3 AD.TECH3 AD | 60 |  |  | 7264 | 7264 | 0
S350950 | Install Large Support Rings and Cross Braces and South-Side IHCal Support Tabs | 40 | 4758 | 2021-10-12 | 2021-10-18 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4758 | 4758 | 0
S350950 | Install Large Support Rings and Cross Braces and South-Side IHCal Support Tabs | 40 | 6140 | 2021-10-12 | 2021-10-18 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6140 | 6140 | 0
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 64 | 9708 | 21-Jun-21 A | 2021-09-03 | 8% | PROF4 PO M.PROF4 PO M | 58.88 |  |  | 8931.36 | 8931.36 | 0
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 48 | 5642 | 21-Jun-21 A | 2021-09-03 | 8% | TECH3 PO D.TECH3 PO D | 44.16 |  |  | 5190.64 | 5190.64 | 0
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 512 | 60183 | 21-Jun-21 A | 2021-09-03 | 8% | TECH3 PO M.TECH3 PO M | 471.04 |  |  | 55368.36 | 55368.36 | 0
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 600 | 77294 | 21-Jun-21 A | 2021-09-03 | 8% | CRAFT3.CRAFT3 | 552 |  |  | 71110.48 | 71110.48 | 0
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 8 | 1250 | 2021-10-19 | 2021-11-01 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 256 | 33968 | 2021-10-19 | 2021-11-01 | 0% | CRAFT3.CRAFT3 | 256 |  |  | 33968 | 33968 | 0
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 8 | 969 | 2021-10-19 | 2021-11-01 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 128 | 15497 | 2021-10-19 | 2021-11-01 | 0% | TECH3 PO M.TECH3 PO M | 128 |  |  | 15497 | 15497 | 0
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 64 | 9999 | 2021-10-26 | 2021-11-23 | 0% | PROF4 PO M.PROF4 PO M | 64 |  |  | 9999 | 9999 | 0
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 64 | 7749 | 2021-10-26 | 2021-11-23 | 0% | TECH3 PO D.TECH3 PO D | 64 |  |  | 7749 | 7749 | 0
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 512 | 61989 | 2021-10-26 | 2021-11-23 | 0% | TECH3 PO M.TECH3 PO M | 512 |  |  | 61989 | 61989 | 0
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 480 | 63690 | 2021-10-26 | 2021-11-23 | 0% | CRAFT3.CRAFT3 | 480 |  |  | 63690 | 63690 | 0
2.05.05 SC Magnet Installation
S352400 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s) | 10 | 1517 | 17-Mar-21 A | 2021-07-29 | 75% | PROF4 AD.PROF4 AD | 2.5 |  |  | 379.25 | 379.25 | 0
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | 16 | 2427 | 2021-09-21 | 2021-09-22 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2427 | 2427 | 0
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | 4 | 470 | 2021-09-21 | 2021-09-22 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 470 | 470 | 0
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | 32 | 3761 | 2021-09-21 | 2021-09-22 | 0% | TECH3 PO M.TECH3 PO M | 32 |  |  | 3761 | 3761 | 0
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | 16 | 2427 | 2021-09-23 | 2021-09-24 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2427 | 2427 | 0
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | 2 | 235 | 2021-09-23 | 2021-09-24 | 0% | TECH3 PO D.TECH3 PO D | 2 |  |  | 235 | 235 | 0
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | 32 | 3761 | 2021-09-23 | 2021-09-24 | 0% | TECH3 PO M.TECH3 PO M | 32 |  |  | 3761 | 3761 | 0
S353500 | Align/Survey SC Magnet to Cradle - Labor - Physics Resource(s) | 80 | 9404 | 2021-09-27 | 2021-10-08 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9404 | 9404 | 0
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | 16 | 2489 | 2021-10-12 | 2021-11-08 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2489 | 2489 | 0
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | 16 | 1929 | 2021-10-12 | 2021-11-08 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1929 | 1929 | 0
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | 16 | 1929 | 2021-10-12 | 2021-11-08 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1929 | 1929 | 0
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | 16 | 2500 | 2021-11-09 | 2021-12-09 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2500 | 2500 | 0
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | 16 | 1937 | 2021-11-09 | 2021-12-09 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | 160 | 19372 | 2021-11-09 | 2021-12-09 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 8 | 1250 | 2021-12-10 | 2021-12-23 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 8 | 969 | 2021-12-10 | 2021-12-23 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 8 | 969 | 2021-12-10 | 2021-12-23 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 8 | 1250 | 2021-12-27 | 2022-01-10 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S352500 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - M&S | 30000 | 34821 | 17-Mar-21 A | 2021-07-29 | 75% | Purch 1st $2M.Material (Purchase (1st $2M) | 7500 |  |  | 8705.25 | 8705.25 | 0
S353200 | Transport SC Magnet from 912 to AH - M&S | 1500 | 1741 | 2021-09-21 | 2021-09-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 1500 |  |  | 1741 | 1741 | 0
S353400 | Install SC Magnet on Cradle - M&S | 1500 | 1741 | 2021-09-23 | 2021-09-24 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 1500 |  |  | 1741 | 1741 | 0
S353600 | Align/Survey SC Magnet to Cradle - M&S | 3500 | 4062 | 2021-09-27 | 2021-10-08 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 3500 |  |  | 4062 | 4062 | 0
S353800 | Prep SC Magnet for Run (Cryo) - M&S | 3500 | 4131 | 2021-10-12 | 2021-11-08 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 3500 |  |  | 4131 | 4131 | 0
S354000 | Prep SC Magnet for Run (Electric) - M&S | 3500 | 4144 | 2021-11-09 | 2021-12-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 3500 |  |  | 4144 | 4144 | 0
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | 64 | 8245 | 2021-09-21 | 2021-09-22 | 0% | CRAFT3.CRAFT3 | 64 |  |  | 8245 | 8245 | 0
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | 16 | 2427 | 2021-09-21 | 2021-09-22 | 0% | PROF4 AD.PROF4 AD | 16 |  |  | 2427 | 2427 | 0
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | 16 | 2427 | 2021-09-21 | 2021-09-22 | 0% | PROF4 AD.PROF4 AD | 16 |  |  | 2427 | 2427 | 0
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | 64 | 8245 | 2021-09-23 | 2021-09-24 | 0% | CRAFT3.CRAFT3 | 64 |  |  | 8245 | 8245 | 0
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | 16 | 2427 | 2021-09-23 | 2021-09-24 | 0% | PROF4 AD.PROF4 AD | 16 |  |  | 2427 | 2427 | 0
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | 16 | 2427 | 2021-09-23 | 2021-09-24 | 0% | PROF4 AD.PROF4 AD | 16 |  |  | 2427 | 2427 | 0
S353510 | Align/Survey SC Magnet to Cradle - Labor - CA-D Resource(s) | 160 | 20612 | 2021-09-27 | 2021-10-08 | 0% | CRAFT3.CRAFT3 | 160 |  |  | 20612 | 20612 | 0
S353510 | Align/Survey SC Magnet to Cradle - Labor - CA-D Resource(s) | 240 | 28211 | 2021-09-27 | 2021-10-08 | 0% | TECH3 AD.TECH3 AD | 240 |  |  | 28211 | 28211 | 0
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | 320 | 38574 | 2021-10-12 | 2021-11-08 | 0% | TECH3 AD.TECH3 AD | 320 |  |  | 38574 | 38574 | 0
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | 16 | 3262 | 2021-10-12 | 2021-11-08 | 0% | PROF6 AD.PROF6 AD | 16 |  |  | 3262 | 3262 | 0
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | 40 | 6222 | 2021-10-12 | 2021-11-08 | 0% | PROF4 AD.PROF4 AD | 40 |  |  | 6222 | 6222 | 0
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | 160 | 19372 | 2021-11-09 | 2021-12-09 | 0% | TECH3 AD.TECH3 AD | 160 |  |  | 19372 | 19372 | 0
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | 16 | 3276 | 2021-11-09 | 2021-12-09 | 0% | PROF6 AD.PROF6 AD | 16 |  |  | 3276 | 3276 | 0
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | 40 | 6249 | 2021-11-09 | 2021-12-09 | 0% | PROF4 AD.PROF4 AD | 40 |  |  | 6249 | 6249 | 0
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 8 | 969 | 2021-12-10 | 2021-12-23 | 0% | TECH3 AD.TECH3 AD | 8 |  |  | 969 | 969 | 0
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 8 | 1638 | 2021-12-10 | 2021-12-23 | 0% | PROF6 AD.PROF6 AD | 8 |  |  | 1638 | 1638 | 0
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 8 | 1250 | 2021-12-10 | 2021-12-23 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | TECH3 AD.TECH3 AD | 8 |  |  | 969 | 969 | 0
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 8 | 1638 | 2021-12-27 | 2022-01-10 | 0% | PROF6 AD.PROF6 AD | 8 |  |  | 1638 | 1638 | 0
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 8 | 1250 | 2021-12-27 | 2022-01-10 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | 30 | 4550 | 17-Mar-21 A | 2021-07-29 | 75% | PROF4 PO M.PROF4 PO M | 7.5 |  |  | 1137.5 | 1137.5 | 0
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | 10 | 1175 | 17-Mar-21 A | 2021-07-29 | 75% | TECH3 PO M.TECH3 PO M | 2.5 |  |  | 293.75 | 293.75 | 0
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | 10 | 1175 | 17-Mar-21 A | 2021-07-29 | 75% | TECH3 PO D.TECH3 PO D | 2.5 |  |  | 293.75 | 293.75 | 0
2.05.06 Inner Hcal Installation
S354500 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - Labor | 120 | 17672 | 2021-07-21 | 2021-10-14 | 0% | PROF4 PO M.PROF4 PO M | 120 |  |  | 17672 | 17672 | 0
S354500 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - Labor | 40 | 4565 | 2021-07-21 | 2021-10-14 | 0% | TECH3 PO D.TECH3 PO D | 40 |  |  | 4565 | 4565 | 0
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | 80 | 12046 | 08-Feb-21 A | 2021-11-12 | 75% | PROF4 PO M.PROF4 PO M | 20 |  |  | 3011.5 | 3011.5 | 0
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | 40 | 4668 | 08-Feb-21 A | 2021-11-12 | 75% | TECH3 PO D.TECH3 PO D | 10 |  |  | 1167 | 1167 | 0
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1213 | 15-Jun-21 A | 2021-11-30 | 25% | PROF4 PO M.PROF4 PO M | 6 |  |  | 909.75 | 909.75 | 0
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 15-Jun-21 A | 2021-11-30 | 25% | TECH3 PO M.TECH3 PO M | 6 |  |  | 705 | 705 | 0
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 15-Jun-21 A | 2021-11-30 | 25% | TECH3 PO D.TECH3 PO D | 6 |  |  | 705 | 705 | 0
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1213 | 2021-12-01 | 2021-12-14 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 940 | 2021-12-01 | 2021-12-14 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 940 | 2021-12-01 | 2021-12-14 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S355400 | Install Inner Hcal Assembly Insertion Fixture - Labor | 4 | 607 | 2021-12-15 | 2021-12-20 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 607 | 607 | 0
S355400 | Install Inner Hcal Assembly Insertion Fixture - Labor | 4 | 470 | 2021-12-15 | 2021-12-20 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 470 | 470 | 0
S355400 | Install Inner Hcal Assembly Insertion Fixture - Labor | 80 | 9404 | 2021-12-15 | 2021-12-20 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9404 | 9404 | 0
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | 64 | 9708 | 2021-12-21 | 2021-12-27 | 0% | PROF4 PO M.PROF4 PO M | 64 |  |  | 9708 | 9708 | 0
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | 64 | 7523 | 2021-12-21 | 2021-12-27 | 0% | TECH3 PO D.TECH3 PO D | 64 |  |  | 7523 | 7523 | 0
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | 512 | 60183 | 2021-12-21 | 2021-12-27 | 0% | TECH3 PO M.TECH3 PO M | 512 |  |  | 60183 | 60183 | 0
S355800 | Install 1st Inner HCal Support Ring - Labor | 8 | 1250 | 2021-12-28 | 2021-12-29 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S355800 | Install 1st Inner HCal Support Ring - Labor | 2 | 242 | 2021-12-28 | 2021-12-29 | 0% | TECH3 PO D.TECH3 PO D | 2 |  |  | 242 | 242 | 0
S355800 | Install 1st Inner HCal Support Ring - Labor | 32 | 3874 | 2021-12-28 | 2021-12-29 | 0% | TECH3 PO M.TECH3 PO M | 32 |  |  | 3874 | 3874 | 0
S356000 | Install Inner HCal - Labor - CA-D Resource(s) | 120 | 16626 | 2021-12-30 | 2022-01-03 | 0% | TECH4 AD.TECH4 AD | 120 |  |  | 16626 | 16626 | 0
S356000 | Install Inner HCal - Labor - CA-D Resource(s) | 4 | 625 | 2021-12-30 | 2022-01-03 | 0% | PROF4 AD.PROF4 AD | 4 |  |  | 625 | 625 | 0
S356200 | Install 2nd Inner HCal Support Ring and South-Side IHCal Support Tabs - Labor | 8 | 1250 | 2022-01-04 | 2022-01-05 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S356200 | Install 2nd Inner HCal Support Ring and South-Side IHCal Support Tabs - Labor | 2 | 242 | 2022-01-04 | 2022-01-05 | 0% | TECH3 PO D.TECH3 PO D | 2 |  |  | 242 | 242 | 0
S356200 | Install 2nd Inner HCal Support Ring and South-Side IHCal Support Tabs - Labor | 32 | 3874 | 2022-01-04 | 2022-01-05 | 0% | TECH3 PO M.TECH3 PO M | 32 |  |  | 3874 | 3874 | 0
S356400 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - Physics Resource(s) | 4 | 484 | 2022-01-06 | 2022-01-12 | 0% | TECH3 PO D.TECH3 PO D | 4 |  |  | 484 | 484 | 0
S356400 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421 | 2022-01-06 | 2022-01-12 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2421 | 2421 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 9686 | 2022-01-13 | 2022-02-10 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 160 | 19372 | 2022-01-13 | 2022-02-10 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 12499 | 2022-01-13 | 2022-02-10 | 0% | PROF4 PO E.PROF4 PO E | 80 |  |  | 12499 | 12499 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 1250 | 2022-02-11 | 2022-02-25 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 1250 | 2022-02-11 | 2022-02-25 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 969 | 2022-02-11 | 2022-02-25 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 969 | 2022-02-11 | 2022-02-25 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | 8 | 969 | 2022-02-11 | 2022-02-25 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S356900 | Address Action Items from Inner Hcal ORR | 8 | 1250 | 2022-02-28 | 2022-03-11 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S356900 | Address Action Items from Inner Hcal ORR | 8 | 1250 | 2022-02-28 | 2022-03-11 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S356900 | Address Action Items from Inner Hcal ORR | 8 | 969 | 2022-02-28 | 2022-03-11 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S356900 | Address Action Items from Inner Hcal ORR | 8 | 969 | 2022-02-28 | 2022-03-11 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S356900 | Address Action Items from Inner Hcal ORR | 8 | 969 | 2022-02-28 | 2022-03-11 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 320 | 58428 | 2022-03-14 | 2022-03-18 | 0% | SCI3 PO.SCI3 PO | 320 |  |  | 58428 | 58428 | 0
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 160 | 24997 | 2022-03-14 | 2022-03-18 | 0% | PROF4 PO E.PROF4 PO E | 160 |  |  | 24997 | 24997 | 0
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 160 | 19372 | 2022-03-14 | 2022-03-18 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 32 | 3874 | 2022-03-14 | 2022-03-18 | 0% | TECH3 PO M.TECH3 PO M | 32 |  |  | 3874 | 3874 | 0
S354600 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - M&S | 80000 | 91034 | 21-Jul-21* | 2021-10-14 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 80000 |  |  | 91034 | 91034 | 0
S355500 | Install Inner Hcal Assembly Insertion Fixture - M&S | 500 | 580 | 2021-12-15 | 2021-12-20 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 580 | 580 | 0
S355700 | Install Inner HCal assembly on Insertion Fixture - M&S | 500 | 580 | 2021-12-21 | 2021-12-27 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 580 | 580 | 0
S355900 | Install 1st Inner HCal Support Ring - M&S | 500 | 592 | 2021-12-28 | 2021-12-29 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S356100 | Install Inner HCal - M&S | 500 | 592 | 2021-12-30 | 2022-01-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S356300 | Install 2nd Inner HCal Support Ring and South-Side IHCal Support Tabs - M&S | 500 | 592 | 2022-01-04 | 2022-01-05 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S356500 | Align/Survey Inner HCal to SC Magnet Centerline - M&S | 500 | 592 | 2022-01-06 | 2022-01-12 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S356700 | Install Inner HCal Cables and Services (if instrumented) - M&S | 500 | 592 | 2022-01-13 | 2022-02-10 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S357200 | Commission Inner HCal - M&S | 500 | 592 | 2022-03-14 | 2022-03-18 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures FY20 | 60 | 8836 | 01-Oct-19 A | 2021-07-20 | 95% | PROF4 PO M.PROF4 PO M | 3 |  |  | 441.8 | 441.8 | 0
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures FY20 | 120 | 13695 | 01-Oct-19 A | 2021-07-20 | 95% | TECH3 PO D.TECH3 PO D | 6 |  |  | 684.75 | 684.75 | 0
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615 | 2022-01-06 | 2022-01-12 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10615 | 10615 | 0
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264 | 2022-01-06 | 2022-01-12 | 0% | TECH3 AD.TECH3 AD | 60 |  |  | 7264 | 7264 | 0
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8313 | 2022-01-06 | 2022-01-12 | 0% | TECH4 AD.TECH4 AD | 60 |  |  | 8313 | 8313 | 0
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | 8 | 1250 | 2021-12-30 | 2022-01-03 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | 2 | 242 | 2021-12-30 | 2022-01-03 | 0% | TECH3 PO D.TECH3 PO D | 2 |  |  | 242 | 242 | 0
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | 32 | 3874 | 2021-12-30 | 2022-01-03 | 0% | TECH3 PO M.TECH3 PO M | 32 |  |  | 3874 | 3874 | 0
2.05.07 EMCal Installation
S357500 | (Planning Package) Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | 120 | 18202 | 01-Feb-21 A | 2021-07-30 | 40% | PROF4 PO M.PROF4 PO M | 72 |  |  | 10921.2 | 10921.2 | 0
S357500 | (Planning Package) Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | 48 | 5642 | 01-Feb-21 A | 2021-07-30 | 40% | TECH3 PO M.TECH3 PO M | 28.8 |  |  | 3385.2 | 3385.2 | 0
S357500 | (Planning Package) Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | 40 | 4702 | 01-Feb-21 A | 2021-07-30 | 40% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821.2 | 2821.2 | 0
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | 80 | 12135 | 01-Feb-21 A | 2021-08-13 | 40% | PROF4 PO M.PROF4 PO M | 48 |  |  | 7281 | 7281 | 0
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | 8 | 940 | 01-Feb-21 A | 2021-08-13 | 40% | TECH3 PO M.TECH3 PO M | 4.8 |  |  | 564 | 564 | 0
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | 40 | 4702 | 01-Feb-21 A | 2021-08-13 | 40% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2821.2 | 2821.2 | 0
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 8 | 1250 | 2022-01-13 | 2022-02-17 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S358400 | Install EMCal Sectors - Labor | 64 | 9999 | 2022-01-14 | 2022-02-07 | 0% | PROF4 PO M.PROF4 PO M | 64 |  |  | 9999 | 9999 | 0
S358400 | Install EMCal Sectors - Labor | 64 | 7749 | 2022-01-14 | 2022-02-07 | 0% | TECH3 PO D.TECH3 PO D | 64 |  |  | 7749 | 7749 | 0
S358400 | Install EMCal Sectors - Labor | 512 | 61989 | 2022-01-14 | 2022-02-07 | 0% | TECH3 PO M.TECH3 PO M | 512 |  |  | 61989 | 61989 | 0
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421 | 2022-02-08 | 2022-02-16 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2421 | 2421 | 0
S358800 | Install EMCal Cables and Services - Labor | 160 | 19372 | 2022-02-17 | 2022-03-08 | 0% | TECH3 PO E.TECH3 PO E | 160 |  |  | 19372 | 19372 | 0
S358800 | Install EMCal Cables and Services - Labor | 64 | 7749 | 2022-02-17 | 2022-03-08 | 0% | TECH3 PO M.TECH3 PO M | 64 |  |  | 7749 | 7749 | 0
S358800 | Install EMCal Cables and Services - Labor | 32 | 4999 | 2022-02-17 | 2022-03-08 | 0% | PROF4 PO M.PROF4 PO M | 32 |  |  | 4999 | 4999 | 0
S358800 | Install EMCal Cables and Services - Labor | 32 | 3874 | 2022-02-17 | 2022-03-08 | 0% | TECH3 PO D.TECH3 PO D | 32 |  |  | 3874 | 3874 | 0
S358800 | Install EMCal Cables and Services - Labor | 320 | 42460 | 2022-02-17 | 2022-03-08 | 0% | CRAFT3.CRAFT3 | 320 |  |  | 42460 | 42460 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | 8 | 1250 | 2022-03-09 | 2022-03-15 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | 8 | 969 | 2022-03-09 | 2022-03-15 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | 8 | 969 | 2022-03-09 | 2022-03-15 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | 8 | 969 | 2022-03-09 | 2022-03-15 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S359100 | Address Action Items from EMCal ORR | 8 | 1250 | 2022-03-16 | 2022-03-29 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S359100 | Address Action Items from EMCal ORR | 8 | 969 | 2022-03-16 | 2022-03-29 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S359100 | Address Action Items from EMCal ORR | 8 | 969 | 2022-03-16 | 2022-03-29 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S359100 | Address Action Items from EMCal ORR | 8 | 969 | 2022-03-16 | 2022-03-29 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S359200 | Commission EMCal - Labor | 400 | 73035 | 2022-03-30 | 2022-05-03 | 0% | SCI3 PO.SCI3 PO | 400 |  |  | 73035 | 73035 | 0
S359200 | Commission EMCal - Labor | 40 | 6249 | 2022-03-30 | 2022-05-03 | 0% | PROF4 PO E.PROF4 PO E | 40 |  |  | 6249 | 6249 | 0
S359200 | Commission EMCal - Labor | 40 | 4843 | 2022-03-30 | 2022-05-03 | 0% | TECH3 PO E.TECH3 PO E | 40 |  |  | 4843 | 4843 | 0
S359200 | Commission EMCal - Labor | 40 | 6249 | 2022-03-30 | 2022-05-03 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6249 | 6249 | 0
S359200 | Commission EMCal - Labor | 40 | 4843 | 2022-03-30 | 2022-05-03 | 0% | TECH3 PO D.TECH3 PO D | 40 |  |  | 4843 | 4843 | 0
S359200 | Commission EMCal - Labor | 40 | 4843 | 2022-03-30 | 2022-05-03 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4843 | 4843 | 0
S357600 | (Planning Package) Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - M&S | 30000 | 34821 | 01-Feb-21 A | 2021-07-30 | 40% | Purch 1st $2M.Material (Purchase (1st $2M) | 18000 |  |  | 20892.6 | 20892.6 | 0
S358300 | Transport Assembled EMCal Sectors to AH - M&S | 500 | 592 | 2022-01-13 | 2022-02-17 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S358500 | Install EMCal Sectors - M&S | 500 | 592 | 2022-01-14 | 2022-02-07 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S358700 | Align/Survey EMCal to SC Magnet Centerline - M&S | 500 | 592 | 2022-02-08 | 2022-02-16 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S358900 | Install EMCal Cables and Services - M&S | 500 | 592 | 2022-02-17 | 2022-03-08 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S359400 | Commission EMCal - M&S | 500 | 592 | 2022-03-30 | 2022-05-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615 | 2022-02-08 | 2022-02-16 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10615 | 10615 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264 | 2022-02-08 | 2022-02-16 | 0% | TECH3 AD.TECH3 AD | 60 |  |  | 7264 | 7264 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8313 | 2022-02-08 | 2022-02-16 | 0% | TECH4 AD.TECH4 AD | 60 |  |  | 8313 | 8313 | 0
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 120 | 15923 | 2022-01-13 | 2022-02-17 | 0% | CRAFT3.CRAFT3 | 120 |  |  | 15923 | 15923 | 0
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 64 | 7749 | 2022-01-13 | 2022-02-17 | 0% | TECH3 PO M.TECH3 PO M | 64 |  |  | 7749 | 7749 | 0
2.05.08 TPC Installation
S359700 | (Planning Package) Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 60 | 9101 | 2021-07-15 | 2021-11-22 | 0% | PROF4 PO M.PROF4 PO M | 60 |  |  | 9101 | 9101 | 0
S359700 | (Planning Package) Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 20 | 2351 | 2021-07-15 | 2021-11-22 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2351 | 2351 | 0
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 40 | 6067 | 10-Feb-21 A | 2021-12-08 | 50% | PROF4 PO M.PROF4 PO M | 20 |  |  | 3033.5 | 3033.5 | 0
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 8 | 940 | 10-Feb-21 A | 2021-12-08 | 50% | TECH3 PO M.TECH3 PO M | 4 |  |  | 470 | 470 | 0
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 20 | 2351 | 10-Feb-21 A | 2021-12-08 | 50% | TECH3 PO D.TECH3 PO D | 10 |  |  | 1175.5 | 1175.5 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1213 | 2021-12-09 | 2021-12-22 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 2021-12-09 | 2021-12-22 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 2021-12-09 | 2021-12-22 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1213 | 2021-12-23 | 2022-01-07 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 940 | 2021-12-23 | 2022-01-07 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 940 | 2021-12-23 | 2022-01-07 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 1250 | 2022-06-30 | 2022-07-07 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 24 | 2906 | 2022-06-30 | 2022-07-07 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2906 | 2906 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 969 | 2022-06-30 | 2022-07-07 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S360700 | Install TPC Support - Labor | 4 | 625 | 2022-07-11 | 2022-07-15 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 625 | 625 | 0
S360700 | Install TPC Support - Labor | 16 | 1937 | 2022-07-11 | 2022-07-15 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S360700 | Install TPC Support - Labor | 80 | 9686 | 2022-07-11 | 2022-07-15 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 8 | 851 | 2022-07-18 | 2022-07-22 | 0% | PROF2 AD.PROF2 AD | 8 |  |  | 851 | 851 | 0
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421 | 2022-07-25 | 2022-07-29 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2421 | 2421 | 0
S361300 | Install TPC Cables and Services - Labor | 120 | 14529 | 2022-08-10 | 2022-08-30 | 0% | TECH3 PO E.TECH3 PO E | 120 |  |  | 14529 | 14529 | 0
S361300 | Install TPC Cables and Services - Labor | 60 | 7264 | 2022-08-10 | 2022-08-30 | 0% | TECH3 PO M.TECH3 PO M | 60 |  |  | 7264 | 7264 | 0
S361300 | Install TPC Cables and Services - Labor | 24 | 3750 | 2022-08-10 | 2022-08-30 | 0% | PROF4 PO M.PROF4 PO M | 24 |  |  | 3750 | 3750 | 0
S361300 | Install TPC Cables and Services - Labor | 24 | 2906 | 2022-08-10 | 2022-08-30 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2906 | 2906 | 0
S361300 | Install TPC Cables and Services - Labor | 240 | 31845 | 2022-08-10 | 2022-08-30 | 0% | CRAFT3.CRAFT3 | 240 |  |  | 31845 | 31845 | 0
S361500 | TPC - Operational Readiness Review (ORR) | 8 | 1250 | 2022-08-31 | 2022-09-07 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S361500 | TPC - Operational Readiness Review (ORR) | 8 | 969 | 2022-08-31 | 2022-09-07 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S361500 | TPC - Operational Readiness Review (ORR) | 8 | 969 | 2022-08-31 | 2022-09-07 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S361500 | TPC - Operational Readiness Review (ORR) | 8 | 1074 | 2022-08-31 | 2022-09-07 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1074 | 1074 | 0
S361600 | Address Action Items from TPC ORR | 8 | 1250 | 2022-09-08 | 2022-09-14 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S361600 | Address Action Items from TPC ORR | 8 | 969 | 2022-09-08 | 2022-09-14 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S361600 | Address Action Items from TPC ORR | 8 | 1074 | 2022-09-08 | 2022-09-14 | 0% | PROF3 PO E.PROF3 PO E | 8 |  |  | 1074 | 1074 | 0
S361600 | Address Action Items from TPC ORR | 8 | 969 | 2022-09-08 | 2022-09-14 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S361700 | Commission TPC - Labor Phys | 40 | 6262 | 2022-09-15 | 2022-10-05 | 0% | PROF4 PO E.PROF4 PO E | 40 |  |  | 6262 | 6262 | 0
S361700 | Commission TPC - Labor Phys | 40 | 4853 | 2022-09-15 | 2022-10-05 | 0% | TECH3 PO E.TECH3 PO E | 40 |  |  | 4853 | 4853 | 0
S361700 | Commission TPC - Labor Phys | 400 | 73181 | 2022-09-15 | 2022-10-05 | 0% | SCI3 PO.SCI3 PO | 400 |  |  | 73181 | 73181 | 0
S361700 | Commission TPC - Labor Phys | 40 | 4853 | 2022-09-15 | 2022-10-05 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4853 | 4853 | 0
S361700 | Commission TPC - Labor Phys | 40 | 6262 | 2022-09-15 | 2022-10-05 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6262 | 6262 | 0
S361700 | Commission TPC - Labor Phys | 40 | 4853 | 2022-09-15 | 2022-10-05 | 0% | TECH3 PO D.TECH3 PO D | 40 |  |  | 4853 | 4853 | 0
S359800 | (Planning Package) Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - M&S | 30000 | 34821 | 2021-07-15 | 2021-11-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 |  |  | 34821 | 34821 | 0
S360500 | Transport Assembled TPC Sections to AH - M&S | 500 | 592 | 2022-06-30 | 2022-07-07 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S360800 | Install TPC Support - M&S | 500 | 592 | 2022-07-11 | 2022-07-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S361000 | Install TPC (Mechanical) - M&S | 500 | 592 | 2022-07-18 | 2022-07-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S361200 | Align/Survey TPC to SC Magnet Centerline - M&S | 500 | 592 | 2022-07-25 | 2022-07-29 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S361400 | Install TPC Cables and Services - M&S | 500 | 592 | 2022-08-10 | 2022-08-30 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S361900 | Commission TPC - M&S | 500 | 593 | 2022-09-15 | 2022-10-05 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 593 | 593 | 0
S360600 | Open SC Magnet Pole Tip Doors | 4 | 625 | 2022-07-08 | 2022-07-08 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 625 | 625 | 0
S360600 | Open SC Magnet Pole Tip Doors | 16 | 1937 | 2022-07-08 | 2022-07-08 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1937 | 1937 | 0
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 8 | 1250 | 2022-06-30 | 2022-07-07 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615 | 2022-07-25 | 2022-07-29 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10615 | 10615 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264 | 2022-07-25 | 2022-07-29 | 0% | TECH3 AD.TECH3 AD | 60 |  |  | 7264 | 7264 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8313 | 2022-07-25 | 2022-07-29 | 0% | TECH4 AD.TECH4 AD | 60 |  |  | 8313 | 8313 | 0
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | 77 | 11680 | 02-Dec-19 A | 2021-07-14 | 95% | PROF4 PO M.PROF4 PO M | 3.85 |  |  | 584 | 584 | 0
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | 48 | 5642 | 02-Dec-19 A | 2021-07-14 | 95% | TECH3 PO M.TECH3 PO M | 2.4 |  |  | 282.1 | 282.1 | 0
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | 77 | 9051 | 02-Dec-19 A | 2021-07-14 | 95% | TECH3 PO D.TECH3 PO D | 3.85 |  |  | 452.55 | 452.55 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 4 | 625 | 2022-07-18 | 2022-07-22 | 0% | PROF4 PO M.PROF4 PO M | 4 |  |  | 625 | 625 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 16 | 1937 | 2022-07-18 | 2022-07-22 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 60 | 7264 | 2022-07-18 | 2022-07-22 | 0% | TECH3 PO M.TECH3 PO M | 60 |  |  | 7264 | 7264 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 36 | 4777 | 2022-07-18 | 2022-07-22 | 0% | CRAFT3.CRAFT3 | 36 |  |  | 4777 | 4777 | 0
2.05.09 INTT Installation
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 30 | 4550 | 01-Oct-19 A | 2021-07-30 | 80% | PROF4 PO M.PROF4 PO M | 6 |  |  | 910 | 910 | 0
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 60 | 7053 | 01-Oct-19 A | 2021-07-30 | 80% | TECH3 PO D.TECH3 PO D | 12 |  |  | 1410.6 | 1410.6 | 0
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | 60 | 9101 | 2021-08-02 | 2021-10-26 | 0% | PROF4 PO M.PROF4 PO M | 60 |  |  | 9101 | 9101 | 0
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | 20 | 2351 | 2021-08-02 | 2021-10-26 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2351 | 2351 | 0
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 40 | 6067 | 2021-10-27 | 2021-11-09 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6067 | 6067 | 0
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 20 | 2351 | 2021-10-27 | 2021-11-09 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2351 | 2351 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1213 | 2021-11-10 | 2021-11-24 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 2021-11-10 | 2021-11-24 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 2021-11-10 | 2021-11-24 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 1213 | 2021-11-29 | 2021-12-10 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 940 | 2021-11-29 | 2021-12-10 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 940 | 2021-11-29 | 2021-12-10 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 1250 | 2022-08-10 | 2022-08-11 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | 24 | 2906 | 2022-08-10 | 2022-08-11 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2906 | 2906 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 969 | 2022-08-10 | 2022-08-11 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S363000 | Install INTT Support - Labor | 8 | 1250 | 2022-08-12 | 2022-08-15 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S363000 | Install INTT Support - Labor | 8 | 969 | 2022-08-12 | 2022-08-15 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S363000 | Install INTT Support - Labor | 60 | 7264 | 2022-08-12 | 2022-08-15 | 0% | TECH3 PO M.TECH3 PO M | 60 |  |  | 7264 | 7264 | 0
S363200 | Install INTT (mechanical) - Labor | 8 | 1250 | 2022-08-16 | 2022-08-18 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S363200 | Install INTT (mechanical) - Labor | 8 | 969 | 2022-08-16 | 2022-08-18 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S363200 | Install INTT (mechanical) - Labor | 60 | 7264 | 2022-08-16 | 2022-08-18 | 0% | TECH3 PO M.TECH3 PO M | 60 |  |  | 7264 | 7264 | 0
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421 | 2022-08-19 | 2022-08-25 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2421 | 2421 | 0
S363600 | Install INTT Cables and Services - Labor | 120 | 14529 | 2022-08-26 | 2022-09-01 | 0% | TECH3 PO E.TECH3 PO E | 120 |  |  | 14529 | 14529 | 0
S363600 | Install INTT Cables and Services - Labor | 120 | 14529 | 2022-08-26 | 2022-09-01 | 0% | TECH3 PO M.TECH3 PO M | 120 |  |  | 14529 | 14529 | 0
S363600 | Install INTT Cables and Services - Labor | 24 | 3750 | 2022-08-26 | 2022-09-01 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3750 | 3750 | 0
S363600 | Install INTT Cables and Services - Labor | 24 | 3750 | 2022-08-26 | 2022-09-01 | 0% | PROF4 PO M.PROF4 PO M | 24 |  |  | 3750 | 3750 | 0
S363600 | Install INTT Cables and Services - Labor | 24 | 2906 | 2022-08-26 | 2022-09-01 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2906 | 2906 | 0
S363600 | Install INTT Cables and Services - Labor | 240 | 31845 | 2022-08-26 | 2022-09-01 | 0% | CRAFT3.CRAFT3 | 240 |  |  | 31845 | 31845 | 0
S363800 | INTT - Operational Readiness Review (ORR) | 8 | 1250 | 2022-09-02 | 2022-09-09 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S363800 | INTT - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-02 | 2022-09-09 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S363800 | INTT - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-02 | 2022-09-09 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S363800 | INTT - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-02 | 2022-09-09 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S363900 | Address Action Items from INTT ORR | 8 | 1250 | 2022-09-12 | 2022-09-16 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S363900 | Address Action Items from INTT ORR | 8 | 969 | 2022-09-12 | 2022-09-16 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S363900 | Address Action Items from INTT ORR | 8 | 969 | 2022-09-12 | 2022-09-16 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S363900 | Address Action Items from INTT ORR | 8 | 969 | 2022-09-12 | 2022-09-16 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S364000 | Commission INTT - Labor | 40 | 6249 | 2022-09-19 | 2022-09-30 | 0% | PROF4 PO E.PROF4 PO E | 40 |  |  | 6249 | 6249 | 0
S364000 | Commission INTT - Labor | 400 | 73035 | 2022-09-19 | 2022-09-30 | 0% | SCI3 PO.SCI3 PO | 400 |  |  | 73035 | 73035 | 0
S364000 | Commission INTT - Labor | 40 | 4843 | 2022-09-19 | 2022-09-30 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4843 | 4843 | 0
S364000 | Commission INTT - Labor | 40 | 4843 | 2022-09-19 | 2022-09-30 | 0% | TECH3 PO E.TECH3 PO E | 40 |  |  | 4843 | 4843 | 0
S364000 | Commission INTT - Labor | 40 | 6249 | 2022-09-19 | 2022-09-30 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6249 | 6249 | 0
S364000 | Commission INTT - Labor | 40 | 4843 | 2022-09-19 | 2022-09-30 | 0% | TECH3 PO D.TECH3 PO D | 40 |  |  | 4843 | 4843 | 0
S362200 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - M&S | 30000 | 34821 | 2021-08-02 | 2021-10-26 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 |  |  | 34821 | 34821 | 0
S362900 | Transport Assembled INTT Sections to AH - M&S | 500 | 592 | 2022-08-10 | 2022-08-11 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S363100 | Install INTT Support - M&S | 500 | 592 | 2022-08-12 | 2022-08-15 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S363300 | Install INTT (mechanical) - M&S | 500 | 592 | 2022-08-16 | 2022-08-18 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S363500 | Align/Survey INTT to SC Magnet Centerline - M&S | 500 | 592 | 2022-08-19 | 2022-08-25 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S363700 | Install INTT Cables and Services - M&S | 500 | 592 | 2022-08-26 | 2022-09-01 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S364200 | Commission INTT - M&S | 500 | 592 | 2022-09-19 | 2022-09-30 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615 | 2022-08-19 | 2022-08-25 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10615 | 10615 | 0
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264 | 2022-08-19 | 2022-08-25 | 0% | TECH3 AD.TECH3 AD | 60 |  |  | 7264 | 7264 | 0
2.05.10 MVTX Installation
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | 30 | 4550 | 01-Oct-19 A | 2021-07-30 | 95% | PROF4 PO M.PROF4 PO M | 1.5 |  |  | 227.5 | 227.5 | 0
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | 60 | 7053 | 01-Oct-19 A | 2021-07-30 | 95% | TECH3 PO D.TECH3 PO D | 3 |  |  | 352.65 | 352.65 | 0
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 60 | 9101 | 2021-08-02 | 2021-10-26 | 0% | PROF4 PO M.PROF4 PO M | 60 |  |  | 9101 | 9101 | 0
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 20 | 2351 | 2021-08-02 | 2021-10-26 | 0% | TECH3 PO D.TECH3 PO D | 20 |  |  | 2351 | 2351 | 0
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 20 | 2351 | 2021-08-02 | 2021-10-26 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2351 | 2351 | 0
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 40 | 6067 | 29-Apr-21 A | 2021-10-28 | 35% | PROF4 PO M.PROF4 PO M | 26 |  |  | 3943.55 | 3943.55 | 0
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 10 | 1175 | 29-Apr-21 A | 2021-10-28 | 35% | TECH3 PO D.TECH3 PO D | 6.5 |  |  | 763.75 | 763.75 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1213 | 2021-10-29 | 2021-11-12 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 2021-10-29 | 2021-11-12 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 2021-10-29 | 2021-11-12 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1213 | 2021-11-15 | 2021-11-30 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 1250 | 2022-03-28 | 2022-04-01 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | 24 | 2906 | 2022-03-28 | 2022-04-01 | 0% | TECH3 PO M.TECH3 PO M | 24 |  |  | 2906 | 2906 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 969 | 2022-03-28 | 2022-04-01 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S365500 | Install MVTX Support - Labor | 8 | 1250 | 2022-08-12 | 2022-08-16 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S365500 | Install MVTX Support - Labor | 8 | 969 | 2022-08-12 | 2022-08-16 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S365500 | Install MVTX Support - Labor | 60 | 7264 | 2022-08-12 | 2022-08-16 | 0% | TECH3 PO M.TECH3 PO M | 60 |  |  | 7264 | 7264 | 0
S366700 | Align/Survey MVTX to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2421 | 2022-09-06 | 2022-09-07 | 0% | TECH3 PO M.TECH3 PO M | 20 |  |  | 2421 | 2421 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9686 | 2022-09-08 | 2022-09-12 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3750 | 2022-09-08 | 2022-09-12 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3750 | 3750 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9686 | 2022-09-08 | 2022-09-12 | 0% | TECH3 PO E.TECH3 PO E | 80 |  |  | 9686 | 9686 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 2906 | 2022-09-08 | 2022-09-12 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2906 | 2906 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3750 | 2022-09-08 | 2022-09-12 | 0% | PROF4 PO M.PROF4 PO M | 24 |  |  | 3750 | 3750 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 160 | 21230 | 2022-09-08 | 2022-09-12 | 0% | CRAFT3.CRAFT3 | 160 |  |  | 21230 | 21230 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | 8 | 1250 | 2022-09-13 | 2022-09-19 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-13 | 2022-09-19 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-13 | 2022-09-19 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-13 | 2022-09-19 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S367300 | Address Action Items from MVTX ORR | 8 | 1250 | 2022-09-20 | 2022-09-26 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S367300 | Address Action Items from MVTX ORR | 8 | 969 | 2022-09-20 | 2022-09-26 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S367300 | Address Action Items from MVTX ORR | 8 | 969 | 2022-09-20 | 2022-09-26 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S367300 | Address Action Items from MVTX ORR | 8 | 969 | 2022-09-20 | 2022-09-26 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S364500 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - M&S | 30000 | 34821 | 2021-08-02 | 2021-10-26 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 |  |  | 34821 | 34821 | 0
S365400 | Transport Assembled MVTX Sections to IR - M&S | 500 | 592 | 2022-03-28 | 2022-04-01 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S365600 | Install MVTX Support - M&S | 500 | 592 | 2022-08-12 | 2022-08-16 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S366800 | Align/Survey MVTX to SC Magnet Centerline - M&S | 500 | 592 | 2022-09-06 | 2022-09-07 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S367000 | Install MVTX Remaining Cables and Services - M&S | 500 | 592 | 2022-09-08 | 2022-09-12 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S367600 | Commission MVTX - M&S | 500 | 592 | 2022-09-27 | 2022-10-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S365700 | Install FELIX | 16 | 2147 | 2022-08-17 | 2022-08-18 | 0% | PROF3 IO E.PROF3 IO E | 16 |  |  | 2147 | 2147 | 0
S365900 | Install Optical fibers | 40 | 4843 | 2022-08-17 | 2022-08-18 | 0% | TECH3 PO E.TECH3 PO E | 40 |  |  | 4843 | 4843 | 0
S366000 | Install RU | 40 | 5369 | 2022-08-17 | 2022-08-18 | 0% | PROF3 IO E.PROF3 IO E | 40 |  |  | 5369 | 5369 | 0
S366200 | Install Samtec Cables | 40 | 4843 | 2022-08-17 | 2022-08-18 | 0% | TECH3 PO E.TECH3 PO E | 40 |  |  | 4843 | 4843 | 0
S366300 | Install Half-Barrel 1 | 80 | 10737 | 2022-08-19 | 2022-08-26 | 0% | PROF3 PO M.PROF3 PO M | 80 |  |  | 10737 | 10737 | 0
S366300 | Install Half-Barrel 1 | 80 | 9686 | 2022-08-19 | 2022-08-26 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S366500 | Install Half-Barrel 2 | 80 | 9686 | 2022-08-29 | 2022-09-02 | 0% | TECH3 PO M.TECH3 PO M | 80 |  |  | 9686 | 9686 | 0
S366500 | Install Half-Barrel 2 | 80 | 10737 | 2022-08-29 | 2022-09-02 | 0% | PROF3 PO M.PROF3 PO M | 80 |  |  | 10737 | 10737 | 0
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10615 | 2022-09-06 | 2022-09-07 | 0% | CRAFT3.CRAFT3 | 80 |  |  | 10615 | 10615 | 0
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7264 | 2022-09-06 | 2022-09-07 | 0% | TECH3 AD.TECH3 AD | 60 |  |  | 7264 | 7264 | 0
2.05.11 Min Bias Installation
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | 16 | 2427 | 13-May-20 A | 2021-07-30 | 75% | PROF4 PO M.PROF4 PO M | 4 |  |  | 606.75 | 606.75 | 0
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | 30 | 3526 | 13-May-20 A | 2021-07-30 | 75% | TECH3 PO D.TECH3 PO D | 7.5 |  |  | 881.5 | 881.5 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 30 | 4550 | 2021-08-02 | 2021-10-26 | 0% | PROF4 PO M.PROF4 PO M | 30 |  |  | 4550 | 4550 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1175 | 2021-08-02 | 2021-10-26 | 0% | TECH3 PO D.TECH3 PO D | 10 |  |  | 1175 | 1175 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1175 | 2021-08-02 | 2021-10-26 | 0% | TECH3 PO M.TECH3 PO M | 10 |  |  | 1175 | 1175 | 0
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 40 | 6067 | 29-Apr-21 A | 2021-11-12 | 20% | PROF4 PO M.PROF4 PO M | 32 |  |  | 4853.6 | 4853.6 | 0
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 20 | 2351 | 29-Apr-21 A | 2021-11-12 | 20% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1880.8 | 1880.8 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1213 | 2021-11-15 | 2021-11-30 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1213 | 2021-12-01 | 2021-12-14 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1213 | 1213 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 940 | 2021-12-01 | 2021-12-14 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 940 | 940 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 940 | 2021-12-01 | 2021-12-14 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 940 | 940 | 0
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 1250 | 2022-08-10 | 2022-08-10 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 969 | 2022-08-10 | 2022-08-10 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S368700 | Install Min Bias Support - Labor | 8 | 1250 | 2022-08-11 | 2022-08-22 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S368700 | Install Min Bias Support - Labor | 8 | 969 | 2022-08-11 | 2022-08-22 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S368700 | Install Min Bias Support - Labor | 16 | 1937 | 2022-08-11 | 2022-08-22 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1937 | 1937 | 0
S368900 | Install Min Bias (mechanical) - Labor | 8 | 1250 | 2022-08-23 | 2022-08-29 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S368900 | Install Min Bias (mechanical) - Labor | 8 | 969 | 2022-08-23 | 2022-08-29 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S368900 | Install Min Bias (mechanical) - Labor | 16 | 1937 | 2022-08-23 | 2022-08-29 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1937 | 1937 | 0
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 8 | 969 | 2022-08-30 | 2022-09-06 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S369300 | Install Min Bias Cables and Services - Labor | 120 | 14529 | 2022-09-07 | 2022-09-13 | 0% | TECH3 PO M.TECH3 PO M | 120 |  |  | 14529 | 14529 | 0
S369300 | Install Min Bias Cables and Services - Labor | 24 | 3750 | 2022-09-07 | 2022-09-13 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3750 | 3750 | 0
S369300 | Install Min Bias Cables and Services - Labor | 120 | 14529 | 2022-09-07 | 2022-09-13 | 0% | TECH3 PO E.TECH3 PO E | 120 |  |  | 14529 | 14529 | 0
S369300 | Install Min Bias Cables and Services - Labor | 24 | 2906 | 2022-09-07 | 2022-09-13 | 0% | TECH3 PO D.TECH3 PO D | 24 |  |  | 2906 | 2906 | 0
S369300 | Install Min Bias Cables and Services - Labor | 24 | 3750 | 2022-09-07 | 2022-09-13 | 0% | PROF4 PO M.PROF4 PO M | 24 |  |  | 3750 | 3750 | 0
S369300 | Install Min Bias Cables and Services - Labor | 240 | 31845 | 2022-09-07 | 2022-09-13 | 0% | CRAFT3.CRAFT3 | 240 |  |  | 31845 | 31845 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | 8 | 1250 | 2022-09-14 | 2022-09-20 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | 8 | 969 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S369600 | Address Action Items from Min Bias ORR | 8 | 1250 | 2022-09-21 | 2022-09-27 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S369600 | Address Action Items from Min Bias ORR | 8 | 969 | 2022-09-21 | 2022-09-27 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S369600 | Address Action Items from Min Bias ORR | 8 | 969 | 2022-09-21 | 2022-09-27 | 0% | TECH3 PO M.TECH3 PO M | 8 |  |  | 969 | 969 | 0
S369600 | Address Action Items from Min Bias ORR | 8 | 969 | 2022-09-21 | 2022-09-27 | 0% | TECH3 PO E.TECH3 PO E | 8 |  |  | 969 | 969 | 0
S369700 | Commission Min Bias - Labor | 400 | 73035 | 2022-09-28 | 2022-10-04 | 0% | SCI3 PO.SCI3 PO | 400 |  |  | 73035 | 73035 | 0
S369700 | Commission Min Bias - Labor | 40 | 4843 | 2022-09-28 | 2022-10-04 | 0% | TECH3 PO M.TECH3 PO M | 40 |  |  | 4843 | 4843 | 0
S369700 | Commission Min Bias - Labor | 40 | 6249 | 2022-09-28 | 2022-10-04 | 0% | PROF4 PO E.PROF4 PO E | 40 |  |  | 6249 | 6249 | 0
S369700 | Commission Min Bias - Labor | 40 | 4843 | 2022-09-28 | 2022-10-04 | 0% | TECH3 PO E.TECH3 PO E | 40 |  |  | 4843 | 4843 | 0
S369700 | Commission Min Bias - Labor | 40 | 6249 | 2022-09-28 | 2022-10-04 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6249 | 6249 | 0
S369700 | Commission Min Bias - Labor | 40 | 4843 | 2022-09-28 | 2022-10-04 | 0% | TECH3 PO D.TECH3 PO D | 40 |  |  | 4843 | 4843 | 0
S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - M&S | 10000 | 11607 | 2021-08-02 | 2021-10-26 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 |  |  | 11607 | 11607 | 0
S368600 | Transport Assembled Min Bias Sections to AH - M&S | 500 | 592 | 2022-08-10 | 2022-08-10 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S368800 | Install Min Bias Support - M&S | 500 | 592 | 2022-08-11 | 2022-08-22 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S369000 | Install Min Bias (mechanical) - M&S | 500 | 592 | 2022-08-23 | 2022-08-29 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S369200 | Align/Survey Min Bias to SC Magnet Centerline - M&S | 500 | 592 | 2022-08-30 | 2022-09-06 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S369400 | Install Min Bias Cables and Services - M&S | 500 | 592 | 2022-09-07 | 2022-09-13 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S369900 | Commission Min Bias - M&S | 500 | 592 | 2022-09-28 | 2022-10-04 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 500 |  |  | 592 | 592 | 0
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 20 | 2654 | 2022-08-30 | 2022-09-06 | 0% | CRAFT3.CRAFT3 | 20 |  |  | 2654 | 2654 | 0
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 24 | 2906 | 2022-08-30 | 2022-09-06 | 0% | TECH3 AD.TECH3 AD | 24 |  |  | 2906 | 2906 | 0
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 24 | 3325 | 2022-08-30 | 2022-09-06 | 0% | TECH4 AD.TECH4 AD | 24 |  |  | 3325 | 3325 | 0
2.05.12 Full System Integration and ORR
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 40 | 5542 | 2022-03-23 | 2022-03-29 | 0% | TECH4 AD.TECH4 AD | 40 |  |  | 5542 | 5542 | 0
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 8 | 851 | 2022-03-23 | 2022-03-29 | 0% | PROF2 AD.PROF2 AD | 8 |  |  | 851 | 851 | 0
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 8 | 1250 | 2022-03-23 | 2022-03-29 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S370200 | Align Full sPHENIX to Nominal Beamline and IP - Labor - Physics Resource(s) | 16 | 1937 | 2022-08-24 | 2022-08-30 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1937 | 1937 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 2500 | 2022-09-14 | 2022-09-20 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2500 | 2500 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 1937 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO E.TECH3 PO E | 16 |  |  | 1937 | 1937 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 1937 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1937 | 1937 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 1937 | 2022-09-14 | 2022-09-20 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1937 | 1937 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 2500 | 2022-09-14 | 2022-09-20 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2500 | 2500 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 2147 | 2022-09-14 | 2022-09-20 | 0% | PROF3 PO E.PROF3 PO E | 16 |  |  | 2147 | 2147 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 3495 | 2022-09-14 | 2022-09-20 | 0% | SCI4 PO.SCI 4 PO | 16 |  |  | 3495 | 3495 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 16 | 2887 | 2022-09-14 | 2022-09-20 | 0% | PROF5 AD.PROF5 AD | 16 |  |  | 2887 | 2887 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 2525 | 2022-09-21 | 2022-10-12 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2525 | 2525 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 1957 | 2022-09-21 | 2022-10-12 | 0% | TECH3 PO E.TECH3 PO E | 16 |  |  | 1957 | 1957 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 1957 | 2022-09-21 | 2022-10-12 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1957 | 1957 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 1957 | 2022-09-21 | 2022-10-12 | 0% | TECH3 PO D.TECH3 PO D | 16 |  |  | 1957 | 1957 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 2525 | 2022-09-21 | 2022-10-12 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2525 | 2525 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 2916 | 2022-09-21 | 2022-10-12 | 0% | PROF5 AD.PROF5 AD | 16 |  |  | 2916 | 2916 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 2169 | 2022-09-21 | 2022-10-12 | 0% | PROF3 PO M.PROF3 PO M | 16 |  |  | 2169 | 2169 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | 16 | 3530 | 2022-09-21 | 2022-10-12 | 0% | SCI4 PO.SCI 4 PO | 16 |  |  | 3530 | 3530 | 0
S370100 | Move Full sPHENIX to IR - M&S | 1000 | 1184 | 2022-03-23 | 2022-03-29 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 |  |  | 1184 | 1184 | 0
S370300 | Align Full sPHENIX to Nominal Beamline and IP - M&S | 1000 | 1184 | 2022-08-24 | 2022-08-30 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 |  |  | 1184 | 1184 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 40 | 5308 | 2022-08-24 | 2022-08-30 | 0% | CRAFT3.CRAFT3 | 40 |  |  | 5308 | 5308 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 48 | 5811 | 2022-08-24 | 2022-08-30 | 0% | TECH3 AD.TECH3 AD | 48 |  |  | 5811 | 5811 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 48 | 6650 | 2022-08-24 | 2022-08-30 | 0% | TECH4 AD.TECH4 AD | 48 |  |  | 6650 | 6650 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 8 | 851 | 2022-08-24 | 2022-08-30 | 0% | PROF2 AD.PROF2 AD | 8 |  |  | 851 | 851 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 8 | 1250 | 2022-08-24 | 2022-08-30 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 8 | 1250 | 2022-03-23 | 2022-03-29 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 24 | 2906 | 2022-03-23 | 2022-03-29 | 0% | TECH3 PO E.TECH3 PO E | 24 |  |  | 2906 | 2906 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 96 | 11623 | 2022-03-23 | 2022-03-29 | 0% | TECH3 PO M.TECH3 PO M | 96 |  |  | 11623 | 11623 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 8 | 969 | 2022-03-23 | 2022-03-29 | 0% | TECH3 PO D.TECH3 PO D | 8 |  |  | 969 | 969 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 40 | 4843 | 2022-03-23 | 2022-03-29 | 0% | TECH3 AM.TECH3 AM | 40 |  |  | 4843 | 4843 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249 | 2022-05-09 | 2022-06-06 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6249 | 6249 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249 | 2022-05-09 | 2022-06-06 | 0% | PROF4 PO E.PROF4 PO E | 40 |  |  | 6249 | 6249 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 7303 | 2022-05-09 | 2022-06-06 | 0% | SCI3 PO.SCI3 PO | 40 |  |  | 7303 | 7303 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 8738 | 2022-05-09 | 2022-06-06 | 0% | SCI4 PO.SCI 4 PO | 40 |  |  | 8738 | 8738 | 0
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1250 | 2022-06-07 | 2022-06-09 | 0% | PROF4 PO M.PROF4 PO M | 8 |  |  | 1250 | 1250 | 0
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1250 | 2022-06-07 | 2022-06-09 | 0% | PROF4 PO E.PROF4 PO E | 8 |  |  | 1250 | 1250 | 0
S370510 | Review of Safety System Design by CAD ESRC | 24 | 5243 | 2022-06-07 | 2022-06-09 | 0% | SCI4 PO.SCI 4 PO | 24 |  |  | 5243 | 5243 | 0
S370510 | Review of Safety System Design by CAD ESRC | 24 | 4382 | 2022-06-07 | 2022-06-09 | 0% | SCI3 PO.SCI3 PO | 24 |  |  | 4382 | 4382 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249 | 2022-06-10 | 2022-07-08 | 0% | PROF4 PO M.PROF4 PO M | 40 |  |  | 6249 | 6249 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249 | 2022-06-10 | 2022-07-08 | 0% | PROF4 PO E.PROF4 PO E | 40 |  |  | 6249 | 6249 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 7303 | 2022-06-10 | 2022-07-08 | 0% | SCI3 PO.SCI3 PO | 40 |  |  | 7303 | 7303 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 8738 | 2022-06-10 | 2022-07-08 | 0% | SCI4 PO.SCI 4 PO | 40 |  |  | 8738 | 8738 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3608 | 2022-06-10 | 2022-07-08 | 0% | PROF5 AD.PROF5 AD | 20 |  |  | 3608 | 3608 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 4095 | 2022-06-10 | 2022-07-08 | 0% | PROF6 AD.PROF6 AD | 20 |  |  | 4095 | 4095 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 2126 | 2022-06-10 | 2022-07-08 | 0% | PROF2 AD.PROF2 AD | 20 |  |  | 2126 | 2126 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3125 | 2022-06-10 | 2022-07-08 | 0% | PROF4 AD.PROF4 AD | 20 |  |  | 3125 | 3125 | 0
S370530 | Review and approve procedures | 16 | 2500 | 2022-07-11 | 2022-07-12 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2500 | 2500 | 0
S370530 | Review and approve procedures | 16 | 2500 | 2022-07-11 | 2022-07-12 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2500 | 2500 | 0
S370530 | Review and approve procedures | 16 | 2921 | 2022-07-11 | 2022-07-12 | 0% | SCI3 PO.SCI3 PO | 16 |  |  | 2921 | 2921 | 0
S370530 | Review and approve procedures | 16 | 3495 | 2022-07-11 | 2022-07-12 | 0% | SCI4 PO.SCI 4 PO | 16 |  |  | 3495 | 3495 | 0
S370530 | Review and approve procedures | 16 | 2887 | 2022-07-11 | 2022-07-12 | 0% | PROF5 AD.PROF5 AD | 16 |  |  | 2887 | 2887 | 0
S370530 | Review and approve procedures | 16 | 3276 | 2022-07-11 | 2022-07-12 | 0% | PROF6 AD.PROF6 AD | 16 |  |  | 3276 | 3276 | 0
S370540 | Magnet Checkout After Power Testing | 16 | 2921 | 2022-07-13 | 2022-07-19 | 0% | SCI3 AD.SCI3 AD | 16 |  |  | 2921 | 2921 | 0
S370540 | Magnet Checkout After Power Testing | 16 | 3276 | 2022-07-13 | 2022-07-19 | 0% | PROF6 AD.PROF6 AD | 16 |  |  | 3276 | 3276 | 0
S370540 | Magnet Checkout After Power Testing | 16 | 2887 | 2022-07-13 | 2022-07-19 | 0% | PROF5 AD.PROF5 AD | 16 |  |  | 2887 | 2887 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 2906 | 2022-07-20 | 2022-07-26 | 0% | TECH3 PO E.TECH3 PO E | 24 |  |  | 2906 | 2906 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 3750 | 2022-07-20 | 2022-07-26 | 0% | PROF4 PO E.PROF4 PO E | 24 |  |  | 3750 | 3750 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 5243 | 2022-07-20 | 2022-07-26 | 0% | SCI4 PO.SCI 4 PO | 24 |  |  | 5243 | 5243 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2921 | 2022-07-27 | 2022-08-09 | 0% | SCI3 AD.SCI3 AD | 16 |  |  | 2921 | 2921 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2887 | 2022-07-27 | 2022-08-09 | 0% | PROF5 AD.PROF5 AD | 16 |  |  | 2887 | 2887 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 3276 | 2022-07-27 | 2022-08-09 | 0% | PROF6 AD.PROF6 AD | 16 |  |  | 3276 | 3276 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2500 | 2022-08-10 | 2022-08-16 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2500 | 2500 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937 | 2022-08-10 | 2022-08-16 | 0% | TECH3 PO E.TECH3 PO E | 16 |  |  | 1937 | 1937 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937 | 2022-08-10 | 2022-08-16 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1937 | 1937 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2500 | 2022-08-10 | 2022-08-16 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2500 | 2500 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 3495 | 2022-08-10 | 2022-08-16 | 0% | SCI4 PO.SCI 4 PO | 16 |  |  | 3495 | 3495 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2500 | 2022-08-17 | 2022-08-23 | 0% | PROF4 PO M.PROF4 PO M | 16 |  |  | 2500 | 2500 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937 | 2022-08-17 | 2022-08-23 | 0% | TECH3 PO E.TECH3 PO E | 16 |  |  | 1937 | 1937 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937 | 2022-08-17 | 2022-08-23 | 0% | TECH3 PO M.TECH3 PO M | 16 |  |  | 1937 | 1937 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2500 | 2022-08-17 | 2022-08-23 | 0% | PROF4 PO E.PROF4 PO E | 16 |  |  | 2500 | 2500 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 3495 | 2022-08-17 | 2022-08-23 | 0% | SCI4 PO.SCI 4 PO | 16 |  |  | 3495 | 3495 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2921 | 2022-08-17 | 2022-08-23 | 0% | SCI3 PO.SCI3 PO | 16 |  |  | 2921 | 2921 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1461 | 2022-08-17 | 2022-08-23 | 0% | SCI3 AD.SCI3 AD | 8 |  |  | 1461 | 1461 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1250 | 2022-08-17 | 2022-08-23 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1250 | 2022-08-17 | 2022-08-23 | 0% | PROF4 AD.PROF4 AD | 8 |  |  | 1250 | 1250 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1638 | 2022-08-17 | 2022-08-23 | 0% | PROF6 AD.PROF6 AD | 8 |  |  | 1638 | 1638 | 0
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 16 | 3495 | 2022-08-24 | 2022-08-30 | 0% | SCI4 PO.SCI 4 PO | 16 |  |  | 3495 | 3495 | 0
T Non BNL Contributions
1.02.01.02 TPC v2 Field Cage
S110400 | Assemble TPC v2 Outer Field Cage | 480 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 9.6 |  |  | 0 | 0 | 0
S110400 | Assemble TPC v2 Outer Field Cage | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 1.6 |  |  | 0 | 0 | 0
S110400 | Assemble TPC v2 Outer Field Cage | 160 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 3.2 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 8 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 8 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 8 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 136 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 136 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 136 |  |  | 0 | 0 | 0
1.02.01.08 TPC Assembly
S121610 | Install TPC Modules into Field Cage | 576 | 0 | 25-Aug-21* | 2021-10-15 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 576 |  |  | 0 | 0 | 0
S121610 | Install TPC Modules into Field Cage | 4800 | 0 | 25-Aug-21* | 2021-10-15 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 4800 |  |  | 0 | 0 | 0
S121610 | Install TPC Modules into Field Cage | 1920 | 0 | 25-Aug-21* | 2021-10-15 | 0% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 1920 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | 2600 | 0 | 2021-11-01 | 2022-02-02 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 2600 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | 312 | 0 | 2021-11-01 | 2022-02-02 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 312 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | 520 | 0 | 2021-11-01 | 2022-02-02 | 0% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 520 |  |  | 0 | 0 | 0
S121600 | Production Readiness Review for TPC Final Assembly | 8 | 0 | 2021-08-24 | 2021-08-24 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 8 |  |  | 0 | 0 | 0
S121600 | Production Readiness Review for TPC Final Assembly | 8 | 0 | 2021-08-24 | 2021-08-24 | 0% | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 8 |  |  | 0 | 0 | 0
1.02.02.03 TPC R1 Module Production
S125505 | Build TPC R1 Modules - Contributed Labor | 288 | 0 | 11-Jan-21 A | 2021-09-03 | 85% | SCI3 Wayne - Unpaid.SCI3 Wayne - Unpaid | 43.2 |  |  | 0 | 0 | 0
S125505 | Build TPC R1 Modules - Contributed Labor | 2400 | 0 | 11-Jan-21 A | 2021-09-03 | 85% | STUDENT Wayne - Unpaid.STUDENT Wayne - Unpaid | 360 |  |  | 0 | 0 | 0
S125605 | Test TPC R1 Modules - Contributed Labor | 288 | 0 | 11-Jan-21 A | 2021-09-20 | 85% | SCI3 Wayne - Unpaid.SCI3 Wayne - Unpaid | 43.2 |  |  | 0 | 0 | 0
S125605 | Test TPC R1 Modules - Contributed Labor | 2400 | 0 | 11-Jan-21 A | 2021-09-20 | 85% | STUDENT Wayne - Unpaid.STUDENT Wayne - Unpaid | 360 |  |  | 0 | 0 | 0
1.02.03.03 TPC R2 Module Production
S129500 | Build TPC R2 Modules | 288 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | SCI3 Vanderbilt - Unpaid.SCI3 Vanderbilt - Unpaid | 43.2 |  |  | 0 | 0 | 0
S129500 | Build TPC R2 Modules | 960 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | TECH3 Vanderbilt - Unpaid.TECH3 Vanderbilt - Unpaid | 144 |  |  | 0 | 0 | 0
S129500 | Build TPC R2 Modules | 2400 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 360 |  |  | 0 | 0 | 0
S129600 | Test TPC R2 Modules | 288 | 0 | 17-Nov-20 A | 2021-07-22 | 85% | SCI3 Vanderbilt - Unpaid.SCI3 Vanderbilt - Unpaid | 43.2 |  |  | 0 | 0 | 0
S129600 | Test TPC R2 Modules | 2400 | 0 | 17-Nov-20 A | 2021-07-22 | 85% | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 360 |  |  | 0 | 0 | 0
1.02.04.03 TPC R3 Module Production
S133700 | Build TPC R3a Modules | 288 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 43.2 |  |  | 0 | 0 | 0
S133700 | Build TPC R3a Modules | 960 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | TECH3 WIS - Unpaid.TECH3 WIS - Unpaid | 144 |  |  | 0 | 0 | 0
S133700 | Build TPC R3a Modules | 2400 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 360 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | 288 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 43.2 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | 960 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | TECH3 WIS - Unpaid.TECH3 WIS - Unpaid | 144 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | 2400 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 360 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | 288 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 43.2 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | 960 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | TECH3 Temple - Unpaid.TECH3 Temple - Unpaid | 144 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | 2400 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 360 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | 288 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 43.2 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | 2400 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 360 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | 960 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | TECH3 Temple - Unpaid.TECH3 Temple - Unpaid | 144 |  |  | 0 | 0 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S263700 | Trigger LL1 Preproduction Prototype: Test trigger systems | 280 | 0 | 2021-08-09 | 2021-08-27 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 280 |  |  | 0 | 0 | 0
1.06.02.04 LL1 Trigger Production
S264000 | Trigger LL1 Production: Updates to trigger board: Production | 136 | 0 | 2021-09-03 | 2021-09-28 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 136 |  |  | 0 | 0 | 0
S264100 | Trigger LL1 Production: final updates to trigger crate requirements | 20 | 0 | 2021-09-29 | 2021-10-13 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 20 |  |  | 0 | 0 | 0
S265000 | Trigger LL1 Production: Program and commission trigger boards | 60 | 0 | 2021-11-12 | 2021-12-06 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 60 |  |  | 0 | 0 | 0
S265100 | Trigger LL1 Production: Assemble trigger system | 120 | 0 | 2021-12-07 | 2021-12-13 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 120 |  |  | 0 | 0 | 0
S265200 | Trigger LL1 Production: Commission trigger systems | 120 | 0 | 2021-12-14 | 2021-12-20 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 120 |  |  | 0 | 0 | 0
2.05.06 Inner Hcal Installation
S357100 | Commission Inner HCal (labor - if instrumented) - Labor | 640 | 0 | 2022-03-14 | 2022-03-18 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 640 |  |  | 0 | 0 | 0
2.05.07 EMCal Installation
S359300 | Commission EMCal - Labor | 1600 | 0 | 2022-03-30 | 2022-05-03 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 |  |  | 0 | 0 | 0
2.05.08 TPC Installation
S361800 | Commission TPC - Labor Students | 1600 | 0 | 2022-09-15 | 2022-10-05 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 |  |  | 0 | 0 | 0
2.05.09 INTT Installation
S364100 | Commission INTT - Student Labor | 1600 | 0 | 2022-09-19 | 2022-09-30 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 |  |  | 0 | 0 | 0
2.05.10 MVTX Installation
S367500 | Commission MVTX - Labor | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | POSTD LBNL.POSTD LBNL | 480 |  |  | 0 | 0 | 0
S367500 | Commission MVTX - Labor | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 480 |  |  | 0 | 0 | 0
S367500 | Commission MVTX - Labor | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | SCI3 LANL.SCI3 LANL | 480 |  |  | 0 | 0 | 0
S365100 | Installation Prep | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | SCI3 LANL.SCI3 LANL | 80 |  |  | 0 | 0 | 0
S365100 | Installation Prep | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 80 |  |  | 0 | 0 | 0
S365100 | Installation Prep | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | POSTD LBNL.POSTD LBNL | 80 |  |  | 0 | 0 | 0
S365200 | Installation Review | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 8 |  |  | 0 | 0 | 0
S365200 | Installation Review | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | POSTD LBNL.POSTD LBNL | 8 |  |  | 0 | 0 | 0
S365200 | Installation Review | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | SCI3 LANL.SCI3 LANL | 8 |  |  | 0 | 0 | 0
S365800 | Install FELIX | 16 | 0 | 2022-08-17 | 2022-08-18 | 0% | SCI3 LANL.SCI3 LANL | 16 |  |  | 0 | 0 | 0
S366100 | Install RU | 40 | 0 | 2022-08-17 | 2022-08-18 | 0% | SCI3 LANL.SCI3 LANL | 40 |  |  | 0 | 0 | 0
S366400 | Install Half-Barrel 1 | 30 | 0 | 2022-08-19 | 2022-08-26 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 30 |  |  | 0 | 0 | 0
S366400 | Install Half-Barrel 1 | 30 | 0 | 2022-08-19 | 2022-08-26 | 0% | POSTD LBNL.POSTD LBNL | 30 |  |  | 0 | 0 | 0
S366600 | Install Half-Barrel 2 | 30 | 0 | 2022-08-29 | 2022-09-02 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 30 |  |  | 0 | 0 | 0
S366600 | Install Half-Barrel 2 | 30 | 0 | 2022-08-29 | 2022-09-02 | 0% | POSTD LBNL.POSTD LBNL | 30 |  |  | 0 | 0 | 0
S367400 | Address Action Items from MVTX ORR | 16 | 0 | 2022-09-20 | 2022-09-26 | 0% | SCI3 LANL.SCI3 LANL | 16 |  |  | 0 | 0 | 0
S367400 | Address Action Items from MVTX ORR | 16 | 0 | 2022-09-20 | 2022-09-26 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 16 |  |  | 0 | 0 | 0
S367200 | MVTX - Operational Readiness Review (ORR) | 16 | 0 | 2022-09-13 | 2022-09-19 | 0% | SCI3 LANL.SCI3 LANL | 16 |  |  | 0 | 0 | 0
S367200 | MVTX - Operational Readiness Review (ORR) | 16 | 0 | 2022-09-13 | 2022-09-19 | 0% | STAFFPHYS LBNL.STAFFPHYS LBNL | 16 |  |  | 0 | 0 | 0
2.05.11 Min Bias Installation
S369800 | Commission Min Bias - Labor | 1600 | 0 | 2022-09-28 | 2022-10-04 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 |  |  | 0 | 0 | 0
B_T Multiple B_T
1.02.01.08 TPC Assembly
S121700 | Install TPC Electronics | 400 | 0 | 2021-10-18 | 2021-10-29 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 400 |  |  | 0 | 0 | 0
S121700 | Install TPC Electronics | 160 | 18807 | 2021-10-18 | 2021-10-29 | 0% | TECH3 PO M.TECH3 PO M | 160 |  |  | 18807 | 18807 | 0
S121700 | Install TPC Electronics | 48 | 0 | 2021-10-18 | 2021-10-29 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 48 |  |  | 0 | 0 | 0
1.02.05.04 TPC FEE Production
S143300 | Perform QA Testing on TPC FEE | 56 | 8494 | 2021-10-06 | 2022-01-19 | 0% | PROF4 PO E.PROF4 PO E | 56 |  |  | 8494 | 8494 | 0
S143300 | Perform QA Testing on TPC FEE | 56 | 0 | 2021-10-06 | 2022-01-19 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 56 |  |  | 0 | 0 | 0
S143300 | Perform QA Testing on TPC FEE | 280 | 0 | 2021-10-06 | 2022-01-19 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 280 |  |  | 0 | 0 | 0
S143300 | Perform QA Testing on TPC FEE | 168 | 19748 | 2021-10-06 | 2022-01-19 | 0% | TECH3 PO E.TECH3 PO E | 168 |  |  | 19748 | 19748 | 0
S143300 | Perform QA Testing on TPC FEE | 323 | 57258 | 2021-10-06 | 2022-01-19 | 0% | SCI3 PO.SCI3 PO | 323 |  |  | 57258 | 57258 | 0
1.02.06.03 TPC DAM Production
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 44 | 6674 | 08-Mar-21 A | 2021-08-03 | 10% | PROF4 PO E.PROF4 PO E | 39.6 |  |  | 6006.6 | 6006.6 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 264 | 31032 | 08-Mar-21 A | 2021-08-03 | 10% | TECH3 PO E.TECH3 PO E | 237.6 |  |  | 27928.8 | 27928.8 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 44 | 0 | 08-Mar-21 A | 2021-08-03 | 10% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 39.6 |  |  | 0 | 0 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 220 | 0 | 08-Mar-21 A | 2021-08-03 | 10% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 198 |  |  | 0 | 0 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 183 | 32440 | 08-Mar-21 A | 2021-08-03 | 10% | SCI3 PO.SCI3 PO | 164.7 |  |  | 29196 | 29196 | 0
S148500 | Test Full TPC DAM System | 960 | 145959 | 2021-08-04 | 2021-12-14 | 0% | PROF4 PO E.PROF4 PO E | 960 |  |  | 145959 | 145959 | 0
S148500 | Test Full TPC DAM System | 440 | 0 | 2021-08-04 | 2021-12-14 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 440 |  |  | 0 | 0 | 0
S148500 | Test Full TPC DAM System | 440 | 78182 | 2021-08-04 | 2021-12-14 | 0% | SCI3 PO.SCI3 PO | 440 |  |  | 78182 | 78182 | 0
1.02.07.01 TPC Laser System
S150400 | Procure TPC mirror bundles with supports Labor | 24 | 0 | 13-Jan-21 A | 2021-08-31 | 50% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 12 |  |  | 0 | 0 | 0
S150400 | Procure TPC mirror bundles with supports Labor | 24 | 3533 | 13-Jan-21 A | 2021-08-31 | 50% | PROF4 PO M.PROF4 PO M | 12 |  |  | 1766.5 | 1766.5 | 0
1.02.07.02 TPC Gas System
S152800 | Assemble TPC Gas System controls | 48 | 7069 | 22-Mar-21 A | 2021-08-24 | 10% | PROF4 PO M.PROF4 PO M | 43.2 |  |  | 6362.1 | 6362.1 | 0
S152800 | Assemble TPC Gas System controls | 1920 | 0 | 22-Mar-21 A | 2021-08-24 | 10% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 1728 |  |  | 0 | 0 | 0
S152800 | Assemble TPC Gas System controls | 480 | 54779 | 22-Mar-21 A | 2021-08-24 | 10% | TECH3 PO M.TECH3 PO M | 432 |  |  | 49301.1 | 49301.1 | 0
S152900 | Set up TPC Gas System computer control Labor | 24 | 3543 | 15-Mar-21 A | 2021-10-14 | 25% | PROF4 PO M.PROF4 PO M | 18 |  |  | 2657.25 | 2657.25 | 0
S152900 | Set up TPC Gas System computer control Labor | 480 | 0 | 15-Mar-21 A | 2021-10-14 | 25% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 360 |  |  | 0 | 0 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S196900 | Test final sectors with LEDs & cosmic rays | 462 | 70218 | 23-Feb-21 A | 2022-02-04 | 10% | PROF4 PO E.PROF4 PO E | 415.8 |  |  | 63196.2 | 63196.2 | 0
S196900 | Test final sectors with LEDs & cosmic rays | 462 | 54415 | 23-Feb-21 A | 2022-02-04 | 10% | TECH3 PO E.TECH3 PO E | 415.8 |  |  | 48973.5 | 48973.5 | 0
S196900 | Test final sectors with LEDs & cosmic rays | 4608 | 0 | 23-Feb-21 A | 2022-02-04 | 10% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 4147.2 |  |  | 0 | 0 | 0
S197000 | Repair or rework any sectors as required | 231 | 35114 | 16-Mar-21 A | 2022-02-04 | 31% | PROF4 PO M.PROF4 PO M | 159.39 |  |  | 24228.66 | 24228.66 | 0
S197000 | Repair or rework any sectors as required | 462 | 54423 | 16-Mar-21 A | 2022-02-04 | 31% | TECH3 PO M.TECH3 PO M | 318.78 |  |  | 37551.87 | 37551.87 | 0
S197000 | Repair or rework any sectors as required | 2304 | 0 | 16-Mar-21 A | 2022-02-04 | 31% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1589.76 |  |  | 0 | 0 | 0
S197000 | Repair or rework any sectors as required | 462 | 98193 | 16-Mar-21 A | 2022-02-04 | 31% | SCI4 PO.SCI 4 PO | 318.78 |  |  | 67753.17 | 67753.17 | 0
S197000 | Repair or rework any sectors as required | 231 | 35114 | 16-Mar-21 A | 2022-02-04 | 31% | PROF4 PO E.PROF4 PO E | 159.39 |  |  | 24228.66 | 24228.66 | 0
S197000 | Repair or rework any sectors as required | 231 | 27211 | 16-Mar-21 A | 2022-02-04 | 31% | TECH3 PO E.TECH3 PO E | 159.39 |  |  | 18775.59 | 18775.59 | 0
1.05.02.02 EMCal Electronics: Production
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 321 | 41744 | 01-Dec-20 A | 2021-07-20 | 60% | PROF3 PO E.PROF3 PO E | 128.4 |  |  | 16697.6 | 16697.6 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 80 | 14153 | 01-Dec-20 A | 2021-07-20 | 60% | SCI3 PO.SCI3 PO | 32 |  |  | 5661.2 | 5661.2 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 80 | 9385 | 01-Dec-20 A | 2021-07-20 | 60% | TECH3 PO E.TECH3 PO E | 32 |  |  | 3754 | 3754 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 176 | 0 | 01-Dec-20 A | 2021-07-20 | 60% | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 70.4 |  |  | 0 | 0 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 176 | 0 | 01-Dec-20 A | 2021-07-20 | 60% | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 70.4 |  |  | 0 | 0 | 0
1.06.01.03 DAQ Production
S256000 | DAQ Production Boards: Firmware updates | 64 | 11345 | 2021-11-02 | 2022-01-18 | 0% | SCI3 PO.SCI3 PO | 64 |  |  | 11345 | 11345 | 0
S256000 | DAQ Production Boards: Firmware updates | 240 | 0 | 2021-11-02 | 2022-01-18 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 240 |  |  | 0 | 0 | 0
S256000 | DAQ Production Boards: Firmware updates | 960 | 125093 | 2021-11-02 | 2022-01-18 | 0% | PROF3 PO E.PROF3 PO E | 960 |  |  | 125093 | 125093 | 0
S260600 | DAQ Production: DAQ Software development | 880 | 130060 | 16-Nov-20 A | 2021-11-30 | 90% | PROF4 PO M.PROF4 PO M | 88 |  |  | 13006 | 13006 | 0
S260600 | DAQ Production: DAQ Software development | 880 | 151998 | 16-Nov-20 A | 2021-11-30 | 90% | SCI3 PO.SCI3 PO | 88 |  |  | 15199.8 | 15199.8 | 0
S260600 | DAQ Production: DAQ Software development | 1760 | 0 | 16-Nov-20 A | 2021-11-30 | 90% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 176 |  |  | 0 | 0 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S263800 | Final Design Review - DAQ Local Level-1 | 32 | 0 | 2021-08-30 | 2021-09-02 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 32 |  |  | 0 | 0 | 0
S263800 | Final Design Review - DAQ Local Level-1 | 32 | 5673 | 2021-08-30 | 2021-09-02 | 0% | SCI3 PO.SCI3 PO | 32 |  |  | 5673 | 5673 | 0
1.06.02.04 LL1 Trigger Production
S264200 | Production Readiness Review - DAQ Local Level-1 | 32 | 0 | 2021-10-14 | 2021-10-27 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 32 |  |  | 0 | 0 | 0
S264200 | Production Readiness Review - DAQ Local Level-1 | 32 | 5673 | 2021-10-14 | 2021-10-27 | 0% | SCI3 PO.SCI3 PO | 32 |  |  | 5673 | 5673 | 0
1.06.03.02 GL1 Trigger Prototype
S266600 | GL1 Prototype: test prototype | 80 | 13768 | 17-Dec-19 A | 2021-07-30 | 95% | SCI3 PO.SCI3 PO | 4 |  |  | 688.4 | 688.4 | 0
S266600 | GL1 Prototype: test prototype | 240 | 0 | 17-Dec-19 A | 2021-07-30 | 95% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 12 |  |  | 0 | 0 | 0
S266600 | GL1 Prototype: test prototype | 240 | 30362 | 17-Dec-19 A | 2021-07-30 | 95% | PROF3 PO E.PROF3 PO E | 12 |  |  | 1518.1 | 1518.1 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 80 | 13768 | 03-Nov-20 A | 2021-08-30 | 60% | SCI3 PO.SCI3 PO | 32 |  |  | 5507.2 | 5507.2 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 100 | 0 | 03-Nov-20 A | 2021-08-30 | 60% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 40 |  |  | 0 | 0 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 200 | 0 | 03-Nov-20 A | 2021-08-30 | 60% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 80 |  |  | 0 | 0 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 80 | 10121 | 03-Nov-20 A | 2021-08-30 | 60% | PROF3 PO E.PROF3 PO E | 32 |  |  | 4048.4 | 4048.4 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | 64 | 11015 | 2021-07-02 | 2021-07-30 | 0% | SCI3 PO.SCI3 PO | 64 |  |  | 11015 | 11015 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | 60 | 0 | 2021-07-02 | 2021-07-30 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 60 |  |  | 0 | 0 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | 80 | 10121 | 2021-07-02 | 2021-07-30 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10121 | 10121 | 0
1.06.03.03 GL1 Trigger Production
S266900 | GL1 Production: final firmware updates | 64 | 0 | 2021-08-02 | 2021-10-26 | 0% | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 64 |  |  | 0 | 0 | 0
S266900 | GL1 Production: final firmware updates | 64 | 11015 | 2021-08-02 | 2021-10-26 | 0% | SCI3 PO.SCI3 PO | 64 |  |  | 11015 | 11015 | 0
S266900 | GL1 Production: final firmware updates | 406 | 51363 | 2021-08-02 | 2021-10-26 | 0% | PROF3 PO E.PROF3 PO E | 406 |  |  | 51363 | 51363 | 0
S267900 | GL1 Production: install GL1 system | 80 | 10424 | 2021-10-27 | 2021-12-03 | 0% | PROF3 PO E.PROF3 PO E | 80 |  |  | 10424 | 10424 | 0
S267900 | GL1 Production: install GL1 system | 320 | 37615 | 2021-10-27 | 2021-12-03 | 0% | TECH3 PO E.TECH3 PO E | 320 |  |  | 37615 | 37615 | 0
S267900 | GL1 Production: install GL1 system | 160 | 0 | 2021-10-27 | 2021-12-03 | 0% | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 160 |  |  | 0 | 0 | 0
S268000 | GL1 Production: commission GL1 system | 72 | 12763 | 2021-12-06 | 2022-01-19 | 0% | SCI3 PO.SCI3 PO | 72 |  |  | 12763 | 12763 | 0
S268000 | GL1 Production: commission GL1 system | 108 | 0 | 2021-12-06 | 2022-01-19 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 108 |  |  | 0 | 0 | 0
S268000 | GL1 Production: commission GL1 system | 108 | 14073 | 2021-12-06 | 2022-01-19 | 0% | PROF3 PO E.PROF3 PO E | 108 |  |  | 14073 | 14073 | 0
1.06.04.02 Timing System Prototype
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | 16 | 2754 | 24-Feb-20 A | 2021-07-30 | 95% | SCI3 PO.SCI3 PO | 0.8 |  |  | 137.7 | 137.7 | 0
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | 80 | 0 | 24-Feb-20 A | 2021-07-30 | 95% | STUDENT UCol - Unpaid.STUDENT UCol - Unpaid | 4 |  |  | 0 | 0 | 0
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | 40 | 0 | 24-Feb-20 A | 2021-07-30 | 95% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 2 |  |  | 0 | 0 | 0
S269600 | Update design specifications; incorporate final design choice | 12 | 2065 | 2021-08-02 | 2021-08-13 | 0% | SCI3 PO.SCI3 PO | 12 |  |  | 2065 | 2065 | 0
S269600 | Update design specifications; incorporate final design choice | 30 | 0 | 2021-08-02 | 2021-08-13 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 30 |  |  | 0 | 0 | 0
1.06.04.03 Timing System Production
S270500 | Timing System Production: final firmware updates | 64 | 11015 | 15-Mar-21 A | 2021-08-16 | 60% | SCI3 PO.SCI3 PO | 25.6 |  |  | 4406 | 4406 | 0
S270500 | Timing System Production: final firmware updates | 64 | 0 | 15-Mar-21 A | 2021-08-16 | 60% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 25.6 |  |  | 0 | 0 | 0
S270500 | Timing System Production: final firmware updates | 560 | 70845 | 15-Mar-21 A | 2021-08-16 | 60% | PROF3 PO E.PROF3 PO E | 224 |  |  | 28338 | 28338 | 0
S270700 | Timing System Production: commission timing system | 128 | 22690 | 2021-12-13 | 2022-01-11 | 0% | SCI3 PO.SCI3 PO | 128 |  |  | 22690 | 22690 | 0
S270700 | Timing System Production: commission timing system | 192 | 0 | 2021-12-13 | 2022-01-11 | 0% | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 192 |  |  | 0 | 0 | 0
S270700 | Timing System Production: commission timing system | 320 | 41698 | 2021-12-13 | 2022-01-11 | 0% | PROF3 PO E.PROF3 PO E | 320 |  |  | 41698 | 41698 | 0
S270800 | Timing System Production: additional firmware updates | 144 | 18764 | 2022-01-12 | 2022-02-04 | 0% | PROF3 PO E.PROF3 PO E | 144 |  |  | 18764 | 18764 | 0
1.07 Min Bias Trigger Detector
S273800 | Test Full Min/Bias Electronics | 16 | 2085 | 2021-12-10 | 2022-01-18 | 0% | PROF3 PO M.PROF3 PO M | 16 |  |  | 2085 | 2085 | 0
S273800 | Test Full Min/Bias Electronics | 48 | 8509 | 2021-12-10 | 2022-01-18 | 0% | SCI3 PO.SCI3 PO | 48 |  |  | 8509 | 8509 | 0
S273800 | Test Full Min/Bias Electronics | 48 | 0 | 2021-12-10 | 2022-01-18 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 48 |  |  | 0 | 0 | 0
S274000 | Bench Test Min/Bias Detector | 80 | 14182 | 2022-01-19 | 2022-01-25 | 0% | SCI3 PO.SCI3 PO | 80 |  |  | 14182 | 14182 | 0
S274000 | Bench Test Min/Bias Detector | 80 | 0 | 2022-01-19 | 2022-01-25 | 0% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 80 |  |  | 0 | 0 | 0
A-TEC TEC
1.01.02 Labor by FY
S103200 | Mgmt Labor - A - MIE - FY21 | 1050 | 170568 | 01-Oct-20 A | 30-Sep-21* | 74.4% | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 268.8 |  |  | 43665.408 | 43665.408 | 0
S103400 | Mgmt labor - A - MIE - FY22 | 68 | 11361 | 01-Oct-21* | 2022-01-05 | 0% | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 68 |  |  | 11361 | 11361 | 0
1.01.03 Management Travel
S104200 | Travel FY21 | 5000 | 6905 | 01-Oct-20 A | 2021-09-30 | 74.4% | Travel.Travel Cost | 1280 |  |  | 1767.68 | 1767.68 | 0
1.02.01.08 TPC Assembly
S121650 | Procure Piping Fittings | 1102 | 1279 | 17-May-21 A | 2021-09-09 | 50% | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 551 |  |  | 639.5 | 639.5 | 0
S121950 | TPC Assembly technical Support | 20000 | 23254 | 01-Jun-21 A | 2021-09-20 | 33% | Purch 1st $2M.Material (Purchase (1st $2M) | 13400 |  |  | 15580.18 | 15580.18 | 0
S121605 | TPC Assembly Mechanical Engineering Support | 1500 | 156234 | 01-Feb-21 A | 2022-01-20 | 43.62% | PROF2.PROF2 | 845.7 |  |  | 88084.7292 | 88084.7292 | 0
1.02.02.03 TPC R1 Module Production
S125500 | Build TPC R1 Modules | 960 | 63130 | 11-Jan-21 A | 2021-09-03 | 85% | TECH3 Wayne - PS.TECH3 Wayne - Purchased Services | 144 |  |  | 9469.5 | 9469.5 | 0
S125600 | Test TPC R1 Modules | 960 | 63173 | 11-Jan-21 A | 2021-09-20 | 85% | TECH3 Wayne - PS.TECH3 Wayne - Purchased Services | 144 |  |  | 9475.95 | 9475.95 | 0
1.02.05.04 TPC FEE Production
S136500 | Procure TPC FEE Cooling System - Delivery Acceptance | 60155 | 69821 | 15-Mar-21 A | 2021-07-30 | 17.8% | Purch 1st $2M.Material (Purchase (1st $2M) | 49447.41 |  |  | 57392.862 | 57392.862 | 0
S141500 | Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Delivery Acceptance | 29663 | 34429 | 15-Mar-21 A | 2021-07-30 | 33.2% | Purch 1st $2M.Material (Purchase (1st $2M) | 19814.884 |  |  | 22998.572 | 22998.572 | 0
S142500 | Procure TPC FEE LV Power Supplies - Delivery Acceptance | 190056 | 220595 | 25-Jan-21 A | 2021-07-30 | 80.2% | Purch 1st $2M.Material (Purchase (1st $2M) | 37631.088 |  |  | 43677.81 | 43677.81 | 0
S143200 | Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | 150983 | 175244 | 2021-09-29 | 2021-10-05 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 150983 |  |  | 175244 | 175244 | 0
S141800 | Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | 266694 | 309548 | 02-Nov-20 A | 2021-07-30 | 85% | Purch 1st $2M.Material (Purchase (1st $2M) | 40004.1 |  |  | 46432.2 | 46432.2 | 0
S143250 | TPC Front End Electronics | 150000 | 174103 | 15-Feb-21 A | 2021-07-30 | 33.2% | Purch 1st $2M.Material (Purchase (1st $2M) | 100200 |  |  | 116300.804 | 116300.804 | 0
S143270 | TPC FEE Electrical Engineering Support 1 | 1500 | 119731 | 01-Feb-21 A | 2021-12-29 | 46.52% | TECH1.TECH1 | 802.2 |  |  | 64032.1388 | 64032.1388 | 0
S143271 | TPC FEE Electrical Engineering Support 2 | 0 | 0 | 01-Feb-21 A | 2021-12-29 | 46.52% | PROF3.PROF3 | 0 |  |  | 0 | 0 | 0
1.02.06.03 TPC DAM Production
S147300 | Procure TPC DAM Felix 2.0 Boards - Delivery Acceptance | 130362 | 151309 | 02-Dec-20 A | 2021-07-29 | 80% | Purch 1st $2M.Material (Purchase (1st $2M) | 26072.4 |  |  | 30261.8 | 30261.8 | 0
S147370 | Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Delivery Acceptance | 80745 | 93719 | 2021-10-20 | 2021-10-26 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 80745 |  |  | 93719 | 93719 | 0
S147380 | TPC DAM Electrical Engineering Support | 368 | 48327 | 01-Feb-21 A | 2021-12-30 | 45% | PROF3.PROF3 | 202.4 |  |  | 26579.85 | 26579.85 | 0
1.02.07.01 TPC Laser System
S149600 | Procure TPC Lasers - Delivery Acceptance | 145840 | 165955 | 06-Oct-20 A | 2021-08-16 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 72920 |  |  | 82977.5 | 82977.5 | 0
S150300 | Procure TPC Optics with Mirrors - Delivery Acceptance | 58800 | 66910 | 13-Oct-20 A | 2021-08-12 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 29400 |  |  | 33455 | 33455 | 0
S150500 | Procure TPC mirror bundles with supports M&S | 15000 | 17060 | 13-Jan-21 A | 2021-08-31 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 7500 |  |  | 8530 | 8530 | 0
S150800 | Install &Test TPC Laser safety interlocks M&S | 2000 | 2276 | 2021-08-20 | 2021-08-31 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 2000 |  |  | 2276 | 2276 | 0
S149650 | TPC Diffuse Lasers | 200000 | 232137 | 04-Jan-21 A | 2021-08-02 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 100000 |  |  | 116068.5 | 116068.5 | 0
1.02.07.02 TPC Gas System
S152300 | Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | 33035 | 37591 | 12-Jan-21 A | 2021-07-29 | 70% | Purch 1st $2M.Material (Purchase (1st $2M) | 9910.5 |  |  | 11277.3 | 11277.3 | 0
S153000 | Procure TPC Gas System Computer Controller M&S | 18401 | 20975 | 2021-08-25 | 2021-10-14 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 18401 |  |  | 20975 | 20975 | 0
S153700 | Procure TPC Gas System Components for Installation - Delivery Acceptance | 34086 | 39563 | 08-Mar-21 A | 2021-08-31 | 70% | Purch 1st $2M.Material (Purchase (1st $2M) | 10225.8 |  |  | 11868.9 | 11868.9 | 0
1.02.07.03 TPC Cooling System
S155700 | Procure TPC Plumbing - Contract/PO M&S | 11667 | 13542 | 2021-09-15 | 2021-10-13 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 11667 |  |  | 13542 | 13542 | 0
S155900 | Set up TPC Cooling System computer controls M&S | 10493 | 12179 | 2021-10-14 | 2021-10-20 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 10493 |  |  | 12179 | 12179 | 0
1.03.01.03.01 Order Material for EMCAL Final Block Production
S172800 | Prepare fiber assemblies for final blocks | 0 | 0 | 21-Jun-19 A | 2021-08-02 | 96% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 0 |  |  | 0 | 0 | 0
S172800 | Prepare fiber assemblies for final blocks | 9360 | 163757 | 21-Jun-19 A | 2021-08-02 | 96% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 374.4 |  |  | 6550.28 | 6550.28 | 0
S172800 | Prepare fiber assemblies for final blocks | 0 | 0 | 21-Jun-19 A | 2021-08-02 | 96% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 0 |  |  | 0 | 0 | 0
S171800 | Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | 90653 | 104592 | 03-Aug-20 A | 2021-07-19 | 55% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 40793.85 |  |  | 47066.4 | 47066.4 | 0
S172500 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | 26230 | 30218 | 03-Aug-20 A | 2021-07-19 | 75% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6557.5 |  |  | 7554.5 | 7554.5 | 0
S172850 | Supervise EMCal Final Block Production | 52800 | 60868 | 01-May-20 A | 2021-11-30 | 65% | Purch 1st $2M.Material (Purchase (1st $2M) | 18480 |  |  | 21303.8 | 21303.8 | 0
S172870 | EMCal Block Production QA | 460000 | 533915 | 01-Dec-20 A | 2021-09-27 | 70% | Purch 1st $2M.Material (Purchase (1st $2M) | 138000 |  |  | 160174.5 | 160174.5 | 0
1.03.01.03.02 Fabricate final blocks
S175900 | Fabricate final blocks sector 42 | 50 | 2663 | 30-Jun-21 A | 2021-07-08 | 88% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 6 |  |  | 319.56 | 319.56 | 0
S175900 | Fabricate final blocks sector 42 | 75 | 1337 | 30-Jun-21 A | 2021-07-08 | 88% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 9 |  |  | 160.44 | 160.44 | 0
S175900 | Fabricate final blocks sector 42 | 10 | 1162 | 30-Jun-21 A | 2021-07-08 | 88% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 1.2 |  |  | 139.44 | 139.44 | 0
S176000 | Fabricate final blocks sector 43 | 50 | 2663 | 2021-07-09 | 2021-07-16 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176000 | Fabricate final blocks sector 43 | 75 | 1337 | 2021-07-09 | 2021-07-16 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176000 | Fabricate final blocks sector 43 | 10 | 1162 | 2021-07-09 | 2021-07-16 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176100 | Fabricate final blocks sector 44 | 50 | 2663 | 2021-07-19 | 2021-07-26 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176100 | Fabricate final blocks sector 44 | 75 | 1337 | 2021-07-19 | 2021-07-26 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176100 | Fabricate final blocks sector 44 | 10 | 1162 | 2021-07-19 | 2021-07-26 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176200 | Fabricate final blocks sector 45 | 50 | 2663 | 2021-07-27 | 2021-08-03 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176200 | Fabricate final blocks sector 45 | 75 | 1337 | 2021-07-27 | 2021-08-03 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176200 | Fabricate final blocks sector 45 | 10 | 1162 | 2021-07-27 | 2021-08-03 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176300 | Fabricate final blocks sector 46 | 50 | 2663 | 2021-08-04 | 2021-08-11 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176300 | Fabricate final blocks sector 46 | 75 | 1337 | 2021-08-04 | 2021-08-11 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176300 | Fabricate final blocks sector 46 | 10 | 1162 | 2021-08-04 | 2021-08-11 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176400 | Fabricate final blocks sector 47 | 50 | 2663 | 2021-08-12 | 2021-08-19 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176400 | Fabricate final blocks sector 47 | 75 | 1337 | 2021-08-12 | 2021-08-19 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176400 | Fabricate final blocks sector 47 | 10 | 1162 | 2021-08-12 | 2021-08-19 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176500 | Fabricate final blocks sector 48 | 50 | 2663 | 2021-08-20 | 2021-08-27 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176500 | Fabricate final blocks sector 48 | 75 | 1337 | 2021-08-20 | 2021-08-27 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176500 | Fabricate final blocks sector 48 | 10 | 1162 | 2021-08-20 | 2021-08-27 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176600 | Fabricate final blocks sector 49 | 50 | 2663 | 2021-08-30 | 2021-09-07 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176600 | Fabricate final blocks sector 49 | 75 | 1337 | 2021-08-30 | 2021-09-07 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176600 | Fabricate final blocks sector 49 | 10 | 1162 | 2021-08-30 | 2021-09-07 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176700 | Fabricate final blocks sector 50 | 50 | 2663 | 2021-09-08 | 2021-09-15 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176700 | Fabricate final blocks sector 50 | 75 | 1337 | 2021-09-08 | 2021-09-15 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176700 | Fabricate final blocks sector 50 | 10 | 1162 | 2021-09-08 | 2021-09-15 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176800 | Fabricate final blocks sector 51 | 50 | 2663 | 2021-09-16 | 2021-09-23 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176800 | Fabricate final blocks sector 51 | 75 | 1337 | 2021-09-16 | 2021-09-23 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176800 | Fabricate final blocks sector 51 | 10 | 1162 | 2021-09-16 | 2021-09-23 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S176900 | Fabricate final blocks sector 52 | 50 | 2663 | 2021-09-24 | 2021-10-01 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S176900 | Fabricate final blocks sector 52 | 75 | 1337 | 2021-09-24 | 2021-10-01 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S176900 | Fabricate final blocks sector 52 | 10 | 1162 | 2021-09-24 | 2021-10-01 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177000 | Fabricate final blocks sector 53 | 50 | 2663 | 2021-10-04 | 2021-10-12 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177000 | Fabricate final blocks sector 53 | 75 | 1337 | 2021-10-04 | 2021-10-12 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177000 | Fabricate final blocks sector 53 | 10 | 1162 | 2021-10-04 | 2021-10-12 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177100 | Fabricate final blocks sector 54 | 50 | 2663 | 2021-10-13 | 2021-10-20 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177100 | Fabricate final blocks sector 54 | 75 | 1337 | 2021-10-13 | 2021-10-20 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177100 | Fabricate final blocks sector 54 | 10 | 1162 | 2021-10-13 | 2021-10-20 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177200 | Fabricate final blocks sector 55 | 50 | 2663 | 2021-10-21 | 2021-10-28 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177200 | Fabricate final blocks sector 55 | 75 | 1337 | 2021-10-21 | 2021-10-28 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177200 | Fabricate final blocks sector 55 | 10 | 1162 | 2021-10-21 | 2021-10-28 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177300 | Fabricate final blocks sector 56 | 50 | 2663 | 2021-10-29 | 2021-11-04 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177300 | Fabricate final blocks sector 56 | 75 | 1337 | 2021-10-29 | 2021-11-04 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177300 | Fabricate final blocks sector 56 | 10 | 1162 | 2021-10-29 | 2021-11-04 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177400 | Fabricate final blocks sector 57 | 50 | 2663 | 2021-11-05 | 2021-11-12 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177400 | Fabricate final blocks sector 57 | 75 | 1337 | 2021-11-05 | 2021-11-12 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177400 | Fabricate final blocks sector 57 | 10 | 1162 | 2021-11-05 | 2021-11-12 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177500 | Fabricate final blocks sector 58 | 50 | 2663 | 2021-11-15 | 2021-11-19 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177500 | Fabricate final blocks sector 58 | 75 | 1337 | 2021-11-15 | 2021-11-19 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177500 | Fabricate final blocks sector 58 | 10 | 1162 | 2021-11-15 | 2021-11-19 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177600 | Fabricate final blocks sector 59 | 50 | 2663 | 2021-11-22 | 2021-11-30 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177600 | Fabricate final blocks sector 59 | 75 | 1337 | 2021-11-22 | 2021-11-30 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177600 | Fabricate final blocks sector 59 | 10 | 1162 | 2021-11-22 | 2021-11-30 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177700 | Fabricate final blocks sector 60 | 50 | 2663 | 2021-12-01 | 2021-12-07 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177700 | Fabricate final blocks sector 60 | 75 | 1337 | 2021-12-01 | 2021-12-07 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177700 | Fabricate final blocks sector 60 | 10 | 1162 | 2021-12-01 | 2021-12-07 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177800 | Fabricate final blocks sector 61 | 50 | 2663 | 2021-12-08 | 2021-12-14 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177800 | Fabricate final blocks sector 61 | 75 | 1337 | 2021-12-08 | 2021-12-14 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177800 | Fabricate final blocks sector 61 | 10 | 1162 | 2021-12-08 | 2021-12-14 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S177900 | Fabricate final blocks sector 62 | 50 | 2663 | 2021-12-15 | 2021-12-21 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S177900 | Fabricate final blocks sector 62 | 75 | 1337 | 2021-12-15 | 2021-12-21 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S177900 | Fabricate final blocks sector 62 | 10 | 1162 | 2021-12-15 | 2021-12-21 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S178000 | Fabricate final blocks sector 63 | 50 | 2663 | 2021-12-22 | 2021-12-29 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S178000 | Fabricate final blocks sector 63 | 75 | 1337 | 2021-12-22 | 2021-12-29 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S178000 | Fabricate final blocks sector 63 | 10 | 1162 | 2021-12-22 | 2021-12-29 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
S178100 | Fabricate final blocks sector 64 | 50 | 2663 | 2021-12-30 | 2022-01-06 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 |  |  | 2663 | 2663 | 0
S178100 | Fabricate final blocks sector 64 | 75 | 1337 | 2021-12-30 | 2022-01-06 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 |  |  | 1337 | 1337 | 0
S178100 | Fabricate final blocks sector 64 | 10 | 1162 | 2021-12-30 | 2022-01-06 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 |  |  | 1162 | 1162 | 0
1.03.01.03.03 Pack and ship final blocks to BNL
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | 16 | 285 | 15-Jun-21 A | 2021-09-03 | 5% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 15.2 |  |  | 270.75 | 270.75 | 0
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | 10 | 533 | 15-Jun-21 A | 2021-09-03 | 5% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 9.5 |  |  | 506.35 | 506.35 | 0
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | 15 | 1743 | 15-Jun-21 A | 2021-09-03 | 5% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 14.25 |  |  | 1655.85 | 1655.85 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | 16 | 285 | 2021-11-05 | 2021-11-12 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 |  |  | 285 | 285 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | 10 | 533 | 2021-11-05 | 2021-11-12 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 |  |  | 533 | 533 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | 15 | 1743 | 2021-11-05 | 2021-11-12 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 |  |  | 1743 | 1743 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 16 | 285 | 2022-01-07 | 2022-01-07 | 0% | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 |  |  | 285 | 285 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 10 | 533 | 2022-01-07 | 2022-01-07 | 0% | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 |  |  | 533 | 533 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 15 | 1743 | 2022-01-07 | 2022-01-07 | 0% | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 |  |  | 1743 | 1743 | 0
S178710 | Pack and ship final blocks for sectors 40-48 to BNL - M&S | 6480 | 7521 | 15-Jun-21 A | 2021-09-03 | 5% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6156 |  |  | 7144.95 | 7144.95 | 0
S178910 | Pack and ship final blocks for sectors 49-56 to BNL - M&S | 6480 | 7521 | 2021-11-05 | 2021-11-12 | 0% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 |  |  | 7521 | 7521 | 0
S176010 | Pack and ship final blocks for sectors 57-64 to BNL - M&S | 6480 | 7521 | 2022-01-07 | 2022-01-07 | 0% | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 |  |  | 7521 | 7521 | 0
1.03.02.02.03 EMCAL Final Module Fabrication
S187700 | Install light guides on final blocks M&S | 1650 | 1912 | 21-Jan-21 A | 2022-01-31 | 35% | Purch 1st $2M.Material (Purchase (1st $2M) | 1072.5 |  |  | 1242.8 | 1242.8 | 0
S188100 | Install SiPMs daughterboards on final blocks M&S | 300 | 348 | 22-Jan-21 A | 2022-02-03 | 35% | Purch 1st $2M.Material (Purchase (1st $2M) | 195 |  |  | 226.2 | 226.2 | 0
S187400 | Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | 215244 | 240129 | 22-Dec-20 A | 2021-07-30 | 74% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 55963.44 |  |  | 62433.54 | 62433.54 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S196100 | Procure EMCAL Cooling System for Final Sectors - Delivery Acceptance | 70893 | 82284 | 18-Jan-21 A | 2021-07-14 | 42% | Purch 1st $2M.Material (Purchase (1st $2M) | 41117.94 |  |  | 47724.72 | 47724.72 | 0
S196910 | Technical support labor for EMCal assembly | 3520 | 281000 | 04-Jan-21 A | 2022-01-12 | 50% | TECH1.TECH1 | 1760 |  |  | 140500 | 140500 | 0
1.04.01 Inner HCAL Support Structure & Support Rings
S199310 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 2 | 237500 | 264958 | 16-Aug-21* | 2021-08-20 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 |  |  | 264958 | 264958 | 0
S199320 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 3 | 237500 | 264958 | 24-Sep-21* | 2021-09-30 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 |  |  | 264958 | 264958 | 0
S199330 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 4 | 237500 | 264958 | 15-Nov-21* | 2021-11-19 | 0% | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 |  |  | 264958 | 264958 | 0
1.05.02.02 EMCal Electronics: Production
S228100 | Test SiPM Daughter Boards Production Sectors 13-64 | 176 | 2888 | 01-Dec-20 A | 2021-07-20 | 60% | STUDENT UM - PS.STUDENT UM - Purchased Services | 70.4 |  |  | 1155.2 | 1155.2 | 0
S229400 | Test EMCal Preamp Boards: Production Sectors 13-64 | 384 | 6313 | 26-Feb-21 A | 2021-07-14 | 40% | STUDENT UM - PS.STUDENT UM - Purchased Services | 230.4 |  |  | 3787.8 | 3787.8 | 0
S233200 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Delivery Acceptance | 177356 | 205854 | 2021-12-27 | 2022-01-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 177356 |  |  | 205854 | 205854 | 0
S233250 | Trunk Signal Cables - EMCal | 670160 | 777844 | 2021-07-30 | 2021-12-23 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 670160 |  |  | 777844 | 777844 | 0
1.05.02.04 HCal Electronics: Production
S244400 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | 87827 | 101939 | 14-Dec-20 A | 2021-08-27 | 50% | Purch 1st $2M.Material (Purchase (1st $2M) | 43913.5 |  |  | 50969.5 | 50969.5 | 0
S244450 | Trunk Signal Cables - OuterHCal | 128640 | 149310 | 2021-07-30 | 2021-12-23 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 128640 |  |  | 149310 | 149310 | 0
1.05.03.02 Calorimeter Digitizers: Production
S252800 | Procure Production Digitizer (Boards) - Delivery Acceptance | 129049 | 149785 | 2021-08-03 | 2021-08-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 129049 |  |  | 149785 | 149785 | 0
S252900 | Procure Production Digitizer (Assembly & Tests) - Delivery Acceptance | 199077 | 231066 | 2021-10-28 | 2021-11-03 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 199077 |  |  | 231066 | 231066 | 0
S252700 | Procure Production Digitizer (Parts) - Delivery Acceptance | 584602 | 678538 | 30-Apr-21 A | 2021-08-09 | 37% | Purch 1st $2M.Material (Purchase (1st $2M) | 368299.26 |  |  | 427478.94 | 427478.94 | 0
1.06.01.03 DAQ Production
S255900 | Procure DAQ Production Boards - Delivery Acceptance | 104682 | 121503 | 2021-10-26 | 2021-11-01 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 104682 |  |  | 121503 | 121503 | 0
S256700 | Procure DAQ Production Crates - Delivery Acceptance | 64000 | 74284 | 2021-11-24 | 2021-12-02 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 64000 |  |  | 74284 | 74284 | 0
S258700 | Procure DAQ Production jSEB Slow control computers - Delivery Acceptance | 16856 | 19181 | 2021-08-02 | 2021-08-06 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 16856 |  |  | 19181 | 19181 | 0
S259500 | Procure DAQ Production Buffer Boxes - Delivery Acceptance | 223540 | 259459 | 23-Nov-20 A | 2021-10-29 | 18% | Purch 1st $2M.Material (Purchase (1st $2M) | 183302.8 |  |  | 212756.38 | 212756.38 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S263600 | Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance | 60000 | 69641 | 2021-08-02 | 2021-08-06 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 60000 |  |  | 69641 | 69641 | 0
1.06.02.04 LL1 Trigger Production
S264900 | Procure Production LL1 System - Delivery Acceptance | 117000 | 135800 | 2021-11-04 | 2021-11-10 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 117000 |  |  | 135800 | 135800 | 0
1.06.03.03 GL1 Trigger Production
S267600 | Procure Production GL1 Components - final hardware - Delivery Acceptance | 28150 | 32673 | 2021-09-14 | 2021-09-20 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 28150 |  |  | 32673 | 32673 | 0
1.06.04.03 Timing System Production
S270300 | Timing System Production (FPGA Boards) - Delivery Acceptance | 41600 | 48284 | 2021-10-27 | 2021-11-02 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 41600 |  |  | 48284 | 48284 | 0
1.07 Min Bias Trigger Detector
S273500 | Procure Min/Bias Electronics (sPHENIX Production Digitizers) - Delivery Acceptance | 14770 | 17143 | 2021-12-03 | 2021-12-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 14770 |  |  | 17143 | 17143 | 0
S273600 | Procure MBD Shaper/Disc Board 128 Channels - Delivery Acceptance | 46420 | 53879 | 2021-12-03 | 2021-12-09 | 0% | Purch 1st $2M.Material (Purchase (1st $2M) | 46420 |  |  | 53879 | 53879 | 0
Formulas:
Forecast Finish = VLOOKUP([Activity ID],'forecast data dump'!$A1:H3450,5,FALSE)
Forecast Start = VLOOKUP([Activity ID],'forecast data dump'!$A1:H3450,4,FALSE)

## ETC sheet-full (hidden)
Baseline data |  |  |  |  | Forecast Data (June status file)
Activity ID | Activity Name | Resource ID Name | Baseline Units | Baseline Cost | Forecast Start | Forecast Finish | % Complete | Calc ETC Units | Updated ETC Units | Potential PCR? | Calc ETC Cost | Updated ETC Cost | EAC Growth
B BNL Contributed Labor
POM02B-PCR026 POM02 sPHENIX WBS 1.x, 2.x Baseline PCR026 Approved
1 MIE Project
1.01 Project Management
S102600 | Actuals - Labor - B - BNL Contributed Labor - sPHENIX Project Management FY18 | Actual Labor.Actual Labor | 6861 | 1146441 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S102200 | Actuals - Labor - B - BNL Contributed Labor - sPHENIX Project Management FY17 | Actual Labor.Actual Labor | 2984 | 498662 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S102610 | Actuals - Labor - B - BNL Contributed Labor - sPHENIX Project Management FY19M8 | Actual Labor.Actual Labor | 6325 | 1056792 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.01.02 Labor by FY
S103110 | Mgmt labor - B - BNL Contributed Labor - FY20 - CA-D Resource(s) | PROF5 AD.PROF5 AD | 884 | 150254 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103310 | Mgmt labor - B - BNL Contributed Labor - FY21 - CA-D Resource(s) | PROF5 AD.PROF5 AD | 880 | 154145 | 01-Oct-20 A | 30-Sep-21* | 74.3% | 226.16 |  |  | 39615.265 | 39615.265 | 0
S103510 | Mgmt labor - B - BNL Contributed Labor - FY22 - CA-D Resource(s) | PROF5 AD.PROF5 AD | 35 | 6351 | 01-Oct-21* | 2022-01-05 | 0% | 35 |  |  | 6351 | 6351 | 0
S103100 | Mgmt labor - B - BNL Contributed Labor - FY20 - Physics Resource(s) | SCI4 PO.SCI 4 PO | 2965 | 610516 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103100 | Mgmt labor - B - BNL Contributed Labor - FY20 - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 101 | 14815 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103100 | Mgmt labor - B - BNL Contributed Labor - FY20 - Physics Resource(s) | PROF5 PO M.PROF5 PO M | 470 | 79908 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103100 | Mgmt labor - B - BNL Contributed Labor - FY20 - Physics Resource(s) | SCI2 PO.SCI2 PO | 1896 | 283337 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103100 | Mgmt labor - B - BNL Contributed Labor - FY20 - Physics Resource(s) | PROF2 PO PC.PROF2 PO PC | 1639 | 164212 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103100 | Mgmt labor - B - BNL Contributed Labor - FY20 - Physics Resource(s) | ADMIN1 PO.ADMIN1 PO | 428 | 25983 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103100 | Mgmt labor - B - BNL Contributed Labor - FY20 - Physics Resource(s) | ADMIN7 PO.ADMIN7 PO | 1619 | 366597 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | SCI4 PO.SCI 4 PO | 2965 | 628831 | 01-Oct-20 A | 30-Sep-21* | 74.3% | 762.005 |  |  | 161609.567 | 161609.567 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | SCI2 PO.SCI2 PO | 1896 | 291837 | 01-Oct-20 A | 30-Sep-21* | 74.3% | 487.272 |  |  | 75002.109 | 75002.109 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 100 | 15199 | 01-Oct-20 A | 30-Sep-21* | 74.3% | 25.7 |  |  | 3906.143 | 3906.143 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | PROF5 PO M.PROF5 PO M | 468 | 81977 | 01-Oct-20 A | 30-Sep-21* | 74.3% | 120.276 |  |  | 21068.089 | 21068.089 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | PROF2 PO PC.PROF2 PO PC | 1632 | 168465 | 01-Oct-20 A | 30-Sep-21* | 74.3% | 419.424 |  |  | 43295.505 | 43295.505 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | ADMIN1 PO.ADMIN1 PO | 426 | 26656 | 01-Oct-20 A | 30-Sep-21* | 74.3% | 109.482 |  |  | 6850.592 | 6850.592 | 0
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | ADMIN7 PO.ADMIN7 PO | 1613 | 376091 | 01-Oct-20 A | 30-Sep-21* | 74.3% | 414.541 |  |  | 96655.387 | 96655.387 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 4 | 626 | 01-Oct-21* | 2022-01-05 | 0% | 4 |  |  | 626 | 626 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | PROF5 PO M.PROF5 PO M | 19 | 3377 | 01-Oct-21* | 2022-01-05 | 0% | 19 |  |  | 3377 | 3377 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | SCI2 PO.SCI2 PO | 75 | 11891 | 01-Oct-21* | 2022-01-05 | 0% | 75 |  |  | 11891 | 11891 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | PROF2 PO PC.PROF2 PO PC | 65 | 6941 | 01-Oct-21* | 2022-01-05 | 0% | 65 |  |  | 6941 | 6941 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | ADMIN1 PO.ADMIN1 PO | 17 | 1098 | 01-Oct-21* | 2022-01-05 | 0% | 17 |  |  | 1098 | 1098 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | ADMIN7 PO.ADMIN7 PO | 65 | 15494 | 01-Oct-21* | 2022-01-05 | 0% | 65 |  |  | 15494 | 15494 | 0
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | SCI4 PO.SCI 4 PO | 118 | 25777 | 01-Oct-21* | 2022-01-05 | 0% | 118 |  |  | 25777 | 25777 | 0
S103705 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) Split | ADMIN1 PO.ADMIN1 PO | 143 | 8434 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S103705 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) Split | ADMIN7 PO.ADMIN7 PO | 542 | 119134 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S103705 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) Split | PROF2 PO PC.PROF2 PO PC | 548 | 53321 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S103705 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) Split | PROF4 PO M.PROF4 PO M | 34 | 4861 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S103705 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) Split | PROF5 PO M.PROF5 PO M | 157 | 25922 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S103705 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) Split | SCI4 PO.SCI 4 PO | 996 | 199111 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S103705 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) Split | SCI2 PO.SCI2 PO | 637 | 92420 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S103715 | Mgmt labor - B - BNL Contributed Labor - FY19 - CA-D Resource(s) Split | PROF5 AD.PROF5 AD | 296 | 48872 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02 TPC
S104400 | Actuals - Labor - sPHENIX TPC FY17 | Actual Labor.Actual Labor | 1405 | 234824 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S104500 | Actuals - Labor - sPHENIX TPC FY18 | Actual Labor.Actual Labor | 4288 | 716473 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S104510 | Actuals - Labor - sPHENIX TPC FY19M8 | Actual Labor.Actual Labor | 2218 | 370642 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1000799 | Actuals - NonLabor - sPHENIX TPC FY19M8 | Actual NonLabor.Actual Nonlabor | 140825 | 155367 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01 TPC Mechanics
1.02.01.01 TPC v1 Field Cage Prototype
S109200 | Preliminary Design Review - TPC Field Cage | PROF4 PO M.PROF4 PO M | 4 | 589 | 27-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109200 | Preliminary Design Review - TPC Field Cage | SCI3 PO.SCI3 PO | 4 | 688 | 27-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S108700 | Procure TPC Handling Cart Labor | TECH3 PO M.TECH3 PO M | 32 | 3761 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.02 TPC v2 Field Cage
S112200 | TPC Field Cage Safety Review | SCI3 PO.SCI3 PO | 4 | 688 | 2021-08-16 | 2021-08-18 | 0% | 4 |  |  | 688 | 688 | 0
S112200 | TPC Field Cage Safety Review | PROF4 PO M.PROF4 PO M | 4 | 589 | 2021-08-16 | 2021-08-18 | 0% | 4 |  |  | 589 | 589 | 0
S112300 | Final Design Review - TPC Field Cage | SCI3 PO.SCI3 PO | 4 | 688 | 2021-08-19 | 2021-08-23 | 0% | 4 |  |  | 688 | 688 | 0
S112300 | Final Design Review - TPC Field Cage | PROF4 PO M.PROF4 PO M | 4 | 589 | 2021-08-19 | 2021-08-23 | 0% | 4 |  |  | 589 | 589 | 0
S112100 | Benchtest TPC v2 Field Cage | SCI3 PO.SCI3 PO | 4 | 688 | 2021-08-02 | 2021-08-06 | 0% | 4 |  |  | 688 | 688 | 0
S112100 | Benchtest TPC v2 Field Cage | PROF4 PO M.PROF4 PO M | 4 | 589 | 2021-08-02 | 2021-08-06 | 0% | 4 |  |  | 589 | 589 | 0
1.02.01.03 TPC Final Field Cage
S112700 | Procure TPC v2 Field Cage Modification Parts Labor | TECH3 PO M.TECH3 PO M | 32 | 3652 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S112500 | TPC Field Cage Safety Review | PROF4 PO M.PROF4 PO M | 4 | 589 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S112500 | TPC Field Cage Safety Review | SCI3 PO.SCI3 PO | 4 | 688 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S112600 | Procurement Readiness Review - TPC Field Cage | PROF4 PO M.PROF4 PO M | 4 | 589 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S112600 | Procurement Readiness Review - TPC Field Cage | SCI3 PO.SCI3 PO | 4 | 688 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.04 TPC v1 Modules
1.02.01.04.04 TPC v1b Module Prototype
S116801 | Final Design Review - TPC Module | PROF4 PO M.PROF4 PO M | 4 | 572 | 02-Dec-19 A | 02-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S116801 | Final Design Review - TPC Module | SCI3 PO.SCI3 PO | 4 | 668 | 02-Dec-19 A | 02-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.05 TPC v2 Modules
1.02.01.05.02 TPC v2 Module Common Mechanics
S117000 | Procure TPC v2 Module Strongback Labor | TECH3 PO M.TECH3 PO M | 16 | 1826 | 05-Feb-20 A | 26-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117300 | Procure TPC v2 Module Frames Labor | TECH3 PO M.TECH3 PO M | 24 | 2739 | 11-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117600 | Procure TPC v2 Module Grid Parts Labor | TECH3 PO M.TECH3 PO M | 24 | 2739 | 14-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117800 | Assemble TPC v2 Module Grid | TECH3 PO M.TECH3 PO M | 80 | 9130 | 14-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.05.03 TPC v2a Module Prototype
S118000 | Procure TPC v2a Module Padplane Labor | TECH3 PO E.TECH3 PO E | 16 | 1826 | 26-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118300 | Procure TPC v2a Module GEMs Labor | TECH3 PO E.TECH3 PO E | 32 | 3652 | 26-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118600 | Frame TPC v2a Module GEMs | TECH3 PO M.TECH3 PO M | 40 | 4565 | 08-Apr-20 A | 14-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S119000 | TPC Module Safety Review | PROF4 PO M.PROF4 PO M | 4 | 589 | 01-Oct-20 A | 01-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S119000 | TPC Module Safety Review | SCI3 PO.SCI3 PO | 4 | 688 | 01-Oct-20 A | 01-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S119100 | Production Readiness Review - TPC Module | PROF4 PO M.PROF4 PO M | 4 | 589 | 06-May-20 A | 06-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S119100 | Production Readiness Review - TPC Module | SCI3 PO.SCI3 PO | 4 | 688 | 06-May-20 A | 06-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.07 TPC High Voltage System
S120700 | Procure TPC GEM HV Power Supplies and Membrane Power Supply - Provide Requirements to Procurement | TECH3 PO M.TECH3 PO M | 32 | 3652 | 21-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.02 TPC R1 Modules
1.02.02.02 TPC R1 Pre-Production Module
S123800 | Production Readiness Review - TPC Module Factories | PROF4 PO M.PROF4 PO M | 4 | 589 | 17-Dec-19 A | 17-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S123800 | Production Readiness Review - TPC Module Factories | SCI3 PO.SCI3 PO | 4 | 688 | 17-Dec-19 A | 17-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.02.03 TPC R1 Module Production
S123900 | Procure TPC R1 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | TECH3 PO M.TECH3 PO M | 128 | 14608 | 02-Oct-19 A | 08-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S123900 | Procure TPC R1 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | PROF4 AM.PROF4 AM | 64 | 9425 | 02-Oct-19 A | 08-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.03 TPC R2 Modules
1.02.03.02 TPC R2 Pre-Production Module
S127502 | Procure TPC R2 Pre-Production Module GEMs Labor Split | TECH3 PO M.TECH3 PO M | 12 | 1330 | 01-Aug-19 A | 20-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.03.03 TPC R2 Module Production
S127900 | Procure TPC R2 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | TECH3 PO M.TECH3 PO M | 128 | 14608 | 02-Oct-19 A | 08-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S127900 | Procure TPC R2 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | PROF4 AM.PROF4 AM | 64 | 9425 | 02-Oct-19 A | 08-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.04 TPC R3 Modules
1.02.04.02 TPC R3 Pre-Production Module
S130900 | Procure TPC R3 Pre-Production Module Frames - Labor | TECH3 PO M.TECH3 PO M | 24 | 2659 | 01-Aug-19 A | 29-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S131500 | Procure TPC R3 Pre-Production Module GEMs Labor | TECH3 PO M.TECH3 PO M | 24 | 2659 | 01-Aug-19 A | 29-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.04.03 TPC R3 Module Production
S132100 | Procure TPC R3 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | TECH3 PO M.TECH3 PO M | 128 | 14608 | 02-Oct-19 A | 08-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S132100 | Procure TPC R3 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | PROF4 AM.PROF4 AM | 64 | 9425 | 02-Oct-19 A | 08-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.05 TPC FEE
1.02.05.02 TPC FEE Prototype v2 (Pre-Production)
S136900 | v2 Procure TPC FEE preproducion prototype components Labor | PROF4 PO E.PROF4 PO E | 16 | 2356 | 02-Jan-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137100 | v2 Fabricate TPC FEE preproduction prototype boards Labor | PROF4 PO E.PROF4 PO E | 20 | 2945 | 01-Apr-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137700 | Final Design Review, Production Readiness Review - TPC FEE | PROF4 PO M.PROF4 PO M | 4 | 589 | 13-Apr-20 A | 2021-07-28 | 95% | 0.2 |  |  | 29.45 | 29.45 | 0
S137700 | Final Design Review, Production Readiness Review - TPC FEE | SCI3 PO.SCI3 PO | 4 | 688 | 13-Apr-20 A | 2021-07-28 | 95% | 0.2 |  |  | 34.4 | 34.4 | 0
S136802 | v2 Design TPC FEE preproduction prototype Split | PROF4 PO E.PROF4 PO E | 332 | 47468 | 01-Aug-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S136802 | v2 Design TPC FEE preproduction prototype Split | TECH3 PO D.TECH3 PO D | 396 | 43876 | 01-Aug-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.05.03 SAMPA chip 80 nsec
S140600 | Test v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip March 2020 | SCI3 PO.SCI3 PO | 10 | 1721 | 02-Mar-20 A | 03-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S140600 | Test v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip March 2020 | PROF3 PO E.PROF3 PO E | 10 | 1265 | 02-Mar-20 A | 03-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S140700 | Review Results of SAMPA 80 nsec Full Chip Performance with v2 Prototype TPC FEE Board | PROF5 PO S.PROF5 PO S Software | 40 | 6803 | 17-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S140700 | Review Results of SAMPA 80 nsec Full Chip Performance with v2 Prototype TPC FEE Board | SCI3 PO.SCI3 PO | 185 | 31840 | 17-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S140700 | Review Results of SAMPA 80 nsec Full Chip Performance with v2 Prototype TPC FEE Board | PROF4 PO E.PROF4 PO E | 40 | 5891 | 17-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S138900 | Review Design of Full-scale Production Chip (USP + BNL) | PROF3 IO E.PROF3 IO E | 20 | 2456 | 29-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S138900 | Review Design of Full-scale Production Chip (USP + BNL) | SCI3 PO.SCI3 PO | 20 | 3342 | 29-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S139800 | Procure Engineering Run of Full SAMPA Chip - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 40 | 6884 | 27-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S140701 | Production Readiness Review for TPC FEE full production | PROF3 IO E.PROF3 IO E | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | 8 |  |  | 1012 | 1012 | 0
S140701 | Production Readiness Review for TPC FEE full production | PROF4 PO E.PROF4 PO E | 8 | 1178 | 2021-07-01 | 2021-07-01 | 0% | 8 |  |  | 1178 | 1178 | 0
S140701 | Production Readiness Review for TPC FEE full production | SCI3 PO.SCI3 PO | 8 | 1377 | 2021-07-01 | 2021-07-01 | 0% | 8 |  |  | 1377 | 1377 | 0
S138901 | Final Design Review - SAMPA chip 80 nsec | PROF3 IO E.PROF3 IO E | 8 | 983 | 28-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S138901 | Final Design Review - SAMPA chip 80 nsec | SCI3 PO.SCI3 PO | 8 | 1337 | 28-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S140605 | Test v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip | SCI3 PO.SCI3 PO | 190 | 32700 | 03-Aug-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S140605 | Test v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip | PROF3 PO E.PROF3 PO E | 190 | 24037 | 03-Aug-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.05.04 TPC FEE Production
S135900 | Procure TPC FEE Cooling System - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 10 | 1721 | 11-Jan-21 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S135900 | Procure TPC FEE Cooling System - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 10 | 1265 | 11-Jan-21 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S141900 | Procure TPC FEE LV power supplies - Provide Requirements to Procurement | PROF4 PO E.PROF4 PO E | 32 | 4712 | 25-Aug-20 A | 27-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S142600 | Procure TPC FEE Production Boards & Assembly - Provide Requirements to Procurement | PROF4 PO E.PROF4 PO E | 44 | 6480 | 13-May-20 A | 26-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S135802 | Design TPC FEE Cooling System Split | PROF3 PO M.PROF3 PO M | 160 | 19652 | 01-Aug-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.06 TPC DAM
1.02.06.02 TPC DAM Evaluation -- FELIX 2.0
S146500 | Production Readiness Review - TPC DAM | PROF4 PO M.PROF4 PO M | 4 | 589 | 03-Feb-20 A | 04-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146500 | Production Readiness Review - TPC DAM | SCI3 PO.SCI3 PO | 4 | 688 | 03-Feb-20 A | 04-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146201 | Final Design Review - TPC DAM | PROF4 PO M.PROF4 PO M | 4 | 572 | 02-Jan-20 A | 02-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146201 | Final Design Review - TPC DAM | SCI3 PO.SCI3 PO | 4 | 668 | 02-Jan-20 A | 02-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146402 | Measure Throughput of FELIX 2.0 for TPC DAM Split | PROF4 PO E.PROF4 PO E | 41 | 6025 | 21-Aug-19 A | 22-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146402 | Measure Throughput of FELIX 2.0 for TPC DAM Split | SCI3 PO.SCI3 PO | 85 | 14599 | 21-Aug-19 A | 22-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.06.03 TPC DAM Production
S147500 | TPC DAM Felix 2.0 Bandwidth test in 1008 | PROF4 PO E.PROF4 PO E | 320 | 48539 | 15-Mar-21 A | 2021-08-31 | 40% | 192 |  |  | 29123.4 | 29123.4 | 0
S147500 | TPC DAM Felix 2.0 Bandwidth test in 1008 | SCI3 PO.SCI3 PO | 67 | 11877 | 15-Mar-21 A | 2021-08-31 | 40% | 40.2 |  |  | 7126.2 | 7126.2 | 0
1.02.07 TPC Support Systems
1.02.07.01 TPC Laser System
S148800 | TPC Laser System Safety Review | PROF4 PO M.PROF4 PO M | 4 | 572 | 22-Mar-21 A | 2021-07-22 | 20% | 3.2 |  |  | 457.6 | 457.6 | 0
S148800 | TPC Laser System Safety Review | SCI3 PO.SCI3 PO | 4 | 668 | 22-Mar-21 A | 2021-07-22 | 20% | 3.2 |  |  | 534.4 | 534.4 | 0
S148900 | Procurement Readiness Review - TPC Laser System | PROF4 PO M.PROF4 PO M | 4 | 572 | 22-Mar-21 A | 2021-07-30 | 50% | 2 |  |  | 286 | 286 | 0
S148900 | Procurement Readiness Review - TPC Laser System | SCI3 PO.SCI3 PO | 4 | 668 | 22-Mar-21 A | 2021-07-30 | 50% | 2 |  |  | 334 | 334 | 0
S150600 | Install & Test TPC lasers | TECH3 PO M.TECH3 PO M | 24 | 2739 | 2021-08-17 | 2021-08-19 | 0% | 24 |  |  | 2739 | 2739 | 0
S150700 | Install &Test TPC Laser safety interlocks Labor | SCI3 PO.SCI3 PO | 64 | 11015 | 2021-08-20 | 2021-08-31 | 0% | 64 |  |  | 11015 | 11015 | 0
S150700 | Install &Test TPC Laser safety interlocks Labor | PROF4 PO M.PROF4 PO M | 64 | 9425 | 2021-08-20 | 2021-08-31 | 0% | 64 |  |  | 9425 | 9425 | 0
S150900 | Install &Test TPC Laser optics with mounts | TECH3 PO M.TECH3 PO M | 64 | 7304 | 2021-08-20 | 2021-08-31 | 0% | 64 |  |  | 7304 | 7304 | 0
S151000 | Install &Test TPC mirror bundles and supports | TECH3 PO M.TECH3 PO M | 24 | 2739 | 2021-09-01 | 2021-09-03 | 0% | 24 |  |  | 2739 | 2739 | 0
S148701 | Final Design Review - TPC Laser System | PROF4 PO M.PROF4 PO M | 4 | 572 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S148701 | Final Design Review - TPC Laser System | SCI3 PO.SCI3 PO | 4 | 668 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.07.02 TPC Gas System
S151300 | TPC Gas System Safety Review | PROF4 PO M.PROF4 PO M | 4 | 589 | 15-Jun-21 A | 18-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S151300 | TPC Gas System Safety Review | SCI3 PO.SCI3 PO | 4 | 688 | 15-Jun-21 A | 18-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S151400 | Procurement Readiness Review - TPC Gas System | PROF4 PO M.PROF4 PO M | 4 | 589 | 22-Jun-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S151400 | Procurement Readiness Review - TPC Gas System | SCI3 PO.SCI3 PO | 4 | 688 | 22-Jun-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S151500 | Procure TPC Gas System mass flow meters Labor | PROF4 PO M.PROF4 PO M | 24 | 3534 | 13-Apr-20 A | 29-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S151700 | Procure TPC Gas System Analyzers (2 for redundancy) - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 24 | 3534 | 13-Apr-20 A | 17-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S152400 | Procure TPC Gas System scrubbers Labor | PROF4 PO M.PROF4 PO M | 24 | 3534 | 13-Apr-20 A | 29-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S152600 | Procure TPC Gas System oxygen and water sensors Labor | PROF4 PO M.PROF4 PO M | 24 | 3534 | 13-Apr-20 A | 29-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S153100 | Procure TPC Gas System Components for Installation - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 24 | 3534 | 11-Mar-21 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S153100 | Procure TPC Gas System Components for Installation - Provide Requirements to Procurement | TECH3 PO M.TECH3 PO M | 40 | 4565 | 11-Mar-21 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S153900 | Install and Test TPC Gas System Interlocks | PROF4 PO M.PROF4 PO M | 40 | 6067 | 2021-12-01 | 2021-12-07 | 0% | 40 |  |  | 6067 | 6067 | 0
S153800 | Assemble and Plumb TPC Gas System | TECH3 PO M.TECH3 PO M | 440 | 51720 | 16-Mar-21 A | 2021-11-30 | 30% | 308 |  |  | 36204 | 36204 | 0
S151201 | Final Design Review - TPC Gas Handling System | PROF4 PO M.PROF4 PO M | 4 | 589 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S151201 | Final Design Review - TPC Gas Handling System | SCI3 PO.SCI3 PO | 4 | 688 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.07.03 TPC Cooling System
S154200 | TPC Cooling System Safety Review | PROF4 PO M.PROF4 PO M | 4 | 589 | 15-Oct-20 A | 15-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S154200 | TPC Cooling System Safety Review | SCI3 PO.SCI3 PO | 4 | 688 | 15-Oct-20 A | 15-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S154300 | Procurement Readiness Review - TPC Cooling System | PROF4 PO M.PROF4 PO M | 4 | 589 | 23-Oct-20 A | 23-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S154300 | Procurement Readiness Review - TPC Cooling System | SCI3 PO.SCI3 PO | 4 | 688 | 23-Oct-20 A | 23-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S154400 | Procure TPC Cooling System equipment (pumps, heat exchanger, PH control, manifolds, tanks…) - Provide Requirements to Pr | TECH3 PO M.TECH3 PO M | 48 | 5478 | 17-Nov-20 A | 02-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S154400 | Procure TPC Cooling System equipment (pumps, heat exchanger, PH control, manifolds, tanks…) - Provide Requirements to Pr | PROF4 PO M.PROF4 PO M | 48 | 7069 | 17-Nov-20 A | 02-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S155100 | Install TPC Cooling System pumps | TECH3 PO M.TECH3 PO M | 24 | 2739 | 2021-07-01 | 2021-07-06 | 0% | 24 |  |  | 2739 | 2739 | 0
S155200 | Install TPC Cooling System heat exchanger | TECH3 PO M.TECH3 PO M | 24 | 2739 | 2021-07-07 | 2021-07-09 | 0% | 24 |  |  | 2739 | 2739 | 0
S155300 | Install TPC Cooling System PH control | TECH3 PO M.TECH3 PO M | 24 | 2739 | 2021-07-12 | 2021-07-14 | 0% | 24 |  |  | 2739 | 2739 | 0
S155400 | Install TPC Cooling System end cap manifolds | TECH3 PO M.TECH3 PO M | 80 | 9130 | 2021-07-15 | 2021-07-28 | 0% | 80 |  |  | 9130 | 9130 | 0
S155500 | Install TPC Cooling System tanks | TECH3 PO M.TECH3 PO M | 24 | 2739 | 2021-07-29 | 2021-08-02 | 0% | 24 |  |  | 2739 | 2739 | 0
S155600 | Install TPC Cooling System plumbing Labor | TECH3 PO M.TECH3 PO M | 240 | 27453 | 2021-08-03 | 2021-09-14 | 0% | 240 |  |  | 27453 | 27453 | 0
S155800 | Set up TPC Cooling System computer controls Labor | TECH3 PO M.TECH3 PO M | 40 | 4702 | 2021-10-14 | 2021-10-20 | 0% | 40 |  |  | 4702 | 4702 | 0
S156000 | Set up and Test TPC Cooling System & Interlocks | TECH3 PO M.TECH3 PO M | 40 | 4702 | 2021-10-21 | 2021-10-27 | 0% | 40 |  |  | 4702 | 4702 | 0
S154101 | Final Design Review - TPC Cooling System | PROF4 PO M.PROF4 PO M | 4 | 589 | 28-Aug-20 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S154101 | Final Design Review - TPC Cooling System | SCI3 PO.SCI3 PO | 4 | 688 | 28-Aug-20 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.03 EMCal
S156200 | Actuals - Labor - sPHENIX EMCal FY17 | Actual Labor.Actual Labor | 980 | 163723 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S156300 | Actuals - Labor - sPHENIX EMCal FY18 | Actual Labor.Actual Labor | 2869 | 479465 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S156310 | Actuals - Labor - sPHENIX EMCal FY19M8 | Actual Labor.Actual Labor | 2337 | 390503 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02 EMCAL Module Fabrication and Sector Assembly
1.03.02.01 Set up Module Fabrication, Sector Assembly and Test area
S180202 | Set up EMCAL Final module production and sector assembly areas Labor Split_75% | SCI3 PO.SCI3 PO | 14 | 2339 | 03-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S180202 | Set up EMCAL Final module production and sector assembly areas Labor Split_75% | TECH3 PO M.TECH3 PO M | 17 | 1884 | 03-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02.02 EMCAL Module Fabrication
1.03.02.02.02 EMCAL Preprod Sector 0, 1-12 Module Fabrication
S185700 | Receive, unpack, log & inspect blocks for Prepro Sectors 1-12 Labor | PROF4 PO E.PROF4 PO E | 218 | 32104 | 21-Oct-19 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S185700 | Receive, unpack, log & inspect blocks for Prepro Sectors 1-12 Labor | TECH3 PO M.TECH3 PO M | 314 | 35834 | 21-Oct-19 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S185900 | Install reflectors on blocks for modules for Prepro Sectors 1-12 Labor | PROF4 PO E.PROF4 PO E | 218 | 32104 | 21-Oct-19 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S185900 | Install reflectors on blocks for modules for Prepro Sectors 1-12 Labor | TECH3 PO M.TECH3 PO M | 339 | 38687 | 21-Oct-19 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S186100 | Install SiPM daughterboards on blocks for modules in Sectors (Prepro) 1-12 Labor | PROF4 PO E.PROF4 PO E | 218 | 32104 | 25-Feb-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S186100 | Install SiPM daughterboards on blocks for modules in Sectors (Prepro) 1-12 Labor | TECH3 PO M.TECH3 PO M | 339 | 38687 | 25-Feb-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S186200 | Glue blocks together into modules for modules in Sectors (Prepro) 1-12 Labor | PROF4 PO E.PROF4 PO E | 218 | 32104 | 25-Feb-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S186200 | Glue blocks together into modules for modules in Sectors (Prepro) 1-12 Labor | TECH3 PO M.TECH3 PO M | 339 | 38687 | 25-Feb-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S184900 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Provide Requirements to Procurement | PROF3 PO M.PROF3 PO M | 40 | 4913 | 01-Aug-19 A | 07-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S186000 | Install light guides on preproduction prototype blocks Labor | PROF4 PO E.PROF4 PO E | 218 | 32104 | 09-Jan-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S186000 | Install light guides on preproduction prototype blocks Labor | TECH3 PO M.TECH3 PO M | 339 | 38687 | 09-Jan-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S183801 | Final Design Review, Production Readiness Review - EMCal Modules for Sectors 1-12 | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 8 | 0 | 01-Aug-19 A | 01-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S183801 | Final Design Review, Production Readiness Review - EMCal Modules for Sectors 1-12 | PROF3 PO M.PROF3 PO M | 8 | 983 | 01-Aug-19 A | 01-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S183801 | Final Design Review, Production Readiness Review - EMCal Modules for Sectors 1-12 | SCI4 PO.SCI 4 PO | 8 | 1599 | 01-Aug-19 A | 01-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02.02.03 EMCAL Final Module Fabrication
S186300 | Revise module production procedure based on module production for Prepro Sectors 1-12 | PROF4 PO M.PROF4 PO M | 144 | 21206 | 24-Mar-20 A | 30-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S186400 | Production Readiness Review - EMCal Modules for Sectors 13-64 | PROF4 PO E.PROF4 PO E | 80 | 11781 | 27-Jul-20 A | 29-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S186400 | Production Readiness Review - EMCal Modules for Sectors 13-64 | SCI3 PO PM.SCI3 PO PM | 120 | 20653 | 27-Jul-20 A | 29-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S186400 | Production Readiness Review - EMCal Modules for Sectors 13-64 | SCI4 PO.SCI 4 PO | 160 | 32945 | 27-Jul-20 A | 29-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S186500 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 56 | 6391 | 14-Apr-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S187500 | Receive, unpack, log & inspect final blocks | PROF4 PO E.PROF4 PO E | 462 | 69911 | 23-Nov-20 A | 2022-01-31 | 58% | 194.04 |  |  | 29362.62 | 29362.62 | 0
S187500 | Receive, unpack, log & inspect final blocks | TECH3 PO M.TECH3 PO M | 922 | 108120 | 23-Nov-20 A | 2022-01-31 | 58% | 387.24 |  |  | 45410.4 | 45410.4 | 0
S187600 | Install light guides on final blocks Labor | PROF4 PO E.PROF4 PO E | 462 | 69926 | 21-Jan-21 A | 2022-01-31 | 35% | 300.3 |  |  | 45451.9 | 45451.9 | 0
S187600 | Install light guides on final blocks Labor | TECH3 PO M.TECH3 PO M | 922 | 108143 | 21-Jan-21 A | 2022-01-31 | 35% | 599.3 |  |  | 70292.95 | 70292.95 | 0
S187800 | Install reflectors on final blocks Labor | PROF4 PO E.PROF4 PO E | 462 | 69957 | 23-Nov-20 A | 2022-01-31 | 38% | 286.44 |  |  | 43373.34 | 43373.34 | 0
S187800 | Install reflectors on final blocks Labor | TECH3 PO M.TECH3 PO M | 922 | 108191 | 23-Nov-20 A | 2022-01-31 | 38% | 571.64 |  |  | 67078.42 | 67078.42 | 0
S188000 | Install SiPMs daughterboards on final blocks Labor | PROF4 PO E.PROF4 PO E | 462 | 70018 | 22-Jan-21 A | 2022-02-03 | 35% | 300.3 |  |  | 45511.7 | 45511.7 | 0
S188000 | Install SiPMs daughterboards on final blocks Labor | TECH3 PO M.TECH3 PO M | 922 | 108286 | 22-Jan-21 A | 2022-02-03 | 35% | 599.3 |  |  | 70385.9 | 70385.9 | 0
S188200 | Glue final blocks together into modules | PROF4 PO E.PROF4 PO E | 462 | 70049 | 22-Jan-21 A | 2022-02-03 | 33% | 309.54 |  |  | 46932.83 | 46932.83 | 0
S188200 | Glue final blocks together into modules | TECH3 PO M.TECH3 PO M | 922 | 108333 | 22-Jan-21 A | 2022-02-03 | 33% | 617.74 |  |  | 72583.11 | 72583.11 | 0
1.03.02.03 EMCAL Sector Assembly
1.03.02.03.02 EMCAL Preproduction Sector Assembly and Testing
S191100 | Build mechanical stand/support for preproduction prototype Sector 0 - Labor | TECH3 PO M.TECH3 PO M | 48 | 5318 | 01-Jul-19 A | 29-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191400 | Install readout electronics on preproduction prototype Sector 0 | PROF4 PO E.PROF4 PO E | 32 | 4575 | 03-Jun-19 A | 30-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191400 | Install readout electronics on preproduction prototype Sector 0 | TECH3 PO E.TECH3 PO E | 64 | 7091 | 03-Jun-19 A | 30-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191400 | Install readout electronics on preproduction prototype Sector 0 | TECH3 PO M.TECH3 PO M | 32 | 3546 | 03-Jun-19 A | 30-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191500 | Install cables and cooling system on preproduction prototype Sector 0 | PROF4 PO E.PROF4 PO E | 32 | 4575 | 01-Jul-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191500 | Install cables and cooling system on preproduction prototype Sector 0 | PROF4 PO M.PROF4 PO M | 32 | 4575 | 01-Jul-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191500 | Install cables and cooling system on preproduction prototype Sector 0 | TECH3 PO M.TECH3 PO M | 32 | 3546 | 01-Jul-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191900 | Performance review of preproduction prototype Sector 0 | PROF4 PO E.PROF4 PO E | 160 | 23151 | 07-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191900 | Performance review of preproduction prototype Sector 0 | SCI3 PO PM.SCI3 PO PM | 120 | 20292 | 07-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191900 | Performance review of preproduction prototype Sector 0 | SCI4 PO.SCI 4 PO | 160 | 32369 | 07-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S192200 | Procure mechanical parts for Prepro Sectors 1-12 - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 24 | 2659 | 02-Aug-19 A | 08-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S192900 | Procure parts for cooling system for Prepro Sectors 1-12 - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 24 | 3431 | 02-Aug-19 A | 08-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S193600 | Build mechanical enclosure for Prepro Sectors 1-12 | TECH3 PO M.TECH3 PO M | 336 | 38345 | 13-Nov-19 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S193700 | Build mechanical stand/support for Prepro Sectors 1-12 - Labor | TECH3 PO M.TECH3 PO M | 336 | 38345 | 14-Nov-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S193800 | Build cooling system for Prepro Sectors 1-12 | TECH3 PO M.TECH3 PO M | 216 | 24650 | 03-Feb-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S193900 | Install modules in Prepro Sectors 1-12 | PROF4 PO E.PROF4 PO E | 218 | 32104 | 11-Mar-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S193900 | Install modules in Prepro Sectors 1-12 | TECH3 PO M.TECH3 PO M | 557 | 63566 | 11-Mar-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194000 | Install readout electronics on Prepro Sectors 1-12 | PROF4 PO E.PROF4 PO E | 218 | 32104 | 24-Mar-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194000 | Install readout electronics on Prepro Sectors 1-12 | TECH3 PO E.TECH3 PO E | 371 | 42339 | 24-Mar-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194000 | Install readout electronics on Prepro Sectors 1-12 | TECH3 PO M.TECH3 PO M | 186 | 21227 | 24-Mar-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194100 | Install cables and cooling system on Prepro Sectors 1-12 | PROF4 PO E.PROF4 PO E | 218 | 32104 | 25-Mar-20 A | 01-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194100 | Install cables and cooling system on Prepro Sectors 1-12 | PROF4 PO M.PROF4 PO M | 608 | 89537 | 25-Mar-20 A | 01-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194100 | Install cables and cooling system on Prepro Sectors 1-12 | TECH3 PO M.TECH3 PO M | 493 | 56262 | 25-Mar-20 A | 01-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S191600 | Revise module and sector design based on performance of Sector 0 | PROF4 PO E.PROF4 PO E | 160 | 22876 | 31-Jul-19 A | 27-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191600 | Revise module and sector design based on performance of Sector 0 | SCI4 PO.SCI 4 PO | 160 | 31986 | 31-Jul-19 A | 27-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191600 | Revise module and sector design based on performance of Sector 0 | SCI3 PO PM.SCI3 PO PM | 120 | 20051 | 31-Jul-19 A | 27-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S192100 | Final Design Review, Production Readiness Review - EMCal Sectors 1-12 | SCI3 PO.SCI3 PO | 8 | 1337 | 01-Aug-19 A | 01-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S190502 | Procure mechanical parts for preproduction prototype Sector 0 Labor FY19 Split | TECH3 PO D.TECH3 PO D | 0 | 0 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S190702 | Procure parts for cooling system for preproduction prototype Sector 0 Labor FY19 Split | PROF4 PO M.PROF4 PO M | 9 | 1287 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S194500 | Revise sector assembly procedure based on preproduction Sector 1-12 fabrication | PROF4 PO M.PROF4 PO M | 144 | 21206 | 30-Jul-20 A | 30-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S194600 | Production Readiness Review - EMCal Sectors 13-63 | PROF4 PO E.PROF4 PO E | 40 | 5891 | 30-Jul-20 A | 30-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S194600 | Production Readiness Review - EMCal Sectors 13-63 | SCI3 PO PM.SCI3 PO PM | 40 | 6884 | 30-Jul-20 A | 30-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S194600 | Production Readiness Review - EMCal Sectors 13-63 | SCI4 PO.SCI 4 PO | 80 | 16473 | 30-Jul-20 A | 30-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S194800 | Procure EMCAL Mechanical Parts for Final Sectors - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 56 | 6391 | 15-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S195500 | Procure EMCAL Cooling System for Final Sectors - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 56 | 8247 | 09-Jun-20 A | 15-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S196200 | Build mechanical enclosures for final sectors | TECH3 PO M.TECH3 PO M | 720 | 84633 | 12-Jan-21 A | 2021-07-14 | 33% | 482.4 |  |  | 56704.11 | 56704.11 | 0
S196300 | Build mechanical fixtures for final sectors | TECH3 PO M.TECH3 PO M | 720 | 84017 | 12-Jan-21 A | 2021-07-14 | 45% | 396 |  |  | 46209.35 | 46209.35 | 0
S196400 | Build cooling system for final sectors | PROF4 PO M.PROF4 PO M | 180 | 27303 | 12-Jan-21 A | 2021-07-14 | 33% | 120.6 |  |  | 18293.01 | 18293.01 | 0
S196500 | Install modules in final sectors | PROF4 PO E.PROF4 PO E | 462 | 70145 | 26-Jan-21 A | 2022-02-03 | 33% | 309.54 |  |  | 46997.15 | 46997.15 | 0
S196500 | Install modules in final sectors | TECH3 PO M.TECH3 PO M | 1383 | 162722 | 26-Jan-21 A | 2022-02-03 | 33% | 926.61 |  |  | 109023.74 | 109023.74 | 0
S196700 | Install readout electronics on final sectors | TECH3 PO M.TECH3 PO M | 1383 | 162798 | 22-Feb-21 A | 2022-02-04 | 31% | 954.27 |  |  | 112330.62 | 112330.62 | 0
S196700 | Install readout electronics on final sectors | PROF4 PO E.PROF4 PO E | 462 | 70178 | 22-Feb-21 A | 2022-02-04 | 31% | 318.78 |  |  | 48422.82 | 48422.82 | 0
S196800 | Install cables & cooling system on final sectors | PROF4 PO E.PROF4 PO E | 462 | 70198 | 22-Feb-21 A | 2022-02-04 | 31% | 318.78 |  |  | 48436.62 | 48436.62 | 0
S196800 | Install cables & cooling system on final sectors | PROF4 PO M.PROF4 PO M | 1728 | 262557 | 22-Feb-21 A | 2022-02-04 | 31% | 1192.32 |  |  | 181164.33 | 181164.33 | 0
S196800 | Install cables & cooling system on final sectors | TECH3 PO M.TECH3 PO M | 1383 | 162845 | 22-Feb-21 A | 2022-02-04 | 31% | 954.27 |  |  | 112363.05 | 112363.05 | 0
1.04 HCal
S197400 | Actuals - Labor - sPHENIX HCal FY17 | Actual Labor.Actual Labor | 1557 | 260083 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S197500 | Actuals - Labor - sPHENIX HCal FY18 | Actual Labor.Actual Labor | 3467 | 579301 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S197510 | Actuals - Labor - sPHENIX HCal FY19M8 | Actual Labor.Actual Labor | 1571 | 262446 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.02 Outer HCAL Sector Mechanical Structure
S204500 | Procure Outer HCAL Splice Plates - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 36 | 5147 | 04-Feb-20 A | 10-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S204500 | Procure Outer HCAL Splice Plates - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 36 | 3989 | 04-Feb-20 A | 10-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S205200 | Design Revision of Outer HCAL Lifting Fixture and Supports | PROF4 PO M.PROF4 PO M | 16 | 2288 | 24-Jul-19 A | 17-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205200 | Design Revision of Outer HCAL Lifting Fixture and Supports | SCI3 PO.SCI3 PO | 16 | 2673 | 24-Jul-19 A | 17-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205200 | Design Revision of Outer HCAL Lifting Fixture and Supports | TECH3 PO M.TECH3 PO M | 40 | 4432 | 24-Jul-19 A | 17-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205300 | Final Design Review, Procurement Readiness Review - Outer HCAL Lifting Fixture and Supports | PROF4 PO M.PROF4 PO M | 8 | 1144 | 02-Oct-19 A | 02-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205300 | Final Design Review, Procurement Readiness Review - Outer HCAL Lifting Fixture and Supports | SCI3 PO.SCI3 PO | 8 | 1337 | 02-Oct-19 A | 02-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205300 | Final Design Review, Procurement Readiness Review - Outer HCAL Lifting Fixture and Supports | TECH3 PO M.TECH3 PO M | 8 | 886 | 02-Oct-19 A | 02-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205400 | Address Issues from Internal Review of Outer HCAL Lifting Fixture and Supports | PROF4 PO M.PROF4 PO M | 8 | 1144 | 03-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205400 | Address Issues from Internal Review of Outer HCAL Lifting Fixture and Supports | SCI3 PO.SCI3 PO | 8 | 1337 | 03-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205400 | Address Issues from Internal Review of Outer HCAL Lifting Fixture and Supports | TECH3 PO M.TECH3 PO M | 20 | 2216 | 03-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205600 | Procure Outer HCAL Lifting Fixtures & Supports - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 72 | 10294 | 01-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205600 | Procure Outer HCAL Lifting Fixtures & Supports - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 36 | 6015 | 01-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205600 | Procure Outer HCAL Lifting Fixtures & Supports - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 72 | 7977 | 01-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S204450 | Procurement Readiness Review - Outer HCAL Splice Plates (Dog bones) | PROF4 PO M.PROF4 PO M | 4 | 572 | 03-Feb-20 A | 03-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S204450 | Procurement Readiness Review - Outer HCAL Splice Plates (Dog bones) | PROF3 PO M.PROF3 PO M | 8 | 983 | 03-Feb-20 A | 03-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S204450 | Procurement Readiness Review - Outer HCAL Splice Plates (Dog bones) | SCI4 PO.SCI 4 PO | 4 | 800 | 03-Feb-20 A | 03-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S204401 | Final Design Review - Outer HCAL Splice Plates (Dog bones) | PROF3 PO M.PROF3 PO M | 8 | 983 | 17-Sep-19 A | 18-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S204401 | Final Design Review - Outer HCAL Splice Plates (Dog bones) | PROF4 PO M.PROF4 PO M | 4 | 572 | 17-Sep-19 A | 18-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S204401 | Final Design Review - Outer HCAL Splice Plates (Dog bones) | SCI4 PO.SCI 4 PO | 4 | 800 | 17-Sep-19 A | 18-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205201 | Preliminary Design Review - Outer HCAL Lifting Fixture and Supports | PROF4 PO M.PROF4 PO M | 4 | 572 | 01-Oct-19 A | 01-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205201 | Preliminary Design Review - Outer HCAL Lifting Fixture and Supports | SCI3 PO.SCI3 PO | 4 | 668 | 01-Oct-19 A | 01-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S205201 | Preliminary Design Review - Outer HCAL Lifting Fixture and Supports | TECH3 PO M.TECH3 PO M | 4 | 443 | 01-Oct-19 A | 01-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.01 Inner HCAL Support Structure & Support Rings
S197900 | Final Design Review. Procurement Readiness Review - Inner HCAL Support Structure | PROF4 PO M.PROF4 PO M | 16 | 2288 | 24-Mar-20 A | 24-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S197900 | Final Design Review. Procurement Readiness Review - Inner HCAL Support Structure | SCI3 PO.SCI3 PO | 16 | 2673 | 24-Mar-20 A | 24-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S197900 | Final Design Review. Procurement Readiness Review - Inner HCAL Support Structure | TECH3 PO D.TECH3 PO D | 16 | 1773 | 24-Mar-20 A | 24-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198000 | Address Issues from Internal Review Support Structure | PROF4 PO M.PROF4 PO M | 8 | 1144 | 25-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198000 | Address Issues from Internal Review Support Structure | SCI3 PO.SCI3 PO | 8 | 1337 | 25-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198000 | Address Issues from Internal Review Support Structure | TECH3 PO D.TECH3 PO D | 20 | 2216 | 25-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198200 | Manufacture Inner HCAL Support Structure - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 14 | 2339 | 13-May-20 A | 26-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198200 | Manufacture Inner HCAL Support Structure - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 20 | 2860 | 13-May-20 A | 26-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198200 | Manufacture Inner HCAL Support Structure - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 40 | 4432 | 13-May-20 A | 26-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198800 | Manufacture Inner HCAL Support Structure - Prepare & Send Solicitation | PROF4 PO M.PROF4 PO M | 28 | 4003 | 01-Jul-20 A | 18-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198800 | Manufacture Inner HCAL Support Structure - Prepare & Send Solicitation | SCI3 PO.SCI3 PO | 7 | 1170 | 01-Jul-20 A | 18-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198800 | Manufacture Inner HCAL Support Structure - Prepare & Send Solicitation | TECH3 PO D.TECH3 PO D | 40 | 4432 | 01-Jul-20 A | 18-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198800 | Manufacture Inner HCAL Support Structure - Prepare & Send Solicitation | TECH3 PO M.TECH3 PO M | 8 | 886 | 01-Jul-20 A | 18-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S199000 | Manufacture Inner HCAL Support Structure - Vendor Selection | TECH3 PO M.TECH3 PO M | 40 | 4565 | 24-Dec-20 A | 28-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S199000 | Manufacture Inner HCAL Support Structure - Vendor Selection | TECH3 PO D.TECH3 PO D | 40 | 4565 | 24-Dec-20 A | 28-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S199000 | Manufacture Inner HCAL Support Structure - Vendor Selection | SCI3 PO.SCI3 PO | 7 | 1205 | 24-Dec-20 A | 28-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S199000 | Manufacture Inner HCAL Support Structure - Vendor Selection | PROF4 PO M.PROF4 PO M | 40 | 5891 | 24-Dec-20 A | 28-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198500 | Final Design Review. Procurement Readiness Review - Inner HCAL Support Rings | PROF4 PO M.PROF4 PO M | 16 | 2356 | 24-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198500 | Final Design Review. Procurement Readiness Review - Inner HCAL Support Rings | SCI3 PO.SCI3 PO | 16 | 2754 | 24-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198500 | Final Design Review. Procurement Readiness Review - Inner HCAL Support Rings | TECH3 PO D.TECH3 PO D | 16 | 1826 | 24-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198600 | Address Issues from Internal Review of Inner HCAL Support Rings | PROF4 PO M.PROF4 PO M | 8 | 1178 | 20-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198600 | Address Issues from Internal Review of Inner HCAL Support Rings | SCI3 PO.SCI3 PO | 8 | 1377 | 20-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198600 | Address Issues from Internal Review of Inner HCAL Support Rings | TECH3 PO D.TECH3 PO D | 20 | 2282 | 20-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S199400 | Manufacture Inner HCAL Support Rings - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 28 | 4819 | 01-Jul-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S199400 | Manufacture Inner HCAL Support Rings - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 88 | 12959 | 01-Jul-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S199400 | Manufacture Inner HCAL Support Rings - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 88 | 10043 | 01-Jul-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S199400 | Manufacture Inner HCAL Support Rings - Provide Requirements to Procurement | TECH3 PO M.TECH3 PO M | 80 | 9130 | 01-Jul-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198402 | Design Inner HCAL Support Rings FY20 Split | PROF4 PO M.PROF4 PO M | 21 | 3093 | 01-Oct-19 A | 18-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S198402 | Design Inner HCAL Support Rings FY20 Split | TECH3 PO D.TECH3 PO D | 51 | 5820 | 01-Oct-19 A | 18-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.04 Outer HCAL Sector Assembly and Testing
1.04.04.01 Outer HCAL Sector Assembly and Testing - Preproduction
S203600 | Outer HCAL Sector Transportation to Storage Area (Preproduction) | TECH3 PO M.TECH3 PO M | 12 | 1369 | 23-Nov-20 A | 22-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S203600 | Outer HCAL Sector Transportation to Storage Area (Preproduction) | CRAFT3.CRAFT3 | 48 | 6003 | 23-Nov-20 A | 22-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.04.02 Outer HCAL Sector Assembly and Testing - Production
S210300 | Outer HCAL Sector Transportation to Temp Storage | TECH3 PO M.TECH3 PO M | 104 | 12225 | 11-Jan-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210300 | Outer HCAL Sector Transportation to Temp Storage | CRAFT3.CRAFT3 | 208 | 26795 | 11-Jan-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S209701 | Production Readiness Review - OHCal Sector Assembly 7-32 | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 8 | 0 | 25-Aug-20 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209701 | Production Readiness Review - OHCal Sector Assembly 7-32 | SCI4 PO.SCI 4 PO | 4 | 848 | 25-Aug-20 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209701 | Production Readiness Review - OHCal Sector Assembly 7-32 | PROF3 PO M.PROF3 PO M | 4 | 521 | 25-Aug-20 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.05 Calorimeter Electronics
S211200 | Actuals - Labor - sPHENIX Calorimeter Electronics FY17 | Actual Labor.Actual Labor | 1634 | 273082 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S211300 | Actuals - Labor - sPHENIX Calorimeter Electronics FY18 | Actual Labor.Actual Labor | 3554 | 593810 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1000839 | Actuals - Labor - sPHENIX Calorimeter Electronics FY19 M8 | Actual Labor.Actual Labor | 2520 | 421099 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02 Calorimeter Front End Electronics
1.05.02.01 EMCal Electronics: Preproduction
S220200 | Layout per Change Specification - EMCal Preamp: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 46 | 5650 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220200 | Layout per Change Specification - EMCal Preamp: Sectors 1-12 | TECH3 PO E.TECH3 PO E | 32 | 3546 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220400 | Layout per Change Specification - EMCal Interface: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 54 | 6633 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220400 | Layout per Change Specification - EMCal Interface: Sectors 1-12 | TECH3 PO E.TECH3 PO E | 60 | 6648 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220600 | Layout per Change Specification - Calorimeter Controller: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 24 | 2948 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220600 | Layout per Change Specification - Calorimeter Controller: Sectors 1-12 | TECH3 PO E.TECH3 PO E | 40 | 4432 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220900 | Safety and Final Design Review to ensure Change Specifications have been met: EMCal Sectors 1-12 | PROF3 PO E.PROF3 PO E | 20 | 2456 | 11-Sep-19 A | 24-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220900 | Safety and Final Design Review to ensure Change Specifications have been met: EMCal Sectors 1-12 | SCI3 PO.SCI3 PO | 20 | 3342 | 11-Sep-19 A | 24-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220900 | Safety and Final Design Review to ensure Change Specifications have been met: EMCal Sectors 1-12 | TECH3 PO E.TECH3 PO E | 8 | 886 | 11-Sep-19 A | 24-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S221100 | Review Safety and Design Review Report and Procurement Readiness Review Sectors 1-12 | PROF3 PO E.PROF3 PO E | 20 | 2456 | 11-Sep-19 A | 24-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S221100 | Review Safety and Design Review Report and Procurement Readiness Review Sectors 1-12 | SCI3 PO.SCI3 PO | 20 | 3342 | 11-Sep-19 A | 24-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S222400 | Fabricate EMCal Interface Board: Sectors 1-12 - Provide Requirements to Fabricator | PROF3 PO E.PROF3 PO E | 86 | 10880 | 01-Oct-19 A | 07-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S222400 | Fabricate EMCal Interface Board: Sectors 1-12 - Provide Requirements to Fabricator | TECH3 PO E.TECH3 PO E | 64 | 7304 | 01-Oct-19 A | 07-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S224500 | Test Pulse Boards 1-12 - Labor | PROF3 PO E.PROF3 PO E | 23 | 2910 | 01-Apr-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S224500 | Test Pulse Boards 1-12 - Labor | TECH3 PO E.TECH3 PO E | 32 | 3652 | 01-Apr-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S224500 | Test Pulse Boards 1-12 - Labor | TECH3 PO D.TECH3 PO D | 23 | 2625 | 01-Apr-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S226500 | Review and Write EMCal Electronics Design Change Specifications: Final Production | PROF3 PO E.PROF3 PO E | 20 | 2530 | 25-Nov-19 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S226500 | Review and Write EMCal Electronics Design Change Specifications: Final Production | SCI3 PO.SCI3 PO | 20 | 3442 | 25-Nov-19 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S219700 | Review and Write EMCal Electronics Design Change Specifications: Sector 1-12 Labor | PROF3 PO E.PROF3 PO E | 20 | 2456 | 15-Aug-19 A | 31-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S219700 | Review and Write EMCal Electronics Design Change Specifications: Sector 1-12 Labor | SCI3 PO.SCI3 PO | 20 | 3342 | 15-Aug-19 A | 31-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220100 | Update Design per Change Specification - EMCal Preamp: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 70 | 8598 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220300 | Update Design per Change Specification - EMCal Interface Board: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 70 | 8598 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220500 | Update Design per Change Specification - Calorimeter Controller: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 70 | 8598 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220700 | Specify Signal and Power Cables per Change Specification - for EMCal: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 60 | 7369 | 12-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220700 | Specify Signal and Power Cables per Change Specification - for EMCal: Sectors 1-12 | SCI3 PO.SCI3 PO | 60 | 10026 | 12-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220800 | Specify Power System per Change Specification - for EMCal: Sectors 1-12 | SCI3 PO.SCI3 PO | 60 | 10026 | 12-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S220800 | Specify Power System per Change Specification - for EMCal: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 60 | 7369 | 12-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S221600 | Fabricate EMCal Preamp Boards: Sectors 1-12 - Provide Requirements to Fabricator | TECH3 PO E.TECH3 PO E | 60 | 6847 | 01-Oct-19 A | 22-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S221600 | Fabricate EMCal Preamp Boards: Sectors 1-12 - Provide Requirements to Fabricator | PROF3 PO M.PROF3 PO M | 84 | 10627 | 01-Oct-19 A | 22-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223600 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12 - Labor | PROF3 PO E.PROF3 PO E | 23 | 2910 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223600 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12 - Labor | TECH3 PO E.TECH3 PO E | 32 | 3652 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223600 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12 - Labor | TECH3 PO D.TECH3 PO D | 23 | 2625 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223800 | Procure EMCal External LV/Bias Cables: Sectors 1-12 - Labor | PROF3 PO E.PROF3 PO E | 23 | 2910 | 01-Nov-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223800 | Procure EMCal External LV/Bias Cables: Sectors 1-12 - Labor | TECH3 PO E.TECH3 PO E | 32 | 3652 | 01-Nov-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223800 | Procure EMCal External LV/Bias Cables: Sectors 1-12 - Labor | TECH3 PO D.TECH3 PO D | 23 | 2625 | 01-Nov-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S224100 | Assemble EMCal External Power Cables: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 23 | 2910 | 15-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S224100 | Assemble EMCal External Power Cables: Sectors 1-12 | TECH3 PO E.TECH3 PO E | 32 | 3652 | 15-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S224100 | Assemble EMCal External Power Cables: Sectors 1-12 | TECH3 PO D.TECH3 PO D | 23 | 2625 | 15-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S225500 | Procure EMCal External Bias Power System: Sectors 1-12 - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 23 | 2910 | 02-Jan-20 A | 15-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S225500 | Procure EMCal External Bias Power System: Sectors 1-12 - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 32 | 3652 | 02-Jan-20 A | 15-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S225500 | Procure EMCal External Bias Power System: Sectors 1-12 - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 23 | 2625 | 02-Jan-20 A | 15-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S224200 | Procure EMCal Low Voltage Power Systems: Sectors 1-12 - Labor | PROF3 PO E.PROF3 PO E | 23 | 2910 | 01-Oct-19 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S224200 | Procure EMCal Low Voltage Power Systems: Sectors 1-12 - Labor | TECH3 PO E.TECH3 PO E | 32 | 3652 | 01-Oct-19 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S224200 | Procure EMCal Low Voltage Power Systems: Sectors 1-12 - Labor | TECH3 PO D.TECH3 PO D | 23 | 2625 | 01-Oct-19 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S219210 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Preproduction [Sector 0] Labor Split | PROF3 PO E.PROF3 PO E | 7 | 860 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S219210 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Preproduction [Sector 0] Labor Split | TECH3 PO D.TECH3 PO D | 7 | 776 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S219210 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Preproduction [Sector 0] Labor Split | TECH3 PO E.TECH3 PO E | 10 | 1108 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S219402 | Procure EMCal External Signal and Power Cables, and Power Systems: Preproduction [Sector 0] Labor Split | TECH3 PO D.TECH3 PO D | 10 | 1108 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S219402 | Procure EMCal External Signal and Power Cables, and Power Systems: Preproduction [Sector 0] Labor Split | TECH3 PO E.TECH3 PO E | 14 | 1551 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S219402 | Procure EMCal External Signal and Power Cables, and Power Systems: Preproduction [Sector 0] Labor Split | PROF3 PO E.PROF3 PO E | 10 | 1228 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223202 | Fabricate Calorimeter Controller Boards: Sectors 1-12 Labor Split | TECH3 PO E.TECH3 PO E | 50 | 5706 | 01-Jul-19 A | 15-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223202 | Fabricate Calorimeter Controller Boards: Sectors 1-12 Labor Split | PROF3 PO E.PROF3 PO E | 110 | 13916 | 01-Jul-19 A | 15-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02.02 EMCal Electronics: Production
S226700 | Production Readiness and Safety Review: EMCal Production Electronics | PROF3 PO E.PROF3 PO E | 24 | 3036 | 31-Mar-20 A | 22-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S226700 | Production Readiness and Safety Review: EMCal Production Electronics | SCI3 PO.SCI3 PO | 24 | 4131 | 31-Mar-20 A | 22-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S226700 | Production Readiness and Safety Review: EMCal Production Electronics | TECH3 PO E.TECH3 PO E | 8 | 913 | 31-Mar-20 A | 22-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S226900 | Respond to Results of EMCal Production Readiness and Safety Review | PROF3 PO E.PROF3 PO E | 16 | 2024 | 29-May-20 A | 08-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S226900 | Respond to Results of EMCal Production Readiness and Safety Review | SCI3 PO.SCI3 PO | 16 | 2754 | 29-May-20 A | 08-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S228700 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Provide Requirements to Procure & Assem | PROF3 PO E.PROF3 PO E | 36 | 4554 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S228700 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Provide Requirements to Procure & Assem | TECH3 PO E.TECH3 PO E | 36 | 4108 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S228700 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Provide Requirements to Procure & Assem | PROF4 PO E.PROF4 PO E | 24 | 3534 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S229500 | Fabricate EMCAL Interface Board Sectors 13-64 - Provide Requirements to Fabricator | PROF3 PO E.PROF3 PO E | 36 | 4554 | 02-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S229500 | Fabricate EMCAL Interface Board Sectors 13-64 - Provide Requirements to Fabricator | TECH3 PO E.TECH3 PO E | 36 | 4108 | 02-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S229500 | Fabricate EMCAL Interface Board Sectors 13-64 - Provide Requirements to Fabricator | PROF4 PO E.PROF4 PO E | 24 | 3534 | 02-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S231200 | Procure Internal EMCal Signal/Test/Comm and LV/Bias Cables: Production - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 32 | 4048 | 11-Mar-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S231200 | Procure Internal EMCal Signal/Test/Comm and LV/Bias Cables: Production - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 16 | 1826 | 11-Mar-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S231200 | Procure Internal EMCal Signal/Test/Comm and LV/Bias Cables: Production - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 32 | 3652 | 11-Mar-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S231900 | Fabricate Test-pulse Boards 13 - 64 - Labor | PROF3 PO E.PROF3 PO E | 32 | 4048 | 12-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S231900 | Fabricate Test-pulse Boards 13 - 64 - Labor | SCI3 PO.SCI3 PO | 32 | 5507 | 12-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S231900 | Fabricate Test-pulse Boards 13 - 64 - Labor | TECH3 PO E.TECH3 PO E | 16 | 1826 | 12-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S227000 | Fabricate SiPM Daughter Boards Sectors 13-64 - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 40 | 5060 | 18-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S227000 | Fabricate SiPM Daughter Boards Sectors 13-64 - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 24 | 4131 | 18-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S227000 | Fabricate SiPM Daughter Boards Sectors 13-64 - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 56 | 6391 | 18-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S232600 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 32 | 4048 | 22-Feb-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S232600 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 32 | 5507 | 22-Feb-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S232600 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 16 | 1826 | 22-Feb-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S233400 | Procure EMCal Bias Power System Sectors 13-64 - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 32 | 4048 | 07-Apr-20 A | 20-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S233400 | Procure EMCal Bias Power System Sectors 13-64 - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 32 | 5507 | 07-Apr-20 A | 20-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S233400 | Procure EMCal Bias Power System Sectors 13-64 - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 16 | 1826 | 07-Apr-20 A | 20-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S233300 | Assemble Power Cables | PROF3 PO E.PROF3 PO E | 32 | 4170 | 08-Dec-20 A | 29-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S233300 | Assemble Power Cables | SCI3 PO.SCI3 PO | 32 | 5673 | 08-Dec-20 A | 29-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S233300 | Assemble Power Cables | TECH3 PO E.TECH3 PO E | 16 | 1881 | 08-Dec-20 A | 29-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S229405 | Test EMCal Preamp Boards: Production Sectors 13-64 - Contributed Labor | TECH3 PO E.TECH3 PO E | 96 | 11284 | 29-Mar-21 A | 2021-07-14 | 40% | 57.6 |  |  | 6770.4 | 6770.4 | 0
S229405 | Test EMCal Preamp Boards: Production Sectors 13-64 - Contributed Labor | PROF3 PO E.PROF3 PO E | 153 | 19937 | 29-Mar-21 A | 2021-07-14 | 40% | 91.8 |  |  | 11962.2 | 11962.2 | 0
S231105 | Test Calorimeter Controller Boards: Production Sectors 13-64 - Contributed Labor | PROF3 PO E.PROF3 PO E | 92 | 11988 | 10-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S231105 | Test Calorimeter Controller Boards: Production Sectors 13-64 - Contributed Labor | TECH3 PO E.TECH3 PO E | 96 | 11284 | 10-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S230205 | Test EMCal Interface Boards: Production Sectors 13-64 - Contributed Labor | TECH3 PO E.TECH3 PO E | 96 | 11284 | 01-Dec-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S230205 | Test EMCal Interface Boards: Production Sectors 13-64 - Contributed Labor | PROF3 PO E.PROF3 PO E | 153 | 19937 | 01-Dec-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02.03 HCal Electronics: Preproduction
S236300 | Test HCal SiPM Boards: (6 Modules) | TECH3 PO E.TECH3 PO E | 16 | 1817 | 18-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S236300 | Test HCal SiPM Boards: (6 Modules) | PROF3 PO E.PROF3 PO E | 24 | 3021 | 18-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S236102 | Fabricate HCal SiPM Boards: (6 Modules) Labor Split | PROF3 PO E.PROF3 PO E | 24 | 2948 | 02-Jul-19 A | 10-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S236102 | Fabricate HCal SiPM Boards: (6 Modules) Labor Split | TECH3 PO E.TECH3 PO E | 28 | 3102 | 02-Jul-19 A | 10-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S237602 | Procure Hcal Power and Signal Cables and Power System: (6 Modules) - Labor Split | PROF3 PO E.PROF3 PO E | 39 | 4790 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S237602 | Procure Hcal Power and Signal Cables and Power System: (6 Modules) - Labor Split | TECH3 PO E.TECH3 PO E | 77 | 8531 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02.04 HCal Electronics: Production
S238200 | Production Readiness Review, Safety Review - HCal FEE Sectors 7-32 | PROF3 PO E.PROF3 PO E | 16 | 2024 | 03-Feb-20 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S238200 | Production Readiness Review, Safety Review - HCal FEE Sectors 7-32 | SCI3 PO.SCI3 PO | 16 | 2754 | 03-Feb-20 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S238200 | Production Readiness Review, Safety Review - HCal FEE Sectors 7-32 | TECH3 PO E.TECH3 PO E | 16 | 1826 | 03-Feb-20 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S238400 | Review Hcal Production Readiness & Safety Review Report | PROF3 PO E.PROF3 PO E | 10 | 1265 | 03-Feb-20 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S238400 | Review Hcal Production Readiness & Safety Review Report | SCI3 PO.SCI3 PO | 10 | 1721 | 03-Feb-20 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241900 | Fabricate HCal Backplane Boards: Production - Labor | PROF3 PO E.PROF3 PO E | 48 | 6072 | 01-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241900 | Fabricate HCal Backplane Boards: Production - Labor | TECH3 PO E.TECH3 PO E | 80 | 9130 | 01-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243100 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 48 | 6072 | 01-May-20 A | 07-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243100 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 24 | 4131 | 01-May-20 A | 07-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243100 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 80 | 9130 | 01-May-20 A | 07-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S239300 | Test HCal SiPM Boards: Production | PROF3 PO E.PROF3 PO E | 145 | 18894 | 15-Sep-20 A | 22-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S239300 | Test HCal SiPM Boards: Production | TECH3 PO E.TECH3 PO E | 48 | 5642 | 15-Sep-20 A | 22-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S238500 | Fabricate HCal SiPM Boards - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 44 | 5566 | 02-Mar-20 A | 06-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S238500 | Fabricate HCal SiPM Boards - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 88 | 10043 | 02-Mar-20 A | 06-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241100 | Fabricate HCal LED Boards - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 44 | 5566 | 01-Apr-20 A | 07-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241100 | Fabricate HCal LED Boards - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 28 | 3195 | 01-Apr-20 A | 07-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243800 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Provide Requirements to Procurements | PROF3 PO E.PROF3 PO E | 48 | 6072 | 01-Apr-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243800 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Provide Requirements to Procurements | TECH3 PO E.TECH3 PO E | 80 | 9130 | 01-Apr-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243800 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Provide Requirements to Procurements | SCI3 PO.SCI3 PO | 24 | 4131 | 01-Apr-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S239800 | Fabricate HCal Preamp Boards - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 88 | 11133 | 02-Mar-20 A | 13-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S239800 | Fabricate HCal Preamp Boards - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 136 | 15521 | 02-Mar-20 A | 13-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.03 Calorimeter Digitizer System
1.05.03.01 Calorimeter Digitizer: Preproduction Prototype
S248400 | Review and write design change specifications for calorimeter digitizer system: 7-Crate Preproduction | PROF4 PO E.PROF4 PO E | 28 | 4003 | 15-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S249400 | Final Design Review, Procurement Readiness Review, Electrical Safety Review - Calorimeter Digitizer 7-crate | PROF4 PO E.PROF4 PO E | 80 | 11438 | 15-Aug-19 A | 22-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S249600 | Review Calorimeter Digitizer Safety Review Report | PROF4 PO E.PROF4 PO E | 120 | 17157 | 22-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S248810 | Design Digitizer Clock Master: 7-Crate Preproduction Split | PROF4 PO E.PROF4 PO E | 10 | 1430 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S249310 | Layout Digitizer Clock Master: 7-Crate Preproduction Split | PROF4 PO E.PROF4 PO E | 10 | 1430 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.03.02 Calorimeter Digitizers: Production
S251400 | Production Readiness & Safety Review: Calorimeter Digitizers | PROF4 PO E.PROF4 PO E | 160 | 23562 | 01-Dec-20 A | 07-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S251600 | Review Calorimeter Electronics Readiness & Safety Review Report | PROF4 PO E.PROF4 PO E | 136 | 20028 | 08-Dec-20 A | 21-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S251700 | Procure Production Digitizer - Provide Requirements to Procurement | PROF4 PO E.PROF4 PO E | 160 | 23562 | 13-May-20 A | 27-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.06 DAQ/Trigger
S253200 | Actuals - Labor - sPHENIX DAQ&Trigger FY17 | Actual Labor.Actual Labor | 766 | 127930 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S253300 | Actuals - Labor - sPHENIX DAQ&Trigger FY18 | Actual Labor.Actual Labor | 2563 | 428318 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1000919 | Actuals - Labor - sPHENIX DAQ&Trigger FY19 M8 | Actual Labor.Actual Labor | 1639 | 273849 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.01 DAQ
1.06.01.02 DAQ Prototype
S255000 | DAQ Prototype: Review of DAQ Prototype Results and Production Readiness Review | SCI3 PO.SCI3 PO | 80 | 13768 | 07-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S255000 | DAQ Prototype: Review of DAQ Prototype Results and Production Readiness Review | PROF4 PO M.PROF4 PO M | 40 | 5891 | 07-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S255100 | Production Readiness Review - DAQ | SCI3 PO.SCI3 PO | 4 | 688 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S255100 | Production Readiness Review - DAQ | PROF3 PO E.PROF3 PO E | 4 | 506 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S255100 | Production Readiness Review - DAQ | PROF3 IO E.PROF3 IO E | 4 | 506 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S255100 | Production Readiness Review - DAQ | SCI4 PO.SCI 4 PO | 4 | 824 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S255100 | Production Readiness Review - DAQ | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 | 0 | 24-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S254600 | DAQ Prototype: Software development - INTT FELIX readout test_80% | SCI3 PO.SCI3 PO | 134 | 22390 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S254600 | DAQ Prototype: Software development - INTT FELIX readout test_80% | TECH3 PO D.TECH3 PO D | 200 | 22160 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S254700 | DAQ Prototype: Software development - INTT FELIX/DCM2 Downselect Review | SCI3 PO.SCI3 PO | 134 | 22390 | 13-Nov-19 A | 20-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S254700 | DAQ Prototype: Software development - INTT FELIX/DCM2 Downselect Review | TECH3 PO D.TECH3 PO D | 200 | 22160 | 13-Nov-19 A | 20-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S254502 | DAQ Prototype: Software development - Calorimeters & TPC FY19 Split | PROF4 PO E.PROF4 PO E | 461 | 65912 | 03-Jun-19 A | 02-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S254502 | DAQ Prototype: Software development - Calorimeters & TPC FY19 Split | SCI3 PO.SCI3 PO | 134 | 22390 | 03-Jun-19 A | 02-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.01.03 DAQ Production
S255200 | DAQ Production: Design and layout the various types of front-end boards | PROF4 PO E.PROF4 PO E | 32 | 4712 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S255200 | DAQ Production: Design and layout the various types of front-end boards | SCI3 PO.SCI3 PO | 64 | 11015 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S255300 | Procure DAQ Production Boards - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 64 | 9425 | 10-Aug-20 A | 12-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S256100 | Procure DAQ Production Crates - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 80 | 11781 | 16-Mar-21 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S256100 | Procure DAQ Production Crates - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 80 | 13768 | 16-Mar-21 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S256800 | DAQ Production: Crate installation | PROF4 PO M.PROF4 PO M | 32 | 4854 | 07-Dec-20 A | 2021-12-17 | 30% | 22.4 |  |  | 3397.8 | 3397.8 | 0
S256800 | DAQ Production: Crate installation | SCI3 PO.SCI3 PO | 32 | 5673 | 07-Dec-20 A | 2021-12-17 | 30% | 22.4 |  |  | 3971.1 | 3971.1 | 0
S256800 | DAQ Production: Crate installation | TECH3 PO M.TECH3 PO M | 512 | 60183 | 07-Dec-20 A | 2021-12-17 | 30% | 358.4 |  |  | 42128.1 | 42128.1 | 0
S256800 | DAQ Production: Crate installation | CRAFT3.CRAFT3 | 32 | 4122 | 07-Dec-20 A | 2021-12-17 | 30% | 22.4 |  |  | 2885.4 | 2885.4 | 0
S257000 | Procure DAQ Production SEBs - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 80 | 11781 | 04-Feb-20 A | 18-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S257000 | Procure DAQ Production SEBs - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 80 | 13768 | 04-Feb-20 A | 18-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S257800 | Procure DAQ Production ATPs - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 80 | 11781 | 30-Jun-20 A | 25-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S257800 | Procure DAQ Production ATPs - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 80 | 13768 | 30-Jun-20 A | 25-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S258600 | DAQ Production: Procure jSEB Slow control computers | PROF4 PO M.PROF4 PO M | 80 | 11781 | 20-Jul-20 A | 2021-07-30 | 50% | 40 |  |  | 5890.5 | 5890.5 | 0
S258600 | DAQ Production: Procure jSEB Slow control computers | SCI3 PO.SCI3 PO | 80 | 13768 | 20-Jul-20 A | 2021-07-30 | 50% | 40 |  |  | 6884 | 6884 | 0
S260500 | DAQ Production: Modify and Debug event builder software | PROF4 PO M.PROF4 PO M | 320 | 48539 | 26-Apr-21 A | 2021-08-25 | 90% | 32 |  |  | 4853.9 | 4853.9 | 0
S260500 | DAQ Production: Modify and Debug event builder software | SCI3 PO.SCI3 PO | 320 | 56726 | 26-Apr-21 A | 2021-08-25 | 90% | 32 |  |  | 5672.6 | 5672.6 | 0
S258900 | Procure DAQ Production Buffer Boxes - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 40 | 5891 | 10-Aug-20 A | 25-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S258900 | Procure DAQ Production Buffer Boxes - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 40 | 6884 | 10-Aug-20 A | 25-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S256900 | DAQ Production: Selecting the right technology and brands | PROF4 PO M.PROF4 PO M | 96 | 14137 | 02-Dec-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S256900 | DAQ Production: Selecting the right technology and brands | SCI3 PO.SCI3 PO | 96 | 16522 | 02-Dec-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S259700 | Procure DAQ Production Main Switches - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 96 | 14137 | 02-Mar-20 A | 16-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S259700 | Procure DAQ Production Main Switches - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 96 | 16522 | 02-Mar-20 A | 16-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S260400 | DAQ Production: Setting up the switches | PROF4 PO M.PROF4 PO M | 56 | 8494 | 12-Feb-21 A | 2021-07-30 | 80% | 11.2 |  |  | 1698.8 | 1698.8 | 0
S260400 | DAQ Production: Setting up the switches | SCI3 PO.SCI3 PO | 88 | 15600 | 12-Feb-21 A | 2021-07-30 | 80% | 17.6 |  |  | 3120 | 3120 | 0
S260400 | DAQ Production: Setting up the switches | TECH3 PO M.TECH3 PO M | 44 | 5172 | 12-Feb-21 A | 2021-07-30 | 80% | 8.8 |  |  | 1034.4 | 1034.4 | 0
S260700 | DAQ Production: Internal Readiness Review | PROF4 PO M.PROF4 PO M | 80 | 12135 | 2022-01-19 | 2022-02-01 | 0% | 80 |  |  | 12135 | 12135 | 0
S260700 | DAQ Production: Internal Readiness Review | SCI3 PO.SCI3 PO | 240 | 42545 | 2022-01-19 | 2022-02-01 | 0% | 240 |  |  | 42545 | 42545 | 0
S257700 | Production SEBs - Setup Machines | SCI3 PO.SCI3 PO | 40 | 7091 | 09-Nov-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S258500 | Production ATPs - Setup Machines | SCI3 PO.SCI3 PO | 40 | 7091 | 10-Nov-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S258800 | Production jSEB Slow control computers - Setup Machines | SCI3 PO.SCI3 PO | 40 | 6884 | 2021-08-09 | 2021-08-13 | 0% | 40 |  |  | 6884 | 6884 | 0
S259600 | Production Buffer Boxes - Setup Machines | SCI3 PO.SCI3 PO | 40 | 7091 | 23-Nov-20 A | 2021-11-05 | 16% | 33.6 |  |  | 5956.44 | 5956.44 | 0
1.06.02 Local Level 1 Trigger (LL1)
1.06.02.02 LL1 Trigger Prototype v1
S262801 | Preliminary Design Review - DAQ Local Level-1 | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 4 | 0 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S262801 | Preliminary Design Review - DAQ Local Level-1 | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 | 0 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S262801 | Preliminary Design Review - DAQ Local Level-1 | SCI4 PO.SCI 4 PO | 4 | 824 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S262801 | Preliminary Design Review - DAQ Local Level-1 | SCI3 PO.SCI3 PO | 4 | 688 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S262801 | Preliminary Design Review - DAQ Local Level-1 | PROF3 IO E.PROF3 IO E | 4 | 506 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.03 Global Level 1 Trigger (GL1)
1.06.03.02 GL1 Trigger Prototype
S266300 | GL1 Prototype: Design I/O Transition Module FY19 | TECH3 PO D.TECH3 PO D | 64 | 7123 | 03-Jun-19 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S266701 | Final Design Review - DAQ Global Level-1 | PROF3 IO E.PROF3 IO E | 4 | 506 | 2021-07-01 | 2021-07-01 | 0% | 4 |  |  | 506 | 506 | 0
S266701 | Final Design Review - DAQ Global Level-1 | SCI3 PO.SCI3 PO | 4 | 688 | 2021-07-01 | 2021-07-01 | 0% | 4 |  |  | 688 | 688 | 0
S266701 | Final Design Review - DAQ Global Level-1 | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 | 0 | 2021-07-01 | 2021-07-01 | 0% | 4 |  |  | 0 | 0 | 0
S266701 | Final Design Review - DAQ Global Level-1 | SCI4 PO.SCI 4 PO | 4 | 824 | 2021-07-01 | 2021-07-01 | 0% | 4 |  |  | 824 | 824 | 0
S266701 | Final Design Review - DAQ Global Level-1 | PROF3 PO E.PROF3 PO E | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | 8 |  |  | 1012 | 1012 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | PROF3 PO E.PROF3 PO E | 4 | 506 | 2021-07-01 | 2021-07-01 | 0% | 4 |  |  | 506 | 506 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | PROF3 IO E.PROF3 IO E | 8 | 1012 | 2021-07-01 | 2021-07-01 | 0% | 8 |  |  | 1012 | 1012 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | SCI3 PO.SCI3 PO | 4 | 688 | 2021-07-01 | 2021-07-01 | 0% | 4 |  |  | 688 | 688 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 | 0 | 2021-07-01 | 2021-07-01 | 0% | 4 |  |  | 0 | 0 | 0
S266702 | Procurement Readiness Review - DAQ Global Level-1 | SCI4 PO.SCI 4 PO | 4 | 824 | 2021-07-01 | 2021-07-01 | 0% | 4 |  |  | 824 | 824 | 0
S266110 | GL1 Prototype: develop firmware FY19 Split | PROF3 PO E.PROF3 PO E | 354 | 43480 | 03-Jun-19 A | 06-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S266110 | GL1 Prototype: develop firmware FY19 Split | SCI3 PO.SCI3 PO | 97 | 16208 | 03-Jun-19 A | 06-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.03.03 GL1 Trigger Production
S268100 | GL1 Production: additional firmware improvements | PROF3 PO E.PROF3 PO E | 156 | 20328 | 2022-01-20 | 2022-02-04 | 0% | 156 |  |  | 20328 | 20328 | 0
S268010 | GL1 Production: commission GL1 system | PROF3 IO E.PROF3 IO E | 108 | 14073 | 2021-12-06 | 2022-01-19 | 0% | 108 |  |  | 14073 | 14073 | 0
1.06.04 Timing System
1.06.04.02 Timing System Prototype
S269100 | Timing System Prototype: Design I/O Transition Module FY19 | TECH3 PO D.TECH3 PO D | 76 | 8421 | 03-Jun-19 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S269501 | Final Design Review - DAQ Timing System | PROF3 IO E.PROF3 IO E | 8 | 1012 | 2021-08-02 | 2021-08-02 | 0% | 8 |  |  | 1012 | 1012 | 0
S269501 | Final Design Review - DAQ Timing System | PROF3 PO E.PROF3 PO E | 4 | 506 | 2021-08-02 | 2021-08-02 | 0% | 4 |  |  | 506 | 506 | 0
S269501 | Final Design Review - DAQ Timing System | SCI3 PO.SCI3 PO | 4 | 688 | 2021-08-02 | 2021-08-02 | 0% | 4 |  |  | 688 | 688 | 0
S269501 | Final Design Review - DAQ Timing System | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 | 0 | 2021-08-02 | 2021-08-02 | 0% | 4 |  |  | 0 | 0 | 0
S269501 | Final Design Review - DAQ Timing System | SCI4 PO.SCI 4 PO | 4 | 824 | 2021-08-02 | 2021-08-02 | 0% | 4 |  |  | 824 | 824 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | SCI4 PO.SCI 4 PO | 4 | 824 | 2021-07-30 | 2021-07-30 | 0% | 4 |  |  | 824 | 824 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | SCI3 PO.SCI3 PO | 4 | 688 | 2021-07-30 | 2021-07-30 | 0% | 4 |  |  | 688 | 688 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 4 | 0 | 2021-07-30 | 2021-07-30 | 0% | 4 |  |  | 0 | 0 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | PROF3 PO E.PROF3 PO E | 4 | 506 | 2021-07-30 | 2021-07-30 | 0% | 4 |  |  | 506 | 506 | 0
S269502 | Procurement Readiness Review - DAQ Timing System | PROF3 IO E.PROF3 IO E | 8 | 1012 | 2021-07-30 | 2021-07-30 | 0% | 8 |  |  | 1012 | 1012 | 0
S268915 | Timing System Prototype: develop firmware FY19 Split | PROF3 IO E.PROF3 IO E | 55 | 6755 | 03-Jun-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.04.03 Timing System Production
S270600 | Timing System Production: install timing system | PROF3 PO E.PROF3 PO E | 80 | 10424 | 2021-11-03 | 2021-12-10 | 0% | 80 |  |  | 10424 | 10424 | 0
S270600 | Timing System Production: install timing system | SCI3 PO.SCI3 PO | 40 | 7091 | 2021-11-03 | 2021-12-10 | 0% | 40 |  |  | 7091 | 7091 | 0
S270600 | Timing System Production: install timing system | TECH3 PO E.TECH3 PO E | 320 | 37615 | 2021-11-03 | 2021-12-10 | 0% | 320 |  |  | 37615 | 37615 | 0
S270510 | Timing System Production: final firmware updates | PROF3 IO E.PROF3 IO E | 322 | 40736 | 15-Mar-21 A | 2021-08-16 | 60% | 128.8 |  |  | 16294.4 | 16294.4 | 0
S270610 | Timing System Production: install timing system | PROF3 IO E.PROF3 IO E | 160 | 20849 | 2021-11-03 | 2021-12-10 | 0% | 160 |  |  | 20849 | 20849 | 0
S270710 | Timing System Production: commission timing system | PROF3 IO E.PROF3 IO E | 192 | 25019 | 2021-12-13 | 2022-01-11 | 0% | 192 |  |  | 25019 | 25019 | 0
1.07 Min Bias Trigger Detector
S271000 | Actuals - Labor - sPHENIX MinBias Trigger FY17 | Actual Labor.Actual Labor | 205 | 34217 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S271100 | Actuals - Labor - sPHENIX MinBias Trigger FY18 | Actual Labor.Actual Labor | 489 | 81740 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S272800 | Procure Min/Bias Electronics - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 112 | 19276 | 25-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S273700 | Oversight of sPHENIX MBD Digitizers Procurement | SCI3 PO.SCI3 PO | 16 | 2762 | 2021-07-01 | 2021-12-02 | 0% | 16 |  |  | 2762 | 2762 | 0
S1000999 | Actuals - Labor - sPHENIX MinBias Trigger FY19 M8 | Actual Labor.Actual Labor | 302 | 50490 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
C Infrastructure / Facility Upgrade
POM02B-PCR026 POM02 sPHENIX WBS 1.x, 2.x Baseline PCR026 Approved
2 Infrastructure/Facility
2.01 Infrastructure/Facility Management
2.01.02 Magnet Management and Technical Oversight
S278400 | Actuals - Labor - sPHENIX Magnet FY17 16716 | Actual Labor.Actual Labor | 117 | 19542 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S278500 | Actuals - Labor - sPHENIX Magnet FY18 16716 and 16717 | Actual Labor.Actual Labor | 488 | 81575 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S278700 | Actuals - Nonlabor - sPHENIX Magnet FY18 16716 | Actual NonLabor.Actual Nonlabor | 25268 | 28189 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S274600 | 2020 Magnet Project Management | SCI3 AD.SCI3 AD | 880 | 151453 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S274700 | 2021 Magnet Project Management | SCI3 AD.SCI3 AD | 880 | 155997 | 01-Oct-20 A | 2021-09-30 | 74.4% | 225.28 |  |  | 39935.232 | 39935.232 | 0
S274800 | 2022 Magnet Project Management | SCI3 AD.SCI3 AD | 880 | 160676 | 2021-10-01 | 2022-09-30 | 0% | 880 |  |  | 160676 | 160676 | 0
S275200 | 2020 Cryo L3 Project Management | PROF6 AD.PROF6 AD | 352 | 67934 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S275300 | 2021 Cryo L3 Project Management | PROF6 AD.PROF6 AD | 235 | 46714 | 01-Oct-20 A | 31-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S275700 | 2020 PS & Quench Protection L3 Project Management | PROF5 AD.PROF5 AD | 352 | 59862 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S275800 | 2021 PS & Quench Protection L3 Project Management | PROF5 AD.PROF5 AD | 352 | 61658 | 01-Oct-20 A | 2021-09-30 | 74.4% | 90.112 |  |  | 15784.448 | 15784.448 | 0
S275900 | 2022 PS & Quench Protection L3 Project Management | PROF5 AD.PROF5 AD | 352 | 63508 | 2021-10-01 | 2022-09-30 | 0% | 352 |  |  | 63508 | 63508 | 0
S1001199 | Actuals - Labor - sPHENIX Magnet FY19 M8 16716 | Actual Labor.Actual Labor | 565 | 94443 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004320 | Actuals - Labor FY19 Jun-Sep 16716 | Actual Labor.Actual Labor | 347 | 58057 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.01.03 Carriage and Structural Component Management
S1000559 | Actuals - Labor - sPHENIX Infrastructure FY17 16725 | Actual Labor.Actual Labor | 134 | 22417 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000719 | Actuals - Labor - sPHENIX Infrastructure FY18 16725 | Actual Labor.Actual Labor | 102 | 17027 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1001719 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16725 | Actual Labor.Actual Labor | 120 | 19969 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004680 | Actuals - Labor FY19 Jun-Sep 16725 | Actual Labor.Actual Labor | 137 | 22941 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.01.04 Infrastructure Management
S309200 | Actuals - Labor - sPHENIX Infrastructure FY17 16721 | Actual Labor.Actual Labor | 460 | 76844 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S309300 | Actuals - Labor - sPHENIX Infrastructure FY18 16721 | Actual Labor.Actual Labor | 1177 | 196648 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S276200 | 2020 Infrastructure Project Management | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 890 | 140366 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S276200 | 2020 Infrastructure Project Management | PROF3 PO E.PROF3 PO E | 880 | 111328 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S276300 | 2021 Infrastructure Project Management | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 890 | 144577 | 01-Oct-20 A | 2021-09-30 | 74.4% | 227.84 |  |  | 37011.712 | 37011.712 | 0
S276300 | 2021 Infrastructure Project Management | PROF3 PO E.PROF3 PO E | 860 | 112062 | 01-Oct-20 A | 2021-09-30 | 74.4% | 220.16 |  |  | 28687.872 | 28687.872 | 0
S276400 | 2022 Infrastructure Project Management | PROF3 PO E.PROF3 PO E | 800 | 107371 | 2021-10-01 | 2022-09-30 | 0% | 800 |  |  | 107371 | 107371 | 0
S276800 | 2020 Facility Support Systems L3 Project Management | PROF2 AD.PROF2 AD | 352 | 35277 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S276900 | 2021 Facility Support Systems L3 Project Management | PROF2 AD.PROF2 AD | 352 | 36335 | 01-Oct-20 A | 2021-09-30 | 74.4% | 90.112 |  |  | 9301.76 | 9301.76 | 0
S277400 | 2020 Detector Support Systems L3 Project Management | PROF4 PO E.PROF4 PO E | 440 | 64797 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S277400 | 2020 Detector Support Systems L3 Project Management | PROF3 PO E.PROF3 PO E | 352 | 44531 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S277500 | 2021 Detector Support Systems L3 Project Management | PROF4 PO E.PROF4 PO E | 440 | 66741 | 01-Oct-20 A | 2021-09-30 | 74.4% | 112.64 |  |  | 17085.696 | 17085.696 | 0
S277500 | 2021 Detector Support Systems L3 Project Management | PROF3 PO E.PROF3 PO E | 352 | 45867 | 01-Oct-20 A | 2021-09-30 | 74.4% | 90.112 |  |  | 11741.952 | 11741.952 | 0
S276500 | 2023 Infrastructure Project Management | PROF3 PO E.PROF3 PO E | 40 | 5530 | 2022-10-03 | 2022-10-07 | 0% | 40 |  |  | 5530 | 5530 | 0
S1001519 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16721 | Actual Labor.Actual Labor | 354 | 59221 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004640 | Actuals - Labor FY19 Jun-Sep 16721 | Actual Labor.Actual Labor | 8 | 1351 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004720 | Actuals - NonLabor FY19 Jun-Sep 16721 | Actual NonLabor.Actual Nonlabor | 6516 | 7188 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.01.05 Installation Management
S343900 | Actuals - Labor - sPHENIX Integration and Installation FY17 16726 | Actual Labor.Actual Labor | 511 | 85433 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S344000 | Actuals - Labor - sPHENIX Integration and Installation FY18 16726 | Actual Labor.Actual Labor | 707 | 118130 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S344200 | Actuals - Nonlabor - sPHENIX Integration and Installation FY18 16726 16727 and 16728 | Actual NonLabor.Actual Nonlabor | 2700 | 3012 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S278000 | 2020 Integration & Installation Project Management | PROF5 PO M.PROF5 PO M | 880 | 149656 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S278000 | 2020 Integration & Installation Project Management | PROF3 PO E.PROF3 PO E | 440 | 55664 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S278000 | 2020 Integration & Installation Project Management | SCI3 PO.SCI3 PO | 440 | 75726 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S278100 | 2021 Integration & Installation Project Management | PROF5 PO M.PROF5 PO M | 880 | 154145 | 02-Oct-20 A | 2021-09-30 | 74.4% | 225.28 |  |  | 39461.12 | 39461.12 | 0
S278100 | 2021 Integration & Installation Project Management | PROF3 PO E.PROF3 PO E | 440 | 57334 | 02-Oct-20 A | 2021-09-30 | 74.4% | 112.64 |  |  | 14677.504 | 14677.504 | 0
S278100 | 2021 Integration & Installation Project Management | SCI3 PO.SCI3 PO | 440 | 77998 | 02-Oct-20 A | 2021-09-30 | 74.4% | 112.64 |  |  | 19967.488 | 19967.488 | 0
S278200 | 2022 Integration & Installation Project Management | PROF5 PO M.PROF5 PO M | 880 | 158770 | 2021-10-01 | 2022-09-30 | 0% | 880 |  |  | 158770 | 158770 | 0
S278300 | 2023 Integration & Installation Project Management | PROF5 PO M.PROF5 PO M | 282 | 52405 | 2022-10-03 | 2022-10-05 | 0% | 282 |  |  | 52405 | 52405 | 0
S1001079 | Actuals - Labor - sPHENIX Integration and Installation FY19 M8 16726 | Actual Labor.Actual Labor | 172 | 28728 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004760 | Actuals - Labor FY19 Jun-Sep 16726 | Actual Labor.Actual Labor | 52 | 8728 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.02 SC Magnet
2.02.01 Safety Reviews, Cooldown, Power Tests
2.02.01.01 Safety Reviews
S278800 | LESHC-PSSC Review Cryogenic Safety Review | SCI3 AD.SCI3 AD | 16 | 2921 | 08-Mar-21 A | 2022-05-04 | 50% | 8 |  |  | 1460.5 | 1460.5 | 0
S278800 | LESHC-PSSC Review Cryogenic Safety Review | PROF4 AM.PROF4 AM | 8 | 1250 | 08-Mar-21 A | 2022-05-04 | 50% | 4 |  |  | 625 | 625 | 0
S278800 | LESHC-PSSC Review Cryogenic Safety Review | PROF6 AD.PROF6 AD | 16 | 3276 | 08-Mar-21 A | 2022-05-04 | 50% | 8 |  |  | 1638 | 1638 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | SCI3 AD.SCI3 AD | 16 | 2921 | 2022-04-28 | 2022-04-28 | 0% | 16 |  |  | 2921 | 2921 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | PROF4 AM.PROF4 AM | 8 | 1250 | 2022-04-28 | 2022-04-28 | 0% | 8 |  |  | 1250 | 1250 | 0
S278900 | LESHC Review Magnet Overall System Safety Review | PROF6 AD.PROF6 AD | 16 | 3276 | 2022-04-28 | 2022-04-28 | 0% | 16 |  |  | 3276 | 3276 | 0
S279000 | ASSRC REVIEW and Full Walkthrough | SCI3 AD.SCI3 AD | 16 | 2921 | 2022-04-29 | 2022-04-29 | 0% | 16 |  |  | 2921 | 2921 | 0
S279000 | ASSRC REVIEW and Full Walkthrough | PROF6 AD.PROF6 AD | 16 | 3276 | 2022-04-29 | 2022-04-29 | 0% | 16 |  |  | 3276 | 3276 | 0
2.02.01.02 Cooldown & Power Tests
S279100 | Cooldown | PROF3 AD.PROF3 AD | 60 | 8053 | 2022-05-05 | 2022-05-25 | 0% | 60 |  |  | 8053 | 8053 | 0
S279100 | Cooldown | TECH3 AD.TECH3 AD | 60 | 7264 | 2022-05-05 | 2022-05-25 | 0% | 60 |  |  | 7264 | 7264 | 0
S279100 | Cooldown | PROF6 AD.PROF6 AD | 60 | 12285 | 2022-05-05 | 2022-05-25 | 0% | 60 |  |  | 12285 | 12285 | 0
S279200 | 4.5K Static Heat Load test | PROF3 AD.PROF3 AD | 8 | 1074 | 2022-05-26 | 2022-05-27 | 0% | 8 |  |  | 1074 | 1074 | 0
S279200 | 4.5K Static Heat Load test | TECH3 AD.TECH3 AD | 8 | 969 | 2022-05-26 | 2022-05-27 | 0% | 8 |  |  | 969 | 969 | 0
S279200 | 4.5K Static Heat Load test | PROF6 AD.PROF6 AD | 8 | 1638 | 2022-05-26 | 2022-05-27 | 0% | 8 |  |  | 1638 | 1638 | 0
S279300 | 4.5K Low power test | PROF3 AD.PROF3 AD | 20 | 2684 | 2022-05-31 | 2022-06-06 | 0% | 20 |  |  | 2684 | 2684 | 0
S279300 | 4.5K Low power test | SCI3 AD.SCI3 AD | 80 | 14607 | 2022-05-31 | 2022-06-06 | 0% | 80 |  |  | 14607 | 14607 | 0
S279300 | 4.5K Low power test | TECH3 AD.TECH3 AD | 80 | 9686 | 2022-05-31 | 2022-06-06 | 0% | 80 |  |  | 9686 | 9686 | 0
S279300 | 4.5K Low power test | PROF6 AD.PROF6 AD | 80 | 16380 | 2022-05-31 | 2022-06-06 | 0% | 80 |  |  | 16380 | 16380 | 0
S279400 | 4.5K High Power Test | PROF3 AD.PROF3 AD | 20 | 2684 | 2022-06-07 | 2022-06-13 | 0% | 20 |  |  | 2684 | 2684 | 0
S279400 | 4.5K High Power Test | SCI3 AD.SCI3 AD | 80 | 14607 | 2022-06-07 | 2022-06-13 | 0% | 80 |  |  | 14607 | 14607 | 0
S279400 | 4.5K High Power Test | TECH3 AD.TECH3 AD | 80 | 9686 | 2022-06-07 | 2022-06-13 | 0% | 80 |  |  | 9686 | 9686 | 0
S279400 | 4.5K High Power Test | PROF6 AD.PROF6 AD | 80 | 16380 | 2022-06-07 | 2022-06-13 | 0% | 80 |  |  | 16380 | 16380 | 0
2.02.02 Magnet Transport & Assembly
S281200 | Magnet - Prepare for Coil Shipment - Shipping Constraints and Tooling | TECH3 AM.TECH3 AM | 160 | 18260 | 01-Oct-19 A | 30-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S281200 | Magnet - Prepare for Coil Shipment - Shipping Constraints and Tooling | PROF4 AM.PROF4 AM | 16 | 2356 | 01-Oct-19 A | 30-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S281400 | Magnet and Solenoid Valvebox - Reinstall | TECH3 AM.TECH3 AM | 400 | 48260 | 2021-10-12 | 2021-11-16 | 0% | 400 |  |  | 48260 | 48260 | 0
S281400 | Magnet and Solenoid Valvebox - Reinstall | PROF4 AM.PROF4 AM | 40 | 6227 | 2021-10-12 | 2021-11-16 | 0% | 40 |  |  | 6227 | 6227 | 0
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | TECH3 AM.TECH3 AM | 160 | 19372 | 2021-11-17 | 2021-12-02 | 0% | 160 |  |  | 19372 | 19372 | 0
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | PROF4 AM.PROF4 AM | 16 | 2500 | 2021-11-17 | 2021-12-02 | 0% | 16 |  |  | 2500 | 2500 | 0
S1000039 | Actuals - Labor - sPHENIX Magnet FY17 16717 | Actual Labor.Actual Labor | 6 | 969 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1001239 | Actuals - Labor - sPHENIX Magnet FY19 M8 16717 | Actual Labor.Actual Labor | 3 | 508 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1001279 | Actuals - NonLabor - sPHENIX Magnet FY19 M8 16717 | Actual NonLabor.Actual Nonlabor | 2857 | 3152 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004360 | Actuals - Labor FY19 Jun-Sep 16717 | Actual Labor.Actual Labor | 42 | 7093 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004400 | Actuals - NonLabor FY19 Jun-Sep 16717 | Actual NonLabor.Actual Nonlabor | 19416 | 21421 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03 Magnet Cryogenic Systems
S1000079 | Actuals - Labor - sPHENIX Magnet FY17 16718 | Actual Labor.Actual Labor | 16 | 2593 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000159 | Actuals - Labor - sPHENIX Magnet FY18 16718 | Actual Labor.Actual Labor | 822 | 137267 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1001319 | Actuals - Labor - sPHENIX Magnet FY19 M8 16718 | Actual Labor.Actual Labor | 1602 | 267683 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1001359 | Actuals - NonLabor - sPHENIX Magnet FY19 M8 16718 | Actual NonLabor.Actual Nonlabor | 13286 | 14657 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004440 | Actuals - Labor FY19 Jun-Sep 16718 | Actual Labor.Actual Labor | 272 | 45398 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004480 | Actuals - NonLabor FY19 Jun-Sep 16718 | Actual NonLabor.Actual Nonlabor | 17882 | 19728 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.01 Helium System: 1008BColdbox, Transferlines, & IR8 Coldbox
2.02.03.01.04 Vendor Manufacturing - Helium System: 1008B Coldbox, Transferlines, & IR8 Coldbox
2.02.03.01.04.01 Group 1
2.02.03.01.04.01.01 5 Multiple Process Line Cryogenixc Spools
S1005200 | BNL review for PDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 | 26200 | 16-Jan-20 A | 27-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1005280 | AET submits FDR report to BNL for approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 70455 | 78600 | 13-Apr-20 A | 08-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1005260 | BNL review for IDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 | 26200 | 13-Mar-20 A | 10-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.01.04.01.02 3 Interconnect Spools, Vaccum Break, Field Joint Tee and Sleeve
S1005560 | BNL review for PDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 31313 | 34933 | 27-May-20 A | 02-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1005640 | AET submits FDR report to BNL for approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 70455 | 78600 | 17-Jun-20 A | 27-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1005760 | Delivery Interconnect (S-Line, H-Line, U-Line), vacuum break, Field Joint Tee and Sleeve | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 93940 | 104800 | 02-Nov-20 A | 06-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1005620 | BNL review for IDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 31313 | 34933 | 10-Jun-20 A | 13-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.01.04.01.03 Service Building 1008B Cold Box
S1005880 | BNL review for PDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 | 26200 | 01-Oct-20 A | 15-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1006040 | AET submits FDR report to BNL for approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 93940 | 104800 | 04-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1006000 | BNL review for IDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 | 26200 | 15-Dec-20 A | 29-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1006200 | Delivery of the 1008B Cold Box and Document Package | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 93940 | 104800 | 28-Apr-21 A | 31-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.01.04.02 Group 2
2.02.03.01.04.02.01 IP8 Cold Box
S1006280 | BNL review for PDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 31313 | 34933 | 2021-07-16 | 2021-07-29 | 0% | 31313 |  |  | 34933 | 34933 | 0
S1006440 | AET submits FDR report to BNL for approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 125253 | 139734 | 2021-08-20 | 2021-09-17 | 0% | 125253 |  |  | 139734 | 139734 | 0
S1006400 | BNL review for IDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 31313 | 34933 | 2021-08-13 | 2021-08-19 | 0% | 31313 |  |  | 34933 | 34933 | 0
2.02.03.01.04.02.02 Three Manifold Jumper Transfer Lines
S1006680 | BNL review for PDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 | 26200 | 2021-07-30 | 2021-08-05 | 0% | 23485 |  |  | 26200 | 26200 | 0
S1006800 | AET submits FDR report to BNL for approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 93940 | 104800 | 2021-08-20 | 2021-09-02 | 0% | 93940 |  |  | 104800 | 104800 | 0
S1006760 | BNL review for IDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 | 26200 | 2021-08-13 | 2021-08-19 | 0% | 23485 |  |  | 26200 | 26200 | 0
2.02.03.01.04.02.03 Three Solenoid Valve Box Transfer Lines
S1007000 | BNL review for PDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 | 26200 | 2021-11-24 | 2021-12-02 | 0% | 23485 |  |  | 26200 | 26200 | 0
S1007120 | AET submits FDR report to BNL for approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 93940 | 104800 | 2021-12-17 | 2021-12-23 | 0% | 93940 |  |  | 104800 | 104800 | 0
S1007080 | BNL review for IDR approval | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 23485 | 26200 | 2021-12-10 | 2021-12-16 | 0% | 23485 |  |  | 26200 | 26200 | 0
S1007240 | Delivery of all three Solenoid Valve Box Transfer Lines and two 4" & 5" NPS Field Joint Sleeves | Purch 1st $2M.Material (Purchase (1st $2M) | 203536 | 240966 | 2022-02-02 | 2022-02-08 | 0% | 203536 |  |  | 240966 | 240966 | 0
S1007280 | Approval of all Data/Documentation/ Reports | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 78283 | 87334 | 2022-02-09 | 2022-02-15 | 0% | 78283 |  |  | 87334 | 87334 | 0
2.02.03.01.04.03 Group 3
S1007320 | Delivery two male bayonets and one vapor return female bayonet | Purch 1st $2M.Material (Purchase (1st $2M) | 78283 | 89080 | 03-Aug-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.01.04.04 Vendor Engineering and Design
S284100 | RHIC Helium Interface - Engineering supervision by BNL | PROF3 AD.PROF3 AD | 240 | 30692 | 02-Dec-19 A | 2021-11-30 | 76% | 57.6 |  |  | 7366.08 | 7366.08 | 0
S284100 | RHIC Helium Interface - Engineering supervision by BNL | TECH3 AD.TECH3 AD | 54 | 6230 | 02-Dec-19 A | 2021-11-30 | 76% | 12.96 |  |  | 1495.2 | 1495.2 | 0
S284100 | RHIC Helium Interface - Engineering supervision by BNL | PROF6 AD.PROF6 AD | 207 | 40384 | 02-Dec-19 A | 2021-11-30 | 76% | 49.68 |  |  | 9692.16 | 9692.16 | 0
S284220 | Procure RHIC Helium Interface, MS1 (Manufacturing Program Plan) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 0 | 0 | 18-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S284220 | Procure RHIC Helium Interface, MS1 (Manufacturing Program Plan) - Delivery Acceptance | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 156566 | 174667 | 18-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.01.06 Installation
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | PROF3 AD.PROF3 AD | 20 | 2606 | 2021-07-01 | 2021-07-08 | 0% | 20 |  |  | 2606 | 2606 | 0
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | TECH3 AD.TECH3 AD | 20 | 2351 | 2021-07-01 | 2021-07-08 | 0% | 20 |  |  | 2351 | 2351 | 0
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | CRAFT3.CRAFT3 | 40 | 5153 | 2021-07-01 | 2021-07-08 | 0% | 40 |  |  | 5153 | 5153 | 0
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | PROF6 AD.PROF6 AD | 8 | 1590 | 2021-07-01 | 2021-07-08 | 0% | 8 |  |  | 1590 | 1590 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | PROF3 AD.PROF3 AD | 24 | 3127 | 2021-07-09 | 2021-08-19 | 0% | 24 |  |  | 3127 | 3127 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | TECH3 AD.TECH3 AD | 360 | 42316 | 2021-07-09 | 2021-08-19 | 0% | 360 |  |  | 42316 | 42316 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | CRAFT3.CRAFT3 | 180 | 23188 | 2021-07-09 | 2021-08-19 | 0% | 180 |  |  | 23188 | 23188 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | TECH3 AD.TECH3 AD | 40 | 4702 | 2021-07-09 | 2021-08-19 | 0% | 40 |  |  | 4702 | 4702 | 0
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | PROF6 AD.PROF6 AD | 24 | 4771 | 2021-07-09 | 2021-08-19 | 0% | 24 |  |  | 4771 | 4771 | 0
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | PROF3 AD.PROF3 AD | 12 | 1611 | 2022-01-11 | 2022-02-08 | 0% | 12 |  |  | 1611 | 1611 | 0
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | TECH3 AD.TECH3 AD | 40 | 4843 | 2022-01-11 | 2022-02-08 | 0% | 40 |  |  | 4843 | 4843 | 0
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | PROF6 AD.PROF6 AD | 12 | 2457 | 2022-01-11 | 2022-02-08 | 0% | 12 |  |  | 2457 | 2457 | 0
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | PROF3 AD.PROF3 AD | 80 | 10737 | 2022-03-30 | 2022-04-12 | 0% | 80 |  |  | 10737 | 10737 | 0
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | TECH3 AD.TECH3 AD | 120 | 14529 | 2022-03-30 | 2022-04-12 | 0% | 120 |  |  | 14529 | 14529 | 0
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | PROF6 AD.PROF6 AD | 80 | 16380 | 2022-03-30 | 2022-04-12 | 0% | 80 |  |  | 16380 | 16380 | 0
S287600 | RHIC Helium Interface - Final pump and purge | PROF3 AD.PROF3 AD | 24 | 3221 | 2022-04-13 | 2022-04-26 | 0% | 24 |  |  | 3221 | 3221 | 0
S287600 | RHIC Helium Interface - Final pump and purge | TECH3 AD.TECH3 AD | 120 | 14529 | 2022-04-13 | 2022-04-26 | 0% | 120 |  |  | 14529 | 14529 | 0
S287600 | RHIC Helium Interface - Final pump and purge | PROF6 AD.PROF6 AD | 4 | 819 | 2022-04-13 | 2022-04-26 | 0% | 4 |  |  | 819 | 819 | 0
S287000 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Rigging in place | PROF3 AD.PROF3 AD | 8 | 1042 | 22-Sep-20 A | 12-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287000 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Rigging in place | TECH3 AD.TECH3 AD | 120 | 14105 | 22-Sep-20 A | 12-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287000 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Rigging in place | CRAFT3.CRAFT3 | 80 | 10306 | 22-Sep-20 A | 12-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | PROF3 AD.PROF3 AD | 40 | 5212 | 13-Oct-20 A | 29-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | TECH3 AD.TECH3 AD | 320 | 37615 | 13-Oct-20 A | 29-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | CRAFT3.CRAFT3 | 160 | 20612 | 13-Oct-20 A | 29-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | TECH3 AD.TECH3 AD | 80 | 9404 | 13-Oct-20 A | 29-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287200 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: Rigging in place | PROF3 AD.PROF3 AD | 8 | 1012 | 22-Sep-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287200 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: Rigging in place | TECH3 AD.TECH3 AD | 80 | 9130 | 22-Sep-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287200 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: Rigging in place | CRAFT3.CRAFT3 | 20 | 2501 | 22-Sep-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | PROF3 AD.PROF3 AD | 40 | 5091 | 04-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | TECH3 AD.TECH3 AD | 320 | 36738 | 04-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | CRAFT3.CRAFT3 | 160 | 20131 | 04-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | TECH3 AD.TECH3 AD | 40 | 4592 | 04-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | PROF6 AD.PROF6 AD | 8 | 1553 | 04-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.02 LN2 Supply Transfer Line System
2.02.03.02.01 Engineering and Design, LN2 Supply Transfer Line System
S288200 | (LN2 supply transfer line system) SOW & Technical Specifications | PROF3 AD.PROF3 AD | 36 | 4554 | 22-Nov-19 A | 01-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S288200 | (LN2 supply transfer line system) SOW & Technical Specifications | PROF6 AD.PROF6 AD | 36 | 6948 | 22-Nov-19 A | 01-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S288100 | (LN2 supply transfer line system) Mechanical Engineering Tasks FY19 | PROF3 AD.PROF3 AD | 40 | 5060 | 01-Oct-19 A | 01-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S288100 | (LN2 supply transfer line system) Mechanical Engineering Tasks FY19 | PROF6 AD.PROF6 AD | 40 | 7720 | 01-Oct-19 A | 01-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.02.02 Design/Drafting, LN2 Supply Transfer Line System
S288500 | (LN2 supply transfer line system) Detailed dwg package for Procurement | PROF3 AD.PROF3 AD | 120 | 15181 | 10-Dec-19 A | 10-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S288500 | (LN2 supply transfer line system) Detailed dwg package for Procurement | PROF6 AD.PROF6 AD | 48 | 9264 | 10-Dec-19 A | 10-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S288410 | (LN2 supply transfer line system) LN2 supply transfer line detail layout Split | PROF3 AD.PROF3 AD | 17 | 2151 | 01-Oct-19 A | 09-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S288410 | (LN2 supply transfer line system) LN2 supply transfer line detail layout Split | PROF6 AD.PROF6 AD | 17 | 3281 | 01-Oct-19 A | 09-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.02.03 Procurement, LN2 Supply Transfer Line System
S288600 | Procure LN2 supply transfer line system - Provide requirements to Procurement | PROF3 AD.PROF3 AD | 48 | 6072 | 04-May-20 A | 15-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S288600 | Procure LN2 supply transfer line system - Provide requirements to Procurement | PROF6 AD.PROF6 AD | 88 | 16983 | 04-May-20 A | 15-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.02.04 Fabrication at Vendor, LN2 Supply Transfer Line System
2.02.03.02.04.01 Vendor Engineering and Design
S289400 | (LN2 supply transfer line system) Kick off meeting | PROF6 AD.PROF6 AD | 8 | 1544 | 01-Dec-20 A | 01-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S289500 | Engineering Support for Procure LN2 supply transfer line system | PROF6 AD.PROF6 AD | 36 | 6948 | 02-Dec-20 A | 2021-08-16 | 88% | 4.32 |  |  | 833.76 | 833.76 | 0
S289600 | (LN2 supply transfer line system) Preliminary Design Review Labor | PROF6 AD.PROF6 AD | 8 | 1544 | 02-Dec-20 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S289900 | (LN2 supply transfer line system) Detail dwg package | PROF6 AD.PROF6 AD | 48 | 9542 | 18-Jan-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S290300 | (LN2 supply transfer line system) Final Design Review Labor | PROF6 AD.PROF6 AD | 8 | 1590 | 01-Feb-21 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S290000 | Long lead items Support Labor for LN2 supply transfer line system | PROF6 AD.PROF6 AD | 24 | 4771 | 01-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S290600 | (LN2 supply transfer line system) Drawings approvals | PROF6 AD.PROF6 AD | 0 | 0 | 26-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S289800 | Procure LN2 supply transfer line system, Phase 1 (Preliminary Design Review) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 22000 | 25535 | 13-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S290500 | Procure LN2 supply transfer line system, Phase 3 (Final Design Review) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 58034 | 02-Feb-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S290200 | Procure LN2 supply transfer line system, Phase 2 (Long lead items) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 58034 | 16-Mar-21 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.02.04.02 Vendor Fabrication
S290700 | (LN2 supply transfer line system) Raw Material procur Labor | PROF6 AD.PROF6 AD | 0 | 0 | 21-Apr-21 A | 25-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S291000 | (LN2 supply transfer line system) Main fabrication items | PROF6 AD.PROF6 AD | 0 | 0 | 21-Apr-21 A | 25-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S291100 | (LN2 supply transfer line system) Final assemblies | PROF6 AD.PROF6 AD | 0 | 0 | 2021-08-17 | 2021-09-28 | 0% | 0 |  |  | 0 | 0 | 0
S291200 | (LN2 supply transfer line system) BNL Holdpoint witness | PROF6 AD.PROF6 AD | 0 | 0 | 2021-09-29 | 2021-09-29 | 0% | 0 |  |  | 0 | 0 | 0
S291300 | (LN2 supply transfer line system) Shipping Labor | PROF6 AD.PROF6 AD | 0 | 0 | 2021-09-30 | 2021-10-19 | 0% | 0 |  |  | 0 | 0 | 0
S290900 | Procure LN2 supply transfer line system, Phase 4 (Raw Material) - Planned Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 0 | 0 | 21-Apr-21 A | 25-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S291500 | Procure LN2 supply transfer line system - Final Docs Package | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 107261 | 119662 | 20-Oct-21* | 2021-10-20 | 0% | 107261 |  |  | 119662 | 119662 | 0
S1008520 | (LN2 supply transfer line system) LOE Supervision Labor | PROF6 AD.PROF6 AD | 140 | 27830 | 15-Apr-21 A | 25-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.02.05 Delivery and receiving, LN2 Supply Transfer Line System
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | PROF3 AD.PROF3 AD | 5 | 652 | 2021-10-20 | 2021-10-20 | 0% | 5 |  |  | 652 | 652 | 0
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | CRAFT3.CRAFT3 | 16 | 2061 | 2021-10-20 | 2021-10-20 | 0% | 16 |  |  | 2061 | 2061 | 0
S291700 | (LN2 supply transfer line system) Inspection | PROF6 AD.PROF6 AD | 1 | 199 | 2021-10-21 | 2021-10-21 | 0% | 1 |  |  | 199 | 199 | 0
2.02.03.02.06 Installation, LN2 Supply Transfer Line System
S291900 | (LN2 supply transfer line system) Piping supports procure materials Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 17-Mar-21 A | 19-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | PROF3 AD.PROF3 AD | 48 | 6072 | 17-May-21 A | 2021-07-20 | 3% | 46.56 |  |  | 5889.84 | 5889.84 | 0
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | TECH3 AD.TECH3 AD | 40 | 4565 | 17-May-21 A | 2021-07-20 | 3% | 38.8 |  |  | 4428.05 | 4428.05 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | PROF3 AD.PROF3 AD | 16 | 2085 | 2021-10-22 | 2021-11-04 | 0% | 16 |  |  | 2085 | 2085 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | TECH3 AD.TECH3 AD | 240 | 28211 | 2021-10-22 | 2021-11-04 | 0% | 240 |  |  | 28211 | 28211 | 0
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | CRAFT3.CRAFT3 | 16 | 2061 | 2021-10-22 | 2021-11-04 | 0% | 16 |  |  | 2061 | 2061 | 0
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | PROF3 AD.PROF3 AD | 24 | 3127 | 2021-11-05 | 2021-11-30 | 0% | 24 |  |  | 3127 | 3127 | 0
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | TECH3 AD.TECH3 AD | 96 | 11284 | 2021-11-05 | 2021-11-30 | 0% | 96 |  |  | 11284 | 11284 | 0
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | PROF3 AD.PROF3 AD | 20 | 2606 | 2021-12-01 | 2021-12-14 | 0% | 20 |  |  | 2606 | 2606 | 0
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | TECH3 AD.TECH3 AD | 64 | 7523 | 2021-12-01 | 2021-12-14 | 0% | 64 |  |  | 7523 | 7523 | 0
S291800 | (LN2 supply transfer line system) Piping supports procure materials M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 13000 | 14793 | 17-Mar-21 A | 19-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S292120 | Welding LN2 Segment #1 to LN2 Dewar | CRAFT3.CRAFT3 | 80 | 10306 | 2021-11-05 | 2021-11-19 | 0% | 80 |  |  | 10306 | 10306 | 0
2.02.03.03 Warm Piping System
2.02.03.03.01 Engineering and Design, Warm Piping System
S292700 | (Warm Piping System) Technical Specifications | PROF3 AD.PROF3 AD | 6 | 759 | 01-May-20 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S292700 | (Warm Piping System) Technical Specifications | PROF6 AD.PROF6 AD | 12 | 2316 | 01-May-20 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | PROF3 AD.PROF3 AD | 19 | 2404 | 02-Dec-19 A | 2021-08-30 | 85% | 2.85 |  |  | 360.6 | 360.6 | 0
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | PROF6 AD.PROF6 AD | 38 | 7334 | 02-Dec-19 A | 2021-08-30 | 85% | 5.7 |  |  | 1100.1 | 1100.1 | 0
2.02.03.03.02 Design/Drafting, Warm Piping System
2.02.03.03.02.01 Warm Piping tie in to WR header
S292800 | (Warm Piping tie in to WR header) General Arrangement Layout | PROF3 AD.PROF3 AD | 20 | 2530 | 03-Aug-20 A | 2021-07-20 | 97% | 0.6 |  |  | 75.9 | 75.9 | 0
S292800 | (Warm Piping tie in to WR header) General Arrangement Layout | PROF6 AD.PROF6 AD | 80 | 15439 | 03-Aug-20 A | 2021-07-20 | 97% | 2.4 |  |  | 463.17 | 463.17 | 0
S292900 | (Warm Piping tie in to WR header) Detailed drawing package with weld map | PROF3 AD.PROF3 AD | 16 | 2024 | 17-Nov-20 A | 2021-07-22 | 82% | 2.88 |  |  | 364.32 | 364.32 | 0
S292900 | (Warm Piping tie in to WR header) Detailed drawing package with weld map | PROF6 AD.PROF6 AD | 16 | 3088 | 17-Nov-20 A | 2021-07-22 | 82% | 2.88 |  |  | 555.84 | 555.84 | 0
2.02.03.03.02.02 Warm Piping tie in Bldg 1010B Compressor
S293000 | (Warm Piping tie in bldg. 1010B compressor) General Arrangement Layout | PROF3 AD.PROF3 AD | 16 | 2024 | 03-Aug-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S293000 | (Warm Piping tie in bldg. 1010B compressor) General Arrangement Layout | PROF6 AD.PROF6 AD | 80 | 15439 | 03-Aug-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S293100 | (Warm Piping tie in bldg. 1010B compressor) Detailed drawing package with weld map | PROF3 AD.PROF3 AD | 16 | 2024 | 16-Feb-21 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S293100 | (Warm Piping tie in bldg. 1010B compressor) Detailed drawing package with weld map | PROF6 AD.PROF6 AD | 80 | 15439 | 16-Feb-21 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.03.02.03 GN2 Vent Line from Platform Coldbox
S293300 | (GN2 Vent Line from platform coldbox) Detailed drawing package with weld map | PROF3 AD.PROF3 AD | 16 | 2024 | 09-Dec-19 A | 15-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S293300 | (GN2 Vent Line from platform coldbox) Detailed drawing package with weld map | PROF6 AD.PROF6 AD | 80 | 15439 | 09-Dec-19 A | 15-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.03.02.04 Warm Piping for Summer 80K Hold Helium Compressor Loop
S293500 | (Current Leads Warm Piping) Detailed drawing package with weld map | PROF3 AD.PROF3 AD | 26 | 3289 | 16-Dec-19 A | 2021-07-30 | 85% | 3.9 |  |  | 493.35 | 493.35 | 0
S293500 | (Current Leads Warm Piping) Detailed drawing package with weld map | PROF6 AD.PROF6 AD | 128 | 24703 | 16-Dec-19 A | 2021-07-30 | 85% | 19.2 |  |  | 3705.45 | 3705.45 | 0
2.02.03.03.03 Procurement of Materials, Warm Piping System
S293700 | (Warm Piping System Materials Procurement) Reliefs Labor | PROF3 AD.PROF3 AD | 72 | 9109 | 31-Dec-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S293700 | (Warm Piping System Materials Procurement) Reliefs Labor | PROF6 AD.PROF6 AD | 72 | 13895 | 31-Dec-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S293900 | (Warm Piping System Materials Procurement) Warm Valves | PROF6 AD.PROF6 AD | 36 | 6948 | 31-Dec-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S294700 | (Warm Piping System Materials Procurement) Piping supports Labor | PROF6 AD.PROF6 AD | 24 | 4632 | 08-Mar-21 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S293600 | (Warm Piping System Materials Procurement) Reliefs M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 8000 | 9103 | 31-Dec-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S293800 | (Warm Piping System Materials Procurement) Warm Valves M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 15000 | 17069 | 31-Dec-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S294000 | Procure Warm Piping and fittings - Provide Requirements to Procurement | PROF4 AD.PROF4 AD | 24 | 3534 | 01-Feb-21 A | 25-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S294600 | (Warm Piping System Materials Procurement) Piping supports M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 | 11379 | 08-Mar-21 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S294500 | Procure Warm Piping and fittings - Delivery acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 32000 | 37142 | 14-Jun-21 A | 2021-08-04 | 50% | 16000 |  |  | 18571 | 18571 | 0
2.02.03.03.04 Installation: Warm Piping Systems
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | PROF3 AD.PROF3 AD | 144 | 18764 | 2021-08-31 | 2022-01-12 | 0% | 144 |  |  | 18764 | 18764 | 0
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | TECH3 AD.TECH3 AD | 360 | 42316 | 2021-08-31 | 2022-01-12 | 0% | 360 |  |  | 42316 | 42316 | 0
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | CRAFT3.CRAFT3 | 240 | 30918 | 2021-08-31 | 2022-01-12 | 0% | 240 |  |  | 30918 | 30918 | 0
S294840 | (Warm Piping System) Remaining outside /1008B/Westwall work (between run21 and run22) | PROF3 AD.PROF3 AD | 36 | 4691 | 2021-07-09 | 2021-08-19 | 0% | 36 |  |  | 4691 | 4691 | 0
S294840 | (Warm Piping System) Remaining outside /1008B/Westwall work (between run21 and run22) | TECH3 AD.TECH3 AD | 180 | 21158 | 2021-07-09 | 2021-08-19 | 0% | 180 |  |  | 21158 | 21158 | 0
S294840 | (Warm Piping System) Remaining outside /1008B/Westwall work (between run21 and run22) | CRAFT3.CRAFT3 | 40 | 5153 | 2021-07-09 | 2021-08-19 | 0% | 40 |  |  | 5153 | 5153 | 0
S295000 | (Warm Piping System) Pressure and leak check | PROF3 AD.PROF3 AD | 32 | 4295 | 2022-04-13 | 2022-04-19 | 0% | 32 |  |  | 4295 | 4295 | 0
S295000 | (Warm Piping System) Pressure and leak check | TECH3 AD.TECH3 AD | 32 | 3874 | 2022-04-13 | 2022-04-19 | 0% | 32 |  |  | 3874 | 3874 | 0
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | PROF3 AD.PROF3 AD | 20 | 2684 | 2022-01-26 | 2022-02-08 | 0% | 20 |  |  | 2684 | 2684 | 0
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | TECH3 AD.TECH3 AD | 64 | 7749 | 2022-01-26 | 2022-02-08 | 0% | 64 |  |  | 7749 | 7749 | 0
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | PROF3 AD.PROF3 AD | 32 | 4295 | 2022-04-20 | 2022-04-26 | 0% | 32 |  |  | 4295 | 4295 | 0
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | TECH3 AD.TECH3 AD | 32 | 3874 | 2022-04-20 | 2022-04-26 | 0% | 32 |  |  | 3874 | 3874 | 0
S295300 | (Warm Piping System) Vacuum Pumping System installation | PROF3 AD.PROF3 AD | 8 | 1074 | 2022-01-26 | 2022-02-01 | 0% | 8 |  |  | 1074 | 1074 | 0
S295300 | (Warm Piping System) Vacuum Pumping System installation | TECH3 AD.TECH3 AD | 38 | 4601 | 2022-01-26 | 2022-02-01 | 0% | 38 |  |  | 4601 | 4601 | 0
S294860 | (Warm Piping System) Assembly hall work on Platform | PROF3 AD.PROF3 AD | 18 | 2416 | 2022-01-04 | 2022-01-25 | 0% | 18 |  |  | 2416 | 2416 | 0
S294860 | (Warm Piping System) Assembly hall work on Platform | TECH3 AD.TECH3 AD | 90 | 10896 | 2022-01-04 | 2022-01-25 | 0% | 90 |  |  | 10896 | 10896 | 0
S294860 | (Warm Piping System) Assembly hall work on Platform | CRAFT3.CRAFT3 | 20 | 2654 | 2022-01-04 | 2022-01-25 | 0% | 20 |  |  | 2654 | 2654 | 0
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | PROF3 AD.PROF3 AD | 18 | 2416 | 2022-03-30 | 2022-04-19 | 0% | 18 |  |  | 2416 | 2416 | 0
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | TECH3 AD.TECH3 AD | 90 | 10896 | 2022-03-30 | 2022-04-19 | 0% | 90 |  |  | 10896 | 10896 | 0
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | CRAFT3.CRAFT3 | 20 | 2654 | 2022-03-30 | 2022-04-19 | 0% | 20 |  |  | 2654 | 2654 | 0
2.02.03.04 Cryo Controls Hardware
2.02.03.04.01 Engineering and Design
S295500 | (Controls Hardware) Wire diagram drawings | TECH3 AD.TECH3 AD | 128 | 14608 | 19-Apr-21 A | 2021-09-28 | 25% | 96 |  |  | 10956 | 10956 | 0
S295600 | (Controls Hardware) Power distribution drawings | TECH3 AD.TECH3 AD | 40 | 4565 | 15-Feb-21 A | 2021-10-27 | 25% | 30 |  |  | 3423.75 | 3423.75 | 0
S295700 | (Controls Hardware) I/O list table | PROF3 AD.PROF3 AD | 48 | 6072 | 07-Aug-20 A | 2021-07-23 | 90% | 4.8 |  |  | 607.2 | 607.2 | 0
S295700 | (Controls Hardware) I/O list table | TECH3 AD.TECH3 AD | 48 | 5478 | 07-Aug-20 A | 2021-07-23 | 90% | 4.8 |  |  | 547.8 | 547.8 | 0
S295401 | (Controls Hardware) Cryo instrument and equipment specifications 70% | PROF3 AD.PROF3 AD | 84 | 10627 | 01-Oct-19 A | 2021-07-28 | 91% | 7.56 |  |  | 956.43 | 956.43 | 0
S295401 | (Controls Hardware) Cryo instrument and equipment specifications 70% | PROF4 AD.PROF4 AD | 84 | 12370 | 01-Oct-19 A | 2021-07-28 | 91% | 7.56 |  |  | 1113.3 | 1113.3 | 0
2.02.03.04.02 Procurement
S295800 | (Cryo Controls Hardware procurement) PLC I/O cards & expansion chassis Labor | PROF3 AD.PROF3 AD | 15 | 1898 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S296000 | (Cryo Controls Hardware procurement) Rack components Labor | PROF3 AD.PROF3 AD | 4 | 506 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S296200 | (Cryo Controls Hardware procurement) Lakeshore Temperature Controller/conditioners Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 07-Jul-20 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S296400 | (Cryo Controls Hardware procurement) Lakeshore Temperature sensors Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 01-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S296600 | (Cryo Controls Hardware procurement) SC level probes Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 01-Oct-20 A | 2021-08-27 | 50% | 6 |  |  | 759 | 759 | 0
S296800 | (Cryo Controls Hardware procurement) Pressure transmitters Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 12-Jun-20 A | 15-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S297000 | (Cryo Controls Hardware procurement) Flowmeters Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 01-Dec-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S297200 | (Cryo Controls Hardware procurement) Vacuum gages and cables Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 04-Jan-21 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S297500 | (Cryo Controls Hardware procurement) 32 conductor cables, IP8 to 1008B racks Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 02-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S297600 | (Cryo Controls Hardware procurement) 8 conductor cables, IP8 to 1008B racks Labor | PROF3 AD.PROF3 AD | 12 | 1518 | 22-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S297800 | (Cryo Controls Hardware procurement) Heaters 480VAC Labor | PROF3 AD.PROF3 AD | 14 | 1824 | 22-Mar-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S298000 | (Cryo Controls Hardware procurement) Heater UL listed Control Panel Labor | PROF3 AD.PROF3 AD | 14 | 1824 | 15-Jun-20 A | 18-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S298200 | (Cryo Controls Hardware procurement) Switch, 480 VAC Labor | PROF3 AD.PROF3 AD | 5 | 633 | 2021-07-26 | 2021-08-27 | 0% | 5 |  |  | 633 | 633 | 0
S298400 | (Cryo Controls Hardware procurement) Network switch and Ethernet fiber drop Labor | PROF3 AD.PROF3 AD | 5 | 633 | 03-May-21 A | 24-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S298600 | (Cryo Controls Hardware procurement) Cable tray and supports Labor | PROF3 AD.PROF3 AD | 46 | 5819 | 22-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S295900 | (Cryo Controls Hardware procurement) PLC I/O cards & expansion chassis M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 7500 | 8534 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S296100 | (Cryo Controls Hardware procurement) Rack components M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 6000 | 6828 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S296300 | (Cryo Controls Hardware procurement) Lakeshore Temperature Controller/conditioners M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 5000 | 5690 | 07-Jul-20 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S296500 | (Cryo Controls Hardware procurement) Lakeshore Temperature sensors M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 22000 | 25034 | 01-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S296700 | (Cryo Controls Hardware procurement) SC level probes M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3000 | 3414 | 01-Oct-20 A | 2021-08-27 | 50% | 1500 |  |  | 1707 | 1707 | 0
S296900 | (Cryo Controls Hardware procurement) Pressure transmitters M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 6400 | 7283 | 12-Jun-20 A | 15-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S297100 | (Cryo Controls Hardware procurement) Flowmeters M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 4600 | 5234 | 01-Dec-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S297300 | (Cryo Controls Hardware procurement) Vacuum gages and cables M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 6000 | 6828 | 04-Jan-21 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S297400 | (Cryo Controls Hardware procurement) 32 conductor cables, IP8 to 1008B racks M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 16000 | 18207 | 02-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S297700 | (Cryo Controls Hardware procurement) 8 conductor cables, IP8 to 1008B racks M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 6200 | 7055 | 22-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S297900 | (Cryo Controls Hardware procurement) Heaters 480VAC M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 17000 | 19732 | 22-Mar-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S298100 | (Cryo Controls Hardware procurement) Heater UL listed Control Panel M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 18000 | 20892 | 15-Jun-20 A | 18-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S298300 | (Cryo Controls Hardware procurement) Switch, 480 VAC M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1220 | 1388 | 2021-07-26 | 2021-08-27 | 0% | 1220 |  |  | 1388 | 1388 | 0
S298500 | (Cryo Controls Hardware procurement) Network switch and Ethernet fiber drop M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3500 | 3983 | 03-May-21 A | 24-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S298700 | (Cryo Controls Hardware procurement) Cable tray and supports M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 4000 | 4552 | 22-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S298800 | (Cryo Controls Hardware Procurement) 32 conductor cable LN2 | Purch 1st $2M.Material (Purchase (1st $2M) | 6500 | 7397 | 20-Jul-20 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S298900 | (Cryo Controls Hardware Procurement) Plastic general 32 conductor connectors (pairs) | Purch 1st $2M.Material (Purchase (1st $2M) | 300 | 341 | 01-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S299000 | (Cryo Controls Hardware Procurement) Acopian 24V power Supply | Purch 1st $2M.Material (Purchase (1st $2M) | 2000 | 2276 | 03-Aug-20 A | 25-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S299100 | (Cryo Controls Hardware Procurement) +/- 15 volt Power Supply | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 569 | 01-Oct-20 A | 26-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S299200 | (Cryo Controls Hardware Procurement) 72 inch enclosure | Purch 1st $2M.Material (Purchase (1st $2M) | 1500 | 1707 | 03-Aug-20 A | 25-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S299300 | (Cryo Controls Hardware Procurement) LN2 Conduit/couplings | Purch 1st $2M.Material (Purchase (1st $2M) | 3400 | 3869 | 01-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S299400 | (Cryo Controls Hardware Procurement) Turbo pump and Controller | Purch 1st $2M.Material (Purchase (1st $2M) | 25000 | 28448 | 01-Dec-20 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.03.04.03 Installation: Cryo Controls Hardware
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | PROF3 AD.PROF3 AD | 48 | 6072 | 2021-08-30 | 2021-09-27 | 0% | 48 |  |  | 6072 | 6072 | 0
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | TECH3 AD.TECH3 AD | 280 | 31954 | 2021-08-30 | 2021-09-27 | 0% | 280 |  |  | 31954 | 31954 | 0
S299700 | (Cryo Controls Hardware) Rack install | PROF3 AD.PROF3 AD | 4 | 506 | 2021-09-28 | 2021-10-04 | 0% | 4 |  |  | 506 | 506 | 0
S299700 | (Cryo Controls Hardware) Rack install | TECH3 AD.TECH3 AD | 13 | 1484 | 2021-09-28 | 2021-10-04 | 0% | 13 |  |  | 1484 | 1484 | 0
S299800 | (Cryo Controls Hardware) Cable pulling | TECH3 AD.TECH3 AD | 52 | 6087 | 2021-10-05 | 2021-12-17 | 0% | 52 |  |  | 6087 | 6087 | 0
S299800 | (Cryo Controls Hardware) Cable pulling | CRAFT3.CRAFT3 | 150 | 19245 | 2021-10-05 | 2021-12-17 | 0% | 150 |  |  | 19245 | 19245 | 0
S299900 | (Cryo Controls Hardware) Cable termination | TECH3 AD.TECH3 AD | 160 | 19372 | 2022-02-09 | 2022-03-09 | 0% | 160 |  |  | 19372 | 19372 | 0
S300000 | (Cryo Controls Hardware) Check out continuity | TECH3 AD.TECH3 AD | 40 | 4843 | 2022-03-31 | 2022-04-13 | 0% | 40 |  |  | 4843 | 4843 | 0
S300100 | (Cryo Controls Hardware) Heater Control Panel Install | CRAFT3.CRAFT3 | 32 | 4122 | 15-Jun-21 A | 2022-01-13 | 50% | 16 |  |  | 2061 | 2061 | 0
S300200 | (Cryo Controls Hardware) Heater 480VAC wiring | CRAFT3.CRAFT3 | 480 | 63690 | 2022-02-09 | 2022-02-15 | 0% | 480 |  |  | 63690 | 63690 | 0
S300400 | (Cryo Controls Hardware) Heater I/O wiring, temp sensors | TECH3 AD.TECH3 AD | 16 | 1937 | 2022-03-03 | 2022-03-09 | 0% | 16 |  |  | 1937 | 1937 | 0
S300500 | (Cryo Controls Hardware) Wire up instruments and control valves | TECH3 AD.TECH3 AD | 96 | 11623 | 2022-03-10 | 2022-03-30 | 0% | 96 |  |  | 11623 | 11623 | 0
S300300 | (Cryo Controls Hardware) Insulating vacuum roughing pumps 480VAC Breaker install and 480V wiring to roughing pumps | CRAFT3.CRAFT3 | 8 | 1062 | 15-Jun-21 A | 2022-03-21 | 50% | 4 |  |  | 531 | 531 | 0
2.02.03.05 Cryo Controls Software
S300700 | (Cryo Controls Hardware) Control Logic eng document revision by Cryo process engineering | PROF3 AD.PROF3 AD | 240 | 30362 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S300700 | (Cryo Controls Hardware) Control Logic eng document revision by Cryo process engineering | PROF4 AD.PROF4 AD | 240 | 35344 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | PROF3 AD.PROF3 AD | 8 | 1012 | 03-Aug-20 A | 2021-08-27 | 60% | 3.2 |  |  | 404.8 | 404.8 | 0
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | PROF4 AD.PROF4 AD | 8 | 1178 | 03-Aug-20 A | 2021-08-27 | 60% | 3.2 |  |  | 471.2 | 471.2 | 0
S300900 | (Cryo Controls Hardware) Built HMI operator screens | PROF3 AD.PROF3 AD | 576 | 75056 | 08-Mar-21 A | 2021-09-20 | 45% | 316.8 |  |  | 41280.8 | 41280.8 | 0
S300900 | (Cryo Controls Hardware) Built HMI operator screens | PROF4 AD.PROF4 AD | 72 | 10921 | 08-Mar-21 A | 2021-09-20 | 45% | 39.6 |  |  | 6006.55 | 6006.55 | 0
S301000 | (Cryo Controls Hardware) PLC programming | PROF3 AD.PROF3 AD | 576 | 77132 | 13-Jul-20 A | 2021-08-27 | 92% | 46.08 |  |  | 6170.56 | 6170.56 | 0
S301000 | (Cryo Controls Hardware) PLC programming | PROF4 AD.PROF4 AD | 72 | 11223 | 13-Jul-20 A | 2021-08-27 | 92% | 5.76 |  |  | 897.84 | 897.84 | 0
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | PROF3 AD.PROF3 AD | 120 | 16106 | 2022-04-14 | 2022-04-27 | 0% | 120 |  |  | 16106 | 16106 | 0
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | TECH3 AD.TECH3 AD | 120 | 14529 | 2022-04-14 | 2022-04-27 | 0% | 120 |  |  | 14529 | 14529 | 0
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | PROF4 AD.PROF4 AD | 24 | 3750 | 2022-04-14 | 2022-04-27 | 0% | 24 |  |  | 3750 | 3750 | 0
2.02.04 Magnet Power Supplies/Controls/Quench Protection
S1000119 | Actuals - Labor - sPHENIX Magnet FY17 16719 | Actual Labor.Actual Labor | 89 | 14920 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000199 | Actuals - Labor - sPHENIX Magnet FY18 16719 | Actual Labor.Actual Labor | 41 | 6767 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1001399 | Actuals - Labor - sPHENIX Magnet FY19 M8 16719 | Actual Labor.Actual Labor | 69 | 11595 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004520 | Actuals - Labor FY19 Jun-Sep 16719 | Actual Labor.Actual Labor | 109 | 18242 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004560 | Actuals - NonLabor FY19 Jun-Sep 16719 | Actual NonLabor.Actual Nonlabor | 512 | 565 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.04.01 AC/DC Power Distribution
2.02.04.01.01 Design AC/DC Power Distribution
S301800 | Magnet: 1008 IR Design Quench Detector AC Power Hook-up | PROF4 AD.PROF4 AD | 16 | 2356 | 12-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S301610 | Magnet: 1008 IR Design Power Supply AC and Quench Detector Power Distribution Split | PROF4 AD.PROF4 AD | 30 | 4418 | 01-Oct-19 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S301710 | Magnet: 1008 IR Design Power Supply AC Power Hook-up Split | PROF4 AD.PROF4 AD | 18 | 2651 | 12-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S301910 | Magnet: 1008 IR Design Power Supply, Magnet, Dump Resistor DC Cabling Split | PROF4 AD.PROF4 AD | 12 | 1767 | 12-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S302010 | Magnet: Design Cable Tray and Supports for Power and Signal Distribution Split | PROF4 AD.PROF4 AD | 60 | 8836 | 23-Nov-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S302101 | Magnet: Design DC Flags 50% | PROF4 AD.PROF4 AD | 5 | 736 | 01-Jul-21* | 2021-07-28 | 0% | 5 |  |  | 736 | 736 | 0
2.02.04.01.02 Procure PS System Connections
S302500 | Magnet: Order AC Power Distribution Parts Labor | PROF4 AD.PROF4 AD | 8 | 1178 | 20-May-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S302700 | Magnet: Order Power Supply, Magnet, Dump Resistor DC Cabling and Interconnects Labor | PROF4 AD.PROF4 AD | 16 | 2356 | 15-Dec-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S302800 | Magnet: Fabricate DC flags | CRAFT3.CRAFT3 | 40 | 5003 | 22-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S303000 | Magnet: Order Cable Tray and Supports M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 2000 | 2276 | 24-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S302300 | Magnet: Delivery Power Supply and Quench Detector AC Power Cables and Interconnects M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 4000 | 4552 | 25-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S302400 | Magnet: Delivery Power Supply, Magnet, Dump Resistor DC Cabling and Interconnects M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 21000 | 23896 | 23-Nov-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S302201 | Magnet: Delivery AC Power Distribution Parts M&S_50% | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 | 11379 | 02-Dec-19 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S302601 | Magnet: Order Power Supply and Quench Detector AC Power Cables and Interconnects Labor 95% | PROF4 AD.PROF4 AD | 8 | 1119 | 01-Nov-19 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S302901 | Magnet: Order Cable Tray and Supports_85% | PROF4 AD.PROF4 AD | 68 | 10014 | 24-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.04.01.03 Install PS AC/DC Cabling
S303100 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008B | PROF4 AD.PROF4 AD | 40 | 5891 | 22-Sep-20 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S303100 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008B | CRAFT3.CRAFT3 | 160 | 20011 | 22-Sep-20 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S303400 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B | PROF4 AD.PROF4 AD | 16 | 2356 | 22-Sep-20 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S303400 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B | TECH3 AD.TECH3 AD | 160 | 18260 | 22-Sep-20 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S303400 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B | CRAFT3.CRAFT3 | 220 | 27516 | 22-Sep-20 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S303200 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution in 1008B to 1008IR | PROF4 AD.PROF4 AD | 60 | 8836 | 16-Sep-20 A | 2021-09-08 | 30% | 42 |  |  | 6185.2 | 6185.2 | 0
S303200 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution in 1008B to 1008IR | CRAFT3.CRAFT3 | 240 | 30017 | 16-Sep-20 A | 2021-09-08 | 30% | 168 |  |  | 21011.9 | 21011.9 | 0
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | PROF4 AD.PROF4 AD | 60 | 8836 | 2021-09-09 | 2021-09-29 | 0% | 60 |  |  | 8836 | 8836 | 0
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | TECH3 AD.TECH3 AD | 240 | 27389 | 2021-09-09 | 2021-09-29 | 0% | 240 |  |  | 27389 | 27389 | 0
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | CRAFT3.CRAFT3 | 300 | 37521 | 2021-09-09 | 2021-09-29 | 0% | 300 |  |  | 37521 | 37521 | 0
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | CRAFT3.CRAFT3 | 240 | 30017 | 2021-09-09 | 2021-09-29 | 0% | 240 |  |  | 30017 | 30017 | 0
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | PROF4 AD.PROF4 AD | 60 | 8836 | 2021-09-09 | 2021-09-29 | 0% | 60 |  |  | 8836 | 8836 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | PROF4 AD.PROF4 AD | 40 | 6249 | 2022-01-04 | 2022-01-18 | 0% | 40 |  |  | 6249 | 6249 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | TECH3 AD.TECH3 AD | 160 | 19372 | 2022-01-04 | 2022-01-18 | 0% | 160 |  |  | 19372 | 19372 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | CRAFT3.CRAFT3 | 220 | 29191 | 2022-01-04 | 2022-01-18 | 0% | 220 |  |  | 29191 | 29191 | 0
2.02.04.02 Power Supply
2.02.04.02.01 Install Power Supply
S303900 | Magnet Power Supply Installation: Move Power Supply to location | CRAFT3.CRAFT3 | 16 | 2001 | 18-Aug-20 A | 27-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S304000 | Magnet Power Supply Installation: Connect AC Power to Power Supply | CRAFT3.CRAFT3 | 32 | 4002 | 22-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S304000 | Magnet Power Supply Installation: Connect AC Power to Power Supply | PROF4 AD.PROF4 AD | 5 | 736 | 22-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S304100 | Magnet Power Supply Installation: Connect DC Cabling to Power Supply, Dump Resistor, Magnet | PROF4 AD.PROF4 AD | 8 | 1178 | 11-Aug-20 A | 17-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S304100 | Magnet Power Supply Installation: Connect DC Cabling to Power Supply, Dump Resistor, Magnet | TECH3 AD.TECH3 AD | 80 | 9130 | 11-Aug-20 A | 17-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | PROF4 AD.PROF4 AD | 7 | 1031 | 24-May-21 A | 2021-08-31 | 10% | 6.3 |  |  | 927.9 | 927.9 | 0
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | TECH3 AD.TECH3 AD | 32 | 3652 | 24-May-21 A | 2021-08-31 | 10% | 28.8 |  |  | 3286.8 | 3286.8 | 0
S305000 | Magnet Power Supply Installation: Power Supply Testing | PROF4 AD.PROF4 AD | 80 | 12499 | 2022-04-06 | 2022-04-19 | 0% | 80 |  |  | 12499 | 12499 | 0
S305000 | Magnet Power Supply Installation: Power Supply Testing | TECH3 AD.TECH3 AD | 80 | 9686 | 2022-04-06 | 2022-04-19 | 0% | 80 |  |  | 9686 | 9686 | 0
S304400 | Magnet Power Supply Installation: Cooling Water Installation 1008B | TECH3 AD.TECH3 AD | 70 | 7989 | 03-Aug-20 A | 24-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S304500 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008B L | TECH3 AD.TECH3 AD | 70 | 7989 | 03-Aug-20 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | TECH3 AD.TECH3 AD | 70 | 8475 | 2022-03-30 | 2022-04-05 | 0% | 70 |  |  | 8475 | 8475 | 0
S304600 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008B M&S | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 8000 | 8925 | 03-Aug-20 A | 24-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S304800 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR M&S | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 3137 | 3500 | 2022-03-30 | 2022-04-05 | 0% | 3137 |  |  | 3500 | 3500 | 0
S304310 | Magnet Power Supply Installation: Cooling Water Design Split | PROF4 AD.PROF4 AD | 64 | 9425 | 01-Nov-19 A | 28-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S305110 | Magnet Power Supply Installation: Documentation Split | TECH3 AD.TECH3 AD | 216 | 24795 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S305110 | Magnet Power Supply Installation: Documentation Split | PROF5 AD.PROF5 AD | 108 | 18475 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S304901 | Magnet Power Supply Installation: Design and Test Control Interface update software_50% | PROF4 AD.PROF4 AD | 60 | 8836 | 13-Nov-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S304901 | Magnet Power Supply Installation: Design and Test Control Interface update software_50% | PROF5 AD.PROF5 AD | 30 | 5102 | 13-Nov-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.04.03 Quench Detector
2.02.04.03.02 Procure Quench Detector System Connections
S306501 | Magnet: Order Quench Detector Signal Cables and Interconnects M&S_90% | Purch 1st $2M.Material (Purchase (1st $2M) | 1800 | 2048 | 20-Nov-19 A | 02-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.04.03.02.01 Install Quench Detector
S306900 | Magnet: Move Quench Detector to location | CRAFT3.CRAFT3 | 16 | 2001 | 14-May-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S307000 | Magnet: Connect AC Power to Quench Detector | CRAFT3.CRAFT3 | 24 | 3002 | 12-Jan-21 A | 05-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S307100 | Magnet: Connect Signal Interconnections | TECH3 AD.TECH3 AD | 80 | 9130 | 08-Mar-21 A | 2021-08-31 | 30% | 56 |  |  | 6391 | 6391 | 0
S307200 | Magnet: Quench Detector Testing | TECH3 AD.TECH3 AD | 80 | 9404 | 2022-04-13 | 2022-04-19 | 0% | 80 |  |  | 9404 | 9404 | 0
S307200 | Magnet: Quench Detector Testing | PROF5 AD.PROF5 AD | 80 | 14013 | 2022-04-13 | 2022-04-19 | 0% | 80 |  |  | 14013 | 14013 | 0
S306800 | Magnet: Disconnect Quench Detector from Test System in 912 | TECH3 AD.TECH3 AD | 8 | 913 | 13-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S307311 | Magnet: Quench Detector Documentation Split_85% | TECH3 AD.TECH3 AD | 54 | 6226 | 01-Oct-19 A | 2021-10-29 | 90% | 5.4 |  |  | 622.6 | 622.6 | 0
S307311 | Magnet: Quench Detector Documentation Split_85% | PROF5 AD.PROF5 AD | 27 | 4639 | 01-Oct-19 A | 2021-10-29 | 90% | 2.7 |  |  | 463.9 | 463.9 | 0
2.02.05 Magnet Field Measurements
S1000239 | Actuals - Labor - sPHENIX Magnet FY18 16720 | Actual Labor.Actual Labor | 6 | 925 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1001439 | Actuals - Labor - sPHENIX Magnet FY19 M8 16720 | Actual Labor.Actual Labor | 38 | 6430 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1001479 | Actuals - NonLabor - sPHENIX Magnet FY19 M8 16720 | Actual NonLabor.Actual Nonlabor | 1217 | 1343 | 01-Oct-18 A | 30-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004600 | Actuals - Labor FY19 Jun-Sep 16720 | Actual Labor.Actual Labor | 13 | 2145 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.05.01 Magnet Field Measurements Engineering and Design, Field Studies and Stress Analysis
S307600 | Magnet Field Measurements: Design mounts for probes to monitor field - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4565 | 03-Feb-20 A | 14-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S307700 | Magnet Field Measurements: Design readout for probes to monitor field - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4565 | 18-Feb-20 A | 24-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S307610 | Magnet Field Measurements: Design mounts for probes to monitor field - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1178 | 03-Feb-20 A | 14-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S307710 | Magnet Field Measurements: Design readout for probes to monitor field - CA-D Resource(s) | PROF4 AD.PROF4 AD | 4 | 589 | 18-Feb-20 A | 24-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S307511 | Magnet Field Measurements: Setup a detailed 3D model of the coil, return yoke and internal calorimeters FY19 Split_60% | SCI3 PO.SCI3 PO | 19 | 3304 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S307511 | Magnet Field Measurements: Setup a detailed 3D model of the coil, return yoke and internal calorimeters FY19 Split_60% | TECH3 PO D.TECH3 PO D | 6 | 685 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S307921 | Magnet Field Measurements: Perform Magnet Assembly Stress Analysis FY19 - CA-D Resource(s) Split_70% | PROF4 AD.PROF4 AD | 48 | 7010 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S307922 | Final Field Calculations Pre-measurement - Phys | SCI4 PO.SCI 4 PO | 20 | 4229 | 21-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S307923 | Final Field Calculations Pre-measurement - CAD | PROF4 AD.PROF4 AD | 60 | 9073 | 21-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication
S308611 | Specify and test probes for field monitoring | SCI4 PO.SCI 4 PO | 16 | 3393 | 01-Oct-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308611 | Specify and test probes for field monitoring | PROF4 PO E.PROF4 PO E | 16 | 2427 | 01-Oct-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308611 | Specify and test probes for field monitoring | PROF4 PO M.PROF4 PO M | 16 | 2427 | 01-Oct-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308613 | Purchase probes for Magnetic Field Measurements | Purch 1st $2M.Material (Purchase (1st $2M) | 7000 | 8125 | 04-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308615 | Develop readout electronics | PROF4 PO E.PROF4 PO E | 90 | 13651 | 30-Oct-20 A | 2021-09-01 | 90% | 9 |  |  | 1365.1 | 1365.1 | 0
S308617 | Calibrate probes | SCI4 PO.SCI 4 PO | 24 | 5090 | 2021-09-02 | 2021-12-01 | 0% | 24 |  |  | 5090 | 5090 | 0
S308617 | Calibrate probes | PROF4 PO E.PROF4 PO E | 24 | 3640 | 2021-09-02 | 2021-12-01 | 0% | 24 |  |  | 3640 | 3640 | 0
S308617 | Calibrate probes | TECH3 PO E.TECH3 PO E | 24 | 2821 | 2021-09-02 | 2021-12-01 | 0% | 24 |  |  | 2821 | 2821 | 0
S308619 | Install probes and readout on TPC | TECH3 PO E.TECH3 PO E | 40 | 4843 | 2022-02-03 | 2022-02-16 | 0% | 40 |  |  | 4843 | 4843 | 0
S308100 | Magnet Field Measurements: Procure NMR probes Labor | PROF4 PO M.PROF4 PO M | 10 | 1473 | 24-Jan-20 A | 20-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308300 | Magnet Field Measurements: Procure NMR probe readout parts Labor | PROF4 PO M.PROF4 PO M | 10 | 1473 | 24-Jan-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308500 | Magnet Field Measurements: Fabricate NMR probe readout parts | SCI3 PO.SCI3 PO | 16 | 2754 | 01-May-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308500 | Magnet Field Measurements: Fabricate NMR probe readout parts | TECH3 PO D.TECH3 PO D | 160 | 18260 | 01-May-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308500 | Magnet Field Measurements: Fabricate NMR probe readout parts | PROF4 PO M.PROF4 PO M | 16 | 2356 | 01-May-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308600 | Magnet Field Measurements: Fabricate NMR probe mounts - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 160 | 18260 | 16-Jan-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308600 | Magnet Field Measurements: Fabricate NMR probe mounts - Physics Resource(s) | SCI3 PO.SCI3 PO | 16 | 2754 | 16-Jan-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308200 | Magnet Field Measurements: Procure NMR probes M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 6000 | 6828 | 24-Jan-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308400 | Magnet Field Measurements: Procure NMR probe readout parts M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 | 1138 | 24-Jan-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308610 | Magnet Field Measurements: Fabricate NMR probe mounts - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 01-May-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-05-26 | 2022-06-09 | 0% | 80 |  |  | 9686 | 9686 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2022-05-26 | 2022-06-09 | 0% | 160 |  |  | 19372 | 19372 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | PROF3 PO E.PROF3 PO E | 80 | 10737 | 2022-05-26 | 2022-06-09 | 0% | 80 |  |  | 10737 | 10737 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | SCI4 PO.SCI 4 PO | 160 | 34952 | 2022-05-26 | 2022-06-09 | 0% | 160 |  |  | 34952 | 34952 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-06-14 | 2022-07-05 | 0% | 80 |  |  | 9686 | 9686 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | SCI4 PO.SCI 4 PO | 160 | 34952 | 2022-06-14 | 2022-07-05 | 0% | 160 |  |  | 34952 | 34952 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | PROF3 PO E.PROF3 PO E | 80 | 10737 | 2022-06-14 | 2022-07-05 | 0% | 80 |  |  | 10737 | 10737 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2022-06-14 | 2022-07-05 | 0% | 160 |  |  | 19372 | 19372 | 0
S309100 | Magnet Field Measurements: Remove Field Mapping Equipment | TECH3 PO M.TECH3 PO M | 40 | 4843 | 2022-07-06 | 2022-07-07 | 0% | 40 |  |  | 4843 | 4843 | 0
S309100 | Magnet Field Measurements: Remove Field Mapping Equipment | TECH3 PO E.TECH3 PO E | 80 | 9686 | 2022-07-06 | 2022-07-07 | 0% | 80 |  |  | 9686 | 9686 | 0
S309005 | Magnet Field Measurements: Perform Magnetic Survey of as-build structure in IR | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-06-14 | 2022-07-05 | 0% | 80 |  |  | 9686 | 9686 | 0
S309005 | Magnet Field Measurements: Perform Magnetic Survey of as-build structure in IR | SCI4 PO.SCI 4 PO | 160 | 34952 | 2022-06-14 | 2022-07-05 | 0% | 160 |  |  | 34952 | 34952 | 0
S309005 | Magnet Field Measurements: Perform Magnetic Survey of as-build structure in IR | PROF3 PO E.PROF3 PO E | 80 | 10737 | 2022-06-14 | 2022-07-05 | 0% | 80 |  |  | 10737 | 10737 | 0
S309005 | Magnet Field Measurements: Perform Magnetic Survey of as-build structure in IR | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2022-06-14 | 2022-07-05 | 0% | 160 |  |  | 19372 | 19372 | 0
S308625 | Complete MOU with Vendor | SCI4 PO.SCI 4 PO | 8 | 1697 | 22-Feb-21 A | 2021-10-05 | 20% | 6.4 |  |  | 1357.6 | 1357.6 | 0
S308621 | Conceptual design of mapping campaign | SCI4 PO.SCI 4 PO | 32 | 6787 | 01-Oct-20 A | 2021-09-29 | 60% | 12.8 |  |  | 2714.8 | 2714.8 | 0
S308623 | Develop mapping plan with Vendor | SCI4 PO.SCI 4 PO | 100 | 21208 | 30-Oct-20 A | 2021-11-30 | 50% | 50 |  |  | 10604 | 10604 | 0
S308627 | Place contract with Vendor (Procurement string, $70K obligated at Contract award, paid when mapped?) | Purch 1st $2M.Material (Purchase (1st $2M) | 63000 | 73123 | 2021-09-30 | 2022-02-28 | 0% | 63000 |  |  | 73123 | 73123 | 0
S308629 | Complete mechanical and electrical design for mapping | PROF4 PO M.PROF4 PO M | 60 | 9101 | 23-Nov-20 A | 2021-10-01 | 35% | 39 |  |  | 5915.65 | 5915.65 | 0
S308629 | Complete mechanical and electrical design for mapping | TECH3 PO D.TECH3 PO D | 30 | 3526 | 23-Nov-20 A | 2021-10-01 | 35% | 19.5 |  |  | 2291.9 | 2291.9 | 0
S308631 | Review mapping plan | PROF4 PO M.PROF4 PO M | 16 | 2427 | 2021-09-30 | 2021-10-06 | 0% | 16 |  |  | 2427 | 2427 | 0
S308631 | Review mapping plan | TECH3 PO D.TECH3 PO D | 16 | 1881 | 2021-09-30 | 2021-10-06 | 0% | 16 |  |  | 1881 | 1881 | 0
S308631 | Review mapping plan | SCI4 PO.SCI 4 PO | 10 | 2121 | 2021-09-30 | 2021-10-06 | 0% | 10 |  |  | 2121 | 2121 | 0
S308633 | Construct mapping support (mechanical and electrical) | TECH3 PO M.TECH3 PO M | 32 | 3761 | 08-Mar-21 A | 2021-10-21 | 5% | 30.4 |  |  | 3572.95 | 3572.95 | 0
S309110 | Receive report from CERN, incorporate into analysis | SCI4 PO.SCI 4 PO | 16 | 3495 | 08-Jul-22* | 2022-08-04 | 0% | 16 |  |  | 3495 | 3495 | 0
S308700 | Magnet Field Measurements: Run 3D field simulations and construct field and force maps - Physics Resource(s) | SCI3 PO.SCI3 PO | 40 | 6884 | 24-Jan-20 A | 24-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S308710 | Magnet Field Measurements: Run 3D field simulations and construct field and force maps - CA-D Resource(s) | SCI3 AD.SCI3 AD | 40 | 6884 | 24-Jan-20 A | 24-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.03 Carriage and Structural Components
2.03.01 Cradle Carriage
S310400 | Carriage Cradle - Prepare Procurement Package(s) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 24 | 2739 | 01-Oct-19 A | 15-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310400 | Carriage Cradle - Prepare Procurement Package(s) - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2739 | 01-Oct-19 A | 15-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310900 | Carriage Cradle - Vendor Selection - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 36 | 4108 | 20-Mar-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S310900 | Carriage Cradle - Vendor Selection - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 72 | 8217 | 20-Mar-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311100 | Carriage Cradle - BNL Oversight - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 10 | 1156 | 06-May-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S311100 | Carriage Cradle - BNL Oversight - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 40 | 4623 | 06-May-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S311300 | Carriage Cradle - Delivery Acceptance - Physics Resource(s) - Labor | TECH3 PO D.TECH3 PO D | 16 | 1826 | 02-Sep-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311300 | Carriage Cradle - Delivery Acceptance - Physics Resource(s) - Labor | TECH3 PO M.TECH3 PO M | 80 | 9130 | 02-Sep-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S310500 | Carriage Cradle - Procurement Readiness Review - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 12 | 1369 | 18-Nov-19 A | 22-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310500 | Carriage Cradle - Procurement Readiness Review - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2739 | 18-Nov-19 A | 22-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S311500 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 80 | 9130 | 14-May-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311600 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 80 | 9130 | 14-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311800 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 15 | 1712 | 18-Oct-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312000 | CC Drive & Alignment System - Assembly & Detail Drawings - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 240 | 27389 | 01-Apr-20 A | 01-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311900 | CC Drive & Alignment System - Design Carriage Controls & Limits | PROF4 PO E.PROF4 PO E | 120 | 17672 | 02-Dec-19 A | 01-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S313300 | CC Seismic Restraints - Engineer & Analysis | PROF5 AD.PROF5 AD | 120 | 20408 | 28-Oct-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S313300 | CC Seismic Restraints - Engineer & Analysis | PROF4 AD.PROF4 AD | 240 | 35344 | 28-Oct-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S313400 | CC Seismic Restraints - Assembly & Detail Drawings - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 120 | 13695 | 17-Dec-19 A | 2021-07-16 | 95% | 6 |  |  | 684.75 | 684.75 | 0
S313500 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 2021-07-19 | 2021-07-23 | 0% | 20 |  |  | 2282 | 2282 | 0
S313600 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 2021-07-26 | 2021-07-30 | 0% | 20 |  |  | 2282 | 2282 | 0
S313700 | CC Seismic Restraints - Prepare Procurement Package - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 2021-08-02 | 2021-08-06 | 0% | 20 |  |  | 2282 | 2282 | 0
S313800 | CC Seismic Restraints - Procurement Readiness Review - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 2021-08-09 | 2021-08-13 | 0% | 20 |  |  | 2282 | 2282 | 0
S310600 | Carriage Cradle - Provide Requirement to Procurement | PROF5 AD.PROF5 AD | 8 | 1361 | 25-Nov-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310800 | Carriage Cradle - Vendor Responses - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 36 | 4108 | 08-Jan-20 A | 19-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312100 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4565 | 14-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312300 | CC Drive & Alignment System - Prepare Procurement Package - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 28-Jul-20 A | 21-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312400 | CC Drive & Alignment System - Procurement Readiness Review - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 01-Oct-20 A | 07-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312200 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4565 | 21-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312800 | CC Drive & Alignment System - Vendor Selection - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 18 | 2054 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312800 | CC Drive & Alignment System - Vendor Selection - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 36 | 4108 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S313000 | CC Drive & Alignment System - BNL Oversight - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 10 | 1164 | 03-Nov-20 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S313000 | CC Drive & Alignment System - BNL Oversight - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 40 | 4656 | 03-Nov-20 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S313200 | CC Drive & Alignment System - Delivery Acceptance - Physics Resource(s) - Labor | TECH3 PO D.TECH3 PO D | 16 | 1881 | 12-Apr-21 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S313200 | CC Drive & Alignment System - Delivery Acceptance - Physics Resource(s) - Labor | TECH3 PO M.TECH3 PO M | 80 | 9404 | 12-Apr-21 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S312500 | CC Drive & Alignment System - Provide Requirement to Procurement | PROF5 AD.PROF5 AD | 8 | 1361 | 08-Oct-20 A | 15-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312700 | CC Drive & Alignment System - Vendor Responses - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 18 | 2054 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 18 | 2054 | 2021-10-13 | 2021-11-24 | 0% | 18 |  |  | 2054 | 2054 | 0
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 36 | 4108 | 2021-10-13 | 2021-11-24 | 0% | 36 |  |  | 4108 | 4108 | 0
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 10 | 1160 | 2021-11-30 | 2022-08-16 | 0% | 10 |  |  | 1160 | 1160 | 0
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 40 | 4642 | 2021-11-30 | 2022-08-16 | 0% | 40 |  |  | 4642 | 4642 | 0
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | TECH3 PO D.TECH3 PO D | 4 | 470 | 2022-08-17 | 2022-08-23 | 0% | 4 |  |  | 470 | 470 | 0
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | TECH3 PO M.TECH3 PO M | 20 | 2351 | 2022-08-17 | 2022-08-23 | 0% | 20 |  |  | 2351 | 2351 | 0
S313900 | CC Seismic Restraints - Provide Requirement to Procurement | PROF5 AD.PROF5 AD | 8 | 1361 | 2021-08-16 | 2021-08-20 | 0% | 8 |  |  | 1361 | 1361 | 0
S314100 | CC Seismic Restraints - Vendor Responses - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 18 | 2054 | 2021-08-30 | 2021-10-12 | 0% | 18 |  |  | 2054 | 2054 | 0
S315900 | Steel Track Modifications - BNL Oversight Construction - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 80 | 9130 | 18-Nov-19 A | 31-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S316000 | Steel Track Modifications - Finish Track Work M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 20000 | 23214 | 15-Oct-20 A | 2021-08-30 | 95% | 1000 |  |  | 1160.7 | 1160.7 | 0
S310410 | Carriage Cradle - Prepare Procurement Package(s) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 24 | 3534 | 01-Oct-19 A | 15-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310410 | Carriage Cradle - Prepare Procurement Package(s) - CA-D Resource(s) | PROF5 AD.PROF5 AD | 20 | 3401 | 01-Oct-19 A | 15-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310410 | Carriage Cradle - Prepare Procurement Package(s) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 24 | 2739 | 01-Oct-19 A | 15-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310910 | Carriage Cradle - Vendor Selection - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 2945 | 20-Mar-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S310910 | Carriage Cradle - Vendor Selection - CA-D Resource(s) | PROF5 AD.PROF5 AD | 20 | 3401 | 20-Mar-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S310910 | Carriage Cradle - Vendor Selection - CA-D Resource(s) | TECH3 AD.TECH3 AD | 36 | 4108 | 20-Mar-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311110 | Carriage Cradle - BNL Oversight - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 5966 | 06-May-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S311110 | Carriage Cradle - BNL Oversight - CA-D Resource(s) | PROF5 AD.PROF5 AD | 40 | 6890 | 06-May-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S311110 | Carriage Cradle - BNL Oversight - CA-D Resource(s) | TECH3 AD.TECH3 AD | 10 | 1156 | 06-May-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S311310 | Carriage Cradle - Delivery Acceptance - CA-D Resource(s) - Labor | PROF4 AD.PROF4 AD | 32 | 4712 | 02-Sep-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311310 | Carriage Cradle - Delivery Acceptance - CA-D Resource(s) - Labor | PROF5 AD.PROF5 AD | 8 | 1361 | 02-Sep-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311310 | Carriage Cradle - Delivery Acceptance - CA-D Resource(s) - Labor | TECH3 AD.TECH3 AD | 16 | 1826 | 02-Sep-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S310510 | Carriage Cradle - Procurement Readiness Review - CA-D Resource(s) | PROF4 AD.PROF4 AD | 24 | 3534 | 18-Nov-19 A | 22-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310510 | Carriage Cradle - Procurement Readiness Review - CA-D Resource(s) | TECH3 AD.TECH3 AD | 12 | 1369 | 18-Nov-19 A | 22-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S311510 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - CA-D Resource(s) | PROF4 AD.PROF4 AD | 160 | 23562 | 14-May-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311510 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - CA-D Resource(s) | PROF5 AD.PROF5 AD | 80 | 13605 | 14-May-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311510 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - CA-D Resource(s) | TECH3 AD.TECH3 AD | 80 | 9130 | 14-May-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311610 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - CA-D Resource(s) | PROF4 AD.PROF4 AD | 160 | 23562 | 14-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311610 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - CA-D Resource(s) | PROF5 AD.PROF5 AD | 80 | 13605 | 14-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311610 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - CA-D Resource(s) | TECH3 AD.TECH3 AD | 80 | 9130 | 14-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311810 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 30 | 4418 | 18-Oct-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311810 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - CA-D Resource(s) | PROF5 AD.PROF5 AD | 64 | 10884 | 18-Oct-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311810 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 15 | 1712 | 18-Oct-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312010 | CC Drive & Alignment System - Assembly & Detail Drawings - CA-D Resource(s) | PROF4 AD.PROF4 AD | 120 | 17672 | 01-Apr-20 A | 01-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312010 | CC Drive & Alignment System - Assembly & Detail Drawings - CA-D Resource(s) | PROF5 AD.PROF5 AD | 80 | 13605 | 01-Apr-20 A | 01-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312010 | CC Drive & Alignment System - Assembly & Detail Drawings - CA-D Resource(s) | TECH3 AD.TECH3 AD | 240 | 27389 | 01-Apr-20 A | 01-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S315010 | Steel Track Modifications - Final Design Reviews (Design & Safety) | PROF4 AD.PROF4 AD | 8 | 1178 | 30-Oct-19 A | 31-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S315110 | Steel Track Modifications - Address Action Items from Design & Safety Reviews | PROF3 AD.PROF3 AD | 8 | 1012 | 01-Nov-19 A | 15-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | PROF4 AD.PROF4 AD | 80 | 11781 | 17-Dec-19 A | 2021-07-16 | 95% | 4 |  |  | 589.05 | 589.05 | 0
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | PROF5 AD.PROF5 AD | 40 | 6803 | 17-Dec-19 A | 2021-07-16 | 95% | 2 |  |  | 340.15 | 340.15 | 0
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | TECH3 AD.TECH3 AD | 120 | 13695 | 17-Dec-19 A | 2021-07-16 | 95% | 6 |  |  | 684.75 | 684.75 | 0
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 5891 | 2021-07-19 | 2021-07-23 | 0% | 40 |  |  | 5891 | 5891 | 0
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2282 | 2021-07-19 | 2021-07-23 | 0% | 20 |  |  | 2282 | 2282 | 0
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 5891 | 2021-07-26 | 2021-07-30 | 0% | 40 |  |  | 5891 | 5891 | 0
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | PROF5 AD.PROF5 AD | 20 | 3401 | 2021-07-26 | 2021-07-30 | 0% | 20 |  |  | 3401 | 3401 | 0
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2282 | 2021-07-26 | 2021-07-30 | 0% | 20 |  |  | 2282 | 2282 | 0
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 2945 | 2021-08-02 | 2021-08-06 | 0% | 20 |  |  | 2945 | 2945 | 0
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1361 | 2021-08-02 | 2021-08-06 | 0% | 8 |  |  | 1361 | 1361 | 0
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2282 | 2021-08-02 | 2021-08-06 | 0% | 20 |  |  | 2282 | 2282 | 0
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 2945 | 2021-08-09 | 2021-08-13 | 0% | 20 |  |  | 2945 | 2945 | 0
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1361 | 2021-08-09 | 2021-08-13 | 0% | 8 |  |  | 1361 | 1361 | 0
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2282 | 2021-08-09 | 2021-08-13 | 0% | 20 |  |  | 2282 | 2282 | 0
S310810 | Carriage Cradle - Vendor Responses - CA-D Resource(s) | PROF4 AD.PROF4 AD | 36 | 5302 | 08-Jan-20 A | 19-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S310810 | Carriage Cradle - Vendor Responses - CA-D Resource(s) | PROF5 AD.PROF5 AD | 36 | 6122 | 08-Jan-20 A | 19-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S310810 | Carriage Cradle - Vendor Responses - CA-D Resource(s) | TECH3 AD.TECH3 AD | 36 | 4108 | 08-Jan-20 A | 19-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312110 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 80 | 11781 | 14-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312110 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - CA-D Resource(s) | PROF5 AD.PROF5 AD | 40 | 6803 | 14-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312110 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 40 | 4565 | 14-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312310 | CC Drive & Alignment System - Prepare Procurement Package - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 2945 | 28-Jul-20 A | 21-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312310 | CC Drive & Alignment System - Prepare Procurement Package - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1361 | 28-Jul-20 A | 21-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312310 | CC Drive & Alignment System - Prepare Procurement Package - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2282 | 28-Jul-20 A | 21-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312410 | CC Drive & Alignment System - Procurement Readiness Review - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 2945 | 01-Oct-20 A | 07-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312410 | CC Drive & Alignment System - Procurement Readiness Review - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1361 | 01-Oct-20 A | 07-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312410 | CC Drive & Alignment System - Procurement Readiness Review - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2282 | 01-Oct-20 A | 07-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312210 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | PROF4 AD.PROF4 AD | 80 | 11781 | 21-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312210 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | PROF5 AD.PROF5 AD | 40 | 6803 | 21-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312210 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | TECH3 AD.TECH3 AD | 40 | 4565 | 21-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312810 | CC Drive & Alignment System - Vendor Selection - CA-D Resource(s) | PROF4 AD.PROF4 AD | 18 | 2651 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312810 | CC Drive & Alignment System - Vendor Selection - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1361 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312810 | CC Drive & Alignment System - Vendor Selection - CA-D Resource(s) | TECH3 AD.TECH3 AD | 18 | 2054 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S313010 | CC Drive & Alignment System - BNL Oversight - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 3004 | 03-Nov-20 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S313010 | CC Drive & Alignment System - BNL Oversight - CA-D Resource(s) | PROF5 AD.PROF5 AD | 20 | 3469 | 03-Nov-20 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S313010 | CC Drive & Alignment System - BNL Oversight - CA-D Resource(s) | TECH3 AD.TECH3 AD | 10 | 1164 | 03-Nov-20 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S313210 | CC Drive & Alignment System - Delivery Acceptance - CA-D Resource(s) - Labor | PROF4 AD.PROF4 AD | 32 | 4854 | 12-Apr-21 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S313210 | CC Drive & Alignment System - Delivery Acceptance - CA-D Resource(s) - Labor | PROF5 AD.PROF5 AD | 4 | 701 | 12-Apr-21 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S313210 | CC Drive & Alignment System - Delivery Acceptance - CA-D Resource(s) - Labor | TECH3 AD.TECH3 AD | 16 | 1881 | 12-Apr-21 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S312710 | CC Drive & Alignment System - Vendor Responses - CA-D Resource(s) | PROF4 AD.PROF4 AD | 18 | 2651 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312710 | CC Drive & Alignment System - Vendor Responses - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1361 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S312710 | CC Drive & Alignment System - Vendor Responses - CA-D Resource(s) | TECH3 AD.TECH3 AD | 18 | 2054 | 23-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | PROF4 AD.PROF4 AD | 18 | 2651 | 2021-10-13 | 2021-11-24 | 0% | 18 |  |  | 2651 | 2651 | 0
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1361 | 2021-10-13 | 2021-11-24 | 0% | 8 |  |  | 1361 | 1361 | 0
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | TECH3 AD.TECH3 AD | 18 | 2054 | 2021-10-13 | 2021-11-24 | 0% | 18 |  |  | 2054 | 2054 | 0
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | PROF4 AD.PROF4 AD | 24 | 3594 | 2021-11-30 | 2022-08-16 | 0% | 24 |  |  | 3594 | 3594 | 0
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | PROF5 AD.PROF5 AD | 24 | 4150 | 2021-11-30 | 2022-08-16 | 0% | 24 |  |  | 4150 | 4150 | 0
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | TECH3 AD.TECH3 AD | 10 | 1160 | 2021-11-30 | 2022-08-16 | 0% | 10 |  |  | 1160 | 1160 | 0
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | PROF4 AD.PROF4 AD | 2 | 303 | 2022-08-17 | 2022-08-23 | 0% | 2 |  |  | 303 | 303 | 0
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | PROF5 AD.PROF5 AD | 4 | 701 | 2022-08-17 | 2022-08-23 | 0% | 4 |  |  | 701 | 701 | 0
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | TECH3 AD.TECH3 AD | 4 | 470 | 2022-08-17 | 2022-08-23 | 0% | 4 |  |  | 470 | 470 | 0
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | PROF4 AD.PROF4 AD | 18 | 2651 | 2021-08-30 | 2021-10-12 | 0% | 18 |  |  | 2651 | 2651 | 0
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1361 | 2021-08-30 | 2021-10-12 | 0% | 8 |  |  | 1361 | 1361 | 0
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | TECH3 AD.TECH3 AD | 18 | 2054 | 2021-08-30 | 2021-10-12 | 0% | 18 |  |  | 2054 | 2054 | 0
S315910 | Steel Track Modifications - BNL Oversight Construction - CA-D Resource(s) | PROF4 AD.PROF4 AD | 120 | 17672 | 18-Nov-19 A | 31-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S315910 | Steel Track Modifications - BNL Oversight Construction - CA-D Resource(s) | CRAFT3.CRAFT3 | 300 | 37521 | 18-Nov-19 A | 31-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S311350 | Carriage Cradle - Delivery Acceptance One - M&S | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 204848 | 228531 | 01-Jul-20 A | 02-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S313250 | CC Drive & Alignment System - Delivery Acceptance - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 56580 | 65672 | 12-Apr-21 A | 15-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S314650 | CC Seismic Restraints - Delivery Acceptance - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 126000 | 146246 | 2022-08-17 | 2022-08-23 | 0% | 126000 |  |  | 146246 | 146246 | 0
S1001799 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16729 | Actual Labor.Actual Labor | 1142 | 190783 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S315915 | Steel Track Modifications - Inspection As-Builts and Punchlists Phys | TECH3 PO D.TECH3 PO D | 60 | 6847 | 03-Feb-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S315925 | Steel Track Modifications - Inspection As-Builts and Punchlists CA-D | PROF4 AD.PROF4 AD | 60 | 8836 | 03-Feb-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S316005 | Steel Track Modifications - Finish Track Work Labor | PROF3 AD.PROF3 AD | 24 | 3036 | 15-Oct-20 A | 2021-08-30 | 95% | 1.2 |  |  | 151.8 | 151.8 | 0
S316005 | Steel Track Modifications - Finish Track Work Labor | CRAFT3.CRAFT3 | 40 | 5003 | 15-Oct-20 A | 2021-08-30 | 95% | 2 |  |  | 250.15 | 250.15 | 0
S310006 | Carriage Cradle - Create Assembly & Detail Drawings - Physics Resource(s) Split_10% | TECH3 PO D.TECH3 PO D | 19 | 2191 | 01-Oct-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310006 | Carriage Cradle - Create Assembly & Detail Drawings - Physics Resource(s) Split_10% | TECH3 PO M.TECH3 PO M | 3 | 297 | 01-Oct-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310016 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) Split_10% | PROF4 AD.PROF4 AD | 10 | 1414 | 01-Oct-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310016 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) Split_10% | PROF5 AD.PROF5 AD | 10 | 1633 | 01-Oct-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310016 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) Split_10% | TECH3 AD.TECH3 AD | 19 | 2191 | 01-Oct-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310201 | Carriage Cradle - Address Action Items from Design & Safety Reviews - Physics Resource(s)_75% | TECH3 PO D.TECH3 PO D | 45 | 5135 | 01-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310201 | Carriage Cradle - Address Action Items from Design & Safety Reviews - Physics Resource(s)_75% | SCI3 PO.SCI3 PO | 6 | 1033 | 01-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310201 | Carriage Cradle - Address Action Items from Design & Safety Reviews - Physics Resource(s)_75% | TECH3 PO M.TECH3 PO M | 6 | 685 | 01-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310211 | Carriage Cradle - Address Action Items from Design & Safety Reviews - CA-D Resource(s)_75% | PROF4 AD.PROF4 AD | 60 | 8836 | 01-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310211 | Carriage Cradle - Address Action Items from Design & Safety Reviews - CA-D Resource(s)_75% | PROF5 AD.PROF5 AD | 30 | 5102 | 01-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S310211 | Carriage Cradle - Address Action Items from Design & Safety Reviews - CA-D Resource(s)_75% | TECH3 AD.TECH3 AD | 45 | 5135 | 01-Oct-19 A | 17-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S314716 | Steel Track Modifications - Structural Analysis of Existing Steel Track System & Preliminary Design_85% | TECH3 PO D.TECH3 PO D | 34 | 3880 | 01-Oct-19 A | 30-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004880 | Actuals - Labor FY19 Jun-Sep 16729 | Actual Labor.Actual Labor | 1358 | 226960 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S311355 | Carriage Cradle - Delivery Acceptance Two - M&S | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 1101666 | 1229033 | 21-Dec-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports
S316600 | Create Internal Detector Structural Support Detail Drawings - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 50 | 5706 | 11-Jan-21 A | 18-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316700 | Review Internal Detector Structural Support Safety - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 4 | 456 | 19-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316700 | Review Internal Detector Structural Support Safety - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 4 | 456 | 19-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316800 | Review Internal Detector Structural Support Design - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 913 | 19-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316800 | Review Internal Detector Structural Support Design - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 4 | 456 | 19-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316900 | Address Action Items from Inner HCal Support Tabs Design & Safety Reviews - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 29-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317100 | Prepare Procurement Package(s) for Inner HCal Support Tabs - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 24 | 2739 | 15-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317100 | Prepare Procurement Package(s) for Inner HCal Support Tabs - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2739 | 15-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317200 | Evaluate & Process Bid for Inner HCal Support Tabs - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1826 | 2021-07-01 | 2021-07-29 | 0% | 16 |  |  | 1826 | 1826 | 0
S317200 | Evaluate & Process Bid for Inner HCal Support Tabs - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 16 | 1826 | 2021-07-01 | 2021-07-29 | 0% | 16 |  |  | 1826 | 1826 | 0
S318000 | Perform Inner HCal Support Tabs Acceptance - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2351 | 2021-11-05 | 2021-12-14 | 0% | 20 |  |  | 2351 | 2351 | 0
S318000 | Perform Inner HCal Support Tabs Acceptance - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-11-05 | 2021-12-14 | 0% | 8 |  |  | 940 | 940 | 0
S317400 | Procure IHCal Structural Support - Provide Requirements to Procurement | PROF3 PO M.PROF3 PO M | 32 | 4048 | 2021-07-30 | 2021-08-05 | 0% | 32 |  |  | 4048 | 4048 | 0
S317600 | Procure IHCal Structural Support - Vendor Response and Selection | PROF3 PO M.PROF3 PO M | 32 | 4048 | 2021-08-13 | 2021-08-19 | 0% | 32 |  |  | 4048 | 4048 | 0
S317900 | Procure IHCal Structural Support - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 45850 | 53217 | 2021-10-29 | 2021-11-04 | 0% | 45850 |  |  | 53217 | 53217 | 0
S316510 | Create Internal Detector Structural Support Assembly Drawings - CA-D Resource(s) | PROF4 AD.PROF4 AD | 64 | 9425 | 13-May-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316610 | Create Internal Detector Structural Support Detail Drawings - CA-D Resource(s) | PROF4 AD.PROF4 AD | 48 | 7069 | 11-Jan-21 A | 18-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316710 | Review Internal Detector Structural Support Safety - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1178 | 19-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316810 | Review Internal Detector Structural Support Design - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 19-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S316910 | Address Action Items from Inner HCal Support Tabs Design & Safety Reviews - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 5891 | 29-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317110 | Prepare Procurement Package(s) for Inner HCal Support Tabs - CA-D Resource(s) | PROF4 AD.PROF4 AD | 120 | 17672 | 15-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317210 | Evaluate & Process Bid for Inner HCal Support Tabs - CA-D Resource(s) | PROF4 AD.PROF4 AD | 32 | 4712 | 2021-07-01 | 2021-07-29 | 0% | 32 |  |  | 4712 | 4712 | 0
S318010 | Perform Inner HCal Support Tabs Acceptance - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 2021-11-05 | 2021-12-14 | 0% | 16 |  |  | 2427 | 2427 | 0
S316505 | Create Internal Detector Structural Support Assembly Drawings - Physics Resource(s) Split | TECH3 PO D.TECH3 PO D | 48 | 5478 | 13-May-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1001759 | Actuals - NonLabor - sPHENIX Infrastructure FY19 M8 16731 | Actual NonLabor.Actual Nonlabor | 5225 | 5765 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S317020 | Create Magnet Supports Detailed Design Drawings | PROF3 PO M.PROF3 PO M | 220 | 28389 | 15-Sep-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317020 | Create Magnet Supports Detailed Design Drawings | TECH3 PO D.TECH3 PO D | 300 | 34921 | 15-Sep-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317021 | Review Design and Safety Magnet Supports | PROF3 PO E.PROF3 PO E | 4 | 521 | 01-Dec-20 A | 02-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317021 | Review Design and Safety Magnet Supports | PROF3 PO M.PROF3 PO M | 4 | 521 | 01-Dec-20 A | 02-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317022 | Address Action Items for Magnet Supports | PROF3 PO E.PROF3 PO E | 4 | 521 | 03-Dec-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317022 | Address Action Items for Magnet Supports | PROF3 PO M.PROF3 PO M | 4 | 521 | 03-Dec-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317030 | Create EMCal Supports Detailed Design Drawings | PROF3 PO M.PROF3 PO M | 100 | 13030 | 08-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317030 | Create EMCal Supports Detailed Design Drawings | TECH3 PO D.TECH3 PO D | 120 | 14105 | 08-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317031 | Review Design and Safety EMCal Supports | PROF3 PO E.PROF3 PO E | 0 | 52 | 08-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317031 | Review Design and Safety EMCal Supports | PROF3 PO M.PROF3 PO M | 0 | 52 | 08-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317032 | Address Action Items for EMCal Supports | PROF3 PO E.PROF3 PO E | 0 | 52 | 08-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317032 | Address Action Items for EMCal Supports | PROF3 PO M.PROF3 PO M | 0 | 52 | 08-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317040 | Create TPC Supports Detailed Design Drawings | PROF3 PO M.PROF3 PO M | 80 | 10424 | 17-Nov-20 A | 2021-08-06 | 95% | 4 |  |  | 521.2 | 521.2 | 0
S317040 | Create TPC Supports Detailed Design Drawings | TECH3 PO D.TECH3 PO D | 160 | 18807 | 17-Nov-20 A | 2021-08-06 | 95% | 8 |  |  | 940.35 | 940.35 | 0
S317041 | Review Design and Safety TPC Supports | PROF3 PO E.PROF3 PO E | 8 | 1042 | 2021-08-09 | 2021-08-13 | 0% | 8 |  |  | 1042 | 1042 | 0
S317041 | Review Design and Safety TPC Supports | PROF3 PO M.PROF3 PO M | 8 | 1042 | 2021-08-09 | 2021-08-13 | 0% | 8 |  |  | 1042 | 1042 | 0
S317042 | Address Action Items for TPC Supports | PROF3 PO E.PROF3 PO E | 8 | 1042 | 2021-08-16 | 2021-08-17 | 0% | 8 |  |  | 1042 | 1042 | 0
S317042 | Address Action Items for TPC Supports | PROF3 PO M.PROF3 PO M | 8 | 1042 | 2021-08-16 | 2021-08-17 | 0% | 8 |  |  | 1042 | 1042 | 0
S317050 | Create INTT Supports Detailed Design Drawings | PROF3 PO M.PROF3 PO M | 40 | 5212 | 13-May-20 A | 2021-08-12 | 65% | 14 |  |  | 1824.2 | 1824.2 | 0
S317050 | Create INTT Supports Detailed Design Drawings | TECH3 PO D.TECH3 PO D | 160 | 18807 | 13-May-20 A | 2021-08-12 | 65% | 56 |  |  | 6582.45 | 6582.45 | 0
S317051 | Review Design and Safety INTT Supports | PROF3 PO M.PROF3 PO M | 8 | 1042 | 2021-08-13 | 2021-08-19 | 0% | 8 |  |  | 1042 | 1042 | 0
S317051 | Review Design and Safety INTT Supports | TECH3 PO D.TECH3 PO D | 40 | 4702 | 2021-08-13 | 2021-08-19 | 0% | 40 |  |  | 4702 | 4702 | 0
S317052 | Address Action Items for INTT Supports | PROF3 PO E.PROF3 PO E | 8 | 1042 | 2021-08-20 | 2021-08-23 | 0% | 8 |  |  | 1042 | 1042 | 0
S317052 | Address Action Items for INTT Supports | PROF3 PO M.PROF3 PO M | 8 | 1042 | 2021-08-20 | 2021-08-23 | 0% | 8 |  |  | 1042 | 1042 | 0
S317060 | Create MVTX Supports Detailed Design Drawings | PROF3 PO M.PROF3 PO M | 40 | 5212 | 19-May-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317060 | Create MVTX Supports Detailed Design Drawings | TECH3 PO D.TECH3 PO D | 160 | 18807 | 19-May-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317061 | Review Design and Safety MVTX Supports | PROF3 PO E.PROF3 PO E | 8 | 1042 | 21-Dec-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317061 | Review Design and Safety MVTX Supports | PROF3 PO M.PROF3 PO M | 8 | 1042 | 21-Dec-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317062 | Address Action Items for MVTX Supports | PROF3 PO E.PROF3 PO E | 8 | 1042 | 2021-08-13 | 2021-08-16 | 0% | 8 |  |  | 1042 | 1042 | 0
S317062 | Address Action Items for MVTX Supports | PROF3 PO M.PROF3 PO M | 8 | 1042 | 2021-08-13 | 2021-08-16 | 0% | 8 |  |  | 1042 | 1042 | 0
S317070 | Create MBD Supports Detailed Design Drawings | PROF3 PO M.PROF3 PO M | 60 | 7818 | 18-May-20 A | 2021-08-26 | 70% | 18 |  |  | 2345.4 | 2345.4 | 0
S317070 | Create MBD Supports Detailed Design Drawings | TECH3 PO D.TECH3 PO D | 80 | 9404 | 18-May-20 A | 2021-08-26 | 70% | 24 |  |  | 2821.2 | 2821.2 | 0
S317071 | Review Design and Safety MBD Supports | PROF3 PO E.PROF3 PO E | 4 | 521 | 2021-08-27 | 2021-08-30 | 0% | 4 |  |  | 521 | 521 | 0
S317071 | Review Design and Safety MBD Supports | PROF3 PO M.PROF3 PO M | 4 | 521 | 2021-08-27 | 2021-08-30 | 0% | 4 |  |  | 521 | 521 | 0
S317072 | Address Action Items for MBD Supports | PROF3 PO E.PROF3 PO E | 4 | 521 | 2021-08-31 | 2021-09-01 | 0% | 4 |  |  | 521 | 521 | 0
S317072 | Address Action Items for MBD Supports | PROF3 PO M.PROF3 PO M | 4 | 521 | 2021-08-31 | 2021-09-01 | 0% | 4 |  |  | 521 | 521 | 0
S317080 | Create Large Support Rings Detailed Design Drawings | PROF3 PO E.PROF3 PO E | 100 | 12651 | 13-May-20 A | 09-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317080 | Create Large Support Rings Detailed Design Drawings | PROF3 PO M.PROF3 PO M | 350 | 44278 | 13-May-20 A | 09-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317081 | Review Design and Safety Large Support Rings | PROF3 PO M.PROF3 PO M | 24 | 3036 | 10-Nov-20 A | 24-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317081 | Review Design and Safety Large Support Rings | TECH3 PO D.TECH3 PO D | 24 | 2739 | 10-Nov-20 A | 24-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S317082 | Address Action Items for Large Support Rings | PROF3 PO E.PROF3 PO E | 10 | 1265 | 25-Nov-20 A | 01-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317082 | Address Action Items for Large Support Rings | PROF3 PO M.PROF3 PO M | 10 | 1265 | 25-Nov-20 A | 01-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317090 | Create Beampipe Supports Detailed Design Drawings | PROF3 PO M.PROF3 PO M | 240 | 30362 | 12-Mar-20 A | 2021-07-28 | 90% | 24 |  |  | 3036.2 | 3036.2 | 0
S317090 | Create Beampipe Supports Detailed Design Drawings | TECH3 PO D.TECH3 PO D | 300 | 34237 | 12-Mar-20 A | 2021-07-28 | 90% | 30 |  |  | 3423.7 | 3423.7 | 0
S317091 | Review Design and Safety Beampipe Supports | PROF3 PO M.PROF3 PO M | 20 | 2530 | 2021-07-29 | 2021-08-04 | 0% | 20 |  |  | 2530 | 2530 | 0
S317091 | Review Design and Safety Beampipe Supports | TECH3 PO D.TECH3 PO D | 20 | 2282 | 2021-07-29 | 2021-08-04 | 0% | 20 |  |  | 2282 | 2282 | 0
S317092 | Address Action Items for Beampipe Supports | PROF3 PO E.PROF3 PO E | 4 | 521 | 2021-08-05 | 2021-08-06 | 0% | 4 |  |  | 521 | 521 | 0
S317092 | Address Action Items for Beampipe Supports | PROF3 PO M.PROF3 PO M | 4 | 521 | 2021-08-05 | 2021-08-06 | 0% | 4 |  |  | 521 | 521 | 0
S317120 | Prepare Procurement Package for Magnet Supports | TECH3 PO M.TECH3 PO M | 40 | 4702 | 16-Mar-21 A | 25-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317120 | Prepare Procurement Package for Magnet Supports | PROF3 PO M.PROF3 PO M | 40 | 5212 | 16-Mar-21 A | 25-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317120 | Prepare Procurement Package for Magnet Supports | PROF3 PO E.PROF3 PO E | 40 | 5212 | 16-Mar-21 A | 25-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317130 | Prepare Procurement Package for EMCal Supports | TECH3 PO M.TECH3 PO M | 10 | 1175 | 18-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317130 | Prepare Procurement Package for EMCal Supports | PROF3 PO M.PROF3 PO M | 10 | 1303 | 18-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317130 | Prepare Procurement Package for EMCal Supports | PROF3 PO E.PROF3 PO E | 10 | 1303 | 18-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317140 | Prepare Procurement Package for TPC Supports | TECH3 PO M.TECH3 PO M | 40 | 4702 | 2021-08-18 | 2021-09-15 | 0% | 40 |  |  | 4702 | 4702 | 0
S317140 | Prepare Procurement Package for TPC Supports | PROF3 PO M.PROF3 PO M | 40 | 5212 | 2021-08-18 | 2021-09-15 | 0% | 40 |  |  | 5212 | 5212 | 0
S317140 | Prepare Procurement Package for TPC Supports | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2021-08-18 | 2021-09-15 | 0% | 40 |  |  | 5212 | 5212 | 0
S317150 | Prepare Procurement Package for INTT Supports | TECH3 PO M.TECH3 PO M | 20 | 2351 | 2021-08-24 | 2021-09-07 | 0% | 20 |  |  | 2351 | 2351 | 0
S317150 | Prepare Procurement Package for INTT Supports | PROF3 PO M.PROF3 PO M | 20 | 2606 | 2021-08-24 | 2021-09-07 | 0% | 20 |  |  | 2606 | 2606 | 0
S317150 | Prepare Procurement Package for INTT Supports | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-08-24 | 2021-09-07 | 0% | 20 |  |  | 2606 | 2606 | 0
S317160 | Prepare Procurement Package for MVTX Supports | TECH3 PO M.TECH3 PO M | 20 | 2351 | 2021-08-17 | 2021-08-30 | 0% | 20 |  |  | 2351 | 2351 | 0
S317160 | Prepare Procurement Package for MVTX Supports | PROF3 PO M.PROF3 PO M | 20 | 2606 | 2021-08-17 | 2021-08-30 | 0% | 20 |  |  | 2606 | 2606 | 0
S317160 | Prepare Procurement Package for MVTX Supports | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-08-17 | 2021-08-30 | 0% | 20 |  |  | 2606 | 2606 | 0
S317170 | Prepare Procurement Package for MBD Supports | TECH3 PO M.TECH3 PO M | 10 | 1175 | 2021-09-02 | 2021-09-16 | 0% | 10 |  |  | 1175 | 1175 | 0
S317170 | Prepare Procurement Package for MBD Supports | PROF3 PO M.PROF3 PO M | 10 | 1303 | 2021-09-02 | 2021-09-16 | 0% | 10 |  |  | 1303 | 1303 | 0
S317170 | Prepare Procurement Package for MBD Supports | PROF3 PO E.PROF3 PO E | 10 | 1303 | 2021-09-02 | 2021-09-16 | 0% | 10 |  |  | 1303 | 1303 | 0
S317180 | Prepare Procurement Package for Large Support Rings | TECH3 PO M.TECH3 PO M | 80 | 9130 | 02-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317180 | Prepare Procurement Package for Large Support Rings | PROF3 PO M.PROF3 PO M | 80 | 10121 | 02-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317180 | Prepare Procurement Package for Large Support Rings | PROF3 PO E.PROF3 PO E | 80 | 10121 | 02-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317190 | Prepare Procurement Package for Beampipe Supports | TECH3 PO M.TECH3 PO M | 40 | 4702 | 2021-08-09 | 2021-08-20 | 0% | 40 |  |  | 4702 | 4702 | 0
S317190 | Prepare Procurement Package for Beampipe Supports | PROF3 PO M.PROF3 PO M | 40 | 5212 | 2021-08-09 | 2021-08-20 | 0% | 40 |  |  | 5212 | 5212 | 0
S317190 | Prepare Procurement Package for Beampipe Supports | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2021-08-09 | 2021-08-20 | 0% | 40 |  |  | 5212 | 5212 | 0
S317220 | Evaluate and Process Bid for Magnet Supports | PROF3 PO M.PROF3 PO M | 20 | 2606 | 03-May-21 A | 17-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317220 | Evaluate and Process Bid for Magnet Supports | PROF3 PO E.PROF3 PO E | 20 | 2606 | 03-May-21 A | 17-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317230 | Evaluate and Process Bid for EMCal Supports | PROF3 PO M.PROF3 PO M | 10 | 1303 | 16-Feb-21 A | 25-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317230 | Evaluate and Process Bid for EMCal Supports | PROF3 PO E.PROF3 PO E | 10 | 1303 | 16-Feb-21 A | 25-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317240 | Evaluate and Process Bid for TPC Supports | PROF3 PO M.PROF3 PO M | 20 | 2606 | 2021-09-16 | 2021-10-14 | 0% | 20 |  |  | 2606 | 2606 | 0
S317240 | Evaluate and Process Bid for TPC Supports | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-09-16 | 2021-10-14 | 0% | 20 |  |  | 2606 | 2606 | 0
S317250 | Evaluate and Process Bid for INTT Supports | PROF3 PO M.PROF3 PO M | 20 | 2606 | 2021-09-08 | 2021-10-05 | 0% | 20 |  |  | 2606 | 2606 | 0
S317250 | Evaluate and Process Bid for INTT Supports | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-09-08 | 2021-10-05 | 0% | 20 |  |  | 2606 | 2606 | 0
S317260 | Evaluate and Process Bid for MVTX Supports | PROF3 PO M.PROF3 PO M | 20 | 2606 | 2021-08-31 | 2021-09-28 | 0% | 20 |  |  | 2606 | 2606 | 0
S317260 | Evaluate and Process Bid for MVTX Supports | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-08-31 | 2021-09-28 | 0% | 20 |  |  | 2606 | 2606 | 0
S317270 | Evaluate and Process Bid for MBD Supports | PROF3 PO M.PROF3 PO M | 10 | 1303 | 2021-09-17 | 2021-10-15 | 0% | 10 |  |  | 1303 | 1303 | 0
S317270 | Evaluate and Process Bid for MBD Supports | PROF3 PO E.PROF3 PO E | 10 | 1303 | 2021-09-17 | 2021-10-15 | 0% | 10 |  |  | 1303 | 1303 | 0
S317280 | Evaluate and Process Bid for Large Support Rings | PROF3 PO M.PROF3 PO M | 20 | 2549 | 22-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317280 | Evaluate and Process Bid for Large Support Rings | PROF3 PO E.PROF3 PO E | 20 | 2549 | 22-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317290 | Evaluate and Process Bid for Beampipe Supports | PROF3 PO M.PROF3 PO M | 20 | 2606 | 2021-08-23 | 2021-09-20 | 0% | 20 |  |  | 2606 | 2606 | 0
S317290 | Evaluate and Process Bid for Beampipe Supports | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-08-23 | 2021-09-20 | 0% | 20 |  |  | 2606 | 2606 | 0
S317920 | Procure Magnet Supports - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 58034 | 10-May-21 A | 2021-08-05 | 50% | 25000 |  |  | 29017 | 29017 | 0
S317930 | Procure EMCal Supports - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 18040 | 20939 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S317940 | Procure TPC Supports - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 58034 | 2021-10-18 | 2021-12-15 | 0% | 50000 |  |  | 58034 | 58034 | 0
S317950 | Procure INTT Supports - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 58034 | 2021-10-07 | 2021-12-07 | 0% | 50000 |  |  | 58034 | 58034 | 0
S317960 | Procure MVTX Supports - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 58034 | 2021-09-30 | 2021-11-30 | 0% | 50000 |  |  | 58034 | 58034 | 0
S317970 | Procure MBD Supports - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 | 11607 | 2021-10-18 | 2021-11-15 | 0% | 10000 |  |  | 11607 | 11607 | 0
S317980 | Procure Large Support Rings - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 300000 | 348205 | 15-Apr-21 A | 2021-08-25 | 25% | 225000 |  |  | 261153.75 | 261153.75 | 0
S317990 | Procure Beampipe Supports - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 25000 | 29017 | 2021-09-21 | 2021-10-19 | 0% | 25000 |  |  | 29017 | 29017 | 0
S318120 | Perform Magnet Supports Acceptance | TECH3 PO M.TECH3 PO M | 20 | 2351 | 2021-08-06 | 2021-08-19 | 0% | 20 |  |  | 2351 | 2351 | 0
S318120 | Perform Magnet Supports Acceptance | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-08-06 | 2021-08-19 | 0% | 20 |  |  | 2606 | 2606 | 0
S318130 | Perform EMCal Supports Acceptance | TECH3 PO M.TECH3 PO M | 10 | 1175 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S318130 | Perform EMCal Supports Acceptance | PROF3 PO E.PROF3 PO E | 10 | 1303 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S318140 | Perform TPC Supports Acceptance | TECH3 PO M.TECH3 PO M | 40 | 4702 | 2021-12-16 | 2021-12-30 | 0% | 40 |  |  | 4702 | 4702 | 0
S318140 | Perform TPC Supports Acceptance | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2021-12-16 | 2021-12-30 | 0% | 40 |  |  | 5212 | 5212 | 0
S318150 | Perform INTT Supports Acceptance | TECH3 PO M.TECH3 PO M | 20 | 2351 | 2021-12-08 | 2021-12-21 | 0% | 20 |  |  | 2351 | 2351 | 0
S318150 | Perform INTT Supports Acceptance | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-12-08 | 2021-12-21 | 0% | 20 |  |  | 2606 | 2606 | 0
S318160 | Perform MVTX Supports Acceptance | TECH3 PO M.TECH3 PO M | 20 | 2351 | 2021-12-01 | 2021-12-14 | 0% | 20 |  |  | 2351 | 2351 | 0
S318160 | Perform MVTX Supports Acceptance | PROF3 PO E.PROF3 PO E | 20 | 2606 | 2021-12-01 | 2021-12-14 | 0% | 20 |  |  | 2606 | 2606 | 0
S318170 | Perform MBD Supports Acceptance | TECH3 PO M.TECH3 PO M | 10 | 1175 | 2021-11-16 | 2021-12-01 | 0% | 10 |  |  | 1175 | 1175 | 0
S318170 | Perform MBD Supports Acceptance | PROF3 PO E.PROF3 PO E | 10 | 1303 | 2021-11-16 | 2021-12-01 | 0% | 10 |  |  | 1303 | 1303 | 0
S318180 | Perform Large Support Rings Acceptance | TECH3 PO M.TECH3 PO M | 80 | 9404 | 2021-08-26 | 2021-09-09 | 0% | 80 |  |  | 9404 | 9404 | 0
S318180 | Perform Large Support Rings Acceptance | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2021-08-26 | 2021-09-09 | 0% | 40 |  |  | 5212 | 5212 | 0
S318190 | Perform Beampipe Supports Acceptance | TECH3 PO M.TECH3 PO M | 40 | 4702 | 2021-10-20 | 2021-11-02 | 0% | 40 |  |  | 4702 | 4702 | 0
S318190 | Perform Beampipe Supports Acceptance | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2021-10-20 | 2021-11-02 | 0% | 40 |  |  | 5212 | 5212 | 0
S316406 | Analyze and Evaluate Structural Support for Internal Detectors FY19 - Physics Resource(s) Split_75% | TECH3 PO D.TECH3 PO D | 20 | 2225 | 01-Nov-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S316406 | Analyze and Evaluate Structural Support for Internal Detectors FY19 - Physics Resource(s) Split_75% | TECH3 PO M.TECH3 PO M | 14 | 1626 | 01-Nov-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1004920 | Actuals - Labor FY19 Jun-Sep 16731 | Actual Labor.Actual Labor | 126 | 20995 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S318182 | Assemble Large Support Rings | TECH3 PO M.TECH3 PO M | 80 | 9404 | 2021-09-10 | 2021-09-30 | 0% | 80 |  |  | 9404 | 9404 | 0
S318182 | Assemble Large Support Rings | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2021-09-10 | 2021-09-30 | 0% | 40 |  |  | 5212 | 5212 | 0
S318182 | Assemble Large Support Rings | PROF4 PO M.PROF4 PO M | 40 | 6067 | 2021-09-10 | 2021-09-30 | 0% | 40 |  |  | 6067 | 6067 | 0
2.03.03 Barrel Steel
S309500 | Actuals - Nonlabor - sPHENIX Infrastructure FY18 16722 | Actual NonLabor.Actual Nonlabor | 966502 | 1078243 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
OBLG319501 | Procure Outer HCAL Mechanical Structure Components - Obligation (Raw Mat'l & Sector Assemblies) | OBLG.Obligation Resource | 0 | 0 | 21-Apr-17 A | 21-Apr-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000439 | Actuals - Labor - sPHENIX Infrastructure FY17 16722 | Actual Labor.Actual Labor | 94 | 15648 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000599 | Actuals - Labor - sPHENIX Infrastructure FY18 16722 | Actual Labor.Actual Labor | 1009 | 168592 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1001559 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16722 | Actual Labor.Actual Labor | 691 | 115388 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1001599 | Actuals - NonLabor - sPHENIX Infrastructure FY19 M8 16722 | Actual NonLabor.Actual Nonlabor | 3505619 | 3867626 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004840 | Actuals - NonLabor FY19 Jun-Sep 16722 | Actual NonLabor.Actual Nonlabor | 952324 | 1050666 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.03.04 End Caps/ Pole Tips
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 24 | 3534 | 01-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | SCI3 PO.SCI3 PO | 24 | 4131 | 01-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2739 | 01-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 240 | 27389 | 01-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324300 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 01-Apr-20 A | 21-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324300 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - Physics Resource(s) | SCI3 PO.SCI3 PO | 4 | 688 | 01-Apr-20 A | 21-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324400 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4565 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324400 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 913 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324600 | End Caps/ Pole Tips - Prepare Procurement Package(s) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 120 | 13695 | 01-Apr-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325100 | End Caps/ Pole Tips - Vendor Selection - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 10 | 1141 | 29-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325400 | End Caps/ Pole Tips - Delivery Acceptance | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 890262 | 993188 | 2021-08-26 | 2021-08-26 | 0% | 890262 |  |  | 993188 | 993188 | 0
S324000 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 70 | 7989 | 01-Nov-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324100 | End Caps/ Pole Tips - Design Controls for Drive System - Physics Resource(s) | PROF3 PO E.PROF3 PO E | 120 | 15181 | 01-Apr-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324100 | End Caps/ Pole Tips - Design Controls for Drive System - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 60 | 6847 | 01-Apr-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324700 | End Caps/ Pole Tips - Procurement Readiness Review - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2739 | 21-Dec-20 A | 23-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324700 | End Caps/ Pole Tips - Procurement Readiness Review - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 21-Dec-20 A | 23-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324800 | End Caps/ Pole Tips - Provide Requirement to Procurement | PROF5 AD.PROF5 AD | 16 | 2721 | 15-Dec-20 A | 22-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325000 | End Caps/ Pole Tips - Vendor Responses - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 10 | 1141 | 11-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 40 | 4702 | 2021-08-26 | 2021-09-09 | 0% | 40 |  |  | 4702 | 4702 | 0
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 44 | 5172 | 2021-08-26 | 2021-09-09 | 0% | 44 |  |  | 5172 | 5172 | 0
S324210 | End Caps/ Pole Tips - Assembly & Detail Drawing - CA-D Resource(s) | PROF5 AD.PROF5 AD | 125 | 21258 | 01-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324210 | End Caps/ Pole Tips - Assembly & Detail Drawing - CA-D Resource(s) | TECH3 AD.TECH3 AD | 240 | 27389 | 01-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324210 | End Caps/ Pole Tips - Assembly & Detail Drawing - CA-D Resource(s) | PROF4 AD.PROF4 AD | 245 | 36080 | 01-Apr-20 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324310 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - CA-D Resource(s) | PROF5 AD.PROF5 AD | 20 | 3401 | 01-Apr-20 A | 21-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324310 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2282 | 01-Apr-20 A | 21-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324310 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 5891 | 01-Apr-20 A | 21-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324410 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | PROF5 AD.PROF5 AD | 20 | 3401 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324410 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | TECH3 AD.TECH3 AD | 40 | 4565 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324410 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 5891 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324610 | End Caps/ Pole Tips - Prepare Procurement Package(s) - CA-D Resource(s) | PROF5 AD.PROF5 AD | 16 | 2721 | 01-Apr-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324610 | End Caps/ Pole Tips - Prepare Procurement Package(s) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 120 | 13695 | 01-Apr-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324610 | End Caps/ Pole Tips - Prepare Procurement Package(s) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 5891 | 01-Apr-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325110 | End Caps/ Pole Tips - Vendor Selection - CA-D Resource(s) | PROF5 AD.PROF5 AD | 16 | 2721 | 29-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325110 | End Caps/ Pole Tips - Vendor Selection - CA-D Resource(s) | TECH3 AD.TECH3 AD | 10 | 1141 | 29-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325110 | End Caps/ Pole Tips - Vendor Selection - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 29-Jan-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S324010 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - CA-D Resource(s) | PROF5 AD.PROF5 AD | 140 | 23809 | 01-Nov-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324010 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 70 | 7989 | 01-Nov-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324010 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 240 | 35344 | 01-Nov-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324710 | End Caps/ Pole Tips - Procurement Readiness Review - CA-D Resource(s) | PROF5 AD.PROF5 AD | 16 | 2721 | 21-Dec-20 A | 23-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324710 | End Caps/ Pole Tips - Procurement Readiness Review - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2282 | 21-Dec-20 A | 23-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S324710 | End Caps/ Pole Tips - Procurement Readiness Review - CA-D Resource(s) | PROF4 AD.PROF4 AD | 24 | 3534 | 21-Dec-20 A | 23-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325010 | End Caps/ Pole Tips - Vendor Responses - CA-D Resource(s) | PROF5 AD.PROF5 AD | 16 | 2721 | 11-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325010 | End Caps/ Pole Tips - Vendor Responses - CA-D Resource(s) | TECH3 AD.TECH3 AD | 10 | 1141 | 11-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325010 | End Caps/ Pole Tips - Vendor Responses - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 11-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | PROF5 AD.PROF5 AD | 36 | 6306 | 2021-08-26 | 2021-09-09 | 0% | 36 |  |  | 6306 | 6306 | 0
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 44 | 5172 | 2021-08-26 | 2021-09-09 | 0% | 44 |  |  | 5172 | 5172 | 0
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 52 | 7888 | 2021-08-26 | 2021-09-09 | 0% | 52 |  |  | 7888 | 7888 | 0
S324110 | End Caps/ Pole Tips - Design Controls for Drive System - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 6847 | 01-Apr-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.03.05 CC Bridge, Mid Platforms and Access
S325800 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 32 | 3660 | 01-Apr-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325800 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 320 | 36601 | 01-Apr-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325900 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4702 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325900 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 940 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326000 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 940 | 01-Apr-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326000 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4702 | 01-Apr-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326200 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2821 | 29-Jan-21 A | 12-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326200 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 80 | 9404 | 29-Jan-21 A | 12-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326700 | CC Bridge, Mid Platforms & Access - Vendor Selection - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2821 | 14-Jun-21 A | 22-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326700 | CC Bridge, Mid Platforms & Access - Vendor Selection - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 60 | 7053 | 14-Jun-21 A | 22-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 36 | 4232 | 2021-07-01 | 2021-11-01 | 0% | 36 |  |  | 4232 | 4232 | 0
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 72 | 8463 | 2021-07-01 | 2021-11-01 | 0% | 72 |  |  | 8463 | 8463 | 0
S327100 | CC Bridge, Mid Platforms & Access - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 320659 | 372184 | 01-Dec-21* | 2021-12-14 | 0% | 320659 |  |  | 372184 | 372184 | 0
S325700 | CC Bridge, Mid Platforms & Access - Engineering Analysis - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 160 | 18260 | 01-Nov-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326300 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2821 | 16-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326300 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2351 | 16-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326400 | CC Bridge, Mid Platforms & Access - Provide Requirement to Procurement | PROF5 AD.PROF5 AD | 16 | 2803 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326600 | CC Bridge, Mid Platforms & Access - Vendor Responses - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 60 | 7053 | 15-Mar-21 A | 21-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S327200 | CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 4 | 470 | 01-Jun-21 A | 02-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S327200 | CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 940 | 01-Jun-21 A | 02-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325810 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - CA-D Resource(s) | PROF4 AD.PROF4 AD | 320 | 47231 | 01-Apr-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325810 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - CA-D Resource(s) | PROF5 AD.PROF5 AD | 160 | 27271 | 01-Apr-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325810 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - CA-D Resource(s) | TECH3 AD.TECH3 AD | 320 | 36601 | 01-Apr-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S325910 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 6067 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325910 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - CA-D Resource(s) | PROF5 AD.PROF5 AD | 20 | 3503 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325910 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 40 | 4702 | 01-Apr-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326010 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 6067 | 01-Apr-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326010 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | PROF5 AD.PROF5 AD | 20 | 3503 | 01-Apr-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326010 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | TECH3 AD.TECH3 AD | 40 | 4702 | 01-Apr-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326210 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 6067 | 29-Jan-21 A | 12-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326210 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - CA-D Resource(s) | PROF5 AD.PROF5 AD | 16 | 2803 | 29-Jan-21 A | 12-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326210 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 80 | 9404 | 29-Jan-21 A | 12-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326710 | CC Bridge, Mid Platforms & Access - Vendor Selection - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 14-Jun-21 A | 22-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326710 | CC Bridge, Mid Platforms & Access - Vendor Selection - CA-D Resource(s) | PROF5 AD.PROF5 AD | 16 | 2803 | 14-Jun-21 A | 22-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326710 | CC Bridge, Mid Platforms & Access - Vendor Selection - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 7053 | 14-Jun-21 A | 22-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | PROF4 AD.PROF4 AD | 60 | 9101 | 2021-07-01 | 2021-11-01 | 0% | 60 |  |  | 9101 | 9101 | 0
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | PROF5 AD.PROF5 AD | 30 | 5255 | 2021-07-01 | 2021-11-01 | 0% | 30 |  |  | 5255 | 5255 | 0
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | TECH3 AD.TECH3 AD | 36 | 4232 | 2021-07-01 | 2021-11-01 | 0% | 36 |  |  | 4232 | 4232 | 0
S325710 | CC Bridge, Mid Platforms & Access - Engineering Analysis - CA-D Resource(s) | PROF4 AD.PROF4 AD | 320 | 47125 | 01-Nov-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325710 | CC Bridge, Mid Platforms & Access - Engineering Analysis - CA-D Resource(s) | PROF5 AD.PROF5 AD | 160 | 27210 | 01-Nov-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S325710 | CC Bridge, Mid Platforms & Access - Engineering Analysis - CA-D Resource(s) | TECH3 AD.TECH3 AD | 160 | 18260 | 01-Nov-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S326310 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - CA-D Resource(s) | PROF4 AD.PROF4 AD | 24 | 3640 | 16-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326310 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - CA-D Resource(s) | PROF5 AD.PROF5 AD | 16 | 2803 | 16-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326310 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - CA-D Resource(s) | TECH3 AD.TECH3 AD | 20 | 2351 | 16-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326610 | CC Bridge, Mid Platforms & Access - Vendor Responses - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 15-Mar-21 A | 21-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326610 | CC Bridge, Mid Platforms & Access - Vendor Responses - CA-D Resource(s) | PROF5 AD.PROF5 AD | 8 | 1401 | 15-Mar-21 A | 21-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S326610 | CC Bridge, Mid Platforms & Access - Vendor Responses - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 7053 | 15-Mar-21 A | 21-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S327210 | CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 8 | 1031 | 01-Jun-21 A | 02-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S327210 | CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 01-Jun-21 A | 02-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S327210 | CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor - CA-D Resource(s) | PROF5 AD.PROF5 AD | 16 | 2803 | 01-Jun-21 A | 02-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S327210 | CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 4 | 470 | 01-Jun-21 A | 02-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S327150 | Access stairs for upper platforms | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 45000 | 50203 | 01-Jul-21* | 2022-01-31 | 0% | 45000 |  |  | 50203 | 50203 | 0
2.04 Infrastructure
2.04.01 Infrastructure Detector Support Systems
S1000479 | Actuals - Labor - sPHENIX Infrastructure FY17 16723 | Actual Labor.Actual Labor | 103 | 17157 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000639 | Actuals - Labor - sPHENIX Infrastructure FY18 16723 | Actual Labor.Actual Labor | 124 | 20716 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1001639 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16723 | Actual Labor.Actual Labor | 313 | 52365 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1004960 | Actuals - Labor FY19 Jun-Sep 16723 | Actual Labor.Actual Labor | 126 | 21123 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.04.01.01 Line Electric Power Distribution
S327600 | Evaluate Normal, Emergency and UPS Load Requirements for Line Electric Power | PROF3 PO E.PROF3 PO E | 20 | 2530 | 02-Jan-20 A | 08-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S327700 | Calculate Power Transformer Requirements for Line Electric Power - CA-D Resource(s) | TECH3 AD.TECH3 AD | 16 | 1826 | 09-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S327700 | Calculate Power Transformer Requirements for Line Electric Power - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 09-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S327800 | Size Conductors for Line Electric Power - CA-D Resource(s) | TECH3 AD.TECH3 AD | 16 | 1826 | 17-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S327800 | Size Conductors for Line Electric Power - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 17-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S327900 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - CA-D Resource(s) | PROF4 AD.PROF4 AD | 32 | 4712 | 27-Aug-20 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S327900 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - CA-D Resource(s) | TECH3 AD.TECH3 AD | 32 | 3652 | 27-Aug-20 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S328000 | Review Line Electric Distribution Design/Safety - CA-D Resource(s) | PROF4 AD.PROF4 AD | 24 | 3534 | 17-Nov-20 A | 27-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S328100 | Address Action Items from Line Electric Distribution Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 80 | 9321 | 17-Nov-20 A | 27-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S328100 | Address Action Items from Line Electric Distribution Design & Safety Reviews | PROF3 PO E.PROF3 PO E | 20 | 2583 | 17-Nov-20 A | 27-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S328550 | Prepare Line Electric Power Distribution Components Procurement Package(s) | PROF3 PO E.PROF3 PO E | 60 | 7818 | 01-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S328850 | Evaluate & Process Line Electric Power Distribution Components Bid | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2021-07-29 | 2021-10-22 | 0% | 40 |  |  | 5212 | 5212 | 0
S328500 | Procure Line Electric Power Distribution Components - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 48 | 6255 | 01-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329200 | Perform Line Electric Power Distribution Components Acceptance | TECH3 PO E.TECH3 PO E | 80 | 9404 | 2022-01-25 | 2022-02-22 | 0% | 80 |  |  | 9404 | 9404 | 0
S329200 | Perform Line Electric Power Distribution Components Acceptance | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2022-01-25 | 2022-02-22 | 0% | 40 |  |  | 5212 | 5212 | 0
S329100 | Procure Line Electric Power Distribution Components - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 58034 | 2022-01-25 | 2022-02-22 | 0% | 50000 |  |  | 58034 | 58034 | 0
S327502 | Finalize Design Requirements for All sPHENIX Subsystems for Line Electric Power | PROF3 PO E.PROF3 PO E | 40 | 5060 | 01-Nov-19 A | 18-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1001999 | Calculate Power Transformer Requirements for Line Electric Power - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 40 | 5891 | 09-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1001999 | Calculate Power Transformer Requirements for Line Electric Power - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4565 | 09-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002039 | Size Conductors for Line Electric Power - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 32 | 4712 | 17-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002039 | Size Conductors for Line Electric Power - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 32 | 3652 | 17-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002079 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 32 | 3652 | 27-Aug-20 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002079 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 32 | 4712 | 27-Aug-20 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002119 | Review Line Electric Distribution Design/Safety - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 20 | 2945 | 17-Nov-20 A | 27-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S327501 | Gather Power Reqs for CRYO, Cooling and Lighting | TECH3 PO D.TECH3 PO D | 40 | 4565 | 30-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S327501 | Gather Power Reqs for CRYO, Cooling and Lighting | PROF3 PO E.PROF3 PO E | 20 | 2530 | 30-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S277600 | 2022 Detector Support Systems L3 Project Management | PROF3 PO E.PROF3 PO E | 352 | 47243 | 01-Oct-21* | 2022-09-30 | 0% | 352 |  |  | 47243 | 47243 | 0
S277700 | 2023 Detector Support Systems L3 Project Management | PROF3 PO E.PROF3 PO E | 113 | 15621 | 03-Oct-22* | 2022-10-04 | 0% | 113 |  |  | 15621 | 15621 | 0
2.04.01.02 Detector Support Services Systems (including Cables, Fibers, Cable Trays)
S329500 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp C | PROF4 AD.PROF4 AD | 4 | 589 | 02-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S329600 | Review Detector Support Services Systems Design/Safety - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 3034 | 2021-09-15 | 2021-10-01 | 0% | 20 |  |  | 3034 | 3034 | 0
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 80 | 9404 | 2021-10-01 | 2021-10-20 | 0% | 80 |  |  | 9404 | 9404 | 0
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | PROF3 PO E.PROF3 PO E | 40 | 5212 | 2021-10-01 | 2021-10-20 | 0% | 40 |  |  | 5212 | 5212 | 0
S329900 | Prepare Detector Support Services Systems Components Procurement Package(s) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 3034 | 2021-10-20 | 2021-11-18 | 0% | 20 |  |  | 3034 | 3034 | 0
S330000 | Evaluate & Process Detector Support Services Systems Components Bids - CA-D Resource(s) | PROF4 AD.PROF4 AD | 10 | 1517 | 2021-11-18 | 2021-12-20 | 0% | 10 |  |  | 1517 | 1517 | 0
S330100 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor C | PROF4 AD.PROF4 AD | 2 | 308 | 2021-12-20 | 2022-03-04 | 0% | 2 |  |  | 308 | 308 | 0
S330300 | Perform Detector Support Services Systems Components Acceptance - CA-D Resource(s) | PROF4 AD.PROF4 AD | 4 | 625 | 2022-03-04 | 2022-03-11 | 0% | 4 |  |  | 625 | 625 | 0
S330200 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 32000 | 37528 | 2021-12-20 | 2022-03-04 | 0% | 32000 |  |  | 37528 | 37528 | 0
S330350 | Procure Fiber Optics Trunk Cables and Accessories - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 4 | 625 | 2022-03-11 | 2022-06-06 | 0% | 4 |  |  | 625 | 625 | 0
S330355 | Procure Fiber Optics Trunk Cables and Accessories - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 22000 | 26046 | 2022-03-11 | 2022-06-06 | 0% | 22000 |  |  | 26046 | 26046 | 0
S329405 | Analyze Detector Support Services Systems Requirements Split - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 32 | 4712 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 26 | 2967 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 26 | 2967 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | SCI3 PO.SCI3 PO | 26 | 4475 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002319 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | TECH3 PO D.TECH3 PO D | 32 | 3652 | 02-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002319 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | PROF4 PO M.PROF4 PO M | 32 | 4712 | 02-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002399 | Review Detector Support Services Systems Design/Safety - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-09-15 | 2021-10-01 | 0% | 8 |  |  | 940 | 940 | 0
S1002399 | Review Detector Support Services Systems Design/Safety - Physics Resource(s) | PROF3 PO E.PROF3 PO E | 8 | 1042 | 2021-09-15 | 2021-10-01 | 0% | 8 |  |  | 1042 | 1042 | 0
S1002479 | Prepare Detector Support Services Systems Components Procurement Package(s) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 80 | 9404 | 2021-10-20 | 2021-11-18 | 0% | 80 |  |  | 9404 | 9404 | 0
S1002479 | Prepare Detector Support Services Systems Components Procurement Package(s) - Physics Resource(s) | PROF3 PO E.PROF3 PO E | 80 | 10424 | 2021-10-20 | 2021-11-18 | 0% | 80 |  |  | 10424 | 10424 | 0
S1002559 | Evaluate & Process Detector Support Services Systems Components Bids - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 2021-11-18 | 2021-12-20 | 0% | 16 |  |  | 1881 | 1881 | 0
S1002559 | Evaluate & Process Detector Support Services Systems Components Bids - Physics Resource(s) | PROF3 PO E.PROF3 PO E | 16 | 2085 | 2021-11-18 | 2021-12-20 | 0% | 16 |  |  | 2085 | 2085 | 0
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | TECH3 PO D.TECH3 PO D | 40 | 4775 | 2021-12-20 | 2022-03-04 | 0% | 40 |  |  | 4775 | 4775 | 0
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | PROF3 PO E.PROF3 PO E | 40 | 5294 | 2021-12-20 | 2022-03-04 | 0% | 40 |  |  | 5294 | 5294 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 20 | 2421 | 2022-03-04 | 2022-03-11 | 0% | 20 |  |  | 2421 | 2421 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 4 | 484 | 2022-03-04 | 2022-03-11 | 0% | 4 |  |  | 484 | 484 | 0
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | PROF3 PO E.PROF3 PO E | 4 | 537 | 2022-03-04 | 2022-03-11 | 0% | 4 |  |  | 537 | 537 | 0
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | SCI3 PO.SCI3 PO | 80 | 14607 | 2022-03-11 | 2022-06-06 | 0% | 80 |  |  | 14607 | 14607 | 0
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | PROF3 PO E.PROF3 PO E | 80 | 10737 | 2022-03-11 | 2022-06-06 | 0% | 80 |  |  | 10737 | 10737 | 0
S329410 | Conceptual Design for Cable Routing from Detector to Rack (MVTX) | PROF3 PO E.PROF3 PO E | 8 | 1012 | 09-Nov-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329410 | Conceptual Design for Cable Routing from Detector to Rack (MVTX) | TECH3 PO D.TECH3 PO D | 80 | 9130 | 09-Nov-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329420 | Conceptual Design for Cable Routing from Detector to Rack (MBD) | PROF3 PO E.PROF3 PO E | 8 | 1030 | 23-Oct-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329420 | Conceptual Design for Cable Routing from Detector to Rack (MBD) | TECH3 PO D.TECH3 PO D | 88 | 10224 | 23-Oct-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329430 | Conceptual Design for Routing Fiber Optic Cables from Rack to Patch Panel | PROF3 PO E.PROF3 PO E | 8 | 1042 | 22-Dec-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329430 | Conceptual Design for Routing Fiber Optic Cables from Rack to Patch Panel | TECH3 PO D.TECH3 PO D | 96 | 11284 | 22-Dec-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329440 | Conceptual Design for Routing Rack Cooling System | PROF3 PO E.PROF3 PO E | 104 | 13552 | 23-Oct-20 A | 2021-07-30 | 30% | 72.8 |  |  | 9486.4 | 9486.4 | 0
S329440 | Conceptual Design for Routing Rack Cooling System | TECH3 PO D.TECH3 PO D | 104 | 12225 | 23-Oct-20 A | 2021-07-30 | 30% | 72.8 |  |  | 8557.5 | 8557.5 | 0
S329450 | Conceptual Design for Routing Detector Cooling System | PROF3 PO E.PROF3 PO E | 100 | 13030 | 15-Jul-20 A | 2021-08-03 | 35% | 65 |  |  | 8469.5 | 8469.5 | 0
S329450 | Conceptual Design for Routing Detector Cooling System | TECH3 PO D.TECH3 PO D | 200 | 23509 | 15-Jul-20 A | 2021-08-03 | 35% | 130 |  |  | 15280.85 | 15280.85 | 0
S329460 | Design Package for Detector Cooling System | PROF3 PO E.PROF3 PO E | 120 | 15637 | 2021-08-03 | 2021-09-15 | 0% | 120 |  |  | 15637 | 15637 | 0
S329460 | Design Package for Detector Cooling System | TECH3 PO D.TECH3 PO D | 240 | 28211 | 2021-08-03 | 2021-09-15 | 0% | 240 |  |  | 28211 | 28211 | 0
S329470 | Conceptual Design for Power Distribution / Controls Cable Routing | PROF3 PO E.PROF3 PO E | 68 | 8861 | 22-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329470 | Conceptual Design for Power Distribution / Controls Cable Routing | TECH3 PO D.TECH3 PO D | 136 | 15986 | 22-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329406 | Send proposal packages for approvals (cable types, rack locations, and support components) | TECH3 PO D.TECH3 PO D | 15 | 1712 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S329406 | Send proposal packages for approvals (cable types, rack locations, and support components) | PROF3 PO E.PROF3 PO E | 8 | 1012 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S329407 | Conceptual Design for Cable Routing from Detector to Rack (HCal, EMCal) | TECH3 PO D.TECH3 PO D | 136 | 15521 | 11-Mar-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S329407 | Conceptual Design for Cable Routing from Detector to Rack (HCal, EMCal) | PROF3 PO E.PROF3 PO E | 16 | 2024 | 11-Mar-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S329408 | Conceptual Design for Cable Routing from Detector to Rack (TPC) | TECH3 PO D.TECH3 PO D | 120 | 13695 | 01-Jul-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329408 | Conceptual Design for Cable Routing from Detector to Rack (TPC) | PROF3 PO E.PROF3 PO E | 8 | 1012 | 01-Jul-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329409 | Conceptual Design for Cable Routing from Detector to Rack (INTT) | TECH3 PO D.TECH3 PO D | 88 | 10043 | 22-Dec-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329409 | Conceptual Design for Cable Routing from Detector to Rack (INTT) | PROF3 PO E.PROF3 PO E | 8 | 1012 | 22-Dec-20 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S329475 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | TECH3 PO D.TECH3 PO D | 200 | 23509 | 02-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S329475 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | PROF3 PO E.PROF3 PO E | 80 | 10424 | 02-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S329478 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp C | PROF4 AD.PROF4 AD | 4 | 607 | 02-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
2.04.01.03 Detector Electronics Racks and Rack generic support systems
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | PROF4 PO M.PROF4 PO M | 24 | 3640 | 23-Oct-20 A | 2021-07-14 | 40% | 14.4 |  |  | 2184 | 2184 | 0
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | TECH3 PO D.TECH3 PO D | 96 | 11284 | 23-Oct-20 A | 2021-07-14 | 40% | 57.6 |  |  | 6770.4 | 6770.4 | 0
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | PROF3 PO E.PROF3 PO E | 24 | 3127 | 23-Oct-20 A | 2021-07-14 | 40% | 14.4 |  |  | 1876.2 | 1876.2 | 0
S330800 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1213 | 30-Apr-21 A | 2021-07-28 | 60% | 3.2 |  |  | 485.2 | 485.2 | 0
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 21-Jun-21 A | 2021-07-30 | 25% | 6 |  |  | 909.75 | 909.75 | 0
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 32 | 3761 | 21-Jun-21 A | 2021-07-30 | 25% | 24 |  |  | 2820.75 | 2820.75 | 0
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | PROF3 PO E.PROF3 PO E | 8 | 1042 | 21-Jun-21 A | 2021-07-30 | 25% | 6 |  |  | 781.5 | 781.5 | 0
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | PROF4 PO M.PROF4 PO M | 16 | 2427 | 2021-08-02 | 2021-09-27 | 0% | 16 |  |  | 2427 | 2427 | 0
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | TECH3 PO D.TECH3 PO D | 72 | 8463 | 2021-08-02 | 2021-09-27 | 0% | 72 |  |  | 8463 | 8463 | 0
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | PROF3 PO E.PROF3 PO E | 16 | 2085 | 2021-08-02 | 2021-09-27 | 0% | 16 |  |  | 2085 | 2085 | 0
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | PROF4 PO M.PROF4 PO M | 48 | 7281 | 2021-09-28 | 2021-11-24 | 0% | 48 |  |  | 7281 | 7281 | 0
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | TECH3 PO D.TECH3 PO D | 144 | 16927 | 2021-09-28 | 2021-11-24 | 0% | 144 |  |  | 16927 | 16927 | 0
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | PROF3 PO E.PROF3 PO E | 48 | 6255 | 2021-09-28 | 2021-11-24 | 0% | 48 |  |  | 6255 | 6255 | 0
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | PROF4 PO M.PROF4 PO M | 48 | 7496 | 2021-11-29 | 2022-02-09 | 0% | 48 |  |  | 7496 | 7496 | 0
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | TECH3 PO D.TECH3 PO D | 144 | 17426 | 2021-11-29 | 2022-02-09 | 0% | 144 |  |  | 17426 | 17426 | 0
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | PROF3 PO E.PROF3 PO E | 48 | 6439 | 2021-11-29 | 2022-02-09 | 0% | 48 |  |  | 6439 | 6439 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-02-10 | 2022-02-24 | 0% | 8 |  |  | 1250 | 1250 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | TECH3 PO M.TECH3 PO M | 40 | 4843 | 2022-02-10 | 2022-02-24 | 0% | 40 |  |  | 4843 | 4843 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2022-02-10 | 2022-02-24 | 0% | 16 |  |  | 1937 | 1937 | 0
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | PROF3 PO E.PROF3 PO E | 8 | 1074 | 2022-02-10 | 2022-02-24 | 0% | 8 |  |  | 1074 | 1074 | 0
S331400 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 92000 | 108883 | 2021-11-29 | 2022-02-09 | 0% | 92000 |  |  | 108883 | 108883 | 0
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | PROF4 PO M.PROF4 PO M | 13 | 1914 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | SCI3 PO.SCI3 PO | 13 | 2237 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | TECH3 PO D.TECH3 PO D | 54 | 6163 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | PROF3 PO E.PROF3 PO E | 13 | 1645 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1213 | 30-Apr-21 A | 2021-07-28 | 85% | 1.2 |  |  | 181.95 | 181.95 | 0
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 32 | 3761 | 30-Apr-21 A | 2021-07-28 | 85% | 4.8 |  |  | 564.15 | 564.15 | 0
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | PROF3 PO E.PROF3 PO E | 8 | 1042 | 30-Apr-21 A | 2021-07-28 | 85% | 1.2 |  |  | 156.3 | 156.3 | 0
S330640 | Prototype System Development Labor | TECH3 PO D.TECH3 PO D | 180 | 21083 | 16-Mar-20 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S330640 | Prototype System Development Labor | PROF3 PO E.PROF3 PO E | 180 | 23371 | 16-Mar-20 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S330602 | Gather Power Reqs for Subsystem Racks on Detector | TECH3 PO D.TECH3 PO D | 120 | 13695 | 15-May-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330602 | Gather Power Reqs for Subsystem Racks on Detector | PROF3 PO E.PROF3 PO E | 120 | 15181 | 15-May-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330606 | Gather Rack Interlock Reqs and Specify Interlock Equipment | TECH3 PO D.TECH3 PO D | 80 | 9130 | 11-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330606 | Gather Rack Interlock Reqs and Specify Interlock Equipment | PROF3 PO E.PROF3 PO E | 80 | 10121 | 11-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330608 | Specify Power Controls Distribution Equipment | TECH3 PO D.TECH3 PO D | 120 | 13695 | 22-Jun-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330608 | Specify Power Controls Distribution Equipment | PROF3 PO E.PROF3 PO E | 120 | 15181 | 22-Jun-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330610 | Radiation Test for Water Leak Detection System | TECH3 PO D.TECH3 PO D | 40 | 4565 | 08-Apr-20 A | 29-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330610 | Radiation Test for Water Leak Detection System | PROF3 PO E.PROF3 PO E | 40 | 5060 | 08-Apr-20 A | 29-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330612 | Rack Interlock Conceptual Design | TECH3 PO D.TECH3 PO D | 240 | 27389 | 13-Mar-20 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330612 | Rack Interlock Conceptual Design | PROF3 PO E.PROF3 PO E | 240 | 30362 | 13-Mar-20 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330604 | Power Distribution Conceptual Gesign for Subsystem Racks on Detector | TECH3 PO D.TECH3 PO D | 120 | 13695 | 01-Jun-20 A | 19-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330604 | Power Distribution Conceptual Gesign for Subsystem Racks on Detector | PROF3 PO E.PROF3 PO E | 120 | 15181 | 01-Jun-20 A | 19-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S330642 | Prototype System Development M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 35000 | 40527 | 16-Mar-20 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.04.01.04 Detector Gas and Cooling Services Systems
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Cooling | PROF4 PO M.PROF4 PO M | 96 | 14137 | 22-Feb-21 A | 2021-07-15 | 33% | 64.32 |  |  | 9471.79 | 9471.79 | 0
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Cooling | TECH3 PO D.TECH3 PO D | 48 | 5478 | 22-Feb-21 A | 2021-07-15 | 33% | 32.16 |  |  | 3670.26 | 3670.26 | 0
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Cooling | TECH3 PO M.TECH3 PO M | 48 | 5478 | 22-Feb-21 A | 2021-07-15 | 33% | 32.16 |  |  | 3670.26 | 3670.26 | 0
S331900 | Review Detector Gas and Cooling Services Systems Design/Safety - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 08-Jun-21 A | 2021-08-31 | 50% | 8 |  |  | 1178 | 1178 | 0
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 20 | 3034 | 2021-09-01 | 2021-09-15 | 0% | 20 |  |  | 3034 | 3034 | 0
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 16 | 1881 | 2021-09-01 | 2021-09-15 | 0% | 16 |  |  | 1881 | 1881 | 0
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 16 | 1881 | 2021-09-01 | 2021-09-15 | 0% | 16 |  |  | 1881 | 1881 | 0
S332200 | Prepare Detector Cooling Services Systems Components Procurement Package(s) | PROF4 PO M.PROF4 PO M | 32 | 4854 | 2021-09-16 | 2021-11-30 | 0% | 32 |  |  | 4854 | 4854 | 0
S332200 | Prepare Detector Cooling Services Systems Components Procurement Package(s) | TECH3 PO D.TECH3 PO D | 72 | 8463 | 2021-09-16 | 2021-11-30 | 0% | 72 |  |  | 8463 | 8463 | 0
S332300 | Evaluate & Process Detector Cooling Services Systems Components Bids | PROF4 PO M.PROF4 PO M | 24 | 3640 | 2021-12-01 | 2022-01-13 | 0% | 24 |  |  | 3640 | 3640 | 0
S332300 | Evaluate & Process Detector Cooling Services Systems Components Bids | TECH3 PO D.TECH3 PO D | 24 | 2821 | 2021-12-01 | 2022-01-13 | 0% | 24 |  |  | 2821 | 2821 | 0
S332400 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) L | PROF4 PO M.PROF4 PO M | 96 | 14882 | 2022-01-14 | 2022-05-23 | 0% | 96 |  |  | 14882 | 14882 | 0
S332400 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) L | TECH3 PO D.TECH3 PO D | 96 | 11533 | 2022-01-14 | 2022-05-23 | 0% | 96 |  |  | 11533 | 11533 | 0
S332600 | Perform Detector Cooling Services Systems Components Acceptance | PROF4 PO M.PROF4 PO M | 16 | 2500 | 2022-05-24 | 2022-06-21 | 0% | 16 |  |  | 2500 | 2500 | 0
S332600 | Perform Detector Cooling Services Systems Components Acceptance | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2022-05-24 | 2022-06-21 | 0% | 16 |  |  | 1937 | 1937 | 0
S332600 | Perform Detector Cooling Services Systems Components Acceptance | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-05-24 | 2022-06-21 | 0% | 8 |  |  | 969 | 969 | 0
S332500 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 53000 | 62419 | 2022-01-14 | 2022-05-23 | 0% | 53000 |  |  | 62419 | 62419 | 0
S331705 | Analyze Detector Gas and Cooling Services Systems Requirements Split - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2356 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 168 | 24741 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 66 | 7532 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 66 | 7532 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | SCI3 PO.SCI3 PO | 66 | 11359 | 01-Oct-19 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2356 | 15-Jun-21 A | 2021-08-31 | 50% | 8 |  |  | 1178 | 1178 | 0
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 20 | 2282 | 15-Jun-21 A | 2021-08-31 | 50% | 10 |  |  | 1141 | 1141 | 0
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 913 | 15-Jun-21 A | 2021-08-31 | 50% | 4 |  |  | 456.5 | 456.5 | 0
S331710 | Design Coolin Manifolds for EMCal | PROF4 PO E.PROF4 PO E | 8 | 1178 | 18-Mar-20 A | 2021-07-15 | 40% | 4.8 |  |  | 706.8 | 706.8 | 0
S331710 | Design Coolin Manifolds for EMCal | TECH3 PO D.TECH3 PO D | 24 | 2739 | 18-Mar-20 A | 2021-07-15 | 40% | 14.4 |  |  | 1643.4 | 1643.4 | 0
S331720 | Design Coolin Manifolds for TPC | PROF4 PO E.PROF4 PO E | 8 | 1178 | 17-Mar-20 A | 16-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S331720 | Design Coolin Manifolds for TPC | TECH3 PO D.TECH3 PO D | 24 | 2739 | 17-Mar-20 A | 16-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S331730 | Design Coolin Manifolds for INTT | PROF4 PO E.PROF4 PO E | 8 | 1178 | 08-Dec-20 A | 2021-07-15 | 75% | 2 |  |  | 294.5 | 294.5 | 0
S331730 | Design Coolin Manifolds for INTT | TECH3 PO D.TECH3 PO D | 24 | 2739 | 08-Dec-20 A | 2021-07-15 | 75% | 6 |  |  | 684.75 | 684.75 | 0
S331740 | Design Coolin Manifolds for MVTX | PROF4 PO E.PROF4 PO E | 8 | 1178 | 08-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S331740 | Design Coolin Manifolds for MVTX | TECH3 PO D.TECH3 PO D | 24 | 2739 | 08-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S331750 | Conceptual Design for Routing Detector Cooling Chiller Systems to Det Manifolds | PROF4 PO E.PROF4 PO E | 8 | 1178 | 23-Feb-21 A | 2021-07-15 | 50% | 4 |  |  | 589 | 589 | 0
S331750 | Conceptual Design for Routing Detector Cooling Chiller Systems to Det Manifolds | TECH3 PO D.TECH3 PO D | 24 | 2739 | 23-Feb-21 A | 2021-07-15 | 50% | 12 |  |  | 1369.5 | 1369.5 | 0
S331760 | Conceptual Design for Cooling Tube Routing from Detector to IHCal manifold | PROF4 PO E.PROF4 PO E | 8 | 1178 | 2021-07-01 | 2021-07-08 | 0% | 8 |  |  | 1178 | 1178 | 0
S331760 | Conceptual Design for Cooling Tube Routing from Detector to IHCal manifold | TECH3 PO D.TECH3 PO D | 24 | 2739 | 2021-07-01 | 2021-07-08 | 0% | 24 |  |  | 2739 | 2739 | 0
S331770 | Conceptual Design for Cooling Tube Routing from Detector to EMCal manifold | PROF4 PO E.PROF4 PO E | 8 | 1199 | 08-Dec-20 A | 2021-07-15 | 20% | 6.4 |  |  | 959.2 | 959.2 | 0
S331770 | Conceptual Design for Cooling Tube Routing from Detector to EMCal manifold | TECH3 PO D.TECH3 PO D | 24 | 2788 | 08-Dec-20 A | 2021-07-15 | 20% | 19.2 |  |  | 2230.4 | 2230.4 | 0
S331780 | Conceptual Design for Cooling Tube Routing from Detector to TPC manifold | PROF4 PO E.PROF4 PO E | 8 | 1213 | 08-Dec-20 A | 2021-07-15 | 60% | 3.2 |  |  | 485.2 | 485.2 | 0
S331780 | Conceptual Design for Cooling Tube Routing from Detector to TPC manifold | TECH3 PO D.TECH3 PO D | 24 | 2821 | 08-Dec-20 A | 2021-07-15 | 60% | 9.6 |  |  | 1128.4 | 1128.4 | 0
S331790 | Conceptual Design for Cooling Tube Routing from Detector to INTT, MVTX manifold | PROF4 PO E.PROF4 PO E | 16 | 2427 | 14-Dec-20 A | 2021-07-15 | 5% | 15.2 |  |  | 2305.65 | 2305.65 | 0
S331790 | Conceptual Design for Cooling Tube Routing from Detector to INTT, MVTX manifold | TECH3 PO D.TECH3 PO D | 48 | 5642 | 14-Dec-20 A | 2021-07-15 | 5% | 45.6 |  |  | 5359.9 | 5359.9 | 0
S332705 | Conceptual Design for Routing Operating gas Line from Gas House to TPC Manifold | PROF4 PO M.PROF4 PO M | 8 | 1213 | 13-Jan-21 A | 20-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S332705 | Conceptual Design for Routing Operating gas Line from Gas House to TPC Manifold | TECH3 PO D.TECH3 PO D | 16 | 1881 | 13-Jan-21 A | 20-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S332710 | Conceptual Design for Routing N2 Line from Gas House to N2/Air Manifolds | PROF4 PO M.PROF4 PO M | 8 | 1213 | 18-Dec-20 A | 2021-07-19 | 80% | 1.6 |  |  | 242.6 | 242.6 | 0
S332710 | Conceptual Design for Routing N2 Line from Gas House to N2/Air Manifolds | TECH3 PO D.TECH3 PO D | 16 | 1881 | 18-Dec-20 A | 2021-07-19 | 80% | 3.2 |  |  | 376.2 | 376.2 | 0
S332715 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (MBD) | PROF4 PO M.PROF4 PO M | 8 | 1213 | 15-Feb-21 A | 2021-07-19 | 60% | 3.2 |  |  | 485.2 | 485.2 | 0
S332715 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (MBD) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 15-Feb-21 A | 2021-07-19 | 60% | 6.4 |  |  | 752.4 | 752.4 | 0
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | PROF4 PO M.PROF4 PO M | 8 | 1213 | 18-Dec-20 A | 2021-07-19 | 30% | 5.6 |  |  | 849.1 | 849.1 | 0
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 18-Dec-20 A | 2021-07-19 | 30% | 11.2 |  |  | 1316.7 | 1316.7 | 0
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | PROF4 PO M.PROF4 PO M | 8 | 1213 | 18-Dec-20 A | 2021-07-19 | 30% | 5.6 |  |  | 849.1 | 849.1 | 0
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 18-Dec-20 A | 2021-07-19 | 30% | 11.2 |  |  | 1316.7 | 1316.7 | 0
S332730 | Conceptual Design for Gas Tube Routing from Det to Operating Gas Manifolds (TPC) | PROF4 PO M.PROF4 PO M | 8 | 1213 | 22-Dec-20 A | 2021-07-19 | 50% | 4 |  |  | 606.5 | 606.5 | 0
S332730 | Conceptual Design for Gas Tube Routing from Det to Operating Gas Manifolds (TPC) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 22-Dec-20 A | 2021-07-19 | 50% | 8 |  |  | 940.5 | 940.5 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | PROF4 PO M.PROF4 PO M | 96 | 14562 | 15-Feb-21 A | 2021-09-24 | 30% | 67.2 |  |  | 10193.4 | 10193.4 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | TECH3 PO D.TECH3 PO D | 48 | 5642 | 15-Feb-21 A | 2021-09-24 | 30% | 33.6 |  |  | 3949.4 | 3949.4 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | TECH3 PO M.TECH3 PO M | 48 | 5642 | 15-Feb-21 A | 2021-09-24 | 30% | 33.6 |  |  | 3949.4 | 3949.4 | 0
S332740 | Review Detector Gas Service Systems Design/Safety | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-07-09 | 2021-07-22 | 0% | 8 |  |  | 1213 | 1213 | 0
S332740 | Review Detector Gas Service Systems Design/Safety | TECH3 PO D.TECH3 PO D | 16 | 1881 | 2021-07-09 | 2021-07-22 | 0% | 16 |  |  | 1881 | 1881 | 0
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 20 | 3034 | 2021-07-23 | 2021-08-05 | 0% | 20 |  |  | 3034 | 3034 | 0
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-07-23 | 2021-08-05 | 0% | 8 |  |  | 940 | 940 | 0
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-07-23 | 2021-08-05 | 0% | 8 |  |  | 940 | 940 | 0
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | PROF4 PO M.PROF4 PO M | 32 | 4854 | 2021-08-06 | 2021-12-16 | 0% | 32 |  |  | 4854 | 4854 | 0
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | TECH3 PO D.TECH3 PO D | 72 | 8463 | 2021-08-06 | 2021-12-16 | 0% | 72 |  |  | 8463 | 8463 | 0
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | PROF4 PO M.PROF4 PO M | 24 | 3648 | 2021-12-17 | 2022-02-01 | 0% | 24 |  |  | 3648 | 3648 | 0
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | TECH3 PO D.TECH3 PO D | 24 | 2827 | 2021-12-17 | 2022-02-01 | 0% | 24 |  |  | 2827 | 2827 | 0
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | PROF4 PO M.PROF4 PO M | 96 | 14998 | 2022-02-02 | 2022-07-22 | 0% | 96 |  |  | 14998 | 14998 | 0
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | TECH3 PO D.TECH3 PO D | 96 | 11623 | 2022-02-02 | 2022-07-22 | 0% | 96 |  |  | 11623 | 11623 | 0
S332770 | Procure & Deliver Detector Gas Services Systems Components - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 54000 | 63930 | 2022-02-02 | 2022-07-22 | 0% | 54000 |  |  | 63930 | 63930 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | PROF4 PO M.PROF4 PO M | 16 | 2500 | 2022-07-25 | 2022-08-19 | 0% | 16 |  |  | 2500 | 2500 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2022-07-25 | 2022-08-19 | 0% | 16 |  |  | 1937 | 1937 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-07-25 | 2022-08-19 | 0% | 8 |  |  | 969 | 969 | 0
S332712 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (IHCal) | PROF4 PO M.PROF4 PO M | 8 | 1213 | 15-Feb-21 A | 2021-07-19 | 30% | 5.6 |  |  | 849.1 | 849.1 | 0
S332712 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (IHCal) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 15-Feb-21 A | 2021-07-19 | 30% | 11.2 |  |  | 1316.7 | 1316.7 | 0
S331905 | Review Detector Cooling Services Systems Design/Safety | PROF4 PO E.PROF4 PO E | 16 | 2427 | 01-Jul-21* | 2021-07-15 | 0% | 16 |  |  | 2427 | 2427 | 0
2.04.01.05 Detector Safety Subsystems
S332800 | Analyze Detector Safety Subsystems Requirements - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1213 | 26-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S332900 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - CA-D Resource(s) | PROF4 AD.PROF4 AD | 12 | 1820 | 2021-08-02 | 2021-09-03 | 0% | 12 |  |  | 1820 | 1820 | 0
S333000 | Review Detector Safety Subsystems Design/Safety - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1213 | 2021-09-07 | 2021-09-20 | 0% | 8 |  |  | 1213 | 1213 | 0
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-09-21 | 2021-10-04 | 0% | 8 |  |  | 940 | 940 | 0
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | PROF4 PO E.PROF4 PO E | 16 | 2427 | 2021-09-21 | 2021-10-04 | 0% | 16 |  |  | 2427 | 2427 | 0
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-10-05 | 2021-10-19 | 0% | 8 |  |  | 940 | 940 | 0
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | PROF4 PO E.PROF4 PO E | 8 | 1213 | 2021-10-05 | 2021-10-19 | 0% | 8 |  |  | 1213 | 1213 | 0
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | TECH3 PO D.TECH3 PO D | 24 | 2821 | 2021-10-20 | 2021-12-03 | 0% | 24 |  |  | 2821 | 2821 | 0
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | PROF4 PO E.PROF4 PO E | 24 | 3640 | 2021-10-20 | 2021-12-03 | 0% | 24 |  |  | 3640 | 3640 | 0
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | TECH3 PO D.TECH3 PO D | 48 | 5780 | 2021-12-06 | 2022-03-03 | 0% | 48 |  |  | 5780 | 5780 | 0
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | PROF4 PO E.PROF4 PO E | 48 | 7459 | 2021-12-06 | 2022-03-03 | 0% | 48 |  |  | 7459 | 7459 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | TECH3 PO D.TECH3 PO D | 4 | 484 | 2022-03-04 | 2022-03-17 | 0% | 4 |  |  | 484 | 484 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | TECH3 PO M.TECH3 PO M | 4 | 484 | 2022-03-04 | 2022-03-17 | 0% | 4 |  |  | 484 | 484 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2022-03-04 | 2022-03-17 | 0% | 8 |  |  | 1250 | 1250 | 0
S333700 | Perform Detector Safety Subsystems Components Acceptance | TECH3 PO E.TECH3 PO E | 4 | 484 | 2022-03-04 | 2022-03-17 | 0% | 4 |  |  | 484 | 484 | 0
S333600 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 12000 | 14156 | 2021-12-06 | 2022-03-03 | 0% | 12000 |  |  | 14156 | 14156 | 0
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 48 | 7281 | 26-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | SCI3 PO.SCI3 PO | 24 | 4254 | 26-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 24 | 2821 | 26-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2821 | 26-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 24 | 2821 | 26-Apr-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 24 | 2821 | 2021-08-02 | 2021-09-03 | 0% | 24 |  |  | 2821 | 2821 | 0
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 48 | 7281 | 2021-08-02 | 2021-09-03 | 0% | 48 |  |  | 7281 | 7281 | 0
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-09-07 | 2021-09-20 | 0% | 8 |  |  | 940 | 940 | 0
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 16 | 2427 | 2021-09-07 | 2021-09-20 | 0% | 16 |  |  | 2427 | 2427 | 0
2.04.01.06 Gas Mixing House & Gas Pad Components
S333900 | Analyze Gas Mixing House & Gas Pad Components Requirements - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 01-Apr-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S334000 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents C | PROF4 AD.PROF4 AD | 8 | 1213 | 01-Apr-21 A | 2021-10-28 | 60% | 3.2 |  |  | 485.2 | 485.2 | 0
S334100 | Review Gas Mixing House & Gas Pad Components Design/Safety - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1213 | 2021-10-29 | 2021-11-12 | 0% | 8 |  |  | 1213 | 1213 | 0
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-11-15 | 2021-11-30 | 0% | 8 |  |  | 1213 | 1213 | 0
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | 8 |  |  | 940 | 940 | 0
S334400 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 2 | 303 | 2021-12-01 | 2022-01-13 | 0% | 2 |  |  | 303 | 303 | 0
S334500 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - CA-D Resource(s) | PROF4 AD.PROF4 AD | 2 | 303 | 2022-01-14 | 2022-02-28 | 0% | 2 |  |  | 303 | 303 | 0
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | PROF4 PO M.PROF4 PO M | 72 | 11205 | 2022-03-01 | 2022-05-09 | 0% | 72 |  |  | 11205 | 11205 | 0
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | TECH3 PO D.TECH3 PO D | 72 | 8683 | 2022-03-01 | 2022-05-09 | 0% | 72 |  |  | 8683 | 8683 | 0
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | TECH3 PO M.TECH3 PO M | 72 | 8683 | 2022-03-01 | 2022-05-09 | 0% | 72 |  |  | 8683 | 8683 | 0
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | TECH3 PO E.TECH3 PO E | 72 | 8683 | 2022-03-01 | 2022-05-09 | 0% | 72 |  |  | 8683 | 8683 | 0
S334800 | Perform Gas Mixing House & Gas Pad Components Acceptance - CA-D Resource(s) | PROF4 AD.PROF4 AD | 2 | 312 | 2022-05-10 | 2022-05-23 | 0% | 2 |  |  | 312 | 312 | 0
S334700 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 | 11808 | 2022-03-01 | 2022-05-09 | 0% | 10000 |  |  | 11808 | 11808 | 0
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 60 | 9101 | 01-Apr-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 24 | 2821 | 01-Apr-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2821 | 01-Apr-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 24 | 2821 | 01-Apr-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | PROF4 PO M.PROF4 PO M | 24 | 3640 | 01-Apr-21 A | 2021-10-28 | 60% | 9.6 |  |  | 1456 | 1456 | 0
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | TECH3 PO D.TECH3 PO D | 60 | 7053 | 01-Apr-21 A | 2021-10-28 | 60% | 24 |  |  | 2821.2 | 2821.2 | 0
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | TECH3 PO M.TECH3 PO M | 24 | 2821 | 01-Apr-21 A | 2021-10-28 | 60% | 9.6 |  |  | 1128.4 | 1128.4 | 0
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | TECH3 PO E.TECH3 PO E | 24 | 2821 | 01-Apr-21 A | 2021-10-28 | 60% | 9.6 |  |  | 1128.4 | 1128.4 | 0
S1003119 | Review Gas Mixing House & Gas Pad Components Design/Safety - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-10-29 | 2021-11-12 | 0% | 8 |  |  | 1213 | 1213 | 0
S1003119 | Review Gas Mixing House & Gas Pad Components Design/Safety - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-10-29 | 2021-11-12 | 0% | 8 |  |  | 940 | 940 | 0
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 24 | 3640 | 2021-12-01 | 2022-01-13 | 0% | 24 |  |  | 3640 | 3640 | 0
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 24 | 2821 | 2021-12-01 | 2022-01-13 | 0% | 24 |  |  | 2821 | 2821 | 0
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2821 | 2021-12-01 | 2022-01-13 | 0% | 24 |  |  | 2821 | 2821 | 0
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 24 | 2821 | 2021-12-01 | 2022-01-13 | 0% | 24 |  |  | 2821 | 2821 | 0
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 24 | 3640 | 2022-01-14 | 2022-02-28 | 0% | 24 |  |  | 3640 | 3640 | 0
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 24 | 2821 | 2022-01-14 | 2022-02-28 | 0% | 24 |  |  | 2821 | 2821 | 0
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2821 | 2022-01-14 | 2022-02-28 | 0% | 24 |  |  | 2821 | 2821 | 0
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 24 | 2821 | 2022-01-14 | 2022-02-28 | 0% | 24 |  |  | 2821 | 2821 | 0
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-05-10 | 2022-05-23 | 0% | 8 |  |  | 1250 | 1250 | 0
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-05-10 | 2022-05-23 | 0% | 8 |  |  | 969 | 969 | 0
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-05-10 | 2022-05-23 | 0% | 8 |  |  | 969 | 969 | 0
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-05-10 | 2022-05-23 | 0% | 8 |  |  | 969 | 969 | 0
2.04.01.07 Rack Room Modifications
S335000 | Analyze Rack Room Modifications Requirements - CA-D Resource(s) | PROF4 AD.PROF4 AD | 2 | 303 | 14-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | TECH3 PO D.TECH3 PO D | 8 | 961 | 2021-07-01 | 2021-08-26 | 0% | 8 |  |  | 961 | 961 | 0
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | PROF4 PO E.PROF4 PO E | 32 | 4959 | 2021-07-01 | 2021-08-26 | 0% | 32 |  |  | 4959 | 4959 | 0
S335200 | Review Rack Room Modifications Components Design/Safety | SCI3 PO.SCI3 PO | 8 | 1461 | 2021-08-27 | 2021-09-10 | 0% | 8 |  |  | 1461 | 1461 | 0
S335200 | Review Rack Room Modifications Components Design/Safety | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2021-08-27 | 2021-09-10 | 0% | 8 |  |  | 1250 | 1250 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | SCI3 PO.SCI3 PO | 8 | 1461 | 2021-09-13 | 2021-09-24 | 0% | 8 |  |  | 1461 | 1461 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2021-09-13 | 2021-09-24 | 0% | 16 |  |  | 1937 | 1937 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 969 | 2021-09-13 | 2021-09-24 | 0% | 8 |  |  | 969 | 969 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2021-09-13 | 2021-09-24 | 0% | 8 |  |  | 1250 | 1250 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | TECH3 PO E.TECH3 PO E | 8 | 969 | 2021-09-13 | 2021-09-24 | 0% | 8 |  |  | 969 | 969 | 0
S335500 | Prepare Rack Room Modifications Components Procurement Package(s) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 2 | 312 | 2021-09-27 | 2021-11-08 | 0% | 2 |  |  | 312 | 312 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | TECH3 PO D.TECH3 PO D | 8 | 969 | 2021-11-09 | 2021-12-09 | 0% | 8 |  |  | 969 | 969 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | TECH3 PO M.TECH3 PO M | 16 | 1937 | 2021-11-09 | 2021-12-09 | 0% | 16 |  |  | 1937 | 1937 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | PROF4 PO E.PROF4 PO E | 16 | 2500 | 2021-11-09 | 2021-12-09 | 0% | 16 |  |  | 2500 | 2500 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | TECH3 PO E.TECH3 PO E | 16 | 1937 | 2021-11-09 | 2021-12-09 | 0% | 16 |  |  | 1937 | 1937 | 0
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | TECH3 PO D.TECH3 PO D | 24 | 2906 | 2021-12-10 | 2022-03-09 | 0% | 24 |  |  | 2906 | 2906 | 0
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | TECH3 PO M.TECH3 PO M | 48 | 5811 | 2021-12-10 | 2022-03-09 | 0% | 48 |  |  | 5811 | 5811 | 0
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | PROF4 PO E.PROF4 PO E | 48 | 7499 | 2021-12-10 | 2022-03-09 | 0% | 48 |  |  | 7499 | 7499 | 0
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | TECH3 PO E.TECH3 PO E | 48 | 5811 | 2021-12-10 | 2022-03-09 | 0% | 48 |  |  | 5811 | 5811 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | SCI3 PO.SCI3 PO | 8 | 1461 | 2022-05-05 | 2022-05-18 | 0% | 8 |  |  | 1461 | 1461 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | TECH3 PO D.TECH3 PO D | 4 | 484 | 2022-05-05 | 2022-05-18 | 0% | 4 |  |  | 484 | 484 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-05-05 | 2022-05-18 | 0% | 8 |  |  | 969 | 969 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2022-05-05 | 2022-05-18 | 0% | 8 |  |  | 1250 | 1250 | 0
S335900 | Perform Rack Room Modifications Components Acceptance | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-05-05 | 2022-05-18 | 0% | 8 |  |  | 969 | 969 | 0
S335800 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 20000 | 23678 | 2021-12-10 | 2022-03-09 | 0% | 20000 |  |  | 23678 | 23678 | 0
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 32 | 4854 | 14-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | SCI3 PO.SCI3 PO | 32 | 5673 | 14-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 32 | 3761 | 14-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 32 | 3761 | 14-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 32 | 3761 | 14-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2906 | 2021-09-27 | 2021-11-08 | 0% | 24 |  |  | 2906 | 2906 | 0
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 24 | 3750 | 2021-09-27 | 2021-11-08 | 0% | 24 |  |  | 3750 | 3750 | 0
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 24 | 2906 | 2021-09-27 | 2021-11-08 | 0% | 24 |  |  | 2906 | 2906 | 0
2.04.01.08 Control Room and Offices Modifications
S336100 | Analyze Control Room and Offices Modifications Requirements - CA-D Resource(s) | PROF4 AD.PROF4 AD | 4 | 625 | 2021-09-27 | 2021-10-08 | 0% | 4 |  |  | 625 | 625 | 0
S336200 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents C | PROF4 AD.PROF4 AD | 2 | 312 | 2021-10-12 | 2021-10-18 | 0% | 2 |  |  | 312 | 312 | 0
S336300 | Review Control Room and Offices Modifications Design/Safety | SCI3 PO.SCI3 PO | 4 | 730 | 2021-10-19 | 2021-10-25 | 0% | 4 |  |  | 730 | 730 | 0
S336300 | Review Control Room and Offices Modifications Design/Safety | PROF4 PO E.PROF4 PO E | 4 | 625 | 2021-10-19 | 2021-10-25 | 0% | 4 |  |  | 625 | 625 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | SCI3 PO.SCI3 PO | 8 | 1461 | 2021-10-26 | 2021-11-08 | 0% | 8 |  |  | 1461 | 1461 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 969 | 2021-10-26 | 2021-11-08 | 0% | 8 |  |  | 969 | 969 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 969 | 2021-10-26 | 2021-11-08 | 0% | 8 |  |  | 969 | 969 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2021-10-26 | 2021-11-08 | 0% | 8 |  |  | 1250 | 1250 | 0
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | TECH3 PO E.TECH3 PO E | 8 | 969 | 2021-10-26 | 2021-11-08 | 0% | 8 |  |  | 969 | 969 | 0
S336600 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 2 | 312 | 2021-11-09 | 2021-12-23 | 0% | 2 |  |  | 312 | 312 | 0
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | TECH3 PO D.TECH3 PO D | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 969 | 969 | 0
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | TECH3 PO M.TECH3 PO M | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 969 | 969 | 0
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 1250 | 1250 | 0
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | TECH3 PO E.TECH3 PO E | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 969 | 969 | 0
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | TECH3 PO D.TECH3 PO D | 48 | 5811 | 2022-01-11 | 2022-02-23 | 0% | 48 |  |  | 5811 | 5811 | 0
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | TECH3 PO M.TECH3 PO M | 24 | 2906 | 2022-01-11 | 2022-02-23 | 0% | 24 |  |  | 2906 | 2906 | 0
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | PROF4 PO E.PROF4 PO E | 24 | 3750 | 2022-01-11 | 2022-02-23 | 0% | 24 |  |  | 3750 | 3750 | 0
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | TECH3 PO E.TECH3 PO E | 24 | 2906 | 2022-01-11 | 2022-02-23 | 0% | 24 |  |  | 2906 | 2906 | 0
S337000 | Perform Control Room and Offices Modifications Components Acceptance - CA-D Resource(s) | PROF4 AD.PROF4 AD | 2 | 312 | 2022-02-25 | 2022-03-10 | 0% | 2 |  |  | 312 | 312 | 0
S336900 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 59195 | 2022-01-12 | 2022-02-24 | 0% | 50000 |  |  | 59195 | 59195 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | SCI3 PO.SCI3 PO | 8 | 1461 | 2021-09-27 | 2021-10-08 | 0% | 8 |  |  | 1461 | 1461 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2021-09-27 | 2021-10-08 | 0% | 8 |  |  | 969 | 969 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2021-09-27 | 2021-10-08 | 0% | 8 |  |  | 969 | 969 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2021-09-27 | 2021-10-08 | 0% | 8 |  |  | 969 | 969 | 0
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2021-09-27 | 2021-10-08 | 0% | 8 |  |  | 1250 | 1250 | 0
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | TECH3 PO D.TECH3 PO D | 8 | 969 | 2021-10-12 | 2021-10-18 | 0% | 8 |  |  | 969 | 969 | 0
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | PROF4 PO E.PROF4 PO E | 4 | 625 | 2021-10-12 | 2021-10-18 | 0% | 4 |  |  | 625 | 625 | 0
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2906 | 2021-11-09 | 2021-12-23 | 0% | 24 |  |  | 2906 | 2906 | 0
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 24 | 3750 | 2021-11-09 | 2021-12-23 | 0% | 24 |  |  | 3750 | 3750 | 0
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 24 | 2906 | 2021-11-09 | 2021-12-23 | 0% | 24 |  |  | 2906 | 2906 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | SCI3 PO.SCI3 PO | 8 | 1461 | 2022-02-25 | 2022-03-10 | 0% | 8 |  |  | 1461 | 1461 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 4 | 484 | 2022-02-25 | 2022-03-10 | 0% | 4 |  |  | 484 | 484 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-02-25 | 2022-03-10 | 0% | 8 |  |  | 969 | 969 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2022-02-25 | 2022-03-10 | 0% | 8 |  |  | 1250 | 1250 | 0
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-02-25 | 2022-03-10 | 0% | 8 |  |  | 969 | 969 | 0
2.04.02 Infrastructure Facility Support Systems
S1000519 | Actuals - Labor - sPHENIX Infrastructure FY17 16724 | Actual Labor.Actual Labor | 36 | 6005 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000679 | Actuals - Labor - sPHENIX Infrastructure FY18 16724 | Actual Labor.Actual Labor | 405 | 67591 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1001679 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16724 | Actual Labor.Actual Labor | 250 | 41837 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1005000 | Actuals - Labor FY19 Jun-Sep 16724 | Actual Labor.Actual Labor | 137 | 22906 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1005040 | Actuals - NonLabor FY19 Jun-Sep 16724 | Actual NonLabor.Actual Nonlabor | 61593 | 67953 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR
S337300 | Create Cryo Routing in IR Layout Drawings - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 24 | 3534 | 01-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | TECH3 AD.TECH3 AD | 24 | 2739 | 30-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | TECH3 AD.TECH3 AD | 24 | 2739 | 30-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | TECH4 AD.TECH4 AD | 24 | 3134 | 30-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | PROF2 AD.PROF2 AD | 48 | 4811 | 30-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337500 | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety | TECH4 AD.TECH4 AD | 4 | 522 | 17-Jun-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337500 | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety | PROF2 AD.PROF2 AD | 8 | 802 | 17-Jun-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337600 | Address Action Items from Cryo Structural Support in IR Detail Design & Safety Reviews | TECH4 AD.TECH4 AD | 4 | 522 | 06-Oct-20 A | 13-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337600 | Address Action Items from Cryo Structural Support in IR Detail Design & Safety Reviews | PROF2 AD.PROF2 AD | 16 | 1604 | 06-Oct-20 A | 13-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | TECH4 AD.TECH4 AD | 24 | 3134 | 15-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | PROF2 AD.PROF2 AD | 88 | 8819 | 15-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | TECH4 AD.TECH4 AD | 20 | 2612 | 15-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S337900 | Evaluate & Process Magnet Cryo, Electrical & Control Structural Support in IR Components Bids | TECH4 AD.TECH4 AD | 24 | 3134 | 14-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S337900 | Evaluate & Process Magnet Cryo, Electrical & Control Structural Support in IR Components Bids | PROF2 AD.PROF2 AD | 48 | 4811 | 14-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S338000 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fab incl) - Labor | TECH4 AD.TECH4 AD | 64 | 8574 | 14-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S338000 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fab incl) - Labor | PROF2 AD.PROF2 AD | 128 | 13160 | 14-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S338100 | Perform Magnet Cryo, Electrical & Control Structural Support in IR Components Acceptance | TECH3 AD.TECH3 AD | 8 | 940 | 19-Jan-21 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S338100 | Perform Magnet Cryo, Electrical & Control Structural Support in IR Components Acceptance | PROF2 AD.PROF2 AD | 16 | 1652 | 19-Jan-21 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S337200 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fab incl) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 57892 | 14-Oct-20 A | 26-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S337310 | Create Cryo Routing in IR Layout Drawings - CA-D Resource(s) | TECH3 AD.TECH3 AD | 16 | 1826 | 01-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337310 | Create Cryo Routing in IR Layout Drawings - CA-D Resource(s) | TECH4 AD.TECH4 AD | 24 | 3134 | 01-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S337310 | Create Cryo Routing in IR Layout Drawings - CA-D Resource(s) | PROF2 AD.PROF2 AD | 80 | 8018 | 01-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S277000 | 2022 Facility Support Systems L3 Project Management | PROF2 AD.PROF2 AD | 352 | 37426 | 2021-10-01 | 2022-09-30 | 0% | 352 |  |  | 37426 | 37426 | 0
S277100 | 2023 Facility Support Systems L3 Project Management | PROF2 AD.PROF2 AD | 113 | 12375 | 2022-10-03 | 2022-10-07 | 0% | 113 |  |  | 12375 | 12375 | 0
2.04.02.02 Beampipe/Vacuum
S338400 | Create Beampipe/Vacuum Layout - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2427 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338400 | Create Beampipe/Vacuum Layout - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 32 | 3761 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338400 | Create Beampipe/Vacuum Layout - Physics Resource(s) | SCI3 PO.SCI3 PO | 16 | 2836 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338500 | Create Beampipe/Vacuum Envelope Drawing | TECH3 PO D.TECH3 PO D | 20 | 2351 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338600 | Create Beampipe/Vacuum subassembly and detail Drawings | TECH3 PO D.TECH3 PO D | 40 | 4702 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338700 | Review Beampipe/Vacuum Design/Safety - Physics Resource(s) | SCI3 PO.SCI3 PO | 4 | 709 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338700 | Review Beampipe/Vacuum Design/Safety - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 4 | 470 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338800 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S339000 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 01-Jul-20 A | 15-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S339100 | Evaluate & Process Beampipe/Vacuum Components Bids - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 15-Jul-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S339200 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 64 | 7523 | 04-Jan-21 A | 31-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S339300 | Perform Beampipe/vacuum Acceptance - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 965 | 2021-07-01 | 2022-04-20 | 0% | 8 |  |  | 965 | 965 | 0
S338300 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 58034 | 05-Jan-21 A | 31-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S338410 | Create Beampipe/Vacuum Layout - CA-D Resource(s) | PROF4 AD.PROF4 AD | 80 | 12135 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338710 | Review Beampipe/Vacuum Design/Safety - CA-D Resource(s) | PROF4 AD.PROF4 AD | 30 | 4550 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338710 | Review Beampipe/Vacuum Design/Safety - CA-D Resource(s) | TECH4 AD.TECH4 AD | 20 | 2690 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S338810 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews - CA-D Resource(s) | PROF4 AD.PROF4 AD | 50 | 7584 | 02-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S339010 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation - CA-D Resource(s) | PROF4 AD.PROF4 AD | 32 | 4854 | 16-Jul-20 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S339110 | Evaluate & Process Beampipe/Vacuum Components Bids - CA-D Resource(s) | PROF4 AD.PROF4 AD | 32 | 4854 | 16-Jul-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S339210 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 128 | 19415 | 04-Jan-21 A | 31-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) | TECH3 AD.TECH3 AD | 40 | 4824 | 2021-07-01 | 2022-04-20 | 0% | 40 |  |  | 4824 | 4824 | 0
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2490 | 2021-07-01 | 2022-04-20 | 0% | 16 |  |  | 2490 | 2490 | 0
S339350 | NEG Re-coating of beryllium beampipe | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 100000 | 111561 | 01-Jul-21* | 2022-07-15 | 0% | 100000 |  |  | 111561 | 111561 | 0
2.04.02.03 IR HVAC
S339600 | Model IR HVAC Thermal Requirements | TECH4 AD.TECH4 AD | 24 | 3228 | 01-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S339600 | Model IR HVAC Thermal Requirements | PROF2 AD.PROF2 AD | 48 | 4955 | 01-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S339600 | Model IR HVAC Thermal Requirements | CRAFT3.CRAFT3 | 8 | 1031 | 01-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S339600 | Model IR HVAC Thermal Requirements | PROF4 AD.PROF4 AD | 40 | 6067 | 01-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S339600 | Model IR HVAC Thermal Requirements | PROF6 AD.PROF6 AD | 10 | 1988 | 01-Oct-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | TECH4 AD.TECH4 AD | 8 | 1076 | 21-Dec-20 A | 2021-07-19 | 50% | 4 |  |  | 538 | 538 | 0
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | PROF2 AD.PROF2 AD | 32 | 3303 | 21-Dec-20 A | 2021-07-19 | 50% | 16 |  |  | 1651.5 | 1651.5 | 0
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | PROF4 AD.PROF4 AD | 8 | 1213 | 21-Dec-20 A | 2021-07-19 | 50% | 4 |  |  | 606.5 | 606.5 | 0
S339800 | Review IR HVAC Design/Safety | TECH4 AD.TECH4 AD | 4 | 538 | 2021-07-20 | 2021-07-26 | 0% | 4 |  |  | 538 | 538 | 0
S339800 | Review IR HVAC Design/Safety | PROF2 AD.PROF2 AD | 8 | 826 | 2021-07-20 | 2021-07-26 | 0% | 8 |  |  | 826 | 826 | 0
S339800 | Review IR HVAC Design/Safety | PROF4 AD.PROF4 AD | 4 | 607 | 2021-07-20 | 2021-07-26 | 0% | 4 |  |  | 607 | 607 | 0
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | TECH4 AD.TECH4 AD | 8 | 1076 | 2021-07-27 | 2021-08-09 | 0% | 8 |  |  | 1076 | 1076 | 0
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | PROF2 AD.PROF2 AD | 16 | 1652 | 2021-07-27 | 2021-08-09 | 0% | 16 |  |  | 1652 | 1652 | 0
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | PROF4 AD.PROF4 AD | 8 | 1213 | 2021-07-27 | 2021-08-09 | 0% | 8 |  |  | 1213 | 1213 | 0
S340100 | Prepare IR HVAC Components Procurement Package(s) | TECH4 AD.TECH4 AD | 16 | 2152 | 2021-08-10 | 2021-09-07 | 0% | 16 |  |  | 2152 | 2152 | 0
S340100 | Prepare IR HVAC Components Procurement Package(s) | PROF2 AD.PROF2 AD | 32 | 3303 | 2021-08-10 | 2021-09-07 | 0% | 32 |  |  | 3303 | 3303 | 0
S340100 | Prepare IR HVAC Components Procurement Package(s) | PROF4 AD.PROF4 AD | 4 | 607 | 2021-08-10 | 2021-09-07 | 0% | 4 |  |  | 607 | 607 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | TECH4 AD.TECH4 AD | 16 | 2152 | 2021-09-08 | 2021-10-05 | 0% | 16 |  |  | 2152 | 2152 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | PROF2 AD.PROF2 AD | 32 | 3303 | 2021-09-08 | 2021-10-05 | 0% | 32 |  |  | 3303 | 3303 | 0
S340200 | Evaluate & Process IR HVAC Components Bids | PROF4 AD.PROF4 AD | 4 | 607 | 2021-09-08 | 2021-10-05 | 0% | 4 |  |  | 607 | 607 | 0
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | TECH4 AD.TECH4 AD | 48 | 6457 | 2021-10-06 | 2022-01-05 | 0% | 48 |  |  | 6457 | 6457 | 0
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | PROF2 AD.PROF2 AD | 96 | 9910 | 2021-10-06 | 2022-01-05 | 0% | 96 |  |  | 9910 | 9910 | 0
S340400 | Perform IR HVAC Components Acceptance | TECH3 AD.TECH3 AD | 40 | 4702 | 2022-01-06 | 2022-01-20 | 0% | 40 |  |  | 4702 | 4702 | 0
S340400 | Perform IR HVAC Components Acceptance | TECH4 AD.TECH4 AD | 8 | 1076 | 2022-01-06 | 2022-01-20 | 0% | 8 |  |  | 1076 | 1076 | 0
S340400 | Perform IR HVAC Components Acceptance | PROF2 AD.PROF2 AD | 16 | 1652 | 2022-01-06 | 2022-01-20 | 0% | 16 |  |  | 1652 | 1652 | 0
S340400 | Perform IR HVAC Components Acceptance | PROF4 AD.PROF4 AD | 2 | 303 | 2022-01-06 | 2022-01-20 | 0% | 2 |  |  | 303 | 303 | 0
S339500 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 35000 | 40624 | 2021-10-06 | 2022-01-05 | 0% | 35000 |  |  | 40624 | 40624 | 0
2.04.02.04 IR Electronics Cooling Water Distribution System
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | TECH4 AD.TECH4 AD | 32 | 4304 | 21-Dec-20 A | 2021-07-19 | 80% | 6.4 |  |  | 860.8 | 860.8 | 0
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | PROF2 AD.PROF2 AD | 64 | 6606 | 21-Dec-20 A | 2021-07-19 | 80% | 12.8 |  |  | 1321.2 | 1321.2 | 0
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | PROF4 AD.PROF4 AD | 4 | 607 | 21-Dec-20 A | 2021-07-19 | 80% | 0.8 |  |  | 121.4 | 121.4 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | TECH4 AD.TECH4 AD | 8 | 1076 | 2021-07-20 | 2021-08-02 | 0% | 8 |  |  | 1076 | 1076 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | PROF2 AD.PROF2 AD | 16 | 1652 | 2021-07-20 | 2021-08-02 | 0% | 16 |  |  | 1652 | 1652 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | PROF4 AD.PROF4 AD | 4 | 607 | 2021-07-20 | 2021-08-02 | 0% | 4 |  |  | 607 | 607 | 0
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | TECH4 AD.TECH4 AD | 8 | 1076 | 2021-08-03 | 2021-08-16 | 0% | 8 |  |  | 1076 | 1076 | 0
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | PROF2 AD.PROF2 AD | 16 | 1652 | 2021-08-03 | 2021-08-16 | 0% | 16 |  |  | 1652 | 1652 | 0
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | PROF4 AD.PROF4 AD | 2 | 303 | 2021-08-03 | 2021-08-16 | 0% | 2 |  |  | 303 | 303 | 0
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | TECH4 AD.TECH4 AD | 16 | 2152 | 2021-08-17 | 2021-09-14 | 0% | 16 |  |  | 2152 | 2152 | 0
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | PROF2 AD.PROF2 AD | 32 | 3303 | 2021-08-17 | 2021-09-14 | 0% | 32 |  |  | 3303 | 3303 | 0
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | PROF4 AD.PROF4 AD | 4 | 607 | 2021-08-17 | 2021-09-14 | 0% | 4 |  |  | 607 | 607 | 0
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | TECH4 AD.TECH4 AD | 16 | 2152 | 2021-09-15 | 2021-10-13 | 0% | 16 |  |  | 2152 | 2152 | 0
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | PROF2 AD.PROF2 AD | 32 | 3303 | 2021-09-15 | 2021-10-13 | 0% | 32 |  |  | 3303 | 3303 | 0
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | PROF4 AD.PROF4 AD | 4 | 607 | 2021-09-15 | 2021-10-13 | 0% | 4 |  |  | 607 | 607 | 0
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | TECH4 AD.TECH4 AD | 40 | 5526 | 26-Apr-21 A | 2021-10-26 | 50% | 20 |  |  | 2763 | 2763 | 0
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | PROF2 AD.PROF2 AD | 80 | 8481 | 26-Apr-21 A | 2021-10-26 | 50% | 40 |  |  | 4240.5 | 4240.5 | 0
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | PROF4 AD.PROF4 AD | 2 | 312 | 26-Apr-21 A | 2021-10-26 | 50% | 1 |  |  | 156 | 156 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | TECH3 AD.TECH3 AD | 20 | 2421 | 2022-01-13 | 2022-01-20 | 0% | 20 |  |  | 2421 | 2421 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | TECH4 AD.TECH4 AD | 4 | 554 | 2022-01-13 | 2022-01-20 | 0% | 4 |  |  | 554 | 554 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | PROF2 AD.PROF2 AD | 8 | 851 | 2022-01-13 | 2022-01-20 | 0% | 8 |  |  | 851 | 851 | 0
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | PROF4 AD.PROF4 AD | 4 | 625 | 2022-01-13 | 2022-01-20 | 0% | 4 |  |  | 625 | 625 | 0
S340600 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 65000 | 76953 | 26-Apr-21 A | 2022-01-12 | 50% | 32500 |  |  | 38476.5 | 38476.5 | 0
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | TECH3 AD.TECH3 AD | 32 | 3761 | 01-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | TECH4 AD.TECH4 AD | 32 | 4304 | 01-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | PROF2 AD.PROF2 AD | 160 | 16516 | 01-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | PROF4 AD.PROF4 AD | 20 | 3034 | 01-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S340702 | Model IR Electronics Cooling Water Distribution Thermal Requirements - Physics Resource(s) Split | SCI3 PO.SCI3 PO | 30 | 5318 | 01-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.04.02.05 IR/AH Safety Subsystems
S341800 | Analyze IR/AH Safety Subsystems Requirements - Physics Resource(s) | SCI3 PO.SCI3 PO | 3 | 532 | 14-Dec-20 A | 2021-07-30 | 25% | 2.25 |  |  | 399 | 399 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | TECH4 AD.TECH4 AD | 60 | 8071 | 2021-08-02 | 2021-09-13 | 0% | 60 |  |  | 8071 | 8071 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | PROF2 AD.PROF2 AD | 96 | 9910 | 2021-08-02 | 2021-09-13 | 0% | 96 |  |  | 9910 | 9910 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | PROF4 AD.PROF4 AD | 8 | 1213 | 2021-08-02 | 2021-09-13 | 0% | 8 |  |  | 1213 | 1213 | 0
S342000 | Review IR/AH Safety Subsystems Design/Safety | TECH4 AD.TECH4 AD | 8 | 1076 | 2021-09-14 | 2021-09-27 | 0% | 8 |  |  | 1076 | 1076 | 0
S342000 | Review IR/AH Safety Subsystems Design/Safety | PROF2 AD.PROF2 AD | 32 | 3303 | 2021-09-14 | 2021-09-27 | 0% | 32 |  |  | 3303 | 3303 | 0
S342000 | Review IR/AH Safety Subsystems Design/Safety | PROF4 AD.PROF4 AD | 8 | 1213 | 2021-09-14 | 2021-09-27 | 0% | 8 |  |  | 1213 | 1213 | 0
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | TECH4 AD.TECH4 AD | 8 | 1076 | 2021-09-28 | 2021-10-12 | 0% | 8 |  |  | 1076 | 1076 | 0
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | PROF2 AD.PROF2 AD | 32 | 3303 | 2021-09-28 | 2021-10-12 | 0% | 32 |  |  | 3303 | 3303 | 0
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | PROF4 AD.PROF4 AD | 4 | 607 | 2021-09-28 | 2021-10-12 | 0% | 4 |  |  | 607 | 607 | 0
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | TECH4 AD.TECH4 AD | 8 | 1076 | 2021-10-13 | 2021-10-26 | 0% | 8 |  |  | 1076 | 1076 | 0
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | PROF2 AD.PROF2 AD | 16 | 1652 | 2021-10-13 | 2021-10-26 | 0% | 16 |  |  | 1652 | 1652 | 0
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | PROF4 AD.PROF4 AD | 4 | 607 | 2021-10-13 | 2021-10-26 | 0% | 4 |  |  | 607 | 607 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | TECH4 AD.TECH4 AD | 24 | 3228 | 2021-10-27 | 2021-12-10 | 0% | 24 |  |  | 3228 | 3228 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | PROF2 AD.PROF2 AD | 48 | 4955 | 2021-10-27 | 2021-12-10 | 0% | 48 |  |  | 4955 | 4955 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | PROF4 AD.PROF4 AD | 4 | 607 | 2021-10-27 | 2021-12-10 | 0% | 4 |  |  | 607 | 607 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | TECH4 AD.TECH4 AD | 48 | 6457 | 2021-12-13 | 2022-03-10 | 0% | 48 |  |  | 6457 | 6457 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | PROF2 AD.PROF2 AD | 96 | 9910 | 2021-12-13 | 2022-03-10 | 0% | 96 |  |  | 9910 | 9910 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | PROF4 AD.PROF4 AD | 2 | 303 | 2021-12-13 | 2022-03-10 | 0% | 2 |  |  | 303 | 303 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | TECH4 AD.TECH4 AD | 88 | 11837 | 2022-03-11 | 2022-03-24 | 0% | 88 |  |  | 11837 | 11837 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | PROF2 AD.PROF2 AD | 16 | 1652 | 2022-03-11 | 2022-03-24 | 0% | 16 |  |  | 1652 | 1652 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | PROF4 AD.PROF4 AD | 4 | 607 | 2022-03-11 | 2022-03-24 | 0% | 4 |  |  | 607 | 607 | 0
S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 32000 | 37142 | 2021-12-13 | 2022-03-10 | 0% | 32000 |  |  | 37142 | 37142 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | TECH4 AD.TECH4 AD | 72 | 9685 | 14-Dec-20 A | 2021-07-30 | 25% | 54 |  |  | 7263.75 | 7263.75 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | PROF2 AD.PROF2 AD | 96 | 9910 | 14-Dec-20 A | 2021-07-30 | 25% | 72 |  |  | 7432.5 | 7432.5 | 0
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | PROF4 AD.PROF4 AD | 10 | 1517 | 14-Dec-20 A | 2021-07-30 | 25% | 7.5 |  |  | 1137.75 | 1137.75 | 0
2.04.02.06 Assembly Hall and Interaction Region Modifications
S342900 | Analyze Assembly Hall Modification Requirements | TECH4 AD.TECH4 AD | 72 | 9685 | 04-Jan-21 A | 25-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S342900 | Analyze Assembly Hall Modification Requirements | PROF2 AD.PROF2 AD | 120 | 12387 | 04-Jan-21 A | 25-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S342900 | Analyze Assembly Hall Modification Requirements | PROF4 AD.PROF4 AD | 20 | 3034 | 04-Jan-21 A | 25-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | TECH4 AD.TECH4 AD | 24 | 3228 | 2021-07-01 | 2021-08-12 | 0% | 24 |  |  | 3228 | 3228 | 0
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | PROF2 AD.PROF2 AD | 48 | 4955 | 2021-07-01 | 2021-08-12 | 0% | 48 |  |  | 4955 | 4955 | 0
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | PROF4 AD.PROF4 AD | 20 | 3034 | 2021-07-01 | 2021-08-12 | 0% | 20 |  |  | 3034 | 3034 | 0
S343100 | Review Assembly Hall Modifications Design/Safety | TECH4 AD.TECH4 AD | 8 | 1076 | 2021-08-13 | 2021-08-26 | 0% | 8 |  |  | 1076 | 1076 | 0
S343100 | Review Assembly Hall Modifications Design/Safety | PROF2 AD.PROF2 AD | 16 | 1652 | 2021-08-13 | 2021-08-26 | 0% | 16 |  |  | 1652 | 1652 | 0
S343100 | Review Assembly Hall Modifications Design/Safety | PROF4 AD.PROF4 AD | 5 | 758 | 2021-08-13 | 2021-08-26 | 0% | 5 |  |  | 758 | 758 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | TECH4 AD.TECH4 AD | 8 | 1076 | 2021-08-27 | 2021-09-10 | 0% | 8 |  |  | 1076 | 1076 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | PROF2 AD.PROF2 AD | 16 | 1652 | 2021-08-27 | 2021-09-10 | 0% | 16 |  |  | 1652 | 1652 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | PROF4 AD.PROF4 AD | 5 | 758 | 2021-08-27 | 2021-09-10 | 0% | 5 |  |  | 758 | 758 | 0
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | TECH4 AD.TECH4 AD | 72 | 9685 | 2021-09-13 | 2021-10-25 | 0% | 72 |  |  | 9685 | 9685 | 0
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | PROF2 AD.PROF2 AD | 48 | 4955 | 2021-09-13 | 2021-10-25 | 0% | 48 |  |  | 4955 | 4955 | 0
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | PROF4 AD.PROF4 AD | 4 | 607 | 2021-09-13 | 2021-10-25 | 0% | 4 |  |  | 607 | 607 | 0
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | TECH4 AD.TECH4 AD | 72 | 9685 | 2021-10-26 | 2021-12-09 | 0% | 72 |  |  | 9685 | 9685 | 0
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | PROF2 AD.PROF2 AD | 48 | 4955 | 2021-10-26 | 2021-12-09 | 0% | 48 |  |  | 4955 | 4955 | 0
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | PROF4 AD.PROF4 AD | 2 | 303 | 2021-10-26 | 2021-12-09 | 0% | 2 |  |  | 303 | 303 | 0
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | TECH4 AD.TECH4 AD | 72 | 9685 | 2021-12-10 | 2022-04-20 | 0% | 72 |  |  | 9685 | 9685 | 0
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | PROF2 AD.PROF2 AD | 144 | 14865 | 2021-12-10 | 2022-04-20 | 0% | 144 |  |  | 14865 | 14865 | 0
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | PROF4 AD.PROF4 AD | 8 | 1213 | 2021-12-10 | 2022-04-20 | 0% | 8 |  |  | 1213 | 1213 | 0
S343700 | Perform Assembly Hall Modifications Components Acceptance | TECH4 AD.TECH4 AD | 24 | 3228 | 2022-04-21 | 2022-05-04 | 0% | 24 |  |  | 3228 | 3228 | 0
S343700 | Perform Assembly Hall Modifications Components Acceptance | PROF2 AD.PROF2 AD | 16 | 1652 | 2022-04-21 | 2022-05-04 | 0% | 16 |  |  | 1652 | 1652 | 0
S342800 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 | 11607 | 2021-12-10 | 2022-04-20 | 0% | 10000 |  |  | 11607 | 11607 | 0
S343810 | Start Track Modification - IR Structural Analysis of Existing Track System and Prelim Design | PROF3 AD.PROF3 AD | 120 | 15181 | 18-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343810 | Start Track Modification - IR Structural Analysis of Existing Track System and Prelim Design | PROF4 AD.PROF4 AD | 40 | 5891 | 18-Oct-19 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343814 | Start Track Modification - IR Assembly and Detail Drawings | PROF3 AD.PROF3 AD | 40 | 5060 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343814 | Start Track Modification - IR Assembly and Detail Drawings | PROF4 AD.PROF4 AD | 16 | 2356 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343814 | Start Track Modification - IR Assembly and Detail Drawings | TECH3 AD.TECH3 AD | 100 | 11412 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343812 | Start Track Modification - IR Prelim Design and Safety Review | PROF3 AD.PROF3 AD | 20 | 2530 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343812 | Start Track Modification - IR Prelim Design and Safety Review | PROF4 AD.PROF4 AD | 8 | 1178 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343822 | Start Track Modification - IR Prepare Procur. Package | TECH3 AD.TECH3 AD | 32 | 3652 | 01-Oct-20 A | 15-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343822 | Start Track Modification - IR Prepare Procur. Package | TECH4 AD.TECH4 AD | 16 | 2090 | 01-Oct-20 A | 15-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343818 | Start Track Modification - IR Address Action Items from D&S Review | PROF3 AD.PROF3 AD | 16 | 2024 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343818 | Start Track Modification - IR Address Action Items from D&S Review | TECH3 AD.TECH3 AD | 16 | 1826 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343816 | Start Track Modification - IR Final Design and Safety Review | TECH3 AD.TECH3 AD | 16 | 1826 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343816 | Start Track Modification - IR Final Design and Safety Review | PROF3 AD.PROF3 AD | 16 | 2024 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343816 | Start Track Modification - IR Final Design and Safety Review | PROF4 AD.PROF4 AD | 8 | 1178 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343836 | Start Track Modification - IR Develop and Submit Safety Plan | PROF3 AD.PROF3 AD | 24 | 3036 | 11-Jan-21 A | 16-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343826 | Start Track Modification - IR Provide Requirements to Procurements | PROF3 AD.PROF3 AD | 16 | 2024 | 23-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343824 | Start Track Modification - IR Procur. Readiness Review | PROF3 AD.PROF3 AD | 16 | 2024 | 16-Oct-20 A | 22-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343824 | Start Track Modification - IR Procur. Readiness Review | PROF4 AD.PROF4 AD | 8 | 1178 | 16-Oct-20 A | 22-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343824 | Start Track Modification - IR Procur. Readiness Review | TECH3 AD.TECH3 AD | 16 | 1826 | 16-Oct-20 A | 22-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343832 | Start Track Modification - IR Vendor Selection | PROF3 AD.PROF3 AD | 8 | 1012 | 11-Jan-21 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343830 | Start Track Modification - IR Vendor Responses | PROF3 AD.PROF3 AD | 8 | 1012 | 17-Nov-20 A | 29-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343828 | Start Track Modification - IR Prepare and Send Solicitations | PROF3 AD.PROF3 AD | 8 | 1012 | 02-Nov-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343842 | Start Track Modification - IR BNL Oversight of Construction | PROF3 AD.PROF3 AD | 108 | 13663 | 2021-08-31 | 2021-10-12 | 0% | 108 |  |  | 13663 | 13663 | 0
S343842 | Start Track Modification - IR BNL Oversight of Construction | PROF4 AD.PROF4 AD | 24 | 3534 | 2021-08-31 | 2021-10-12 | 0% | 24 |  |  | 3534 | 3534 | 0
S343850 | Start Track Modification - AH Prelim Design and Safety Review | PROF3 AD.PROF3 AD | 20 | 2530 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343850 | Start Track Modification - AH Prelim Design and Safety Review | PROF4 AD.PROF4 AD | 16 | 2356 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343848 | Start Track Modification - AH Structural Analysis of Existing Track System and Prelim. Design | PROF3 AD.PROF3 AD | 100 | 12651 | 18-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343848 | Start Track Modification - AH Structural Analysis of Existing Track System and Prelim. Design | PROF4 AD.PROF4 AD | 80 | 11781 | 18-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343844 | Start Track Modification - IR Delivery Acceptance Labor | PROF3 AD.PROF3 AD | 16 | 2024 | 2021-10-13 | 2021-10-19 | 0% | 16 |  |  | 2024 | 2024 | 0
S343844 | Start Track Modification - IR Delivery Acceptance Labor | PROF4 AD.PROF4 AD | 8 | 1178 | 2021-10-13 | 2021-10-19 | 0% | 8 |  |  | 1178 | 1178 | 0
S343864 | Start Track Modification - AH Survey and Grout Plates Labor | PROF3 AD.PROF3 AD | 20 | 2606 | 01-Feb-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343864 | Start Track Modification - AH Survey and Grout Plates Labor | PROF4 AD.PROF4 AD | 16 | 2427 | 01-Feb-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343864 | Start Track Modification - AH Survey and Grout Plates Labor | TECH3 AD.TECH3 AD | 180 | 21158 | 01-Feb-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343864 | Start Track Modification - AH Survey and Grout Plates Labor | CRAFT3.CRAFT3 | 144 | 18551 | 01-Feb-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343854 | Start Track Modification - AH Final Design and Safety Review | TECH3 AD.TECH3 AD | 16 | 1826 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343854 | Start Track Modification - AH Final Design and Safety Review | PROF4 AD.PROF4 AD | 16 | 2356 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343854 | Start Track Modification - AH Final Design and Safety Review | PROF3 AD.PROF3 AD | 16 | 2024 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343852 | Start Track Modification - AH Assembly and Detail Drawings | PROF3 AD.PROF3 AD | 60 | 7591 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343852 | Start Track Modification - AH Assembly and Detail Drawings | PROF4 AD.PROF4 AD | 24 | 3534 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343852 | Start Track Modification - AH Assembly and Detail Drawings | TECH3 AD.TECH3 AD | 80 | 9130 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343862 | Start Track Modification - AH Install Track Plates and Blocks | PROF3 AD.PROF3 AD | 80 | 10424 | 01-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343862 | Start Track Modification - AH Install Track Plates and Blocks | PROF4 AD.PROF4 AD | 16 | 2427 | 01-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343862 | Start Track Modification - AH Install Track Plates and Blocks | TECH3 AD.TECH3 AD | 16 | 1881 | 01-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343862 | Start Track Modification - AH Install Track Plates and Blocks | CRAFT3.CRAFT3 | 240 | 30918 | 01-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343860 | Start Track Modification - AH Fabricate Track Plates Labor | PROF3 AD.PROF3 AD | 40 | 5060 | 01-Feb-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343860 | Start Track Modification - AH Fabricate Track Plates Labor | PROF4 AD.PROF4 AD | 16 | 2356 | 01-Feb-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343856 | Start Track Modification - AH Address Action Items from D&S Review | PROF3 AD.PROF3 AD | 16 | 2024 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343856 | Start Track Modification - AH Address Action Items from D&S Review | PROF4 AD.PROF4 AD | 16 | 2356 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343856 | Start Track Modification - AH Address Action Items from D&S Review | TECH3 AD.TECH3 AD | 16 | 1826 | 08-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S343845 | Start Track Modification - IR Delivery Acceptance M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 140000 | 162496 | 2021-10-13 | 2021-10-19 | 0% | 140000 |  |  | 162496 | 162496 | 0
S343861 | Start Track Modification - AH Fabricate Track Plates M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 56896 | 01-Feb-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343865 | Start Track Modification - AH Survey and Grout Plates M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 | 11607 | 01-Feb-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S343849 | Addition of ReBar plus Concrete Forming and Placement for IR Tracks - Acceptance | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 550000 | 613587 | 2021-12-21 | 2021-12-21 | 0% | 550000 |  |  | 613587 | 613587 | 0
2.05 Integration and Installation
S1000279 | Actuals - Labor - sPHENIX Integration and Installation FY17 16727 | Actual Labor.Actual Labor | 109 | 18232 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000319 | Actuals - Labor - sPHENIX Integration and Installation FY17 16728 | Actual Labor.Actual Labor | 1 | 142 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S1000359 | Actuals - Labor - sPHENIX Integration and Installation FY18 16727 | Actual Labor.Actual Labor | 460 | 76883 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1000399 | Actuals - Labor - sPHENIX Integration and Installation FY18 16728 | Actual Labor.Actual Labor | 3 | 523 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1001119 | Actuals - Labor - sPHENIX Integration and Installation FY19 M8 16727 | Actual Labor.Actual Labor | 386 | 64551 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1001159 | Actuals - Labor - sPHENIX Integration and Installation FY19 M8 16728 | Actual Labor.Actual Labor | 14 | 2281 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1005080 | Actuals - Labor FY19 Jun-Sep 16727 | Actual Labor.Actual Labor | 230 | 38498 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1005120 | Actuals - Labor FY19 Jun-Sep 16728 | Actual Labor.Actual Labor | 18 | 2992 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
2.05.01 Subsystem Interface & Integration Plan
S344700 | Create Services Management Plan | PROF4 PO M.PROF4 PO M | 80 | 11781 | 02-Dec-19 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S344700 | Create Services Management Plan | TECH3 PO M.TECH3 PO M | 32 | 3652 | 02-Dec-19 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S344700 | Create Services Management Plan | TECH3 PO D.TECH3 PO D | 40 | 4565 | 02-Dec-19 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S344800 | Create Survey Plan | PROF4 PO M.PROF4 PO M | 40 | 5891 | 15-Sep-20 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S344800 | Create Survey Plan | TECH3 PO M.TECH3 PO M | 32 | 3652 | 15-Sep-20 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S344800 | Create Survey Plan | TECH3 PO D.TECH3 PO D | 40 | 4565 | 15-Sep-20 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345000 | Review Integration and Installation Plan Design/Safety | PROF4 PO M.PROF4 PO M | 20 | 2945 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345000 | Review Integration and Installation Plan Design/Safety | TECH3 PO D.TECH3 PO D | 20 | 2282 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345000 | Review Integration and Installation Plan Design/Safety | SCI3 PO.SCI3 PO | 20 | 3442 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345100 | Review Cable Management Plan | PROF4 PO M.PROF4 PO M | 20 | 2945 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345100 | Review Cable Management Plan | TECH3 PO D.TECH3 PO D | 10 | 1141 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345100 | Review Cable Management Plan | PROF4 PO E.PROF4 PO E | 10 | 1473 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345200 | Review Survey Plan | PROF4 PO M.PROF4 PO M | 10 | 1473 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345200 | Review Survey Plan | TECH3 PO M.TECH3 PO M | 10 | 1141 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345200 | Review Survey Plan | TECH3 PO D.TECH3 PO D | 10 | 1141 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey P | PROF4 PO M.PROF4 PO M | 10 | 1473 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey P | TECH3 PO M.TECH3 PO M | 10 | 1141 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey P | TECH3 PO D.TECH3 PO D | 10 | 1141 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S344900 | Create Installation Plan | PROF4 PO M.PROF4 PO M | 80 | 11781 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S344900 | Create Installation Plan | TECH3 PO D.TECH3 PO D | 160 | 18260 | 12-Jan-21 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.05.02 Infrastructure Installation
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 32 | 4961 | 2022-02-23 | 2022-03-22 | 0% | 32 |  |  | 4961 | 4961 | 0
S346500 | Install Cryogenics Supply Structural Support - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 80 | 12135 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346500 | Install Cryogenics Supply Structural Support - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 80 | 9404 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346500 | Install Cryogenics Supply Structural Support - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346300 | Install Beampipe/Vacuum/Bakeout - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 20 | 3125 | 2022-08-01 | 2022-08-09 | 0% | 20 |  |  | 3125 | 3125 | 0
S346300 | Install Beampipe/Vacuum/Bakeout - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 40 | 4843 | 2022-08-01 | 2022-08-09 | 0% | 40 |  |  | 4843 | 4843 | 0
S346300 | Install Beampipe/Vacuum/Bakeout - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2022-08-01 | 2022-08-09 | 0% | 16 |  |  | 1937 | 1937 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | TECH3 AD.TECH3 AD | 40 | 4702 | 2022-01-21 | 2022-02-03 | 0% | 40 |  |  | 4702 | 4702 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | CRAFT3.CRAFT3 | 64 | 8245 | 2022-01-21 | 2022-02-03 | 0% | 64 |  |  | 8245 | 8245 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | PROF2 AD.PROF2 AD | 40 | 4129 | 2022-01-21 | 2022-02-03 | 0% | 40 |  |  | 4129 | 4129 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | PROF4 AD.PROF4 AD | 40 | 6067 | 2022-01-21 | 2022-02-03 | 0% | 40 |  |  | 6067 | 6067 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | TECH3 AD.TECH3 AD | 80 | 9686 | 2022-01-21 | 2022-02-17 | 0% | 80 |  |  | 9686 | 9686 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | CRAFT3.CRAFT3 | 80 | 10615 | 2022-01-21 | 2022-02-17 | 0% | 80 |  |  | 10615 | 10615 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | PROF2 AD.PROF2 AD | 20 | 2126 | 2022-01-21 | 2022-02-17 | 0% | 20 |  |  | 2126 | 2126 | 0
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | PROF4 AD.PROF4 AD | 8 | 1250 | 2022-01-21 | 2022-02-17 | 0% | 8 |  |  | 1250 | 1250 | 0
S345800 | Install On Detector Safety Subsystems - Labor | TECH3 PO E.TECH3 PO E | 80 | 9686 | 2022-03-18 | 2022-04-14 | 0% | 80 |  |  | 9686 | 9686 | 0
S345800 | Install On Detector Safety Subsystems - Labor | TECH3 PO M.TECH3 PO M | 40 | 4843 | 2022-03-18 | 2022-04-14 | 0% | 40 |  |  | 4843 | 4843 | 0
S345800 | Install On Detector Safety Subsystems - Labor | PROF4 PO E.PROF4 PO E | 20 | 3125 | 2022-03-18 | 2022-04-14 | 0% | 20 |  |  | 3125 | 3125 | 0
S345800 | Install On Detector Safety Subsystems - Labor | PROF4 PO M.PROF4 PO M | 20 | 3125 | 2022-03-18 | 2022-04-14 | 0% | 20 |  |  | 3125 | 3125 | 0
S346900 | Install Detector Support Services Systems - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 40 | 4253 | 2022-06-06 | 2022-07-05 | 0% | 40 |  |  | 4253 | 4253 | 0
S347100 | Install Electronics Racks Rackroom - Labor | PROF4 PO M.PROF4 PO M | 120 | 18748 | 2022-02-25 | 2022-05-19 | 0% | 120 |  |  | 18748 | 18748 | 0
S347100 | Install Electronics Racks Rackroom - Labor | TECH3 PO E.TECH3 PO E | 280 | 33900 | 2022-02-25 | 2022-05-19 | 0% | 280 |  |  | 33900 | 33900 | 0
S347100 | Install Electronics Racks Rackroom - Labor | TECH3 PO M.TECH3 PO M | 280 | 33900 | 2022-02-25 | 2022-05-19 | 0% | 280 |  |  | 33900 | 33900 | 0
S347100 | Install Electronics Racks Rackroom - Labor | TECH3 PO D.TECH3 PO D | 48 | 5811 | 2022-02-25 | 2022-05-19 | 0% | 48 |  |  | 5811 | 5811 | 0
S347100 | Install Electronics Racks Rackroom - Labor | PROF4 PO E.PROF4 PO E | 120 | 18748 | 2022-02-25 | 2022-05-19 | 0% | 120 |  |  | 18748 | 18748 | 0
S347400 | Install Gas and Cooling System Services - Labor | PROF4 PO M.PROF4 PO M | 120 | 18748 | 2022-06-22 | 2022-08-17 | 0% | 120 |  |  | 18748 | 18748 | 0
S347400 | Install Gas and Cooling System Services - Labor | TECH3 PO M.TECH3 PO M | 720 | 87172 | 2022-06-22 | 2022-08-17 | 0% | 720 |  |  | 87172 | 87172 | 0
S347400 | Install Gas and Cooling System Services - Labor | TECH3 PO D.TECH3 PO D | 96 | 11623 | 2022-06-22 | 2022-08-17 | 0% | 96 |  |  | 11623 | 11623 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 80 | 12499 | 2022-05-24 | 2022-07-13 | 0% | 80 |  |  | 12499 | 12499 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2022-05-24 | 2022-07-13 | 0% | 160 |  |  | 19372 | 19372 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 160 | 19372 | 2022-05-24 | 2022-07-13 | 0% | 160 |  |  | 19372 | 19372 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 40 | 4843 | 2022-05-24 | 2022-07-13 | 0% | 40 |  |  | 4843 | 4843 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 80 | 12499 | 2022-05-24 | 2022-07-13 | 0% | 80 |  |  | 12499 | 12499 | 0
S346200 | Install Line Electric Power Distribution Off Detector - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 589 | 2022-02-23 | 2022-03-22 | 0% | 500 |  |  | 589 | 589 | 0
S346600 | Install Cryogenics Supply Structural Support - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 580 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346400 | Install Beampipe/Vacuum/Bakeout - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-01 | 2022-08-09 | 0% | 500 |  |  | 592 | 592 | 0
S345600 | Install IR HVAC - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 580 | 2022-01-21 | 2022-02-03 | 0% | 500 |  |  | 580 | 580 | 0
S347800 | Install IR Electronics Cooling Water Off Detector - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-01-21 | 2022-02-17 | 0% | 500 |  |  | 592 | 592 | 0
S345900 | Install On Detector Safety Subsystems - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-03-18 | 2022-04-14 | 0% | 500 |  |  | 592 | 592 | 0
S347000 | Install Detector Support Services Systems - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-06-06 | 2022-07-05 | 0% | 500 |  |  | 592 | 592 | 0
S347300 | Install Electronics Racks Rackroom - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-02-25 | 2022-05-19 | 0% | 500 |  |  | 592 | 592 | 0
S347500 | Install Gas and Cooling System Services - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-06-22 | 2022-08-17 | 0% | 500 |  |  | 592 | 592 | 0
S346800 | Install Non-IR Infrastructure - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-05-24 | 2022-07-13 | 0% | 500 |  |  | 592 | 592 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | TECH3 AD.TECH3 AD | 80 | 9404 | 2022-03-25 | 2022-04-21 | 0% | 80 |  |  | 9404 | 9404 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | PROF4 AD.PROF4 AD | 16 | 2427 | 2022-03-25 | 2022-04-21 | 0% | 16 |  |  | 2427 | 2427 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | PROF2 AD.PROF2 AD | 40 | 4129 | 2022-03-25 | 2022-04-21 | 0% | 40 |  |  | 4129 | 4129 | 0
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | CRAFT3.CRAFT3 | 24 | 3092 | 2022-03-25 | 2022-04-21 | 0% | 24 |  |  | 3092 | 3092 | 0
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 32 | 4999 | 2022-03-23 | 2022-04-19 | 0% | 32 |  |  | 4999 | 4999 | 0
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | PROF6 AD.PROF6 AD | 4 | 819 | 2022-03-23 | 2022-04-19 | 0% | 4 |  |  | 819 | 819 | 0
S347200 | Install Electronics Racks On Carriage - Labor | PROF4 PO M.PROF4 PO M | 120 | 18748 | 2022-05-20 | 2022-08-15 | 0% | 120 |  |  | 18748 | 18748 | 0
S347200 | Install Electronics Racks On Carriage - Labor | TECH3 PO E.TECH3 PO E | 280 | 33900 | 2022-05-20 | 2022-08-15 | 0% | 280 |  |  | 33900 | 33900 | 0
S347200 | Install Electronics Racks On Carriage - Labor | TECH3 PO M.TECH3 PO M | 280 | 33900 | 2022-05-20 | 2022-08-15 | 0% | 280 |  |  | 33900 | 33900 | 0
S347200 | Install Electronics Racks On Carriage - Labor | TECH3 PO D.TECH3 PO D | 48 | 5811 | 2022-05-20 | 2022-08-15 | 0% | 48 |  |  | 5811 | 5811 | 0
S347200 | Install Electronics Racks On Carriage - Labor | PROF4 PO E.PROF4 PO E | 120 | 18748 | 2022-05-20 | 2022-08-15 | 0% | 120 |  |  | 18748 | 18748 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-01-04 | 2022-02-01 | 0% | 80 |  |  | 9686 | 9686 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2022-01-04 | 2022-02-01 | 0% | 16 |  |  | 1937 | 1937 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | CRAFT3.CRAFT3 | 32 | 4246 | 2022-01-04 | 2022-02-01 | 0% | 32 |  |  | 4246 | 4246 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | PROF4 PO E.PROF4 PO E | 20 | 3125 | 2022-01-04 | 2022-02-01 | 0% | 20 |  |  | 3125 | 3125 | 0
S345910 | Install Off Detector Safety Subsystems - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 580 | 2022-03-25 | 2022-04-21 | 0% | 500 |  |  | 580 | 580 | 0
S346210 | Install Line Electric Power Distribution On Detector - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-03-23 | 2022-04-19 | 0% | 500 |  |  | 592 | 592 | 0
S347810 | Install IR Electronics Cooling Water On Detector - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-01-04 | 2022-02-01 | 0% | 500 |  |  | 592 | 592 | 0
S347310 | Install Electronics Racks On Carriage - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-05-20 | 2022-08-15 | 0% | 500 |  |  | 592 | 592 | 0
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 80 | 9404 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 160 | 20612 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 80 | 8258 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 32 | 4854 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | PROF6 AD.PROF6 AD | 8 | 1590 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 80 | 9686 | 2022-08-01 | 2022-08-09 | 0% | 80 |  |  | 9686 | 9686 | 0
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 80 | 8506 | 2022-08-01 | 2022-08-09 | 0% | 80 |  |  | 8506 | 8506 | 0
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 24 | 2906 | 2022-08-01 | 2022-08-09 | 0% | 24 |  |  | 2906 | 2906 | 0
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 6249 | 2022-08-01 | 2022-08-09 | 0% | 40 |  |  | 6249 | 6249 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 160 | 19372 | 2022-05-24 | 2022-07-13 | 0% | 160 |  |  | 19372 | 19372 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 160 | 21230 | 2022-05-24 | 2022-07-13 | 0% | 160 |  |  | 21230 | 21230 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 20 | 2126 | 2022-05-24 | 2022-07-13 | 0% | 20 |  |  | 2126 | 2126 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1250 | 2022-05-24 | 2022-07-13 | 0% | 8 |  |  | 1250 | 1250 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 32 | 3874 | 2022-06-06 | 2022-07-05 | 0% | 32 |  |  | 3874 | 3874 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 200 | 26538 | 2022-06-06 | 2022-07-05 | 0% | 200 |  |  | 26538 | 26538 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 80 | 12499 | 2022-06-06 | 2022-07-05 | 0% | 80 |  |  | 12499 | 12499 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 200 | 24214 | 2022-06-06 | 2022-07-05 | 0% | 200 |  |  | 24214 | 24214 | 0
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 200 | 24214 | 2022-06-06 | 2022-07-05 | 0% | 200 |  |  | 24214 | 24214 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 160 | 21065 | 2022-02-23 | 2022-03-22 | 0% | 160 |  |  | 21065 | 21065 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 40 | 6201 | 2022-02-23 | 2022-03-22 | 0% | 40 |  |  | 6201 | 6201 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | PROF6 AD.PROF6 AD | 4 | 813 | 2022-02-23 | 2022-03-22 | 0% | 4 |  |  | 813 | 813 | 0
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 80 | 10615 | 2022-03-23 | 2022-04-19 | 0% | 80 |  |  | 10615 | 10615 | 0
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | PROF4 PO E.PROF4 PO E | 40 | 6249 | 2022-03-23 | 2022-04-19 | 0% | 40 |  |  | 6249 | 6249 | 0
2.05.03 Cradle Carriage Assembly/Installation
S347900 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 20 | 2945 | 01-Oct-19 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S347900 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 160 | 18260 | 01-Oct-19 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348000 | (Planning Package) Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - Physics Resourc | PROF4 PO M.PROF4 PO M | 48 | 7069 | 01-May-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348000 | (Planning Package) Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - Physics Resourc | TECH3 PO D.TECH3 PO D | 160 | 18260 | 01-May-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348200 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 48 | 7069 | 01-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348200 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 30 | 3424 | 01-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348300 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resou | PROF4 PO M.PROF4 PO M | 8 | 1178 | 26-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348300 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resou | TECH3 PO D.TECH3 PO D | 8 | 913 | 26-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348400 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design&Safety Reviews-PO | PROF4 PO M.PROF4 PO M | 8 | 1192 | 26-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348400 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design&Safety Reviews-PO | TECH3 PO D.TECH3 PO D | 8 | 924 | 26-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348700 | Assemble base, carriage alignment and carriage roller supports - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2427 | 03-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348700 | Assemble base, carriage alignment and carriage roller supports - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 480 | 56422 | 03-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348700 | Assemble base, carriage alignment and carriage roller supports - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 03-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348900 | Assemble HCal cradle onto base - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2427 | 01-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348900 | Assemble HCal cradle onto base - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 80 | 9404 | 01-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348900 | Assemble HCal cradle onto base - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 01-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S349100 | Install magnet mounting feet - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 4 | 607 | 2021-09-07 | 2021-09-20 | 0% | 4 |  |  | 607 | 607 | 0
S349300 | Install platforms & access - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2500 | 2021-12-15 | 2022-01-03 | 0% | 16 |  |  | 2500 | 2500 | 0
S349300 | Install platforms & access - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 240 | 29057 | 2021-12-15 | 2022-01-03 | 0% | 240 |  |  | 29057 | 29057 | 0
S349300 | Install platforms & access - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2021-12-15 | 2022-01-03 | 0% | 16 |  |  | 1937 | 1937 | 0
S349500 | Install Pole Tips - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-03-09 | 2022-03-22 | 0% | 8 |  |  | 1250 | 1250 | 0
S349500 | Install Pole Tips - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 64 | 7749 | 2022-03-09 | 2022-03-22 | 0% | 64 |  |  | 7749 | 7749 | 0
S349500 | Install Pole Tips - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-03-09 | 2022-03-22 | 0% | 8 |  |  | 969 | 969 | 0
S348100 | (Planning Package) Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 40000 | 45517 | 01-Jul-20 A | 31-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348800 | Assemble base, carriage alignment and carriage roller supports - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 2500 | 2902 | 03-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348915 | Assemble HCal cradle onto base - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3000 | 3482 | 01-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S349200 | Install magnet mounting feet - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3000 | 3482 | 2021-09-07 | 2021-09-20 | 0% | 3000 |  |  | 3482 | 3482 | 0
S349400 | Install platforms & access - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 | 1184 | 2021-12-15 | 2022-01-03 | 0% | 1000 |  |  | 1184 | 1184 | 0
S349600 | Install Pole Tips - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3000 | 3552 | 2022-03-09 | 2022-03-22 | 0% | 3000 |  |  | 3552 | 3552 | 0
S347910 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - CA-D Resource(s) | PROF4 AD.PROF4 AD | 80 | 11781 | 01-Oct-19 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S347910 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - CA-D Resource(s) | TECH4 AD.TECH4 AD | 80 | 10448 | 01-Oct-19 A | 05-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348010 | (Planning Package) Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s | PROF4 AD.PROF4 AD | 192 | 28275 | 01-May-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348010 | (Planning Package) Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s | TECH4 AD.TECH4 AD | 20 | 2612 | 01-May-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348210 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 5891 | 01-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348210 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - CA-D Resource(s) | TECH4 AD.TECH4 AD | 20 | 2612 | 01-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348310 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource | PROF4 AD.PROF4 AD | 12 | 1767 | 26-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348310 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource | TECH4 AD.TECH4 AD | 8 | 1045 | 26-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348410 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design&Safety Reviews-AD | PROF4 AD.PROF4 AD | 8 | 1192 | 26-Oct-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 160 | 20612 | 03-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 88 | 13348 | 03-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 32 | 4304 | 03-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 72 | 8463 | 03-May-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348910 | Assemble HCal cradle onto base - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 6067 | 01-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S348910 | Assemble HCal cradle onto base - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 64 | 8245 | 01-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S349310 | Install platforms & access - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 176 | 27497 | 2021-12-15 | 2022-01-03 | 0% | 176 |  |  | 27497 | 27497 | 0
S349310 | Install platforms & access - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 72 | 8717 | 2021-12-15 | 2022-01-03 | 0% | 72 |  |  | 8717 | 8717 | 0
S349310 | Install platforms & access - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 80 | 11084 | 2021-12-15 | 2022-01-03 | 0% | 80 |  |  | 11084 | 11084 | 0
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 136 | 21248 | 2022-03-09 | 2022-03-22 | 0% | 136 |  |  | 21248 | 21248 | 0
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 120 | 15923 | 2022-03-09 | 2022-03-22 | 0% | 120 |  |  | 15923 | 15923 | 0
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 80 | 11084 | 2022-03-09 | 2022-03-22 | 0% | 80 |  |  | 11084 | 11084 | 0
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 10 | 1517 | 2021-09-07 | 2021-09-20 | 0% | 10 |  |  | 1517 | 1517 | 0
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 160 | 18807 | 2021-09-07 | 2021-09-20 | 0% | 160 |  |  | 18807 | 18807 | 0
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-09-07 | 2021-09-20 | 0% | 8 |  |  | 940 | 940 | 0
2.05.04 Outer Hcal Installation
S349900 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - Labor | PROF4 PO M.PROF4 PO M | 48 | 7069 | 15-Nov-19 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S349900 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - Labor | TECH3 PO D.TECH3 PO D | 48 | 5478 | 15-Nov-19 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S349900 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - Labor | TECH3 PO M.TECH3 PO M | 48 | 5478 | 15-Nov-19 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | PROF4 PO M.PROF4 PO M | 40 | 5891 | 16-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | TECH3 PO D.TECH3 PO D | 16 | 1826 | 16-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | TECH3 PO M.TECH3 PO M | 16 | 1826 | 16-Sep-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350200 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource(s) | PROF2 AD.PROF2 AD | 4 | 401 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350200 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource(s) | PROF4 AD.PROF4 AD | 4 | 589 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350300 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - C | PROF2 AD.PROF2 AD | 4 | 401 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350300 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - C | PROF4 AD.PROF4 AD | 4 | 589 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350600 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 8 | 826 | 29-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 600 | 80708 | 21-Jun-21 A | 2021-09-03 | 8% | 552 |  |  | 74251.36 | 74251.36 | 0
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 20 | 2065 | 21-Jun-21 A | 2021-09-03 | 8% | 18.4 |  |  | 1899.8 | 1899.8 | 0
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1213 | 21-Jun-21 A | 2021-09-03 | 8% | 7.36 |  |  | 1115.96 | 1115.96 | 0
S351000 | Transport Remainder of Outer Hcal Sectors to AH - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 8 | 851 | 2021-10-19 | 2021-11-01 | 0% | 8 |  |  | 851 | 851 | 0
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 480 | 66503 | 2021-10-26 | 2021-11-23 | 0% | 480 |  |  | 66503 | 66503 | 0
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 20 | 2126 | 2021-10-26 | 2021-11-23 | 0% | 20 |  |  | 2126 | 2126 | 0
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1250 | 2021-10-26 | 2021-11-23 | 0% | 8 |  |  | 1250 | 1250 | 0
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 4 | 484 | 2021-11-24 | 2021-12-02 | 0% | 4 |  |  | 484 | 484 | 0
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 20 | 2421 | 2021-11-24 | 2021-12-02 | 0% | 20 |  |  | 2421 | 2421 | 0
S351600 | Install Outer HCal Cables and Services - Labor | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2021-12-03 | 2022-01-03 | 0% | 80 |  |  | 9686 | 9686 | 0
S351600 | Install Outer HCal Cables and Services - Labor | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2021-12-03 | 2022-01-03 | 0% | 160 |  |  | 19372 | 19372 | 0
S351600 | Install Outer HCal Cables and Services - Labor | PROF4 PO E.PROF4 PO E | 80 | 12499 | 2021-12-03 | 2022-01-03 | 0% | 80 |  |  | 12499 | 12499 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-01-04 | 2022-01-18 | 0% | 8 |  |  | 1250 | 1250 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-01-04 | 2022-01-18 | 0% | 8 |  |  | 969 | 969 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-01-04 | 2022-01-18 | 0% | 8 |  |  | 969 | 969 | 0
S351800 | Review Outer HCal for Operational Readiness (ORR) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-01-04 | 2022-01-18 | 0% | 8 |  |  | 969 | 969 | 0
S351900 | Address Action Items from Outer Hcal ORR | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-01-19 | 2022-02-01 | 0% | 8 |  |  | 1250 | 1250 | 0
S351900 | Address Action Items from Outer Hcal ORR | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-01-19 | 2022-02-01 | 0% | 8 |  |  | 969 | 969 | 0
S351900 | Address Action Items from Outer Hcal ORR | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-01-19 | 2022-02-01 | 0% | 8 |  |  | 969 | 969 | 0
S351900 | Address Action Items from Outer Hcal ORR | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-01-19 | 2022-02-01 | 0% | 8 |  |  | 969 | 969 | 0
S352000 | Commission Outer HCal - Labor | PROF4 PO M.PROF4 PO M | 32 | 4999 | 2022-02-02 | 2022-03-02 | 0% | 32 |  |  | 4999 | 4999 | 0
S352000 | Commission Outer HCal - Labor | SCI3 PO.SCI3 PO | 160 | 29214 | 2022-02-02 | 2022-03-02 | 0% | 160 |  |  | 29214 | 29214 | 0
S352000 | Commission Outer HCal - Labor | TECH3 PO D.TECH3 PO D | 32 | 3874 | 2022-02-02 | 2022-03-02 | 0% | 32 |  |  | 3874 | 3874 | 0
S352000 | Commission Outer HCal - Labor | TECH3 PO M.TECH3 PO M | 320 | 38743 | 2022-02-02 | 2022-03-02 | 0% | 320 |  |  | 38743 | 38743 | 0
S352000 | Commission Outer HCal - Labor | PROF4 PO E.PROF4 PO E | 160 | 24997 | 2022-02-02 | 2022-03-02 | 0% | 160 |  |  | 24997 | 24997 | 0
S352000 | Commission Outer HCal - Labor | TECH3 PO E.TECH3 PO E | 320 | 38743 | 2022-02-02 | 2022-03-02 | 0% | 320 |  |  | 38743 | 38743 | 0
S350000 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 60000 | 68276 | 15-Nov-19 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S350700 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 580 | 29-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S350900 | Install Partial Outer HCal (Prior to SC Magnet Install) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 580 | 21-Jun-21 A | 2021-09-03 | 8% | 460 |  |  | 533.6 | 533.6 | 0
S351100 | Transport Remainder of Outer Hcal Sectors to AH - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2021-10-19 | 2021-11-01 | 0% | 500 |  |  | 592 | 592 | 0
S351300 | Install Remainder of Outer HCal Sectors - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2021-10-26 | 2021-11-23 | 0% | 500 |  |  | 592 | 592 | 0
S351500 | Align/Survey Outer Hcal to Centerline - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2021-11-24 | 2021-12-02 | 0% | 500 |  |  | 592 | 592 | 0
S351700 | Install Outer HCal Cables and Services - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2021-12-03 | 2022-01-03 | 0% | 500 |  |  | 592 | 592 | 0
S352200 | Commission Outer HCal - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-02-02 | 2022-03-02 | 0% | 500 |  |  | 592 | 592 | 0
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures FY20 | PROF4 PO M.PROF4 PO M | 30 | 4418 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures FY20 | TECH3 PO M.TECH3 PO M | 24 | 2739 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures FY20 | TECH3 PO D.TECH3 PO D | 60 | 6847 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S352100 | Commission Outer HCal - Labor | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 640 | 0 | 2022-02-02 | 2022-03-02 | 0% | 640 |  |  | 0 | 0 | 0
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 80 | 10615 | 2021-11-24 | 2021-12-02 | 0% | 80 |  |  | 10615 | 10615 | 0
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 7264 | 2021-11-24 | 2021-12-02 | 0% | 60 |  |  | 7264 | 7264 | 0
S350950 | Install Large Support Rings and Cross Braces and South-Side IHCal Support Tabs | TECH3 PO M.TECH3 PO M | 40 | 4758 | 2021-10-12 | 2021-10-18 | 0% | 40 |  |  | 4758 | 4758 | 0
S350950 | Install Large Support Rings and Cross Braces and South-Side IHCal Support Tabs | PROF4 PO M.PROF4 PO M | 40 | 6140 | 2021-10-12 | 2021-10-18 | 0% | 40 |  |  | 6140 | 6140 | 0
S1002279 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1178 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002279 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 913 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002279 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 913 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002359 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - P | PROF4 PO M.PROF4 PO M | 8 | 1178 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002359 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - P | TECH3 PO D.TECH3 PO D | 8 | 913 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002359 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - P | TECH3 PO M.TECH3 PO M | 8 | 913 | 15-Mar-21 A | 23-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1213 | 29-Jun-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 256 | 32979 | 29-Jun-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 940 | 29-Jun-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 128 | 15046 | 29-Jun-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 64 | 9708 | 21-Jun-21 A | 2021-09-03 | 8% | 58.88 |  |  | 8931.36 | 8931.36 | 0
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 48 | 5642 | 21-Jun-21 A | 2021-09-03 | 8% | 44.16 |  |  | 5190.64 | 5190.64 | 0
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 512 | 60183 | 21-Jun-21 A | 2021-09-03 | 8% | 471.04 |  |  | 55368.36 | 55368.36 | 0
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 600 | 77294 | 21-Jun-21 A | 2021-09-03 | 8% | 552 |  |  | 71110.48 | 71110.48 | 0
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2021-10-19 | 2021-11-01 | 0% | 8 |  |  | 1250 | 1250 | 0
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 256 | 33968 | 2021-10-19 | 2021-11-01 | 0% | 256 |  |  | 33968 | 33968 | 0
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2021-10-19 | 2021-11-01 | 0% | 8 |  |  | 969 | 969 | 0
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 128 | 15497 | 2021-10-19 | 2021-11-01 | 0% | 128 |  |  | 15497 | 15497 | 0
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 64 | 9999 | 2021-10-26 | 2021-11-23 | 0% | 64 |  |  | 9999 | 9999 | 0
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 64 | 7749 | 2021-10-26 | 2021-11-23 | 0% | 64 |  |  | 7749 | 7749 | 0
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 512 | 61989 | 2021-10-26 | 2021-11-23 | 0% | 512 |  |  | 61989 | 61989 | 0
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 480 | 63690 | 2021-10-26 | 2021-11-23 | 0% | 480 |  |  | 63690 | 63690 | 0
2.05.05 SC Magnet Installation
S352300 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 6067 | 15-Apr-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S352400 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 10 | 1517 | 17-Mar-21 A | 2021-07-29 | 75% | 2.5 |  |  | 379.25 | 379.25 | 0
S352600 | Prepare SC Magnet Integration/Installation Procedures - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1213 | 08-Feb-21 A | 23-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S352600 | Prepare SC Magnet Integration/Installation Procedures - CA-D Resource(s) | TECH4 AD.TECH4 AD | 80 | 10761 | 08-Feb-21 A | 23-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S352700 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D | PROF4 AD.PROF4 AD | 4 | 607 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S352700 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D | TECH4 AD.TECH4 AD | 4 | 538 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 940 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2427 | 2021-09-21 | 2021-09-22 | 0% | 16 |  |  | 2427 | 2427 | 0
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 4 | 470 | 2021-09-21 | 2021-09-22 | 0% | 4 |  |  | 470 | 470 | 0
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 32 | 3761 | 2021-09-21 | 2021-09-22 | 0% | 32 |  |  | 3761 | 3761 | 0
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2427 | 2021-09-23 | 2021-09-24 | 0% | 16 |  |  | 2427 | 2427 | 0
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 2 | 235 | 2021-09-23 | 2021-09-24 | 0% | 2 |  |  | 235 | 235 | 0
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 32 | 3761 | 2021-09-23 | 2021-09-24 | 0% | 32 |  |  | 3761 | 3761 | 0
S353500 | Align/Survey SC Magnet to Cradle - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 80 | 9404 | 2021-09-27 | 2021-10-08 | 0% | 80 |  |  | 9404 | 9404 | 0
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2489 | 2021-10-12 | 2021-11-08 | 0% | 16 |  |  | 2489 | 2489 | 0
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1929 | 2021-10-12 | 2021-11-08 | 0% | 16 |  |  | 1929 | 1929 | 0
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 16 | 1929 | 2021-10-12 | 2021-11-08 | 0% | 16 |  |  | 1929 | 1929 | 0
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2500 | 2021-11-09 | 2021-12-09 | 0% | 16 |  |  | 2500 | 2500 | 0
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2021-11-09 | 2021-12-09 | 0% | 16 |  |  | 1937 | 1937 | 0
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2021-11-09 | 2021-12-09 | 0% | 160 |  |  | 19372 | 19372 | 0
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2021-12-10 | 2021-12-23 | 0% | 8 |  |  | 1250 | 1250 | 0
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2021-12-10 | 2021-12-23 | 0% | 8 |  |  | 969 | 969 | 0
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2021-12-10 | 2021-12-23 | 0% | 8 |  |  | 969 | 969 | 0
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 1250 | 1250 | 0
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 969 | 969 | 0
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 969 | 969 | 0
S352500 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 | 34821 | 17-Mar-21 A | 2021-07-29 | 75% | 7500 |  |  | 8705.25 | 8705.25 | 0
S353200 | Transport SC Magnet from 912 to AH - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1500 | 1741 | 2021-09-21 | 2021-09-22 | 0% | 1500 |  |  | 1741 | 1741 | 0
S353400 | Install SC Magnet on Cradle - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1500 | 1741 | 2021-09-23 | 2021-09-24 | 0% | 1500 |  |  | 1741 | 1741 | 0
S353600 | Align/Survey SC Magnet to Cradle - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3500 | 4062 | 2021-09-27 | 2021-10-08 | 0% | 3500 |  |  | 4062 | 4062 | 0
S353800 | Prep SC Magnet for Run (Cryo) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3500 | 4131 | 2021-10-12 | 2021-11-08 | 0% | 3500 |  |  | 4131 | 4131 | 0
S354000 | Prep SC Magnet for Run (Electric) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3500 | 4144 | 2021-11-09 | 2021-12-09 | 0% | 3500 |  |  | 4144 | 4144 | 0
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 64 | 8245 | 2021-09-21 | 2021-09-22 | 0% | 64 |  |  | 8245 | 8245 | 0
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 2021-09-21 | 2021-09-22 | 0% | 16 |  |  | 2427 | 2427 | 0
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 2021-09-21 | 2021-09-22 | 0% | 16 |  |  | 2427 | 2427 | 0
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 64 | 8245 | 2021-09-23 | 2021-09-24 | 0% | 64 |  |  | 8245 | 8245 | 0
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 2021-09-23 | 2021-09-24 | 0% | 16 |  |  | 2427 | 2427 | 0
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 16 | 2427 | 2021-09-23 | 2021-09-24 | 0% | 16 |  |  | 2427 | 2427 | 0
S353510 | Align/Survey SC Magnet to Cradle - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 160 | 20612 | 2021-09-27 | 2021-10-08 | 0% | 160 |  |  | 20612 | 20612 | 0
S353510 | Align/Survey SC Magnet to Cradle - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 240 | 28211 | 2021-09-27 | 2021-10-08 | 0% | 240 |  |  | 28211 | 28211 | 0
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 320 | 38574 | 2021-10-12 | 2021-11-08 | 0% | 320 |  |  | 38574 | 38574 | 0
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | PROF6 AD.PROF6 AD | 16 | 3262 | 2021-10-12 | 2021-11-08 | 0% | 16 |  |  | 3262 | 3262 | 0
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 6222 | 2021-10-12 | 2021-11-08 | 0% | 40 |  |  | 6222 | 6222 | 0
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 160 | 19372 | 2021-11-09 | 2021-12-09 | 0% | 160 |  |  | 19372 | 19372 | 0
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | PROF6 AD.PROF6 AD | 16 | 3276 | 2021-11-09 | 2021-12-09 | 0% | 16 |  |  | 3276 | 3276 | 0
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 40 | 6249 | 2021-11-09 | 2021-12-09 | 0% | 40 |  |  | 6249 | 6249 | 0
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | TECH3 AD.TECH3 AD | 8 | 969 | 2021-12-10 | 2021-12-23 | 0% | 8 |  |  | 969 | 969 | 0
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | PROF6 AD.PROF6 AD | 8 | 1638 | 2021-12-10 | 2021-12-23 | 0% | 8 |  |  | 1638 | 1638 | 0
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1250 | 2021-12-10 | 2021-12-23 | 0% | 8 |  |  | 1250 | 1250 | 0
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | TECH3 AD.TECH3 AD | 8 | 969 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 969 | 969 | 0
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | PROF6 AD.PROF6 AD | 8 | 1638 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 1638 | 1638 | 0
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1250 | 2021-12-27 | 2022-01-10 | 0% | 8 |  |  | 1250 | 1250 | 0
S1003399 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 120 | 18202 | 15-Apr-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1003399 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2821 | 15-Apr-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1003399 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 120 | 14105 | 15-Apr-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 30 | 4550 | 17-Mar-21 A | 2021-07-29 | 75% | 7.5 |  |  | 1137.5 | 1137.5 | 0
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 10 | 1175 | 17-Mar-21 A | 2021-07-29 | 75% | 2.5 |  |  | 293.75 | 293.75 | 0
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 10 | 1175 | 17-Mar-21 A | 2021-07-29 | 75% | 2.5 |  |  | 293.75 | 293.75 | 0
S1003559 | Prepare SC Magnet Integration/Installation Procedures - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 20 | 3034 | 08-Feb-21 A | 23-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003559 | Prepare SC Magnet Integration/Installation Procedures - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 10 | 1175 | 08-Feb-21 A | 23-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003639 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics | PROF4 PO M.PROF4 PO M | 8 | 1213 | 15-Dec-20 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003639 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics | TECH3 PO M.TECH3 PO M | 8 | 940 | 15-Dec-20 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003639 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics | TECH3 PO D.TECH3 PO D | 8 | 940 | 15-Dec-20 A | 27-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
2.05.06 Inner Hcal Installation
S354500 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - Labor | PROF4 PO M.PROF4 PO M | 120 | 17672 | 2021-07-21 | 2021-10-14 | 0% | 120 |  |  | 17672 | 17672 | 0
S354500 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - Labor | TECH3 PO D.TECH3 PO D | 40 | 4565 | 2021-07-21 | 2021-10-14 | 0% | 40 |  |  | 4565 | 4565 | 0
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | PROF4 PO M.PROF4 PO M | 80 | 12046 | 08-Feb-21 A | 2021-11-12 | 75% | 20 |  |  | 3011.5 | 3011.5 | 0
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | TECH3 PO D.TECH3 PO D | 40 | 4668 | 08-Feb-21 A | 2021-11-12 | 75% | 10 |  |  | 1167 | 1167 | 0
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | PROF4 PO M.PROF4 PO M | 8 | 1213 | 15-Jun-21 A | 2021-11-30 | 25% | 6 |  |  | 909.75 | 909.75 | 0
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO M.TECH3 PO M | 8 | 940 | 15-Jun-21 A | 2021-11-30 | 25% | 6 |  |  | 705 | 705 | 0
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO D.TECH3 PO D | 8 | 940 | 15-Jun-21 A | 2021-11-30 | 25% | 6 |  |  | 705 | 705 | 0
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-12-01 | 2021-12-14 | 0% | 8 |  |  | 1213 | 1213 | 0
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-12-01 | 2021-12-14 | 0% | 8 |  |  | 940 | 940 | 0
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-12-01 | 2021-12-14 | 0% | 8 |  |  | 940 | 940 | 0
S355200 | Transport assembled Inner HCal Sectors to AH - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1213 | 08-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S355400 | Install Inner Hcal Assembly Insertion Fixture - Labor | PROF4 PO M.PROF4 PO M | 4 | 607 | 2021-12-15 | 2021-12-20 | 0% | 4 |  |  | 607 | 607 | 0
S355400 | Install Inner Hcal Assembly Insertion Fixture - Labor | TECH3 PO D.TECH3 PO D | 4 | 470 | 2021-12-15 | 2021-12-20 | 0% | 4 |  |  | 470 | 470 | 0
S355400 | Install Inner Hcal Assembly Insertion Fixture - Labor | TECH3 PO M.TECH3 PO M | 80 | 9404 | 2021-12-15 | 2021-12-20 | 0% | 80 |  |  | 9404 | 9404 | 0
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | PROF4 PO M.PROF4 PO M | 64 | 9708 | 2021-12-21 | 2021-12-27 | 0% | 64 |  |  | 9708 | 9708 | 0
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | TECH3 PO D.TECH3 PO D | 64 | 7523 | 2021-12-21 | 2021-12-27 | 0% | 64 |  |  | 7523 | 7523 | 0
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | TECH3 PO M.TECH3 PO M | 512 | 60183 | 2021-12-21 | 2021-12-27 | 0% | 512 |  |  | 60183 | 60183 | 0
S355800 | Install 1st Inner HCal Support Ring - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2021-12-28 | 2021-12-29 | 0% | 8 |  |  | 1250 | 1250 | 0
S355800 | Install 1st Inner HCal Support Ring - Labor | TECH3 PO D.TECH3 PO D | 2 | 242 | 2021-12-28 | 2021-12-29 | 0% | 2 |  |  | 242 | 242 | 0
S355800 | Install 1st Inner HCal Support Ring - Labor | TECH3 PO M.TECH3 PO M | 32 | 3874 | 2021-12-28 | 2021-12-29 | 0% | 32 |  |  | 3874 | 3874 | 0
S356000 | Install Inner HCal - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 120 | 16626 | 2021-12-30 | 2022-01-03 | 0% | 120 |  |  | 16626 | 16626 | 0
S356000 | Install Inner HCal - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 4 | 625 | 2021-12-30 | 2022-01-03 | 0% | 4 |  |  | 625 | 625 | 0
S356200 | Install 2nd Inner HCal Support Ring and South-Side IHCal Support Tabs - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-01-04 | 2022-01-05 | 0% | 8 |  |  | 1250 | 1250 | 0
S356200 | Install 2nd Inner HCal Support Ring and South-Side IHCal Support Tabs - Labor | TECH3 PO D.TECH3 PO D | 2 | 242 | 2022-01-04 | 2022-01-05 | 0% | 2 |  |  | 242 | 242 | 0
S356200 | Install 2nd Inner HCal Support Ring and South-Side IHCal Support Tabs - Labor | TECH3 PO M.TECH3 PO M | 32 | 3874 | 2022-01-04 | 2022-01-05 | 0% | 32 |  |  | 3874 | 3874 | 0
S356400 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 4 | 484 | 2022-01-06 | 2022-01-12 | 0% | 4 |  |  | 484 | 484 | 0
S356400 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 20 | 2421 | 2022-01-06 | 2022-01-12 | 0% | 20 |  |  | 2421 | 2421 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-01-13 | 2022-02-10 | 0% | 80 |  |  | 9686 | 9686 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2022-01-13 | 2022-02-10 | 0% | 160 |  |  | 19372 | 19372 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | PROF4 PO E.PROF4 PO E | 80 | 12499 | 2022-01-13 | 2022-02-10 | 0% | 80 |  |  | 12499 | 12499 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2022-02-11 | 2022-02-25 | 0% | 8 |  |  | 1250 | 1250 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-02-11 | 2022-02-25 | 0% | 8 |  |  | 1250 | 1250 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-02-11 | 2022-02-25 | 0% | 8 |  |  | 969 | 969 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-02-11 | 2022-02-25 | 0% | 8 |  |  | 969 | 969 | 0
S356800 | Inner HCal - Operational Readiness Review (ORR) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-02-11 | 2022-02-25 | 0% | 8 |  |  | 969 | 969 | 0
S356900 | Address Action Items from Inner Hcal ORR | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2022-02-28 | 2022-03-11 | 0% | 8 |  |  | 1250 | 1250 | 0
S356900 | Address Action Items from Inner Hcal ORR | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-02-28 | 2022-03-11 | 0% | 8 |  |  | 1250 | 1250 | 0
S356900 | Address Action Items from Inner Hcal ORR | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-02-28 | 2022-03-11 | 0% | 8 |  |  | 969 | 969 | 0
S356900 | Address Action Items from Inner Hcal ORR | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-02-28 | 2022-03-11 | 0% | 8 |  |  | 969 | 969 | 0
S356900 | Address Action Items from Inner Hcal ORR | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-02-28 | 2022-03-11 | 0% | 8 |  |  | 969 | 969 | 0
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | SCI3 PO.SCI3 PO | 320 | 58428 | 2022-03-14 | 2022-03-18 | 0% | 320 |  |  | 58428 | 58428 | 0
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | PROF4 PO E.PROF4 PO E | 160 | 24997 | 2022-03-14 | 2022-03-18 | 0% | 160 |  |  | 24997 | 24997 | 0
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2022-03-14 | 2022-03-18 | 0% | 160 |  |  | 19372 | 19372 | 0
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | TECH3 PO M.TECH3 PO M | 32 | 3874 | 2022-03-14 | 2022-03-18 | 0% | 32 |  |  | 3874 | 3874 | 0
S354600 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 80000 | 91034 | 21-Jul-21* | 2021-10-14 | 0% | 80000 |  |  | 91034 | 91034 | 0
S355300 | Transport assembled Inner HCal Sectors to AH - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 580 | 08-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S355500 | Install Inner Hcal Assembly Insertion Fixture - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 580 | 2021-12-15 | 2021-12-20 | 0% | 500 |  |  | 580 | 580 | 0
S355700 | Install Inner HCal assembly on Insertion Fixture - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 580 | 2021-12-21 | 2021-12-27 | 0% | 500 |  |  | 580 | 580 | 0
S355900 | Install 1st Inner HCal Support Ring - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2021-12-28 | 2021-12-29 | 0% | 500 |  |  | 592 | 592 | 0
S356100 | Install Inner HCal - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2021-12-30 | 2022-01-03 | 0% | 500 |  |  | 592 | 592 | 0
S356300 | Install 2nd Inner HCal Support Ring and South-Side IHCal Support Tabs - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-01-04 | 2022-01-05 | 0% | 500 |  |  | 592 | 592 | 0
S356500 | Align/Survey Inner HCal to SC Magnet Centerline - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-01-06 | 2022-01-12 | 0% | 500 |  |  | 592 | 592 | 0
S356700 | Install Inner HCal Cables and Services (if instrumented) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-01-13 | 2022-02-10 | 0% | 500 |  |  | 592 | 592 | 0
S357200 | Commission Inner HCal - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-03-14 | 2022-03-18 | 0% | 500 |  |  | 592 | 592 | 0
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures FY20 | PROF4 PO M.PROF4 PO M | 60 | 8836 | 01-Oct-19 A | 2021-07-20 | 95% | 3 |  |  | 441.8 | 441.8 | 0
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures FY20 | TECH3 PO D.TECH3 PO D | 120 | 13695 | 01-Oct-19 A | 2021-07-20 | 95% | 6 |  |  | 684.75 | 684.75 | 0
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 80 | 10615 | 2022-01-06 | 2022-01-12 | 0% | 80 |  |  | 10615 | 10615 | 0
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 7264 | 2022-01-06 | 2022-01-12 | 0% | 60 |  |  | 7264 | 7264 | 0
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 60 | 8313 | 2022-01-06 | 2022-01-12 | 0% | 60 |  |  | 8313 | 8313 | 0
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 16 | 2427 | 08-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 160 | 20612 | 08-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1881 | 08-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 120 | 14105 | 08-Feb-21 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2021-12-30 | 2022-01-03 | 0% | 8 |  |  | 1250 | 1250 | 0
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 2 | 242 | 2021-12-30 | 2022-01-03 | 0% | 2 |  |  | 242 | 242 | 0
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 32 | 3874 | 2021-12-30 | 2022-01-03 | 0% | 32 |  |  | 3874 | 3874 | 0
2.05.07 EMCal Installation
S357400 | Design EMCal Integration/Installation Tooling/Fixtures FY21 | PROF4 PO M.PROF4 PO M | 26 | 3944 | 11-Mar-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S357400 | Design EMCal Integration/Installation Tooling/Fixtures FY21 | TECH3 PO M.TECH3 PO M | 21 | 2468 | 11-Mar-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S357400 | Design EMCal Integration/Installation Tooling/Fixtures FY21 | TECH3 PO D.TECH3 PO D | 53 | 6230 | 11-Mar-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S357500 | (Planning Package) Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | PROF4 PO M.PROF4 PO M | 120 | 18202 | 01-Feb-21 A | 2021-07-30 | 40% | 72 |  |  | 10921.2 | 10921.2 | 0
S357500 | (Planning Package) Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | TECH3 PO M.TECH3 PO M | 48 | 5642 | 01-Feb-21 A | 2021-07-30 | 40% | 28.8 |  |  | 3385.2 | 3385.2 | 0
S357500 | (Planning Package) Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | TECH3 PO D.TECH3 PO D | 40 | 4702 | 01-Feb-21 A | 2021-07-30 | 40% | 24 |  |  | 2821.2 | 2821.2 | 0
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | PROF4 PO M.PROF4 PO M | 80 | 12135 | 01-Feb-21 A | 2021-08-13 | 40% | 48 |  |  | 7281 | 7281 | 0
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | TECH3 PO M.TECH3 PO M | 8 | 940 | 01-Feb-21 A | 2021-08-13 | 40% | 4.8 |  |  | 564 | 564 | 0
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | TECH3 PO D.TECH3 PO D | 40 | 4702 | 01-Feb-21 A | 2021-08-13 | 40% | 24 |  |  | 2821.2 | 2821.2 | 0
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | PROF4 PO M.PROF4 PO M | 8 | 1213 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO M.TECH3 PO M | 8 | 940 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO D.TECH3 PO D | 8 | 940 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 940 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 22-Mar-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1250 | 2022-01-13 | 2022-02-17 | 0% | 8 |  |  | 1250 | 1250 | 0
S358400 | Install EMCal Sectors - Labor | PROF4 PO M.PROF4 PO M | 64 | 9999 | 2022-01-14 | 2022-02-07 | 0% | 64 |  |  | 9999 | 9999 | 0
S358400 | Install EMCal Sectors - Labor | TECH3 PO D.TECH3 PO D | 64 | 7749 | 2022-01-14 | 2022-02-07 | 0% | 64 |  |  | 7749 | 7749 | 0
S358400 | Install EMCal Sectors - Labor | TECH3 PO M.TECH3 PO M | 512 | 61989 | 2022-01-14 | 2022-02-07 | 0% | 512 |  |  | 61989 | 61989 | 0
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 20 | 2421 | 2022-02-08 | 2022-02-16 | 0% | 20 |  |  | 2421 | 2421 | 0
S358800 | Install EMCal Cables and Services - Labor | TECH3 PO E.TECH3 PO E | 160 | 19372 | 2022-02-17 | 2022-03-08 | 0% | 160 |  |  | 19372 | 19372 | 0
S358800 | Install EMCal Cables and Services - Labor | TECH3 PO M.TECH3 PO M | 64 | 7749 | 2022-02-17 | 2022-03-08 | 0% | 64 |  |  | 7749 | 7749 | 0
S358800 | Install EMCal Cables and Services - Labor | PROF4 PO M.PROF4 PO M | 32 | 4999 | 2022-02-17 | 2022-03-08 | 0% | 32 |  |  | 4999 | 4999 | 0
S358800 | Install EMCal Cables and Services - Labor | TECH3 PO D.TECH3 PO D | 32 | 3874 | 2022-02-17 | 2022-03-08 | 0% | 32 |  |  | 3874 | 3874 | 0
S358800 | Install EMCal Cables and Services - Labor | CRAFT3.CRAFT3 | 320 | 42460 | 2022-02-17 | 2022-03-08 | 0% | 320 |  |  | 42460 | 42460 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-03-09 | 2022-03-15 | 0% | 8 |  |  | 1250 | 1250 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-03-09 | 2022-03-15 | 0% | 8 |  |  | 969 | 969 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-03-09 | 2022-03-15 | 0% | 8 |  |  | 969 | 969 | 0
S359000 | EMCal - Operational Readiness Review (ORR) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-03-09 | 2022-03-15 | 0% | 8 |  |  | 969 | 969 | 0
S359100 | Address Action Items from EMCal ORR | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-03-16 | 2022-03-29 | 0% | 8 |  |  | 1250 | 1250 | 0
S359100 | Address Action Items from EMCal ORR | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-03-16 | 2022-03-29 | 0% | 8 |  |  | 969 | 969 | 0
S359100 | Address Action Items from EMCal ORR | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-03-16 | 2022-03-29 | 0% | 8 |  |  | 969 | 969 | 0
S359100 | Address Action Items from EMCal ORR | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-03-16 | 2022-03-29 | 0% | 8 |  |  | 969 | 969 | 0
S359200 | Commission EMCal - Labor | SCI3 PO.SCI3 PO | 400 | 73035 | 2022-03-30 | 2022-05-03 | 0% | 400 |  |  | 73035 | 73035 | 0
S359200 | Commission EMCal - Labor | PROF4 PO E.PROF4 PO E | 40 | 6249 | 2022-03-30 | 2022-05-03 | 0% | 40 |  |  | 6249 | 6249 | 0
S359200 | Commission EMCal - Labor | TECH3 PO E.TECH3 PO E | 40 | 4843 | 2022-03-30 | 2022-05-03 | 0% | 40 |  |  | 4843 | 4843 | 0
S359200 | Commission EMCal - Labor | PROF4 PO M.PROF4 PO M | 40 | 6249 | 2022-03-30 | 2022-05-03 | 0% | 40 |  |  | 6249 | 6249 | 0
S359200 | Commission EMCal - Labor | TECH3 PO D.TECH3 PO D | 40 | 4843 | 2022-03-30 | 2022-05-03 | 0% | 40 |  |  | 4843 | 4843 | 0
S359200 | Commission EMCal - Labor | TECH3 PO M.TECH3 PO M | 40 | 4843 | 2022-03-30 | 2022-05-03 | 0% | 40 |  |  | 4843 | 4843 | 0
S357600 | (Planning Package) Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 | 34821 | 01-Feb-21 A | 2021-07-30 | 40% | 18000 |  |  | 20892.6 | 20892.6 | 0
S358300 | Transport Assembled EMCal Sectors to AH - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-01-13 | 2022-02-17 | 0% | 500 |  |  | 592 | 592 | 0
S358500 | Install EMCal Sectors - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-01-14 | 2022-02-07 | 0% | 500 |  |  | 592 | 592 | 0
S358700 | Align/Survey EMCal to SC Magnet Centerline - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-02-08 | 2022-02-16 | 0% | 500 |  |  | 592 | 592 | 0
S358900 | Install EMCal Cables and Services - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-02-17 | 2022-03-08 | 0% | 500 |  |  | 592 | 592 | 0
S359400 | Commission EMCal - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-03-30 | 2022-05-03 | 0% | 500 |  |  | 592 | 592 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 80 | 10615 | 2022-02-08 | 2022-02-16 | 0% | 80 |  |  | 10615 | 10615 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 7264 | 2022-02-08 | 2022-02-16 | 0% | 60 |  |  | 7264 | 7264 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 60 | 8313 | 2022-02-08 | 2022-02-16 | 0% | 60 |  |  | 8313 | 8313 | 0
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 120 | 15923 | 2022-01-13 | 2022-02-17 | 0% | 120 |  |  | 15923 | 15923 | 0
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 64 | 7749 | 2022-01-13 | 2022-02-17 | 0% | 64 |  |  | 7749 | 7749 | 0
2.05.08 TPC Installation
S359700 | (Planning Package) Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | PROF4 PO M.PROF4 PO M | 60 | 9101 | 2021-07-15 | 2021-11-22 | 0% | 60 |  |  | 9101 | 9101 | 0
S359700 | (Planning Package) Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | TECH3 PO D.TECH3 PO D | 20 | 2351 | 2021-07-15 | 2021-11-22 | 0% | 20 |  |  | 2351 | 2351 | 0
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | PROF4 PO M.PROF4 PO M | 40 | 6067 | 10-Feb-21 A | 2021-12-08 | 50% | 20 |  |  | 3033.5 | 3033.5 | 0
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | TECH3 PO M.TECH3 PO M | 8 | 940 | 10-Feb-21 A | 2021-12-08 | 50% | 4 |  |  | 470 | 470 | 0
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | TECH3 PO D.TECH3 PO D | 20 | 2351 | 10-Feb-21 A | 2021-12-08 | 50% | 10 |  |  | 1175.5 | 1175.5 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-12-09 | 2021-12-22 | 0% | 8 |  |  | 1213 | 1213 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-12-09 | 2021-12-22 | 0% | 8 |  |  | 940 | 940 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-12-09 | 2021-12-22 | 0% | 8 |  |  | 940 | 940 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-12-23 | 2022-01-07 | 0% | 8 |  |  | 1213 | 1213 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-12-23 | 2022-01-07 | 0% | 8 |  |  | 940 | 940 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-12-23 | 2022-01-07 | 0% | 8 |  |  | 940 | 940 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-06-30 | 2022-07-07 | 0% | 8 |  |  | 1250 | 1250 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 24 | 2906 | 2022-06-30 | 2022-07-07 | 0% | 24 |  |  | 2906 | 2906 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-06-30 | 2022-07-07 | 0% | 8 |  |  | 969 | 969 | 0
S360700 | Install TPC Support - Labor | PROF4 PO M.PROF4 PO M | 4 | 625 | 2022-07-11 | 2022-07-15 | 0% | 4 |  |  | 625 | 625 | 0
S360700 | Install TPC Support - Labor | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2022-07-11 | 2022-07-15 | 0% | 16 |  |  | 1937 | 1937 | 0
S360700 | Install TPC Support - Labor | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-07-11 | 2022-07-15 | 0% | 80 |  |  | 9686 | 9686 | 0
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 8 | 851 | 2022-07-18 | 2022-07-22 | 0% | 8 |  |  | 851 | 851 | 0
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 20 | 2421 | 2022-07-25 | 2022-07-29 | 0% | 20 |  |  | 2421 | 2421 | 0
S361300 | Install TPC Cables and Services - Labor | TECH3 PO E.TECH3 PO E | 120 | 14529 | 2022-08-10 | 2022-08-30 | 0% | 120 |  |  | 14529 | 14529 | 0
S361300 | Install TPC Cables and Services - Labor | TECH3 PO M.TECH3 PO M | 60 | 7264 | 2022-08-10 | 2022-08-30 | 0% | 60 |  |  | 7264 | 7264 | 0
S361300 | Install TPC Cables and Services - Labor | PROF4 PO M.PROF4 PO M | 24 | 3750 | 2022-08-10 | 2022-08-30 | 0% | 24 |  |  | 3750 | 3750 | 0
S361300 | Install TPC Cables and Services - Labor | TECH3 PO D.TECH3 PO D | 24 | 2906 | 2022-08-10 | 2022-08-30 | 0% | 24 |  |  | 2906 | 2906 | 0
S361300 | Install TPC Cables and Services - Labor | CRAFT3.CRAFT3 | 240 | 31845 | 2022-08-10 | 2022-08-30 | 0% | 240 |  |  | 31845 | 31845 | 0
S361500 | TPC - Operational Readiness Review (ORR) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-08-31 | 2022-09-07 | 0% | 8 |  |  | 1250 | 1250 | 0
S361500 | TPC - Operational Readiness Review (ORR) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-08-31 | 2022-09-07 | 0% | 8 |  |  | 969 | 969 | 0
S361500 | TPC - Operational Readiness Review (ORR) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-08-31 | 2022-09-07 | 0% | 8 |  |  | 969 | 969 | 0
S361500 | TPC - Operational Readiness Review (ORR) | PROF3 PO E.PROF3 PO E | 8 | 1074 | 2022-08-31 | 2022-09-07 | 0% | 8 |  |  | 1074 | 1074 | 0
S361600 | Address Action Items from TPC ORR | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-09-08 | 2022-09-14 | 0% | 8 |  |  | 1250 | 1250 | 0
S361600 | Address Action Items from TPC ORR | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-09-08 | 2022-09-14 | 0% | 8 |  |  | 969 | 969 | 0
S361600 | Address Action Items from TPC ORR | PROF3 PO E.PROF3 PO E | 8 | 1074 | 2022-09-08 | 2022-09-14 | 0% | 8 |  |  | 1074 | 1074 | 0
S361600 | Address Action Items from TPC ORR | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-09-08 | 2022-09-14 | 0% | 8 |  |  | 969 | 969 | 0
S361700 | Commission TPC - Labor Phys | PROF4 PO E.PROF4 PO E | 40 | 6262 | 2022-09-15 | 2022-10-05 | 0% | 40 |  |  | 6262 | 6262 | 0
S361700 | Commission TPC - Labor Phys | TECH3 PO E.TECH3 PO E | 40 | 4853 | 2022-09-15 | 2022-10-05 | 0% | 40 |  |  | 4853 | 4853 | 0
S361700 | Commission TPC - Labor Phys | SCI3 PO.SCI3 PO | 400 | 73181 | 2022-09-15 | 2022-10-05 | 0% | 400 |  |  | 73181 | 73181 | 0
S361700 | Commission TPC - Labor Phys | TECH3 PO M.TECH3 PO M | 40 | 4853 | 2022-09-15 | 2022-10-05 | 0% | 40 |  |  | 4853 | 4853 | 0
S361700 | Commission TPC - Labor Phys | PROF4 PO M.PROF4 PO M | 40 | 6262 | 2022-09-15 | 2022-10-05 | 0% | 40 |  |  | 6262 | 6262 | 0
S361700 | Commission TPC - Labor Phys | TECH3 PO D.TECH3 PO D | 40 | 4853 | 2022-09-15 | 2022-10-05 | 0% | 40 |  |  | 4853 | 4853 | 0
S359800 | (Planning Package) Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 | 34821 | 2021-07-15 | 2021-11-22 | 0% | 30000 |  |  | 34821 | 34821 | 0
S360500 | Transport Assembled TPC Sections to AH - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-06-30 | 2022-07-07 | 0% | 500 |  |  | 592 | 592 | 0
S360800 | Install TPC Support - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-07-11 | 2022-07-15 | 0% | 500 |  |  | 592 | 592 | 0
S361000 | Install TPC (Mechanical) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-07-18 | 2022-07-22 | 0% | 500 |  |  | 592 | 592 | 0
S361200 | Align/Survey TPC to SC Magnet Centerline - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-07-25 | 2022-07-29 | 0% | 500 |  |  | 592 | 592 | 0
S361400 | Install TPC Cables and Services - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-10 | 2022-08-30 | 0% | 500 |  |  | 592 | 592 | 0
S361900 | Commission TPC - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 593 | 2022-09-15 | 2022-10-05 | 0% | 500 |  |  | 593 | 593 | 0
S360600 | Open SC Magnet Pole Tip Doors | PROF4 PO M.PROF4 PO M | 4 | 625 | 2022-07-08 | 2022-07-08 | 0% | 4 |  |  | 625 | 625 | 0
S360600 | Open SC Magnet Pole Tip Doors | TECH3 PO M.TECH3 PO M | 16 | 1937 | 2022-07-08 | 2022-07-08 | 0% | 16 |  |  | 1937 | 1937 | 0
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1250 | 2022-06-30 | 2022-07-07 | 0% | 8 |  |  | 1250 | 1250 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 80 | 10615 | 2022-07-25 | 2022-07-29 | 0% | 80 |  |  | 10615 | 10615 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 7264 | 2022-07-25 | 2022-07-29 | 0% | 60 |  |  | 7264 | 7264 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 60 | 8313 | 2022-07-25 | 2022-07-29 | 0% | 60 |  |  | 8313 | 8313 | 0
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | PROF4 PO M.PROF4 PO M | 77 | 11680 | 02-Dec-19 A | 2021-07-14 | 95% | 3.85 |  |  | 584 | 584 | 0
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | TECH3 PO M.TECH3 PO M | 48 | 5642 | 02-Dec-19 A | 2021-07-14 | 95% | 2.4 |  |  | 282.1 | 282.1 | 0
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | TECH3 PO D.TECH3 PO D | 77 | 9051 | 02-Dec-19 A | 2021-07-14 | 95% | 3.85 |  |  | 452.55 | 452.55 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 4 | 625 | 2022-07-18 | 2022-07-22 | 0% | 4 |  |  | 625 | 625 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2022-07-18 | 2022-07-22 | 0% | 16 |  |  | 1937 | 1937 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 60 | 7264 | 2022-07-18 | 2022-07-22 | 0% | 60 |  |  | 7264 | 7264 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | CRAFT3.CRAFT3 | 36 | 4777 | 2022-07-18 | 2022-07-22 | 0% | 36 |  |  | 4777 | 4777 | 0
2.05.09 INTT Installation
S362000 | Design INTT Integration/Installation Tooling/Fixtures | PROF4 PO M.PROF4 PO M | 30 | 4550 | 01-Oct-19 A | 2021-07-30 | 80% | 6 |  |  | 910 | 910 | 0
S362000 | Design INTT Integration/Installation Tooling/Fixtures | TECH3 PO D.TECH3 PO D | 60 | 7053 | 01-Oct-19 A | 2021-07-30 | 80% | 12 |  |  | 1410.6 | 1410.6 | 0
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | PROF4 PO M.PROF4 PO M | 60 | 9101 | 2021-08-02 | 2021-10-26 | 0% | 60 |  |  | 9101 | 9101 | 0
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | TECH3 PO D.TECH3 PO D | 20 | 2351 | 2021-08-02 | 2021-10-26 | 0% | 20 |  |  | 2351 | 2351 | 0
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | PROF4 PO M.PROF4 PO M | 40 | 6067 | 2021-10-27 | 2021-11-09 | 0% | 40 |  |  | 6067 | 6067 | 0
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | TECH3 PO D.TECH3 PO D | 20 | 2351 | 2021-10-27 | 2021-11-09 | 0% | 20 |  |  | 2351 | 2351 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-11-10 | 2021-11-24 | 0% | 8 |  |  | 1213 | 1213 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-11-10 | 2021-11-24 | 0% | 8 |  |  | 940 | 940 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-11-10 | 2021-11-24 | 0% | 8 |  |  | 940 | 940 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-11-29 | 2021-12-10 | 0% | 8 |  |  | 1213 | 1213 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-11-29 | 2021-12-10 | 0% | 8 |  |  | 940 | 940 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-11-29 | 2021-12-10 | 0% | 8 |  |  | 940 | 940 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-08-10 | 2022-08-11 | 0% | 8 |  |  | 1250 | 1250 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | TECH3 PO M.TECH3 PO M | 24 | 2906 | 2022-08-10 | 2022-08-11 | 0% | 24 |  |  | 2906 | 2906 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-08-10 | 2022-08-11 | 0% | 8 |  |  | 969 | 969 | 0
S363000 | Install INTT Support - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-08-12 | 2022-08-15 | 0% | 8 |  |  | 1250 | 1250 | 0
S363000 | Install INTT Support - Labor | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-08-12 | 2022-08-15 | 0% | 8 |  |  | 969 | 969 | 0
S363000 | Install INTT Support - Labor | TECH3 PO M.TECH3 PO M | 60 | 7264 | 2022-08-12 | 2022-08-15 | 0% | 60 |  |  | 7264 | 7264 | 0
S363200 | Install INTT (mechanical) - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-08-16 | 2022-08-18 | 0% | 8 |  |  | 1250 | 1250 | 0
S363200 | Install INTT (mechanical) - Labor | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-08-16 | 2022-08-18 | 0% | 8 |  |  | 969 | 969 | 0
S363200 | Install INTT (mechanical) - Labor | TECH3 PO M.TECH3 PO M | 60 | 7264 | 2022-08-16 | 2022-08-18 | 0% | 60 |  |  | 7264 | 7264 | 0
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 20 | 2421 | 2022-08-19 | 2022-08-25 | 0% | 20 |  |  | 2421 | 2421 | 0
S363600 | Install INTT Cables and Services - Labor | TECH3 PO E.TECH3 PO E | 120 | 14529 | 2022-08-26 | 2022-09-01 | 0% | 120 |  |  | 14529 | 14529 | 0
S363600 | Install INTT Cables and Services - Labor | TECH3 PO M.TECH3 PO M | 120 | 14529 | 2022-08-26 | 2022-09-01 | 0% | 120 |  |  | 14529 | 14529 | 0
S363600 | Install INTT Cables and Services - Labor | PROF4 PO E.PROF4 PO E | 24 | 3750 | 2022-08-26 | 2022-09-01 | 0% | 24 |  |  | 3750 | 3750 | 0
S363600 | Install INTT Cables and Services - Labor | PROF4 PO M.PROF4 PO M | 24 | 3750 | 2022-08-26 | 2022-09-01 | 0% | 24 |  |  | 3750 | 3750 | 0
S363600 | Install INTT Cables and Services - Labor | TECH3 PO D.TECH3 PO D | 24 | 2906 | 2022-08-26 | 2022-09-01 | 0% | 24 |  |  | 2906 | 2906 | 0
S363600 | Install INTT Cables and Services - Labor | CRAFT3.CRAFT3 | 240 | 31845 | 2022-08-26 | 2022-09-01 | 0% | 240 |  |  | 31845 | 31845 | 0
S363800 | INTT - Operational Readiness Review (ORR) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-09-02 | 2022-09-09 | 0% | 8 |  |  | 1250 | 1250 | 0
S363800 | INTT - Operational Readiness Review (ORR) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-09-02 | 2022-09-09 | 0% | 8 |  |  | 969 | 969 | 0
S363800 | INTT - Operational Readiness Review (ORR) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-09-02 | 2022-09-09 | 0% | 8 |  |  | 969 | 969 | 0
S363800 | INTT - Operational Readiness Review (ORR) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-09-02 | 2022-09-09 | 0% | 8 |  |  | 969 | 969 | 0
S363900 | Address Action Items from INTT ORR | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-09-12 | 2022-09-16 | 0% | 8 |  |  | 1250 | 1250 | 0
S363900 | Address Action Items from INTT ORR | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-09-12 | 2022-09-16 | 0% | 8 |  |  | 969 | 969 | 0
S363900 | Address Action Items from INTT ORR | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-09-12 | 2022-09-16 | 0% | 8 |  |  | 969 | 969 | 0
S363900 | Address Action Items from INTT ORR | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-09-12 | 2022-09-16 | 0% | 8 |  |  | 969 | 969 | 0
S364000 | Commission INTT - Labor | PROF4 PO E.PROF4 PO E | 40 | 6249 | 2022-09-19 | 2022-09-30 | 0% | 40 |  |  | 6249 | 6249 | 0
S364000 | Commission INTT - Labor | SCI3 PO.SCI3 PO | 400 | 73035 | 2022-09-19 | 2022-09-30 | 0% | 400 |  |  | 73035 | 73035 | 0
S364000 | Commission INTT - Labor | TECH3 PO M.TECH3 PO M | 40 | 4843 | 2022-09-19 | 2022-09-30 | 0% | 40 |  |  | 4843 | 4843 | 0
S364000 | Commission INTT - Labor | TECH3 PO E.TECH3 PO E | 40 | 4843 | 2022-09-19 | 2022-09-30 | 0% | 40 |  |  | 4843 | 4843 | 0
S364000 | Commission INTT - Labor | PROF4 PO M.PROF4 PO M | 40 | 6249 | 2022-09-19 | 2022-09-30 | 0% | 40 |  |  | 6249 | 6249 | 0
S364000 | Commission INTT - Labor | TECH3 PO D.TECH3 PO D | 40 | 4843 | 2022-09-19 | 2022-09-30 | 0% | 40 |  |  | 4843 | 4843 | 0
S362200 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 | 34821 | 2021-08-02 | 2021-10-26 | 0% | 30000 |  |  | 34821 | 34821 | 0
S362900 | Transport Assembled INTT Sections to AH - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-10 | 2022-08-11 | 0% | 500 |  |  | 592 | 592 | 0
S363100 | Install INTT Support - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-12 | 2022-08-15 | 0% | 500 |  |  | 592 | 592 | 0
S363300 | Install INTT (mechanical) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-16 | 2022-08-18 | 0% | 500 |  |  | 592 | 592 | 0
S363500 | Align/Survey INTT to SC Magnet Centerline - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-19 | 2022-08-25 | 0% | 500 |  |  | 592 | 592 | 0
S363700 | Install INTT Cables and Services - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-26 | 2022-09-01 | 0% | 500 |  |  | 592 | 592 | 0
S364200 | Commission INTT - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-09-19 | 2022-09-30 | 0% | 500 |  |  | 592 | 592 | 0
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 80 | 10615 | 2022-08-19 | 2022-08-25 | 0% | 80 |  |  | 10615 | 10615 | 0
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 7264 | 2022-08-19 | 2022-08-25 | 0% | 60 |  |  | 7264 | 7264 | 0
2.05.10 MVTX Installation
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | PROF4 PO M.PROF4 PO M | 30 | 4550 | 01-Oct-19 A | 2021-07-30 | 95% | 1.5 |  |  | 227.5 | 227.5 | 0
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | TECH3 PO D.TECH3 PO D | 60 | 7053 | 01-Oct-19 A | 2021-07-30 | 95% | 3 |  |  | 352.65 | 352.65 | 0
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | PROF4 PO M.PROF4 PO M | 60 | 9101 | 2021-08-02 | 2021-10-26 | 0% | 60 |  |  | 9101 | 9101 | 0
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | TECH3 PO D.TECH3 PO D | 20 | 2351 | 2021-08-02 | 2021-10-26 | 0% | 20 |  |  | 2351 | 2351 | 0
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | TECH3 PO M.TECH3 PO M | 20 | 2351 | 2021-08-02 | 2021-10-26 | 0% | 20 |  |  | 2351 | 2351 | 0
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | PROF4 PO M.PROF4 PO M | 40 | 6067 | 29-Apr-21 A | 2021-10-28 | 35% | 26 |  |  | 3943.55 | 3943.55 | 0
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | TECH3 PO D.TECH3 PO D | 10 | 1175 | 29-Apr-21 A | 2021-10-28 | 35% | 6.5 |  |  | 763.75 | 763.75 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-10-29 | 2021-11-12 | 0% | 8 |  |  | 1213 | 1213 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-10-29 | 2021-11-12 | 0% | 8 |  |  | 940 | 940 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-10-29 | 2021-11-12 | 0% | 8 |  |  | 940 | 940 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-11-15 | 2021-11-30 | 0% | 8 |  |  | 1213 | 1213 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | 8 |  |  | 940 | 940 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | 8 |  |  | 940 | 940 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-03-28 | 2022-04-01 | 0% | 8 |  |  | 1250 | 1250 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | TECH3 PO M.TECH3 PO M | 24 | 2906 | 2022-03-28 | 2022-04-01 | 0% | 24 |  |  | 2906 | 2906 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-03-28 | 2022-04-01 | 0% | 8 |  |  | 969 | 969 | 0
S365500 | Install MVTX Support - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-08-12 | 2022-08-16 | 0% | 8 |  |  | 1250 | 1250 | 0
S365500 | Install MVTX Support - Labor | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-08-12 | 2022-08-16 | 0% | 8 |  |  | 969 | 969 | 0
S365500 | Install MVTX Support - Labor | TECH3 PO M.TECH3 PO M | 60 | 7264 | 2022-08-12 | 2022-08-16 | 0% | 60 |  |  | 7264 | 7264 | 0
S366700 | Align/Survey MVTX to SC Magnet Centerline - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 20 | 2421 | 2022-09-06 | 2022-09-07 | 0% | 20 |  |  | 2421 | 2421 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-09-08 | 2022-09-12 | 0% | 80 |  |  | 9686 | 9686 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | PROF4 PO E.PROF4 PO E | 24 | 3750 | 2022-09-08 | 2022-09-12 | 0% | 24 |  |  | 3750 | 3750 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | TECH3 PO E.TECH3 PO E | 80 | 9686 | 2022-09-08 | 2022-09-12 | 0% | 80 |  |  | 9686 | 9686 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | TECH3 PO D.TECH3 PO D | 24 | 2906 | 2022-09-08 | 2022-09-12 | 0% | 24 |  |  | 2906 | 2906 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | PROF4 PO M.PROF4 PO M | 24 | 3750 | 2022-09-08 | 2022-09-12 | 0% | 24 |  |  | 3750 | 3750 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | CRAFT3.CRAFT3 | 160 | 21230 | 2022-09-08 | 2022-09-12 | 0% | 160 |  |  | 21230 | 21230 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-09-13 | 2022-09-19 | 0% | 8 |  |  | 1250 | 1250 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-09-13 | 2022-09-19 | 0% | 8 |  |  | 969 | 969 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-09-13 | 2022-09-19 | 0% | 8 |  |  | 969 | 969 | 0
S367100 | MVTX - Operational Readiness Review (ORR) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-09-13 | 2022-09-19 | 0% | 8 |  |  | 969 | 969 | 0
S367300 | Address Action Items from MVTX ORR | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-09-20 | 2022-09-26 | 0% | 8 |  |  | 1250 | 1250 | 0
S367300 | Address Action Items from MVTX ORR | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-09-20 | 2022-09-26 | 0% | 8 |  |  | 969 | 969 | 0
S367300 | Address Action Items from MVTX ORR | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-09-20 | 2022-09-26 | 0% | 8 |  |  | 969 | 969 | 0
S367300 | Address Action Items from MVTX ORR | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-09-20 | 2022-09-26 | 0% | 8 |  |  | 969 | 969 | 0
S364500 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 30000 | 34821 | 2021-08-02 | 2021-10-26 | 0% | 30000 |  |  | 34821 | 34821 | 0
S365400 | Transport Assembled MVTX Sections to IR - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-03-28 | 2022-04-01 | 0% | 500 |  |  | 592 | 592 | 0
S365600 | Install MVTX Support - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-12 | 2022-08-16 | 0% | 500 |  |  | 592 | 592 | 0
S366800 | Align/Survey MVTX to SC Magnet Centerline - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-09-06 | 2022-09-07 | 0% | 500 |  |  | 592 | 592 | 0
S367000 | Install MVTX Remaining Cables and Services - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-09-08 | 2022-09-12 | 0% | 500 |  |  | 592 | 592 | 0
S367600 | Commission MVTX - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-09-27 | 2022-10-03 | 0% | 500 |  |  | 592 | 592 | 0
S365700 | Install FELIX | PROF3 IO E.PROF3 IO E | 16 | 2147 | 2022-08-17 | 2022-08-18 | 0% | 16 |  |  | 2147 | 2147 | 0
S365900 | Install Optical fibers | TECH3 PO E.TECH3 PO E | 40 | 4843 | 2022-08-17 | 2022-08-18 | 0% | 40 |  |  | 4843 | 4843 | 0
S366000 | Install RU | PROF3 IO E.PROF3 IO E | 40 | 5369 | 2022-08-17 | 2022-08-18 | 0% | 40 |  |  | 5369 | 5369 | 0
S366200 | Install Samtec Cables | TECH3 PO E.TECH3 PO E | 40 | 4843 | 2022-08-17 | 2022-08-18 | 0% | 40 |  |  | 4843 | 4843 | 0
S366300 | Install Half-Barrel 1 | PROF3 PO M.PROF3 PO M | 80 | 10737 | 2022-08-19 | 2022-08-26 | 0% | 80 |  |  | 10737 | 10737 | 0
S366300 | Install Half-Barrel 1 | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-08-19 | 2022-08-26 | 0% | 80 |  |  | 9686 | 9686 | 0
S366500 | Install Half-Barrel 2 | TECH3 PO M.TECH3 PO M | 80 | 9686 | 2022-08-29 | 2022-09-02 | 0% | 80 |  |  | 9686 | 9686 | 0
S366500 | Install Half-Barrel 2 | PROF3 PO M.PROF3 PO M | 80 | 10737 | 2022-08-29 | 2022-09-02 | 0% | 80 |  |  | 10737 | 10737 | 0
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 80 | 10615 | 2022-09-06 | 2022-09-07 | 0% | 80 |  |  | 10615 | 10615 | 0
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 60 | 7264 | 2022-09-06 | 2022-09-07 | 0% | 60 |  |  | 7264 | 7264 | 0
2.05.11 Min Bias Installation
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | PROF4 PO M.PROF4 PO M | 16 | 2427 | 13-May-20 A | 2021-07-30 | 75% | 4 |  |  | 606.75 | 606.75 | 0
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | TECH3 PO D.TECH3 PO D | 30 | 3526 | 13-May-20 A | 2021-07-30 | 75% | 7.5 |  |  | 881.5 | 881.5 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | PROF4 PO M.PROF4 PO M | 30 | 4550 | 2021-08-02 | 2021-10-26 | 0% | 30 |  |  | 4550 | 4550 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | TECH3 PO D.TECH3 PO D | 10 | 1175 | 2021-08-02 | 2021-10-26 | 0% | 10 |  |  | 1175 | 1175 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | TECH3 PO M.TECH3 PO M | 10 | 1175 | 2021-08-02 | 2021-10-26 | 0% | 10 |  |  | 1175 | 1175 | 0
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | PROF4 PO M.PROF4 PO M | 40 | 6067 | 29-Apr-21 A | 2021-11-12 | 20% | 32 |  |  | 4853.6 | 4853.6 | 0
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | TECH3 PO D.TECH3 PO D | 20 | 2351 | 29-Apr-21 A | 2021-11-12 | 20% | 16 |  |  | 1880.8 | 1880.8 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-11-15 | 2021-11-30 | 0% | 8 |  |  | 1213 | 1213 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | 8 |  |  | 940 | 940 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-11-15 | 2021-11-30 | 0% | 8 |  |  | 940 | 940 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | PROF4 PO M.PROF4 PO M | 8 | 1213 | 2021-12-01 | 2021-12-14 | 0% | 8 |  |  | 1213 | 1213 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO D.TECH3 PO D | 8 | 940 | 2021-12-01 | 2021-12-14 | 0% | 8 |  |  | 940 | 940 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | TECH3 PO M.TECH3 PO M | 8 | 940 | 2021-12-01 | 2021-12-14 | 0% | 8 |  |  | 940 | 940 | 0
S368500 | Transport Assembled Min Bias Sections to AH - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-08-10 | 2022-08-10 | 0% | 8 |  |  | 1250 | 1250 | 0
S368500 | Transport Assembled Min Bias Sections to AH - Labor | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-08-10 | 2022-08-10 | 0% | 8 |  |  | 969 | 969 | 0
S368700 | Install Min Bias Support - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-08-11 | 2022-08-22 | 0% | 8 |  |  | 1250 | 1250 | 0
S368700 | Install Min Bias Support - Labor | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-08-11 | 2022-08-22 | 0% | 8 |  |  | 969 | 969 | 0
S368700 | Install Min Bias Support - Labor | TECH3 PO M.TECH3 PO M | 16 | 1937 | 2022-08-11 | 2022-08-22 | 0% | 16 |  |  | 1937 | 1937 | 0
S368900 | Install Min Bias (mechanical) - Labor | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-08-23 | 2022-08-29 | 0% | 8 |  |  | 1250 | 1250 | 0
S368900 | Install Min Bias (mechanical) - Labor | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-08-23 | 2022-08-29 | 0% | 8 |  |  | 969 | 969 | 0
S368900 | Install Min Bias (mechanical) - Labor | TECH3 PO M.TECH3 PO M | 16 | 1937 | 2022-08-23 | 2022-08-29 | 0% | 16 |  |  | 1937 | 1937 | 0
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-08-30 | 2022-09-06 | 0% | 8 |  |  | 969 | 969 | 0
S369300 | Install Min Bias Cables and Services - Labor | TECH3 PO M.TECH3 PO M | 120 | 14529 | 2022-09-07 | 2022-09-13 | 0% | 120 |  |  | 14529 | 14529 | 0
S369300 | Install Min Bias Cables and Services - Labor | PROF4 PO E.PROF4 PO E | 24 | 3750 | 2022-09-07 | 2022-09-13 | 0% | 24 |  |  | 3750 | 3750 | 0
S369300 | Install Min Bias Cables and Services - Labor | TECH3 PO E.TECH3 PO E | 120 | 14529 | 2022-09-07 | 2022-09-13 | 0% | 120 |  |  | 14529 | 14529 | 0
S369300 | Install Min Bias Cables and Services - Labor | TECH3 PO D.TECH3 PO D | 24 | 2906 | 2022-09-07 | 2022-09-13 | 0% | 24 |  |  | 2906 | 2906 | 0
S369300 | Install Min Bias Cables and Services - Labor | PROF4 PO M.PROF4 PO M | 24 | 3750 | 2022-09-07 | 2022-09-13 | 0% | 24 |  |  | 3750 | 3750 | 0
S369300 | Install Min Bias Cables and Services - Labor | CRAFT3.CRAFT3 | 240 | 31845 | 2022-09-07 | 2022-09-13 | 0% | 240 |  |  | 31845 | 31845 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-09-14 | 2022-09-20 | 0% | 8 |  |  | 1250 | 1250 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-09-14 | 2022-09-20 | 0% | 8 |  |  | 969 | 969 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-09-14 | 2022-09-20 | 0% | 8 |  |  | 969 | 969 | 0
S369500 | Min Bias - Operational Readiness Review (ORR) | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-09-14 | 2022-09-20 | 0% | 8 |  |  | 969 | 969 | 0
S369600 | Address Action Items from Min Bias ORR | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-09-21 | 2022-09-27 | 0% | 8 |  |  | 1250 | 1250 | 0
S369600 | Address Action Items from Min Bias ORR | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-09-21 | 2022-09-27 | 0% | 8 |  |  | 969 | 969 | 0
S369600 | Address Action Items from Min Bias ORR | TECH3 PO M.TECH3 PO M | 8 | 969 | 2022-09-21 | 2022-09-27 | 0% | 8 |  |  | 969 | 969 | 0
S369600 | Address Action Items from Min Bias ORR | TECH3 PO E.TECH3 PO E | 8 | 969 | 2022-09-21 | 2022-09-27 | 0% | 8 |  |  | 969 | 969 | 0
S369700 | Commission Min Bias - Labor | SCI3 PO.SCI3 PO | 400 | 73035 | 2022-09-28 | 2022-10-04 | 0% | 400 |  |  | 73035 | 73035 | 0
S369700 | Commission Min Bias - Labor | TECH3 PO M.TECH3 PO M | 40 | 4843 | 2022-09-28 | 2022-10-04 | 0% | 40 |  |  | 4843 | 4843 | 0
S369700 | Commission Min Bias - Labor | PROF4 PO E.PROF4 PO E | 40 | 6249 | 2022-09-28 | 2022-10-04 | 0% | 40 |  |  | 6249 | 6249 | 0
S369700 | Commission Min Bias - Labor | TECH3 PO E.TECH3 PO E | 40 | 4843 | 2022-09-28 | 2022-10-04 | 0% | 40 |  |  | 4843 | 4843 | 0
S369700 | Commission Min Bias - Labor | PROF4 PO M.PROF4 PO M | 40 | 6249 | 2022-09-28 | 2022-10-04 | 0% | 40 |  |  | 6249 | 6249 | 0
S369700 | Commission Min Bias - Labor | TECH3 PO D.TECH3 PO D | 40 | 4843 | 2022-09-28 | 2022-10-04 | 0% | 40 |  |  | 4843 | 4843 | 0
S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 10000 | 11607 | 2021-08-02 | 2021-10-26 | 0% | 10000 |  |  | 11607 | 11607 | 0
S368600 | Transport Assembled Min Bias Sections to AH - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-10 | 2022-08-10 | 0% | 500 |  |  | 592 | 592 | 0
S368800 | Install Min Bias Support - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-11 | 2022-08-22 | 0% | 500 |  |  | 592 | 592 | 0
S369000 | Install Min Bias (mechanical) - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-23 | 2022-08-29 | 0% | 500 |  |  | 592 | 592 | 0
S369200 | Align/Survey Min Bias to SC Magnet Centerline - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-08-30 | 2022-09-06 | 0% | 500 |  |  | 592 | 592 | 0
S369400 | Install Min Bias Cables and Services - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-09-07 | 2022-09-13 | 0% | 500 |  |  | 592 | 592 | 0
S369900 | Commission Min Bias - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 592 | 2022-09-28 | 2022-10-04 | 0% | 500 |  |  | 592 | 592 | 0
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 20 | 2654 | 2022-08-30 | 2022-09-06 | 0% | 20 |  |  | 2654 | 2654 | 0
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 24 | 2906 | 2022-08-30 | 2022-09-06 | 0% | 24 |  |  | 2906 | 2906 | 0
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 24 | 3325 | 2022-08-30 | 2022-09-06 | 0% | 24 |  |  | 3325 | 3325 | 0
2.05.12 Full System Integration and ORR
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 40 | 5542 | 2022-03-23 | 2022-03-29 | 0% | 40 |  |  | 5542 | 5542 | 0
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 8 | 851 | 2022-03-23 | 2022-03-29 | 0% | 8 |  |  | 851 | 851 | 0
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1250 | 2022-03-23 | 2022-03-29 | 0% | 8 |  |  | 1250 | 1250 | 0
S370200 | Align Full sPHENIX to Nominal Beamline and IP - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 16 | 1937 | 2022-08-24 | 2022-08-30 | 0% | 16 |  |  | 1937 | 1937 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | PROF4 PO M.PROF4 PO M | 16 | 2500 | 2022-09-14 | 2022-09-20 | 0% | 16 |  |  | 2500 | 2500 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | TECH3 PO E.TECH3 PO E | 16 | 1937 | 2022-09-14 | 2022-09-20 | 0% | 16 |  |  | 1937 | 1937 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | TECH3 PO M.TECH3 PO M | 16 | 1937 | 2022-09-14 | 2022-09-20 | 0% | 16 |  |  | 1937 | 1937 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | TECH3 PO D.TECH3 PO D | 16 | 1937 | 2022-09-14 | 2022-09-20 | 0% | 16 |  |  | 1937 | 1937 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | PROF4 PO E.PROF4 PO E | 16 | 2500 | 2022-09-14 | 2022-09-20 | 0% | 16 |  |  | 2500 | 2500 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | PROF3 PO E.PROF3 PO E | 16 | 2147 | 2022-09-14 | 2022-09-20 | 0% | 16 |  |  | 2147 | 2147 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | SCI4 PO.SCI 4 PO | 16 | 3495 | 2022-09-14 | 2022-09-20 | 0% | 16 |  |  | 3495 | 3495 | 0
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | PROF5 AD.PROF5 AD | 16 | 2887 | 2022-09-14 | 2022-09-20 | 0% | 16 |  |  | 2887 | 2887 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | PROF4 PO M.PROF4 PO M | 16 | 2525 | 2022-09-21 | 2022-10-12 | 0% | 16 |  |  | 2525 | 2525 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | TECH3 PO E.TECH3 PO E | 16 | 1957 | 2022-09-21 | 2022-10-12 | 0% | 16 |  |  | 1957 | 1957 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | TECH3 PO M.TECH3 PO M | 16 | 1957 | 2022-09-21 | 2022-10-12 | 0% | 16 |  |  | 1957 | 1957 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | TECH3 PO D.TECH3 PO D | 16 | 1957 | 2022-09-21 | 2022-10-12 | 0% | 16 |  |  | 1957 | 1957 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | PROF4 PO E.PROF4 PO E | 16 | 2525 | 2022-09-21 | 2022-10-12 | 0% | 16 |  |  | 2525 | 2525 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | PROF5 AD.PROF5 AD | 16 | 2916 | 2022-09-21 | 2022-10-12 | 0% | 16 |  |  | 2916 | 2916 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | PROF3 PO M.PROF3 PO M | 16 | 2169 | 2022-09-21 | 2022-10-12 | 0% | 16 |  |  | 2169 | 2169 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | SCI4 PO.SCI 4 PO | 16 | 3530 | 2022-09-21 | 2022-10-12 | 0% | 16 |  |  | 3530 | 3530 | 0
S370100 | Move Full sPHENIX to IR - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 | 1184 | 2022-03-23 | 2022-03-29 | 0% | 1000 |  |  | 1184 | 1184 | 0
S370300 | Align Full sPHENIX to Nominal Beamline and IP - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1000 | 1184 | 2022-08-24 | 2022-08-30 | 0% | 1000 |  |  | 1184 | 1184 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | CRAFT3.CRAFT3 | 40 | 5308 | 2022-08-24 | 2022-08-30 | 0% | 40 |  |  | 5308 | 5308 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | TECH3 AD.TECH3 AD | 48 | 5811 | 2022-08-24 | 2022-08-30 | 0% | 48 |  |  | 5811 | 5811 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | TECH4 AD.TECH4 AD | 48 | 6650 | 2022-08-24 | 2022-08-30 | 0% | 48 |  |  | 6650 | 6650 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | PROF2 AD.PROF2 AD | 8 | 851 | 2022-08-24 | 2022-08-30 | 0% | 8 |  |  | 851 | 851 | 0
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | PROF4 AD.PROF4 AD | 8 | 1250 | 2022-08-24 | 2022-08-30 | 0% | 8 |  |  | 1250 | 1250 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-03-23 | 2022-03-29 | 0% | 8 |  |  | 1250 | 1250 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | TECH3 PO E.TECH3 PO E | 24 | 2906 | 2022-03-23 | 2022-03-29 | 0% | 24 |  |  | 2906 | 2906 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | TECH3 PO M.TECH3 PO M | 96 | 11623 | 2022-03-23 | 2022-03-29 | 0% | 96 |  |  | 11623 | 11623 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | TECH3 PO D.TECH3 PO D | 8 | 969 | 2022-03-23 | 2022-03-29 | 0% | 8 |  |  | 969 | 969 | 0
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | TECH3 AM.TECH3 AM | 40 | 4843 | 2022-03-23 | 2022-03-29 | 0% | 40 |  |  | 4843 | 4843 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | PROF4 PO M.PROF4 PO M | 40 | 6249 | 2022-05-09 | 2022-06-06 | 0% | 40 |  |  | 6249 | 6249 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | PROF4 PO E.PROF4 PO E | 40 | 6249 | 2022-05-09 | 2022-06-06 | 0% | 40 |  |  | 6249 | 6249 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | SCI3 PO.SCI3 PO | 40 | 7303 | 2022-05-09 | 2022-06-06 | 0% | 40 |  |  | 7303 | 7303 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | SCI4 PO.SCI 4 PO | 40 | 8738 | 2022-05-09 | 2022-06-06 | 0% | 40 |  |  | 8738 | 8738 | 0
S370510 | Review of Safety System Design by CAD ESRC | PROF4 PO M.PROF4 PO M | 8 | 1250 | 2022-06-07 | 2022-06-09 | 0% | 8 |  |  | 1250 | 1250 | 0
S370510 | Review of Safety System Design by CAD ESRC | PROF4 PO E.PROF4 PO E | 8 | 1250 | 2022-06-07 | 2022-06-09 | 0% | 8 |  |  | 1250 | 1250 | 0
S370510 | Review of Safety System Design by CAD ESRC | SCI4 PO.SCI 4 PO | 24 | 5243 | 2022-06-07 | 2022-06-09 | 0% | 24 |  |  | 5243 | 5243 | 0
S370510 | Review of Safety System Design by CAD ESRC | SCI3 PO.SCI3 PO | 24 | 4382 | 2022-06-07 | 2022-06-09 | 0% | 24 |  |  | 4382 | 4382 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | PROF4 PO M.PROF4 PO M | 40 | 6249 | 2022-06-10 | 2022-07-08 | 0% | 40 |  |  | 6249 | 6249 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | PROF4 PO E.PROF4 PO E | 40 | 6249 | 2022-06-10 | 2022-07-08 | 0% | 40 |  |  | 6249 | 6249 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | SCI3 PO.SCI3 PO | 40 | 7303 | 2022-06-10 | 2022-07-08 | 0% | 40 |  |  | 7303 | 7303 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | SCI4 PO.SCI 4 PO | 40 | 8738 | 2022-06-10 | 2022-07-08 | 0% | 40 |  |  | 8738 | 8738 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | PROF5 AD.PROF5 AD | 20 | 3608 | 2022-06-10 | 2022-07-08 | 0% | 20 |  |  | 3608 | 3608 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | PROF6 AD.PROF6 AD | 20 | 4095 | 2022-06-10 | 2022-07-08 | 0% | 20 |  |  | 4095 | 4095 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | PROF2 AD.PROF2 AD | 20 | 2126 | 2022-06-10 | 2022-07-08 | 0% | 20 |  |  | 2126 | 2126 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | PROF4 AD.PROF4 AD | 20 | 3125 | 2022-06-10 | 2022-07-08 | 0% | 20 |  |  | 3125 | 3125 | 0
S370530 | Review and approve procedures | PROF4 PO M.PROF4 PO M | 16 | 2500 | 2022-07-11 | 2022-07-12 | 0% | 16 |  |  | 2500 | 2500 | 0
S370530 | Review and approve procedures | PROF4 PO E.PROF4 PO E | 16 | 2500 | 2022-07-11 | 2022-07-12 | 0% | 16 |  |  | 2500 | 2500 | 0
S370530 | Review and approve procedures | SCI3 PO.SCI3 PO | 16 | 2921 | 2022-07-11 | 2022-07-12 | 0% | 16 |  |  | 2921 | 2921 | 0
S370530 | Review and approve procedures | SCI4 PO.SCI 4 PO | 16 | 3495 | 2022-07-11 | 2022-07-12 | 0% | 16 |  |  | 3495 | 3495 | 0
S370530 | Review and approve procedures | PROF5 AD.PROF5 AD | 16 | 2887 | 2022-07-11 | 2022-07-12 | 0% | 16 |  |  | 2887 | 2887 | 0
S370530 | Review and approve procedures | PROF6 AD.PROF6 AD | 16 | 3276 | 2022-07-11 | 2022-07-12 | 0% | 16 |  |  | 3276 | 3276 | 0
S370540 | Magnet Checkout After Power Testing | SCI3 AD.SCI3 AD | 16 | 2921 | 2022-07-13 | 2022-07-19 | 0% | 16 |  |  | 2921 | 2921 | 0
S370540 | Magnet Checkout After Power Testing | PROF6 AD.PROF6 AD | 16 | 3276 | 2022-07-13 | 2022-07-19 | 0% | 16 |  |  | 3276 | 3276 | 0
S370540 | Magnet Checkout After Power Testing | PROF5 AD.PROF5 AD | 16 | 2887 | 2022-07-13 | 2022-07-19 | 0% | 16 |  |  | 2887 | 2887 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | TECH3 PO E.TECH3 PO E | 24 | 2906 | 2022-07-20 | 2022-07-26 | 0% | 24 |  |  | 2906 | 2906 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | PROF4 PO E.PROF4 PO E | 24 | 3750 | 2022-07-20 | 2022-07-26 | 0% | 24 |  |  | 3750 | 3750 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | SCI4 PO.SCI 4 PO | 24 | 5243 | 2022-07-20 | 2022-07-26 | 0% | 24 |  |  | 5243 | 5243 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | SCI3 AD.SCI3 AD | 16 | 2921 | 2022-07-27 | 2022-08-09 | 0% | 16 |  |  | 2921 | 2921 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | PROF5 AD.PROF5 AD | 16 | 2887 | 2022-07-27 | 2022-08-09 | 0% | 16 |  |  | 2887 | 2887 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | PROF6 AD.PROF6 AD | 16 | 3276 | 2022-07-27 | 2022-08-09 | 0% | 16 |  |  | 3276 | 3276 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | PROF4 PO M.PROF4 PO M | 16 | 2500 | 2022-08-10 | 2022-08-16 | 0% | 16 |  |  | 2500 | 2500 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | TECH3 PO E.TECH3 PO E | 16 | 1937 | 2022-08-10 | 2022-08-16 | 0% | 16 |  |  | 1937 | 1937 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | TECH3 PO M.TECH3 PO M | 16 | 1937 | 2022-08-10 | 2022-08-16 | 0% | 16 |  |  | 1937 | 1937 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | PROF4 PO E.PROF4 PO E | 16 | 2500 | 2022-08-10 | 2022-08-16 | 0% | 16 |  |  | 2500 | 2500 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | SCI4 PO.SCI 4 PO | 16 | 3495 | 2022-08-10 | 2022-08-16 | 0% | 16 |  |  | 3495 | 3495 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | PROF4 PO M.PROF4 PO M | 16 | 2500 | 2022-08-17 | 2022-08-23 | 0% | 16 |  |  | 2500 | 2500 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | TECH3 PO E.TECH3 PO E | 16 | 1937 | 2022-08-17 | 2022-08-23 | 0% | 16 |  |  | 1937 | 1937 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | TECH3 PO M.TECH3 PO M | 16 | 1937 | 2022-08-17 | 2022-08-23 | 0% | 16 |  |  | 1937 | 1937 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | PROF4 PO E.PROF4 PO E | 16 | 2500 | 2022-08-17 | 2022-08-23 | 0% | 16 |  |  | 2500 | 2500 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | SCI4 PO.SCI 4 PO | 16 | 3495 | 2022-08-17 | 2022-08-23 | 0% | 16 |  |  | 3495 | 3495 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | SCI3 PO.SCI3 PO | 16 | 2921 | 2022-08-17 | 2022-08-23 | 0% | 16 |  |  | 2921 | 2921 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | SCI3 AD.SCI3 AD | 8 | 1461 | 2022-08-17 | 2022-08-23 | 0% | 8 |  |  | 1461 | 1461 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | PROF4 AD.PROF4 AD | 8 | 1250 | 2022-08-17 | 2022-08-23 | 0% | 8 |  |  | 1250 | 1250 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | PROF4 AD.PROF4 AD | 8 | 1250 | 2022-08-17 | 2022-08-23 | 0% | 8 |  |  | 1250 | 1250 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | PROF6 AD.PROF6 AD | 8 | 1638 | 2022-08-17 | 2022-08-23 | 0% | 8 |  |  | 1638 | 1638 | 0
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | SCI4 PO.SCI 4 PO | 16 | 3495 | 2022-08-24 | 2022-08-30 | 0% | 16 |  |  | 3495 | 3495 | 0
T Non BNL Contributions
POM02B-PCR026 POM02 sPHENIX WBS 1.x, 2.x Baseline PCR026 Approved
1 MIE Project
1.02 TPC
1.02.01 TPC Mechanics
1.02.01.01 TPC v1 Field Cage Prototype
S108900 | Assemble TPC v1 Central Membrane | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 80 | 0 | 14-Aug-19 A | 30-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S108900 | Assemble TPC v1 Central Membrane | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 80 | 0 | 14-Aug-19 A | 30-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S108900 | Assemble TPC v1 Central Membrane | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 80 | 0 | 14-Aug-19 A | 30-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S109000 | Assemble TPC v1 Field Cage Prototype | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 120 | 0 | 02-Dec-19 A | 23-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S109000 | Assemble TPC v1 Field Cage Prototype | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 120 | 0 | 02-Dec-19 A | 23-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S109000 | Assemble TPC v1 Field Cage Prototype | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 120 | 0 | 02-Dec-19 A | 23-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S109100 | Benchtest TPC v1 Field Cage Prototype | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 40 | 0 | 02-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109100 | Benchtest TPC v1 Field Cage Prototype | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 40 | 0 | 02-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109100 | Benchtest TPC v1 Field Cage Prototype | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 40 | 0 | 02-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S106100 | Assemble TPC v1 Inner Field Cage FY19 | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 96 | 0 | 01-Oct-18 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S106100 | Assemble TPC v1 Inner Field Cage FY19 | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 96 | 0 | 01-Oct-18 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S106100 | Assemble TPC v1 Inner Field Cage FY19 | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 96 | 0 | 01-Oct-18 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S108200 | Procure TPC v1 Central Membrane Parts Labor FY19 | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 256 | 0 | 01-Oct-18 A | 30-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.02 TPC v2 Field Cage
S109500 | Assemble TPC v2 Mandrel | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 120 | 0 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109500 | Assemble TPC v2 Mandrel | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 20 | 0 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109500 | Assemble TPC v2 Mandrel | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 40 | 0 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S110400 | Assemble TPC v2 Outer Field Cage | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 480 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | 9.6 |  |  | 0 | 0 | 0
S110400 | Assemble TPC v2 Outer Field Cage | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | 1.6 |  |  | 0 | 0 | 0
S110400 | Assemble TPC v2 Outer Field Cage | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 160 | 0 | 01-Jun-20 A | 2021-07-22 | 98% | 3.2 |  |  | 0 | 0 | 0
S111300 | Assemble TPC v2 Inner Field Cage | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 80 | 0 | 14-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111300 | Assemble TPC v2 Inner Field Cage | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 80 | 0 | 14-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111300 | Assemble TPC v2 Inner Field Cage | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 80 | 0 | 14-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111700 | Procure TPC v2 Central Membrane Parts Labor | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 320 | 0 | 08-Oct-19 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | 8 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | 8 |  |  | 0 | 0 | 0
S111900 | Assemble TPC v2 Central Membrane | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 80 | 0 | 01-Jun-20 A | 2021-07-22 | 90% | 8 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | 136 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | 136 |  |  | 0 | 0 | 0
S112000 | Assemble TPC v2 Field Cage Prototype | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 160 | 0 | 11-May-21 A | 2021-07-30 | 15% | 136 |  |  | 0 | 0 | 0
1.02.01.03 TPC Final Field Cage
S112900 | Modify TPC v2 Field Cage | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 80 | 0 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S112900 | Modify TPC v2 Field Cage | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 80 | 0 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S113000 | Benchtest TPC Final Field Cage | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 80 | 0 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S113000 | Benchtest TPC Final Field Cage | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 80 | 0 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.04 TPC v1 Modules
1.02.01.04.04 TPC v1b Module Prototype
S116800 | Test TPC v1b Module Prototype and Final Design Review | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 160 | 0 | 24-Apr-19 A | 06-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S116800 | Test TPC v1b Module Prototype and Final Design Review | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 160 | 0 | 24-Apr-19 A | 06-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.05 TPC v2 Modules
1.02.01.05.03 TPC v2a Module Prototype
S118700 | Test TPC v2a Module Framed GEMs | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 40 | 0 | 15-Apr-20 A | 21-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118700 | Test TPC v2a Module Framed GEMs | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 40 | 0 | 15-Apr-20 A | 21-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118800 | Assemble TPC v2a Module Prototype | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 40 | 0 | 02-Apr-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118800 | Assemble TPC v2a Module Prototype | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 40 | 0 | 02-Apr-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118900 | Test TPC v2a Module Prototype | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 160 | 0 | 03-Jul-19 A | 30-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S118900 | Test TPC v2a Module Prototype | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 160 | 0 | 03-Jul-19 A | 30-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.06 TPC Production GEM Acquisition
S119300 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Provide Requirements to Procurement | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 20 | 0 | 03-Feb-20 A | 26-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.07 TPC High Voltage System
S120600 | Select TPC GEM HV Power Supplies | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 80 | 0 | 07-May-20 A | 20-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S120500 | Select TPC Membrane HV Power Supply | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 32 | 0 | 08-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.08 TPC Assembly
S121610 | Install TPC Modules into Field Cage | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 576 | 0 | 25-Aug-21* | 2021-10-15 | 0% | 576 |  |  | 0 | 0 | 0
S121610 | Install TPC Modules into Field Cage | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 4800 | 0 | 25-Aug-21* | 2021-10-15 | 0% | 4800 |  |  | 0 | 0 | 0
S121610 | Install TPC Modules into Field Cage | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 1920 | 0 | 25-Aug-21* | 2021-10-15 | 0% | 1920 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 2600 | 0 | 2021-11-01 | 2022-02-02 | 0% | 2600 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 312 | 0 | 2021-11-01 | 2022-02-02 | 0% | 312 |  |  | 0 | 0 | 0
S121800 | Test TPC Prior to Installation | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 520 | 0 | 2021-11-01 | 2022-02-02 | 0% | 520 |  |  | 0 | 0 | 0
S121600 | Production Readiness Review for TPC Final Assembly | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 8 | 0 | 2021-08-24 | 2021-08-24 | 0% | 8 |  |  | 0 | 0 | 0
S121600 | Production Readiness Review for TPC Final Assembly | TECH4 SBU - Unpaid.TECH4 SBU - Unpaid | 8 | 0 | 2021-08-24 | 2021-08-24 | 0% | 8 |  |  | 0 | 0 | 0
1.02.02 TPC R1 Modules
1.02.02.01 TPC R1 Module Factory Preparation
S122205 | Prepare TPC R1 Factory Tooling Labor - Contributed Labor | STUDENT Wayne - Unpaid.STUDENT Wayne - Unpaid | 48 | 0 | 01-Oct-18 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.02.02 TPC R1 Pre-Production Module
S123605 | Test TPC R1 Pre-Production Module - Contributed Labor | STUDENT Wayne - Unpaid.STUDENT Wayne - Unpaid | 80 | 0 | 01-Jul-19 A | 08-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.02.03 TPC R1 Module Production
S125505 | Build TPC R1 Modules - Contributed Labor | SCI3 Wayne - Unpaid.SCI3 Wayne - Unpaid | 288 | 0 | 11-Jan-21 A | 2021-09-03 | 85% | 43.2 |  |  | 0 | 0 | 0
S125505 | Build TPC R1 Modules - Contributed Labor | STUDENT Wayne - Unpaid.STUDENT Wayne - Unpaid | 2400 | 0 | 11-Jan-21 A | 2021-09-03 | 85% | 360 |  |  | 0 | 0 | 0
S125605 | Test TPC R1 Modules - Contributed Labor | SCI3 Wayne - Unpaid.SCI3 Wayne - Unpaid | 288 | 0 | 11-Jan-21 A | 2021-09-20 | 85% | 43.2 |  |  | 0 | 0 | 0
S125605 | Test TPC R1 Modules - Contributed Labor | STUDENT Wayne - Unpaid.STUDENT Wayne - Unpaid | 2400 | 0 | 11-Jan-21 A | 2021-09-20 | 85% | 360 |  |  | 0 | 0 | 0
1.02.03 TPC R2 Modules
1.02.03.01 TPC R2 Module Factory Preparation
S126400 | Prepare TPC R2 Factory Tooling Labor | PROF3 Vanderbilt - Unpaid.PROF3 Vanderbilt - Unpaid | 160 | 0 | 01-Oct-18 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S126400 | Prepare TPC R2 Factory Tooling Labor | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 480 | 0 | 01-Oct-18 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.03.02 TPC R2 Pre-Production Module
S127700 | Assemble TPC R2 Pre-Production Module in TPC R2 Factory | SCI3 Vanderbilt - Unpaid.SCI3 Vanderbilt - Unpaid | 240 | 0 | 21-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S127700 | Assemble TPC R2 Pre-Production Module in TPC R2 Factory | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 720 | 0 | 21-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S127800 | Test TPC R2 Pre-Production Module | SCI3 Vanderbilt - Unpaid.SCI3 Vanderbilt - Unpaid | 80 | 0 | 21-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S127800 | Test TPC R2 Pre-Production Module | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 240 | 0 | 21-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.03.03 TPC R2 Module Production
S129500 | Build TPC R2 Modules | SCI3 Vanderbilt - Unpaid.SCI3 Vanderbilt - Unpaid | 288 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | 43.2 |  |  | 0 | 0 | 0
S129500 | Build TPC R2 Modules | TECH3 Vanderbilt - Unpaid.TECH3 Vanderbilt - Unpaid | 960 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | 144 |  |  | 0 | 0 | 0
S129500 | Build TPC R2 Modules | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 2400 | 0 | 02-Nov-20 A | 2021-07-22 | 85% | 360 |  |  | 0 | 0 | 0
S129600 | Test TPC R2 Modules | SCI3 Vanderbilt - Unpaid.SCI3 Vanderbilt - Unpaid | 288 | 0 | 17-Nov-20 A | 2021-07-22 | 85% | 43.2 |  |  | 0 | 0 | 0
S129600 | Test TPC R2 Modules | STUDENT Vanderbilt - Unpaid.STUDENT Vanderbilt - Unpaid | 2400 | 0 | 17-Nov-20 A | 2021-07-22 | 85% | 360 |  |  | 0 | 0 | 0
1.02.04 TPC R3 Modules
1.02.04.01 TPC R3 Module Factory Preparation
S130000 | Prepare TPC R3a Factory Tooling Labor | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 160 | 0 | 01-Oct-18 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S130000 | Prepare TPC R3a Factory Tooling Labor | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 480 | 0 | 01-Oct-18 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S130400 | Prepare TPC R3b Factory Tooling Labor | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 160 | 0 | 01-Oct-18 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S130400 | Prepare TPC R3b Factory Tooling Labor | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 480 | 0 | 01-Oct-18 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.04.02 TPC R3 Pre-Production Module
S131700 | Assemble TPC R3a Pre-Production Module in TPC R3a Factory | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 240 | 0 | 03-Sep-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S131700 | Assemble TPC R3a Pre-Production Module in TPC R3a Factory | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 240 | 0 | 03-Sep-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S131800 | Test TPC R3a Pre-Production Module | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 80 | 0 | 03-Sep-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S131800 | Test TPC R3a Pre-Production Module | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 80 | 0 | 03-Sep-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S131900 | Assemble TPC R3b Pre-Production Module in TPC R3b Factory | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 240 | 0 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S131900 | Assemble TPC R3b Pre-Production Module in TPC R3b Factory | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 240 | 0 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S132000 | Test TPC R3b Pre-Production Module | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 80 | 0 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S132000 | Test TPC R3b Pre-Production Module | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 80 | 0 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.04.03 TPC R3 Module Production
S133700 | Build TPC R3a Modules | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 288 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | 43.2 |  |  | 0 | 0 | 0
S133700 | Build TPC R3a Modules | TECH3 WIS - Unpaid.TECH3 WIS - Unpaid | 960 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | 144 |  |  | 0 | 0 | 0
S133700 | Build TPC R3a Modules | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 2400 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | 360 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | SCI3 WIS - Unpaid.SCI3 WIS - Unpaid | 288 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | 43.2 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | TECH3 WIS - Unpaid.TECH3 WIS - Unpaid | 960 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | 144 |  |  | 0 | 0 | 0
S133800 | Test TPC R3a Modules | STUDENT WIS - Unpaid.STUDENT WIS - Unpaid | 2400 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | 360 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 288 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | 43.2 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | TECH3 Temple - Unpaid.TECH3 Temple - Unpaid | 960 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | 144 |  |  | 0 | 0 | 0
S133900 | Build TPC R3b Modules | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 2400 | 0 | 06-Oct-20 A | 2021-07-14 | 85% | 360 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | SCI3 Temple - Unpaid.SCI3 Temple - Unpaid | 288 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | 43.2 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | STUDENT Temple - Unpaid.STUDENT Temple - Unpaid | 2400 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | 360 |  |  | 0 | 0 | 0
S134000 | Test TPC R3b Modules | TECH3 Temple - Unpaid.TECH3 Temple - Unpaid | 960 | 0 | 21-Oct-20 A | 2021-07-14 | 85% | 144 |  |  | 0 | 0 | 0
1.06 DAQ/Trigger
1.06.02 Local Level 1 Trigger (LL1)
1.06.02.02 LL1 Trigger Prototype v1
S262600 | Trigger Prototype v1: Test trigger systems | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 240 | 0 | 01-Jun-20 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S262900 | Trigger LL1 Preproduction Prototype: Electrical Safety and Final Design Review | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 10 | 0 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S263000 | Procure Trigger Preproduction Prototype LL1 - Provide Requirements to Procurement | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 48 | 0 | 22-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S263700 | Trigger LL1 Preproduction Prototype: Test trigger systems | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 280 | 0 | 2021-08-09 | 2021-08-27 | 0% | 280 |  |  | 0 | 0 | 0
1.06.02.04 LL1 Trigger Production
S264000 | Trigger LL1 Production: Updates to trigger board: Production | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 136 | 0 | 2021-09-03 | 2021-09-28 | 0% | 136 |  |  | 0 | 0 | 0
S264100 | Trigger LL1 Production: final updates to trigger crate requirements | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 20 | 0 | 2021-09-29 | 2021-10-13 | 0% | 20 |  |  | 0 | 0 | 0
S264300 | Procure Production LL1 System - Provide Requirements to Procurement | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 40 | 0 | 15-Mar-21 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S265000 | Trigger LL1 Production: Program and commission trigger boards | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 60 | 0 | 2021-11-12 | 2021-12-06 | 0% | 60 |  |  | 0 | 0 | 0
S265100 | Trigger LL1 Production: Assemble trigger system | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 120 | 0 | 2021-12-07 | 2021-12-13 | 0% | 120 |  |  | 0 | 0 | 0
S265200 | Trigger LL1 Production: Commission trigger systems | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 120 | 0 | 2021-12-14 | 2021-12-20 | 0% | 120 |  |  | 0 | 0 | 0
2 Infrastructure/Facility
2.05 Integration and Installation
2.05.06 Inner Hcal Installation
S357100 | Commission Inner HCal (labor - if instrumented) - Labor | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 640 | 0 | 2022-03-14 | 2022-03-18 | 0% | 640 |  |  | 0 | 0 | 0
2.05.07 EMCal Installation
S359300 | Commission EMCal - Labor | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 | 0 | 2022-03-30 | 2022-05-03 | 0% | 1600 |  |  | 0 | 0 | 0
2.05.08 TPC Installation
S361800 | Commission TPC - Labor Students | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 | 0 | 2022-09-15 | 2022-10-05 | 0% | 1600 |  |  | 0 | 0 | 0
2.05.09 INTT Installation
S364100 | Commission INTT - Student Labor | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 | 0 | 2022-09-19 | 2022-09-30 | 0% | 1600 |  |  | 0 | 0 | 0
2.05.10 MVTX Installation
S367500 | Commission MVTX - Labor | POSTD LBNL.POSTD LBNL | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | 480 |  |  | 0 | 0 | 0
S367500 | Commission MVTX - Labor | STAFFPHYS LBNL.STAFFPHYS LBNL | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | 480 |  |  | 0 | 0 | 0
S367500 | Commission MVTX - Labor | SCI3 LANL.SCI3 LANL | 480 | 0 | 2022-09-27 | 2022-10-03 | 0% | 480 |  |  | 0 | 0 | 0
S365100 | Installation Prep | SCI3 LANL.SCI3 LANL | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | 80 |  |  | 0 | 0 | 0
S365100 | Installation Prep | STAFFPHYS LBNL.STAFFPHYS LBNL | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | 80 |  |  | 0 | 0 | 0
S365100 | Installation Prep | POSTD LBNL.POSTD LBNL | 80 | 0 | 2022-03-18 | 2022-03-24 | 0% | 80 |  |  | 0 | 0 | 0
S365200 | Installation Review | STAFFPHYS LBNL.STAFFPHYS LBNL | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | 8 |  |  | 0 | 0 | 0
S365200 | Installation Review | POSTD LBNL.POSTD LBNL | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | 8 |  |  | 0 | 0 | 0
S365200 | Installation Review | SCI3 LANL.SCI3 LANL | 8 | 0 | 2022-03-25 | 2022-03-25 | 0% | 8 |  |  | 0 | 0 | 0
S365800 | Install FELIX | SCI3 LANL.SCI3 LANL | 16 | 0 | 2022-08-17 | 2022-08-18 | 0% | 16 |  |  | 0 | 0 | 0
S366100 | Install RU | SCI3 LANL.SCI3 LANL | 40 | 0 | 2022-08-17 | 2022-08-18 | 0% | 40 |  |  | 0 | 0 | 0
S366400 | Install Half-Barrel 1 | STAFFPHYS LBNL.STAFFPHYS LBNL | 30 | 0 | 2022-08-19 | 2022-08-26 | 0% | 30 |  |  | 0 | 0 | 0
S366400 | Install Half-Barrel 1 | POSTD LBNL.POSTD LBNL | 30 | 0 | 2022-08-19 | 2022-08-26 | 0% | 30 |  |  | 0 | 0 | 0
S366600 | Install Half-Barrel 2 | STAFFPHYS LBNL.STAFFPHYS LBNL | 30 | 0 | 2022-08-29 | 2022-09-02 | 0% | 30 |  |  | 0 | 0 | 0
S366600 | Install Half-Barrel 2 | POSTD LBNL.POSTD LBNL | 30 | 0 | 2022-08-29 | 2022-09-02 | 0% | 30 |  |  | 0 | 0 | 0
S367400 | Address Action Items from MVTX ORR | SCI3 LANL.SCI3 LANL | 16 | 0 | 2022-09-20 | 2022-09-26 | 0% | 16 |  |  | 0 | 0 | 0
S367400 | Address Action Items from MVTX ORR | STAFFPHYS LBNL.STAFFPHYS LBNL | 16 | 0 | 2022-09-20 | 2022-09-26 | 0% | 16 |  |  | 0 | 0 | 0
S367200 | MVTX - Operational Readiness Review (ORR) | SCI3 LANL.SCI3 LANL | 16 | 0 | 2022-09-13 | 2022-09-19 | 0% | 16 |  |  | 0 | 0 | 0
S367200 | MVTX - Operational Readiness Review (ORR) | STAFFPHYS LBNL.STAFFPHYS LBNL | 16 | 0 | 2022-09-13 | 2022-09-19 | 0% | 16 |  |  | 0 | 0 | 0
2.05.11 Min Bias Installation
S369800 | Commission Min Bias - Labor | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1600 | 0 | 2022-09-28 | 2022-10-04 | 0% | 1600 |  |  | 0 | 0 | 0
B_T Multiple B_T
POM02B-PCR026 POM02 sPHENIX WBS 1.x, 2.x Baseline PCR026 Approved
1 MIE Project
1.02 TPC
1.02.01 TPC Mechanics
1.02.01.01 TPC v1 Field Cage Prototype
S108600 | Design TPC Handling Cart | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 120 | 0 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S108600 | Design TPC Handling Cart | PROF4 AM.PROF4 AM | 120 | 18175 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.02 TPC v2 Field Cage
S111400 | Design TPC Field Cage Prototype v2 End Rings | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 16 | 0 | 03-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111400 | Design TPC Field Cage Prototype v2 End Rings | TECH3 PO M.TECH3 PO M | 16 | 1826 | 03-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111400 | Design TPC Field Cage Prototype v2 End Rings | PROF4 AM.PROF4 AM | 16 | 2356 | 03-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109305 | Produce TPC v2 Field Cage Prototype Conceptual Design Split | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 2 | 0 | 02-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109305 | Produce TPC v2 Field Cage Prototype Conceptual Design Split | TECH3 PO M.TECH3 PO M | 4 | 453 | 02-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109305 | Produce TPC v2 Field Cage Prototype Conceptual Design Split | PROF4 AM.PROF4 AM | 4 | 585 | 02-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109605 | Produce TPC v2 Outer Field Cage Conceptual Design Split | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 1 | 0 | 02-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109605 | Produce TPC v2 Outer Field Cage Conceptual Design Split | TECH3 PO M.TECH3 PO M | 2 | 226 | 02-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S109605 | Produce TPC v2 Outer Field Cage Conceptual Design Split | PROF4 AM.PROF4 AM | 2 | 292 | 02-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S110505 | Produce TPC v2 Inner Field Cage Conceptual Design Split | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 2 | 0 | 01-Nov-19 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S110505 | Produce TPC v2 Inner Field Cage Conceptual Design Split | TECH3 PO M.TECH3 PO M | 2 | 227 | 01-Nov-19 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S110505 | Produce TPC v2 Inner Field Cage Conceptual Design Split | PROF4 AM.PROF4 AM | 2 | 293 | 01-Nov-19 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111605 | Produce TPC v2 Central Membrane Conceptual Design Split | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 5 | 0 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S111605 | Produce TPC v2 Central Membrane Conceptual Design Split | TECH3 PO M.TECH3 PO M | 5 | 567 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S111605 | Produce TPC v2 Central Membrane Conceptual Design Split | PROF4 AM.PROF4 AM | 5 | 731 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.03 TPC Final Field Cage
S112400 | Design TPC v2 Field Cage Modifications | SCI4 SBU - Unpaid.SCI4 SBU - Unpaid | 16 | 0 | 08-Mar-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S112400 | Design TPC v2 Field Cage Modifications | TECH3 PO M.TECH3 PO M | 16 | 1826 | 08-Mar-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S112400 | Design TPC v2 Field Cage Modifications | PROF4 AM.PROF4 AM | 16 | 2356 | 08-Mar-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.05 TPC v2 Modules
1.02.01.05.02 TPC v2 Module Common Mechanics
S116900 | Design TPC v2 Module Strongback | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 80 | 0 | 31-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S116900 | Design TPC v2 Module Strongback | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 80 | 0 | 31-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S116900 | Design TPC v2 Module Strongback | PROF4 AM.PROF4 AM | 80 | 11781 | 31-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117200 | Design TPC v2 Module Frames | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 8 | 0 | 31-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117200 | Design TPC v2 Module Frames | TECH3 PO M.TECH3 PO M | 8 | 913 | 31-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117200 | Design TPC v2 Module Frames | PROF4 AM.PROF4 AM | 8 | 1178 | 31-Jan-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117500 | Design TPC v2 Module Grid | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 8 | 0 | 15-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117500 | Design TPC v2 Module Grid | TECH3 PO M.TECH3 PO M | 8 | 913 | 15-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117500 | Design TPC v2 Module Grid | PROF4 AM.PROF4 AM | 8 | 1178 | 15-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.05.03 TPC v2a Module Prototype
S117900 | Design TPC v2a Module Padplane | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 80 | 0 | 31-Jan-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117900 | Design TPC v2a Module Padplane | PROF4 PO E.PROF4 PO E | 80 | 11781 | 31-Jan-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117900 | Design TPC v2a Module Padplane | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 160 | 0 | 31-Jan-20 A | 25-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118200 | Design TPC v2a Module GEMs | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 160 | 0 | 14-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118200 | Design TPC v2a Module GEMs | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 160 | 0 | 14-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118200 | Design TPC v2a Module GEMs | PROF4 AM.PROF4 AM | 40 | 5891 | 14-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118500 | Test TPC v2a Module GEMS | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 40 | 0 | 01-Apr-20 A | 07-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118500 | Test TPC v2a Module GEMS | TECH3 PO M.TECH3 PO M | 40 | 4565 | 01-Apr-20 A | 07-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.07 TPC High Voltage System
S120300 | Procure TPC Membrane HV Cables - Labor | TECH3 PO M.TECH3 PO M | 32 | 3652 | 08-Jan-20 A | 27-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S120300 | Procure TPC Membrane HV Cables - Labor | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 32 | 0 | 08-Jan-20 A | 27-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.08 TPC Assembly
S121700 | Install TPC Electronics | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 400 | 0 | 2021-10-18 | 2021-10-29 | 0% | 400 |  |  | 0 | 0 | 0
S121700 | Install TPC Electronics | TECH3 PO M.TECH3 PO M | 160 | 18807 | 2021-10-18 | 2021-10-29 | 0% | 160 |  |  | 18807 | 18807 | 0
S121700 | Install TPC Electronics | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 48 | 0 | 2021-10-18 | 2021-10-29 | 0% | 48 |  |  | 0 | 0 | 0
1.02.05 TPC FEE
1.02.05.02 TPC FEE Prototype v2 (Pre-Production)
S137300 | v2 Modify TPC FEE Test Stand Labor | SCI3 PO.SCI3 PO | 24 | 4131 | 02-Dec-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137300 | v2 Modify TPC FEE Test Stand Labor | TECH3 PO E.TECH3 PO E | 60 | 6847 | 02-Dec-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137300 | v2 Modify TPC FEE Test Stand Labor | TECH3 PO D.TECH3 PO D | 72 | 8217 | 02-Dec-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137300 | v2 Modify TPC FEE Test Stand Labor | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 24 | 0 | 02-Dec-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137300 | v2 Modify TPC FEE Test Stand Labor | PROF4 PO E.PROF4 PO E | 240 | 35344 | 02-Dec-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137500 | v2 Assemble and test TPC FEE preproduction prototype | PROF4 PO E.PROF4 PO E | 248 | 36522 | 13-Apr-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S137500 | v2 Assemble and test TPC FEE preproduction prototype | SCI3 PO.SCI3 PO | 240 | 41305 | 13-Apr-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S137500 | v2 Assemble and test TPC FEE preproduction prototype | TECH3 PO E.TECH3 PO E | 64 | 7304 | 13-Apr-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S137500 | v2 Assemble and test TPC FEE preproduction prototype | TECH3 PO D.TECH3 PO D | 64 | 7304 | 13-Apr-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S137500 | v2 Assemble and test TPC FEE preproduction prototype | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 96 | 0 | 13-Apr-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.05.04 TPC FEE Production
S140900 | Procure TPC FEE Production Components - Provide Requirements to Procurement | PROF4 PO E.PROF4 PO E | 80 | 11781 | 05-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S140900 | Procure TPC FEE Production Components - Provide Requirements to Procurement | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 56 | 0 | 05-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S140900 | Procure TPC FEE Production Components - Provide Requirements to Procurement | TECH3 PO E.TECH3 PO E | 80 | 9130 | 05-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S143300 | Perform QA Testing on TPC FEE | PROF4 PO E.PROF4 PO E | 56 | 8494 | 2021-10-06 | 2022-01-19 | 0% | 56 |  |  | 8494 | 8494 | 0
S143300 | Perform QA Testing on TPC FEE | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 56 | 0 | 2021-10-06 | 2022-01-19 | 0% | 56 |  |  | 0 | 0 | 0
S143300 | Perform QA Testing on TPC FEE | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 280 | 0 | 2021-10-06 | 2022-01-19 | 0% | 280 |  |  | 0 | 0 | 0
S143300 | Perform QA Testing on TPC FEE | TECH3 PO E.TECH3 PO E | 168 | 19748 | 2021-10-06 | 2022-01-19 | 0% | 168 |  |  | 19748 | 19748 | 0
S143300 | Perform QA Testing on TPC FEE | SCI3 PO.SCI3 PO | 323 | 57258 | 2021-10-06 | 2022-01-19 | 0% | 323 |  |  | 57258 | 57258 | 0
1.02.06 TPC DAM
1.02.06.02 TPC DAM Evaluation -- FELIX 2.0
S146700 | Develop TPC DAM FPGA Algorithm - Round 2 | PROF4 PO E.PROF4 PO E | 630 | 92378 | 03-Sep-19 A | 30-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146700 | Develop TPC DAM FPGA Algorithm - Round 2 | SCI3 PO.SCI3 PO | 210 | 35987 | 03-Sep-19 A | 30-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146700 | Develop TPC DAM FPGA Algorithm - Round 2 | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 44 | 0 | 03-Sep-19 A | 30-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146700 | Develop TPC DAM FPGA Algorithm - Round 2 | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 210 | 0 | 03-Sep-19 A | 30-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146202 | Develop TPC DAM FPGA Algorithm - Round 1 Split | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 42 | 0 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S146202 | Develop TPC DAM FPGA Algorithm - Round 1 Split | PROF4 PO E.PROF4 PO E | 427 | 61051 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S146202 | Develop TPC DAM FPGA Algorithm - Round 1 Split | SCI3 PO.SCI3 PO | 385 | 64331 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S146202 | Develop TPC DAM FPGA Algorithm - Round 1 Split | TECH3 PO D.TECH3 PO D | 259 | 28697 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S146202 | Develop TPC DAM FPGA Algorithm - Round 1 Split | TECH3 PO E.TECH3 PO E | 259 | 28697 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.06.03 TPC DAM Production
S146600 | Procure TPC DAM Felix 2.0 boards - Provide Requirements to Procurement | PROF4 PO E.PROF4 PO E | 300 | 44180 | 02-Mar-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146600 | Procure TPC DAM Felix 2.0 boards - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 240 | 27389 | 02-Mar-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S146600 | Procure TPC DAM Felix 2.0 boards - Provide Requirements to Procurement | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 30 | 0 | 02-Mar-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | PROF4 PO E.PROF4 PO E | 44 | 6674 | 08-Mar-21 A | 2021-08-03 | 10% | 39.6 |  |  | 6006.6 | 6006.6 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | TECH3 PO E.TECH3 PO E | 264 | 31032 | 08-Mar-21 A | 2021-08-03 | 10% | 237.6 |  |  | 27928.8 | 27928.8 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 44 | 0 | 08-Mar-21 A | 2021-08-03 | 10% | 39.6 |  |  | 0 | 0 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 220 | 0 | 08-Mar-21 A | 2021-08-03 | 10% | 198 |  |  | 0 | 0 | 0
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | SCI3 PO.SCI3 PO | 183 | 32440 | 08-Mar-21 A | 2021-08-03 | 10% | 164.7 |  |  | 29196 | 29196 | 0
S147800 | Procure TPC EDBC Computers & Peripherals - Provide Requirements to Procurement | PROF4 PO E.PROF4 PO E | 192 | 28275 | 01-Jul-20 A | 28-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S147800 | Procure TPC EDBC Computers & Peripherals - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 144 | 16434 | 01-Jul-20 A | 28-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S147800 | Procure TPC EDBC Computers & Peripherals - Provide Requirements to Procurement | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 144 | 0 | 01-Jul-20 A | 28-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S148500 | Test Full TPC DAM System | PROF4 PO E.PROF4 PO E | 960 | 145959 | 2021-08-04 | 2021-12-14 | 0% | 960 |  |  | 145959 | 145959 | 0
S148500 | Test Full TPC DAM System | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 440 | 0 | 2021-08-04 | 2021-12-14 | 0% | 440 |  |  | 0 | 0 | 0
S148500 | Test Full TPC DAM System | SCI3 PO.SCI3 PO | 440 | 78182 | 2021-08-04 | 2021-12-14 | 0% | 440 |  |  | 78182 | 78182 | 0
S147700 | (Planning Package) Develop TPC DAM FPGA Algorithm - Round 3 | PROF4 PO E.PROF4 PO E | 120 | 17977 | 16-Jun-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S147700 | (Planning Package) Develop TPC DAM FPGA Algorithm - Round 3 | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 44 | 0 | 16-Jun-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S147700 | (Planning Package) Develop TPC DAM FPGA Algorithm - Round 3 | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 220 | 0 | 16-Jun-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S147700 | (Planning Package) Develop TPC DAM FPGA Algorithm - Round 3 | SCI3 PO.SCI3 PO | 120 | 21010 | 16-Jun-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S147310 | Procure TPC DAM Felix 2.0 Optical Components - Provide Requirements to Procurement | PROF4 PO E.PROF4 PO E | 300 | 44180 | 02-Mar-20 A | 23-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S147310 | Procure TPC DAM Felix 2.0 Optical Components - Provide Requirements to Procurement | TECH3 PO D.TECH3 PO D | 240 | 27389 | 02-Mar-20 A | 23-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S147310 | Procure TPC DAM Felix 2.0 Optical Components - Provide Requirements to Procurement | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 30 | 0 | 02-Mar-20 A | 23-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.07 TPC Support Systems
1.02.07.01 TPC Laser System
S148700 | Design TPC Laser System | PROF4 PO M.PROF4 PO M | 320 | 45752 | 12-Sep-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S148700 | Design TPC Laser System | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 320 | 0 | 12-Sep-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S148700 | Design TPC Laser System | TECH3 PO M.TECH3 PO M | 320 | 35455 | 12-Sep-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S149000 | Procure TPC Laser(s) - Provide Requirements to Procurement | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 48 | 0 | 13-Oct-20 A | 19-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S149000 | Procure TPC Laser(s) - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 48 | 7028 | 13-Oct-20 A | 19-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S149700 | Procure TPC Optics with mirrors - Provide Requirements to Procurement | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 24 | 0 | 13-Oct-20 A | 19-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S149700 | Procure TPC Optics with mirrors - Provide Requirements to Procurement | PROF4 PO M.PROF4 PO M | 24 | 3514 | 13-Oct-20 A | 19-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S150400 | Procure TPC mirror bundles with supports Labor | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 24 | 0 | 13-Jan-21 A | 2021-08-31 | 50% | 12 |  |  | 0 | 0 | 0
S150400 | Procure TPC mirror bundles with supports Labor | PROF4 PO M.PROF4 PO M | 24 | 3533 | 13-Jan-21 A | 2021-08-31 | 50% | 12 |  |  | 1766.5 | 1766.5 | 0
1.02.07.02 TPC Gas System
S151200 | Design TPC Gas Handling System | PROF4 PO M.PROF4 PO M | 800 | 116165 | 12-Sep-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S151200 | Design TPC Gas Handling System | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 800 | 0 | 12-Sep-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S151200 | Design TPC Gas Handling System | TECH3 PO M.TECH3 PO M | 800 | 90021 | 12-Sep-19 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S152800 | Assemble TPC Gas System controls | PROF4 PO M.PROF4 PO M | 48 | 7069 | 22-Mar-21 A | 2021-08-24 | 10% | 43.2 |  |  | 6362.1 | 6362.1 | 0
S152800 | Assemble TPC Gas System controls | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 1920 | 0 | 22-Mar-21 A | 2021-08-24 | 10% | 1728 |  |  | 0 | 0 | 0
S152800 | Assemble TPC Gas System controls | TECH3 PO M.TECH3 PO M | 480 | 54779 | 22-Mar-21 A | 2021-08-24 | 10% | 432 |  |  | 49301.1 | 49301.1 | 0
S152900 | Set up TPC Gas System computer control Labor | PROF4 PO M.PROF4 PO M | 24 | 3543 | 15-Mar-21 A | 2021-10-14 | 25% | 18 |  |  | 2657.25 | 2657.25 | 0
S152900 | Set up TPC Gas System computer control Labor | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 480 | 0 | 15-Mar-21 A | 2021-10-14 | 25% | 360 |  |  | 0 | 0 | 0
1.02.07.03 TPC Cooling System
S154100 | Design TPC Cooling System | PROF4 PO M.PROF4 PO M | 640 | 92603 | 12-Sep-19 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S154100 | Design TPC Cooling System | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 640 | 0 | 12-Sep-19 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S154100 | Design TPC Cooling System | TECH3 PO M.TECH3 PO M | 212 | 23771 | 12-Sep-19 A | 14-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.03 EMCal
1.03.02 EMCAL Module Fabrication and Sector Assembly
1.03.02.03 EMCAL Sector Assembly
1.03.02.03.02 EMCAL Preproduction Sector Assembly and Testing
S191700 | Test preproduction prototype Sector 0 with LEDs & cosmic rays_10% | PROF4 PO E.PROF4 PO E | 32 | 4575 | 30-Jul-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191700 | Test preproduction prototype Sector 0 with LEDs & cosmic rays_10% | SCI4 PO.SCI 4 PO | 16 | 3199 | 30-Jul-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191700 | Test preproduction prototype Sector 0 with LEDs & cosmic rays_10% | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 160 | 0 | 30-Jul-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191800 | Analyze test results from preproduction prototype Sector 0 | SCI3 PO.SCI3 PO | 64 | 10694 | 07-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191800 | Analyze test results from preproduction prototype Sector 0 | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 320 | 0 | 07-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S191800 | Analyze test results from preproduction prototype Sector 0 | SCI4 PO.SCI 4 PO | 32 | 6397 | 07-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S194200 | Test and Review Preproduction Sectors 1-12 with LEDs & cosmic rays | PROF4 PO E.PROF4 PO E | 218 | 32104 | 24-Mar-20 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194200 | Test and Review Preproduction Sectors 1-12 with LEDs & cosmic rays | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1698 | 0 | 24-Mar-20 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194200 | Test and Review Preproduction Sectors 1-12 with LEDs & cosmic rays | SCI4 PO.SCI 4 PO | 170 | 35004 | 24-Mar-20 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194300 | Analyze and Review Test Results from Prepro Sectors 1-12 | SCI3 PO.SCI3 PO | 64 | 11015 | 24-Mar-20 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194300 | Analyze and Review Test Results from Prepro Sectors 1-12 | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1088 | 0 | 24-Mar-20 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194300 | Analyze and Review Test Results from Prepro Sectors 1-12 | SCI4 PO.SCI 4 PO | 186 | 38299 | 24-Mar-20 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194300 | Analyze and Review Test Results from Prepro Sectors 1-12 | PROF4 PO E.PROF4 PO E | 77 | 11339 | 24-Mar-20 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194300 | Analyze and Review Test Results from Prepro Sectors 1-12 | PROF4 PO M.PROF4 PO M | 77 | 11339 | 24-Mar-20 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194300 | Analyze and Review Test Results from Prepro Sectors 1-12 | TECH3 PO E.TECH3 PO E | 77 | 8787 | 24-Mar-20 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S194300 | Analyze and Review Test Results from Prepro Sectors 1-12 | TECH3 PO M.TECH3 PO M | 154 | 17575 | 24-Mar-20 A | 05-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S196900 | Test final sectors with LEDs & cosmic rays | PROF4 PO E.PROF4 PO E | 462 | 70218 | 23-Feb-21 A | 2022-02-04 | 10% | 415.8 |  |  | 63196.2 | 63196.2 | 0
S196900 | Test final sectors with LEDs & cosmic rays | TECH3 PO E.TECH3 PO E | 462 | 54415 | 23-Feb-21 A | 2022-02-04 | 10% | 415.8 |  |  | 48973.5 | 48973.5 | 0
S196900 | Test final sectors with LEDs & cosmic rays | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 4608 | 0 | 23-Feb-21 A | 2022-02-04 | 10% | 4147.2 |  |  | 0 | 0 | 0
S197000 | Repair or rework any sectors as required | PROF4 PO M.PROF4 PO M | 231 | 35114 | 16-Mar-21 A | 2022-02-04 | 31% | 159.39 |  |  | 24228.66 | 24228.66 | 0
S197000 | Repair or rework any sectors as required | TECH3 PO M.TECH3 PO M | 462 | 54423 | 16-Mar-21 A | 2022-02-04 | 31% | 318.78 |  |  | 37551.87 | 37551.87 | 0
S197000 | Repair or rework any sectors as required | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 2304 | 0 | 16-Mar-21 A | 2022-02-04 | 31% | 1589.76 |  |  | 0 | 0 | 0
S197000 | Repair or rework any sectors as required | SCI4 PO.SCI 4 PO | 462 | 98193 | 16-Mar-21 A | 2022-02-04 | 31% | 318.78 |  |  | 67753.17 | 67753.17 | 0
S197000 | Repair or rework any sectors as required | PROF4 PO E.PROF4 PO E | 231 | 35114 | 16-Mar-21 A | 2022-02-04 | 31% | 159.39 |  |  | 24228.66 | 24228.66 | 0
S197000 | Repair or rework any sectors as required | TECH3 PO E.TECH3 PO E | 231 | 27211 | 16-Mar-21 A | 2022-02-04 | 31% | 159.39 |  |  | 18775.59 | 18775.59 | 0
1.04 HCal
1.04.03 Outer HCAL Procure Scintillating Tiles
S208410 | Outer HCAL Scintillating Tile Acceptance Testing - Contributed Labor | PROF3 PO E.PROF3 PO E | 80 | 10225 | 01-Jul-20 A | 22-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208410 | Outer HCAL Scintillating Tile Acceptance Testing - Contributed Labor | PROF4 PO M.PROF4 PO M | 40 | 5951 | 01-Jul-20 A | 22-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208410 | Outer HCAL Scintillating Tile Acceptance Testing - Contributed Labor | SCI3 PO.SCI3 PO | 83 | 14432 | 01-Jul-20 A | 22-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208410 | Outer HCAL Scintillating Tile Acceptance Testing - Contributed Labor | TECH3 PO D.TECH3 PO D | 40 | 4612 | 01-Jul-20 A | 22-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208410 | Outer HCAL Scintillating Tile Acceptance Testing - Contributed Labor | STUDENT GSU OnC- PS1.STUDENT GSU OnC - Purchased Services | 650 | 11583 | 01-Jul-20 A | 22-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.04 Outer HCAL Sector Assembly and Testing
1.04.04.01 Outer HCAL Sector Assembly and Testing - Preproduction
S203110 | Populate Outer HCAL sectors with scintillating tiles (Preproduction) - Contributed Labor | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 62 | 0 | 02-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S203110 | Populate Outer HCAL sectors with scintillating tiles (Preproduction) - Contributed Labor | SCI4 PO.SCI 4 PO | 97 | 19973 | 02-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S203110 | Populate Outer HCAL sectors with scintillating tiles (Preproduction) - Contributed Labor | TECH3 PO M.TECH3 PO M | 372 | 42453 | 02-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S203210 | Populate Outer HCAL sectors with electronics (Preproduction) - Contributed Labor_50% | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 62 | 0 | 01-Aug-19 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203210 | Populate Outer HCAL sectors with electronics (Preproduction) - Contributed Labor_50% | SCI4 PO.SCI 4 PO | 97 | 19973 | 01-Aug-19 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203210 | Populate Outer HCAL sectors with electronics (Preproduction) - Contributed Labor_50% | TECH3 PO M.TECH3 PO M | 372 | 42453 | 01-Aug-19 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203310 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) - Contributed Labor | TECH3 PO M.TECH3 PO M | 248 | 28302 | 04-Nov-19 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203310 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) - Contributed Labor | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 62 | 0 | 04-Nov-19 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203310 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) - Contributed Labor | SCI4 PO.SCI 4 PO | 97 | 19973 | 04-Nov-19 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203510 | Outer HCAL Cosmics testing and initial calibration (Preproduction) - Contributed Labor | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 62 | 0 | 25-Nov-19 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203510 | Outer HCAL Cosmics testing and initial calibration (Preproduction) - Contributed Labor | SCI4 PO.SCI 4 PO | 97 | 19973 | 25-Nov-19 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203050 | Production Readiness Review - Outer HCAL Sector Assembly 1-6 | FACULTY ISU - Unpaid.FACULTY ISU - Unpaid | 8 | 0 | 13-Nov-19 A | 18-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S203050 | Production Readiness Review - Outer HCAL Sector Assembly 1-6 | PROF3 PO M.PROF3 PO M | 4 | 506 | 13-Nov-19 A | 18-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S203050 | Production Readiness Review - Outer HCAL Sector Assembly 1-6 | SCI4 PO.SCI 4 PO | 4 | 824 | 13-Nov-19 A | 18-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202502 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction), Contributed Labor Split | PROF3 PO E.PROF3 PO E | 13 | 1597 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202502 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction), Contributed Labor Split | PROF4 PO M.PROF4 PO M | 6 | 858 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202502 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction), Contributed Labor Split | SCI4 PO.SCI 4 PO | 57 | 11395 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202502 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction), Contributed Labor Split | SCI3 PO.SCI3 PO | 13 | 2172 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202502 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction), Contributed Labor Split | STUDENT GSU OnC- PS1.STUDENT GSU OnC - Purchased Services | 125 | 2117 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202502 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction), Contributed Labor Split | TECH3 PO D.TECH3 PO D | 6 | 665 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202802 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) Labor Split | CRAFT3.CRAFT3 | 1 | 121 | 03-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202802 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) Labor Split | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 1 | 0 | 03-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202802 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) Labor Split | STUDENT GSU - Unpaid.STUDENT GSU - Unpaid | 1 | 0 | 03-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S202802 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) Labor Split | TECH3 PO M.TECH3 PO M | 1 | 111 | 03-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.04.02 Outer HCAL Sector Assembly and Testing - Production
S209000 | Procure Outer HCAL Assembly & Testing Equipment - Provide Requirements to Procurement | TECH3 PO M.TECH3 PO M | 40 | 4565 | 03-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209000 | Procure Outer HCAL Assembly & Testing Equipment - Provide Requirements to Procurement | CRAFT3.CRAFT3 | 40 | 5003 | 03-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209000 | Procure Outer HCAL Assembly & Testing Equipment - Provide Requirements to Procurement | STUDENT GSU - Unpaid.STUDENT GSU - Unpaid | 40 | 0 | 03-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209000 | Procure Outer HCAL Assembly & Testing Equipment - Provide Requirements to Procurement | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 40 | 0 | 03-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209700 | Prepare Outer HCal Assembly Area for Production | TECH3 PO M.TECH3 PO M | 320 | 37615 | 10-Aug-20 A | 24-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209700 | Prepare Outer HCal Assembly Area for Production | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 160 | 0 | 10-Aug-20 A | 24-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209700 | Prepare Outer HCal Assembly Area for Production | STUDENT GSU - Unpaid.STUDENT GSU - Unpaid | 160 | 0 | 10-Aug-20 A | 24-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209700 | Prepare Outer HCal Assembly Area for Production | CRAFT3.CRAFT3 | 160 | 20612 | 10-Aug-20 A | 24-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S209810 | Populate Outer HCAL sectors with scintillating tiles - Contributed Labor | TECH3 PO M.TECH3 PO M | 1318 | 154925 | 17-Aug-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S209810 | Populate Outer HCAL sectors with scintillating tiles - Contributed Labor | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 260 | 0 | 17-Aug-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S209810 | Populate Outer HCAL sectors with scintillating tiles - Contributed Labor | SCI4 PO.SCI 4 PO | 209 | 44326 | 17-Aug-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S209910 | Populate Outer HCAL sectors with electronics - Contributed Labor | TECH3 PO M.TECH3 PO M | 1318 | 154925 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S209910 | Populate Outer HCAL sectors with electronics - Contributed Labor | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 260 | 0 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S209910 | Populate Outer HCAL sectors with electronics - Contributed Labor | SCI4 PO.SCI 4 PO | 209 | 44326 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210010 | Outer HCAL Sector LED testing and Light Tighting - Contributed Labor | TECH3 PO M.TECH3 PO M | 1318 | 154925 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210010 | Outer HCAL Sector LED testing and Light Tighting - Contributed Labor | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 260 | 0 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210010 | Outer HCAL Sector LED testing and Light Tighting - Contributed Labor | SCI4 PO.SCI 4 PO | 209 | 44326 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210210 | Outer HCAL Cosmics testing and initial calibration - Contributed Labor | POSTDOC GSU - Unpaid.POSTDOC GSU - Unpaid | 260 | 0 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210210 | Outer HCAL Cosmics testing and initial calibration - Contributed Labor | SCI4 PO.SCI 4 PO | 209 | 44326 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.05 Calorimeter Electronics
1.05.01 SiPMs
S215605 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 01-Jul-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215605 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 01-Jul-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215605 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 01-Jul-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215805 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 01-Jul-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215805 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 01-Jul-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215805 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 01-Jul-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215905 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 01-Aug-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215905 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 01-Aug-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215905 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 01-Aug-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S216005 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 02-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216005 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 02-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216005 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 02-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216105 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216105 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216105 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216205 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216205 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216205 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S213205 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213205 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213205 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9579 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213305 | Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 70 | 0 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213305 | Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 9 | 0 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213305 | Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 - Contributed Labor | PROF4 PO E.PROF4 PO E | 58 | 8293 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S216305 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216305 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216305 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216405 | Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 50 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216405 | Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 6 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216405 | Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 - Contributed Labor | PROF4 PO E.PROF4 PO E | 42 | 6185 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S213215 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213215 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9579 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213215 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S216315 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216315 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216315 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216325 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 80 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216325 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 10 | 0 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216325 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 - Contributed Labor | PROF4 PO E.PROF4 PO E | 67 | 9867 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02 Calorimeter Front End Electronics
1.05.02.01 EMCal Electronics: Preproduction
S221500 | Test EMCal SiPM Daughter Boards: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 53 | 6705 | 15-Jan-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S221500 | Test EMCal SiPM Daughter Boards: Sectors 1-12 | TECH3 PO E.TECH3 PO E | 28 | 3195 | 15-Jan-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S221500 | Test EMCal SiPM Daughter Boards: Sectors 1-12 | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 60 | 0 | 15-Jan-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S221500 | Test EMCal SiPM Daughter Boards: Sectors 1-12 | POSTDOC ISU - Unpaid.POSTDOC ISU - Unpaid | 20 | 0 | 15-Jan-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S221500 | Test EMCal SiPM Daughter Boards: Sectors 1-12 | SCI3 PO.SCI3 PO | 14 | 2409 | 15-Jan-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223100 | Test EMCal Interface Boards: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 45 | 5693 | 19-Feb-20 A | 16-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223100 | Test EMCal Interface Boards: Sectors 1-12 | TECH3 PO E.TECH3 PO E | 32 | 3652 | 19-Feb-20 A | 16-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223100 | Test EMCal Interface Boards: Sectors 1-12 | POSTDOC ISU - Unpaid.POSTDOC ISU - Unpaid | 20 | 0 | 19-Feb-20 A | 16-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223100 | Test EMCal Interface Boards: Sectors 1-12 | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 60 | 0 | 19-Feb-20 A | 16-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223100 | Test EMCal Interface Boards: Sectors 1-12 | SCI3 PO.SCI3 PO | 24 | 4131 | 19-Feb-20 A | 16-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223400 | Test calorimeter controller boards: Sectors 1-12 | PROF3 PO E.PROF3 PO E | 60 | 7591 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223400 | Test calorimeter controller boards: Sectors 1-12 | TECH3 PO E.TECH3 PO E | 24 | 2739 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223400 | Test calorimeter controller boards: Sectors 1-12 | POSTDOC ISU - Unpaid.POSTDOC ISU - Unpaid | 20 | 0 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223400 | Test calorimeter controller boards: Sectors 1-12 | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 60 | 0 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S223400 | Test calorimeter controller boards: Sectors 1-12 | SCI3 PO.SCI3 PO | 45 | 7745 | 01-Oct-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02.02 EMCal Electronics: Production
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | PROF3 PO E.PROF3 PO E | 321 | 41744 | 01-Dec-20 A | 2021-07-20 | 60% | 128.4 |  |  | 16697.6 | 16697.6 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | SCI3 PO.SCI3 PO | 80 | 14153 | 01-Dec-20 A | 2021-07-20 | 60% | 32 |  |  | 5661.2 | 5661.2 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | TECH3 PO E.TECH3 PO E | 80 | 9385 | 01-Dec-20 A | 2021-07-20 | 60% | 32 |  |  | 3754 | 3754 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 176 | 0 | 01-Dec-20 A | 2021-07-20 | 60% | 70.4 |  |  | 0 | 0 | 0
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 176 | 0 | 01-Dec-20 A | 2021-07-20 | 60% | 70.4 |  |  | 0 | 0 | 0
1.05.02.03 HCal Electronics: Preproduction
S236900 | Test HCal LED Boards: (6 Modules) | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 40 | 0 | 15-Aug-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S236900 | Test HCal LED Boards: (6 Modules) | POSTDOC ISU - Unpaid.POSTDOC ISU - Unpaid | 40 | 0 | 15-Aug-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S236900 | Test HCal LED Boards: (6 Modules) | PROF3 PO E.PROF3 PO E | 24 | 2948 | 15-Aug-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S236900 | Test HCal LED Boards: (6 Modules) | SCI3 PO.SCI3 PO | 40 | 6684 | 15-Aug-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S236900 | Test HCal LED Boards: (6 Modules) | TECH3 PO E.TECH3 PO E | 24 | 2659 | 15-Aug-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S237900 | Assemble HCal Power and Signal Cables and Power System: (6 Modules) | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 20 | 0 | 01-Oct-19 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S237900 | Assemble HCal Power and Signal Cables and Power System: (6 Modules) | PROF3 PO E.PROF3 PO E | 52 | 6571 | 01-Oct-19 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S237900 | Assemble HCal Power and Signal Cables and Power System: (6 Modules) | TECH3 PO E.TECH3 PO E | 103 | 11741 | 01-Oct-19 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S237900 | Assemble HCal Power and Signal Cables and Power System: (6 Modules) | POSTDOC ISU - Unpaid.POSTDOC ISU - Unpaid | 20 | 0 | 01-Oct-19 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02.04 HCal Electronics: Production
S240700 | Test HCal Preamp Boards: Production | PROF3 PO E.PROF3 PO E | 161 | 20979 | 28-Sep-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S240700 | Test HCal Preamp Boards: Production | SCI3 PO.SCI3 PO | 40 | 7091 | 28-Sep-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S240700 | Test HCal Preamp Boards: Production | TECH3 PO E.TECH3 PO E | 80 | 9404 | 28-Sep-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S240700 | Test HCal Preamp Boards: Production | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 80 | 0 | 28-Sep-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S240700 | Test HCal Preamp Boards: Production | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 192 | 0 | 28-Sep-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S241800 | Test HCal LED Boards: Production | PROF3 PO E.PROF3 PO E | 151 | 19561 | 20-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241800 | Test HCal LED Boards: Production | SCI3 PO.SCI3 PO | 60 | 10574 | 20-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241800 | Test HCal LED Boards: Production | TECH3 PO E.TECH3 PO E | 240 | 28047 | 20-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241800 | Test HCal LED Boards: Production | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 60 | 0 | 20-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241800 | Test HCal LED Boards: Production | STUDENT GRAD Other - Unpaid.STUDENT GRAD Other - Unpaid | 160 | 0 | 20-Nov-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S242100 | Test Hcal Backplane Boards: Production | PROF3 PO E.PROF3 PO E | 211 | 27494 | 15-Oct-20 A | 01-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S242100 | Test Hcal Backplane Boards: Production | SCI3 PO.SCI3 PO | 60 | 10636 | 15-Oct-20 A | 01-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S242100 | Test Hcal Backplane Boards: Production | TECH3 PO E.TECH3 PO E | 240 | 28211 | 15-Oct-20 A | 01-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S242100 | Test Hcal Backplane Boards: Production | SCI3 UM - Unpaid.SCI3 UM - Unpaid | 60 | 0 | 15-Oct-20 A | 01-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S242100 | Test Hcal Backplane Boards: Production | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 160 | 0 | 15-Oct-20 A | 01-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243000 | Test HCal Interface Boards: Production | PROF3 PO E.PROF3 PO E | 99 | 12524 | 15-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243000 | Test HCal Interface Boards: Production | SCI3 PO.SCI3 PO | 8 | 1377 | 15-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243000 | Test HCal Interface Boards: Production | TECH3 PO E.TECH3 PO E | 8 | 913 | 15-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243000 | Test HCal Interface Boards: Production | SCI2 UM - Unpaid.SCI2 UM - Unpaid | 8 | 0 | 15-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243000 | Test HCal Interface Boards: Production | STUDENT GRAD UM - Unpaid.STUDENT GRAD UM - Unpaid | 40 | 0 | 15-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.06 DAQ/Trigger
1.06.01 DAQ
1.06.01.02 DAQ Prototype
S254800 | DAQ Prototype: Software development - Multiple Subsystem Test | PROF3 PO E.PROF3 PO E | 640 | 78765 | 03-Jun-19 A | 15-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S254800 | DAQ Prototype: Software development - Multiple Subsystem Test | SCI3 PO.SCI3 PO | 96 | 16073 | 03-Jun-19 A | 15-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S254800 | DAQ Prototype: Software development - Multiple Subsystem Test | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 72 | 0 | 03-Jun-19 A | 15-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S254900 | DAQ Prototype: Installation and testing | SCI3 PO.SCI3 PO | 16 | 2754 | 15-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S254900 | DAQ Prototype: Installation and testing | TECH3 PO E.TECH3 PO E | 40 | 4565 | 15-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S254900 | DAQ Prototype: Installation and testing | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 40 | 0 | 15-Jan-20 A | 29-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.01.03 DAQ Production
S256000 | DAQ Production Boards: Firmware updates | SCI3 PO.SCI3 PO | 64 | 11345 | 2021-11-02 | 2022-01-18 | 0% | 64 |  |  | 11345 | 11345 | 0
S256000 | DAQ Production Boards: Firmware updates | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 240 | 0 | 2021-11-02 | 2022-01-18 | 0% | 240 |  |  | 0 | 0 | 0
S256000 | DAQ Production Boards: Firmware updates | PROF3 PO E.PROF3 PO E | 960 | 125093 | 2021-11-02 | 2022-01-18 | 0% | 960 |  |  | 125093 | 125093 | 0
S260600 | DAQ Production: DAQ Software development | PROF4 PO M.PROF4 PO M | 880 | 130060 | 16-Nov-20 A | 2021-11-30 | 90% | 88 |  |  | 13006 | 13006 | 0
S260600 | DAQ Production: DAQ Software development | SCI3 PO.SCI3 PO | 880 | 151998 | 16-Nov-20 A | 2021-11-30 | 90% | 88 |  |  | 15199.8 | 15199.8 | 0
S260600 | DAQ Production: DAQ Software development | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 1760 | 0 | 16-Nov-20 A | 2021-11-30 | 90% | 176 |  |  | 0 | 0 | 0
1.06.02 Local Level 1 Trigger (LL1)
1.06.02.02 LL1 Trigger Prototype v1
S262800 | Trigger Prototype v1: Preproduction Readiness Review and Design Specifications Update | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 32 | 0 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S262800 | Trigger Prototype v1: Preproduction Readiness Review and Design Specifications Update | SCI3 PO.SCI3 PO | 32 | 5507 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S263800 | Final Design Review - DAQ Local Level-1 | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 32 | 0 | 2021-08-30 | 2021-09-02 | 0% | 32 |  |  | 0 | 0 | 0
S263800 | Final Design Review - DAQ Local Level-1 | SCI3 PO.SCI3 PO | 32 | 5673 | 2021-08-30 | 2021-09-02 | 0% | 32 |  |  | 5673 | 5673 | 0
1.06.02.04 LL1 Trigger Production
S264200 | Production Readiness Review - DAQ Local Level-1 | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 32 | 0 | 2021-10-14 | 2021-10-27 | 0% | 32 |  |  | 0 | 0 | 0
S264200 | Production Readiness Review - DAQ Local Level-1 | SCI3 PO.SCI3 PO | 32 | 5673 | 2021-10-14 | 2021-10-27 | 0% | 32 |  |  | 5673 | 5673 | 0
1.06.03 Global Level 1 Trigger (GL1)
1.06.03.02 GL1 Trigger Prototype
S266600 | GL1 Prototype: test prototype | SCI3 PO.SCI3 PO | 80 | 13768 | 17-Dec-19 A | 2021-07-30 | 95% | 4 |  |  | 688.4 | 688.4 | 0
S266600 | GL1 Prototype: test prototype | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 240 | 0 | 17-Dec-19 A | 2021-07-30 | 95% | 12 |  |  | 0 | 0 | 0
S266600 | GL1 Prototype: test prototype | PROF3 PO E.PROF3 PO E | 240 | 30362 | 17-Dec-19 A | 2021-07-30 | 95% | 12 |  |  | 1518.1 | 1518.1 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | SCI3 PO.SCI3 PO | 80 | 13768 | 03-Nov-20 A | 2021-08-30 | 60% | 32 |  |  | 5507.2 | 5507.2 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 100 | 0 | 03-Nov-20 A | 2021-08-30 | 60% | 40 |  |  | 0 | 0 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 200 | 0 | 03-Nov-20 A | 2021-08-30 | 60% | 80 |  |  | 0 | 0 | 0
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | PROF3 PO E.PROF3 PO E | 80 | 10121 | 03-Nov-20 A | 2021-08-30 | 60% | 32 |  |  | 4048.4 | 4048.4 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | SCI3 PO.SCI3 PO | 64 | 11015 | 2021-07-02 | 2021-07-30 | 0% | 64 |  |  | 11015 | 11015 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 60 | 0 | 2021-07-02 | 2021-07-30 | 0% | 60 |  |  | 0 | 0 | 0
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | PROF3 PO E.PROF3 PO E | 80 | 10121 | 2021-07-02 | 2021-07-30 | 0% | 80 |  |  | 10121 | 10121 | 0
1.06.03.03 GL1 Trigger Production
S267000 | Procure Production GL1 Components - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 36 | 6196 | 02-Apr-21 A | 08-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S267000 | Procure Production GL1 Components - Provide Requirements to Procurement | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 36 | 0 | 02-Apr-21 A | 08-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S266900 | GL1 Production: final firmware updates | SCI3 SBU - Unpaid.SCI3 SBU - Unpaid | 64 | 0 | 2021-08-02 | 2021-10-26 | 0% | 64 |  |  | 0 | 0 | 0
S266900 | GL1 Production: final firmware updates | SCI3 PO.SCI3 PO | 64 | 11015 | 2021-08-02 | 2021-10-26 | 0% | 64 |  |  | 11015 | 11015 | 0
S266900 | GL1 Production: final firmware updates | PROF3 PO E.PROF3 PO E | 406 | 51363 | 2021-08-02 | 2021-10-26 | 0% | 406 |  |  | 51363 | 51363 | 0
S267900 | GL1 Production: install GL1 system | PROF3 PO E.PROF3 PO E | 80 | 10424 | 2021-10-27 | 2021-12-03 | 0% | 80 |  |  | 10424 | 10424 | 0
S267900 | GL1 Production: install GL1 system | TECH3 PO E.TECH3 PO E | 320 | 37615 | 2021-10-27 | 2021-12-03 | 0% | 320 |  |  | 37615 | 37615 | 0
S267900 | GL1 Production: install GL1 system | STUDENT SBU - Unpaid.STUDENT SBU - Unpaid | 160 | 0 | 2021-10-27 | 2021-12-03 | 0% | 160 |  |  | 0 | 0 | 0
S268000 | GL1 Production: commission GL1 system | SCI3 PO.SCI3 PO | 72 | 12763 | 2021-12-06 | 2022-01-19 | 0% | 72 |  |  | 12763 | 12763 | 0
S268000 | GL1 Production: commission GL1 system | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 108 | 0 | 2021-12-06 | 2022-01-19 | 0% | 108 |  |  | 0 | 0 | 0
S268000 | GL1 Production: commission GL1 system | PROF3 PO E.PROF3 PO E | 108 | 14073 | 2021-12-06 | 2022-01-19 | 0% | 108 |  |  | 14073 | 14073 | 0
1.06.04 Timing System
1.06.04.02 Timing System Prototype
S269400 | Timing System Prototype: test prototype | SCI3 PO.SCI3 PO | 24 | 4123 | 19-Dec-19 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S269400 | Timing System Prototype: test prototype | STUDENT UCol - Unpaid.STUDENT UCol - Unpaid | 120 | 0 | 19-Dec-19 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S269400 | Timing System Prototype: test prototype | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 36 | 0 | 19-Dec-19 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | SCI3 PO.SCI3 PO | 16 | 2754 | 24-Feb-20 A | 2021-07-30 | 95% | 0.8 |  |  | 137.7 | 137.7 | 0
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | STUDENT UCol - Unpaid.STUDENT UCol - Unpaid | 80 | 0 | 24-Feb-20 A | 2021-07-30 | 95% | 4 |  |  | 0 | 0 | 0
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 40 | 0 | 24-Feb-20 A | 2021-07-30 | 95% | 2 |  |  | 0 | 0 | 0
S269600 | Update design specifications; incorporate final design choice | SCI3 PO.SCI3 PO | 12 | 2065 | 2021-08-02 | 2021-08-13 | 0% | 12 |  |  | 2065 | 2065 | 0
S269600 | Update design specifications; incorporate final design choice | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 30 | 0 | 2021-08-02 | 2021-08-13 | 0% | 30 |  |  | 0 | 0 | 0
S268905 | Timing System Prototype: develop firmware FY19 Split | PROF3 PO E.PROF3 PO E | 326 | 40041 | 03-Jun-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S268905 | Timing System Prototype: develop firmware FY19 Split | SCI3 PO.SCI3 PO | 19 | 3175 | 03-Jun-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S268905 | Timing System Prototype: develop firmware FY19 Split | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 19 | 0 | 03-Jun-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.04.03 Timing System Production
S269700 | Timing System Production (FPGA Boards) - Provide Requirements to Procurement | PROF3 PO E.PROF3 PO E | 40 | 5060 | 01-Apr-21 A | 07-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S269700 | Timing System Production (FPGA Boards) - Provide Requirements to Procurement | SCI3 PO.SCI3 PO | 80 | 13768 | 01-Apr-21 A | 07-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S269700 | Timing System Production (FPGA Boards) - Provide Requirements to Procurement | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 40 | 0 | 01-Apr-21 A | 07-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S270500 | Timing System Production: final firmware updates | SCI3 PO.SCI3 PO | 64 | 11015 | 15-Mar-21 A | 2021-08-16 | 60% | 25.6 |  |  | 4406 | 4406 | 0
S270500 | Timing System Production: final firmware updates | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 64 | 0 | 15-Mar-21 A | 2021-08-16 | 60% | 25.6 |  |  | 0 | 0 | 0
S270500 | Timing System Production: final firmware updates | PROF3 PO E.PROF3 PO E | 560 | 70845 | 15-Mar-21 A | 2021-08-16 | 60% | 224 |  |  | 28338 | 28338 | 0
S270700 | Timing System Production: commission timing system | SCI3 PO.SCI3 PO | 128 | 22690 | 2021-12-13 | 2022-01-11 | 0% | 128 |  |  | 22690 | 22690 | 0
S270700 | Timing System Production: commission timing system | SCI3 UCol - Unpaid.SCI3 UCol - Unpaid | 192 | 0 | 2021-12-13 | 2022-01-11 | 0% | 192 |  |  | 0 | 0 | 0
S270700 | Timing System Production: commission timing system | PROF3 PO E.PROF3 PO E | 320 | 41698 | 2021-12-13 | 2022-01-11 | 0% | 320 |  |  | 41698 | 41698 | 0
S270800 | Timing System Production: additional firmware updates | PROF3 PO E.PROF3 PO E | 144 | 18764 | 2022-01-12 | 2022-02-04 | 0% | 144 |  |  | 18764 | 18764 | 0
1.07 Min Bias Trigger Detector
S273800 | Test Full Min/Bias Electronics | PROF3 PO M.PROF3 PO M | 16 | 2085 | 2021-12-10 | 2022-01-18 | 0% | 16 |  |  | 2085 | 2085 | 0
S273800 | Test Full Min/Bias Electronics | SCI3 PO.SCI3 PO | 48 | 8509 | 2021-12-10 | 2022-01-18 | 0% | 48 |  |  | 8509 | 8509 | 0
S273800 | Test Full Min/Bias Electronics | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 48 | 0 | 2021-12-10 | 2022-01-18 | 0% | 48 |  |  | 0 | 0 | 0
S274000 | Bench Test Min/Bias Detector | SCI3 PO.SCI3 PO | 80 | 14182 | 2022-01-19 | 2022-01-25 | 0% | 80 |  |  | 14182 | 14182 | 0
S274000 | Bench Test Min/Bias Detector | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 80 | 0 | 2022-01-19 | 2022-01-25 | 0% | 80 |  |  | 0 | 0 | 0
S272700 | Prototype Shaper/Disc Board Testing and evaluation, revisions; Final Design and Procurment Readiness Reviews | PROF3 PO E.PROF3 PO E | 72 | 8978 | 09-Jul-19 A | 25-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S272700 | Prototype Shaper/Disc Board Testing and evaluation, revisions; Final Design and Procurment Readiness Reviews | SCI3 PO.SCI3 PO | 72 | 12214 | 09-Jul-19 A | 25-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S272700 | Prototype Shaper/Disc Board Testing and evaluation, revisions; Final Design and Procurment Readiness Reviews | STUDENT Other - Unpaid.STUDENT Other - Unpaid | 72 | 0 | 09-Jul-19 A | 25-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S272701 | Final Design Review, Procurement Readiness Review - MBD (Discriminator/Shaper board) | SCI3 PO.SCI3 PO | 8 | 1377 | 25-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S272701 | Final Design Review, Procurement Readiness Review - MBD (Discriminator/Shaper board) | SCI3 Other - Unpaid.SCI3 Other - Unpaid | 8 | 0 | 25-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S272701 | Final Design Review, Procurement Readiness Review - MBD (Discriminator/Shaper board) | SCI4 PO.SCI 4 PO | 4 | 824 | 25-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S272701 | Final Design Review, Procurement Readiness Review - MBD (Discriminator/Shaper board) | PROF3 PO E.PROF3 PO E | 8 | 1012 | 25-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
A-TEC TEC
POM02B-PCR026 POM02 sPHENIX WBS 1.x, 2.x Baseline PCR026 Approved
1 MIE Project
1.01 Project Management
S1001839 | Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | Actual NonLabor.Actual Nonlabor | 22509 | 24834 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.01.02 Labor by FY
S103000 | Mgmt Labor - A - MIE - FY20 | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 1559 | 245877 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S103200 | Mgmt Labor - A - MIE - FY21 | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 1050 | 170568 | 01-Oct-20 A | 30-Sep-21* | 74.4% | 268.8 |  |  | 43665.408 | 43665.408 | 0
S103400 | Mgmt labor - A - MIE - FY22 | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 68 | 11361 | 01-Oct-21* | 2022-01-05 | 0% | 68 |  |  | 11361 | 11361 | 0
S102915 | Mgmt labor - A - MIE, Phase 2 - FY19 split | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 285 | 43639 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.01.03 Management Travel
S104100 | Travel FY20 | Travel.Travel Cost | 20000 | 27080 | 01-Oct-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S104200 | Travel FY21 | Travel.Travel Cost | 5000 | 6905 | 01-Oct-20 A | 2021-09-30 | 74.4% | 1280 |  |  | 1767.68 | 1767.68 | 0
1.02 TPC
1.02.01 TPC Mechanics
1.02.01.01 TPC v1 Field Cage Prototype
S108800 | Procure TPC Handling Cart M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 13000 | 15089 | 01-Apr-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.03 TPC Final Field Cage
S112800 | Procure TPC v2 Field Cage Modification Parts M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 6000 | 6828 | 30-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S113050 | TPC Module technical Support | Purch 1st $2M.Material (Purchase (1st $2M) | 80000 | 92855 | 01-Dec-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.06 TPC Production GEM Acquisition
S120000 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 39080 | 44470 | 14-May-20 A | 20-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S120100 | Procure Production of TPC GEM foils (includes Technician fees) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 133200 | 154002 | 21-May-20 A | 17-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.07 TPC High Voltage System
S121400 | Procure TPC GEM HV Power Supplies - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 107922 | 125263 | 22-Sep-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S120400 | Procure TPC Membrane HV Cables - M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 600 | 683 | 08-Jan-20 A | 20-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S121500 | Procure TPC GEM HV Membrane Power Supply - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 10550 | 12245 | 06-Oct-20 A | 13-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.08 TPC Assembly
S121650 | Procure Piping Fittings | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 1102 | 1279 | 17-May-21 A | 2021-09-09 | 50% | 551 |  |  | 639.5 | 639.5 | 0
S121950 | TPC Assembly technical Support | Purch 1st $2M.Material (Purchase (1st $2M) | 20000 | 23254 | 01-Jun-21 A | 2021-09-20 | 33% | 13400 |  |  | 15580.18 | 15580.18 | 0
S121605 | TPC Assembly Mechanical Engineering Support | PROF2.PROF2 | 1500 | 156234 | 01-Feb-21 A | 2022-01-20 | 43.62% | 845.7 |  |  | 88084.7292 | 88084.7292 | 0
1.02.02 TPC R1 Modules
1.02.02.03 TPC R1 Module Production
S125500 | Build TPC R1 Modules | TECH3 Wayne - PS.TECH3 Wayne - Purchased Services | 960 | 63130 | 11-Jan-21 A | 2021-09-03 | 85% | 144 |  |  | 9469.5 | 9469.5 | 0
S125600 | Test TPC R1 Modules | TECH3 Wayne - PS.TECH3 Wayne - Purchased Services | 960 | 63173 | 11-Jan-21 A | 2021-09-20 | 85% | 144 |  |  | 9475.95 | 9475.95 | 0
S124500 | Procure TPC R1 Module Parts (Frames) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 14601 | 16615 | 17-Mar-20 A | 27-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S124800 | Procure TPC R1 Module Parts (Strongbacks) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 8216 | 9349 | 25-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S125100 | Procure TPC R1 Module Parts (Padplanes) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 44039 | 50113 | 22-Mar-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S125400 | Procure TPC R1 Module Parts (Grids) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 9797 | 11148 | 24-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.03 TPC R2 Modules
1.02.03.03 TPC R2 Module Production
S128500 | Procure TPC R2 Module Prod. Parts (Frames) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 14601 | 16615 | 18-Mar-20 A | 27-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S128800 | Procure TPC R2 Module Prod. Parts (Strongbacks) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 9184 | 10451 | 17-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S129100 | Procure TPC R2 Module Prod. Parts (Padplanes) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 52990 | 60299 | 27-Aug-20 A | 29-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S129400 | Procure TPC R2 Module Prod. Parts (Grids) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 9797 | 11148 | 24-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.04 TPC R3 Modules
1.02.04.03 TPC R3 Module Production
S132700 | Procure TPC R3 Module Prod. Parts (Frames) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 16819 | 19139 | 18-Mar-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S133000 | Procure TPC R3 Module Prod. Parts (Strongbacks) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 10762 | 12246 | 17-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S133300 | Procure TPC R3 Module Prod. Parts (Padplanes) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 71770 | 81669 | 16-Jun-20 A | 22-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S133600 | Procure TPC R3 Module Prod. Parts (Grids) - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 10288 | 11707 | 24-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.05 TPC FEE
1.02.05.03 SAMPA chip 80 nsec
S140500 | Populate v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip | Purch 1st $2M.Material (Purchase (1st $2M) | 3000 | 3414 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S140400 | Procure Engineering Run of Full SAMPA Chip - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 233000 | 265137 | 30-Dec-19 A | 06-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.05.04 TPC FEE Production
S136500 | Procure TPC FEE Cooling System - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 60155 | 69821 | 15-Mar-21 A | 2021-07-30 | 17.8% | 49447.41 |  |  | 57392.862 | 57392.862 | 0
S141500 | Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 29663 | 34429 | 15-Mar-21 A | 2021-07-30 | 33.2% | 19814.884 |  |  | 22998.572 | 22998.572 | 0
S142500 | Procure TPC FEE LV Power Supplies - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 190056 | 220595 | 25-Jan-21 A | 2021-07-30 | 80.2% | 37631.088 |  |  | 43677.81 | 43677.81 | 0
S143200 | Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 150983 | 175244 | 2021-09-29 | 2021-10-05 | 0% | 150983 |  |  | 175244 | 175244 | 0
S141800 | Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 266694 | 309548 | 02-Nov-20 A | 2021-07-30 | 85% | 40004.1 |  |  | 46432.2 | 46432.2 | 0
S143250 | TPC Front End Electronics | Purch 1st $2M.Material (Purchase (1st $2M) | 150000 | 174103 | 15-Feb-21 A | 2021-07-30 | 33.2% | 100200 |  |  | 116300.804 | 116300.804 | 0
S143270 | TPC FEE Electrical Engineering Support 1 | TECH1.TECH1 | 1500 | 119731 | 01-Feb-21 A | 2021-12-29 | 46.52% | 802.2 |  |  | 64032.1388 | 64032.1388 | 0
S143271 | TPC FEE Electrical Engineering Support 2 | PROF3.PROF3 | 0 | 0 | 01-Feb-21 A | 2021-12-29 | 46.52% | 0 |  |  | 0 | 0 | 0
1.02.06 TPC DAM
1.02.06.03 TPC DAM Production
S147300 | Procure TPC DAM Felix 2.0 Boards - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 130362 | 151309 | 02-Dec-20 A | 2021-07-29 | 80% | 26072.4 |  |  | 30261.8 | 30261.8 | 0
S148400 | Procure TPC EDBC Computers & Peripherals - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 210883 | 244769 | 01-Jun-21 A | 14-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S147370 | Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 80745 | 93719 | 2021-10-20 | 2021-10-26 | 0% | 80745 |  |  | 93719 | 93719 | 0
S147380 | TPC DAM Electrical Engineering Support | PROF3.PROF3 | 368 | 48327 | 01-Feb-21 A | 2021-12-30 | 45% | 202.4 |  |  | 26579.85 | 26579.85 | 0
1.02.07 TPC Support Systems
1.02.07.01 TPC Laser System
S149600 | Procure TPC Lasers - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 145840 | 165955 | 06-Oct-20 A | 2021-08-16 | 50% | 72920 |  |  | 82977.5 | 82977.5 | 0
S150300 | Procure TPC Optics with Mirrors - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 58800 | 66910 | 13-Oct-20 A | 2021-08-12 | 50% | 29400 |  |  | 33455 | 33455 | 0
S150500 | Procure TPC mirror bundles with supports M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 15000 | 17060 | 13-Jan-21 A | 2021-08-31 | 50% | 7500 |  |  | 8530 | 8530 | 0
S150800 | Install &Test TPC Laser safety interlocks M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 2000 | 2276 | 2021-08-20 | 2021-08-31 | 0% | 2000 |  |  | 2276 | 2276 | 0
S149650 | TPC Diffuse Lasers | Purch 1st $2M.Material (Purchase (1st $2M) | 200000 | 232137 | 04-Jan-21 A | 2021-08-02 | 50% | 100000 |  |  | 116068.5 | 116068.5 | 0
1.02.07.02 TPC Gas System
S151600 | Procure TPC Gas System mass flow meters M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 6831 | 7773 | 13-Apr-20 A | 30-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S152300 | Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 33035 | 37591 | 12-Jan-21 A | 2021-07-29 | 70% | 9910.5 |  |  | 11277.3 | 11277.3 | 0
S152500 | Procure TPC Gas System scrubbers M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 7727 | 8793 | 13-Apr-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S152700 | Procure TPC Gas System oxygen and water sensors M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 11164 | 12704 | 13-Apr-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S153000 | Procure TPC Gas System Computer Controller M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 18401 | 20975 | 2021-08-25 | 2021-10-14 | 0% | 18401 |  |  | 20975 | 20975 | 0
S153700 | Procure TPC Gas System Components for Installation - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 34086 | 39563 | 08-Mar-21 A | 2021-08-31 | 70% | 10225.8 |  |  | 11868.9 | 11868.9 | 0
1.02.07.03 TPC Cooling System
S155000 | Procure TPC Cooling System Equipment - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 44339 | 50454 | 15-Feb-21 A | 31-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S155700 | Procure TPC Plumbing - Contract/PO M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 11667 | 13542 | 2021-09-15 | 2021-10-13 | 0% | 11667 |  |  | 13542 | 13542 | 0
S155900 | Set up TPC Cooling System computer controls M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 10493 | 12179 | 2021-10-14 | 2021-10-20 | 0% | 10493 |  |  | 12179 | 12179 | 0
1.03 EMCal
S1001879 | Actuals - Nonlabor - sPHENIX EMCal FY19M8 | Actual NonLabor.Actual Nonlabor | 73248 | 80812 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.01 EMCAL Block Fabrication
1.03.01.03 EMCAL Final Block Production
1.03.01.03.01 Order Material for EMCAL Final Block Production
S169500 | Establish EMCAL final blocks contract with UIUC | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1083 | 12-Sep-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171200 | Procure EMCAL Epoxy for Final Blocks - Provide Requirements to Procurement | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 8 | 414 | 19-Mar-20 A | 24-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171200 | Procure EMCAL Epoxy for Final Blocks - Provide Requirements to Procurement | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 8 | 903 | 19-Mar-20 A | 24-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S172600 | Set up factory for final blocks Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 29 | 1473 | 05-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S172600 | Set up factory for final blocks Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 50 | 5543 | 05-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S172800 | Prepare fiber assemblies for final blocks | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 0 | 0 | 21-Jun-19 A | 2021-08-02 | 96% | 0 |  |  | 0 | 0 | 0
S172800 | Prepare fiber assemblies for final blocks | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 9360 | 163757 | 21-Jun-19 A | 2021-08-02 | 96% | 374.4 |  |  | 6550.28 | 6550.28 | 0
S172800 | Prepare fiber assemblies for final blocks | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 0 | 0 | 21-Jun-19 A | 2021-08-02 | 96% | 0 |  |  | 0 | 0 | 0
S172900 | Production Readiness Review, Safety Review - EMCal Blocks | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 | 496 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S172900 | Production Readiness Review, Safety Review - EMCal Blocks | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1083 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S170200 | Procure EMCAL W Powder for Final Blocks - Sectors 13-38 - Delivery Acceptance | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 475410 | 540981 | 01-Nov-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171800 | Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 90653 | 104592 | 03-Aug-20 A | 2021-07-19 | 55% | 40793.85 |  |  | 47066.4 | 47066.4 | 0
S172700 | Set up factory for final blocks M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 2530 | 2840 | 05-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S172500 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 26230 | 30218 | 03-Aug-20 A | 2021-07-19 | 75% | 6557.5 |  |  | 7554.5 | 7554.5 | 0
S170210 | Procure EMCAL W Powder for Final Blocks - Sectors 39-64 - Delivery Acceptance | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 475410 | 540981 | 15-Jun-20 A | 26-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171023 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 23 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 34272 | 38234 | 01-Feb-21 A | 25-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S171003 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 3 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40406 | 03-Jun-19 A | 18-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171004 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 4 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40406 | 19-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171005 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 5 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40406 | 01-Aug-19 A | 20-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171006 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 6 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40406 | 03-Sep-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171007 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 7 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 01-Oct-19 A | 30-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171008 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 8 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 08-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171009 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 9 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 03-Dec-19 A | 18-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S171010 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 10 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 02-Jan-20 A | 31-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171011 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 11 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171012 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 12 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 02-Mar-20 A | 26-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171013 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 13 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 01-May-20 A | 12-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171014 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 14 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 13-May-20 A | 27-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171015 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 15 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 01-Jun-20 A | 26-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171016 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 16 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 01-Jul-20 A | 30-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171017 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 17 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 03-Aug-20 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171018 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 18 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 01-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171019 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 19 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 01-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171020 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 20 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 02-Nov-20 A | 27-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S171021 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 21 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 04-Jan-21 A | 18-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S171022 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 22 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 36624 | 40858 | 19-Jan-21 A | 28-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S172850 | Supervise EMCal Final Block Production | Purch 1st $2M.Material (Purchase (1st $2M) | 52800 | 60868 | 01-May-20 A | 2021-11-30 | 65% | 18480 |  |  | 21303.8 | 21303.8 | 0
S172870 | EMCal Block Production QA | Purch 1st $2M.Material (Purchase (1st $2M) | 460000 | 533915 | 01-Dec-20 A | 2021-09-27 | 70% | 138000 |  |  | 160174.5 | 160174.5 | 0
1.03.01.03.02 Fabricate final blocks
S173000 | Fabricate final blocks sector 13 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 13-Oct-20 A | 20-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173000 | Fabricate final blocks sector 13 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 13-Oct-20 A | 20-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173000 | Fabricate final blocks sector 13 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 13-Oct-20 A | 20-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173100 | Fabricate final blocks sector 14 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 21-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173100 | Fabricate final blocks sector 14 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 21-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173100 | Fabricate final blocks sector 14 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 21-Oct-20 A | 28-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173200 | Fabricate final blocks sector 15 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 22-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173200 | Fabricate final blocks sector 15 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 22-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173200 | Fabricate final blocks sector 15 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 22-Oct-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173300 | Fabricate final blocks sector 16 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 21-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173300 | Fabricate final blocks sector 16 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 21-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173300 | Fabricate final blocks sector 16 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 21-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173400 | Fabricate final blocks sector 17 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 17-Nov-20 A | 24-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173400 | Fabricate final blocks sector 17 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 17-Nov-20 A | 24-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173400 | Fabricate final blocks sector 17 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 17-Nov-20 A | 24-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173500 | Fabricate final blocks sector 18 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 25-Nov-20 A | 08-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173500 | Fabricate final blocks sector 18 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 25-Nov-20 A | 08-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173500 | Fabricate final blocks sector 18 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 25-Nov-20 A | 08-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173600 | Fabricate final blocks sector 19 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 09-Dec-20 A | 16-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173600 | Fabricate final blocks sector 19 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 09-Dec-20 A | 16-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173600 | Fabricate final blocks sector 19 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 09-Dec-20 A | 16-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S173700 | Fabricate final blocks sector 20 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 17-Dec-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S173700 | Fabricate final blocks sector 20 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 17-Dec-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S173700 | Fabricate final blocks sector 20 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 17-Dec-20 A | 11-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S173800 | Fabricate final blocks sector 21 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 12-Jan-21 A | 20-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S173800 | Fabricate final blocks sector 21 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 12-Jan-21 A | 20-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S173800 | Fabricate final blocks sector 21 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 12-Jan-21 A | 20-Jan-21 A | 100% | 0 |  |  | 0 | 0 | 0
S173900 | Fabricate final blocks sector 22 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 21-Jan-21 A | 08-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S173900 | Fabricate final blocks sector 22 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 21-Jan-21 A | 08-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S173900 | Fabricate final blocks sector 22 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 21-Jan-21 A | 08-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174000 | Fabricate final blocks sector 23 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 09-Feb-21 A | 17-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174000 | Fabricate final blocks sector 23 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 09-Feb-21 A | 17-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174000 | Fabricate final blocks sector 23 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 09-Feb-21 A | 17-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174100 | Fabricate final blocks sector 24 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2585 | 18-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174100 | Fabricate final blocks sector 24 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1298 | 18-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174100 | Fabricate final blocks sector 24 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1128 | 18-Feb-21 A | 22-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174200 | Fabricate final blocks sector 25 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2611 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174200 | Fabricate final blocks sector 25 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1311 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174200 | Fabricate final blocks sector 25 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1140 | 23-Feb-21 A | 26-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174300 | Fabricate final blocks sector 26 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 26-Feb-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174300 | Fabricate final blocks sector 26 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 26-Feb-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174300 | Fabricate final blocks sector 26 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 26-Feb-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174400 | Fabricate final blocks sector 27 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 16-Mar-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174400 | Fabricate final blocks sector 27 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 16-Mar-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174400 | Fabricate final blocks sector 27 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 16-Mar-21 A | 29-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174500 | Fabricate final blocks sector 28 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 18-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174500 | Fabricate final blocks sector 28 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 18-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174500 | Fabricate final blocks sector 28 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 18-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174600 | Fabricate final blocks sector 29 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 26-Mar-21 A | 02-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174600 | Fabricate final blocks sector 29 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 26-Mar-21 A | 02-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174600 | Fabricate final blocks sector 29 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 26-Mar-21 A | 02-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174700 | Fabricate final blocks sector 30 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 05-Apr-21 A | 12-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174700 | Fabricate final blocks sector 30 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 05-Apr-21 A | 12-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174700 | Fabricate final blocks sector 30 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 05-Apr-21 A | 12-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174800 | Fabricate final blocks sector 31 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 13-Apr-21 A | 20-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174800 | Fabricate final blocks sector 31 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 13-Apr-21 A | 20-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174800 | Fabricate final blocks sector 31 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 13-Apr-21 A | 20-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174900 | Fabricate final blocks sector 32 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 21-Apr-21 A | 28-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174900 | Fabricate final blocks sector 32 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 21-Apr-21 A | 28-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S174900 | Fabricate final blocks sector 32 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 21-Apr-21 A | 28-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175000 | Fabricate final blocks sector 33 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 29-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175000 | Fabricate final blocks sector 33 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 29-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175000 | Fabricate final blocks sector 33 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 29-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175100 | Fabricate final blocks sector 34 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 29-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175100 | Fabricate final blocks sector 34 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 29-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175100 | Fabricate final blocks sector 34 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 29-Apr-21 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175200 | Fabricate final blocks sector 35 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 30-Apr-21 A | 07-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175200 | Fabricate final blocks sector 35 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 30-Apr-21 A | 07-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175200 | Fabricate final blocks sector 35 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 30-Apr-21 A | 07-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175300 | Fabricate final blocks sector 36 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 10-May-21 A | 17-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175300 | Fabricate final blocks sector 36 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 10-May-21 A | 17-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175300 | Fabricate final blocks sector 36 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 10-May-21 A | 17-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175400 | Fabricate final blocks sector 37 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 18-May-21 A | 25-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175400 | Fabricate final blocks sector 37 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 18-May-21 A | 25-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175400 | Fabricate final blocks sector 37 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 18-May-21 A | 25-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175500 | Fabricate final blocks sector 38 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 26-May-21 A | 03-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175500 | Fabricate final blocks sector 38 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 26-May-21 A | 03-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175500 | Fabricate final blocks sector 38 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 26-May-21 A | 03-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175600 | Fabricate final blocks sector 39 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 04-Jun-21 A | 11-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175600 | Fabricate final blocks sector 39 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 04-Jun-21 A | 11-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175600 | Fabricate final blocks sector 39 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 04-Jun-21 A | 11-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175700 | Fabricate final blocks sector 40 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 14-Jun-21 A | 21-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175700 | Fabricate final blocks sector 40 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 14-Jun-21 A | 21-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175700 | Fabricate final blocks sector 40 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 14-Jun-21 A | 21-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175800 | Fabricate final blocks sector 41 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 22-Jun-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175800 | Fabricate final blocks sector 41 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 22-Jun-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175800 | Fabricate final blocks sector 41 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 22-Jun-21 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S175900 | Fabricate final blocks sector 42 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 30-Jun-21 A | 2021-07-08 | 88% | 6 |  |  | 319.56 | 319.56 | 0
S175900 | Fabricate final blocks sector 42 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 30-Jun-21 A | 2021-07-08 | 88% | 9 |  |  | 160.44 | 160.44 | 0
S175900 | Fabricate final blocks sector 42 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 30-Jun-21 A | 2021-07-08 | 88% | 1.2 |  |  | 139.44 | 139.44 | 0
S176000 | Fabricate final blocks sector 43 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-07-09 | 2021-07-16 | 0% | 50 |  |  | 2663 | 2663 | 0
S176000 | Fabricate final blocks sector 43 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-07-09 | 2021-07-16 | 0% | 75 |  |  | 1337 | 1337 | 0
S176000 | Fabricate final blocks sector 43 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-07-09 | 2021-07-16 | 0% | 10 |  |  | 1162 | 1162 | 0
S176100 | Fabricate final blocks sector 44 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-07-19 | 2021-07-26 | 0% | 50 |  |  | 2663 | 2663 | 0
S176100 | Fabricate final blocks sector 44 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-07-19 | 2021-07-26 | 0% | 75 |  |  | 1337 | 1337 | 0
S176100 | Fabricate final blocks sector 44 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-07-19 | 2021-07-26 | 0% | 10 |  |  | 1162 | 1162 | 0
S176200 | Fabricate final blocks sector 45 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-07-27 | 2021-08-03 | 0% | 50 |  |  | 2663 | 2663 | 0
S176200 | Fabricate final blocks sector 45 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-07-27 | 2021-08-03 | 0% | 75 |  |  | 1337 | 1337 | 0
S176200 | Fabricate final blocks sector 45 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-07-27 | 2021-08-03 | 0% | 10 |  |  | 1162 | 1162 | 0
S176300 | Fabricate final blocks sector 46 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-08-04 | 2021-08-11 | 0% | 50 |  |  | 2663 | 2663 | 0
S176300 | Fabricate final blocks sector 46 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-08-04 | 2021-08-11 | 0% | 75 |  |  | 1337 | 1337 | 0
S176300 | Fabricate final blocks sector 46 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-08-04 | 2021-08-11 | 0% | 10 |  |  | 1162 | 1162 | 0
S176400 | Fabricate final blocks sector 47 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-08-12 | 2021-08-19 | 0% | 50 |  |  | 2663 | 2663 | 0
S176400 | Fabricate final blocks sector 47 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-08-12 | 2021-08-19 | 0% | 75 |  |  | 1337 | 1337 | 0
S176400 | Fabricate final blocks sector 47 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-08-12 | 2021-08-19 | 0% | 10 |  |  | 1162 | 1162 | 0
S176500 | Fabricate final blocks sector 48 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-08-20 | 2021-08-27 | 0% | 50 |  |  | 2663 | 2663 | 0
S176500 | Fabricate final blocks sector 48 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-08-20 | 2021-08-27 | 0% | 75 |  |  | 1337 | 1337 | 0
S176500 | Fabricate final blocks sector 48 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-08-20 | 2021-08-27 | 0% | 10 |  |  | 1162 | 1162 | 0
S176600 | Fabricate final blocks sector 49 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-08-30 | 2021-09-07 | 0% | 50 |  |  | 2663 | 2663 | 0
S176600 | Fabricate final blocks sector 49 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-08-30 | 2021-09-07 | 0% | 75 |  |  | 1337 | 1337 | 0
S176600 | Fabricate final blocks sector 49 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-08-30 | 2021-09-07 | 0% | 10 |  |  | 1162 | 1162 | 0
S176700 | Fabricate final blocks sector 50 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-09-08 | 2021-09-15 | 0% | 50 |  |  | 2663 | 2663 | 0
S176700 | Fabricate final blocks sector 50 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-09-08 | 2021-09-15 | 0% | 75 |  |  | 1337 | 1337 | 0
S176700 | Fabricate final blocks sector 50 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-09-08 | 2021-09-15 | 0% | 10 |  |  | 1162 | 1162 | 0
S176800 | Fabricate final blocks sector 51 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-09-16 | 2021-09-23 | 0% | 50 |  |  | 2663 | 2663 | 0
S176800 | Fabricate final blocks sector 51 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-09-16 | 2021-09-23 | 0% | 75 |  |  | 1337 | 1337 | 0
S176800 | Fabricate final blocks sector 51 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-09-16 | 2021-09-23 | 0% | 10 |  |  | 1162 | 1162 | 0
S176900 | Fabricate final blocks sector 52 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-09-24 | 2021-10-01 | 0% | 50 |  |  | 2663 | 2663 | 0
S176900 | Fabricate final blocks sector 52 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-09-24 | 2021-10-01 | 0% | 75 |  |  | 1337 | 1337 | 0
S176900 | Fabricate final blocks sector 52 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-09-24 | 2021-10-01 | 0% | 10 |  |  | 1162 | 1162 | 0
S177000 | Fabricate final blocks sector 53 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-10-04 | 2021-10-12 | 0% | 50 |  |  | 2663 | 2663 | 0
S177000 | Fabricate final blocks sector 53 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-10-04 | 2021-10-12 | 0% | 75 |  |  | 1337 | 1337 | 0
S177000 | Fabricate final blocks sector 53 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-10-04 | 2021-10-12 | 0% | 10 |  |  | 1162 | 1162 | 0
S177100 | Fabricate final blocks sector 54 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-10-13 | 2021-10-20 | 0% | 50 |  |  | 2663 | 2663 | 0
S177100 | Fabricate final blocks sector 54 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-10-13 | 2021-10-20 | 0% | 75 |  |  | 1337 | 1337 | 0
S177100 | Fabricate final blocks sector 54 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-10-13 | 2021-10-20 | 0% | 10 |  |  | 1162 | 1162 | 0
S177200 | Fabricate final blocks sector 55 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-10-21 | 2021-10-28 | 0% | 50 |  |  | 2663 | 2663 | 0
S177200 | Fabricate final blocks sector 55 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-10-21 | 2021-10-28 | 0% | 75 |  |  | 1337 | 1337 | 0
S177200 | Fabricate final blocks sector 55 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-10-21 | 2021-10-28 | 0% | 10 |  |  | 1162 | 1162 | 0
S177300 | Fabricate final blocks sector 56 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-10-29 | 2021-11-04 | 0% | 50 |  |  | 2663 | 2663 | 0
S177300 | Fabricate final blocks sector 56 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-10-29 | 2021-11-04 | 0% | 75 |  |  | 1337 | 1337 | 0
S177300 | Fabricate final blocks sector 56 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-10-29 | 2021-11-04 | 0% | 10 |  |  | 1162 | 1162 | 0
S177400 | Fabricate final blocks sector 57 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-11-05 | 2021-11-12 | 0% | 50 |  |  | 2663 | 2663 | 0
S177400 | Fabricate final blocks sector 57 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-11-05 | 2021-11-12 | 0% | 75 |  |  | 1337 | 1337 | 0
S177400 | Fabricate final blocks sector 57 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-11-05 | 2021-11-12 | 0% | 10 |  |  | 1162 | 1162 | 0
S177500 | Fabricate final blocks sector 58 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-11-15 | 2021-11-19 | 0% | 50 |  |  | 2663 | 2663 | 0
S177500 | Fabricate final blocks sector 58 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-11-15 | 2021-11-19 | 0% | 75 |  |  | 1337 | 1337 | 0
S177500 | Fabricate final blocks sector 58 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-11-15 | 2021-11-19 | 0% | 10 |  |  | 1162 | 1162 | 0
S177600 | Fabricate final blocks sector 59 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-11-22 | 2021-11-30 | 0% | 50 |  |  | 2663 | 2663 | 0
S177600 | Fabricate final blocks sector 59 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-11-22 | 2021-11-30 | 0% | 75 |  |  | 1337 | 1337 | 0
S177600 | Fabricate final blocks sector 59 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-11-22 | 2021-11-30 | 0% | 10 |  |  | 1162 | 1162 | 0
S177700 | Fabricate final blocks sector 60 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-12-01 | 2021-12-07 | 0% | 50 |  |  | 2663 | 2663 | 0
S177700 | Fabricate final blocks sector 60 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-12-01 | 2021-12-07 | 0% | 75 |  |  | 1337 | 1337 | 0
S177700 | Fabricate final blocks sector 60 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-12-01 | 2021-12-07 | 0% | 10 |  |  | 1162 | 1162 | 0
S177800 | Fabricate final blocks sector 61 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-12-08 | 2021-12-14 | 0% | 50 |  |  | 2663 | 2663 | 0
S177800 | Fabricate final blocks sector 61 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-12-08 | 2021-12-14 | 0% | 75 |  |  | 1337 | 1337 | 0
S177800 | Fabricate final blocks sector 61 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-12-08 | 2021-12-14 | 0% | 10 |  |  | 1162 | 1162 | 0
S177900 | Fabricate final blocks sector 62 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-12-15 | 2021-12-21 | 0% | 50 |  |  | 2663 | 2663 | 0
S177900 | Fabricate final blocks sector 62 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-12-15 | 2021-12-21 | 0% | 75 |  |  | 1337 | 1337 | 0
S177900 | Fabricate final blocks sector 62 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-12-15 | 2021-12-21 | 0% | 10 |  |  | 1162 | 1162 | 0
S178000 | Fabricate final blocks sector 63 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-12-22 | 2021-12-29 | 0% | 50 |  |  | 2663 | 2663 | 0
S178000 | Fabricate final blocks sector 63 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-12-22 | 2021-12-29 | 0% | 75 |  |  | 1337 | 1337 | 0
S178000 | Fabricate final blocks sector 63 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-12-22 | 2021-12-29 | 0% | 10 |  |  | 1162 | 1162 | 0
S178100 | Fabricate final blocks sector 64 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 50 | 2663 | 2021-12-30 | 2022-01-06 | 0% | 50 |  |  | 2663 | 2663 | 0
S178100 | Fabricate final blocks sector 64 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 75 | 1337 | 2021-12-30 | 2022-01-06 | 0% | 75 |  |  | 1337 | 1337 | 0
S178100 | Fabricate final blocks sector 64 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 10 | 1162 | 2021-12-30 | 2022-01-06 | 0% | 10 |  |  | 1162 | 1162 | 0
1.03.01.03.03 Pack and ship final blocks to BNL
S178300 | Pack and ship final blocks for sectors 13-16 to BNL - Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 139 | 22-Oct-20 A | 23-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S178300 | Pack and ship final blocks for sectors 13-16 to BNL - Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 5 | 259 | 22-Oct-20 A | 23-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S178300 | Pack and ship final blocks for sectors 13-16 to BNL - Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 7 | 790 | 22-Oct-20 A | 23-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S178400 | Pack and ship final blocks for sectors 17-24 to BNL - Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 | 279 | 16-Nov-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178400 | Pack and ship final blocks for sectors 17-24 to BNL - Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 | 520 | 16-Nov-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178400 | Pack and ship final blocks for sectors 17-24 to BNL - Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 | 1703 | 16-Nov-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178500 | Pack and ship final blocks for sectors 25-32 to BNL - Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 | 285 | 22-Mar-21 A | 07-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178500 | Pack and ship final blocks for sectors 25-32 to BNL - Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 | 533 | 22-Mar-21 A | 07-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178500 | Pack and ship final blocks for sectors 25-32 to BNL - Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 | 1743 | 22-Mar-21 A | 07-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178600 | Pack and ship final blocks for sectors 33-40 to BNL - Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 | 285 | 17-May-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178600 | Pack and ship final blocks for sectors 33-40 to BNL - Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 | 533 | 17-May-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178600 | Pack and ship final blocks for sectors 33-40 to BNL - Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 | 1743 | 17-May-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 | 285 | 15-Jun-21 A | 2021-09-03 | 5% | 15.2 |  |  | 270.75 | 270.75 | 0
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 | 533 | 15-Jun-21 A | 2021-09-03 | 5% | 9.5 |  |  | 506.35 | 506.35 | 0
S178700 | Pack and ship final blocks for sectors 40-48 to BNL - Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 | 1743 | 15-Jun-21 A | 2021-09-03 | 5% | 14.25 |  |  | 1655.85 | 1655.85 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 | 285 | 2021-11-05 | 2021-11-12 | 0% | 16 |  |  | 285 | 285 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 | 533 | 2021-11-05 | 2021-11-12 | 0% | 10 |  |  | 533 | 533 | 0
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 | 1743 | 2021-11-05 | 2021-11-12 | 0% | 15 |  |  | 1743 | 1743 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 16 | 285 | 2022-01-07 | 2022-01-07 | 0% | 16 |  |  | 285 | 285 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 10 | 533 | 2022-01-07 | 2022-01-07 | 0% | 10 |  |  | 533 | 533 | 0
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 15 | 1743 | 2022-01-07 | 2022-01-07 | 0% | 15 |  |  | 1743 | 1743 | 0
S178310 | Pack and ship final blocks for sectors 13-16 to BNL - M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 3240 | 3687 | 22-Oct-20 A | 23-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S178410 | Pack and ship final blocks for sectors 17-24 to BNL - M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 | 7403 | 16-Nov-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178510 | Pack and ship final blocks for sectors 25-32 to BNL - M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 | 7521 | 22-Mar-21 A | 07-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178610 | Pack and ship final blocks for sectors 33-40 to BNL - M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 | 7521 | 17-May-21 A | 28-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S178710 | Pack and ship final blocks for sectors 40-48 to BNL - M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 | 7521 | 15-Jun-21 A | 2021-09-03 | 5% | 6156 |  |  | 7144.95 | 7144.95 | 0
S178910 | Pack and ship final blocks for sectors 49-56 to BNL - M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 | 7521 | 2021-11-05 | 2021-11-12 | 0% | 6480 |  |  | 7521 | 7521 | 0
S176010 | Pack and ship final blocks for sectors 57-64 to BNL - M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 6480 | 7521 | 2022-01-07 | 2022-01-07 | 0% | 6480 |  |  | 7521 | 7521 | 0
1.03.02 EMCAL Module Fabrication and Sector Assembly
1.03.02.02 EMCAL Module Fabrication
1.03.02.02.03 EMCAL Final Module Fabrication
S187100 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 52680 | 61145 | 15-Oct-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S187700 | Install light guides on final blocks M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1650 | 1912 | 21-Jan-21 A | 2022-01-31 | 35% | 1072.5 |  |  | 1242.8 | 1242.8 | 0
S188100 | Install SiPMs daughterboards on final blocks M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 300 | 348 | 22-Jan-21 A | 2022-02-03 | 35% | 195 |  |  | 226.2 | 226.2 | 0
S187400 | Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 215244 | 240129 | 22-Dec-20 A | 2021-07-30 | 74% | 55963.44 |  |  | 62433.54 | 62433.54 | 0
1.03.02.03 EMCAL Sector Assembly
1.03.02.03.02 EMCAL Preproduction Sector Assembly and Testing
S192810 | Procure mechanical parts for Prepro Sectors 1-12, Phase 2 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 36798 | 41873 | 10-Oct-19 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02.03.03 EMCAL Final Production Sector Assembly
S195400 | Procure EMCAL Mechanical Parts for Final Sectors - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 251357 | 291746 | 14-Sep-20 A | 14-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S196100 | Procure EMCAL Cooling System for Final Sectors - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 70893 | 82284 | 18-Jan-21 A | 2021-07-14 | 42% | 41117.94 |  |  | 47724.72 | 47724.72 | 0
S196910 | Technical support labor for EMCal assembly | TECH1.TECH1 | 3520 | 281000 | 04-Jan-21 A | 2022-01-12 | 50% | 1760 |  |  | 140500 | 140500 | 0
1.04 HCal
S1001919 | Actuals - Nonlabor - sPHENIX HCal FY19M8 | Actual NonLabor.Actual Nonlabor | 16812 | 18548 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.02 Outer HCAL Sector Mechanical Structure
S205100 | Procure Outer HCAL Splice Plates - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 266560 | 303325 | 22-Feb-21 A | 26-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S206200 | Procure Outer HCAL Lifting Fixtures & Supports - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 40000 | 45517 | 14-Nov-19 A | 23-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.01 Inner HCAL Support Structure & Support Rings
S199300 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 1 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 | 264958 | 28-Jun-21 A | 30-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S200000 | Manufacture Inner HCAL Support Rings - Delivery Acceptance | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 127182 | 141886 | 17-May-21 A | 20-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S199310 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 2 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 | 264958 | 16-Aug-21* | 2021-08-20 | 0% | 237500 |  |  | 264958 | 264958 | 0
S199320 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 3 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 | 264958 | 24-Sep-21* | 2021-09-30 | 0% | 237500 |  |  | 264958 | 264958 | 0
S199330 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 4 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 237500 | 264958 | 15-Nov-21* | 2021-11-19 | 0% | 237500 |  |  | 264958 | 264958 | 0
1.04.03 Outer HCAL Procure Scintillating Tiles
S208400 | Outer HCAL Scintillating Tile Acceptance Testing | STUDENT GSU OnC- PS1.STUDENT GSU OnC - Purchased Services | 650 | 11583 | 15-Jun-20 A | 22-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208300 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 1 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 143106 | 159651 | 25-Sep-19 A | 04-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S208312 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 11&12 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 211458 | 235905 | 17-Aug-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208302 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 2 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 113203 | 126291 | 12-Nov-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S208303 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 3 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 113203 | 126291 | 20-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208304 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 4 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 113203 | 126291 | 20-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208306 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 5&6 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 226406 | 252582 | 15-Jun-20 A | 22-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208308 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 7&8 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 226406 | 252582 | 23-Jun-20 A | 30-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208310 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 9&10 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 211458 | 235905 | 23-Jun-20 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S208220 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 0 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 185242 | 204371 | 18-Sep-19 A | 24-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.04 Outer HCAL Sector Assembly and Testing
1.04.04.02 Outer HCAL Sector Assembly and Testing - Production
S209800 | Populate Outer HCAL sectors with scintillating tiles | STUDENT GSU OffC- PS-2.STUDENT GSU OffC - Purchased Services | 1040 | 15509 | 17-Aug-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S209900 | Populate Outer HCAL sectors with electronics | STUDENT GSU OffC- PS-2.STUDENT GSU OffC - Purchased Services | 1040 | 15509 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210000 | Outer HCAL Sector LED testing and Light Tighting | STUDENT GSU OffC- PS-2.STUDENT GSU OffC - Purchased Services | 1040 | 15509 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210200 | Outer HCAL Cosmics testing and initial calibration | STUDENT GSU OffC- PS-2.STUDENT GSU OffC - Purchased Services | 1040 | 15509 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S209600 | Procure Outer HCAL Assembly & Testing Equipment- Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 75000 | 87051 | 20-Jul-20 A | 30-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S210100 | Procure Outer HCAL LED Testing & Light Tighting M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 19200 | 22285 | 15-Dec-20 A | 30-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S210310 | Technical support labor for HCal | TECH1.TECH1 | 0 | 0 | 01-Mar-21 A | 31-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.05 Calorimeter Electronics
S1001959 | Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | Actual NonLabor.Actual Nonlabor | 58345 | 64370 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.01 SiPMs
S214800 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 5 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 69520 | 76699 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S214900 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 6 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 69520 | 76699 | 01-Jul-19 A | 26-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215000 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 7 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 69520 | 76699 | 16-Aug-19 A | 31-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215100 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 8 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 69520 | 76699 | 01-Oct-19 A | 03-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215200 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 9 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 69520 | 77512 | 01-Nov-19 A | 14-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215600 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 01-Jul-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215800 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 01-Jul-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215900 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 01-Aug-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S216000 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 02-Jan-20 A | 30-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216100 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216200 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S215300 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 10 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 69520 | 77557 | 16-Dec-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S215400 | EMCal/HCal sensors Production - 5K Units - Delivery Acceptance No. 13 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 43450 | 48473 | 03-Feb-20 A | 04-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216300 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216400 | Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 | STUDENT UM - PS.STUDENT UM - Purchased Services | 50 | 798 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S215310 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 11 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 69520 | 77557 | 02-Jan-20 A | 16-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S215320 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 12 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 69520 | 77557 | 03-Feb-20 A | 04-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216310 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S216320 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1277 | 03-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02 Calorimeter Front End Electronics
1.05.02.01 EMCal Electronics: Preproduction
S224000 | Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 2 - M&S | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 42880 | 47838 | 01-Apr-20 A | 07-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S226400 | Procure EMCal External Bias Power System: Sectors 1-12, Phase 2 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 30454 | 34654 | 15-Dec-20 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S224400 | Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 2 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 12320 | 14019 | 01-Oct-19 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S223001 | Fabricate EMCal Interface Board: Sectors 1-12, Phase 2 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 29435 | 33495 | 19-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S222201 | Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 2 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 78925 | 89811 | 03-Jan-20 A | 09-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223701 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 2 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 42072 | 47875 | 01-Oct-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02.02 EMCal Electronics: Production
S228100 | Test SiPM Daughter Boards Production Sectors 13-64 | STUDENT UM - PS.STUDENT UM - Purchased Services | 176 | 2888 | 01-Dec-20 A | 2021-07-20 | 60% | 70.4 |  |  | 1155.2 | 1155.2 | 0
S229400 | Test EMCal Preamp Boards: Production Sectors 13-64 | STUDENT UM - PS.STUDENT UM - Purchased Services | 384 | 6313 | 26-Feb-21 A | 2021-07-14 | 40% | 230.4 |  |  | 3787.8 | 3787.8 | 0
S231100 | Test Calorimeter Controller Boards: Production Sectors 13-64 | STUDENT UM - PS.STUDENT UM - Purchased Services | 120 | 1973 | 10-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S229300 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 473550 | 549642 | 26-Feb-21 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S230100 | Fabricate EMCAL Interface Board Sectors 13-64 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 187690 | 217849 | 26-Oct-20 A | 31-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S231800 | Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 248296 | 288193 | 31-Dec-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S232500 | Fabricate Test-pulse Boards 13 - 64 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 7050 | 8022 | 17-May-21 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S227600 | Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance Part 1 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 34668 | 38676 | 13-May-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S233200 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 177356 | 205854 | 2021-12-27 | 2022-01-03 | 0% | 177356 |  |  | 205854 | 205854 | 0
S234000 | Procure EMCal Bias Power System Sectors 13-64 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 134128 | 155680 | 22-Feb-21 A | 15-Mar-21 A | 100% | 0 |  |  | 0 | 0 | 0
S234100 | EMCal Low Voltage Power System Sectors 13-64 - M&S | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 35200 | 39270 | 31-Aug-20 A | 29-Jun-21 A | 100% | 0 |  |  | 0 | 0 | 0
S230200 | Test EMCal Interface Boards: Production Sectors 13-64 | STUDENT UM - PS.STUDENT UM - Purchased Services | 384 | 6313 | 01-Dec-20 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S234200 | EMCal Crates for Controllers - M&S | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 5332 | 5948 | 26-Oct-20 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
S231000 | Fabricate Calorimeter Production Controller Boards - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 79397 | 92155 | 10-Aug-20 A | 26-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S227605 | Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance Part 2 | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 20801 | 23206 | 01-Dec-20 A | 30-Apr-21 A | 100% | 0 |  |  | 0 | 0 | 0
S233250 | Trunk Signal Cables - EMCal | Purch 1st $2M.Material (Purchase (1st $2M) | 670160 | 777844 | 2021-07-30 | 2021-12-23 | 0% | 670160 |  |  | 777844 | 777844 | 0
1.05.02.03 HCal Electronics: Preproduction
S237800 | Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 2 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 19828 | 21876 | 03-Jun-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02.04 HCal Electronics: Production
S239100 | Fabricate HCal SiPM Boards - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 95480 | 110822 | 14-Sep-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S241700 | Fabricate HCal LED Boards - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 44067 | 50145 | 11-May-20 A | 15-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S242000 | Fabricate HCal Backplane Boards: Production - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 15416 | 17542 | 01-May-20 A | 28-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S243700 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 81327 | 94395 | 27-May-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S244400 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 87827 | 101939 | 14-Dec-20 A | 2021-08-27 | 50% | 43913.5 |  |  | 50969.5 | 50969.5 | 0
S240400 | Fabricate HCal Preamp Boards - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 41364 | 48011 | 11-Aug-20 A | 31-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S242900 | Fabricate HCal Interface Boards Production - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 29290 | 33330 | 14-Oct-20 A | 16-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S244450 | Trunk Signal Cables - OuterHCal | Purch 1st $2M.Material (Purchase (1st $2M) | 128640 | 149310 | 2021-07-30 | 2021-12-23 | 0% | 128640 |  |  | 149310 | 149310 | 0
1.05.03 Calorimeter Digitizer System
1.05.03.02 Calorimeter Digitizers: Production
S252800 | Procure Production Digitizer (Boards) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 129049 | 149785 | 2021-08-03 | 2021-08-09 | 0% | 129049 |  |  | 149785 | 149785 | 0
S252900 | Procure Production Digitizer (Assembly & Tests) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 199077 | 231066 | 2021-10-28 | 2021-11-03 | 0% | 199077 |  |  | 231066 | 231066 | 0
S252700 | Procure Production Digitizer (Parts) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 584602 | 678538 | 30-Apr-21 A | 2021-08-09 | 37% | 368299.26 |  |  | 427478.94 | 427478.94 | 0
1.06 DAQ/Trigger
1.06.01 DAQ
1.06.01.03 DAQ Production
S255900 | Procure DAQ Production Boards - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 104682 | 121503 | 2021-10-26 | 2021-11-01 | 0% | 104682 |  |  | 121503 | 121503 | 0
S256700 | Procure DAQ Production Crates - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 64000 | 74284 | 2021-11-24 | 2021-12-02 | 0% | 64000 |  |  | 74284 | 74284 | 0
S257600 | Procure DAQ Production SEBs - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 41040 | 47634 | 28-Oct-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S258400 | Procure DAQ Production ATPs - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 98048 | 113803 | 22-Oct-20 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S258700 | Procure DAQ Production jSEB Slow control computers - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 16856 | 19181 | 2021-08-02 | 2021-08-06 | 0% | 16856 |  |  | 19181 | 19181 | 0
S259500 | Procure DAQ Production Buffer Boxes - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 223540 | 259459 | 23-Nov-20 A | 2021-10-29 | 18% | 183302.8 |  |  | 212756.38 | 212756.38 | 0
S260300 | Procure DAQ Production Main Switches - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 86151 | 99994 | 21-Apr-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.02 Local Level 1 Trigger (LL1)
1.06.02.02 LL1 Trigger Prototype v1
S262500 | Procure Prototype V1 Trigger Board - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 173000 | 196861 | 11-Mar-20 A | 17-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.06.02.03 LL1 Trigger Preproduction Prototype
S263600 | Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 60000 | 69641 | 2021-08-02 | 2021-08-06 | 0% | 60000 |  |  | 69641 | 69641 | 0
1.06.02.04 LL1 Trigger Production
S264900 | Procure Production LL1 System - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 117000 | 135800 | 2021-11-04 | 2021-11-10 | 0% | 117000 |  |  | 135800 | 135800 | 0
1.06.03 Global Level 1 Trigger (GL1)
1.06.03.03 GL1 Trigger Production
S267600 | Procure Production GL1 Components - final hardware - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 28150 | 32673 | 2021-09-14 | 2021-09-20 | 0% | 28150 |  |  | 32673 | 32673 | 0
1.06.04 Timing System
1.06.04.03 Timing System Production
S270300 | Timing System Production (FPGA Boards) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 41600 | 48284 | 2021-10-27 | 2021-11-02 | 0% | 41600 |  |  | 48284 | 48284 | 0
1.07 Min Bias Trigger Detector
S273500 | Procure Min/Bias Electronics (sPHENIX Production Digitizers) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 14770 | 17143 | 2021-12-03 | 2021-12-09 | 0% | 14770 |  |  | 17143 | 17143 | 0
S273600 | Procure MBD Shaper/Disc Board 128 Channels - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 46420 | 53879 | 2021-12-03 | 2021-12-09 | 0% | 46420 |  |  | 53879 | 53879 | 0
A-OPC OPC
POM02B-PCR026 POM02 sPHENIX WBS 1.x, 2.x Baseline PCR026 Approved
1 MIE Project
1.01 Project Management
S102400 | Actuals - Labor - A - MIE - sPHENIX Project Management FY18 | Actual Labor.Actual Labor | 1694 | 283044 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S102500 | Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY18 | Actual NonLabor.Actual Nonlabor | 547599 | 610909 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S102300 | Actuals - Labor - A - MIE - sPHENIX Project Management FY17 | Actual Labor.Actual Labor | 641 | 107107 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S102605 | Actuals - Labor - A - MIE - sPHENIX Project Management FY19M8 | Actual Labor.Actual Labor | 69 | 11566 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
S102606 | Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | Actual NonLabor.Actual Nonlabor | 298116 | 328902 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.01.02 Labor by FY
S102905 | Mgmt labor - A - MIE, Phase 1 - FY19 split | PM Spec - PS.Project Mgmt Specialist - Purchased Services | 464 | 71048 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.01.03 Management Travel
S104010 | Travel FY19 Split | Travel.Travel Cost | 6720 | 8838 | 03-Jun-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02 TPC
S104600 | Actuals - Nonlabor - sPHENIX TPC FY17 | Actual NonLabor.Actual Nonlabor | 18789 | 20961 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S104700 | Actuals - Nonlabor - sPHENIX TPC FY18 | Actual NonLabor.Actual Nonlabor | 0 | 0 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S104710 | Actuals - Nonlabor - sPHENIX TPC FY18 | Actual NonLabor.Actual Nonlabor | 246200 | 274664 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1000759 | Actuals - NonLabor - sPHENIX TPC FY19M8 | Actual NonLabor.Actual Nonlabor | 390830 | 431189 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01 TPC Mechanics
1.02.01.01 TPC v1 Field Cage Prototype
S107905 | Procure TPC v1 Central Membrane Parts M&S FY19 Split | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 2400 | 2648 | 03-Sep-19 A | 31-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.02 TPC v2 Field Cage
S109400 | Procure TPC v2 Mandrel Parts M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 10433 | 11872 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S110300 | Procure TPC v2 Outer Field Cage Parts - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 75827 | 86285 | 13-Jan-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111200 | Procure TPC v2 Inner Field Cage Parts - Delivery Acceptance | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 34559 | 39326 | 14-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111500 | Procure TPC Field Cage Prototype v2 End Rings | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 20000 | 22759 | 01-Apr-20 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S111800 | Procure TPC v2 Central Membrane Parts M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 8000 | 9103 | 10-Oct-19 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.05 TPC v2 Modules
1.02.01.05.02 TPC v2 Module Common Mechanics
S117100 | Procure TPC v2 Module Strongback M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 1200 | 1366 | 18-Feb-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117400 | Procure TPC v2 Module Frames M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 1000 | 1138 | 04-Feb-20 A | 24-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S117700 | Procure TPC v2 Module Grid Parts M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 500 | 569 | 14-Jan-20 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.01.05.03 TPC v2a Module Prototype
S118100 | Procure TPC v2a Module Padplane M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 3700 | 4210 | 26-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S118400 | Procure TPC v2a Module GEMs M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 6500 | 7397 | 26-Mar-20 A | 31-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.02 TPC R1 Modules
1.02.02.01 TPC R1 Module Factory Preparation
S122202 | Prepare TPC R1 Factory Tooling Labor Split | PROF3 Wayne - PS.PROF3 Wayne - Purchased Services | 3 | 295 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S122302 | Prepare TPC R1 Factory Tooling M&S Split | Wayne Contracted Purchase.Wayne Contracted Purchase <$2M M&S | 2400 | 2648 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.02.02 TPC R1 Pre-Production Module
S123600 | Test TPC R1 Pre-Production Module | PROF3 Wayne - PS.PROF3 Wayne - Purchased Services | 80 | 7868 | 01-Jul-19 A | 09-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S123700 | Common production line & QA certification | Wayne Contracted Purchase.Wayne Contracted Purchase <$2M M&S | 95000 | 106168 | 25-Jul-19 A | 31-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.03 TPC R2 Modules
1.02.03.01 TPC R2 Module Factory Preparation
S126502 | Prepare TPC R2 Factory Tooling M&S Split | Vanderbilt Contracted Purchase.Vanderbilt Contracted Purchase <$2M M&S | 3600 | 3972 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.03.02 TPC R2 Pre-Production Module
S127602 | Procure TPC R2 Pre-Production Module GEMs M&S Split | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 2500 | 2758 | 01-Aug-19 A | 20-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.04 TPC R3 Modules
1.02.04.01 TPC R3 Module Factory Preparation
S130102 | Prepare TPC R3a Factory Tooling M&S Split | Weizmann Contracted Purchase.Weizmann Contracted Purchase <$2M M&S | 3600 | 3972 | 01-Jul-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S130502 | Prepare TPC R3b Factory Tooling M&S Split | Temple Contracted Purchase.Temple Contracted Purchase <$2M M&S | 3600 | 3972 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.04.02 TPC R3 Pre-Production Module
S131000 | Procure TPC R3 Pre-Production Module frames - M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 2000 | 2207 | 01-Aug-19 A | 29-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S131600 | Procure TPC R3 Pre-Production Module GEMs M&S | SBU Contracted Purchase.SBU Contracted Purchase <$2M M&S | 10000 | 11033 | 01-Aug-19 A | 29-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.05 TPC FEE
1.02.05.02 TPC FEE Prototype v2 (Pre-Production)
S137000 | v2 Procure TPC FEE preproducion prototype components M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 5871 | 6681 | 01-Apr-20 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137200 | v2 Fabricate TPC FEE preproduction prototype boards M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 1476 | 1680 | 01-Apr-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137400 | v2 Modify TPC FEE Test Stand M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 8000 | 9103 | 02-Dec-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S137600 | v2 Assemble and test TPC FEE preproduction prototype M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 5630 | 6407 | 13-Apr-20 A | 23-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.05.03 SAMPA chip 80 nsec
S139720 | Procure second phase of SAMPA development - Delivery of First Chip Layout | Purch 1st $2M.Material (Purchase (1st $2M) | 35000 | 38614 | 02-Jul-19 A | 16-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S139725 | Procure second phase of SAMPA development - Delivery of Final Review of test results | Purch 1st $2M.Material (Purchase (1st $2M) | 70000 | 77229 | 17-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S139730 | Procure second phase of SAMPA development - Delivery of Eng Design Review | Purch 1st $2M.Material (Purchase (1st $2M) | 47500 | 52405 | 01-Aug-19 A | 28-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S139735 | Procure second phase of SAMPA development - Delivery of Eng Run Preparation | Purch 1st $2M.Material (Purchase (1st $2M) | 20000 | 22100 | 29-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.02.06 TPC DAM
1.02.06.02 TPC DAM Evaluation -- FELIX 2.0
S146300 | Miscellaneous Parts for TPC DAM FPGA Algorithm Development - Round 1 | Purch 1st $2M.Material (Purchase (1st $2M) | 2563 | 2828 | 01-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S145700 | Procure TPC DAM Felix 2.0 Boards Throughput - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 73524 | 81116 | 01-Aug-19 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S145750 | Procure Full Set of Data Fibers for Design Validation - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 2876 | 3173 | 01-Aug-19 A | 14-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03 EMCal
S156400 | Actuals - Nonlabor - sPHENIX EMCal FY17 | Actual NonLabor.Actual Nonlabor | 40977 | 45714 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S156500 | Actuals - Nonlabor - sPHENIX EMCal FY18 | Actual NonLabor.Actual Nonlabor | 415271 | 463282 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S156510 | Actuals - Nonlabor - sPHENIX EMCal FY19M8 | Actual NonLabor.Actual Nonlabor | 634129 | 699612 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.01 EMCAL Block Fabrication
1.03.01.02 EMCAL Preproduction Prototype Block Production
1.03.01.02.04 Order Material for EMCal Block Preproduction
S161700 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Delivery acceptance Phase 2 of 2 Phases (Sectors 4-12) | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 219420 | 242078 | 03-Sep-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S164702 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Delivery acceptance Split | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 33239 | 36671 | 01-Jul-19 A | 30-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S165802 | Prepare fiber assemblies for EMCal Prepro Sectors 1-12 Blocks Split | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 0 | 0 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S165802 | Prepare fiber assemblies for EMCal Prepro Sectors 1-12 Blocks Split | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 662 | 11004 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S165802 | Prepare fiber assemblies for EMCal Prepro Sectors 1-12 Blocks Split | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 0 | 0 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.01.02.05 Fabricate EMCal Prepro blocks Sectors 1-12
S166000 | Fabricate EMCAL Prepro blocks sector 2 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S166000 | Fabricate EMCAL Prepro blocks sector 2 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S166000 | Fabricate EMCAL Prepro blocks sector 2 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 01-Oct-19 A | 31-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S166100 | Fabricate EMCAL Prepro blocks sector 3 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 19-Dec-19 A | 31-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166100 | Fabricate EMCAL Prepro blocks sector 3 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 19-Dec-19 A | 31-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166100 | Fabricate EMCAL Prepro blocks sector 3 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 19-Dec-19 A | 31-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166200 | Fabricate EMCAL Prepro blocks sector 4 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 03-Feb-20 A | 04-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166200 | Fabricate EMCAL Prepro blocks sector 4 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 03-Feb-20 A | 04-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166200 | Fabricate EMCAL Prepro blocks sector 4 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 03-Feb-20 A | 04-Mar-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166300 | Fabricate EMCAL Prepro blocks sector 5 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 05-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166300 | Fabricate EMCAL Prepro blocks sector 5 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 05-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166300 | Fabricate EMCAL Prepro blocks sector 5 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 05-Mar-20 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166400 | Fabricate EMCAL Prepro blocks sector 6 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 06-May-20 A | 17-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166400 | Fabricate EMCAL Prepro blocks sector 6 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 06-May-20 A | 17-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166400 | Fabricate EMCAL Prepro blocks sector 6 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 06-May-20 A | 17-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166500 | Fabricate EMCAL Prepro blocks sector 7 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 01-Jul-20 A | 15-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166500 | Fabricate EMCAL Prepro blocks sector 7 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 01-Jul-20 A | 15-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166500 | Fabricate EMCAL Prepro blocks sector 7 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 01-Jul-20 A | 15-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166600 | Fabricate EMCAL Prepro blocks sector 8 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 16-Jul-20 A | 29-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166600 | Fabricate EMCAL Prepro blocks sector 8 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 16-Jul-20 A | 29-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166600 | Fabricate EMCAL Prepro blocks sector 8 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 16-Jul-20 A | 29-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166700 | Fabricate EMCAL Prepro blocks sector 9 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 30-Jul-20 A | 14-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166700 | Fabricate EMCAL Prepro blocks sector 9 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 30-Jul-20 A | 14-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166700 | Fabricate EMCAL Prepro blocks sector 9 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 30-Jul-20 A | 14-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166800 | Fabricate EMCAL Prepro blocks sector 10 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 17-Aug-20 A | 11-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166800 | Fabricate EMCAL Prepro blocks sector 10 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 17-Aug-20 A | 11-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166800 | Fabricate EMCAL Prepro blocks sector 10 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 17-Aug-20 A | 11-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166900 | Fabricate EMCAL Prepro blocks sector 11 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 14-Sep-20 A | 25-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166900 | Fabricate EMCAL Prepro blocks sector 11 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 14-Sep-20 A | 25-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S166900 | Fabricate EMCAL Prepro blocks sector 11 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 14-Sep-20 A | 25-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167000 | Fabricate EMCAL Prepro blocks sector 12 | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 143 | 7384 | 28-Sep-20 A | 09-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167000 | Fabricate EMCAL Prepro blocks sector 12 | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 8 | 145 | 28-Sep-20 A | 09-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167000 | Fabricate EMCAL Prepro blocks sector 12 | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 17 | 1896 | 28-Sep-20 A | 09-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S165902 | Fabricate EMCAL Prepro blocks sector 1 Split | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 107 | 5533 | 01-Jul-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S165902 | Fabricate EMCAL Prepro blocks sector 1 Split | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 6 | 104 | 01-Jul-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
S165902 | Fabricate EMCAL Prepro blocks sector 1 Split | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 13 | 1467 | 01-Jul-19 A | 30-Sep-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.01.02.06 Pack and ship EMCal Blocks for Prepro Sectors 1-12 to BNL
S168900 | Pack and ship EMCAL blocks for Prepro sector 10 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 14-Sep-20 A | 18-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168900 | Pack and ship EMCAL blocks for Prepro sector 10 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 14-Sep-20 A | 18-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168900 | Pack and ship EMCAL blocks for Prepro sector 10 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 14-Sep-20 A | 18-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168700 | Pack and ship EMCAL blocks for Prepro sector 9 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 01-Sep-20 A | 08-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168700 | Pack and ship EMCAL blocks for Prepro sector 9 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 01-Sep-20 A | 08-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168700 | Pack and ship EMCAL blocks for Prepro sector 9 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 01-Sep-20 A | 08-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169100 | Pack and ship EMCAL blocks for Prepro sector 11 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 01-Oct-20 A | 07-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169100 | Pack and ship EMCAL blocks for Prepro sector 11 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 01-Oct-20 A | 07-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169100 | Pack and ship EMCAL blocks for Prepro sector 11 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 01-Oct-20 A | 07-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169300 | Pack and ship EMCAL blocks for Prepro sector 12 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 13-Oct-20 A | 19-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169300 | Pack and ship EMCAL blocks for Prepro sector 12 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 13-Oct-20 A | 19-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169300 | Pack and ship EMCAL blocks for Prepro sector 12 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 13-Oct-20 A | 19-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167100 | Pack and ship EMCAL blocks for Prepro sector 1 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 01-Jul-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S167100 | Pack and ship EMCAL blocks for Prepro sector 1 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 01-Jul-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S167100 | Pack and ship EMCAL blocks for Prepro sector 1 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 01-Jul-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S167300 | Pack and ship EMCAL blocks for Prepro sector 2 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 11-Dec-19 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167300 | Pack and ship EMCAL blocks for Prepro sector 2 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 11-Dec-19 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167300 | Pack and ship EMCAL blocks for Prepro sector 2 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 11-Dec-19 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167500 | Pack and ship EMCAL blocks for Prepro sector 3 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 03-Feb-20 A | 07-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167500 | Pack and ship EMCAL blocks for Prepro sector 3 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 03-Feb-20 A | 07-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167500 | Pack and ship EMCAL blocks for Prepro sector 3 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 03-Feb-20 A | 07-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167700 | Pack and ship EMCAL blocks for Prepro sector 4 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 01-May-20 A | 07-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167700 | Pack and ship EMCAL blocks for Prepro sector 4 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 01-May-20 A | 07-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167700 | Pack and ship EMCAL blocks for Prepro sector 4 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 01-May-20 A | 07-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167900 | Pack and ship EMCAL blocks for Prepro sector 5 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 01-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167900 | Pack and ship EMCAL blocks for Prepro sector 5 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 01-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167900 | Pack and ship EMCAL blocks for Prepro sector 5 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 01-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168100 | Pack and ship EMCAL blocks for Prepro sector 6 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 01-Jul-20 A | 08-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168100 | Pack and ship EMCAL blocks for Prepro sector 6 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 01-Jul-20 A | 08-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168100 | Pack and ship EMCAL blocks for Prepro sector 6 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 01-Jul-20 A | 08-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168300 | Pack and ship EMCAL blocks for Prepro sector 7 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 16-Jul-20 A | 22-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168300 | Pack and ship EMCAL blocks for Prepro sector 7 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 16-Jul-20 A | 22-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168300 | Pack and ship EMCAL blocks for Prepro sector 7 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 16-Jul-20 A | 22-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168500 | Pack and ship EMCAL blocks for Prepro sector 8 to BNL Purchased Services | STUDENT UIUC - PS.STUDENT UIUC - Purchased Services | 12 | 208 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168500 | Pack and ship EMCAL blocks for Prepro sector 8 to BNL Purchased Services | TECH3 UIUC - PS.TECH3 UIUC - Purchased Services | 4 | 207 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168500 | Pack and ship EMCAL blocks for Prepro sector 8 to BNL Purchased Services | TECH3 Senior UIUC - PS.TECH3 Senior UIUC - Purchased Services | 4 | 451 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169200 | Pack and ship EMCAL blocks for Prepro sector 11 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 01-Oct-20 A | 07-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168800 | Pack and ship EMCAL blocks for Prepro sector 9 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 01-Sep-20 A | 08-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169000 | Pack and ship EMCAL blocks for Prepro sector 10 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 14-Sep-20 A | 18-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S169400 | Pack and ship EMCAL blocks for Prepro sector 12 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 13-Oct-20 A | 19-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167200 | Pack and ship EMCAL blocks for Prepro sector 1 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 01-Jul-19 A | 29-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S167400 | Pack and ship EMCAL blocks for Prepro sector 2 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 11-Dec-19 A | 28-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167600 | Pack and ship EMCAL blocks for Prepro sector 3 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 03-Feb-20 A | 07-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S167800 | Pack and ship EMCAL blocks for Prepro sector 4 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 01-May-20 A | 07-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168000 | Pack and ship EMCAL blocks for Prepro sector 5 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 01-Jun-20 A | 05-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168200 | Pack and ship EMCAL blocks for Prepro sector 6 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 01-Jul-20 A | 08-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168400 | Pack and ship EMCAL blocks for Prepro sector 7 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 16-Jul-20 A | 22-Jul-20 A | 100% | 0 |  |  | 0 | 0 | 0
S168600 | Pack and ship EMCAL blocks for Prepro sector 8 to BNL M&S | UIUC Contracted Purchase.UIUC Contracted Purchase <$2M M&S | 1080 | 1229 | 03-Aug-20 A | 07-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02 EMCAL Module Fabrication and Sector Assembly
1.03.02.01 Set up Module Fabrication, Sector Assembly and Test area
S180402 | Set up EMCAL Final module production and sector assembly areas M&S Split | Purch 1st $2M.Material (Purchase (1st $2M) | 10150 | 11198 | 03-Jun-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02.02 EMCAL Module Fabrication
1.03.02.02.02 EMCAL Preprod Sector 0, 1-12 Module Fabrication
S185500 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 13148 | 14961 | 16-Oct-19 A | 31-Oct-19 A | 100% | 0 |  |  | 0 | 0 | 0
S185800 | Install reflectors on blocks for modules for Prepro Sectors 1-12 M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 350 | 398 | 09-Oct-19 A | 30-Oct-20 A | 100% | 0 |  |  | 0 | 0 | 0
S184800 | Procure light guides for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 79700 | 87930 | 03-Sep-19 A | 14-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.03.02.03 EMCAL Sector Assembly
1.03.02.03.02 EMCAL Preproduction Sector Assembly and Testing
S192800 | Procure mechanical parts for Prepro Sectors 1-12, Phase 1 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 36798 | 41873 | 23-Oct-19 A | 29-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S193500 | Procure parts for cooling system for Prepro Sectors 1-12 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 19780 | 22508 | 16-Oct-19 A | 14-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S191110 | Build mechanical stand/support for preproduction prototype Sector 0 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 552 | 01-Jul-19 A | 29-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S193710 | Build mechanical stand/support for Prepro Sectors 1-12 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 500 | 569 | 13-Nov-19 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S190302 | Procure mechanical parts for preproduction prototype Sector 0 M&S FY19 Split | Purch 1st $2M.Material (Purchase (1st $2M) | 0 | 0 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.04 HCal
S197600 | Actuals - Nonlabor - sPHENIX HCal FY17 | Actual NonLabor.Actual Nonlabor | 2708 | 3021 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S197700 | Actuals - Nonlabor - sPHENIX HCal FY18 | Actual NonLabor.Actual Nonlabor | 127709 | 142473 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S197710 | Actuals - Nonlabor - sPHENIX HCal FY19M8 | Actual NonLabor.Actual Nonlabor | 415146 | 458016 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.04.04 Outer HCAL Sector Assembly and Testing
1.04.04.01 Outer HCAL Sector Assembly and Testing - Preproduction
S203100 | Populate Outer HCAL sectors with scintillating tiles (Preproduction) | STUDENT GSU OffC- PS-2.STUDENT GSU OffC - Purchased Services | 248 | 3591 | 02-Aug-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S203200 | Populate Outer HCAL sectors with electronics (Preproduction) | STUDENT GSU OffC- PS-2.STUDENT GSU OffC - Purchased Services | 248 | 3591 | 01-Aug-19 A | 30-Nov-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203300 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) Labor | STUDENT GSU OffC- PS-2.STUDENT GSU OffC - Purchased Services | 248 | 3591 | 04-Nov-19 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203400 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 4800 | 5462 | 04-Nov-19 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S203500 | Outer HCAL Cosmics testing and initial calibration (Preproduction) | STUDENT GSU OffC- PS-2.STUDENT GSU OffC - Purchased Services | 248 | 3591 | 25-Nov-19 A | 30-Dec-20 A | 100% | 0 |  |  | 0 | 0 | 0
S202512 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction) Split | STUDENT GSU OnC- PS1.STUDENT GSU OnC - Purchased Services | 125 | 2117 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S203002 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) - M&S Split | Purch 1st $2M.Material (Purchase (1st $2M) | 2000 | 2207 | 03-Jun-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05 Calorimeter Electronics
S211400 | Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY17 | Actual NonLabor.Actual Nonlabor | 29927 | 33387 | 01-Feb-17 A | 29-Sep-17 A | 100% | 0 |  |  | 0 | 0 | 0
S211500 | Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY18 | Actual NonLabor.Actual Nonlabor | 35131 | 39193 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1000879 | Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | Actual NonLabor.Actual Nonlabor | 347247 | 383105 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.01 SiPMs
S245000 | Procure Test stand for SiPMs | UM Contracted Purchase.UM Contracted Purchase <$2M M&S | 22000 | 24272 | 01-Aug-19 A | 30-Dec-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213200 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1226 | 03-Jun-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213300 | Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 | STUDENT UM - PS.STUDENT UM - Purchased Services | 70 | 1073 | 01-Jul-19 A | 31-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S213210 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 | STUDENT UM - PS.STUDENT UM - Purchased Services | 80 | 1226 | 01-Jul-19 A | 15-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02 Calorimeter Front End Electronics
1.05.02.01 EMCal Electronics: Preproduction
S221300 | Fabricate EMCal SiPM Boards: Sectors 1-12 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 25487 | 29002 | 25-Nov-19 A | 20-May-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223000 | Fabricate EMCal Interface Board: Sectors 1-12, Phase 1 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 29435 | 33495 | 19-Feb-20 A | 28-Feb-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223300 | Fabricate Calorimeter Controller Boards: Sectors 1-12 M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 20221 | 23010 | 01-Jul-19 A | 15-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
S222300 | Test EMCal Preamp Boards: Sectors 1-12 | STUDENT UM - PS.STUDENT UM - Purchased Services | 120 | 1915 | 10-Jan-20 A | 29-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
S225300 | Test Pulse Boards 1-12 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 4222 | 4804 | 03-Aug-20 A | 14-Aug-20 A | 100% | 0 |  |  | 0 | 0 | 0
S222200 | Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 1 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 78925 | 89811 | 03-Jan-20 A | 09-Jan-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223700 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 1 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 42072 | 47875 | 01-Oct-19 A | 30-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S223900 | Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 1 - M&S | Purch 1st $2M Fixed.Material (Purchase (1st $2M) | 10720 | 11959 | 01-Apr-20 A | 07-Apr-20 A | 100% | 0 |  |  | 0 | 0 | 0
S226300 | Procure EMCal External Bias Power System: Sectors 1-12, Phase 1 - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 7613 | 8663 | 15-Dec-20 A | 24-Feb-21 A | 100% | 0 |  |  | 0 | 0 | 0
S224300 | Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 1 - M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 3080 | 3505 | 01-Oct-19 A | 28-May-21 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.02.03 HCal Electronics: Preproduction
S236200 | Fabricate HCal SiPM Boards: (6 Modules) M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 28710 | 31675 | 11-Jul-19 A | 17-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S236800 | Fabricate HCal LED Boards: (6 Modules) M&S | Purch 1st $2M.Material (Purchase (1st $2M) | 13070 | 14420 | 03-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S237710 | Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 1 - M&S Split | Purch 1st $2M.Material (Purchase (1st $2M) | 4957 | 5469 | 03-Jun-19 A | 30-Aug-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.05.03 Calorimeter Digitizer System
1.05.03.01 Calorimeter Digitizer: Preproduction Prototype
S248200 | Procure 1/2-Crate Digitizer - Contract/PO - Delivery Acceptance for Assembly & Tests | Purch 1st $2M.Material (Purchase (1st $2M) | 50000 | 55163 | 20-Jun-19 A | 28-Jun-19 A | 100% | 0 |  |  | 0 | 0 | 0
S251000 | Procure EMCAL 7-Crate Digitizer - Parts - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 177359 | 195674 | 03-Sep-19 A | 25-Nov-19 A | 100% | 0 |  |  | 0 | 0 | 0
S251100 | Procure EMCAL 7-Crate Digitizer (Boards) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 39371 | 43437 | 19-Nov-19 A | 30-Jun-20 A | 100% | 0 |  |  | 0 | 0 | 0
S251200 | Procure EMCAL 7-Crate Digitizer (Assembly & Tests) - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 79858 | 90872 | 03-Aug-20 A | 30-Sep-20 A | 100% | 0 |  |  | 0 | 0 | 0
1.06 DAQ/Trigger
S253500 | Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | Actual NonLabor.Actual Nonlabor | 2493 | 2782 | 02-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S1000959 | Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | Actual NonLabor.Actual Nonlabor | 21020 | 23191 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
1.07 Min Bias Trigger Detector
S271300 | Actuals - Nonlabor - sPHENIX MinBias Trigger FY18 | Actual NonLabor.Actual Nonlabor | 371 | 414 | 01-Oct-17 A | 28-Sep-18 A | 100% | 0 |  |  | 0 | 0 | 0
S272600 | Procure Prototype Shaper/Disc Electronics - Delivery Acceptance | Purch 1st $2M.Material (Purchase (1st $2M) | 70000 | 77229 | 03-Jun-19 A | 08-Jul-19 A | 100% | 0 |  |  | 0 | 0 | 0
S1001039 | Actuals - Nonlabor - sPHENIX MinBias Trigger FY19 M8 | Actual NonLabor.Actual Nonlabor | 19492 | 21505 | 01-Oct-18 A | 31-May-19 A | 100% | 0 |  |  | 0 | 0 | 0
Formulas:
Forecast Finish = VLOOKUP([Activity ID],'forecast data dump'!$A1:H3450,5,FALSE)
Forecast Start = VLOOKUP([Activity ID],'forecast data dump'!$A1:H3450,4,FALSE)

## forecast data dump (hidden)
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Total Cost | BL Project Total Cost | Activity % Complete
S100010 | Approve Mission Need CD-0 | 0 | 27-Sep-16 A |  | 0 | 0 | 100%
S100000 | Start sPHENIX MIE Project | 0 | 27-Sep-16 A |  | 0 | 0 | 100%
S100090 | Initial Project Funding Release | 0 | 01-Feb-17 A |  | 0 | 0 | 100%
S318200 | Outer HCAL Sector Mechanical Structure production and assembly - Provide Requirements to Procurement | 0 | 01-Feb-17 A | 01-Feb-17 A | 0 | 0 | 100%
S104800 | Produce TPC v1 Field Cage Prototype Conceptual Design | 1 | 01-Feb-17 A | 02-Feb-17 A | 0 | 0 | 100%
S104900 | Produce TPC v1 Mandrel Conceptual Design | 1 | 01-Feb-17 A | 02-Feb-17 A | 0 | 0 | 100%
S105000 | Procure TPC v1 Mandrel Parts Labor | 1 | 01-Feb-17 A | 02-Feb-17 A | 0 | 0 | 100%
S105100 | Assemble TPC v1 Mandrel | 1 | 01-Feb-17 A | 02-Feb-17 A | 0 | 0 | 100%
S105300 | Produce TPC v1 Outer Field Cage Conceptual Design | 1 | 01-Feb-17 A | 02-Feb-17 A | 0 | 0 | 100%
S105800 | Produce TPC v1 Inner Field Cage Conceptual Design | 1 | 01-Feb-17 A | 02-Feb-17 A | 0 | 0 | 100%
S105200 | Procure TPC v1 Mandrel Parts M&S | 1 | 01-Feb-17 A | 02-Feb-17 A | 0 | 0 | 100%
S134200 | Write TPC FEE prototype v1 design specification | 1 | 01-Feb-17 A | 02-Feb-17 A | 0 | 0 | 100%
S106300 | Design TPC Field Cage Prototype v1 End Rings | 3 | 01-Feb-17 A | 06-Feb-17 A | 0 | 0 | 100%
S301500 | Magnet: Design Power Supply, Magnet, Dump Resistor DC Cabling | 4 | 01-Feb-17 A | 07-Feb-17 A | 0 | 0 | 100%
S303700 | Magnet Power Supply Installation: Design Signal Interconnects | 4 | 01-Feb-17 A | 07-Feb-17 A | 0 | 0 | 100%
S211600 | Write and Review Design Change Specifications for Optical Sensors: Sector 0 - Labor | 9 | 01-Feb-17 A | 14-Feb-17 A | 0 | 0 | 100%
S301200 | Magnet: Design Power Supply AC and Quench Detector Power Distribution | 9 | 01-Feb-17 A | 14-Feb-17 A | 0 | 0 | 100%
S200200 | Outer HCAL Prototype v2.0 Test Beam Operation | 16 | 01-Feb-17 A | 24-Feb-17 A | 0 | 0 | 100%
S143500 | Write Design Spec for TPC DAM prototype v1 | 21 | 01-Feb-17 A | 03-Mar-17 A | 0 | 0 | 100%
S206300 | Design Outer HCAL Scintillating Tiles | 39 | 01-Feb-17 A | 29-Mar-17 A | 0 | 0 | 100%
S245500 | Review and write design change specifications for calorimeter digitizer system: 1/2-Crate Prototype | 39 | 01-Feb-17 A | 29-Mar-17 A | 0 | 0 | 100%
S200400 | Procurement for Outer HCAL Prototype v2.1 Mechanical Structure | 59 | 01-Feb-17 A | 26-Apr-17 A | 0 | 0 | 100%
S253600 | DAQ Design: DAQ Prototype Design | 99 | 01-Feb-17 A | 22-Jun-17 A | 0 | 0 | 100%
S106600 | Produce TPC v1 End Cap Conceptual Design | 149 | 01-Feb-17 A | 01-Sep-17 A | 0 | 0 | 100%
S108000 | Produce TPC v1 Central Membrane Conceptual Design | 162 | 01-Feb-17 A | 21-Sep-17 A | 0 | 0 | 100%
S105400 | Procure TPC v1 Outer Field Cage Parts Labor | 167 | 01-Feb-17 A | 28-Sep-17 A | 0 | 0 | 100%
S105900 | Procure TPC v1 Inner Field Cage Parts Labor | 167 | 01-Feb-17 A | 28-Sep-17 A | 0 | 0 | 100%
S105700 | Procure TPC v1 Outer Field Cage Parts M&S | 167 | 01-Feb-17 A | 28-Sep-17 A | 0 | 0 | 100%
S106200 | Procure TPC v1 Inner Field Cage Parts M&S | 167 | 01-Feb-17 A | 28-Sep-17 A | 0 | 0 | 100%
S102200 | Actuals - Labor - B - BNL Contributed Labor - sPHENIX Project Management FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 498662 | 498662 | 100%
S102300 | Actuals - Labor - A - MIE - sPHENIX Project Management FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 107107 | 107107 | 100%
S103800 | Travel FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S102700 | Mgmt labor FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S104400 | Actuals - Labor - sPHENIX TPC FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 234824 | 234824 | 100%
S104600 | Actuals - Nonlabor - sPHENIX TPC FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 20961 | 20961 | 100%
S134300 | Design TPC FEE prototype v1 | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S135000 | Develop TPC FEE Test Stand Labor | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S135100 | Develop TPC FEE Test Stand M&S | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S156200 | Actuals - Labor - sPHENIX EMCal FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 163723 | 163723 | 100%
S156400 | Actuals - Nonlabor - sPHENIX EMCal FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 45714 | 45714 | 100%
S197400 | Actuals - Labor - sPHENIX HCal FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 260083 | 260083 | 100%
S197600 | Actuals - Nonlabor - sPHENIX HCal FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 3021 | 3021 | 100%
S271000 | Actuals - Labor - sPHENIX MinBias Trigger FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 34217 | 34217 | 100%
S271200 | Actuals - Nonlabor - sPHENIX MinBias Trigger FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S253200 | Actuals - Labor - sPHENIX DAQ&Trigger FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 127930 | 127930 | 100%
S253400 | Actuals - Nonlabor - sPHENIX DAQ&Trigger FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S211200 | Actuals - Labor - sPHENIX Calorimeter Electronics FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 273082 | 273082 | 100%
S211400 | Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 33387 | 33387 | 100%
S278600 | Actuals - Nonlabor - sPHENIX Magnet FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S1000079 | Actuals - Labor - sPHENIX Magnet FY17 16718 | 168 | 01-Feb-17 A | 29-Sep-17 A | 2593 | 2593 | 100%
S1000039 | Actuals - Labor - sPHENIX Magnet FY17 16717 | 168 | 01-Feb-17 A | 29-Sep-17 A | 969 | 969 | 100%
S1000119 | Actuals - Labor - sPHENIX Magnet FY17 16719 | 168 | 01-Feb-17 A | 29-Sep-17 A | 14920 | 14920 | 100%
S344100 | Actuals - Nonlabor - sPHENIX Integration and Installation FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S1000279 | Actuals - Labor - sPHENIX Integration and Installation FY17 16727 | 168 | 01-Feb-17 A | 29-Sep-17 A | 18232 | 18232 | 100%
S1000319 | Actuals - Labor - sPHENIX Integration and Installation FY17 16728 | 168 | 01-Feb-17 A | 29-Sep-17 A | 142 | 142 | 100%
S1000519 | Actuals - Labor - sPHENIX Infrastructure FY17 16724 | 168 | 01-Feb-17 A | 29-Sep-17 A | 6015 | 6005 | 100%
S1000479 | Actuals - Labor - sPHENIX Infrastructure FY17 16723 | 168 | 01-Feb-17 A | 29-Sep-17 A | 17157 | 17157 | 100%
S309400 | Actuals - Nonlabor - sPHENIX Infrastructure FY17 | 168 | 01-Feb-17 A | 29-Sep-17 A | 0 | 0 | 100%
S1000439 | Actuals - Labor - sPHENIX Infrastructure FY17 16722 | 168 | 01-Feb-17 A | 29-Sep-17 A | 15648 | 15648 | 100%
S278400 | Actuals - Labor - sPHENIX Magnet FY17 16716 | 168 | 01-Feb-17 A | 29-Sep-17 A | 19542 | 19542 | 100%
S343900 | Actuals - Labor - sPHENIX Integration and Installation FY17 16726 | 168 | 01-Feb-17 A | 29-Sep-17 A | 85433 | 85433 | 100%
S309200 | Actuals - Labor - sPHENIX Infrastructure FY17 16721 | 168 | 01-Feb-17 A | 29-Sep-17 A | 76844 | 76844 | 100%
S1000559 | Actuals - Labor - sPHENIX Infrastructure FY17 16725 | 168 | 01-Feb-17 A | 29-Sep-17 A | 22417 | 22417 | 100%
S316300 | Analyze and Evaluate Structural Support for Internal Detectors FY18 | 288 | 01-Feb-17 A | 28-Mar-18 A | 0 | 0 | 100%
S260900 | Trigger Design: Write design specifications, Preliminary Design Review | 289 | 01-Feb-17 A | 29-Mar-18 A | 0 | 0 | 100%
S100200 | Prepare for CD-1 Review | 330 | 01-Feb-17 A | 25-May-18 A | 0 | 0 | 100%
S309600 | Carriage Cradle - Create Overall Preliminary Layout | 353 | 01-Feb-17 A | 28-Jun-18 A | 0 | 0 | 100%
S281800 | Cryo System - P&ID development & drawings | 386 | 01-Feb-17 A | 15-Aug-18 A | 0 | 0 | 100%
S281700 | Cryo System - Process Design | 389 | 01-Feb-17 A | 20-Aug-18 A | 0 | 0 | 100%
S287800 | (LN2 supply transfer line system) Cryo Process Design | 389 | 01-Feb-17 A | 20-Aug-18 A | 0 | 0 | 100%
S344300 | Create Subsystem Interface & Integration Plan | 398 | 01-Feb-17 A | 31-Aug-18 A | 0 | 0 | 100%
S287900 | (LN2 supply transfer line system) P&ID development & drawings | 402 | 01-Feb-17 A | 07-Sep-18 A | 0 | 0 | 100%
S102100 | Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY17 | 417 | 01-Feb-17 A | 28-Sep-18 A | 0 | 0 | 100%
S108300 | Design TPC Assembly Fixture | 417 | 01-Feb-17 A | 28-Sep-18 A | 0 | 0 | 100%
S203700 | Build Tile Test Box/Fixture Labor | 417 | 01-Feb-17 A | 28-Sep-18 A | 0 | 0 | 100%
S203800 | Build Tile Test Box/Fixture M&S | 417 | 01-Feb-17 A | 28-Sep-18 A | 0 | 0 | 100%
S349700 | Design Outer HCal Integration/Installation Tooling/Fixtures FY18 | 417 | 01-Feb-17 A | 28-Sep-18 A | 0 | 0 | 100%
S354300 | Design Inner HCal Integration/Installation Tooling/Fixtures FY18 | 417 | 01-Feb-17 A | 28-Sep-18 A | 0 | 0 | 100%
S319200 | Procure Outer HCAL Mechanical Structure Components - Prepare & Send Solicitation | 29 | 02-Feb-17 A | 16-Mar-17 A | 0 | 0 | 100%
S106400 | Procure TPC Field Cage Prototype v1 End Rings Labor | 39 | 07-Feb-17 A | 04-Apr-17 A | 0 | 0 | 100%
S106500 | Procure TPC Field Cage Prototype v1 End Rings M&S | 39 | 07-Feb-17 A | 04-Apr-17 A | 0 | 0 | 100%
S211601 | Final Design Review - EMCal, OHCal - Silicon Photomultipliers (LLP) | 0 |  | 14-Feb-17 A | 0 | 0 | 100%
S301400 | Magnet: Design Quench Detector AC Power Hook-up | 1 | 15-Feb-17 A | 16-Feb-17 A | 0 | 0 | 100%
S301300 | Magnet: Design Power Supply AC Power Hook-up | 2 | 15-Feb-17 A | 17-Feb-17 A | 0 | 0 | 100%
S211700 | Write and Review Design Change Specifications for Optical Sensors: Sector 0 - M&S | 19 | 15-Feb-17 A | 15-Mar-17 A | 0 | 0 | 100%
S200300 | Complete Outer HCAL Prototype v2.0 | 0 |  | 24-Feb-17 A | 0 | 0 | 100%
S271400 | MBD Detector validation using Laser Labor | 188 | 02-Mar-17 A | 30-Nov-17 A | 0 | 0 | 100%
S271500 | MBD Detector validation using Laser M&S | 188 | 02-Mar-17 A | 30-Nov-17 A | 0 | 0 | 100%
S271800 | Readout validation of sPHENIX Prototype Digitizers | 189 | 02-Mar-17 A | 01-Dec-17 A | 0 | 0 | 100%
S143700 | Develop TPC DAM prototype v1 Test Stand M&S | 39 | 06-Mar-17 A | 28-Apr-17 A | 0 | 0 | 100%
S143600 | Develop TPC DAM prototype v1 Test Stand Labor | 194 | 06-Mar-17 A | 12-Dec-17 A | 0 | 0 | 100%
S180800 | Design 2D projective blocks for v2.1 prototype | 9 | 09-Mar-17 A | 22-Mar-17 A | 0 | 0 | 100%
S211800 | Order Sensors: Sector 0 - Labor | 119 | 16-Mar-17 A | 01-Sep-17 A | 0 | 0 | 100%
S211900 | Order Sensors: Sector 0 - M&S | 119 | 16-Mar-17 A | 01-Sep-17 A | 0 | 0 | 100%
S319300 | Procure Outer HCAL Mechanical Structure Components - Vendor Responses | 9 | 17-Mar-17 A | 30-Mar-17 A | 0 | 0 | 100%
S180900 | Design screens for v2.1 prototype blocks | 4 | 23-Mar-17 A | 29-Mar-17 A | 0 | 0 | 100%
S182300 | Design 2D projective blocks for preproduction prototype | 4 | 23-Mar-17 A | 29-Mar-17 A | 0 | 0 | 100%
S206700 | Design Outer HCAL Light Collection | 19 | 23-Mar-17 A | 19-Apr-17 A | 0 | 0 | 100%
S206400 | Internal Review of OHCAL Scint. Tiles; First part of Procurement Readiness Review - OHCAL Scint. Tiles (LLP) | 1 | 30-Mar-17 A | 31-Mar-17 A | 0 | 0 | 100%
S182400 | Design screens for preproduction prototype blocks | 4 | 30-Mar-17 A | 05-Apr-17 A | 0 | 0 | 100%
S181000 | Design light guides for v2.1 prototype blocks | 29 | 30-Mar-17 A | 10-May-17 A | 0 | 0 | 100%
S246000 | Design Digitizer Crate: 1/2-Crate Prototype | 29 | 30-Mar-17 A | 10-May-17 A | 0 | 0 | 100%
S245600 | Design Digitizer ADC Boards: 1/2-Crate Prototype | 39 | 30-Mar-17 A | 24-May-17 A | 0 | 0 | 100%
S245700 | Design Digitizer Controller Board: 1/2-Crate Prototype | 39 | 30-Mar-17 A | 24-May-17 A | 0 | 0 | 100%
S245800 | Design Digitizer XMIT Board: 1/2-Crate Prototype | 39 | 30-Mar-17 A | 24-May-17 A | 0 | 0 | 100%
S245900 | Design Digitizer Clock Master: 1/2-Crate Prototype | 59 | 30-Mar-17 A | 22-Jun-17 A | 0 | 0 | 100%
S319400 | Procure Outer HCAL Mechanical Structure Components - Vendor Selection | 13 | 31-Mar-17 A | 19-Apr-17 A | 0 | 0 | 100%
S158100 | Set up factory for preproduction prototype Sector 0 | 89 | 31-Mar-17 A | 07-Aug-17 A | 0 | 0 | 100%
S206500 | Address Issues from Internal Review of Outer HCAL Scintillating Tile | 9 | 03-Apr-17 A | 14-Apr-17 A | 0 | 0 | 100%
S157300 | Order fibers preproduction prototype Sector 0 | 89 | 06-Apr-17 A | 11-Aug-17 A | 0 | 0 | 100%
S157400 | Order fibers preproduction prototype Sector 0 | 89 | 06-Apr-17 A | 11-Aug-17 A | 0 | 0 | 100%
S113400 | Assemble TPC v1 Module Gas Enclosure | 9 | 07-Apr-17 A | 20-Apr-17 A | 0 | 0 | 100%
S156600 | Order screens for v2.1 prototype | 24 | 13-Apr-17 A | 17-May-17 A | 0 | 0 | 100%
S156700 | Order screens for v2.1 prototype | 24 | 13-Apr-17 A | 17-May-17 A | 0 | 0 | 100%
S206600 | Outer HCAL Scintillating Tile Design Complete | 0 |  | 14-Apr-17 A | 0 | 0 | 100%
S206800 | Internal Review of OHCAL Light collections; Second part of Procurement Readiness Review - OHCAL Scint. Tiles (LLP) | 0 | 20-Apr-17 A | 20-Apr-17 A | 0 | 0 | 100%
S157500 | Order screens for preproduction prototype Sector 0 | 134 | 20-Apr-17 A | 31-Oct-17 A | 0 | 0 | 100%
S157600 | Order screens for preproduction prototype Sector 0 | 134 | 20-Apr-17 A | 31-Oct-17 A | 0 | 0 | 100%
S319500 | Procure Outer HCAL Mechanical Structure Components - Contract Award (Raw Mat'l & Sector Assemblies) | 0 | 21-Apr-17 A |  | 0 | 0 | 100%
OBLG319501 | Procure Outer HCAL Mechanical Structure Components - Obligation (Raw Mat'l & Sector Assemblies) | 0 | 21-Apr-17 A | 21-Apr-17 A | 0 | 0 | 100%
S113500 | Test TPC v1 Module Gas Enclosure | 4 | 21-Apr-17 A | 27-Apr-17 A | 0 | 0 | 100%
S206900 | Address Issues from Internal Review of Outer HCAL Light Collection | 9 | 21-Apr-17 A | 04-May-17 A | 0 | 0 | 100%
S200500 | Award Procurement for Outer HCAL Prototype v2.1 Mechanical Structure | 0 |  | 26-Apr-17 A | 0 | 0 | 100%
S188300 | Design cooling system for V2.1 prototype | 29 | 27-Apr-17 A | 08-Jun-17 A | 0 | 0 | 100%
S200600 | Outer HCAL Prototype v2.1 Mechanical Structure Production | 79 | 27-Apr-17 A | 18-Aug-17 A | 0 | 0 | 100%
S207100 | Design Outer HCAL LED/Fiber Calibration System | 19 | 28-Apr-17 A | 25-May-17 A | 0 | 0 | 100%
S143800 | Measure TPC DAM prototype v1 Throughput | 154 | 01-May-17 A | 12-Dec-17 A | 0 | 0 | 100%
S207000 | Outer HCAL Light Collection Complete | 0 |  | 04-May-17 A | 0 | 0 | 100%
S182500 | Design light guides for preproduction prototype | 56 | 11-May-17 A | 01-Aug-17 A | 0 | 0 | 100%
S181100 | Procure light guides for v2.1 prototype modules Labor | 139 | 11-May-17 A | 01-Dec-17 A | 0 | 0 | 100%
S181800 | Procure light guides for v2.1 prototype modules M&S | 139 | 11-May-17 A | 01-Dec-17 A | 0 | 0 | 100%
S156800 | Fabricate molds for v2.1 prototype | 19 | 18-May-17 A | 15-Jun-17 A | 0 | 0 | 100%
S246100 | Layout Digitizer ADC Board: 1/2-Crate Prototype | 39 | 25-May-17 A | 21-Jul-17 A | 0 | 0 | 100%
S246200 | Layout Digitizer Controller Board: 1/2-Crate Prototype | 39 | 25-May-17 A | 21-Jul-17 A | 0 | 0 | 100%
S246300 | Layout Digitizer XMIT Board: 1/2-Crate Prototype | 39 | 25-May-17 A | 21-Jul-17 A | 0 | 0 | 100%
S207200 | Internal Review of OHCAL LED/Fiber calibration; Third part of Procurement Readiness Review - OHCAL Scint. Tiles (LLP) | 1 | 26-May-17 A | 30-May-17 A | 0 | 0 | 100%
S207300 | Address Issues from Internal Review of Outer HCAL LED/Fiber Calibration System | 9 | 31-May-17 A | 13-Jun-17 A | 0 | 0 | 100%
S125800 | TPC R1 Module Production Procure Contracted Labor and M&S SBU - Provide Requirements to Procurement | 4 | 09-Jun-17 A | 15-Jun-17 A | 0 | 0 | 100%
S179100 | Procure Contracted Labor Univ. Illinois Urbana-Champaign (UIUC) - Provide Requirements to Procurement | 4 | 09-Jun-17 A | 15-Jun-17 A | 0 | 0 | 100%
S157100 | Order W powder preproduction prototype Sector 0 Labor | 39 | 09-Jun-17 A | 04-Aug-17 A | 0 | 0 | 100%
S157200 | Order W powder preproduction prototype Sector 0 M&S | 39 | 09-Jun-17 A | 04-Aug-17 A | 0 | 0 | 100%
S188400 | Procure parts for cooling system for V2.1 prototype Labor | 109 | 09-Jun-17 A | 15-Nov-17 A | 0 | 0 | 100%
S188800 | Procure parts for cooling system for V2.1 prototype M&S | 109 | 09-Jun-17 A | 15-Nov-17 A | 0 | 0 | 100%
S207400 | Outer HCAL LED/Fiber Calibration Conceptual Design Complete | 0 |  | 13-Jun-17 A | 0 | 0 | 100%
S125900 | TPC R1 Module Production Procure Contracted Labor and M&S Wayne - Vendor Selection | 29 | 16-Jun-17 A | 28-Jul-17 A | 0 | 0 | 100%
S179200 | Procure Contracted Labor Univ. Illinois Urbana-Champaign (UIUC) - Vendor Selection | 29 | 16-Jun-17 A | 28-Jul-17 A | 0 | 0 | 100%
S156900 | Fabricate blocks for v2.1 prototype | 78 | 16-Jun-17 A | 06-Oct-17 A | 0 | 0 | 100%
S200900 | Procure Scintillating Tiles for HCAL Prototype v2.1 | 24 | 20-Jun-17 A | 25-Jul-17 A | 0 | 0 | 100%
S246400 | Layout Digitizer Clock Master: 1/2-Crate | 150 | 23-Jun-17 A | 01-Feb-18 A | 0 | 0 | 100%
S253700 | DAQ Design: Specify front-end layout | 240 | 23-Jun-17 A | 10-Jun-18 A | 0 | 0 | 100%
S157700 | Order epoxy for preproduction prototype Sector 0 | 19 | 24-Jul-17 A | 18-Aug-17 A | 0 | 0 | 100%
S157900 | Order parts and fabricate molds for preproduction prototype Sector 0 M&S | 19 | 24-Jul-17 A | 18-Aug-17 A | 0 | 0 | 100%
S157800 | Order epoxy for preproduction prototype Sector 0 | 19 | 24-Jul-17 A | 18-Aug-17 A | 0 | 0 | 100%
S158000 | Order parts and fabricate molds for preproduction prototype Sector 0 Labor | 19 | 24-Jul-17 A | 18-Aug-17 A | 0 | 0 | 100%
S201000 | Award Procurement for Scintillating Tiles for HCAL Test Beam Prototype v2.1 | 0 |  | 26-Jul-17 A | 0 | 0 | 100%
S201100 | Fabricate HCAL Prototype v2.1 Tiles & Ship to BNL | 87 | 27-Jul-17 A | 04-Dec-17 A | 0 | 0 | 100%
S126000 | TPC R1 Module Production Procure Contracted Labor and M&S SBU, Phase 1 - Contract Award | 0 | 31-Jul-17 A |  | 0 | 0 | 100%
OBLG126001 | TPC R1 Module Production Procure Contracted Labor and M&S SBU, Phase 1 - Obligation | 0 | 31-Jul-17 A | 31-Jul-17 A | 0 | 0 | 100%
S126008 | TPC R1 Module Production Procure Contracted Labor and M&S Wayne, Phase 1 - Contract Award | 0 | 31-Jul-17 A |  | 0 | 0 | 100%
OBLG126002 | TPC R1 Module Production Procure Contracted Labor and M&S Wayne, Phase 1 - Obligation | 0 | 31-Jul-17 A | 31-Jul-17 A | 0 | 0 | 100%
S179300 | Procure Contracted Labor Univ. Illinois Urbana-Champaign (UIUC) - Contract Award | 0 | 31-Jul-17 A |  | 0 | 0 | 100%
OBLG179310 | Procure Contracted Labor Univ. Illinois Urbana-Champaign (UIUC) - Obligation | 0 | 31-Jul-17 A | 31-Jul-17 A | 0 | 0 | 100%
S319600 | Procure Outer HCAL Mechanical Structure Components - Contract Award (First Article) | 0 | 03-Aug-17 A |  | 0 | 0 | 100%
S319700 | Procure Outer HCal Mechanical Structure Components - Lead Time (First Article) | 26 | 03-Aug-17 A | 09-Sep-17 A | 0 | 0 | 100%
S200700 | Incorporate Feedback from Prototype v2.1 into Outer HCAL Design | 9 | 21-Aug-17 A | 01-Sep-17 A | 0 | 0 | 100%
S181200 | Procure mechanical parts for V2.1 prototype modules Labor | 35 | 21-Aug-17 A | 11-Oct-17 A | 0 | 0 | 100%
S181900 | Procure mechanical parts for V2.1 prototype modules M&S | 35 | 21-Aug-17 A | 11-Oct-17 A | 0 | 0 | 100%
S200800 | Complete Outer HCAL Prototype v2.1 | 0 |  | 01-Sep-17 A | 0 | 0 | 100%
S200801 | Preliminary Design Review - Outer HCAL Sector Assembly 1-6 | 0 |  | 01-Sep-17 A | 0 | 0 | 100%
S113100 | Design TPC v1 Module Gas Enclosure | 9 | 05-Sep-17 A | 18-Sep-17 A | 0 | 0 | 100%
S113600 | Design TPC v1 Module Strongback | 9 | 05-Sep-17 A | 18-Sep-17 A | 0 | 0 | 100%
S212100 | Q/A Delivered Sensors: Sector 0 - M&S | 72 | 05-Sep-17 A | 20-Dec-17 A | 0 | 0 | 100%
S212000 | Q/A Delivered Sensors: Sector 0 - Labor | 72 | 05-Sep-17 A | 20-Dec-17 A | 0 | 0 | 100%
S318300 | Final Mechanical Design of Outer HCAL Sector | 98 | 05-Sep-17 A | 30-Jan-18 A | 0 | 0 | 100%
S320100 | Procure Outer HCal Mechanical Structure Components - Del. Accept. (First Article) | 40 | 10-Sep-17 A | 07-Nov-17 A | 0 | 0 | 100%
S113200 | Procure TPC v1 Module Gas Enclosure Parts Labor | 0 | 19-Sep-17 A | 19-Sep-17 A | 0 | 0 | 100%
S113300 | Procure TPC v1 Module Gas Enclosure Parts M&S | 0 | 19-Sep-17 A | 19-Sep-17 A | 0 | 0 | 100%
S113900 | Design TPC v1 Module Frames | 61 | 19-Sep-17 A | 19-Dec-17 A | 0 | 0 | 100%
S114200 | Design TPC v1 Module Grid | 61 | 19-Sep-17 A | 19-Dec-17 A | 0 | 0 | 100%
S108100 | Procure TPC v1 Central Membrane Parts Labor FY18 | 254 | 22-Sep-17 A | 28-Sep-18 A | 0 | 0 | 100%
S107800 | Procure TPC v1 Central Membrane Parts M&S FY18 | 266 | 22-Sep-17 A | 17-Oct-18 A | 0 | 0 | 100%
S105500 | Assemble TPC v1 Outer Field Cage FY18 | 249 | 29-Sep-17 A | 28-Sep-18 A | 0 | 0 | 100%
S106000 | Assemble TPC v1 Inner Field Cage FY18 | 249 | 29-Sep-17 A | 28-Sep-18 A | 0 | 0 | 100%
S271100 | Actuals - Labor - sPHENIX MinBias Trigger FY18 | 248 | 01-Oct-17 A | 28-Sep-18 A | 81740 | 81740 | 100%
S271300 | Actuals - Nonlabor - sPHENIX MinBias Trigger FY18 | 248 | 01-Oct-17 A | 28-Sep-18 A | 414 | 414 | 100%
S1000359 | Actuals - Labor - sPHENIX Integration and Installation FY18 16727 | 248 | 01-Oct-17 A | 28-Sep-18 A | 76883 | 76883 | 100%
S1000399 | Actuals - Labor - sPHENIX Integration and Installation FY18 16728 | 248 | 01-Oct-17 A | 28-Sep-18 A | 523 | 523 | 100%
S1000679 | Actuals - Labor - sPHENIX Infrastructure FY18 16724 | 248 | 01-Oct-17 A | 28-Sep-18 A | 6015 | 67591 | 100%
S1000639 | Actuals - Labor - sPHENIX Infrastructure FY18 16723 | 248 | 01-Oct-17 A | 28-Sep-18 A | 20716 | 20716 | 100%
S309500 | Actuals - Nonlabor - sPHENIX Infrastructure FY18 16722 | 248 | 01-Oct-17 A | 28-Sep-18 A | 1078243 | 1078243 | 100%
S1000599 | Actuals - Labor - sPHENIX Infrastructure FY18 16722 | 248 | 01-Oct-17 A | 28-Sep-18 A | 168592 | 168592 | 100%
S344000 | Actuals - Labor - sPHENIX Integration and Installation FY18 16726 | 248 | 01-Oct-17 A | 28-Sep-18 A | 118130 | 118130 | 100%
S344200 | Actuals - Nonlabor - sPHENIX Integration and Installation FY18 16726 16727 and 16728 | 248 | 01-Oct-17 A | 28-Sep-18 A | 3012 | 3012 | 100%
S309300 | Actuals - Labor - sPHENIX Infrastructure FY18 16721 | 248 | 01-Oct-17 A | 28-Sep-18 A | 196648 | 196648 | 100%
S1000719 | Actuals - Labor - sPHENIX Infrastructure FY18 16725 | 248 | 01-Oct-17 A | 28-Sep-18 A | 17027 | 17027 | 100%
S101008 | FY18 funding available | 0 | 02-Oct-17 A |  | 0 | 0 | 100%
S134400 | Procure TPC FEE prototype v1 components Labor | 20 | 02-Oct-17 A | 31-Oct-17 A | 0 | 0 | 100%
S134500 | Procure TPC FEE prototype v1 components M&S | 20 | 02-Oct-17 A | 31-Oct-17 A | 0 | 0 | 100%
S134800 | Procure TPC FEE prototype v1 LV power supplies Labor | 29 | 02-Oct-17 A | 14-Nov-17 A | 0 | 0 | 100%
S134900 | Procure TPC FEE prototype v1 LV power supplies M&S | 29 | 02-Oct-17 A | 14-Nov-17 A | 0 | 0 | 100%
S102600 | Actuals - Labor - B - BNL Contributed Labor - sPHENIX Project Management FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 1146441 | 1146441 | 100%
S102400 | Actuals - Labor - A - MIE - sPHENIX Project Management FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 283044 | 283044 | 100%
S102500 | Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 610909 | 610909 | 100%
S103600 | Mgmt labor - B - BNL Contributed Labor - FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S102800 | Mgmt labor - A - MIE - FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S104500 | Actuals - Labor - sPHENIX TPC FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 716473 | 716473 | 100%
S104700 | Actuals - Nonlabor - sPHENIX TPC FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S104710 | Actuals - Nonlabor - sPHENIX TPC FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 274664 | 274664 | 100%
S156300 | Actuals - Labor - sPHENIX EMCal FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 479465 | 479465 | 100%
S156500 | Actuals - Nonlabor - sPHENIX EMCal FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 463282 | 463282 | 100%
S197500 | Actuals - Labor - sPHENIX HCal FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 579301 | 579301 | 100%
S197700 | Actuals - Nonlabor - sPHENIX HCal FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 142473 | 142473 | 100%
S253300 | Actuals - Labor - sPHENIX DAQ&Trigger FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 428318 | 428318 | 100%
S253500 | Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 2782 | 2782 | 100%
S211300 | Actuals - Labor - sPHENIX Calorimeter Electronics FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 593810 | 593810 | 100%
S211500 | Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY18 | 248 | 02-Oct-17 A | 28-Sep-18 A | 39193 | 39193 | 100%
S1000239 | Actuals - Labor - sPHENIX Magnet FY18 16720 | 248 | 02-Oct-17 A | 28-Sep-18 A | 925 | 925 | 100%
S1000159 | Actuals - Labor - sPHENIX Magnet FY18 16718 | 248 | 02-Oct-17 A | 28-Sep-18 A | 137267 | 137267 | 100%
S1000199 | Actuals - Labor - sPHENIX Magnet FY18 16719 | 248 | 02-Oct-17 A | 28-Sep-18 A | 6767 | 6767 | 100%
S278500 | Actuals - Labor - sPHENIX Magnet FY18 16716 and 16717 | 248 | 02-Oct-17 A | 28-Sep-18 A | 81575 | 81575 | 100%
S278700 | Actuals - Nonlabor - sPHENIX Magnet FY18 16716 | 248 | 02-Oct-17 A | 28-Sep-18 A | 28189 | 28189 | 100%
S274400 | 2018 Magnet Project Management | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S275000 | 2018 Cryo L3 Project Management | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S275500 | 2018 PS & Quench Protection L3 Project Management | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S277800 | 2018 Integration & Installation Project Management | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S276000 | 2018 Infrastructure Project Management | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S276600 | 2018 Facility Support Systems L3 Project Management | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S277200 | 2018 Detector Support Systems L3 Project Management | 248 | 02-Oct-17 A | 28-Sep-18 A | 0 | 0 | 100%
S103900 | Travel FY18 | 249 | 02-Oct-17 A | 01-Oct-18 A | 0 | 0 | 100%
S157000 | Ship v2.1 blocks 1-16 to BNL | 4 | 10-Oct-17 A | 16-Oct-17 A | 0 | 0 | 100%
S188500 | Prepare mounting supports for V2.1 prototype | 2 | 12-Oct-17 A | 16-Oct-17 A | 0 | 0 | 100%
S181300 | Receive, unpack, log and inspect blocks for v2.1 Prototype | 0 | 17-Oct-17 A | 17-Oct-17 A | 0 | 0 | 100%
S181400 | Install reflectors and mounting supports on v2.1 prototype blocks | 0 | 18-Oct-17 A | 18-Oct-17 A | 0 | 0 | 100%
S182000 | Install reflectors and mounting supports on v2.1 prototype blocks | 0 | 18-Oct-17 A | 18-Oct-17 A | 0 | 0 | 100%
S134600 | Fabricate TPC FEE prototype v1 boards Labor | 61 | 01-Nov-17 A | 02-Feb-18 A | 0 | 0 | 100%
S134700 | Fabricate TPC FEE prototype v1 boards M&S | 61 | 01-Nov-17 A | 02-Feb-18 A | 0 | 0 | 100%
S271600 | MBD Detector validation in Magnetic Field Labor | 7 | 01-Dec-17 A | 12-Dec-17 A | 0 | 0 | 100%
S271700 | MBD Detector validation in Magnetic Field M&S | 7 | 01-Dec-17 A | 12-Dec-17 A | 0 | 0 | 100%
S181500 | Prepare light guides for V2.1 prototype | 4 | 04-Dec-17 A | 08-Dec-17 A | 0 | 0 | 100%
S271900 | Preliminary Design Review - MBD (Discriminator/Shaper board) | 11 | 04-Dec-17 A | 19-Dec-17 A | 0 | 0 | 100%
S201200 | Inspect HCAL Prototype v2.1 Scintillating Tiles and Final Design Review and Procurement Readiness Review | 9 | 05-Dec-17 A | 18-Dec-17 A | 0 | 0 | 100%
S181600 | Install light guides on v2.1 prototype blocks | 4 | 11-Dec-17 A | 15-Dec-17 A | 0 | 0 | 100%
S182100 | Procure EMCAL Prototype V2.1 Blocks & Modules - Delivery Acceptance | 4 | 11-Dec-17 A | 15-Dec-17 A | 0 | 0 | 100%
S143900 | Preliminary Design Review - TPC DAM | 0 |  | 12-Dec-17 A | 0 | 0 | 100%
S100300 | Prototype 2018 Spending Authorization | 0 |  | 18-Dec-17 A | 0 | 0 | 100%
S181700 | Install SiPMs & daughterboards on v2.1 prototype blocks | 0 | 18-Dec-17 A | 18-Dec-17 A | 0 | 0 | 100%
S182200 | Install SiPMs & daughterboards on v2.1 prototype blocks | 0 | 18-Dec-17 A | 18-Dec-17 A | 0 | 0 | 100%
S182201 | Preliminary Design Review - EMCal Modules for Sectors 1-12 | 0 |  | 18-Dec-17 A | 0 | 0 | 100%
S201201 | Final Design Review - Outer HCAL Sector Assembly 1-6 | 0 |  | 18-Dec-17 A | 0 | 0 | 100%
S160800 | Establish contract for EMCAL Prepro Sectors 1-12 blocks with UIUC | 118 | 18-Dec-17 A | 07-Jun-18 A | 0 | 0 | 100%
S271901 | Develop Scope and Documentation for Shaper/Disc Boards, Preliminary Design Review | 0 |  | 19-Dec-17 A | 0 | 0 | 100%
S188600 | Install blocks in v2.1 prototype | 1 | 19-Dec-17 A | 20-Dec-17 A | 0 | 0 | 100%
S212200 | EMCal/HCal Sensors Tested, Delivered and Procurement Readiness Review: Sector 0 | 0 |  | 20-Dec-17 A | 0 | 0 | 100%
S212201 | Procurement Readiness Review - EMCal, OHCal - Silicon Photomultipliers (LLP) | 0 |  | 20-Dec-17 A | 0 | 0 | 100%
S188700 | Install readout electronics on v2.1 prototype | 0 | 21-Dec-17 A | 21-Dec-17 A | 0 | 0 | 100%
S188900 | Install cooling system on v2.1 prototype | 4 | 22-Dec-17 A | 29-Dec-17 A | 0 | 0 | 100%
S144000 | Procure TPC DAM Felix 2.0 Boards Evaluation - Provide Requirements to Procurement | 14 | 28-Dec-17 A | 19-Jan-18 A | 0 | 0 | 100%
S189000 | Test v2.1 prototype with LEDs & cosmic rays | 30 | 02-Jan-18 A | 14-Feb-18 A | 0 | 0 | 100%
S189700 | Design mechanical enclosure for preproduction prototype Sector 0 | 131 | 02-Jan-18 A | 10-Jul-18 A | 0 | 0 | 100%
S189800 | Design mechanical support structure for preproduction prototype Sector 0 | 131 | 02-Jan-18 A | 10-Jul-18 A | 0 | 0 | 100%
S189900 | Design cooling system for preproduction prototype Sector 0 | 131 | 02-Jan-18 A | 10-Jul-18 A | 0 | 0 | 100%
S274900 | Cryogenics System Technical Review | 32 | 12-Jan-18 A | 01-Mar-18 A | 0 | 0 | 100%
S144100 | Procure TPC DAM Felix 2.0 Boards Evaluation - Prepare & Send Solicitation | 20 | 20-Jan-18 A | 20-Feb-18 A | 0 | 0 | 100%
S318400 | Internal Review of Outer HCAL Sector Mechanical Design | 1 | 31-Jan-18 A | 01-Feb-18 A | 0 | 0 | 100%
S318700 | Internal Review of Outer HCAL Lifting Fixture and Supports | 9 | 31-Jan-18 A | 13-Feb-18 A | 0 | 0 | 100%
S318500 | Address Issues from Internal Review of Outer HCAL Sector Mechanical Design | 20 | 02-Feb-18 A | 03-Mar-18 A | 0 | 0 | 100%
S100340 | BNL Prototype Spending Authorization | 0 | 13-Feb-18 A |  | 0 | 0 | 100%
S265500 | GL1 Design: Evaluate performance Requirements, Preliminary Design Review | 53 | 13-Feb-18 A | 30-Apr-18 A | 0 | 0 | 100%
S272000 | Procure Prototype Shaper/Disc Electronics - Provide Requirements to Procurement | 54 | 13-Feb-18 A | 01-May-18 A | 0 | 0 | 100%
S268300 | Evaluate performance Requirements, Preliminary Design Review | 75 | 13-Feb-18 A | 31-May-18 A | 0 | 0 | 100%
S307400 | Magnet Field Measurements: Setup a detailed 3D model of the coil, return yoke and internal calorimeters FY18 | 159 | 13-Feb-18 A | 28-Sep-18 A | 0 | 0 | 100%
S189100 | Pack & ship v2.1 prototype to Fermilab Labor | 0 | 14-Feb-18 A | 14-Feb-18 A | 0 | 0 | 100%
S189200 | Pack & ship v2.1 prototype to Fermilab M&S | 0 | 14-Feb-18 A | 14-Feb-18 A | 0 | 0 | 100%
S318800 | Address Issues from Internal Review of Outer HCAL Lifting Fixture and Supports | 29 | 14-Feb-18 A | 28-Mar-18 A | 0 | 0 | 100%
S144200 | Procure TPC DAM Felix 2.0 Boards Evaluation - Vendor Responses | 8 | 21-Feb-18 A | 05-Mar-18 A | 0 | 0 | 100%
S189300 | Test v2.1 prototype in test beam at Fermilab Labor | 63 | 21-Feb-18 A | 21-May-18 A | 0 | 0 | 100%
S189400 | Test v2.1 prototype in test beam at Fermilab M&S | 63 | 21-Feb-18 A | 21-May-18 A | 0 | 0 | 100%
S327400 | Evaluate Existing Power Distribution System for Line Electric Power | 64 | 01-Mar-18 A | 31-May-18 A | 0 | 0 | 100%
S135200 | Assemble and test TPC FEE prototype v1 Labor | 148 | 01-Mar-18 A | 28-Sep-18 A | 0 | 0 | 100%
S135300 | Assemble and test TPC FEE prototype v1 M&S | 148 | 01-Mar-18 A | 28-Sep-18 A | 0 | 0 | 100%
S357300 | Design EMCal Integration/Installation Tooling/Fixtures FY18 | 148 | 01-Mar-18 A | 28-Sep-18 A | 0 | 0 | 100%
S282500 | Helium Lines Routing from 1008B to IP8 hall and LN2 line routing from dewar to IP8 Hall. | 128 | 02-Mar-18 A | 31-Aug-18 A | 0 | 0 | 100%
S292500 | (Warm Piping System) P&ID development & drawings | 132 | 02-Mar-18 A | 07-Sep-18 A | 0 | 0 | 100%
S282000 | RHIC Helium Interface - Mechanical Engineering Design Tasks FY18 | 147 | 02-Mar-18 A | 28-Sep-18 A | 0 | 0 | 100%
S282600 | RHIC interface valvebox and field joint layout at the interconnect where we tie into RHIC VJ lines and modeling FY18 | 147 | 02-Mar-18 A | 28-Sep-18 A | 0 | 0 | 100%
S288000 | (LN2 supply transfer line system) Mechanical Engineering Tasks FY18 | 147 | 02-Mar-18 A | 28-Sep-18 A | 0 | 0 | 100%
S144300 | Procure TPC DAM Felix 2.0 Boards Evaluation - Vendor Selection | 14 | 06-Mar-18 A | 26-Mar-18 A | 0 | 0 | 100%
S246800 | Procure 1/2-Crate Digitizer - Parts - Provide Requirements to Procurement | 5 | 09-Mar-18 A | 16-Mar-18 A | 0 | 0 | 100%
S307800 | Magnet Field Measurements: Perform Magnet Assembly Stress Analysis FY18 | 139 | 14-Mar-18 A | 28-Sep-18 A | 0 | 0 | 100%
S158201 | Preliminary Design Review - EMCal Blocks | 0 |  | 20-Mar-18 A | 0 | 0 | 100%
S158200 | Prepare fiber assemblies for preproduction prototype Sector 0 | 44 | 20-Mar-18 A | 20-May-18 A | 0 | 0 | 100%
S268400 | Timing system Design: Write design specifications | 50 | 21-Mar-18 A | 31-May-18 A | 0 | 0 | 100%
S114600 | Preliminary Design Review - TPC Module | 0 | 23-Mar-18 A | 23-Mar-18 A | 0 | 0 | 100%
S113700 | Procure TPC v1 Module Strongback - Labor | 19 | 23-Mar-18 A | 19-Apr-18 A | 0 | 0 | 100%
S114300 | Procure TPC v1 Grid Parts Labor | 19 | 23-Mar-18 A | 19-Apr-18 A | 0 | 0 | 100%
S113800 | Procure TPC v1 Module Strongback - M&S | 19 | 23-Mar-18 A | 19-Apr-18 A | 0 | 0 | 100%
S114400 | Procure TPC v1 Grid Parts M&S | 19 | 23-Mar-18 A | 19-Apr-18 A | 0 | 0 | 100%
S114000 | Procure TPC v1 Module Frames Labor | 29 | 23-Mar-18 A | 03-May-18 A | 0 | 0 | 100%
S114100 | Procure TPC v1 Module Frames M&S | 29 | 23-Mar-18 A | 03-May-18 A | 0 | 0 | 100%
S144400 | Procure TPC DAM Felix 2.0 Boards Evaluation - Contract Award(s) | 0 | 26-Mar-18 A |  | 0 | 0 | 100%
S114700 | Design TPC v1a Module Padplane | 9 | 26-Mar-18 A | 06-Apr-18 A | 0 | 0 | 100%
S144500 | Procure TPC DAM Felix 2.0 Boards Evaluation - Contract/PO - Leadtime | 111 | 27-Mar-18 A | 31-Aug-18 A | 0 | 0 | 100%
S318900 | Outer HCAL Lifting Fixture and Supports Design Complete | 0 |  | 28-Mar-18 A | 0 | 0 | 100%
S319000 | Procure Outer HCAL Lifting Fixture and Supports - Provide BNL Central Shops | 66 | 29-Mar-18 A | 02-Jul-18 A | 0 | 0 | 100%
S318600 | Outer HCAL Sector Mechanical Design Complete | 0 |  | 30-Mar-18 A | 0 | 0 | 100%
S261000 | Trigger Design, Layout Custom LL1 - Provide Requirements to Procurement | 4 | 30-Mar-18 A | 05-Apr-18 A | 0 | 0 | 100%
S344400 | Create Subsystem Initial Envelope Drawings | 39 | 30-Mar-18 A | 24-May-18 A | 0 | 0 | 100%
S253800 | DAQ Design: Specify the event Builder and back-end layout | 50 | 30-Mar-18 A | 10-Jun-18 A | 0 | 0 | 100%
S309700 | Carriage Cradle - Perform Analyses, Design & System Integration (Initial) | 127 | 30-Mar-18 A | 28-Sep-18 A | 0 | 0 | 100%
S216600 | Review and write design specification: EMCal Preproduction Prototype [Sector 0] | 20 | 01-Apr-18 A | 30-Apr-18 A | 0 | 0 | 100%
S246900 | Procure 1/2-Crate Digitizer - Parts - Prepare & Send Solicitation | 9 | 02-Apr-18 A | 13-Apr-18 A | 0 | 0 | 100%
S268500 | Timing System Prototype: Select FPGA Board | 11 | 06-Apr-18 A | 23-Apr-18 A | 0 | 0 | 100%
S261100 | Trigger Design, Layout Custom LL1 - Prepare & Send Solicitation | 29 | 06-Apr-18 A | 17-May-18 A | 0 | 0 | 100%
S115000 | Design TPC v1a Module GEMs | 4 | 09-Apr-18 A | 13-Apr-18 A | 0 | 0 | 100%
S114800 | Procure TPC v1a Module Padplane Labor | 19 | 09-Apr-18 A | 04-May-18 A | 0 | 0 | 100%
S114900 | Procure TPC v1a Module Padplane M&S | 19 | 09-Apr-18 A | 04-May-18 A | 0 | 0 | 100%
S265600 | GL1 Design: Write design specifications | 46 | 11-Apr-18 A | 15-Jun-18 A | 0 | 0 | 100%
S164100 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Provide Requirements to Procurement | 4 | 12-Apr-18 A | 18-Apr-18 A | 0 | 0 | 100%
S163200 | Order screens for EMCal Prepro Sectors 1-12 & 13-64 Blocks - Provide Requirements to Procurement | 38 | 12-Apr-18 A | 06-Jun-18 A | 0 | 0 | 100%
S165000 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Provide Requirements to Procurement | 48 | 12-Apr-18 A | 20-Jun-18 A | 0 | 0 | 100%
S234400 | Review and Write Design Hcal Frontend Electronics Specifications: (6 Modules) | 24 | 15-Apr-18 A | 18-May-18 A | 0 | 0 | 100%
S247000 | Procure 1/2-Crate Digitizer - Parts - Vendor Responses | 10 | 16-Apr-18 A | 30-Apr-18 A | 0 | 0 | 100%
S115100 | Procure TPC v1a Module GEMs Labor | 19 | 16-Apr-18 A | 11-May-18 A | 0 | 0 | 100%
S115200 | Procure TPC v1a Module GEMs M&S | 19 | 16-Apr-18 A | 11-May-18 A | 0 | 0 | 100%
S164200 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Prepare & Send Solicitation | 4 | 19-Apr-18 A | 25-Apr-18 A | 0 | 0 | 100%
S320200 | Procure Outer HCAL Mechanical Structure Components - Vendor purchases raw material | 14 | 19-Apr-18 A | 09-May-18 A | 0 | 0 | 100%
S163300 | Order screens for EMCal Prepro Sectors 1-12 & 13-64 Blocks - Prepare & Send Solicitation | 38 | 19-Apr-18 A | 13-Jun-18 A | 0 | 0 | 100%
S114500 | Assemble TPC v1 Grid | 9 | 20-Apr-18 A | 03-May-18 A | 0 | 0 | 100%
S268800 | Timing System Prototype: develop firmware FY18 | 110 | 24-Apr-18 A | 28-Sep-18 A | 0 | 0 | 100%
S164300 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Vendor Responses | 4 | 26-Apr-18 A | 02-May-18 A | 0 | 0 | 100%
S163400 | Order screens for EMCal Prepro Sectors 1-12 & 13-64 Blocks - Vendor Responses | 38 | 26-Apr-18 A | 20-Jun-18 A | 0 | 0 | 100%
S161800 | Procurement Readiness Review - EMCal - Scintillating FIbers (LLP) | 0 | 30-Apr-18 A | 30-Apr-18 A | 0 | 0 | 100%
S265501 | Preliminary Design Review - DAQ Global Level-1 | 0 |  | 30-Apr-18 A | 0 | 0 | 100%
S216601 | Preliminary Design Review - EMCal FEE sectors 1-12 | 0 |  | 30-Apr-18 A | 0 | 0 | 100%
S212300 | EMCal/HCal sensors Preproduction - Provide Requirements to Procurement | 33 | 30-Apr-18 A | 15-Jun-18 A | 0 | 0 | 100%
S216700 | Design EMCal SiPM Daughter Board: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S216900 | Design EMCal Preamp: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S217100 | Design EMCal Interface Board: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S217300 | Design Calorimeter Controller: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S217500 | Specify Signal and Power Cables for EMCal: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S217600 | Specify Power System for EMCal: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S216800 | Layout EMCal SiPM Daughter Board: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S217000 | Layout EMCal Preamp: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S217200 | Layout EMCal Interface: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S217400 | Layout Calorimeter Controller: Preproduction [Sector 0] | 51 | 30-Apr-18 A | 12-Jul-18 A | 0 | 0 | 100%
S161900 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Provide Requirements to Procurement | 0 | 01-May-18 A | 01-May-18 A | 0 | 0 | 100%
S247100 | Procure 1/2-Crate Digitizer - Parts - Vendor Selection | 0 | 01-May-18 A | 01-May-18 A | 0 | 0 | 100%
S246500 | Calorimeter Digitizer System Electrical Safety Review | 1 | 01-May-18 A | 02-May-18 A | 0 | 0 | 100%
S180500 | Set up EMCAL test area Labor | 21 | 01-May-18 A | 31-May-18 A | 0 | 0 | 100%
S180600 | Set up EMCAL test area M&S | 21 | 01-May-18 A | 31-May-18 A | 0 | 0 | 100%
S265700 | GL1 Prototype: Select Hardware | 21 | 01-May-18 A | 31-May-18 A | 0 | 0 | 100%
S319800 | Design and procure Outer HCAL acceptance testing tooling Labor | 86 | 01-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S319900 | Design and procure Outer HCAL acceptance testing tooling - M&S | 86 | 01-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S330500 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY18 | 105 | 01-May-18 A | 28-Sep-18 A | 0 | 0 | 100%
S246600 | Calorimeter Digitizer Safety Review Complete | 0 |  | 02-May-18 A | 0 | 0 | 100%
S246701 | Preliminary Design Review - Calorimeter Digitizer 7-crate | 0 |  | 02-May-18 A | 0 | 0 | 100%
S246700 | Review Calorimeter Digitizer Safety Review Report | 12 | 02-May-18 A | 18-May-18 A | 0 | 0 | 100%
S272100 | Procure Prototype Shaper/Disc Electronics - Prepare & Send Solicitation | 20 | 02-May-18 A | 31-May-18 A | 0 | 0 | 100%
S164400 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Vendor Selection | 4 | 03-May-18 A | 09-May-18 A | 0 | 0 | 100%
S247200 | Procure 1/2-Crate Digitizer - Parts - Contract Award(s) | 0 | 07-May-18 A |  | 0 | 0 | 100%
S247300 | Procure 1/2-Crate Digitizer - Boards - Contract Award(s) | 0 | 07-May-18 A |  | 0 | 0 | 100%
S247400 | Procure 1/2-Crate Digitizer - Assembly & Tests - Contract Award(s) | 0 | 07-May-18 A |  | 0 | 0 | 100%
OBLG247310 | Procure 1/2-Crate Digitizer - Boards - Obligation | 0 | 07-May-18 A | 07-May-18 A | 0 | 0 | 100%
OBLG247410 | Procure 1/2-Crate Digitizer - Assembly & Tests - Obligation | 0 | 07-May-18 A | 07-May-18 A | 0 | 0 | 100%
OBLG247210 | Procure 1/2-Crate Digitizer - Parts - Obligation | 0 | 07-May-18 A | 07-May-18 A | 0 | 0 | 100%
S162000 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Prepare & Send Solicitation | 0 | 08-May-18 A | 08-May-18 A | 0 | 0 | 100%
S162100 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Vendor Responses | 0 | 08-May-18 A | 08-May-18 A | 0 | 0 | 100%
S320300 | Procure Outer HCAL Mechanical Structure Components - Payment for purchases raw material | 0 | 10-May-18 A | 10-May-18 A | 0 | 0 | 100%
S201300 | Procure Outer HCAL Scint. Tiles for Preproduction - Provide Requirements to Procurement | 35 | 10-May-18 A | 29-Jun-18 A | 0 | 0 | 100%
S203900 | Design Revision of Outer HCAL Splice Plates (Dog bones) | 41 | 10-May-18 A | 10-Jul-18 A | 0 | 0 | 100%
S115300 | Test TPC v1a Module GEMS | 4 | 14-May-18 A | 18-May-18 A | 0 | 0 | 100%
S115400 | Frame TPC v1a Module GEMs | 4 | 14-May-18 A | 18-May-18 A | 0 | 0 | 100%
S320400 | Procure Outer HCAL Mechanical Structure Components - Lead Time | 86 | 14-May-18 A | 14-Sep-18 A | 0 | 0 | 100%
S234401 | Preliminary Design Review - HCal FEE Sectors 1-6 | 0 |  | 18-May-18 A | 0 | 0 | 100%
S261200 | Trigger Design, Layout Custom LL1 - Vendor Responses | 9 | 18-May-18 A | 01-Jun-18 A | 0 | 0 | 100%
S162200 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Vendor Selection | 0 | 21-May-18 A | 21-May-18 A | 0 | 0 | 100%
S234600 | Design HCal SiPM Board: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S234800 | Design HCal Preamp: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S235000 | Design HCal LED Driver Board: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S235200 | Design HCal Interface Board: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S235400 | Design HCal Backplane: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S235600 | Specify HCal Signal and Power Cables: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S235700 | Design HCal power system: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S234700 | Layout HCal SiPM Board: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S234900 | Layout HCal Preamp: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S235300 | Layout HCal Interface Board: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S235100 | Layout HCal LED Driver Board: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S235500 | Layout HCal Backplane: (6 Modules) | 72 | 21-May-18 A | 31-Aug-18 A | 0 | 0 | 100%
S189500 | Analyze test beam results from v2.1 prototype FY18 | 90 | 22-May-18 A | 28-Sep-18 A | 0 | 0 | 100%
S162300 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Contract Award 1st batch | 0 | 23-May-18 A |  | 0 | 0 | 100%
S162400 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Contract Award 2nd batch FY18 | 0 | 23-May-18 A |  | 0 | 0 | 100%
S162500 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Contract Award 3rd batch FY19 | 0 | 23-May-18 A |  | 0 | 0 | 100%
S162600 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Contract Award 4th batch | 0 | 23-May-18 A |  | 0 | 0 | 100%
OBLG162510 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Obligation 3rd batch FY19 | 0 | 23-May-18 A | 23-May-18 A | 0 | 0 | 100%
OBLG162610 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Obligation 4th batch | 0 | 23-May-18 A | 23-May-18 A | 0 | 0 | 100%
S100400 | CD-1 Review | 2 | 23-May-18 A | 25-May-18 A | 0 | 0 | 100%
S100700 | Start PD-2/3 Review preparation | 89 | 23-May-18 A | 28-Sep-18 A | 0 | 0 | 100%
S182600 | Procure light guides for preproduction prototype sector 0 Labor | 89 | 23-May-18 A | 28-Sep-18 A | 0 | 0 | 100%
S183000 | Procure mechanical parts for modules for preproduction prototype sector 0 Labor FY18 | 89 | 23-May-18 A | 28-Sep-18 A | 0 | 0 | 100%
S182700 | Procure light guides for preproduction prototype sector 0 M&S | 89 | 23-May-18 A | 28-Sep-18 A | 0 | 0 | 100%
S182800 | Procure mechanical parts for modules for preproduction prototype sector 0 M&S FY18 | 89 | 23-May-18 A | 28-Sep-18 A | 0 | 0 | 100%
S359500 | Design TPC Integration/Installation Tooling/Fixtures FY18 | 88 | 24-May-18 A | 28-Sep-18 A | 0 | 0 | 100%
S115500 | Test TPC v1a Module Framed GEMs | 4 | 29-May-18 A | 04-Jun-18 A | 0 | 0 | 100%
S137800 | SAMPA chip 80 nsec development - Provide Requirements to Procurement | 28 | 29-May-18 A | 09-Jul-18 A | 0 | 0 | 100%
S268301 | Preliminary Design Review - DAQ Timing System | 0 |  | 31-May-18 A | 0 | 0 | 100%
S106700 | TPC v1 End Cap Conceptual Design Review | 0 | 01-Jun-18 A | 01-Jun-18 A | 0 | 0 | 100%
S180700 | Safety Review of Assembly and Test Areas | 0 | 01-Jun-18 A | 01-Jun-18 A | 0 | 0 | 100%
S247500 | Procure 1/2-Crate Digitizer - Parts - Leadtime - FY18 | 83 | 01-Jun-18 A | 28-Sep-18 A | 0 | 0 | 100%
S247800 | Procure 1/2-Crate Digitizer - Boards - Contract/PO - Leadtime FY18 | 83 | 01-Jun-18 A | 28-Sep-18 A | 0 | 0 | 100%
S344500 | Create Subsystem Outline/Interface Drawings | 83 | 01-Jun-18 A | 28-Sep-18 A | 0 | 0 | 100%
S261300 | Trigger Design, Layout Custom LL1 - Vendor Selection | 39 | 04-Jun-18 A | 30-Jul-18 A | 0 | 0 | 100%
S115600 | Assemble TPC v1a Module Prototype | 4 | 05-Jun-18 A | 11-Jun-18 A | 0 | 0 | 100%
S106800 | TPC v1 End Cap Production Readiness Review | 0 | 06-Jun-18 A | 06-Jun-18 A | 0 | 0 | 100%
S106900 | Procure TPC v1 End Cap - Provide Requirements to Procurement | 4 | 07-Jun-18 A | 13-Jun-18 A | 0 | 0 | 100%
S253900 | DAQ Design: Specify the high-level components | 10 | 11-Jun-18 A | 25-Jun-18 A | 0 | 0 | 100%
S115700 | Test TPC v1a Module Prototype | 17 | 12-Jun-18 A | 06-Jul-18 A | 0 | 0 | 100%
S107000 | Procure TPC v1 End Cap - Prepare & Send Solicitation | 29 | 14-Jun-18 A | 26-Jul-18 A | 0 | 0 | 100%
S272200 | Procure Prototype Shaper/Disc Electronics - Vendor Responses | 63 | 15-Jun-18 A | 14-Sep-18 A | 0 | 0 | 100%
S158300 | Fabricate & test batch No. 1 of 8 batches of 12 blocks for preproduction prototype Sector 0 | 63 | 21-Jun-18 A | 20-Sep-18 A | 0 | 0 | 100%
S165100 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Prepare & Send Solicitation | 4 | 25-Jun-18 A | 29-Jun-18 A | 0 | 0 | 100%
S107100 | Procure TPC v1 End Cap - Vendor Responses | 50 | 25-Jun-18 A | 05-Sep-18 A | 0 | 0 | 100%
S138200 | SAMPA chip 80 nsec development - Contract Award(s) - Report feasability of 80ns/20MSPS mod | 0 | 02-Jul-18 A |  | 0 | 0 | 100%
S138300 | SAMPA chip 80 nsec development - Contract Award(s) - Design at Layout level of new circuits | 0 | 02-Jul-18 A |  | 0 | 0 | 100%
OBLG138210 | SAMPA chip 80 nsec development - Obligation - MPW to Test Design Changes | 0 | 02-Jul-18 A | 02-Jul-18 A | 0 | 0 | 100%
S138310 | SAMPA chip 80 nsec development - Contract Award(s) - Layout finalization for MPW and submission | 0 | 02-Jul-18 A |  | 0 | 0 | 100%
S207700 | Procure Outer HCAL Scintillating Tiles (Prod) - Provide Requirements to Procurement | 0 | 02-Jul-18 A | 02-Jul-18 A | 0 | 0 | 100%
S165200 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Vendor Responses | 3 | 02-Jul-18 A | 06-Jul-18 A | 0 | 0 | 100%
S201400 | Procure Outer HCAL Scint. Tiles for Preproduction - Prepare & Send Solicitation | 18 | 02-Jul-18 A | 27-Jul-18 A | 0 | 0 | 100%
S254000 | Final Design Review - DAQ Design | 29 | 02-Jul-18 A | 13-Aug-18 A | 0 | 0 | 100%
S268600 | Timing System Prototype: Procure hardware Labor | 31 | 02-Jul-18 A | 15-Aug-18 A | 0 | 0 | 100%
S268700 | Timing System Prototype: Procure hardware M&S | 31 | 02-Jul-18 A | 15-Aug-18 A | 0 | 0 | 100%
S197800 | Design Inner HCAL Support Structure | 39 | 02-Jul-18 A | 27-Aug-18 A | 0 | 0 | 100%
S212400 | EMCal/HCal sensors Preproduction - Prepare & Send Solicitation | 44 | 02-Jul-18 A | 04-Sep-18 A | 0 | 0 | 100%
S198300 | Design Inner HCAL Support Rings FY18 | 62 | 02-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S265800 | GL1 Prototype: Procure hardware Labor | 62 | 02-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S266000 | GL1 Prototype: develop firmware FY18 | 62 | 02-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S265900 | GL1 Prototype: Procure hardware M&S | 62 | 02-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S266200 | GL1 Prototype: Design I/O Transition Module FY18 | 62 | 02-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S162700 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Lead Time | 29 | 03-Jul-18 A | 14-Aug-18 A | 0 | 0 | 100%
S319100 | Procure Outer HCAL Lifting Fixture and Supports - Delivery Acceptance | 51 | 03-Jul-18 A | 14-Sep-18 A | 0 | 0 | 100%
S137801 | Preliminary Design Review - SAMPA chip 80 nsec | 0 |  | 09-Jul-18 A | 0 | 0 | 100%
S115800 | Design TPC v1b Module Padplane | 58 | 09-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S269000 | Timing System Prototype: Design I/O Transition Module FY18 | 58 | 09-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S203901 | Preliminary Design Review - Outer HCAL Splice Plates (Dog bones) | 0 |  | 10-Jul-18 A | 0 | 0 | 100%
S137900 | SAMPA chip 80 nsec development - Prepare & Send Solicitation | 9 | 10-Jul-18 A | 23-Jul-18 A | 0 | 0 | 100%
S207800 | Procure Outer HCAL Scintillating Tiles (Prod) - Prepare & Send Solicitation | 13 | 10-Jul-18 A | 27-Jul-18 A | 0 | 0 | 100%
S204000 | Internal Review of Outer HCAL Splice Plates (Dog bones) | 1 | 11-Jul-18 A | 12-Jul-18 A | 0 | 0 | 100%
S217700 | Final Design Review, Safety Review - EMCal Preproduction Electronics [Sector 0] | 4 | 13-Jul-18 A | 19-Jul-18 A | 0 | 0 | 100%
S204100 | Address Issues from Internal Review of Outer HCAL Splice Plates | 9 | 13-Jul-18 A | 26-Jul-18 A | 0 | 0 | 100%
S165300 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Vendor Selection | 4 | 16-Jul-18 A | 20-Jul-18 A | 0 | 0 | 100%
S272300 | Procure Prototype Shaper/Disc Electronics - Vendor Selection | 52 | 16-Jul-18 A | 27-Sep-18 A | 0 | 0 | 100%
S190000 | Preliminary Design Review - EMCal Sectors 1-12 | 0 | 17-Jul-18 A | 17-Jul-18 A | 0 | 0 | 100%
S190100 | Preliminary Design Review - EMCal Sectors 1-12 | 0 |  | 17-Jul-18 A | 0 | 0 | 100%
S190400 | Procure mechanical parts for preproduction prototype Sector 0 Labor FY18 | 51 | 18-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S190600 | Procure parts for cooling system for preproduction prototype Sector 0 Labor FY18 | 51 | 18-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S190200 | Procure mechanical parts for preproduction prototype Sector 0 M&S FY18 | 51 | 18-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S190800 | Procure parts for cooling system for preproduction prototype Sector 0 M&S FY18 | 51 | 18-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S217800 | Completed: Final Design Review, Safety Review - EMCal Preproduction Electronics [Sector 0] | 0 |  | 19-Jul-18 A | 0 | 0 | 100%
S107200 | Procure TPC v1 End Cap - Vendor Selection | 34 | 19-Jul-18 A | 06-Sep-18 A | 0 | 0 | 100%
S217900 | Review Safety and Design Review Report: EMCal Preproduction Electronics [Sector 0] | 4 | 20-Jul-18 A | 26-Jul-18 A | 0 | 0 | 100%
S165400 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Contract Award(s) | 0 | 23-Jul-18 A |  | 0 | 0 | 100%
OBLG165410 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Obligation | 0 | 23-Jul-18 A | 23-Jul-18 A | 0 | 0 | 100%
S116100 | Design TPC v1b Module GEMs | 40 | 23-Jul-18 A | 18-Sep-18 A | 0 | 0 | 100%
S165500 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Contract/PO - Leadtime FY18 | 48 | 23-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S138000 | SAMPA chip 80 nsec development - Vendor Responses | 7 | 24-Jul-18 A | 02-Aug-18 A | 0 | 0 | 100%
S204200 | Outer HCAL Splice Plate Design Complete | 0 |  | 26-Jul-18 A | 0 | 0 | 100%
S218000 | Procure Components for EMCal SiPM Boards: Preproduction [Sector 0] Labor | 61 | 27-Jul-18 A | 24-Oct-18 A | 0 | 0 | 100%
S218100 | Procure Components for EMCal SiPM Boards: Preproduction [Sector 0] M&S | 61 | 27-Jul-18 A | 24-Oct-18 A | 0 | 0 | 100%
S207900 | Procure Outer HCAL Scintillating Tiles (Prod) - Vendor Responses | 9 | 30-Jul-18 A | 10-Aug-18 A | 0 | 0 | 100%
S201500 | Procure Outer HCAL Scint. Tiles for Preproduction - Vendor Responses | 9 | 30-Jul-18 A | 10-Aug-18 A | 0 | 0 | 100%
S254400 | DAQ Prototype: Software development - Calorimeters & TPC FY18 | 42 | 31-Jul-18 A | 28-Sep-18 A | 0 | 0 | 100%
S138100 | SAMPA chip 80 nsec development - Vendor Selection | 4 | 03-Aug-18 A | 09-Aug-18 A | 0 | 0 | 100%
S208000 | Procure Outer HCAL Scintillating Tiles (Prod) - Vendor Selection | 3 | 13-Aug-18 A | 16-Aug-18 A | 0 | 0 | 100%
S201600 | Procure Outer HCAL Scint. Tiles for Preproduction - Vendor Selection | 3 | 13-Aug-18 A | 16-Aug-18 A | 0 | 0 | 100%
S254100 | DAQ Prototype: Select which hardware to re-use: computers, a network switch, and storage for the prototype, as specified | 9 | 14-Aug-18 A | 27-Aug-18 A | 0 | 0 | 100%
S162800 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Delivery acceptance 1st batch 1-6 of 20 | 9 | 15-Aug-18 A | 28-Aug-18 A | 0 | 0 | 100%
S266400 | GL1 Prototype: setup hardware FY18 | 31 | 15-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S249700 | Procure EMCAL 7-Crate Digitizer - Provide Requirements to Procurement FY18 | 31 | 15-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S249900 | Procure EMCAL 7-Crate Digitizer - Prepare & Send Solicitation FY18 | 31 | 15-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S250100 | Procure EMCAL 7-Crate Digitizer - Vendor Responses FY18 | 31 | 15-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S212500 | EMCal/HCal sensors Preproduction - Vendor Responses & Selection | 14 | 16-Aug-18 A | 06-Sep-18 A | 0 | 0 | 100%
S269200 | Timing System Prototype: setup hardware FY18 | 30 | 16-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S100500 | Approve Cost Range and Long lead Procurement CD-1/3A | 0 |  | 17-Aug-18 A | 0 | 0 | 100%
S201700 | Procure Outer HCAL Scint. Tiles for Preproduction - Contract Award(s) Batch 1 | 0 | 17-Aug-18 A |  | 0 | 0 | 100%
S201800 | Procure Outer HCAL Scint. Tiles for Preproduction - Contract Award(s) Batch 2 | 0 | 17-Aug-18 A |  | 0 | 0 | 100%
S201900 | Procure Outer HCAL Scint. Tiles for Preproduction - Contract Award(s) Batch 3 | 0 | 17-Aug-18 A |  | 0 | 0 | 100%
OBLG201710 | Procure Outer HCAL Scint. Tiles for Preproduction - Obligation Batch 1 | 0 | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 100%
OBLG201810 | Procure Outer HCAL Scint. Tiles for Preproduction - Obligation Batch 2 | 0 | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 100%
OBLG201910 | Procure Outer HCAL Scint. Tiles for Preproduction - Obligation Batch 3 | 0 | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 100%
S202000 | Procure Outer HCAL Scint. Tiles for Preproduction - Contract lead time FY18 | 29 | 17-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S158400 | Fabricate & test batch No. 2 of 8 batches of 12 blocks for preproduction prototype Sector 0 FY18 | 26 | 22-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S197801 | Preliminary Design Review - Inner HCAL Support Structure | 0 |  | 27-Aug-18 A | 0 | 0 | 100%
S160900 | Final Design Review - EMCal Blocks, Procurement Readiness Review - EMCAL - Tungsten Powder (LLP) | 0 | 28-Aug-18 A |  | 0 | 0 | 100%
S163600 | Order screens for EMCal Prepro Sectors 1-12 & 13-64 Blocks - Contract Award | 0 | 28-Aug-18 A |  | 0 | 0 | 100%
OBLG163610 | Order screens for EMCal Prepro Sectors 1-12 Blocks - Obligation | 0 | 28-Aug-18 A | 28-Aug-18 A | 0 | 0 | 100%
S254200 | DAQ Prototype: Setup and install the various operating systems FY18 | 22 | 28-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S162900 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Delivery acceptance 2nd batch 7-12 of 20 FY18 | 21 | 29-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S163800 | Order screens for EMCal Prepro Sectors 1-12 & 13-64 Blocks - Lead Time FY18 | 21 | 29-Aug-18 A | 28-Sep-18 A | 0 | 0 | 100%
S161000 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Provide Requirements to Procurement | 0 | 31-Aug-18 A | 31-Aug-18 A | 0 | 0 | 100%
S144600 | Procure TPC DAM Felix 2.0 Boards Evaluation - Delivery Acceptance | 1 | 01-Sep-18 A | 05-Sep-18 A | 0 | 0 | 100%
S161100 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Prepare & Send Solicitation | 0 | 04-Sep-18 A | 04-Sep-18 A | 0 | 0 | 100%
S161300 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Vendor Selection | 0 | 05-Sep-18 A | 05-Sep-18 A | 0 | 0 | 100%
S161200 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Vendor Responses | 0 | 05-Sep-18 A | 05-Sep-18 A | 0 | 0 | 100%
S144700 | Develop TPC DAM FPGA Algorithm - FY18 | 16 | 06-Sep-18 A | 28-Sep-18 A | 0 | 0 | 100%
S218600 | Fabricate EMCal Preamp Boards: Preproduction [Sector 0] M&S FY18 | 14 | 10-Sep-18 A | 28-Sep-18 A | 0 | 0 | 100%
S218400 | Fabricate EMCal Preamp Boards: Preproduction [Sector 0] Labor FY18 | 14 | 10-Sep-18 A | 28-Sep-18 A | 0 | 0 | 100%
S320000 | Outer HCAL Sector Mechanical Structure First Article Acceptance Testing | 20 | 10-Sep-18 A | 08-Oct-18 A | 0 | 0 | 100%
S107300 | Procure TPC v1 End Cap - Contract Award(s) Phase 1 | 0 | 11-Sep-18 A |  | 0 | 0 | 100%
S107400 | Procure TPC v1 End Cap - Contract Award(s) Phase 2 | 0 | 11-Sep-18 A |  | 0 | 0 | 100%
S212600 | EMCal/HCal sensors Preproduction - 23K Units - Contract Award | 0 | 12-Sep-18 A |  | 0 | 0 | 100%
S212700 | EMCal/HCal sensors Production - 77K Units - Contract Award | 0 | 12-Sep-18 A |  | 0 | 0 | 100%
S212800 | EMCal/HCal sensors Preproduction - Vendor Leadtime FY18 | 11 | 13-Sep-18 A | 28-Sep-18 A | 0 | 0 | 100%
S320500 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 1) | 5 | 21-Sep-18 A | 28-Sep-18 A | 0 | 0 | 100%
S135301 | Preliminary Design Review - TPC FEE | 0 |  | 28-Sep-18 A | 0 | 0 | 100%
S189600 | Completion of v2.1 prototype | 0 |  | 28-Sep-18 A | 0 | 0 | 100%
S272400 | Procure Prototype Shaper/Disc Electronics - Contract Award(s) | 0 | 28-Sep-18 A |  | 0 | 0 | 100%
OBLG272410 | Procure Prototype Shaper/Disc Electronics - Obligation | 0 | 28-Sep-18 A | 28-Sep-18 A | 0 | 0 | 100%
S261400 | Trigger Design, Layout Custom LL1 - Contract Award(s) | 0 | 28-Sep-18 A |  | 0 | 0 | 100%
S100750 | Prepare for PD-2/3 Review | 162 | 28-Sep-18 A | 24-May-19 A | 0 | 0 | 100%
S164500 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Contract Award | 0 | 01-Oct-18 A |  | 0 | 0 | 100%
OBLG164510 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Obligation | 0 | 01-Oct-18 A | 01-Oct-18 A | 0 | 0 | 100%
S163500 | Order screens for EMCal Prepro Sectors 1-12 & 13-64 Blocks - Vendor Selection | 4 | 01-Oct-18 A | 05-Oct-18 A | 0 | 0 | 100%
S169600 | Procure EMCAL W Powder for Final Blocks - Provide Requirements to Procurement | 4 | 01-Oct-18 A | 05-Oct-18 A | 0 | 0 | 100%
S170400 | Procure EMCAL Fibers for final Blocks - Provide Requirements to Procurement | 4 | 01-Oct-18 A | 05-Oct-18 A | 0 | 0 | 100%
S208600 | Procure Contracted Labor Georgia State Univ. (GSU) - Provide Requirements to Procurement | 4 | 01-Oct-18 A | 05-Oct-18 A | 0 | 0 | 100%
S163000 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Delivery acceptance 3rd batch 13-17 of 20 FY19 | 8 | 01-Oct-18 A | 12-Oct-18 A | 0 | 0 | 100%
S163900 | Order screens for EMCal Prepro Sectors 1-12 & 13-64 Blocks - Lead Time FY19 | 9 | 01-Oct-18 A | 15-Oct-18 A | 0 | 0 | 100%
S115900 | Procure TPC v1b Module Padplane Labor | 19 | 01-Oct-18 A | 29-Oct-18 A | 0 | 0 | 100%
S116000 | Procure TPC v1b Module Padplane M&S | 19 | 01-Oct-18 A | 29-Oct-18 A | 0 | 0 | 100%
S164900 | Order parts and fabricate molds for EMCal Prepro Sectors 1-12 Blocks Purchased Services | 19 | 01-Oct-18 A | 29-Oct-18 A | 0 | 0 | 100%
S164800 | Order parts and fabricate molds for EMCal Prepro Sectors 1-12 Blocks M&S | 19 | 01-Oct-18 A | 29-Oct-18 A | 0 | 0 | 100%
S164600 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Lead Time | 19 | 01-Oct-18 A | 29-Oct-18 A | 0 | 0 | 100%
S183100 | Procure mechanical parts for modules for preproduction prototype sector 0 Labor FY19 | 21 | 01-Oct-18 A | 31-Oct-18 A | 0 | 0 | 100%
S182900 | Procure mechanical parts for modules for preproduction prototype sector 0 M&S FY19 | 21 | 01-Oct-18 A | 31-Oct-18 A | 0 | 0 | 100%
S122000 | Prepare TPC R1 Factory Clean Facility Labor | 25 | 01-Oct-18 A | 06-Nov-18 A | 0 | 0 | 100%
S122100 | Prepare TPC R1 Factory Clean Facility M&S | 25 | 01-Oct-18 A | 06-Nov-18 A | 0 | 0 | 100%
S122005 | Prepare TPC R1 Factory Clean Facility Labor - Contributed Labor | 25 | 01-Oct-18 A | 06-Nov-18 A | 0 | 0 | 100%
S158500 | Fabricate & test batch No. 2 of 8 batches of 12 blocks for preproduction prototype Sector 0 FY19 | 32 | 01-Oct-18 A | 16-Nov-18 A | 0 | 0 | 100%
S116200 | Procure TPC v1b Module GEMs Labor | 40 | 01-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S116300 | Procure TPC v1b Module GEMs M&S | 40 | 01-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S108400 | Procure TPC Assembly Fixture Labor | 40 | 01-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S108500 | Procure TPC Assembly Fixture M&S | 40 | 01-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S126200 | Prepare TPC R2 Factory Clean Facility Labor | 40 | 01-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S126300 | Prepare TPC R2 Factory Clean Facility M&S | 40 | 01-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S269300 | Timing System Prototype: setup hardware FY19 | 44 | 01-Oct-18 A | 06-Dec-18 A | 0 | 0 | 100%
S269310 | Timing System Prototype: setup hardware FY19 | 44 | 01-Oct-18 A | 06-Dec-18 A | 0 | 0 | 100%
S105600 | Assemble TPC v1 Outer Field Cage FY19 | 59 | 01-Oct-18 A | 28-Dec-18 A | 0 | 0 | 100%
S254300 | DAQ Prototype: Setup and install the various operating systems FY19 | 101 | 01-Oct-18 A | 01-Mar-19 A | 0 | 0 | 100%
S107500 | Procure TPC v1 End Cap - Contract/PO - Leadtime | 102 | 01-Oct-18 A | 04-Mar-19 A | 0 | 0 | 100%
S202100 | Procure Outer HCAL Scint. Tiles for Preproduction - Contract lead time FY19 | 105 | 01-Oct-18 A | 07-Mar-19 A | 0 | 0 | 100%
S138400 | SAMPA chip 80 nsec development - Leadtime - Report feasability of 80ns/20MSPS mod | 109 | 01-Oct-18 A | 13-Mar-19 A | 0 | 0 | 100%
S165600 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Contract/PO - Leadtime FY19 | 111 | 01-Oct-18 A | 15-Mar-19 A | 0 | 0 | 100%
S129800 | Prepare TPC R3a Factory Clean Facility Labor | 112 | 01-Oct-18 A | 15-Mar-19 A | 0 | 0 | 100%
S129900 | Prepare TPC R3a Factory Clean Facility M&S | 112 | 01-Oct-18 A | 15-Mar-19 A | 0 | 0 | 100%
S130200 | Prepare TPC R3b Factory Clean Facility Labor | 112 | 01-Oct-18 A | 15-Mar-19 A | 0 | 0 | 100%
S130300 | Prepare TPC R3b Factory Clean Facility M&S | 112 | 01-Oct-18 A | 15-Mar-19 A | 0 | 0 | 100%
S266500 | GL1 Prototype: setup hardware FY19 | 115 | 01-Oct-18 A | 20-Mar-19 A | 0 | 0 | 100%
S219300 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Preproduction [Sector 0] M&S | 133 | 01-Oct-18 A | 16-Apr-19 A | 0 | 0 | 100%
S219500 | Procure EMCal External Signal and Power Cables, and Power Systems: Preproduction [Sector 0] M&S | 133 | 01-Oct-18 A | 16-Apr-19 A | 0 | 0 | 100%
S135400 | Assemble and test TPC FEE prototype v1a Labor | 161 | 01-Oct-18 A | 24-May-19 A | 0 | 0 | 100%
S135500 | Assemble and test TPC FEE prototype v1a M&S | 161 | 01-Oct-18 A | 24-May-19 A | 0 | 0 | 100%
S1001479 | Actuals - NonLabor - sPHENIX Magnet FY19 M8 16720 | 164 | 01-Oct-18 A | 30-May-19 A | 1343 | 1343 | 100%
S102605 | Actuals - Labor - A - MIE - sPHENIX Project Management FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 11566 | 11566 | 100%
S102606 | Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 328902 | 328902 | 100%
S102610 | Actuals - Labor - B - BNL Contributed Labor - sPHENIX Project Management FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 1056792 | 1056792 | 100%
S1001839 | Actuals - Nonlabor - A - MIE - sPHENIX Project Management FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 24834 | 24834 | 100%
S104000 | Travel FY19 | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S103700 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S102900 | Mgmt labor - A - MIE, Phase 1 - FY19 | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S103710 | Mgmt labor - B - BNL Contributed Labor - FY19 - CA-D Resource(s) | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S102910 | Mgmt labor - A - MIE, Phase 2 - FY19 | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S104510 | Actuals - Labor - sPHENIX TPC FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 370642 | 370642 | 100%
S1000759 | Actuals - NonLabor - sPHENIX TPC FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 431189 | 431189 | 100%
S1000799 | Actuals - NonLabor - sPHENIX TPC FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 155367 | 155367 | 100%
S122200 | Prepare TPC R1 Factory Tooling Labor | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S122300 | Prepare TPC R1 Factory Tooling M&S | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S126500 | Prepare TPC R2 Factory Tooling M&S | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S130100 | Prepare TPC R3a Factory Tooling M&S | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S130500 | Prepare TPC R3b Factory Tooling M&S | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S156310 | Actuals - Labor - sPHENIX EMCal FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 390503 | 390503 | 100%
S156510 | Actuals - Nonlabor - sPHENIX EMCal FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 699612 | 699612 | 100%
S1001879 | Actuals - Nonlabor - sPHENIX EMCal FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 80812 | 80812 | 100%
S197510 | Actuals - Labor - sPHENIX HCal FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 262446 | 262446 | 100%
S197710 | Actuals - Nonlabor - sPHENIX HCal FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 458016 | 458016 | 100%
S1001919 | Actuals - Nonlabor - sPHENIX HCal FY19M8 | 165 | 01-Oct-18 A | 31-May-19 A | 18548 | 18548 | 100%
S1000999 | Actuals - Labor - sPHENIX MinBias Trigger FY19 M8 | 165 | 01-Oct-18 A | 31-May-19 A | 50490 | 50490 | 100%
S1001039 | Actuals - Nonlabor - sPHENIX MinBias Trigger FY19 M8 | 165 | 01-Oct-18 A | 31-May-19 A | 21505 | 21505 | 100%
S1000919 | Actuals - Labor - sPHENIX DAQ&Trigger FY19 M8 | 165 | 01-Oct-18 A | 31-May-19 A | 273849 | 273849 | 100%
S1000959 | Actuals - Nonlabor - sPHENIX DAQ&Trigger FY18 | 165 | 01-Oct-18 A | 31-May-19 A | 23191 | 23191 | 100%
S268900 | Timing System Prototype: develop firmware FY19 | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S268910 | Timing System Prototype: develop firmware FY19 | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S254500 | DAQ Prototype: Software development - Calorimeters & TPC FY19 | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S266100 | GL1 Prototype: develop firmware FY19 | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S1000839 | Actuals - Labor - sPHENIX Calorimeter Electronics FY19 M8 | 165 | 01-Oct-18 A | 31-May-19 A | 421099 | 421099 | 100%
S1000879 | Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | 165 | 01-Oct-18 A | 31-May-19 A | 383105 | 383105 | 100%
S1001959 | Actuals - Nonlabor - sPHENIX Calorimeter Electronics FY19 M8 | 165 | 01-Oct-18 A | 31-May-19 A | 64370 | 64370 | 100%
S248100 | Procure 1/2-Crate Digitizer - Contract/PO - Leadtime for Assembly & Tests | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S219200 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Preproduction [Sector 0] Labor | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S219400 | Procure EMCal External Signal and Power Cables, and Power Systems: Preproduction [Sector 0] Labor | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S1001439 | Actuals - Labor - sPHENIX Magnet FY19 M8 16720 | 165 | 01-Oct-18 A | 31-May-19 A | 6430 | 6430 | 100%
S1001319 | Actuals - Labor - sPHENIX Magnet FY19 M8 16718 | 165 | 01-Oct-18 A | 31-May-19 A | 267683 | 267683 | 100%
S1001359 | Actuals - NonLabor - sPHENIX Magnet FY19 M8 16718 | 165 | 01-Oct-18 A | 31-May-19 A | 14657 | 14657 | 100%
S1001239 | Actuals - Labor - sPHENIX Magnet FY19 M8 16717 | 165 | 01-Oct-18 A | 31-May-19 A | 508 | 508 | 100%
S1001279 | Actuals - NonLabor - sPHENIX Magnet FY19 M8 16717 | 165 | 01-Oct-18 A | 31-May-19 A | 3152 | 3152 | 100%
S1001399 | Actuals - Labor - sPHENIX Magnet FY19 M8 16719 | 165 | 01-Oct-18 A | 31-May-19 A | 11595 | 11595 | 100%
S1001119 | Actuals - Labor - sPHENIX Integration and Installation FY19 M8 16727 | 165 | 01-Oct-18 A | 31-May-19 A | 64551 | 64551 | 100%
S1001159 | Actuals - Labor - sPHENIX Integration and Installation FY19 M8 16728 | 165 | 01-Oct-18 A | 31-May-19 A | 2281 | 2281 | 100%
S359600 | Design TPC Integration/Installation Tooling/Fixtures FY21 | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S1001679 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16724 | 165 | 01-Oct-18 A | 31-May-19 A | 6015 | 41837 | 100%
S1001639 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16723 | 165 | 01-Oct-18 A | 31-May-19 A | 52365 | 52365 | 100%
S1001799 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16729 | 165 | 01-Oct-18 A | 31-May-19 A | 190783 | 190783 | 100%
S1001759 | Actuals - NonLabor - sPHENIX Infrastructure FY19 M8 16731 | 165 | 01-Oct-18 A | 31-May-19 A | 5765 | 5765 | 100%
S1001559 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16722 | 165 | 01-Oct-18 A | 31-May-19 A | 115388 | 115388 | 100%
S1001599 | Actuals - NonLabor - sPHENIX Infrastructure FY19 M8 16722 | 165 | 01-Oct-18 A | 31-May-19 A | 3867627 | 3867626 | 100%
S274500 | 2019 Magnet Project Management | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S275100 | 2019 Cryo L3 Project Management | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S275600 | 2019 PS & Quench Protection L3 Project Management | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S1001199 | Actuals - Labor - sPHENIX Magnet FY19 M8 16716 | 165 | 01-Oct-18 A | 31-May-19 A | 94443 | 94443 | 100%
S277900 | 2019 Integration & Installation Project Management | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S1001079 | Actuals - Labor - sPHENIX Integration and Installation FY19 M8 16726 | 165 | 01-Oct-18 A | 31-May-19 A | 28728 | 28728 | 100%
S276100 | 2019 Infrastructure Project Management | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S276700 | 2019 Facility Support Systems L3 Project Management | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S277300 | 2019 Detector Support Systems L3 Project Management | 165 | 01-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S1001519 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16721 | 165 | 01-Oct-18 A | 31-May-19 A | 59221 | 59221 | 100%
S1001719 | Actuals - Labor - sPHENIX Infrastructure FY19 M8 16725 | 165 | 01-Oct-18 A | 31-May-19 A | 19969 | 19969 | 100%
S144800 | Procure TPC DAM Felix 2.0 Boards Throughput - Prepare & Send Solicitation | 166 | 01-Oct-18 A | 03-Jun-19 A | 0 | 0 | 100%
S261500 | Trigger Design, Layout Custom LL1 - Contract/PO - Leadtime | 167 | 01-Oct-18 A | 03-Jun-19 A | 0 | 0 | 100%
S272500 | Procure Prototype Shaper/Disc Electronics - Contract/PO - Leadtime | 186 | 01-Oct-18 A | 28-Jun-19 A | 0 | 0 | 100%
S122205 | Prepare TPC R1 Factory Tooling Labor - Contributed Labor | 207 | 01-Oct-18 A | 31-Jul-19 A | 0 | 0 | 100%
S126400 | Prepare TPC R2 Factory Tooling Labor | 207 | 01-Oct-18 A | 31-Jul-19 A | 0 | 0 | 100%
S130000 | Prepare TPC R3a Factory Tooling Labor | 207 | 01-Oct-18 A | 31-Jul-19 A | 0 | 0 | 100%
S130400 | Prepare TPC R3b Factory Tooling Labor | 229 | 01-Oct-18 A | 30-Aug-19 A | 0 | 0 | 100%
S108200 | Procure TPC v1 Central Membrane Parts Labor FY19 | 270 | 01-Oct-18 A | 30-Oct-19 A | 0 | 0 | 100%
S106100 | Assemble TPC v1 Inner Field Cage FY19 | 290 | 01-Oct-18 A | 29-Nov-19 A | 0 | 0 | 100%
S159200 | Ship batch No. 1 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - Purchased Services | 4 | 02-Oct-18 A | 09-Oct-18 A | 0 | 0 | 100%
S159300 | Ship batch No. 1 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - M&S | 4 | 02-Oct-18 A | 09-Oct-18 A | 0 | 0 | 100%
S169700 | Procure EMCAL W Powder for Final Blocks - Prepare & Send Solicitation | 3 | 08-Oct-18 A | 12-Oct-18 A | 0 | 0 | 100%
S170500 | Procure EMCAL Fibers for Final Blocks- Prepare & Send Solicitation | 3 | 08-Oct-18 A | 12-Oct-18 A | 0 | 0 | 100%
S161400 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Contract Award | 0 | 09-Oct-18 A |  | 0 | 0 | 100%
OBLG161410 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Obligation | 0 | 09-Oct-18 A | 09-Oct-18 A | 0 | 0 | 100%
S161500 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Lead Time | 8 | 09-Oct-18 A | 19-Oct-18 A | 0 | 0 | 100%
S159400 | Ship batch No. 2 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - Purchased Services | 4 | 15-Oct-18 A | 19-Oct-18 A | 0 | 0 | 100%
S159500 | Ship batch No. 2 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - M&S | 4 | 15-Oct-18 A | 19-Oct-18 A | 0 | 0 | 100%
S170600 | Procure EMCAL Fibers for Final Blocks- Vendor Responses | 4 | 15-Oct-18 A | 19-Oct-18 A | 0 | 0 | 100%
S169800 | Procure EMCAL W Powder for Final Blocks - Vendor Responses | 9 | 15-Oct-18 A | 26-Oct-18 A | 0 | 0 | 100%
S158600 | Fabricate & test batch No. 3 of 8 batches of 12 blocks for preproduction prototype Sector 0 | 23 | 15-Oct-18 A | 16-Nov-18 A | 0 | 0 | 100%
S163100 | Procure EMCAL fibers for Prepro Sectors 1-12 Blocks - Delivery acceptance 4th batch 18-20 of 20 | 26 | 15-Oct-18 A | 21-Nov-18 A | 0 | 0 | 100%
S208700 | Procure Contracted Labor Georgia State Univ. (GSU) - Vendor Selection | 92 | 16-Oct-18 A | 04-Mar-19 A | 0 | 0 | 100%
S202700 | Procure Table for Outer HCAL sector assembly and testing area (Preproduction) - Labor | 111 | 16-Oct-18 A | 28-Mar-19 A | 0 | 0 | 100%
S202900 | Procure Table for Outer HCAL sector assembly and testing area (Preproduction) - M&S | 111 | 16-Oct-18 A | 28-Mar-19 A | 0 | 0 | 100%
S164000 | Order screens for EMCal Prepro Sectors 1-12 & 13-64 Blocks - Delivery acceptance | 118 | 16-Oct-18 A | 09-Apr-19 A | 0 | 0 | 100%
S204300 | Procure Preproduction Outer HCAL Splice Plates - Delivery Acceptance | 147 | 16-Oct-18 A | 20-May-19 A | 0 | 0 | 100%
S235800 | Final Design Review, Production Readiness Review, Safety Review - HCal FEE Sectors 1-6 | 0 | 17-Oct-18 A | 17-Oct-18 A | 0 | 0 | 100%
S235900 | HCal Electronics Safety & Design Review Complete | 0 |  | 17-Oct-18 A | 0 | 0 | 100%
S236000 | Review Hcal Electronics Safety & Design Review Report | 3 | 17-Oct-18 A | 22-Oct-18 A | 0 | 0 | 100%
S107900 | Procure TPC v1 Central Membrane Parts M&S FY19 | 153 | 18-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S161600 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Delivery acceptance Phase 1 of 2 Phases (Sectors 1-3) | 1 | 22-Oct-18 A | 23-Oct-18 A | 0 | 0 | 100%
S159600 | Ship batch No. 3 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - Purchased Services | 4 | 22-Oct-18 A | 26-Oct-18 A | 0 | 0 | 100%
S159700 | Ship batch No. 3 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - M&S | 4 | 22-Oct-18 A | 26-Oct-18 A | 0 | 0 | 100%
S170700 | Procure EMCAL Fibers for Final Blocks- Vendor Selection | 4 | 22-Oct-18 A | 26-Oct-18 A | 0 | 0 | 100%
S135800 | Design TPC FEE Cooling System | 151 | 22-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S183200 | Receive, unpack, log & inspect preproduction prototype blocks sector 0 M&S | 137 | 25-Oct-18 A | 15-May-19 A | 0 | 0 | 100%
S183300 | Receive, unpack, log & inspect preproduction prototype blocks sector 0 Labor | 138 | 25-Oct-18 A | 15-May-19 A | 0 | 0 | 100%
S323700 | Outer HCAL Sector Mechanical Structure Acceptance Testing FY18 | 3 | 26-Oct-18 A | 31-Oct-18 A | 0 | 0 | 100%
S320600 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 2) | 5 | 26-Oct-18 A | 02-Nov-18 A | 0 | 0 | 100%
S183700 | Install light guides on preproduction prototype blocks sector 0 Labor | 136 | 26-Oct-18 A | 15-May-19 A | 0 | 0 | 100%
S183500 | Install reflectors on preproduction prototype blocks sector 0 Labor | 136 | 26-Oct-18 A | 15-May-19 A | 0 | 0 | 100%
S183600 | Install light guides on preproduction prototype blocks sector 0 M&S | 136 | 26-Oct-18 A | 15-May-19 A | 0 | 0 | 100%
S183400 | Install reflectors on preproduction prototype blocks sector 0 M&S | 136 | 26-Oct-18 A | 15-May-19 A | 0 | 0 | 100%
S122400 | Design TPC R1 Pre-Production Module (strongback, frame, grid, pad, GEMs) | 20 | 30-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S126600 | Design TPC R2 Pre-Production Module (strongback, frame, grid, pad, GEMs) | 20 | 30-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S130600 | Design TPC R3 Pre-Production Module (strongback, frame, grid, pad, GEMs) | 20 | 30-Oct-18 A | 30-Nov-18 A | 0 | 0 | 100%
S164700 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Delivery acceptance | 145 | 30-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S165800 | Prepare fiber assemblies for EMCal Prepro Sectors 1-12 Blocks | 145 | 30-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S180200 | Set up EMCAL Final module production and sector assembly areas Labor | 145 | 30-Oct-18 A | 31-May-19 A | 0 | 0 | 100%
S180300 | Set up EMCAL Prepro module production and sector assembly areas M&S | 39 | 31-Oct-18 A | 31-Dec-18 A | 0 | 0 | 100%
S101009 | FY19 funding available | 0 | 01-Nov-18 A |  | 0 | 0 | 100%
S247600 | Procure 1/2-Crate Digitizer - Parts - Leadtime - FY19 | 0 | 01-Nov-18 A | 01-Nov-18 A | 0 | 0 | 100%
S247900 | Procure 1/2-Crate Digitizer - Boards - Contract/PO - Leadtime FY19 | 0 | 01-Nov-18 A | 01-Nov-18 A | 0 | 0 | 100%
S247700 | Procure 1/2-Crate Digitizer - Parts - Delivery Acceptance | 4 | 01-Nov-18 A | 07-Nov-18 A | 0 | 0 | 100%
S248000 | Procure 1/2-Crate Digitizer - Boards - Delivery Acceptance | 4 | 01-Nov-18 A | 07-Nov-18 A | 0 | 0 | 100%
S218700 | Fabricate EMCal Preamp Boards: Preproduction [Sector 0] M&S FY19 | 6 | 01-Nov-18 A | 09-Nov-18 A | 0 | 0 | 100%
S218500 | Fabricate EMCal Preamp Boards: Preproduction [Sector 0] Labor FY19 | 6 | 01-Nov-18 A | 09-Nov-18 A | 0 | 0 | 100%
S218900 | Fabricate EMCal Interface Board: Preproduction [Sector 0] Labor | 26 | 01-Nov-18 A | 12-Dec-18 A | 0 | 0 | 100%
S219000 | Fabricate EMCal Interface Board: Preproduction [Sector 0] M&S | 26 | 01-Nov-18 A | 12-Dec-18 A | 0 | 0 | 100%
S218200 | Fabricate EMCal SiPM Daughter Boards: Preproduction [Sector 0] Labor | 33 | 01-Nov-18 A | 21-Dec-18 A | 0 | 0 | 100%
S218300 | Fabricate EMCal SiPM Daughter Boards: Preproduction [Sector 0] M&S | 33 | 01-Nov-18 A | 21-Dec-18 A | 0 | 0 | 100%
S212900 | EMCal/HCal sensors Preproduction - Vendor Leadtime FY19 | 101 | 01-Nov-18 A | 02-Apr-19 A | 0 | 0 | 100%
S236400 | Fabricate HCal Preamp Boards: (6 Modules) Labor | 121 | 01-Nov-18 A | 30-Apr-19 A | 0 | 0 | 100%
S236500 | Fabricate HCal Preamp Boards: (6 Modules) M&S | 121 | 01-Nov-18 A | 30-Apr-19 A | 0 | 0 | 100%
S190500 | Procure mechanical parts for preproduction prototype Sector 0 Labor FY19 | 143 | 01-Nov-18 A | 31-May-19 A | 0 | 0 | 100%
S190700 | Procure parts for cooling system for preproduction prototype Sector 0 Labor FY19 | 143 | 01-Nov-18 A | 31-May-19 A | 0 | 0 | 100%
S190300 | Procure mechanical parts for preproduction prototype Sector 0 M&S FY19 | 143 | 01-Nov-18 A | 31-May-19 A | 0 | 0 | 100%
S190900 | Procure parts for cooling system for preproduction prototype Sector 0 M&S FY19 | 143 | 01-Nov-18 A | 31-May-19 A | 0 | 0 | 100%
S320700 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 3) | 28 | 02-Nov-18 A | 17-Dec-18 A | 0 | 0 | 100%
S158700 | Fabricate & test batch No. 4 of 8 batches of 12 blocks for preproduction prototype Sector 0 | 80 | 08-Nov-18 A | 08-Mar-19 A | 0 | 0 | 100%
S320800 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 4) | 4 | 09-Nov-18 A | 16-Nov-18 A | 0 | 0 | 100%
S100600 | CD-3A Budget Appropriation | 0 |  | 13-Nov-18 A | 0 | 0 | 100%
S218800 | Test EMCal Preamp Boards: Preproduction [Sector 0] | 104 | 13-Nov-18 A | 15-Apr-19 A | 0 | 0 | 100%
S320900 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 5) | 4 | 16-Nov-18 A | 23-Nov-18 A | 0 | 0 | 100%
S158800 | Fabricate & test batch No. 5 of 8 batches of 12 blocks for preproduction prototype Sector 0 | 56 | 16-Nov-18 A | 11-Feb-19 A | 0 | 0 | 100%
S321000 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 6) | 0 | 30-Nov-18 A | 30-Nov-18 A | 0 | 0 | 100%
S116400 | Test TPC v1b Module GEMS | 19 | 30-Nov-18 A | 28-Dec-18 A | 0 | 0 | 100%
S122900 | Procure TPC R1 Pre-Production Module Grids - Labor | 19 | 30-Nov-18 A | 28-Dec-18 A | 0 | 0 | 100%
S123000 | Procure TPC R1 Pre-Production Module Grids - M&S | 19 | 30-Nov-18 A | 28-Dec-18 A | 0 | 0 | 100%
S127100 | Procure TPC R2 Pre-Production Module Grids Labor | 19 | 30-Nov-18 A | 28-Dec-18 A | 0 | 0 | 100%
S127200 | Procure TPC R2 Pre-Production Module Grids M&S | 19 | 30-Nov-18 A | 28-Dec-18 A | 0 | 0 | 100%
S131100 | Procure TPC R3 Pre-Production Module Grids Labor | 19 | 30-Nov-18 A | 28-Dec-18 A | 0 | 0 | 100%
S131200 | Procure TPC R3 Pre-Production Module Grids M&S | 19 | 30-Nov-18 A | 28-Dec-18 A | 0 | 0 | 100%
S126700 | Procure TPC R2 Pre-Production Module Stongbacks Labor | 82 | 30-Nov-18 A | 29-Mar-19 A | 0 | 0 | 100%
S126900 | Procure TPC R2 Pre-Production Module Frames - Labor | 82 | 30-Nov-18 A | 29-Mar-19 A | 0 | 0 | 100%
S126800 | Procure TPC R2 Pre-Production Module Stongbacks M&S | 82 | 30-Nov-18 A | 29-Mar-19 A | 0 | 0 | 100%
S127000 | Procure TPC R2 Pre-production Module frames - M&S | 82 | 30-Nov-18 A | 29-Mar-19 A | 0 | 0 | 100%
S127400 | Procure TPC R2 Pre-Production Module Pad Planes M&S | 82 | 30-Nov-18 A | 29-Mar-19 A | 0 | 0 | 100%
S127300 | Procure TPC R2 Pre-Production Module Pad Planes Labor | 82 | 30-Nov-18 A | 01-Apr-19 A | 0 | 0 | 100%
S127500 | Procure TPC R2 Pre-Production Module GEMs Labor | 125 | 30-Nov-18 A | 31-May-19 A | 0 | 0 | 100%
S127600 | Procure TPC R2 Pre-Production Module GEMs M&S | 125 | 30-Nov-18 A | 31-May-19 A | 0 | 0 | 100%
S116500 | Frame TPC v1b Module GEMs | 112 | 07-Dec-18 A | 20-May-19 A | 0 | 0 | 100%
S219100 | Test EMCal Interface Boards: Preproduction [Sector 0] | 82 | 13-Dec-18 A | 11-Apr-19 A | 0 | 0 | 100%
S310000 | Carriage Cradle - Create Assembly & Detail Drawings - Physics Resource(s) | 114 | 17-Dec-18 A | 31-May-19 A | 0 | 0 | 100%
S310010 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) | 114 | 17-Dec-18 A | 31-May-19 A | 0 | 0 | 100%
S170800 | Procure EMCAL Fibers for Final Blocks- Contract Award(s) | 0 | 21-Dec-18 A |  | 0 | 0 | 100%
S250000 | Procure EMCAL 7-Crate Digitizer - Prepare & Send Solicitation FY19 | 0 | 02-Jan-19 A | 02-Jan-19 A | 0 | 0 | 100%
S250200 | Procure EMCAL 7-Crate Digitizer - Vendor Responses FY19 | 0 | 02-Jan-19 A | 02-Jan-19 A | 0 | 0 | 100%
S321100 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 7) | 5 | 02-Jan-19 A | 09-Jan-19 A | 0 | 0 | 100%
S281900 | Cryo System - ODH Analysis | 9 | 02-Jan-19 A | 15-Jan-19 A | 0 | 0 | 100%
S292400 | (Warm Piping System) Cryo Process Design | 10 | 02-Jan-19 A | 16-Jan-19 A | 0 | 0 | 100%
S250300 | Procure EMCAL 7-Crate Digitizer - Vendor Selection | 19 | 02-Jan-19 A | 30-Jan-19 A | 0 | 0 | 100%
S249800 | Procure EMCAL 7-Crate Digitizer - Provide Requirements to Procurement FY19 | 21 | 02-Jan-19 A | 01-Feb-19 A | 0 | 0 | 100%
S279600 | [Magnet] Preliminary Engineering Transport Tooling and Misc. Parts | 30 | 02-Jan-19 A | 14-Feb-19 A | 0 | 0 | 100%
S237400 | Fabricate HCal Backplane: (6 Modules) M&S | 36 | 02-Jan-19 A | 25-Feb-19 A | 0 | 0 | 100%
S184300 | Procure light guides for modules in Sectors (Prepro) 1-12 - Prepare & Send Solicitation | 37 | 02-Jan-19 A | 26-Feb-19 A | 0 | 0 | 100%
S236700 | Fabricate HCal LED Boards: (6 Modules) Labor | 38 | 02-Jan-19 A | 27-Feb-19 A | 0 | 0 | 100%
S237000 | Fabricate HCal Interface Boards: (6 Modules) Labor | 38 | 02-Jan-19 A | 27-Feb-19 A | 0 | 0 | 100%
S237300 | Fabricate HCal Backplane: (6 Modules) Labor | 38 | 02-Jan-19 A | 27-Feb-19 A | 0 | 0 | 100%
S165700 | Set up factory for EMCal Prepro Sectors 1-12 Blocks - Delivery Acceptance | 39 | 02-Jan-19 A | 28-Feb-19 A | 0 | 0 | 100%
S170900 | Procure EMCAL Fibers for Final Blocks- Contract/PO - Leadtime | 72 | 02-Jan-19 A | 15-Apr-19 A | 0 | 0 | 100%
S282700 | RHIC interface valvebox and field joint layout at the interconnect where we tie into RHIC VJ lines and modeling FY19 | 76 | 02-Jan-19 A | 22-Apr-19 A | 0 | 0 | 100%
S237100 | Fabricate HCal Interface Boards: (6 Modules) M&S | 82 | 02-Jan-19 A | 29-Apr-19 A | 0 | 0 | 100%
S282100 | RHIC Helium Interface - Mechanical Engineering Design Tasks FY19 | 93 | 02-Jan-19 A | 15-May-19 A | 0 | 0 | 100%
S146200 | Develop TPC DAM FPGA Algorithm - Round 1 | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S180400 | Set up EMCAL Final module production and sector assembly areas M&S | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S237600 | Procure Hcal Power and Signal Cables and Power System: (6 Modules) - Labor | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S237700 | Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 1 - M&S | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S307500 | Magnet Field Measurements: Setup a detailed 3D model of the coil, return yoke and internal calorimeters FY19 | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S307900 | Magnet Field Measurements: Perform Magnet Assembly Stress Analysis FY19 - Physics Resource(s) | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S307910 | Magnet Field Measurements: Perform Magnet Assembly Stress Analysis FY19 - CA-D Resource(s) | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S288400 | (LN2 supply transfer line system) LN2 supply transfer line detail layout | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S304300 | Magnet Power Supply Installation: Cooling Water Design | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S344600 | Create Cable Management Plan | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S340700 | Model IR Electronics Cooling Water Distribution Thermal Requirements - Physics Resource(s) | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S327500 | Gather Design Requirements for All sPHENIX Subsystems for Line Electric Power | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S329400 | Analyze Detector Support Services Systems Requirements | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S331700 | Analyze Detector Gas and Cooling Services Systems Requirements | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S309800 | Carriage Cradle - Perform Analyses, Design & System Integration (Final) - Physics Resource(s) | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S314700 | Track Modifications - Structural Analysis of Existing Track System & Preliminary Design - Physics Resource(s) | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S309810 | Carriage Cradle - Perform Analyses, Design & System Integration (Final) - CA-D Resource(s) | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S314710 | Steel Track Modifications - Structural Analysis of Existing Steel Track System & Preliminary Design - CA-D Resource(s) | 104 | 02-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S282800 | Transfer line system from 1008B to IP8 hall, detail layout | 75 | 03-Jan-19 A | 22-Apr-19 A | 0 | 0 | 100%
S123100 | Procure TPC R1 Pre-Production Module Pad Planes - Labor | 80 | 07-Jan-19 A | 30-Apr-19 A | 0 | 0 | 100%
S123200 | Procure TPC R1 Pre-Production Module Pad Planes - M&S | 80 | 07-Jan-19 A | 30-Apr-19 A | 0 | 0 | 100%
S122500 | Procure TPC R1 Pre-Production Module Stongbacks - Labor | 100 | 07-Jan-19 A | 30-May-19 A | 0 | 0 | 100%
S122600 | Procure TPC R1 Pre-Production Module Stongbacks - M&S | 100 | 07-Jan-19 A | 30-May-19 A | 0 | 0 | 100%
S321200 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 8) | 5 | 09-Jan-19 A | 16-Jan-19 A | 0 | 0 | 100%
S307300 | Magnet: Quench Detector Documentation | 99 | 09-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S321300 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 9) | 4 | 16-Jan-19 A | 23-Jan-19 A | 0 | 0 | 100%
S305100 | Magnet Power Supply Installation: Documentation | 94 | 16-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
S282200 | Cryo System - SOW & Technical Specifications | 42 | 22-Jan-19 A | 22-Mar-19 A | 0 | 0 | 100%
S248500 | Design Digitizer ADC Boards: 7-Crate Preproduction | 9 | 23-Jan-19 A | 05-Feb-19 A | 0 | 0 | 100%
S248600 | Design Digitizer Controller Board: 7-Crate Preproduction | 9 | 23-Jan-19 A | 05-Feb-19 A | 0 | 0 | 100%
S248700 | Design Digitizer XMIT Board: 7-Crate Preproduction | 9 | 23-Jan-19 A | 05-Feb-19 A | 0 | 0 | 100%
S248900 | Design Digitizer Crate: 7-Crate Preproduction | 9 | 23-Jan-19 A | 05-Feb-19 A | 0 | 0 | 100%
S248800 | Design Digitizer Clock Master: 7-Crate Preproduction | 90 | 23-Jan-19 A | 31-May-19 A | 0 | 0 | 100%
OBLG250410 | Procure EMCAL 7-Crate Digitizer - Parts - Obligation | 0 | 31-Jan-19 A | 31-Jan-19 A | 0 | 0 | 100%
OBLG250510 | Procure EMCAL 7-Crate Digitizer (Boards) - Obligation | 0 | 31-Jan-19 A | 31-Jan-19 A | 0 | 0 | 100%
OBLG250610 | Procure EMCAL 7-Crate Digitizer (Assembly & Tests) - Obligation | 0 | 31-Jan-19 A | 31-Jan-19 A | 0 | 0 | 100%
S144900 | Procure TPC DAM Felix 2.0 Boards Throughput - Vendor Responses | 9 | 01-Feb-19 A | 14-Feb-19 A | 0 | 0 | 100%
S237500 | Test HCal Backplane: (6 Modules) | 15 | 01-Feb-19 A | 25-Feb-19 A | 0 | 0 | 100%
S183900 | Install SiPMs & daughterboards on preproduction prototype blocks sector 0 | 72 | 01-Feb-19 A | 15-May-19 A | 0 | 0 | 100%
S213010 | EMCal/HCal sensors Preproduction - 8K Units - Delivery Acceptance No. 2 | 24 | 04-Feb-19 A | 11-Mar-19 A | 0 | 0 | 100%
S321400 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 10) | 5 | 05-Feb-19 A | 12-Feb-19 A | 0 | 0 | 100%
S249000 | Layout Digitizer ADC Board: 7-Crate Preproduction | 9 | 06-Feb-19 A | 20-Feb-19 A | 0 | 0 | 100%
S249100 | Layout Digitizer Controller Board: 7-Crate Preproduction | 9 | 06-Feb-19 A | 20-Feb-19 A | 0 | 0 | 100%
S249200 | Layout Digitizer XMIT Board: 7-Crate Preproduction | 9 | 06-Feb-19 A | 20-Feb-19 A | 0 | 0 | 100%
S249300 | Layout Digitizer Clock Master: 7-Crate Preproduction | 80 | 06-Feb-19 A | 31-May-19 A | 0 | 0 | 100%
S321700 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 13) | 5 | 08-Feb-19 A | 15-Feb-19 A | 0 | 0 | 100%
S309900 | Carriage Cradle - Preliminary Design Review (Assembly, System Integration, Final Layout) - Physics Resource(s) | 12 | 11-Feb-19 A | 28-Feb-19 A | 0 | 0 | 100%
S309910 | Carriage Cradle - Preliminary Design Review (Assembly, System Integration, Final Layout) - CA-D Resource(s) | 12 | 11-Feb-19 A | 28-Feb-19 A | 0 | 0 | 100%
S321500 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 11) | 4 | 12-Feb-19 A | 19-Feb-19 A | 0 | 0 | 100%
S107700 | Procure TPC v1 End Cap - Delivery Acceptance Phase 2 | 9 | 13-Feb-19 A | 27-Feb-19 A | 0 | 0 | 100%
S282900 | RHIC Helium Interface - Detailed drawing package for Procurement | 46 | 14-Feb-19 A | 22-Apr-19 A | 0 | 0 | 100%
S292600 | (Warm Piping System) Mechanical Engineering Tasks | 74 | 14-Feb-19 A | 31-May-19 A | 0 | 0 | 100%
S293200 | (GN2 Vent Line from platform coldbox) General Arrangement Layout | 74 | 14-Feb-19 A | 31-May-19 A | 0 | 0 | 100%
S321800 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 14) | 7 | 15-Feb-19 A | 27-Feb-19 A | 0 | 0 | 100%
S145000 | Procure TPC DAM Felix 2.0 Boards Throughput - Vendor Selection | 20 | 15-Feb-19 A | 15-Mar-19 A | 0 | 0 | 100%
S122700 | Procure TPC R1 Pre-Production Module Frames - Labor | 51 | 15-Feb-19 A | 30-Apr-19 A | 0 | 0 | 100%
S122800 | Procure TPC R1 Pre-Production Module Frames - M&S | 51 | 15-Feb-19 A | 30-Apr-19 A | 0 | 0 | 100%
S123300 | Procure TPC R1 Pre-Production Module GEMs - Labor | 73 | 15-Feb-19 A | 31-May-19 A | 0 | 0 | 100%
S123400 | Procure TPC R1 Pre-Production Module GEMs - M&S | 73 | 15-Feb-19 A | 31-May-19 A | 0 | 0 | 100%
S321900 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 15) | 12 | 15-Feb-19 A | 05-Mar-19 A | 0 | 0 | 100%
S107600 | Procure TPC v1 End Cap - Delivery Acceptance Phase 1 | 4 | 19-Feb-19 A | 25-Feb-19 A | 0 | 0 | 100%
S321600 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 12) | 5 | 19-Feb-19 A | 26-Feb-19 A | 0 | 0 | 100%
S184200 | Procure light guides for modules in Sectors (Prepro) 1-12 - Provide Requirements to Procurement | 3 | 20-Feb-19 A | 25-Feb-19 A | 0 | 0 | 100%
S139705 | Procure second phase of SAMPA development - Contract Award | 1 | 26-Feb-19 A | 27-Feb-19 A | 0 | 0 | 100%
S184400 | Procure light guides for modules in Sectors (Prepro) 1-12 - Vendor Responses | 1 | 26-Feb-19 A | 27-Feb-19 A | 0 | 0 | 100%
S184500 | Procure light guides for modules in Sectors (Prepro) 1-12 - Vendor Selection | 1 | 27-Feb-19 A | 28-Feb-19 A | 0 | 0 | 100%
S322000 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 16) | 10 | 01-Mar-19 A | 15-Mar-19 A | 0 | 0 | 100%
S184600 | Procure light guides for modules in Sectors (Prepro) 1-12 - Contract Award | 0 | 01-Mar-19 A |  | 0 | 0 | 100%
S130700 | Procure TPC R3 Pre-Production Module Stongbacks Labor | 21 | 01-Mar-19 A | 29-Mar-19 A | 0 | 0 | 100%
S131300 | Procure TPC R3 Pre-Production Module Pad Planes Labor | 21 | 01-Mar-19 A | 29-Mar-19 A | 0 | 0 | 100%
S130800 | Procure TPC R3 Pre-Production Module Stongbacks M&S | 21 | 01-Mar-19 A | 29-Mar-19 A | 0 | 0 | 100%
S131400 | Procure TPC R3 Pre-Production Module Pad Planes M&S | 21 | 01-Mar-19 A | 29-Mar-19 A | 0 | 0 | 100%
S279700 | [Magnet] Preliminary Safety and Design Review | 28 | 01-Mar-19 A | 10-Apr-19 A | 0 | 0 | 100%
S293400 | (Current Leads Warm Piping) General Arrangement Layout | 52 | 01-Mar-19 A | 14-May-19 A | 0 | 0 | 100%
S207500 | Procure Outer HCAL LED/Calibration Fibers Labor | 59 | 01-Mar-19 A | 23-May-19 A | 0 | 0 | 100%
S207600 | Procure Outer HCAL LED/Calibration Fibers M&S | 59 | 01-Mar-19 A | 23-May-19 A | 0 | 0 | 100%
S202800 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) - Labor | 64 | 01-Mar-19 A | 31-May-19 A | 0 | 0 | 100%
S203000 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) - M&S | 64 | 01-Mar-19 A | 31-May-19 A | 0 | 0 | 100%
S316400 | Analyze and Evaluate Structural Support for Internal Detectors FY19 - Physics Resource(s) | 64 | 01-Mar-19 A | 31-May-19 A | 0 | 0 | 100%
S184700 | Procure light guides for modules in Sectors (Prepro) 1-12 - Contract/PO Leadtime | 84 | 01-Mar-19 A | 28-Jun-19 A | 0 | 0 | 100%
S213000 | EMCal/HCal sensors Preproduction - 8K Units - Delivery Acceptance No. 1 | 26 | 04-Mar-19 A | 09-Apr-19 A | 0 | 0 | 100%
S322100 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 17) | 5 | 08-Mar-19 A | 15-Mar-19 A | 0 | 0 | 100%
S261700 | Trigger Design, per Downselect of gFEX mod versus Layout Custom LL1 | 6 | 08-Mar-19 A | 15-Mar-19 A | 0 | 0 | 100%
S159800 | Ship batch No. 4 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - Purchased Services | 14 | 11-Mar-19 A | 29-Mar-19 A | 0 | 0 | 100%
S159900 | Ship batch No. 4 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - M&S | 14 | 11-Mar-19 A | 29-Mar-19 A | 0 | 0 | 100%
S202200 | Procure Outer HCAL Scint. Tiles for Preproduction - Delivery Acceptance Batch 1 | 11 | 12-Mar-19 A | 27-Mar-19 A | 0 | 0 | 100%
S138500 | SAMPA chip 80 nsec development - Delivery Acceptance - Report feasability of 80ns/20MSPS mod | 3 | 14-Mar-19 A | 19-Mar-19 A | 0 | 0 | 100%
S322200 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 18) | 12 | 15-Mar-19 A | 02-Apr-19 A | 0 | 0 | 100%
S139100 | Procure MPW Run of SAMPA v5 components - Provide Requirements to Procurement | 5 | 18-Mar-19 A | 23-Mar-19 A | 0 | 0 | 100%
S261800 | Trigger Design, gFEX Downselect Intermediate Design Review | 1 | 18-Mar-19 A | 18-Mar-19 A | 0 | 0 | 100%
S145600 | Procure TPC DAM Felix 2.0 Boards Throughput - Contract/PO - Leadtime | 96 | 18-Mar-19 A | 01-Aug-19 A | 0 | 0 | 100%
S261900 | Procure Prototype V1 Trigger Board - Provide Requirements to Procurement | 5 | 19-Mar-19 A | 25-Mar-19 A | 0 | 0 | 100%
S158900 | Fabricate & test batch No. 6 of 8 batches of 12 blocks for preproduction prototype Sector 0 | 15 | 20-Mar-19 A | 10-Apr-19 A | 0 | 0 | 100%
S160000 | Ship batch No. 5 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - Purchased Services | 15 | 20-Mar-19 A | 10-Apr-19 A | 0 | 0 | 100%
S160100 | Ship batch No. 5 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - M&S | 15 | 20-Mar-19 A | 10-Apr-19 A | 0 | 0 | 100%
S322300 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 19) | 8 | 21-Mar-19 A | 02-Apr-19 A | 0 | 0 | 100%
S139200 | Procure MPW Run of SAMPA v5 components - Prepare & Send Solicitation | 1 | 25-Mar-19 A | 26-Mar-19 A | 0 | 0 | 100%
S262000 | Procure Prototype V1 Trigger Board - Prepare & Send Solicitation | 18 | 26-Mar-19 A | 18-Apr-19 A | 0 | 0 | 100%
S139300 | Procure MPW Run of SAMPA v5 components - Vendor Responses | 2 | 27-Mar-19 A | 29-Mar-19 A | 0 | 0 | 100%
S160200 | Ship batch No. 6 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - Purchased Services | 10 | 27-Mar-19 A | 10-Apr-19 A | 0 | 0 | 100%
S160300 | Ship batch No. 6 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - M&S | 10 | 27-Mar-19 A | 10-Apr-19 A | 0 | 0 | 100%
S159000 | Fabricate & test batch No. 7 of 8 batches of 12 blocks for preproduction prototype Sector 0 | 27 | 27-Mar-19 A | 03-May-19 A | 0 | 0 | 100%
S139400 | Procure MPW Run of SAMPA v5 components - Vendor Selection | 0 | 29-Mar-19 A | 29-Mar-19 A | 0 | 0 | 100%
S139500 | Procure MPW Run of SAMPA v5 components - Contract Award | 0 | 29-Mar-19 A |  | 0 | 0 | 100%
S322400 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 20) | 12 | 29-Mar-19 A | 16-Apr-19 A | 0 | 0 | 100%
S138800 | SAMPA chip 80 nsec development - Leadtime - Design at Layout level of new circuits | 17 | 01-Apr-19 A | 24-Apr-19 A | 0 | 0 | 100%
S139600 | Procure MPW Run of SAMPA v5 components - Leadtime | 21 | 01-Apr-19 A | 30-Apr-19 A | 0 | 0 | 100%
S165900 | Fabricate EMCAL Prepro blocks sector 1 | 43 | 01-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S135600 | TPC FEE Prototype v1 Safety Review | 24 | 01-Apr-19 A | 03-May-19 A | 0 | 0 | 100%
S191000 | Build mechanical enclosure for preproduction prototype Sector 0 | 42 | 01-Apr-19 A | 30-May-19 A | 0 | 0 | 100%
S146400 | Measure Throughput of FELIX 2.0 for TPC DAM | 43 | 01-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S202300 | Procure Outer HCAL Scint. Tiles for Preproduction - Delivery Acceptance Batch 2 | 14 | 03-Apr-19 A | 23-Apr-19 A | 0 | 0 | 100%
S135700 | TPC FEE Prototype v1 Design Review | 22 | 03-Apr-19 A | 03-May-19 A | 0 | 0 | 100%
S159100 | Fabricate & test batch No. 8 of 8 batches of 12 blocks for preproduction prototype Sector 0 | 22 | 03-Apr-19 A | 03-May-19 A | 0 | 0 | 100%
S160400 | Ship batch No. 7 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - Purchased Services | 22 | 03-Apr-19 A | 03-May-19 A | 0 | 0 | 100%
S160500 | Ship batch No. 7 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - M&S | 22 | 03-Apr-19 A | 03-May-19 A | 0 | 0 | 100%
S171000 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 1 | 8 | 05-Apr-19 A | 17-Apr-19 A | 0 | 0 | 100%
S322500 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 21) | 10 | 05-Apr-19 A | 19-Apr-19 A | 0 | 0 | 100%
S236100 | Fabricate HCal SiPM Boards: (6 Modules) Labor | 38 | 08-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S301600 | Magnet: 1008 IR Design Power Supply AC and Quench Detector Power Distribution | 38 | 08-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S219900 | Update Design per Change Specification - EMCal SiPM Daughter Board: Sectors 1-12 | 31 | 09-Apr-19 A | 22-May-19 A | 0 | 0 | 100%
S191300 | Install modules in preproduction prototype Sector 0 | 37 | 09-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S220000 | Layout per Change Specification - EMCal SiPM Daughter Board: Sectors 1-12 | 10 | 10-Apr-19 A | 24-Apr-19 A | 0 | 0 | 100%
S116600 | Test TPC v1b Module Framed GEMs | 36 | 10-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S322600 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 22) | 26 | 12-Apr-19 A | 20-May-19 A | 0 | 0 | 100%
S208100 | Procure Outer HCAL Scintillating Tiles (Prod) - Contract Award(s) | 0 | 15-Apr-19 A |  | 0 | 0 | 100%
S160600 | Ship batch No. 8 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - Purchased Services | 14 | 15-Apr-19 A | 03-May-19 A | 0 | 0 | 100%
S160700 | Ship batch No. 8 of 8 batches of 12 preproduction prototype blocks for Sector 0 to BNL - M&S | 14 | 15-Apr-19 A | 03-May-19 A | 0 | 0 | 100%
S213100 | EMCal/HCal sensors Preproduction - 7K Units - Delivery Acceptance No. 3 | 24 | 16-Apr-19 A | 20-May-19 A | 0 | 0 | 100%
S204400 | Procure Preproduction Outer HCAL Splice Plates -Use in test assembly | 32 | 16-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S116700 | Assemble TPC v1b Module Prototype | 31 | 17-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S322700 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 23) | 13 | 19-Apr-19 A | 08-May-19 A | 0 | 0 | 100%
S301700 | Magnet: 1008 IR Design Power Supply AC Power Hook-up | 28 | 22-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S138315 | SAMPA chip 80 nsec development - Leadtime - Layout finalization for MPW and submission | 4 | 24-Apr-19 A | 30-Apr-19 A | 0 | 0 | 100%
S116800 | Test TPC v1b Module Prototype and Final Design Review | 73 | 24-Apr-19 A | 06-Aug-19 A | 0 | 0 | 100%
S139000 | SAMPA chip 80 nsec development - Delivery Acceptance - Design at Layout level of new circuits | 1 | 25-Apr-19 A | 26-Apr-19 A | 0 | 0 | 100%
S301900 | Magnet: 1008 IR Design Power Supply, Magnet, Dump Resistor DC Cabling | 23 | 29-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S237200 | Test HCal Interface Boards: (6 Modules) | 22 | 30-Apr-19 A | 31-May-19 A | 0 | 0 | 100%
S139700 | Procure MPW Run of SAMPA v5 components - Delivery Acceptance | 1 | 01-May-19 A | 02-May-19 A | 0 | 0 | 100%
S139010 | SAMPA chip 80 nsec development - Delivery Acceptance - Layout finalization for MPW and submission | 1 | 01-May-19 A | 02-May-19 A | 0 | 0 | 100%
S171002 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 2 | 2 | 01-May-19 A | 03-May-19 A | 0 | 0 | 100%
S190902 | Procure parts for cooling system for preproduction prototype Sector 0 M&S FY19 (second part) | 16 | 01-May-19 A | 23-May-19 A | 0 | 0 | 100%
S191200 | Build cooling system for preproduction prototype Sector 0 | 17 | 01-May-19 A | 24-May-19 A | 0 | 0 | 100%
S198400 | Design Inner HCAL Support Rings FY20 | 21 | 01-May-19 A | 31-May-19 A | 0 | 0 | 100%
S123500 | Assemble TPC R1 Pre-Production Module in TPC R1 Factory | 21 | 01-May-19 A | 31-May-19 A | 0 | 0 | 100%
S123505 | Assemble TPC R1 Pre-Production Module in TPC R1 Factory - Contributed Labor | 21 | 01-May-19 A | 31-May-19 A | 0 | 0 | 100%
S202400 | Procure Outer HCAL Scint. Tiles for Preproduction - Delivery Acceptance Batch 3 | 15 | 02-May-19 A | 23-May-19 A | 0 | 0 | 100%
S184000 | Glue preproduction prototype blocks together into modules sector 0 | 9 | 02-May-19 A | 15-May-19 A | 0 | 0 | 100%
S183800 | EmCal Test Fit Blocks Sector 0 and Preproduction Readiness Review | 15 | 02-May-19 A | 23-May-19 A | 0 | 0 | 100%
S316500 | Create Internal Detector Structural Support Assembly Drawings - Physics Resource(s) | 20 | 02-May-19 A | 31-May-19 A | 0 | 0 | 100%
S139710 | Procure second phase of SAMPA development - Delivery of Test Boards | 3 | 03-May-19 A | 08-May-19 A | 0 | 0 | 100%
S322800 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 24) | 9 | 03-May-19 A | 16-May-19 A | 0 | 0 | 100%
S279800 | [Magnet] Final Design (Magnet Transport) | 10 | 06-May-19 A | 20-May-19 A | 0 | 0 | 100%
S136800 | v2 Design TPC FEE preproduction prototype | 18 | 06-May-19 A | 31-May-19 A | 0 | 0 | 100%
S250700 | Procure EMCAL 7-Crate Digitizer - Parts - Leadtime | 18 | 06-May-19 A | 31-May-19 A | 0 | 0 | 100%
S250800 | Procure EMCAL 7-Crate Digitizer - Boards - Leadtime | 18 | 06-May-19 A | 31-May-19 A | 0 | 0 | 100%
S302000 | Magnet: Design Cable Tray and Supports for Power and Signal Distribution | 18 | 06-May-19 A | 31-May-19 A | 0 | 0 | 100%
S223200 | Fabricate Calorimeter Controller Boards: Sectors 1-12 Labor | 16 | 08-May-19 A | 31-May-19 A | 0 | 0 | 100%
S322900 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 25) | 4 | 10-May-19 A | 16-May-19 A | 0 | 0 | 100%
S184100 | Sector 0 Module Production Complete | 0 |  | 15-May-19 A | 0 | 0 | 100%
S221400 | Fabricate EMCal SiPM Boards: Sectors 1-12 - Labor | 9 | 15-May-19 A | 29-May-19 A | 0 | 0 | 100%
S323000 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 26) | 5 | 17-May-19 A | 24-May-19 A | 0 | 0 | 100%
S139715 | Procure second phase of SAMPA development - Delivery of Results from first round of tests | 4 | 21-May-19 A | 28-May-19 A | 0 | 0 | 100%
S214700 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 4 | 8 | 21-May-19 A | 03-Jun-19 A | 0 | 0 | 100%
S109300 | Produce TPC v2 Field Cage Prototype Conceptual Design | 7 | 21-May-19 A | 31-May-19 A | 0 | 0 | 100%
S109600 | Produce TPC v2 Outer Field Cage Conceptual Design | 7 | 21-May-19 A | 31-May-19 A | 0 | 0 | 100%
S110500 | Produce TPC v2 Inner Field Cage Conceptual Design | 7 | 21-May-19 A | 31-May-19 A | 0 | 0 | 100%
S111600 | Produce TPC v2 Central Membrane Conceptual Design | 7 | 21-May-19 A | 31-May-19 A | 0 | 0 | 100%
S202500 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction), Contributed Labor | 4 | 24-May-19 A | 31-May-19 A | 0 | 0 | 100%
S202510 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction) | 4 | 24-May-19 A | 31-May-19 A | 0 | 0 | 100%
S236600 | Test HCal Preamp Boards: (6 Modules) | 4 | 24-May-19 A | 31-May-19 A | 0 | 0 | 100%
S100800 | PD-2/3 Review | 2 | 28-May-19 A | 30-May-19 A | 0 | 0 | 100%
S169900 | Procure EMCAL W Powder for Final Blocks - Vendor Selection | 2 | 29-May-19 A | 31-May-19 A | 0 | 0 | 100%
S170000 | Procure EMCAL W Powder for Final Blocks - Contract Award(s) | 0 | 31-May-19 A |  | 0 | 0 | 100%
S100900 | Transition to PD2/3 | 77 | 31-May-19 A | 19-Sep-19 A | 0 | 0 | 100%
S248810 | Design Digitizer Clock Master: 7-Crate Preproduction Split | 19 | 03-Jun-19 A | 28-Jun-19 A | 1430 | 1430 | 100%
S249310 | Layout Digitizer Clock Master: 7-Crate Preproduction Split | 19 | 03-Jun-19 A | 28-Jun-19 A | 1430 | 1430 | 100%
S272600 | Procure Prototype Shaper/Disc Electronics - Delivery Acceptance | 24 | 03-Jun-19 A | 08-Jul-19 A | 77229 | 77229 | 100%
S208200 | Procure Outer HCAL Scintillating Tiles (Prod) - Contract/PO - Leadtime | 81 | 03-Jun-19 A | 26-Sep-19 A | 0 | 0 | 100%
S1004320 | Actuals - Labor FY19 Jun-Sep 16716 | 83 | 03-Jun-19 A | 30-Sep-19 A | 58057 | 58057 | 100%
S1004360 | Actuals - Labor FY19 Jun-Sep 16717 | 83 | 03-Jun-19 A | 30-Sep-19 A | 7093 | 7093 | 100%
S1004400 | Actuals - NonLabor FY19 Jun-Sep 16717 | 83 | 03-Jun-19 A | 30-Sep-19 A | 21421 | 21421 | 100%
S1004440 | Actuals - Labor FY19 Jun-Sep 16718 | 83 | 03-Jun-19 A | 30-Sep-19 A | 45398 | 45398 | 100%
S1004480 | Actuals - NonLabor FY19 Jun-Sep 16718 | 83 | 03-Jun-19 A | 30-Sep-19 A | 19728 | 19728 | 100%
S1004520 | Actuals - Labor FY19 Jun-Sep 16719 | 83 | 03-Jun-19 A | 30-Sep-19 A | 18242 | 18242 | 100%
S1004560 | Actuals - NonLabor FY19 Jun-Sep 16719 | 83 | 03-Jun-19 A | 30-Sep-19 A | 565 | 565 | 100%
S1004600 | Actuals - Labor FY19 Jun-Sep 16720 | 83 | 03-Jun-19 A | 30-Sep-19 A | 2145 | 2145 | 100%
S1004640 | Actuals - Labor FY19 Jun-Sep 16721 | 83 | 03-Jun-19 A | 30-Sep-19 A | 1351 | 1351 | 100%
S1004680 | Actuals - Labor FY19 Jun-Sep 16725 | 83 | 03-Jun-19 A | 30-Sep-19 A | 22941 | 22941 | 100%
S1004720 | Actuals - NonLabor FY19 Jun-Sep 16721 | 83 | 03-Jun-19 A | 30-Sep-19 A | 7188 | 7188 | 100%
S1004760 | Actuals - Labor FY19 Jun-Sep 16726 | 83 | 03-Jun-19 A | 30-Sep-19 A | 8728 | 8728 | 100%
S1004840 | Actuals - NonLabor FY19 Jun-Sep 16722 | 83 | 03-Jun-19 A | 30-Sep-19 A | 1050666 | 1050666 | 100%
S1004880 | Actuals - Labor FY19 Jun-Sep 16729 | 83 | 03-Jun-19 A | 30-Sep-19 A | 226960 | 226960 | 100%
S1004920 | Actuals - Labor FY19 Jun-Sep 16731 | 83 | 03-Jun-19 A | 30-Sep-19 A | 20995 | 20995 | 100%
S1004960 | Actuals - Labor FY19 Jun-Sep 16723 | 83 | 03-Jun-19 A | 30-Sep-19 A | 21123 | 21123 | 100%
S1005000 | Actuals - Labor FY19 Jun-Sep 16724 | 83 | 03-Jun-19 A | 30-Sep-19 A | 6015 | 22906 | 100%
S1005040 | Actuals - NonLabor FY19 Jun-Sep 16724 | 83 | 03-Jun-19 A | 30-Sep-19 A | 67953 | 67953 | 100%
S1005080 | Actuals - Labor FY19 Jun-Sep 16727 | 83 | 03-Jun-19 A | 30-Sep-19 A | 38498 | 38498 | 100%
S1005120 | Actuals - Labor FY19 Jun-Sep 16728 | 83 | 03-Jun-19 A | 30-Sep-19 A | 2992 | 2992 | 100%
S282400 | Cryo System - Final Tech Design Review with Pressure Cryo Safety Subcommittee (PCSS) | 1 | 03-Jun-19 A | 03-Jun-19 A | 0 | 0 | 100%
S323100 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 27) | 2 | 03-Jun-19 A | 04-Jun-19 A | 0 | 0 | 100%
S244600 | Procure Contracted Labor & M&S Univ. Michigan (UM) - Provide Requirements to Procurement | 5 | 03-Jun-19 A | 07-Jun-19 A | 0 | 0 | 100%
S279900 | [Magnet] Final Design Review (Magnet Transport) | 5 | 03-Jun-19 A | 07-Jun-19 A | 0 | 0 | 100%
S171003 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 3 | 11 | 03-Jun-19 A | 18-Jun-19 A | 40406 | 40406 | 100%
S248110 | Procure 1/2-Crate Digitizer - Contract/PO - Leadtime for Assembly & Tests Split | 12 | 03-Jun-19 A | 19-Jun-19 A | 0 | 0 | 100%
S316410 | Analyze and Evaluate Structural Support for Internal Detectors FY19 - CA-D Resource(s) | 18 | 03-Jun-19 A | 27-Jun-19 A | 0 | 0 | 100%
S165802 | Prepare fiber assemblies for EMCal Prepro Sectors 1-12 Blocks Split | 19 | 03-Jun-19 A | 28-Jun-19 A | 11004 | 11004 | 100%
S190302 | Procure mechanical parts for preproduction prototype Sector 0 M&S FY19 Split | 19 | 03-Jun-19 A | 28-Jun-19 A | 0 | 0 | 100%
S190502 | Procure mechanical parts for preproduction prototype Sector 0 Labor FY19 Split | 19 | 03-Jun-19 A | 28-Jun-19 A | 0 | 0 | 100%
S190702 | Procure parts for cooling system for preproduction prototype Sector 0 Labor FY19 Split | 19 | 03-Jun-19 A | 28-Jun-19 A | 1287 | 1287 | 100%
S236800 | Fabricate HCal LED Boards: (6 Modules) M&S | 19 | 03-Jun-19 A | 28-Jun-19 A | 14420 | 14420 | 100%
S214800 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 5 | 20 | 03-Jun-19 A | 28-Jun-19 A | 76699 | 76699 | 100%
S293202 | (GN2 Vent Line from platform coldbox) General Arrangement Layout Split | 20 | 03-Jun-19 A | 28-Jun-19 A | 0 | 0 | 100%
S191400 | Install readout electronics on preproduction prototype Sector 0 | 41 | 03-Jun-19 A | 30-Jul-19 A | 15212 | 15212 | 100%
S219210 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Preproduction [Sector 0] Labor Split | 41 | 03-Jun-19 A | 31-Jul-19 A | 2743 | 2743 | 100%
S219402 | Procure EMCal External Signal and Power Cables, and Power Systems: Preproduction [Sector 0] Labor Split | 41 | 03-Jun-19 A | 31-Jul-19 A | 3887 | 3887 | 100%
S213200 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 | 41 | 03-Jun-19 A | 31-Jul-19 A | 1226 | 1226 | 100%
S213205 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 1 - Contributed Labor | 41 | 03-Jun-19 A | 31-Jul-19 A | 9579 | 9579 | 100%
S180402 | Set up EMCAL Final module production and sector assembly areas M&S Split | 63 | 03-Jun-19 A | 30-Aug-19 A | 11198 | 11198 | 100%
S237800 | Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 2 - M&S | 64 | 03-Jun-19 A | 30-Aug-19 A | 21876 | 21876 | 100%
S237710 | Procure Hcal Power and Signal Cables and Power System: (6 Modules), Phase 1 - M&S Split | 64 | 03-Jun-19 A | 30-Aug-19 A | 5469 | 5469 | 100%
S104010 | Travel FY19 Split | 83 | 03-Jun-19 A | 30-Sep-19 A | 8838 | 8838 | 100%
S103705 | Mgmt labor - B - BNL Contributed Labor - FY19 - Physics Resource(s) Split | 83 | 03-Jun-19 A | 30-Sep-19 A | 503204 | 503204 | 100%
S103715 | Mgmt labor - B - BNL Contributed Labor - FY19 - CA-D Resource(s) Split | 83 | 03-Jun-19 A | 30-Sep-19 A | 48872 | 48872 | 100%
S102905 | Mgmt labor - A - MIE, Phase 1 - FY19 split | 83 | 03-Jun-19 A | 30-Sep-19 A | 71048 | 71048 | 100%
S102915 | Mgmt labor - A - MIE, Phase 2 - FY19 split | 83 | 03-Jun-19 A | 30-Sep-19 A | 43639 | 43639 | 100%
S254600 | DAQ Prototype: Software development - INTT FELIX readout test_80% | 83 | 03-Jun-19 A | 30-Sep-19 A | 44550 | 44550 | 100%
S237602 | Procure Hcal Power and Signal Cables and Power System: (6 Modules) - Labor Split | 83 | 03-Jun-19 A | 30-Sep-19 A | 13322 | 13322 | 100%
S307310 | Magnet: Quench Detector Documentation Split_15% | 83 | 03-Jun-19 A | 30-Sep-19 A | 0 | 0 | 100%
S310005 | Carriage Cradle - Create Assembly & Detail Drawings - Physics Resource(s) Split_90% | 83 | 03-Jun-19 A | 30-Sep-19 A | 0 | 0 | 100%
S310015 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) Split_90% | 83 | 03-Jun-19 A | 30-Sep-19 A | 0 | 0 | 100%
S314715 | Steel Track Modifications - Structural Analysis of Existing Steel Track System & Preliminary Design_15% | 83 | 03-Jun-19 A | 30-Sep-19 A | 0 | 0 | 100%
S316405 | Analyze and Evaluate Structural Support for Internal Detectors FY19 - Physics Resource(s) Split_25% | 83 | 03-Jun-19 A | 30-Sep-19 A | 0 | 0 | 100%
S314705 | Track Modifications - Structural Analysis of Existing Track System & Preliminary Design - Physics Resource(s) Split | 105 | 03-Jun-19 A | 30-Oct-19 A | 0 | 0 | 100%
S180202 | Set up EMCAL Final module production and sector assembly areas Labor Split_75% | 121 | 03-Jun-19 A | 25-Nov-19 A | 4223 | 4223 | 100%
S202802 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) Labor Split | 121 | 03-Jun-19 A | 25-Nov-19 A | 232 | 232 | 100%
S203002 | Procure Miscellaneous Tools for Outer HCAL sector assembly and testing area (Preproduction) - M&S Split | 121 | 03-Jun-19 A | 25-Nov-19 A | 2207 | 2207 | 100%
S268905 | Timing System Prototype: develop firmware FY19 Split | 144 | 03-Jun-19 A | 31-Dec-19 A | 43216 | 43216 | 100%
S268915 | Timing System Prototype: develop firmware FY19 Split Instrum | 144 | 03-Jun-19 A | 31-Dec-19 A | 6755 | 6755 | 100%
S254502 | DAQ Prototype: Software development - Calorimeters & TPC FY19 Split | 145 | 03-Jun-19 A | 02-Jan-20 A | 88302 | 88302 | 100%
S266110 | GL1 Prototype: develop firmware FY19 Split | 148 | 03-Jun-19 A | 06-Jan-20 A | 59688 | 59688 | 100%
S269100 | Timing System Prototype: Design I/O Transition Module FY19 | 185 | 03-Jun-19 A | 28-Feb-20 A | 8421 | 8421 | 100%
S266300 | GL1 Prototype: Design I/O Transition Module FY19 | 185 | 03-Jun-19 A | 28-Feb-20 A | 7091 | 7123 | 100%
S254800 | DAQ Prototype: Software development - Multiple Subsystem Test | 445 | 03-Jun-19 A | 15-Mar-21 A | 94649 | 94838 | 100%
S282410 | Completed: Cryo System - Final Tech Design Review with Pressure Cryo Safety Subcommittee (PCSS) | 0 |  | 03-Jun-19 A | 0 | 0 | 100%
S261600 | Trigger Design, Layout Custom LL1 - Delivery Acceptance | 1 | 04-Jun-19 A | 04-Jun-19 A | 0 | 0 | 100%
S282980 | RHIC Helium Interface - Procurement Readiness Review | 5 | 04-Jun-19 A | 10-Jun-19 A | 0 | 0 | 100%
S172700 | Set up factory for final blocks M&S | 119 | 05-Jun-19 A | 25-Nov-19 A | 2840 | 2840 | 100%
S172600 | Set up factory for final blocks Purchased Services | 119 | 05-Jun-19 A | 25-Nov-19 A | 7017 | 7017 | 100%
S262100 | Procure Prototype V1 Trigger Board - Vendor Responses | 7 | 05-Jun-19 A | 13-Jun-19 A | 0 | 0 | 100%
S280000 | [Magnet] Procure Parts (for disassembly, transport & reassembly) - Provide requirements to Procurement | 5 | 10-Jun-19 A | 14-Jun-19 A | 0 | 0 | 100%
S244700 | Procure Contracted Labor & M&S Univ. Michigan (UM) - Vendor Selection | 14 | 10-Jun-19 A | 28-Jun-19 A | 0 | 0 | 100%
S323200 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 28) | 6 | 14-Jun-19 A | 21-Jun-19 A | 0 | 0 | 100%
S262200 | Procure Prototype V1 Trigger Board - Vendor Selection | 10 | 14-Jun-19 A | 28-Jun-19 A | 0 | 0 | 100%
S280100 | [Magnet] Procure Parts (for disassembly, transport & reassembly) - Prepare & Send Solicitation | 10 | 17-Jun-19 A | 28-Jun-19 A | 0 | 0 | 100%
S171004 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 4 | 7 | 19-Jun-19 A | 28-Jun-19 A | 40406 | 40406 | 100%
S248200 | Procure 1/2-Crate Digitizer - Contract/PO - Delivery Acceptance for Assembly & Tests | 6 | 20-Jun-19 A | 28-Jun-19 A | 55163 | 55163 | 100%
S282300 | Cryo System - Bid package Helium System | 0 | 21-Jun-19 A |  | 0 | 0 | 100%
S172800 | Prepare fiber assemblies for final blocks | 529 | 21-Jun-19 A | 2021-08-02 | 163757 | 163757 | 96%
S323300 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 29) | 6 | 21-Jun-19 A | 28-Jun-19 A | 0 | 0 | 100%
S244800 | Procure Contracted Labor & M&S Univ. Michigan (UM), Phase 1 - Contract Award | 0 | 28-Jun-19 A |  | 0 | 0 | 100%
S122202 | Prepare TPC R1 Factory Tooling Labor Split | 21 | 01-Jul-19 A | 31-Jul-19 A | 295 | 295 | 100%
S122302 | Prepare TPC R1 Factory Tooling M&S Split | 21 | 01-Jul-19 A | 31-Jul-19 A | 2648 | 2648 | 100%
S126502 | Prepare TPC R2 Factory Tooling M&S Split | 21 | 01-Jul-19 A | 31-Jul-19 A | 3972 | 3972 | 100%
S220200 | Layout per Change Specification - EMCal Preamp: Sectors 1-12 | 21 | 01-Jul-19 A | 31-Jul-19 A | 9195 | 9195 | 100%
S220400 | Layout per Change Specification - EMCal Interface: Sectors 1-12 | 21 | 01-Jul-19 A | 31-Jul-19 A | 13280 | 13280 | 100%
S220600 | Layout per Change Specification - Calorimeter Controller: Sectors 1-12 | 21 | 01-Jul-19 A | 31-Jul-19 A | 7380 | 7380 | 100%
S220100 | Update Design per Change Specification - EMCal Preamp: Sectors 1-12 | 21 | 01-Jul-19 A | 31-Jul-19 A | 8598 | 8598 | 100%
S220300 | Update Design per Change Specification - EMCal Interface Board: Sectors 1-12 | 21 | 01-Jul-19 A | 31-Jul-19 A | 8598 | 8598 | 100%
S220500 | Update Design per Change Specification - Calorimeter Controller: Sectors 1-12 | 21 | 01-Jul-19 A | 31-Jul-19 A | 8598 | 8598 | 100%
S223300 | Fabricate Calorimeter Controller Boards: Sectors 1-12 M&S | 32 | 01-Jul-19 A | 15-Aug-19 A | 22309 | 23010 | 100%
S223202 | Fabricate Calorimeter Controller Boards: Sectors 1-12 Labor Split | 32 | 01-Jul-19 A | 15-Aug-19 A | 19051 | 19622 | 100%
S130102 | Prepare TPC R3a Factory Tooling M&S Split | 43 | 01-Jul-19 A | 30-Aug-19 A | 3972 | 3972 | 100%
S165902 | Fabricate EMCAL Prepro blocks sector 1 Split | 63 | 01-Jul-19 A | 30-Sep-19 A | 6820 | 7104 | 100%
S215600 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 | 63 | 01-Jul-19 A | 30-Sep-19 A | 1226 | 1277 | 100%
S215605 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 4 - Contributed Labor | 63 | 01-Jul-19 A | 30-Sep-19 A | 9579 | 9867 | 100%
S215800 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 | 125 | 01-Jul-19 A | 31-Dec-19 A | 1277 | 1277 | 100%
S215805 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 5 - Contributed Labor | 125 | 01-Jul-19 A | 31-Dec-19 A | 9579 | 9867 | 100%
S262300 | Procure Prototype V1 Trigger Board - Contract Award(s) | 0 | 01-Jul-19 A |  | 0 | 0 | 100%
S248300 | Calorimeter Digitizer 1/2-Crate Complete | 0 |  | 01-Jul-19 A | 0 | 0 | 100%
S123605 | Test TPC R1 Pre-Production Module - Contributed Labor | 5 | 01-Jul-19 A | 08-Jul-19 A | 0 | 0 | 100%
S123600 | Test TPC R1 Pre-Production Module | 6 | 01-Jul-19 A | 09-Jul-19 A | 7868 | 7868 | 100%
S323400 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Chimney Sector Assembly 1) | 6 | 01-Jul-19 A | 09-Jul-19 A | 0 | 0 | 100%
S202512 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction) Split | 9 | 01-Jul-19 A | 15-Jul-19 A | 2117 | 2117 | 100%
S213210 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 | 9 | 01-Jul-19 A | 15-Jul-19 A | 1226 | 1226 | 100%
S213215 | Prepro Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 2 - Contributed Labor | 9 | 01-Jul-19 A | 15-Jul-19 A | 9579 | 9579 | 100%
S202502 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction), Contributed Labor Split | 10 | 01-Jul-19 A | 15-Jul-19 A | 18803 | 18803 | 100%
S280200 | [Magnet] Procure Parts (for disassembly, transport & reassembly) - Vendor Responses | 10 | 01-Jul-19 A | 15-Jul-19 A | 0 | 0 | 100%
S214900 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 6 | 19 | 01-Jul-19 A | 26-Jul-19 A | 76699 | 76699 | 100%
S191100 | Build mechanical stand/support for preproduction prototype Sector 0 - Labor | 20 | 01-Jul-19 A | 29-Jul-19 A | 5318 | 5318 | 100%
S191110 | Build mechanical stand/support for preproduction prototype Sector 0 - M&S | 20 | 01-Jul-19 A | 29-Jul-19 A | 552 | 552 | 100%
S213300 | Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 | 21 | 01-Jul-19 A | 31-Jul-19 A | 1073 | 1073 | 100%
S213305 | Prepro Q/A Tested & Sorted devices 7 K Units Delivery Batch No. 3 - Contributed Labor | 21 | 01-Jul-19 A | 31-Jul-19 A | 8293 | 8293 | 100%
S323800 | Outer HCAL Sector Mechanical Structure Acceptance Testing FY19 | 21 | 01-Jul-19 A | 31-Jul-19 A | 0 | 0 | 100%
S191500 | Install cables and cooling system on preproduction prototype Sector 0 | 44 | 01-Jul-19 A | 30-Aug-19 A | 12696 | 12696 | 100%
S307510 | Magnet Field Measurements: Setup a detailed 3D model of the coil, return yoke and internal calorimeters FY19 Split_40% | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S307920 | Magnet Field Measurements: Perform Magnet Assembly Stress Analysis FY19 - CA-D Resource(s) Split_30% | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S274510 | 2019 Magnet Project Management Split | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S275110 | 2019 Cryo L3 Project Management Split | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S275610 | 2019 PS & Quench Protection L3 Project Management Split | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S277910 | 2019 Integration & Installation Project Management Split | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S276110 | 2019 Infrastructure Project Management Split | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S276710 | 2019 Facility Support Systems L3 Project Management Split | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S277310 | 2019 Detector Support Systems L3 Project Management Split | 63 | 01-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S167100 | Pack and ship EMCAL blocks for Prepro sector 1 to BNL Purchased Services | 104 | 01-Jul-19 A | 29-Nov-19 A | 831 | 866 | 100%
S167200 | Pack and ship EMCAL blocks for Prepro sector 1 to BNL M&S | 104 | 01-Jul-19 A | 29-Nov-19 A | 1192 | 1229 | 100%
S170100 | Procure EMCAL W Powder for Final Blocks - Contract/PO - Leadtime | 104 | 01-Jul-19 A | 29-Nov-19 A | 0 | 0 | 100%
S344602 | Create Cable Management Plan Split | 104 | 01-Jul-19 A | 29-Nov-19 A | 0 | 0 | 100%
S262400 | Procure Prototype V1 Trigger Board - Contract/PO - Leadtime | 172 | 01-Jul-19 A | 10-Mar-20 A | 0 | 0 | 100%
S164702 | Order epoxy for EMCal Prepro Sectors 1-12 Blocks - Delivery acceptance Split | 185 | 01-Jul-19 A | 30-Mar-20 A | 36671 | 36671 | 100%
S202600 | Completion of Outer HCAL Scintillating Tile Procurement (Preproduction) | 0 |  | 01-Jul-19 A | 0 | 0 | 100%
S236102 | Fabricate HCal SiPM Boards: (6 Modules) Labor Split | 5 | 02-Jul-19 A | 10-Jul-19 A | 6050 | 6050 | 100%
S139720 | Procure second phase of SAMPA development - Delivery of First Chip Layout | 10 | 02-Jul-19 A | 16-Jul-19 A | 38614 | 38614 | 100%
S118900 | Test TPC v2a Module Prototype | 18 | 03-Jul-19 A | 30-Jul-19 A | 0 | 0 | 100%
S323500 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Chimney Sector Assembly 2) | 5 | 09-Jul-19 A | 15-Jul-19 A | 0 | 0 | 100%
S272700 | Prototype Shaper/Disc Board Testing and evaluation, revisions; Final Design and Procurment Readiness Reviews_50% | 407 | 09-Jul-19 A | 25-Feb-21 A | 20874 | 21192 | 100%
S236200 | Fabricate HCal SiPM Boards: (6 Modules) M&S | 4 | 11-Jul-19 A | 17-Jul-19 A | 31675 | 31675 | 100%
S280300 | [Magnet] Procure Parts (for disassembly, transport & reassembly) - Vendor Selection | 10 | 16-Jul-19 A | 29-Jul-19 A | 0 | 0 | 100%
S280600 | [Magnet] Procure Parts (for disassembly, transport & reassembly) - Delivery Acceptance | 10 | 17-Jul-19 A | 31-Jul-19 A | 0 | 0 | 100%
S139725 | Procure second phase of SAMPA development - Delivery of Final Review of test results | 11 | 17-Jul-19 A | 31-Jul-19 A | 77229 | 77229 | 100%
S236300 | Test HCal SiPM Boards: (6 Modules) | 9 | 18-Jul-19 A | 31-Jul-19 A | 4721 | 4839 | 100%
S323600 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Chimney Sector Assembly 3) | 6 | 22-Jul-19 A | 29-Jul-19 A | 0 | 0 | 100%
S299500 | (Cryo Controls Hardware) Rack available from 912 | 0 |  | 24-Jul-19 A | 0 | 0 | 100%
S303800 | Magnet Power Supply Installation: Disconnect Power Supply from Test System in 912 | 1 | 24-Jul-19 A | 24-Jul-19 A | 0 | 0 | 100%
S283000 | Procure RHIC Helium Interface - Provide Requirements to Procurement - Physics Resource(s) | 3 | 24-Jul-19 A | 29-Jul-19 A | 0 | 0 | 100%
S283010 | Procure RHIC Helium Interface - Provide Requirements to Procurement - CA-D Resource(s) | 3 | 24-Jul-19 A | 29-Jul-19 A | 0 | 0 | 100%
S205200 | Design Revision of Outer HCAL Lifting Fixture and Supports | 38 | 24-Jul-19 A | 17-Sep-19 A | 9393 | 9393 | 100%
S295400 | (Controls Hardware) Cryo instrument and equipment specifications 30% | 47 | 24-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S302200 | Magnet: Delivery AC Power Distribution Parts M&S_50% | 47 | 24-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S123700 | Common production line & QA certification | 69 | 25-Jul-19 A | 31-Oct-19 A | 106662 | 106168 | 100%
S283100 | Procure RHIC Helium Interface - Prepare & Send Solicitation | 1 | 30-Jul-19 A | 31-Jul-19 A | 0 | 0 | 100%
S280500 | [Magnet] Procure Parts (for disassembly, transport & reassembly) - Leadtime | 1 | 30-Jul-19 A | 31-Jul-19 A | 0 | 0 | 100%
S250710 | Procure EMCAL 7-Crate Digitizer - Parts - Leadtime Split | 0 | 30-Jul-19 A | 30-Jul-19 A | 0 | 0 | 100%
S250810 | Procure EMCAL 7-Crate Digitizer - Boards - Leadtime Split | 0 | 30-Jul-19 A | 30-Jul-19 A | 0 | 0 | 100%
S280400 | [Magnet] Procure Parts (for disassembly, transport & reassembly) - Contract Award | 0 | 30-Jul-19 A |  | 0 | 0 | 100%
S302100 | Magnet: Design DC Flags 50% | 43 | 30-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S302900 | Magnet: Order Cable Tray and Supports_15% | 43 | 30-Jul-19 A | 30-Sep-19 A | 0 | 0 | 100%
S191700 | Test preproduction prototype Sector 0 with LEDs & cosmic rays_10% | 81 | 30-Jul-19 A | 25-Nov-19 A | 7774 | 7774 | 100%
S191600 | Revise module and sector design based on performance of Sector 0 | 20 | 31-Jul-19 A | 27-Aug-19 A | 74913 | 74913 | 100%
S131900 | Assemble TPC R3b Pre-Production Module in TPC R3b Factory | 21 | 01-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S132000 | Test TPC R3b Pre-Production Module | 21 | 01-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S215900 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 | 102 | 01-Aug-19 A | 31-Dec-19 A | 1277 | 1277 | 100%
S215905 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 6 - Contributed Labor | 102 | 01-Aug-19 A | 31-Dec-19 A | 9579 | 9867 | 100%
S203200 | Populate Outer HCAL sectors with electronics (Preproduction) | 331 | 01-Aug-19 A | 30-Nov-20 A | 3591 | 3591 | 100%
S203210 | Populate Outer HCAL sectors with electronics (Preproduction) - Contributed Labor_50% | 331 | 01-Aug-19 A | 30-Nov-20 A | 60608 | 62426 | 100%
S145100 | Procure TPC DAM Felix 2.0 Boards - Optical - Contract Award(s) | 0 | 01-Aug-19 A |  | 0 | 0 | 100%
S185300 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Contract Award(s) | 0 | 01-Aug-19 A |  | 0 | 0 | 100%
S250400 | Procure EMCAL 7-Crate Digitizer - Parts - Contract Award | 0 | 01-Aug-19 A |  | 0 | 0 | 100%
S250500 | Procure EMCAL 7-Crate Digitizer - Boards - Contract Award | 0 | 01-Aug-19 A |  | 0 | 0 | 100%
S192100 | Final Design Review, Production Readiness Review - EMCal Sectors 1-12 | 1 | 01-Aug-19 A | 01-Aug-19 A | 1337 | 1337 | 100%
S183801 | Final Design Review, Production Readiness Review - EMCal Modules for Sectors 1-12 | 1 | 01-Aug-19 A | 01-Aug-19 A | 2582 | 2582 | 100%
S119200 | (Not needed) Train Technician to work in CERN Shop on TPC GEMs | 5 | 01-Aug-19 A | 07-Aug-19 A | 0 | 0 | 100%
S184900 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Provide Requirements to Procurement | 5 | 01-Aug-19 A | 07-Aug-19 A | 4913 | 4913 | 100%
S145750 | Procure Full Set of Data Fibers for Design Validation - M&S | 10 | 01-Aug-19 A | 14-Aug-19 A | 3173 | 3173 | 100%
S280700 | [Magnet] Assemble and Prepare Parts (Magnet Transport) Labor | 10 | 01-Aug-19 A | 14-Aug-19 A | 0 | 0 | 100%
S280800 | [Magnet] Assemble and Prepare Parts (Magnet Transport) M&S | 10 | 01-Aug-19 A | 14-Aug-19 A | 0 | 0 | 100%
S127502 | Procure TPC R2 Pre-Production Module GEMs Labor Split | 14 | 01-Aug-19 A | 20-Aug-19 A | 0 | 1330 | 100%
S127602 | Procure TPC R2 Pre-Production Module GEMs M&S Split | 14 | 01-Aug-19 A | 20-Aug-19 A | 2758 | 2758 | 100%
S171005 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 5 | 14 | 01-Aug-19 A | 20-Aug-19 A | 40406 | 40406 | 100%
S139730 | Procure second phase of SAMPA development - Delivery of Eng Design Review | 20 | 01-Aug-19 A | 28-Aug-19 A | 52405 | 52405 | 100%
S130900 | Procure TPC R3 Pre-Production Module Frames - Labor | 21 | 01-Aug-19 A | 29-Aug-19 A | 2659 | 2659 | 100%
S131500 | Procure TPC R3 Pre-Production Module GEMs Labor | 21 | 01-Aug-19 A | 29-Aug-19 A | 2659 | 2659 | 100%
S131000 | Procure TPC R3 Pre-Production Module frames - M&S | 21 | 01-Aug-19 A | 29-Aug-19 A | 2207 | 2207 | 100%
S131600 | Procure TPC R3 Pre-Production Module GEMs M&S | 21 | 01-Aug-19 A | 29-Aug-19 A | 11033 | 11033 | 100%
S130502 | Prepare TPC R3b Factory Tooling M&S Split | 21 | 01-Aug-19 A | 30-Aug-19 A | 3972 | 3972 | 100%
S146300 | Miscellaneous Parts for TPC DAM FPGA Algorithm Development - Round 1 | 21 | 01-Aug-19 A | 30-Aug-19 A | 2828 | 2828 | 100%
S146202 | Develop TPC DAM FPGA Algorithm - Round 1 Split | 21 | 01-Aug-19 A | 30-Aug-19 A | 182775 | 182775 | 100%
S307905 | Magnet Field Measurements: Perform Magnet Assembly Stress Analysis FY19 - Physics Resource(s) Split | 21 | 01-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S136802 | v2 Design TPC FEE preproduction prototype Split | 41 | 01-Aug-19 A | 30-Sep-19 A | 91344 | 91344 | 100%
S306500 | Magnet: Order Quench Detector Signal Cables and Interconnects M&S_10% | 41 | 01-Aug-19 A | 30-Sep-19 A | 0 | 0 | 100%
S185400 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Contract/PO - Leadtime | 63 | 01-Aug-19 A | 31-Oct-19 A | 0 | 0 | 100%
S135802 | Design TPC FEE Cooling System Split | 82 | 01-Aug-19 A | 29-Nov-19 A | 19652 | 19652 | 100%
S245000 | Procure Test stand for SiPMs | 101 | 01-Aug-19 A | 30-Dec-19 A | 24272 | 24272 | 100%
S145700 | Procure TPC DAM Felix 2.0 Boards Throughput - Delivery Acceptance | 143 | 01-Aug-19 A | 28-Feb-20 A | 81116 | 81116 | 100%
S306400 | Magnet: Order Quench Detector Signal Cables and Interconnects L | 375 | 01-Aug-19 A | 02-Feb-21 A | 0 | 0 | 100%
S192200 | Procure mechanical parts for Prepro Sectors 1-12 - Provide Requirements to Procurement | 5 | 02-Aug-19 A | 08-Aug-19 A | 2659 | 2659 | 100%
S192900 | Procure parts for cooling system for Prepro Sectors 1-12 - Provide Requirements to Procurement | 5 | 02-Aug-19 A | 08-Aug-19 A | 3431 | 3431 | 100%
S203100 | Populate Outer HCAL sectors with scintillating tiles (Preproduction) | 20 | 02-Aug-19 A | 30-Aug-19 A | 3447 | 3591 | 100%
S203110 | Populate Outer HCAL sectors with scintillating tiles (Preproduction) - Contributed Labor | 20 | 02-Aug-19 A | 30-Aug-19 A | 60608 | 62426 | 100%
S219600 | Sector 0 Production Complete | 0 |  | 07-Aug-19 A | 0 | 0 | 100%
S310100 | Carriage Cradle - Final Review (Design & Safety) - Physics Resource(s) | 1 | 07-Aug-19 A | 08-Aug-19 A | 0 | 0 | 100%
S208800 | Procure Contracted Labor Georgia State Univ. (GSU), Phase 1 - Contract Award | 0 | 07-Aug-19 A |  | 0 | 0 | 100%
S208900 | Procure Contracted Labor Georgia State Univ. (GSU), Phase 1 - Delivery Acceptance | 18 | 07-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S185000 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Prepare & Send Solicitation | 15 | 08-Aug-19 A | 28-Aug-19 A | 0 | 0 | 100%
S306600 | Magnet: Delivery of Quench Detector Signal Cables and Interconnects | 370 | 08-Aug-19 A | 03-Feb-21 A | 0 | 0 | 100%
S192300 | Procure mechanical parts for Prepro Sectors 1-12 - Prepare & Send Solicitation | 15 | 09-Aug-19 A | 29-Aug-19 A | 0 | 0 | 100%
S193000 | Procure parts for cooling system for Prepro Sectors 1-12 - Prepare & Send Solicitation | 15 | 09-Aug-19 A | 29-Aug-19 A | 0 | 0 | 100%
S220700 | Specify Signal and Power Cables per Change Specification - for EMCal: Sectors 1-12 | 15 | 12-Aug-19 A | 30-Aug-19 A | 17395 | 17395 | 100%
S220800 | Specify Power System per Change Specification - for EMCal: Sectors 1-12 | 15 | 12-Aug-19 A | 30-Aug-19 A | 17395 | 17395 | 100%
S302600 | Magnet: Order Power Supply and Quench Detector AC Power Cables and Interconnects Labor 5% | 32 | 14-Aug-19 A | 30-Sep-19 A | 0 | 0 | 100%
S108900 | Assemble TPC v1 Central Membrane | 53 | 14-Aug-19 A | 30-Oct-19 A | 0 | 0 | 100%
S249400 | Final Design Review, Procurement Readiness Review, Electrical Safety Review - Calorimeter Digitizer 7-crate | 5 | 15-Aug-19 A | 22-Aug-19 A | 11438 | 11438 | 100%
S192500 | Procure mechanical parts for Prepro Sectors 1-12 - Vendor Selection | 8 | 15-Aug-19 A | 27-Aug-19 A | 0 | 0 | 100%
S219700 | Review and Write EMCal Electronics Design Change Specifications: Sector 1-12 Labor | 12 | 15-Aug-19 A | 31-Aug-19 A | 5798 | 5798 | 100%
S236900 | Test HCal LED Boards: (6 Modules) | 31 | 15-Aug-19 A | 30-Sep-19 A | 12291 | 12291 | 100%
S280900 | Solenoid Valvebox - Start Disassembly | 0 | 15-Aug-19 A |  | 0 | 0 | 100%
S281000 | Solenoid Valvebox - Disassemble Labor | 11 | 15-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S281100 | Solenoid Valvebox - Disassemble M&S | 11 | 15-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S248400 | Review and write design change specifications for calorimeter digitizer system: 7-Crate Preproduction | 12 | 15-Aug-19 A | 30-Aug-19 A | 4003 | 4003 | 100%
S215000 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 7 | 11 | 16-Aug-19 A | 31-Aug-19 A | 76699 | 76699 | 100%
S127800 | Test TPC R2 Pre-Production Module | 7 | 21-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S192400 | Procure mechanical parts for Prepro Sectors 1-12 - Vendor Responses | 7 | 21-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S185200 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Vendor Selection | 7 | 21-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S146402 | Measure Throughput of FELIX 2.0 for TPC DAM Split | 103 | 21-Aug-19 A | 22-Jan-20 A | 20065 | 20624 | 100%
S127700 | Assemble TPC R2 Pre-Production Module in TPC R2 Factory | 7 | 21-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S139900 | Procure Engineering Run of Full SAMPA Chip - Prepare & Send Solicitation | 5 | 22-Aug-19 A | 29-Aug-19 A | 0 | 0 | 100%
S140000 | Procure Engineering Run of Full SAMPA Chip - Vendor Responses | 6 | 22-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S140100 | Procure Engineering Run of Full SAMPA Chip - Vendor Selection | 6 | 22-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S193200 | Procure parts for cooling system for Prepro Sectors 1-12 - Vendor Selection | 6 | 22-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S249600 | Review Calorimeter Digitizer Safety Review Report | 6 | 22-Aug-19 A | 30-Aug-19 A | 17157 | 17157 | 100%
S193100 | Procure parts for cooling system for Prepro Sectors 1-12 - Vendor Responses | 5 | 23-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S139800 | Procure Engineering Run of Full SAMPA Chip - Provide Requirements to Procurement | 3 | 27-Aug-19 A | 30-Aug-19 A | 6684 | 6884 | 100%
S138901 | Final Design Review - SAMPA chip 80 nsec | 2 | 28-Aug-19 A | 30-Aug-19 A | 2319 | 2319 | 100%
S138900 | Review Design of Full-scale Production Chip (USP + BNL) | 1 | 29-Aug-19 A | 30-Aug-19 A | 5798 | 5798 | 100%
S139735 | Procure second phase of SAMPA development - Delivery of Eng Run Preparation | 1 | 29-Aug-19 A | 30-Aug-19 A | 22065 | 22100 | 100%
S185100 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Vendor Responses | 1 | 29-Aug-19 A | 30-Aug-19 A | 0 | 0 | 100%
S249500 | Calorimeter Digitizer Safety Review Complete | 0 |  | 30-Aug-19 A | 0 | 0 | 100%
S323900 | Completion of Outer HCAL Sector Mechanical Structure Procurement | 0 |  | 03-Sep-19 A | 0 | 0 | 100%
S310110 | Carriage Cradle - Final Review (Design & Safety) - CA-D Resource(s) | 19 | 03-Sep-19 A | 30-Sep-19 A | 0 | 0 | 100%
S131700 | Assemble TPC R3a Pre-Production Module in TPC R3a Factory | 19 | 03-Sep-19 A | 30-Sep-19 A | 0 | 0 | 100%
S131800 | Test TPC R3a Pre-Production Module | 19 | 03-Sep-19 A | 30-Sep-19 A | 0 | 0 | 100%
S304900 | Magnet Power Supply Installation: Design and Test Control Interface update software_50% | 19 | 03-Sep-19 A | 30-Sep-19 A | 0 | 0 | 100%
S161700 | Procure EMCAL W powder for Prepro Sectors 1-12 Blocks - Delivery acceptance Phase 2 of 2 Phases (Sectors 4-12) | 20 | 03-Sep-19 A | 30-Sep-19 A | 242078 | 242078 | 100%
S171006 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 6 | 20 | 03-Sep-19 A | 30-Sep-19 A | 40406 | 40406 | 100%
S193400 | Procure parts for cooling system for Prepro Sectors 1-12 - Contract/PO - Leadtime | 29 | 03-Sep-19 A | 15-Oct-19 A | 0 | 0 | 100%
S192700 | Procure mechanical parts for Prepro Sectors 1-12 - Contract/PO - Leadtime | 34 | 03-Sep-19 A | 22-Oct-19 A | 0 | 0 | 100%
S107905 | Procure TPC v1 Central Membrane Parts M&S FY19 Split | 41 | 03-Sep-19 A | 31-Oct-19 A | 2648 | 2648 | 100%
S251000 | Procure EMCAL 7-Crate Digitizer - Parts - Delivery Acceptance | 57 | 03-Sep-19 A | 25-Nov-19 A | 199806 | 195674 | 100%
S146700 | Develop TPC DAM FPGA Algorithm - Round 2 | 206 | 03-Sep-19 A | 30-Jun-20 A | 125164 | 128365 | 100%
S184800 | Procure light guides for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | 320 | 03-Sep-19 A | 14-Dec-20 A | 89114 | 87930 | 100%
S220900 | Safety and Final Design Review to ensure Change Specifications have been met: EMCal Sectors 1-12 | 10 | 11-Sep-19 A | 24-Sep-19 A | 6685 | 6685 | 100%
S221100 | Review Safety and Design Review Report and Procurement Readiness Review Sectors 1-12 | 10 | 11-Sep-19 A | 24-Sep-19 A | 5798 | 5798 | 100%
S126005 | TPC R1 Module Production Procure Contracted Labor and M&S SBU, Phase 2 - Contract Award | 0 | 12-Sep-19 A |  | 0 | 0 | 100%
S169500 | Establish EMCAL final blocks contract with UIUC | 53 | 12-Sep-19 A | 29-Nov-19 A | 1099 | 1083 | 100%
S151200 | Design TPC Gas Handling System | 135 | 12-Sep-19 A | 31-Mar-20 A | 203019 | 206186 | 100%
S148700 | Design TPC Laser System | 136 | 12-Sep-19 A | 31-Mar-20 A | 81208 | 81208 | 100%
S154100 | Design TPC Cooling System | 273 | 12-Sep-19 A | 14-Oct-20 A | 114994 | 116374 | 100%
S310200 | Carriage Cradle - Address Action Items from Design & Safety Reviews - Physics Resource(s)_25% | 10 | 16-Sep-19 A | 30-Sep-19 A | 0 | 0 | 100%
S310210 | Carriage Cradle - Address Action Items from Design & Safety Reviews - CA-D Resource(s)_25% | 10 | 16-Sep-19 A | 30-Sep-19 A | 0 | 0 | 100%
S204401 | Final Design Review - Outer HCAL Splice Plates (Dog bones) | 1 | 17-Sep-19 A | 18-Sep-19 A | 2354 | 2354 | 100%
S208220 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 0 | 4 | 18-Sep-19 A | 24-Sep-19 A | 204371 | 204371 | 100%
S101000 | Approve Project Baseline and Construction PD2/3 | 0 |  | 20-Sep-19 A | 0 | 0 | 100%
S221000 | Safety and Design Review to ensure Change Specifications have been met -complete: EMCal Electronics: Sectors 1-12 | 0 |  | 24-Sep-19 A | 0 | 0 | 100%
S221200 | Complete: Production Readiness Review, Safety Review - EMCal FEE sectors 1-12 | 0 |  | 24-Sep-19 A | 0 | 0 | 100%
S219800 | EMCal Electronics Review Complete: Preproduction Prototype [Sector 0] | 0 |  | 25-Sep-19 A | 0 | 0 | 100%
S208300 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 1 | 27 | 25-Sep-19 A | 04-Nov-19 A | 159651 | 159651 | 100%
S192600 | Procure mechanical parts for Prepro Sectors 1-12, Phase 1 - Contract Award(s) | 0 | 30-Sep-19 A |  | 0 | 0 | 100%
S193300 | Procure parts for cooling system for Prepro Sectors 1-12 - Contract Award(s) | 0 | 30-Sep-19 A |  | 0 | 0 | 100%
S192620 | Procure mechanical parts for Prepro Sectors 1-12, Phase 2 - Contract Award(s) | 0 | 30-Sep-19 A |  | 0 | 0 | 100%
S310201 | Carriage Cradle - Address Action Items from Design & Safety Reviews - Physics Resource(s)_75% | 11 | 01-Oct-19 A | 17-Oct-19 A | 6853 | 6853 | 100%
S310211 | Carriage Cradle - Address Action Items from Design & Safety Reviews - CA-D Resource(s)_75% | 11 | 01-Oct-19 A | 17-Oct-19 A | 19073 | 19073 | 100%
S283200 | Procure RHIC Helium Interface - Vendor Responses & Selection | 15 | 01-Oct-19 A | 23-Oct-19 A | 0 | 0 | 100%
S310400 | Carriage Cradle - Prepare Procurement Package(s) - Physics Resource(s) | 32 | 01-Oct-19 A | 15-Nov-19 A | 5478 | 5478 | 100%
S310410 | Carriage Cradle - Prepare Procurement Package(s) - CA-D Resource(s) | 32 | 01-Oct-19 A | 15-Nov-19 A | 9675 | 9675 | 100%
S288410 | (LN2 supply transfer line system) LN2 supply transfer line detail layout Split | 46 | 01-Oct-19 A | 09-Dec-19 A | 5432 | 5432 | 100%
S281200 | Magnet - Prepare for Coil Shipment - Shipping Constraints and Tooling | 60 | 01-Oct-19 A | 30-Dec-19 A | 20616 | 20616 | 100%
S305110 | Magnet Power Supply Installation: Documentation Split | 60 | 01-Oct-19 A | 31-Dec-19 A | 43289 | 43270 | 100%
S307511 | Magnet Field Measurements: Setup a detailed 3D model of the coil, return yoke and internal calorimeters FY19 Split_60% | 61 | 01-Oct-19 A | 31-Dec-19 A | 3989 | 3989 | 100%
S307921 | Magnet Field Measurements: Perform Magnet Assembly Stress Analysis FY19 - CA-D Resource(s) Split_70% | 61 | 01-Oct-19 A | 31-Dec-19 A | 7010 | 7010 | 100%
S288100 | (LN2 supply transfer line system) Mechanical Engineering Tasks FY19 | 146 | 01-Oct-19 A | 01-May-20 A | 12780 | 12780 | 100%
S301610 | Magnet: 1008 IR Design Power Supply AC and Quench Detector Power Distribution Split | 349 | 01-Oct-19 A | 26-Feb-21 A | 4418 | 4418 | 100%
S295401 | (Controls Hardware) Cryo instrument and equipment specifications 70% | 456 | 01-Oct-19 A | 2021-07-28 | 22997 | 22997 | 91%
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 458 | 01-Oct-19 A | 2021-07-30 | 11603 | 11603 | 80%
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | 458 | 01-Oct-19 A | 2021-07-30 | 11603 | 11603 | 95%
S307311 | Magnet: Quench Detector Documentation Split_85% | 521 | 01-Oct-19 A | 2021-10-29 | 10867 | 10864 | 90%
S101010 | FY20 funding available | 0 | 01-Oct-19 A |  | 0 | 0 | 100%
S223610 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12 - Contract Award | 0 | 01-Oct-19 A |  | 0 | 0 | 100%
S245100 | Procure Contracted Labor & M&S Univ. Michigan (UM), Phase 2 - Contract Award | 0 | 01-Oct-19 A |  | 0 | 0 | 100%
S205201 | Preliminary Design Review - Outer HCAL Lifting Fixture and Supports | 1 | 01-Oct-19 A | 01-Oct-19 A | 1734 | 1683 | 100%
S215100 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 8 | 2 | 01-Oct-19 A | 03-Oct-19 A | 77557 | 76699 | 100%
S222400 | Fabricate EMCal Interface Board: Sectors 1-12 - Provide Requirements to Fabricator | 5 | 01-Oct-19 A | 07-Oct-19 A | 18184 | 18184 | 100%
S221600 | Fabricate EMCal Preamp Boards: Sectors 1-12 - Provide Requirements to Fabricator | 14 | 01-Oct-19 A | 22-Oct-19 A | 17474 | 17474 | 100%
S171007 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 7 | 21 | 01-Oct-19 A | 30-Oct-19 A | 40858 | 40858 | 100%
S314716 | Steel Track Modifications - Structural Analysis of Existing Steel Track System & Preliminary Design_85% | 21 | 01-Oct-19 A | 30-Oct-19 A | 3880 | 3880 | 100%
S223400 | Test calorimeter controller boards: Sectors 1-12 | 37 | 01-Oct-19 A | 25-Nov-19 A | 18074 | 18074 | 100%
S223600 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12 - Labor | 37 | 01-Oct-19 A | 25-Nov-19 A | 9186 | 9186 | 100%
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures FY20 | 37 | 01-Oct-19 A | 25-Nov-19 A | 14004 | 14004 | 100%
S310006 | Carriage Cradle - Create Assembly & Detail Drawings - Physics Resource(s) Split_10% | 40 | 01-Oct-19 A | 29-Nov-19 A | 2488 | 2488 | 100%
S310016 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) Split_10% | 40 | 01-Oct-19 A | 29-Nov-19 A | 5237 | 5237 | 100%
S111605 | Produce TPC v2 Central Membrane Conceptual Design Split | 60 | 01-Oct-19 A | 31-Dec-19 A | 1307 | 1298 | 100%
S166000 | Fabricate EMCAL Prepro blocks sector 2 | 60 | 01-Oct-19 A | 31-Dec-19 A | 9425 | 9425 | 100%
S237900 | Assemble HCal Power and Signal Cables and Power System: (6 Modules) | 79 | 01-Oct-19 A | 29-Jan-20 A | 18333 | 18312 | 100%
S347900 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - Physics Resource(s) | 85 | 01-Oct-19 A | 05-Feb-20 A | 21205 | 21205 | 100%
S347910 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - CA-D Resource(s) | 85 | 01-Oct-19 A | 05-Feb-20 A | 22229 | 22229 | 100%
S198402 | Design Inner HCAL Support Rings FY20 Split | 114 | 01-Oct-19 A | 18-Mar-20 A | 8913 | 8913 | 100%
S223700 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 1 - M&S | 144 | 01-Oct-19 A | 30-Apr-20 A | 47875 | 47875 | 100%
S223701 | Procure EMCal Internal Signal/Test/Comm/LV/Bias Cables: Sectors 1-12, Phase 2 - M&S | 144 | 01-Oct-19 A | 30-Apr-20 A | 47875 | 47875 | 100%
S329405 | Analyze Detector Support Services Systems Requirements Split - CA-D Resource(s) | 209 | 01-Oct-19 A | 31-Jul-20 A | 2356 | 2356 | 100%
S331705 | Analyze Detector Gas and Cooling Services Systems Requirements Split - CA-D Resource(s) | 209 | 01-Oct-19 A | 31-Jul-20 A | 2356 | 2356 | 100%
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | 209 | 01-Oct-19 A | 31-Jul-20 A | 15122 | 15122 | 100%
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | 209 | 01-Oct-19 A | 31-Jul-20 A | 51164 | 51164 | 100%
S337300 | Create Cryo Routing in IR Layout Drawings - Physics Resource(s) | 230 | 01-Oct-19 A | 31-Aug-20 A | 3534 | 3534 | 100%
S337310 | Create Cryo Routing in IR Layout Drawings - CA-D Resource(s) | 230 | 01-Oct-19 A | 31-Aug-20 A | 13241 | 12978 | 100%
S104100 | Travel FY20 | 250 | 01-Oct-19 A | 30-Sep-20 A | 27080 | 27080 | 100%
S103000 | Mgmt Labor - A - MIE - FY20 | 250 | 01-Oct-19 A | 30-Sep-20 A | 245877 | 245877 | 100%
S103110 | Mgmt labor - B - BNL Contributed Labor - FY20 - CA-D Resource(s) | 250 | 01-Oct-19 A | 30-Sep-20 A | 150254 | 150254 | 100%
S103100 | Mgmt labor - B - BNL Contributed Labor - FY20 - Physics Resource(s) | 250 | 01-Oct-19 A | 30-Sep-20 A | 1545368 | 1545368 | 100%
S274600 | 2020 Magnet Project Management | 250 | 01-Oct-19 A | 30-Sep-20 A | 151453 | 151453 | 100%
S275200 | 2020 Cryo L3 Project Management | 250 | 01-Oct-19 A | 30-Sep-20 A | 67934 | 67934 | 100%
S275700 | 2020 PS & Quench Protection L3 Project Management | 250 | 01-Oct-19 A | 30-Sep-20 A | 59862 | 59862 | 100%
S278000 | 2020 Integration & Installation Project Management | 250 | 01-Oct-19 A | 30-Sep-20 A | 281046 | 281046 | 100%
S276200 | 2020 Infrastructure Project Management | 250 | 01-Oct-19 A | 30-Sep-20 A | 251694 | 251694 | 100%
S276800 | 2020 Facility Support Systems L3 Project Management | 250 | 01-Oct-19 A | 30-Sep-20 A | 35277 | 35277 | 100%
S277400 | 2020 Detector Support Systems L3 Project Management | 250 | 01-Oct-19 A | 30-Sep-20 A | 124659 | 109328 | 100%
S224200 | Procure EMCal Low Voltage Power Systems: Sectors 1-12 - Labor | 414 | 01-Oct-19 A | 28-May-21 A | 9186 | 9186 | 100%
S224300 | Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 1 - M&S | 414 | 01-Oct-19 A | 28-May-21 A | 3505 | 3505 | 100%
S224400 | Procure EMCal Low Voltage Power Systems: Sectors 1-12, Phase 2 - M&S | 414 | 01-Oct-19 A | 28-May-21 A | 14019 | 14019 | 100%
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures FY20 | 450 | 01-Oct-19 A | 2021-07-20 | 22531 | 22531 | 95%
S221900 | Fabricate EMCal Preamp Boards: Sectors 1-12 - Vendor Selection | 13 | 02-Oct-19 A | 22-Oct-19 A | 0 | 0 | 100%
S205300 | Final Design Review, Procurement Readiness Review - Outer HCAL Lifting Fixture and Supports | 1 | 02-Oct-19 A | 02-Oct-19 A | 3468 | 3367 | 100%
S123900 | Procure TPC R1 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | 5 | 02-Oct-19 A | 08-Oct-19 A | 24033 | 24033 | 100%
S127900 | Procure TPC R2 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | 5 | 02-Oct-19 A | 08-Oct-19 A | 24033 | 24033 | 100%
S132100 | Procure TPC R3 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Provide Requirements to Procurement | 5 | 02-Oct-19 A | 08-Oct-19 A | 24033 | 24033 | 100%
S205400 | Address Issues from Internal Review of Outer HCAL Lifting Fixture and Supports | 10 | 03-Oct-19 A | 17-Oct-19 A | 4837 | 4697 | 100%
S111700 | Procure TPC v2 Central Membrane Parts Labor | 96 | 08-Oct-19 A | 28-Feb-20 A | 0 | 0 | 100%
S222500 | Fabricate EMCal Interface Board: Sectors 1-12 - Prepare & Send Solicitation | 2 | 08-Oct-19 A | 10-Oct-19 A | 0 | 0 | 100%
S221700 | Fabricate EMCal Preamp Boards: Sectors 1-12 - Prepare & Send Solicitation | 9 | 08-Oct-19 A | 22-Oct-19 A | 0 | 0 | 100%
S221800 | Fabricate EMCal Preamp Boards: Sectors 1-12 - Vendor Responses | 8 | 09-Oct-19 A | 22-Oct-19 A | 0 | 0 | 100%
S185800 | Install reflectors on blocks for modules for Prepro Sectors 1-12 M&S | 266 | 09-Oct-19 A | 30-Oct-20 A | 398 | 398 | 100%
S124000 | Procure TPC R1 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Prepare & Send Solicitation | 54 | 09-Oct-19 A | 31-Dec-19 A | 0 | 0 | 100%
S128000 | Procure TPC R2 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Prepare & Send Solicitation | 54 | 09-Oct-19 A | 31-Dec-19 A | 0 | 0 | 100%
S132200 | Procure TPC R3 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Prepare & Send Solicitation | 54 | 09-Oct-19 A | 31-Dec-19 A | 0 | 0 | 100%
S222600 | Fabricate EMCal Interface Board: Sectors 1-12 - Vendor Responses | 2 | 10-Oct-19 A | 14-Oct-19 A | 0 | 0 | 100%
S111800 | Procure TPC v2 Central Membrane Parts M&S | 94 | 10-Oct-19 A | 28-Feb-20 A | 9103 | 9103 | 100%
S192810 | Procure mechanical parts for Prepro Sectors 1-12, Phase 2 - Delivery Acceptance | 158 | 10-Oct-19 A | 29-May-20 A | 41873 | 41873 | 100%
S222700 | Fabricate EMCal Interface Board: Sectors 1-12 - Vendor Selection | 1 | 15-Oct-19 A | 16-Oct-19 A | 0 | 0 | 100%
S185500 | Procure mechanical parts for modules in Sectors (Prepro) 1-12 - Delivery Acceptance | 11 | 16-Oct-19 A | 31-Oct-19 A | 14961 | 14961 | 100%
S185600 | Receive, unpack, log & inspect blocks for Prepro Sectors 1-12 M&S | 262 | 16-Oct-19 A | 30-Oct-20 A | 0 | 0 | 100%
S193500 | Procure parts for cooling system for Prepro Sectors 1-12 - Delivery Acceptance | 290 | 16-Oct-19 A | 14-Dec-20 A | 22508 | 22508 | 100%
S205500 | Outer HCAL Lifting Fixture and Supports Design Complete | 0 |  | 17-Oct-19 A | 0 | 0 | 100%
S343809 | Start Track Modification - IR | 0 | 18-Oct-19 A |  | 0 | 0 | 100%
S311800 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - Physics Resource(s) | 133 | 18-Oct-19 A | 30-Apr-20 A | 1712 | 1712 | 100%
S311810 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - CA-D Resource(s) | 133 | 18-Oct-19 A | 30-Apr-20 A | 17014 | 17014 | 100%
S343810 | Start Track Modification - IR Structural Analysis of Existing Track System and Prelim Design | 218 | 18-Oct-19 A | 31-Aug-20 A | 21072 | 21072 | 100%
S343848 | Start Track Modification - AH Structural Analysis of Existing Track System and Prelim. Design | 238 | 18-Oct-19 A | 30-Sep-20 A | 24432 | 24432 | 100%
S185700 | Receive, unpack, log & inspect blocks for Prepro Sectors 1-12 Labor | 259 | 21-Oct-19 A | 30-Oct-20 A | 67938 | 67938 | 100%
S185900 | Install reflectors on blocks for modules for Prepro Sectors 1-12 Labor | 259 | 21-Oct-19 A | 30-Oct-20 A | 70791 | 70791 | 100%
S222000 | Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 1 - Contract Award(s) | 0 | 22-Oct-19 A |  | 0 | 0 | 100%
S222001 | Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 2 - Contract Award(s) | 0 | 22-Oct-19 A |  | 0 | 0 | 100%
S284000 | RHIC Helium Interface - Kick off meeting elapsed after contract award | 3 | 23-Oct-19 A | 28-Oct-19 A | 0 | 0 | 100%
S192800 | Procure mechanical parts for Prepro Sectors 1-12, Phase 1 - Delivery Acceptance | 150 | 23-Oct-19 A | 29-May-20 A | 41873 | 41873 | 100%
S283300 | Procure RHIC Helium Interface - Contract Award | 0 | 24-Oct-19 A |  | 0 | 0 | 100%
S283400 | Procure RHIC Helium Interface, Phase 2 (Long Lead Items) - Contract Award | 0 | 24-Oct-19 A |  | 0 | 0 | 100%
S283500 | Procure RHIC Helium Interface, Phase 3 (Final Design Review) - Contract Award | 0 | 24-Oct-19 A |  | 0 | 0 | 100%
S283600 | Procure RHIC Helium Interface, Phase 4 (Drawings Approvals) - Contract Award | 0 | 24-Oct-19 A |  | 0 | 0 | 100%
S283700 | Procure RHIC Helium Interface, Phase 5 (Raw Materials) - Contract Award | 0 | 24-Oct-19 A |  | 0 | 0 | 100%
S283800 | Procure RHIC Helium Interface, Phase 6 (BNL Holdpoint Witness) - Contract Award | 0 | 24-Oct-19 A |  | 0 | 0 | 100%
S283900 | Procure RHIC Helium Interface, Phase 7 (Shipping) - Contract Award | 0 | 24-Oct-19 A |  | 0 | 0 | 100%
S313300 | CC Seismic Restraints - Engineer & Analysis | 105 | 28-Oct-19 A | 31-Mar-20 A | 55751 | 55751 | 100%
S315010 | Steel Track Modifications - Final Design Reviews (Design & Safety) | 1 | 30-Oct-19 A | 31-Oct-19 A | 1178 | 1178 | 100%
S140300 | Procure Engineering Run of Full SAMPA Chip - Leadtime | 71 | 30-Oct-19 A | 13-Feb-20 A | 0 | 0 | 100%
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | 209 | 30-Oct-19 A | 31-Aug-20 A | 4027 | 13423 | 100%
S140200 | Procure Engineering Run of Full SAMPA Chip - Contract Award | 0 | 31-Oct-19 A |  | 0 | 0 | 100%
S310300 | Carriage Cradle - Design & Safety Reviews Complete Released for Production | 0 |  | 01-Nov-19 A | 0 | 0 | 100%
S205600 | Procure Outer HCAL Lifting Fixtures & Supports - Provide Requirements to Procurement | 15 | 01-Nov-19 A | 25-Nov-19 A | 25016 | 24287 | 100%
S317300 | Procure & Deliver Internal Detector Structural Support (leadtime and fabrication included) - Labor - Physics Resource(s) | 17 | 01-Nov-19 A | 27-Nov-19 A | 0 | 0 | 100%
S170200 | Procure EMCAL W Powder for Final Blocks - Sectors 13-38 - Delivery Acceptance | 18 | 01-Nov-19 A | 29-Nov-19 A | 540981 | 540981 | 100%
S317310 | Procure & Deliver Internal Detector Structural Support (leadtime and fabrication included) - Labor - CA-D Resource(s) | 18 | 01-Nov-19 A | 29-Nov-19 A | 0 | 0 | 100%
S124100 | Procure TPC R1 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Vendor Responses | 38 | 01-Nov-19 A | 31-Dec-19 A | 0 | 0 | 100%
S324000 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - Physics Resource(s) | 101 | 01-Nov-19 A | 31-Mar-20 A | 7989 | 7989 | 100%
S324010 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - CA-D Resource(s) | 101 | 01-Nov-19 A | 31-Mar-20 A | 67141 | 67141 | 100%
S325700 | CC Bridge, Mid Platforms & Access - Engineering Analysis - Physics Resource(s) | 101 | 01-Nov-19 A | 31-Mar-20 A | 18260 | 18260 | 100%
S325710 | CC Bridge, Mid Platforms & Access - Engineering Analysis - CA-D Resource(s) | 101 | 01-Nov-19 A | 31-Mar-20 A | 92594 | 92594 | 100%
S302601 | Magnet: Order Power Supply and Quench Detector AC Power Cables and Interconnects Labor 95% | 327 | 01-Nov-19 A | 26-Feb-21 A | 1119 | 1119 | 100%
S304310 | Magnet Power Supply Installation: Cooling Water Design Split | 371 | 01-Nov-19 A | 28-Apr-21 A | 9425 | 9425 | 100%
S222800 | Fabricate EMCal Interface Board: Sectors 1-12, Phase 1 - Contract Award(s) | 0 | 01-Nov-19 A |  | 0 | 0 | 100%
S222801 | Fabricate EMCal Interface Board: Sectors 1-12, Phase 2 - Contract Award(s) | 0 | 01-Nov-19 A |  | 0 | 0 | 100%
S215200 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 9 | 9 | 01-Nov-19 A | 14-Nov-19 A | 77557 | 77512 | 100%
S315110 | Steel Track Modifications - Address Action Items from Design & Safety Reviews | 10 | 01-Nov-19 A | 15-Nov-19 A | 1012 | 1012 | 100%
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | 15 | 01-Nov-19 A | 25-Nov-19 A | 26811 | 27616 | 100%
S340702 | Model IR Electronics Cooling Water Distribution Thermal Requirements - Physics Resource(s) Split | 15 | 01-Nov-19 A | 25-Nov-19 A | 5163 | 5318 | 100%
S327502 | Gather Design Requirements for All sPHENIX Subsystems for Line Electric Power Split | 30 | 01-Nov-19 A | 18-Dec-19 A | 5060 | 5060 | 100%
S222100 | Fabricate EMCal Preamp Boards: Sectors 1-12 - Contract/PO - Leadtime | 40 | 01-Nov-19 A | 02-Jan-20 A | 0 | 0 | 100%
S110505 | Produce TPC v2 Inner Field Cage Conceptual Design Split | 57 | 01-Nov-19 A | 29-Jan-20 A | 523 | 519 | 100%
S222900 | Fabricate EMCal Interface Board: Sectors 1-12 - Contract/PO - Leadtime | 78 | 01-Nov-19 A | 28-Feb-20 A | 0 | 0 | 100%
S223800 | Procure EMCal External LV/Bias Cables: Sectors 1-12 - Labor | 122 | 01-Nov-19 A | 30-Apr-20 A | 9186 | 9186 | 100%
S316406 | Analyze and Evaluate Structural Support for Internal Detectors FY19 - Physics Resource(s) Split_75% | 187 | 01-Nov-19 A | 31-Jul-20 A | 3852 | 3852 | 100%
S203300 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) Labor | 288 | 04-Nov-19 A | 30-Dec-20 A | 3591 | 3591 | 100%
S203400 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) M&S | 288 | 04-Nov-19 A | 30-Dec-20 A | 5462 | 5462 | 100%
S203310 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) - Contributed Labor | 288 | 04-Nov-19 A | 30-Dec-20 A | 48275 | 48275 | 100%
S124200 | Procure TPC R1 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Vendor Selection | 58 | 06-Nov-19 A | 03-Feb-20 A | 0 | 0 | 100%
S191800 | Analyze test results from preproduction prototype Sector 0 | 11 | 07-Nov-19 A | 25-Nov-19 A | 17604 | 17091 | 100%
S191900 | Performance review of preproduction prototype Sector 0 | 11 | 07-Nov-19 A | 25-Nov-19 A | 77160 | 75812 | 100%
S171008 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 8 | 10 | 08-Nov-19 A | 25-Nov-19 A | 40858 | 40858 | 100%
S208302 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 2 | 9 | 12-Nov-19 A | 25-Nov-19 A | 126291 | 126291 | 100%
S205700 | Procure Outer HCAL Lifting Fixtures & Supports - Prepare & Send Solicitation | 2 | 13-Nov-19 A | 15-Nov-19 A | 0 | 0 | 100%
S203050 | Production Readiness Review - Outer HCAL Sector Assembly 1-6 | 3 | 13-Nov-19 A | 18-Nov-19 A | 1330 | 1330 | 100%
S254700 | DAQ Prototype: Software development - INTT FELIX/DCM2 Downselect Review | 5 | 13-Nov-19 A | 20-Nov-19 A | 45887 | 44550 | 100%
S304901 | Magnet Power Supply Installation: Design and Test Control Interface update software_50% | 11 | 13-Nov-19 A | 29-Nov-19 A | 13938 | 13938 | 100%
S193710 | Build mechanical stand/support for Prepro Sectors 1-12 - M&S | 221 | 13-Nov-19 A | 30-Sep-20 A | 569 | 569 | 100%
S193600 | Build mechanical enclosure for Prepro Sectors 1-12 | 289 | 13-Nov-19 A | 11-Jan-21 A | 38345 | 38345 | 100%
S206200 | Procure Outer HCAL Lifting Fixtures & Supports - Delivery Acceptance | 46 | 14-Nov-19 A | 23-Jan-20 A | 45517 | 45517 | 100%
S193700 | Build mechanical stand/support for Prepro Sectors 1-12 - Labor | 220 | 14-Nov-19 A | 30-Sep-20 A | 38345 | 38345 | 100%
S205800 | Procure Outer HCAL Lifting Fixtures & Supports - Vendor Responses | 4 | 15-Nov-19 A | 21-Nov-19 A | 0 | 0 | 100%
S349900 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - Labor | 49 | 15-Nov-19 A | 30-Jan-20 A | 18024 | 18024 | 100%
S350000 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - M&S | 49 | 15-Nov-19 A | 30-Jan-20 A | 68276 | 68276 | 100%
S284200 | Procure RHIC Helium Interface, MS1 (Manufacturing Program Plan) - Leadtime | 5 | 18-Nov-19 A | 25-Nov-19 A | 0 | 0 | 100%
S284220 | Procure RHIC Helium Interface, MS1 (Manufacturing Program Plan) - Delivery Acceptance | 5 | 18-Nov-19 A | 25-Nov-19 A | 174667 | 174667 | 100%
S310500 | Carriage Cradle - Procurement Readiness Review - Physics Resource(s) | 5 | 18-Nov-19 A | 22-Nov-19 A | 4108 | 4108 | 100%
S310510 | Carriage Cradle - Procurement Readiness Review - CA-D Resource(s) | 5 | 18-Nov-19 A | 22-Nov-19 A | 4904 | 4904 | 100%
S315900 | Steel Track Modifications - BNL Oversight Construction - Physics Resource(s) | 50 | 18-Nov-19 A | 31-Jan-20 A | 9130 | 9130 | 100%
S315910 | Steel Track Modifications - BNL Oversight Construction - CA-D Resource(s) | 50 | 18-Nov-19 A | 31-Jan-20 A | 55193 | 55193 | 100%
S205900 | Procure Outer HCAL Lifting Fixtures & Supports - Vendor Selection | 4 | 19-Nov-19 A | 25-Nov-19 A | 0 | 0 | 100%
S251100 | Procure EMCAL 7-Crate Digitizer (Boards) - Delivery Acceptance | 154 | 19-Nov-19 A | 30-Jun-20 A | 44801 | 43437 | 100%
S206100 | Procure Outer HCAL Lifting Fixtures & Supports - Contract/PO - Leadtime | 5 | 20-Nov-19 A | 27-Nov-19 A | 0 | 0 | 100%
S1005160 | AET submits PDR report to BNL for approval of Multiple Transfer Line Spools and Field Joint Sleeve | 37 | 20-Nov-19 A | 15-Jan-20 A | 0 | 0 | 100%
S306501 | Magnet: Order Quench Detector Signal Cables and Interconnects M&S_90% | 299 | 20-Nov-19 A | 02-Feb-21 A | 2048 | 2048 | 100%
S288200 | (LN2 supply transfer line system) SOW & Technical Specifications | 110 | 22-Nov-19 A | 01-May-20 A | 11502 | 11502 | 100%
S179600 | Procure Contracted Labor and M&S Univ. Illinois Urbana-Champaign (UIUC) - Contract Award FY19 | 0 | 25-Nov-19 A |  | 0 | 0 | 100%
S179601 | Procure Contracted Labor and M&S Univ. Illinois Urbana-Champaign (UIUC) - Contract Award FY20 | 0 | 25-Nov-19 A |  | 0 | 0 | 100%
S192000 | EMCal Preproduction Sector 0 Assembled | 0 |  | 25-Nov-19 A | 0 | 0 | 100%
S221300 | Fabricate EMCal SiPM Boards: Sectors 1-12 - M&S | 122 | 25-Nov-19 A | 20-May-20 A | 29002 | 29002 | 100%
S226500 | Review and Write EMCal Electronics Design Change Specifications: Final Production | 127 | 25-Nov-19 A | 28-May-20 A | 5972 | 5972 | 100%
S203500 | Outer HCAL Cosmics testing and initial calibration (Preproduction) | 274 | 25-Nov-19 A | 30-Dec-20 A | 3591 | 3591 | 100%
S203510 | Outer HCAL Cosmics testing and initial calibration (Preproduction) - Contributed Labor | 274 | 25-Nov-19 A | 30-Dec-20 A | 19973 | 19973 | 100%
S310600 | Carriage Cradle - Provide Requirement to Procurement | 23 | 25-Nov-19 A | 31-Dec-19 A | 1361 | 1361 | 100%
S206000 | Procure Outer HCAL Lifting Fixtures & Supports - Contract Award(s) | 0 | 27-Nov-19 A |  | 0 | 0 | 100%
S101012 | IR Ready for Prep | 0 | 29-Nov-19 A |  | 0 | 0 | 100%
S128100 | Procure TPC R2 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Vendor Responses | 20 | 02-Dec-19 A | 31-Dec-19 A | 0 | 0 | 100%
S128200 | Procure TPC R2 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Vendor Selection | 43 | 02-Dec-19 A | 03-Feb-20 A | 0 | 0 | 100%
S132300 | Procure TPC R3 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Vendor Responses | 43 | 02-Dec-19 A | 03-Feb-20 A | 0 | 0 | 100%
S210600 | Procure Contracted Labor Georgia State Univ. (GSU), Phase 2 - Contract Award | 0 | 02-Dec-19 A |  | 0 | 0 | 100%
S250600 | Procure EMCAL 7-Crate Digitizer - Assembly & Tests - Contract Award | 0 | 02-Dec-19 A |  | 0 | 0 | 100%
S116801 | Final Design Review - TPC Module | 1 | 02-Dec-19 A | 02-Dec-19 A | 1277 | 1240 | 100%
S109000 | Assemble TPC v1 Field Cage Prototype | 15 | 02-Dec-19 A | 23-Dec-19 A | 0 | 0 | 100%
S210700 | Procure Contracted Labor Georgia State Univ. (GSU), Phase 2 - Delivery Acceptance | 21 | 02-Dec-19 A | 31-Dec-19 A | 0 | 0 | 100%
S311900 | CC Drive & Alignment System - Design Carriage Controls & Limits | 191 | 02-Dec-19 A | 01-Sep-20 A | 17672 | 17672 | 100%
S137300 | v2 Modify TPC FEE Test Stand Labor | 210 | 02-Dec-19 A | 30-Sep-20 A | 54538 | 54538 | 100%
S137400 | v2 Modify TPC FEE Test Stand M&S | 210 | 02-Dec-19 A | 30-Sep-20 A | 9103 | 9103 | 100%
S344700 | Create Services Management Plan | 288 | 02-Dec-19 A | 27-Jan-21 A | 19998 | 19998 | 100%
S302201 | Magnet: Delivery AC Power Distribution Parts M&S_50% | 309 | 02-Dec-19 A | 26-Feb-21 A | 11379 | 11379 | 100%
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | 406 | 02-Dec-19 A | 2021-07-14 | 25605 | 26373 | 95%
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | 439 | 02-Dec-19 A | 2021-08-30 | 9737 | 9737 | 85%
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 500 | 02-Dec-19 A | 2021-11-30 | 76474 | 77305 | 76%
S171009 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 9 | 11 | 03-Dec-19 A | 18-Dec-19 A | 40858 | 40858 | 100%
S293300 | (GN2 Vent Line from platform coldbox) Detailed drawing package with weld map | 152 | 09-Dec-19 A | 15-Jul-20 A | 17464 | 17464 | 100%
S288500 | (LN2 supply transfer line system) Detailed dwg package for Procurement | 148 | 10-Dec-19 A | 10-Jul-20 A | 24445 | 24445 | 100%
S167300 | Pack and ship EMCAL blocks for Prepro sector 2 to BNL Purchased Services | 31 | 11-Dec-19 A | 28-Jan-20 A | 866 | 866 | 100%
S167400 | Pack and ship EMCAL blocks for Prepro sector 2 to BNL M&S | 31 | 11-Dec-19 A | 28-Jan-20 A | 1229 | 1229 | 100%
S215300 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 10 | 10 | 16-Dec-19 A | 31-Dec-19 A | 77557 | 77557 | 100%
S310700 | Carriage Cradle - Prepare & Send Solicitation | 31 | 16-Dec-19 A | 31-Jan-20 A | 0 | 0 | 100%
S293500 | (Current Leads Warm Piping) Detailed drawing package with weld map | 408 | 16-Dec-19 A | 2021-07-30 | 27992 | 27992 | 85%
S123800 | Production Readiness Review - TPC Module Factories | 1 | 17-Dec-19 A | 17-Dec-19 A | 1277 | 1277 | 100%
S313400 | CC Seismic Restraints - Assembly & Detail Drawings - Physics Resource(s) | 397 | 17-Dec-19 A | 2021-07-16 | 13695 | 13695 | 95%
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 397 | 17-Dec-19 A | 2021-07-16 | 32278 | 32278 | 95%
S266600 | GL1 Prototype: test prototype | 407 | 17-Dec-19 A | 2021-07-30 | 44131 | 44131 | 95%
S166100 | Fabricate EMCAL Prepro blocks sector 3 | 28 | 19-Dec-19 A | 31-Jan-20 A | 9425 | 9425 | 100%
S269400 | Timing System Prototype: test prototype | 48 | 19-Dec-19 A | 28-Feb-20 A | 4131 | 4123 | 100%
S140400 | Procure Engineering Run of Full SAMPA Chip - Delivery Acceptance | 130 | 30-Dec-19 A | 06-Jul-20 A | 265137 | 265137 | 100%
S126010 | TPC R1 Module Production Procure Contracted Labor and M&S Wayne, Phase 2 - Contract Award | 0 | 02-Jan-20 A |  | 0 | 0 | 100%
S146201 | Final Design Review - TPC DAM | 1 | 02-Jan-20 A | 02-Jan-20 A | 1277 | 1240 | 100%
S327600 | Evaluate Normal, Emergency and UPS Load Requirements for Line Electric Power | 5 | 02-Jan-20 A | 08-Jan-20 A | 2530 | 2530 | 100%
S225500 | Procure EMCal External Bias Power System: Sectors 1-12 - Provide Requirements to Procurement | 10 | 02-Jan-20 A | 15-Jan-20 A | 9186 | 9186 | 100%
S215310 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 11 | 11 | 02-Jan-20 A | 16-Jan-20 A | 77557 | 77557 | 100%
S109605 | Produce TPC v2 Outer Field Cage Conceptual Design Split | 17 | 02-Jan-20 A | 28-Jan-20 A | 523 | 517 | 100%
S109305 | Produce TPC v2 Field Cage Prototype Conceptual Design Split | 18 | 02-Jan-20 A | 29-Jan-20 A | 1046 | 1038 | 100%
S216000 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 | 20 | 02-Jan-20 A | 30-Jan-20 A | 1277 | 1277 | 100%
S216005 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 7 - Contributed Labor | 20 | 02-Jan-20 A | 30-Jan-20 A | 9867 | 9867 | 100%
S171010 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 10 | 21 | 02-Jan-20 A | 31-Jan-20 A | 40858 | 40858 | 100%
S109100 | Benchtest TPC v1 Field Cage Prototype | 39 | 02-Jan-20 A | 28-Feb-20 A | 0 | 0 | 100%
S136900 | v2 Procure TPC FEE preproducion prototype components Labor | 189 | 02-Jan-20 A | 30-Sep-20 A | 2356 | 2356 | 100%
S111400 | Design TPC Field Cage Prototype v2 End Rings | 17 | 03-Jan-20 A | 29-Jan-20 A | 4182 | 4182 | 100%
S222200 | Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 1 - Delivery Acceptance | 5 | 03-Jan-20 A | 09-Jan-20 A | 89811 | 89811 | 100%
S222201 | Fabricate EMCal Preamp Boards: Sectors 1-12, Phase 2 - Delivery Acceptance | 5 | 03-Jan-20 A | 09-Jan-20 A | 89811 | 89811 | 100%
S274300 | RHIC FY20 Run | 176 | 06-Jan-20 A | 15-Sep-20 A | 0 | 0 | 100%
S255000 | DAQ Prototype: Review of DAQ Prototype Results and Production Readiness Review | 16 | 07-Jan-20 A | 30-Jan-20 A | 19659 | 19659 | 100%
S281300 | Magnet - Coil Ready to Ship | 0 | 07-Jan-20 A |  | 0 | 0 | 100%
S120400 | Procure TPC Membrane HV Cables - M&S | 8 | 08-Jan-20 A | 20-Jan-20 A | 683 | 683 | 100%
S120300 | Procure TPC Membrane HV Cables - Labor | 12 | 08-Jan-20 A | 27-Jan-20 A | 3652 | 3652 | 100%
S310800 | Carriage Cradle - Vendor Responses - Physics Resource(s) | 50 | 08-Jan-20 A | 19-Mar-20 A | 4108 | 4108 | 100%
S310810 | Carriage Cradle - Vendor Responses - CA-D Resource(s) | 50 | 08-Jan-20 A | 19-Mar-20 A | 15532 | 15532 | 100%
S186000 | Install light guides on preproduction prototype blocks Labor | 252 | 09-Jan-20 A | 11-Jan-21 A | 70791 | 70791 | 100%
S327700 | Calculate Power Transformer Requirements for Line Electric Power - CA-D Resource(s) | 14 | 09-Jan-20 A | 30-Jan-20 A | 4182 | 4182 | 100%
S1001999 | Calculate Power Transformer Requirements for Line Electric Power - Physics Resource(s) | 14 | 09-Jan-20 A | 30-Jan-20 A | 10455 | 10455 | 100%
S109700 | Procure TPC v2 Outer Field Cage Parts - Provide Requirements to Procurement | 11 | 10-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S109800 | Procure TPC v2 Outer Field Cage Parts - Prepare & Send Solicitation | 11 | 10-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S109900 | Procure TPC v2 Outer Field Cage Parts - Vendor Responses | 11 | 10-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S110000 | Procure TPC v2 Outer Field Cage Parts - Vendor Selection | 11 | 10-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S222300 | Test EMCal Preamp Boards: Sectors 1-12 | 182 | 10-Jan-20 A | 29-Sep-20 A | 1915 | 1915 | 100%
S110300 | Procure TPC v2 Outer Field Cage Parts - Delivery Acceptance | 76 | 13-Jan-20 A | 30-Apr-20 A | 86285 | 86285 | 100%
S111000 | Procure TPC v2 Inner Field Cage Parts - Contract Award(s) | 0 | 14-Jan-20 A |  | 0 | 0 | 100%
S117600 | Procure TPC v2 Module Grid Parts Labor | 9 | 14-Jan-20 A | 28-Jan-20 A | 2739 | 2739 | 100%
S117800 | Assemble TPC v2 Module Grid | 9 | 14-Jan-20 A | 28-Jan-20 A | 9130 | 9130 | 100%
S117700 | Procure TPC v2 Module Grid Parts M&S | 9 | 14-Jan-20 A | 28-Jan-20 A | 569 | 569 | 100%
S111300 | Assemble TPC v2 Inner Field Cage | 9 | 14-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S111200 | Procure TPC v2 Inner Field Cage Parts - Delivery Acceptance | 9 | 14-Jan-20 A | 28-Jan-20 A | 39326 | 39326 | 100%
S110600 | Procure TPC v2 Inner Field Cage Parts - Provide Requirements to Procurement | 9 | 14-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S110700 | Procure TPC v2 Inner Field Cage Parts - Prepare & Send Solicitation | 9 | 14-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S110800 | Procure TPC v2 Inner Field Cage Parts - Vendor Responses | 9 | 14-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S110900 | Procure TPC v2 Inner Field Cage Parts - Vendor Selection | 9 | 14-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S111100 | Procure TPC v2 Inner Field Cage Parts - Contract/PO - Leadtime | 9 | 14-Jan-20 A | 28-Jan-20 A | 0 | 0 | 100%
S254900 | DAQ Prototype: Installation and testing | 9 | 15-Jan-20 A | 29-Jan-20 A | 7319 | 7319 | 100%
S117500 | Design TPC v2 Module Grid | 10 | 15-Jan-20 A | 30-Jan-20 A | 2091 | 2091 | 100%
S221500 | Test EMCal SiPM Daughter Boards: Sectors 1-12 | 219 | 15-Jan-20 A | 30-Nov-20 A | 12310 | 12310 | 100%
S225600 | Procure EMCal External Bias Power System: Sectors 1-12 - Prepare & Send Solicitation | 8 | 16-Jan-20 A | 29-Jan-20 A | 0 | 0 | 100%
S1005200 | BNL review for PDR approval | 29 | 16-Jan-20 A | 27-Feb-20 A | 26200 | 26200 | 100%
S308600 | Magnet Field Measurements: Fabricate NMR probe mounts - Physics Resource(s) | 69 | 16-Jan-20 A | 24-Apr-20 A | 21013 | 21013 | 100%
S208303 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 3 | 7 | 20-Jan-20 A | 30-Jan-20 A | 126291 | 126291 | 100%
S208304 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 4 | 7 | 20-Jan-20 A | 30-Jan-20 A | 126291 | 126291 | 100%
S238000 | HCal Preproduction Electronics Complete | 0 |  | 22-Jan-20 A | 0 | 0 | 100%
S238100 | HCal Preproduction FEE Complete | 0 |  | 22-Jan-20 A | 0 | 0 | 100%
S308700 | Magnet Field Measurements: Run 3D field simulations and construct field and force maps - Physics Resource(s) | 20 | 24-Jan-20 A | 24-Feb-20 A | 6884 | 6884 | 100%
S308710 | Magnet Field Measurements: Run 3D field simulations and construct field and force maps - CA-D Resource(s) | 20 | 24-Jan-20 A | 24-Feb-20 A | 6884 | 6884 | 100%
S308100 | Magnet Field Measurements: Procure NMR probes Labor | 40 | 24-Jan-20 A | 20-Mar-20 A | 1473 | 1473 | 100%
S308300 | Magnet Field Measurements: Procure NMR probe readout parts Labor | 64 | 24-Jan-20 A | 24-Apr-20 A | 1473 | 1473 | 100%
S308200 | Magnet Field Measurements: Procure NMR probes M&S | 64 | 24-Jan-20 A | 24-Apr-20 A | 6828 | 6828 | 100%
S308400 | Magnet Field Measurements: Procure NMR probe readout parts M&S | 64 | 24-Jan-20 A | 24-Apr-20 A | 1138 | 1138 | 100%
S109200 | Preliminary Design Review - TPC Field Cage | 3 | 27-Jan-20 A | 30-Jan-20 A | 1277 | 1277 | 100%
S116900 | Design TPC v2 Module Strongback | 19 | 31-Jan-20 A | 28-Feb-20 A | 11781 | 11781 | 100%
S117200 | Design TPC v2 Module Frames | 19 | 31-Jan-20 A | 28-Feb-20 A | 2091 | 2091 | 100%
S1005240 | AET submits IDR to BNL for approval | 29 | 31-Jan-20 A | 12-Mar-20 A | 0 | 0 | 100%
S117900 | Design TPC v2a Module Padplane | 38 | 31-Jan-20 A | 25-Mar-20 A | 11781 | 11781 | 100%
S215400 | EMCal/HCal sensors Production - 5K Units - Delivery Acceptance No. 13 | 1 | 03-Feb-20 A | 04-Feb-20 A | 48473 | 48473 | 100%
S215320 | EMCal/HCal sensors Production - 8K Units - Delivery Acceptance No. 12 | 1 | 03-Feb-20 A | 04-Feb-20 A | 77557 | 77557 | 100%
S238200 | Production Readiness Review, Safety Review - HCal FEE Sectors 7-32 | 2 | 03-Feb-20 A | 05-Feb-20 A | 6604 | 6604 | 100%
S238400 | Review Hcal Production Readiness & Safety Review Report | 2 | 03-Feb-20 A | 05-Feb-20 A | 2986 | 2986 | 100%
S119300 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Provide Requirements to Procurement | 16 | 03-Feb-20 A | 26-Feb-20 A | 0 | 0 | 100%
S216100 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 | 18 | 03-Feb-20 A | 28-Feb-20 A | 1277 | 1277 | 100%
S216200 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 | 18 | 03-Feb-20 A | 28-Feb-20 A | 1277 | 1277 | 100%
S216300 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 | 18 | 03-Feb-20 A | 28-Feb-20 A | 1277 | 1277 | 100%
S216400 | Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 | 18 | 03-Feb-20 A | 28-Feb-20 A | 798 | 798 | 100%
S216310 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 | 18 | 03-Feb-20 A | 28-Feb-20 A | 1277 | 1277 | 100%
S216320 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 | 18 | 03-Feb-20 A | 28-Feb-20 A | 1277 | 1277 | 100%
S216105 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 8 - Contributed Labor | 18 | 03-Feb-20 A | 28-Feb-20 A | 9867 | 9867 | 100%
S216205 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 9 - Contributed Labor | 18 | 03-Feb-20 A | 28-Feb-20 A | 9867 | 9867 | 100%
S216305 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 10 - Contributed Labor | 18 | 03-Feb-20 A | 28-Feb-20 A | 9867 | 9867 | 100%
S216405 | Production Q/A Tested & Sorted devices 5 K Units Delivery Batch No. 13 - Contributed Labor | 18 | 03-Feb-20 A | 28-Feb-20 A | 6185 | 6185 | 100%
S216315 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 11 - Contributed Labor | 18 | 03-Feb-20 A | 28-Feb-20 A | 9867 | 9867 | 100%
S216325 | Production Q/A Tested & Sorted devices 8 K Units Delivery Batch No. 12 - Contributed Labor | 18 | 03-Feb-20 A | 28-Feb-20 A | 9867 | 9867 | 100%
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | 18 | 03-Feb-20 A | 28-Feb-20 A | 12596 | 11959 | 100%
S193800 | Build cooling system for Prepro Sectors 1-12 | 236 | 03-Feb-20 A | 11-Jan-21 A | 24650 | 24650 | 100%
S308000 | Magnet Field Measurements: Magnet Engineering and Design Complete | 0 |  | 03-Feb-20 A | 0 | 0 | 100%
S204450 | Procurement Readiness Review - Outer HCAL Splice Plates (Dog bones) | 1 | 03-Feb-20 A | 03-Feb-20 A | 2425 | 2354 | 100%
S146500 | Production Readiness Review - TPC DAM | 2 | 03-Feb-20 A | 04-Feb-20 A | 1277 | 1277 | 100%
S167500 | Pack and ship EMCAL blocks for Prepro sector 3 to BNL Purchased Services | 5 | 03-Feb-20 A | 07-Feb-20 A | 866 | 866 | 100%
S167600 | Pack and ship EMCAL blocks for Prepro sector 3 to BNL M&S | 5 | 03-Feb-20 A | 07-Feb-20 A | 1229 | 1229 | 100%
S307600 | Magnet Field Measurements: Design mounts for probes to monitor field - Physics Resource(s) | 10 | 03-Feb-20 A | 14-Feb-20 A | 4565 | 4565 | 100%
S307610 | Magnet Field Measurements: Design mounts for probes to monitor field - CA-D Resource(s) | 10 | 03-Feb-20 A | 14-Feb-20 A | 1178 | 1178 | 100%
S171011 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 11 | 18 | 03-Feb-20 A | 28-Feb-20 A | 40858 | 40858 | 100%
S166200 | Fabricate EMCAL Prepro blocks sector 4 | 22 | 03-Feb-20 A | 04-Mar-20 A | 9425 | 9425 | 100%
S315915 | Steel Track Modifications - Inspection As-Builts and Punchlists Phys | 189 | 03-Feb-20 A | 30-Oct-20 A | 6847 | 6847 | 100%
S315925 | Steel Track Modifications - Inspection As-Builts and Punchlists CA-D | 189 | 03-Feb-20 A | 30-Oct-20 A | 8836 | 8836 | 100%
S132500 | Procure TPC R3 Module Prod. Parts (Frames) - Contract Award(s) | 0 | 04-Feb-20 A |  | 0 | 0 | 100%
S257000 | Procure DAQ Production SEBs - Provide Requirements to Procurement | 9 | 04-Feb-20 A | 18-Feb-20 A | 25550 | 25550 | 100%
S117400 | Procure TPC v2 Module Frames M&S | 58 | 04-Feb-20 A | 24-Apr-20 A | 1138 | 1138 | 100%
S124300 | Procure TPC R1 Module Parts (Frames) - Contract Award(s) | 0 | 04-Feb-20 A |  | 0 | 0 | 100%
S124600 | Procure TPC R1 Module Parts (Strongbacks) - Contract Award(s) | 0 | 04-Feb-20 A |  | 0 | 0 | 100%
S125200 | Procure TPC R1 Module Parts (Grids) - Contract Award(s) | 0 | 04-Feb-20 A |  | 0 | 0 | 100%
S128300 | Procure TPC R2 Module Prod. Parts (Frames) - Contract Award(s) | 0 | 04-Feb-20 A |  | 0 | 0 | 100%
S128600 | Procure TPC R2 Module Prod. Parts (Strongbacks) - Contract Award(s) | 0 | 04-Feb-20 A |  | 0 | 0 | 100%
S129200 | Procure TPC R2 Module Prod. Parts (Grids) - Contract Award(s) | 0 | 04-Feb-20 A |  | 0 | 0 | 100%
S204500 | Procure Outer HCAL Splice Plates - Provide Requirements to Procurement | 5 | 04-Feb-20 A | 10-Feb-20 A | 9410 | 9136 | 100%
S132400 | Procure TPC R3 Module Prod. Parts (Frames, Strongbacks, Padplanes, Grids) - Vendor Selection | 17 | 04-Feb-20 A | 28-Feb-20 A | 0 | 0 | 100%
S124400 | Procure TPC R1 Module Parts (Frames) - Contract/PO - Leadtime | 39 | 04-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S124700 | Procure TPC R1 Module Parts (Strongbacks) - Contract/PO - Leadtime | 40 | 04-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S125300 | Procure TPC R1 Module Parts (Grids) - Contract/PO - Leadtime | 40 | 04-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S128400 | Procure TPC R2 Module Prod. Parts (Frames) - Contract/PO - Leadtime | 40 | 04-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S128700 | Procure TPC R2 Module Prod. Parts (Strongbacks) - Contract/PO - Leadtime | 40 | 04-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S129300 | Procure TPC R2 Module Prod. Parts (Grids) - Contract/PO - Leadtime | 40 | 04-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S132800 | Procure TPC R3 Module Prod. Parts (Strongbacks) - Contract Award(s) | 0 | 05-Feb-20 A |  | 0 | 0 | 100%
S133400 | Procure TPC R3 Module Prod. Parts (Grids) - Contract Award(s) | 0 | 05-Feb-20 A |  | 0 | 0 | 100%
S238300 | Hcal Frontend Electronics Production Review | 0 |  | 05-Feb-20 A | 0 | 0 | 100%
S119400 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Prepare & Send Solicitation | 14 | 05-Feb-20 A | 26-Feb-20 A | 0 | 0 | 100%
S119500 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Vendor Responses | 14 | 05-Feb-20 A | 26-Feb-20 A | 0 | 0 | 100%
S119600 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Vendor Selection | 14 | 05-Feb-20 A | 26-Feb-20 A | 0 | 0 | 100%
S117000 | Procure TPC v2 Module Strongback Labor | 14 | 05-Feb-20 A | 26-Feb-20 A | 1826 | 1826 | 100%
S132600 | Procure TPC R3 Module Prod. Parts (Frames) - Contract/PO - Leadtime | 39 | 05-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S132900 | Procure TPC R3 Module Prod. Parts (Strongbacks) - Contract/PO - Leadtime | 39 | 05-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S133500 | Procure TPC R3 Module Prod. Parts (Grids) - Contract/PO - Leadtime | 39 | 05-Feb-20 A | 31-Mar-20 A | 0 | 0 | 100%
S117300 | Procure TPC v2 Module Frames Labor | 12 | 11-Feb-20 A | 28-Feb-20 A | 2739 | 2739 | 100%
S204600 | Procure Outer HCAL Splice Plates - Prepare & Send Solicitation | 9 | 11-Feb-20 A | 24-Feb-20 A | 0 | 0 | 100%
S118200 | Design TPC v2a Module GEMs | 9 | 14-Feb-20 A | 28-Feb-20 A | 5891 | 5891 | 100%
S117100 | Procure TPC v2 Module Strongback M&S | 30 | 18-Feb-20 A | 31-Mar-20 A | 1366 | 1366 | 100%
S307700 | Magnet Field Measurements: Design readout for probes to monitor field - Physics Resource(s) | 5 | 18-Feb-20 A | 24-Feb-20 A | 4565 | 4565 | 100%
S307710 | Magnet Field Measurements: Design readout for probes to monitor field - CA-D Resource(s) | 5 | 18-Feb-20 A | 24-Feb-20 A | 589 | 589 | 100%
S223000 | Fabricate EMCal Interface Board: Sectors 1-12, Phase 1 - Delivery Acceptance | 7 | 19-Feb-20 A | 28-Feb-20 A | 33495 | 33495 | 100%
S225700 | Procure EMCal External Bias Power System: Sectors 1-12 - Vendor Responses | 7 | 19-Feb-20 A | 28-Feb-20 A | 0 | 0 | 100%
S225800 | Procure EMCal External Bias Power System: Sectors 1-12 - Vendor Selection | 7 | 19-Feb-20 A | 28-Feb-20 A | 0 | 0 | 100%
S223001 | Fabricate EMCal Interface Board: Sectors 1-12, Phase 2 - Delivery Acceptance | 7 | 19-Feb-20 A | 28-Feb-20 A | 33495 | 33495 | 100%
S223100 | Test EMCal Interface Boards: Sectors 1-12 | 19 | 19-Feb-20 A | 16-Mar-20 A | 13475 | 13475 | 100%
S269500 | Timing System Prototype: evaluate performance, Final Design and Production Readiness Review | 362 | 24-Feb-20 A | 2021-07-30 | 2754 | 2754 | 95%
S186200 | Glue blocks together into modules for modules in Sectors (Prepro) 1-12 Labor | 221 | 25-Feb-20 A | 11-Jan-21 A | 70791 | 70791 | 100%
S186100 | Install SiPM daughterboards on blocks for modules in Sectors (Prepro) 1-12 Labor | 221 | 25-Feb-20 A | 11-Jan-21 A | 70791 | 70791 | 100%
S216500 | EMCal/HCal SiPM Sensor Procurement Complete | 0 |  | 28-Feb-20 A | 0 | 0 | 100%
S259700 | Procure DAQ Production Main Switches - Provide Requirements to Procurement | 10 | 02-Mar-20 A | 16-Mar-20 A | 30660 | 30660 | 100%
S338400 | Create Beampipe/Vacuum Layout - Physics Resource(s) | 21 | 02-Mar-20 A | 31-Mar-20 A | 5076 | 9025 | 100%
S338500 | Create Beampipe/Vacuum Envelope Drawing | 21 | 02-Mar-20 A | 31-Mar-20 A | 4232 | 2351 | 100%
S338600 | Create Beampipe/Vacuum subassembly and detail Drawings | 21 | 02-Mar-20 A | 31-Mar-20 A | 4232 | 4702 | 100%
S338700 | Review Beampipe/Vacuum Design/Safety - Physics Resource(s) | 21 | 02-Mar-20 A | 31-Mar-20 A | 5307 | 1179 | 100%
S338800 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews - Physics Resource(s) | 21 | 02-Mar-20 A | 31-Mar-20 A | 4232 | 1881 | 100%
S338410 | Create Beampipe/Vacuum Layout - CA-D Resource(s) | 21 | 02-Mar-20 A | 31-Mar-20 A | 5461 | 12135 | 100%
S338710 | Review Beampipe/Vacuum Design/Safety - CA-D Resource(s) | 21 | 02-Mar-20 A | 31-Mar-20 A | 7241 | 7241 | 100%
S338810 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews - CA-D Resource(s) | 21 | 02-Mar-20 A | 31-Mar-20 A | 5461 | 7584 | 100%
S215500 | EMCal/HCal sensors Production: - delivery complete | 0 |  | 02-Mar-20 A | 0 | 0 | 100%
S140600 | Test v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip March | 2 | 02-Mar-20 A | 03-Mar-20 A | 2986 | 2986 | 100%
S238500 | Fabricate HCal SiPM Boards - Provide Requirements to Procurement | 5 | 02-Mar-20 A | 06-Mar-20 A | 15609 | 15609 | 100%
S204700 | Procure Outer HCAL Splice Plates - Vendor Responses | 10 | 02-Mar-20 A | 13-Mar-20 A | 0 | 0 | 100%
S239800 | Fabricate HCal Preamp Boards - Provide Requirements to Procurement | 10 | 02-Mar-20 A | 13-Mar-20 A | 26653 | 26653 | 100%
S171012 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 12 | 19 | 02-Mar-20 A | 26-Mar-20 A | 40858 | 40858 | 100%
S239900 | Fabricate HCal Preamp Boards - Prepare & Send Solicitation | 30 | 02-Mar-20 A | 10-Apr-20 A | 0 | 0 | 100%
S146600 | Procure TPC DAM Felix 2.0 boards - Provide Requirements to Procurement | 43 | 02-Mar-20 A | 30-Apr-20 A | 71569 | 71569 | 100%
S1005520 | AET submits PDR to BNL for approval of S,H,U Interconnect, vac. break, Field Joint Tee and Sleeve | 61 | 02-Mar-20 A | 26-May-20 A | 0 | 0 | 100%
S329500 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp C | 64 | 02-Mar-20 A | 29-May-20 A | 589 | 589 | 100%
S1002319 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | 64 | 02-Mar-20 A | 29-May-20 A | 8364 | 8364 | 100%
S329475 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | 64 | 02-Mar-20 A | 29-May-20 A | 34952 | 33934 | 100%
S329478 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp C | 64 | 02-Mar-20 A | 29-May-20 A | 625 | 607 | 100%
S146800 | Procure TPC DAM Felix 2.0 Boards - Prepare & Send Solicitation | 116 | 02-Mar-20 A | 12-Aug-20 A | 0 | 0 | 100%
S1005800 | Draft PDR report of 1008B Cold Box Assembly. (Preliminary Layout) | 150 | 02-Mar-20 A | 01-Oct-20 A | 0 | 0 | 100%
S147310 | Procure TPC DAM Felix 2.0 Optical Components - Provide Requirements to Procurement | 245 | 02-Mar-20 A | 23-Feb-21 A | 71569 | 71569 | 100%
S147320 | Procure TPC DAM Felix 2.0 Optical Components - Prepare & Send Solicitation | 271 | 02-Mar-20 A | 31-Mar-21 A | 0 | 0 | 100%
S166300 | Fabricate EMCAL Prepro blocks sector 5 | 61 | 05-Mar-20 A | 29-May-20 A | 9425 | 9425 | 100%
S238600 | Fabricate HCal SiPM Boards - Prepare & Send Solicitation | 5 | 09-Mar-20 A | 13-Mar-20 A | 0 | 0 | 100%
S259800 | Procure DAQ Production Main Switches - Prepare & Send Solicitation | 15 | 10-Mar-20 A | 31-Mar-20 A | 0 | 0 | 100%
S231200 | Procure Internal EMCal Signal/Test/Comm and LV/Bias Cables: Production - Provide Requirements to Procurement | 10 | 11-Mar-20 A | 25-Mar-20 A | 9526 | 9526 | 100%
S330606 | Gather Rack Interlock Reqs and Specify Interlock Equipment | 14 | 11-Mar-20 A | 31-Mar-20 A | 19251 | 19251 | 100%
S329407 | Conceptual Design for Cable Routing from Detector to Rack (HCal, EMCal) | 164 | 11-Mar-20 A | 30-Oct-20 A | 17545 | 17545 | 100%
S357400 | Design EMCal Integration/Installation Tooling/Fixtures FY21 | 203 | 11-Mar-20 A | 31-Dec-20 A | 12642 | 12642 | 100%
S193900 | Install modules in Prepro Sectors 1-12 | 220 | 11-Mar-20 A | 26-Jan-21 A | 95670 | 95670 | 100%
S262500 | Procure Prototype V1 Trigger Board - Delivery Acceptance | 5 | 11-Mar-20 A | 17-Mar-20 A | 196861 | 196861 | 100%
S317090 | Create Beampipe Supports and Beampipe Detailed Design Drawings | 347 | 12-Mar-20 A | 2021-07-28 | 70365 | 64599 | 90%
S330612 | Rack Interlock Conceptual Design | 98 | 13-Mar-20 A | 31-Jul-20 A | 57752 | 57752 | 100%
S1005260 | BNL review for IDR approval | 21 | 13-Mar-20 A | 10-Apr-20 A | 26200 | 26200 | 100%
S257100 | Procure DAQ Production SEBs - Prepare & Send Solicitation | 113 | 16-Mar-20 A | 24-Aug-20 A | 0 | 0 | 100%
S257200 | Procure DAQ Production SEBs - Vendor Responses | 113 | 16-Mar-20 A | 24-Aug-20 A | 0 | 0 | 100%
S330640 | Prototype System Development Labor | 324 | 16-Mar-20 A | 29-Jun-21 A | 44440 | 44454 | 100%
S330642 | Prototype System Development M&S | 324 | 16-Mar-20 A | 29-Jun-21 A | 40518 | 40527 | 100%
S238700 | Fabricate HCal SiPM Boards - Vendor Responses | 5 | 16-Mar-20 A | 20-Mar-20 A | 0 | 0 | 100%
S171400 | Procure EMCAL Epoxy for Final Blocks- Vendor Responses | 6 | 17-Mar-20 A | 25-Mar-20 A | 0 | 0 | 100%
S259900 | Procure DAQ Production Main Switches - Vendor Responses | 6 | 17-Mar-20 A | 25-Mar-20 A | 0 | 0 | 100%
S260000 | Procure DAQ Production Main Switches - Vendor Selection | 9 | 17-Mar-20 A | 30-Mar-20 A | 0 | 0 | 100%
S128800 | Procure TPC R2 Module Prod. Parts (Strongbacks) - Delivery Acceptance | 10 | 17-Mar-20 A | 31-Mar-20 A | 10451 | 10451 | 100%
S133000 | Procure TPC R3 Module Prod. Parts (Strongbacks) - Delivery Acceptance | 10 | 17-Mar-20 A | 31-Mar-20 A | 12246 | 12246 | 100%
S124500 | Procure TPC R1 Module Parts (Frames) - Delivery Acceptance | 51 | 17-Mar-20 A | 27-May-20 A | 16615 | 16615 | 100%
S331720 | Design Cooling Manifolds for TPC | 273 | 17-Mar-20 A | 16-Apr-21 A | 3917 | 3917 | 100%
S171300 | Procure EMCAL Epoxy for Final Blocks- Prepare & Send Solicitation | 4 | 18-Mar-20 A | 24-Mar-20 A | 0 | 0 | 100%
S227200 | Fabricate SiPM Daughter Boards Sectors 13-64 - Vendor Responses | 8 | 18-Mar-20 A | 30-Mar-20 A | 0 | 0 | 100%
S171500 | Procure EMCAL Epoxy for Final Blocks- Vendor Selection | 9 | 18-Mar-20 A | 31-Mar-20 A | 0 | 0 | 100%
S227000 | Fabricate SiPM Daughter Boards Sectors 13-64 - Provide Requirements to Procurement | 9 | 18-Mar-20 A | 31-Mar-20 A | 15582 | 15582 | 100%
S132700 | Procure TPC R3 Module Prod. Parts (Frames) - Delivery Acceptance | 32 | 18-Mar-20 A | 30-Apr-20 A | 19139 | 19139 | 100%
S128500 | Procure TPC R2 Module Prod. Parts (Frames) - Delivery Acceptance | 50 | 18-Mar-20 A | 27-May-20 A | 16615 | 16615 | 100%
S331710 | Design Cooling Manifolds for EMCal | 334 | 18-Mar-20 A | 2021-07-15 | 3917 | 3917 | 40%
S198401 | Preliminary Design Review - Inner HCAL Support Rings | 0 |  | 18-Mar-20 A | 0 | 0 | 100%
S171200 | Procure EMCAL Epoxy for Final Blocks - Provide Requirements to Procurement | 3 | 19-Mar-20 A | 24-Mar-20 A | 1316 | 1316 | 100%
S171900 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Provide Requirements to Procurement | 3 | 19-Mar-20 A | 24-Mar-20 A | 0 | 0 | 100%
S172000 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Prepare & Send Solicitation | 3 | 19-Mar-20 A | 24-Mar-20 A | 0 | 0 | 100%
S172100 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Vendor Responses | 3 | 19-Mar-20 A | 24-Mar-20 A | 0 | 0 | 100%
S172200 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Vendor Selection | 3 | 19-Mar-20 A | 24-Mar-20 A | 0 | 0 | 100%
S227100 | Fabricate SiPM Daughter Boards Sectors 13-64 - Prepare & Send Solicitation | 8 | 19-Mar-20 A | 31-Mar-20 A | 0 | 0 | 100%
S310900 | Carriage Cradle - Vendor Selection - Physics Resource(s) | 3 | 20-Mar-20 A | 25-Mar-20 A | 12325 | 12325 | 100%
S310910 | Carriage Cradle - Vendor Selection - CA-D Resource(s) | 3 | 20-Mar-20 A | 25-Mar-20 A | 10455 | 10455 | 100%
S231500 | Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Vendor Selection | 6 | 23-Mar-20 A | 31-Mar-20 A | 0 | 0 | 100%
S238800 | Fabricate HCal SiPM Boards - Vendor Selection | 5 | 23-Mar-20 A | 27-Mar-20 A | 0 | 0 | 100%
S197900 | Final Design Review. Procurement Readiness Review - Inner HCAL Support Structure | 0 | 24-Mar-20 A | 24-Mar-20 A | 6936 | 6734 | 100%
S125400 | Procure TPC R1 Module Parts (Grids) - Delivery Acceptance | 5 | 24-Mar-20 A | 31-Mar-20 A | 11148 | 11148 | 100%
S129400 | Procure TPC R2 Module Prod. Parts (Grids) - Delivery Acceptance | 5 | 24-Mar-20 A | 31-Mar-20 A | 11148 | 11148 | 100%
S133600 | Procure TPC R3 Module Prod. Parts (Grids) - Delivery Acceptance | 5 | 24-Mar-20 A | 31-Mar-20 A | 11707 | 11707 | 100%
S231400 | Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Vendor Solicitation | 5 | 24-Mar-20 A | 31-Mar-20 A | 0 | 0 | 100%
S198500 | Final Design Review. Procurement Readiness Review - Inner HCAL Support Rings | 48 | 24-Mar-20 A | 29-May-20 A | 6936 | 6936 | 100%
S186300 | Revise module production procedure based on module production for Prepro Sectors 1-12 | 69 | 24-Mar-20 A | 30-Jun-20 A | 21206 | 21206 | 100%
S257300 | Procure DAQ Production SEBs - Vendor Selection | 132 | 24-Mar-20 A | 29-Sep-20 A | 0 | 0 | 100%
S194000 | Install readout electronics on Prepro Sectors 1-12 | 211 | 24-Mar-20 A | 26-Jan-21 A | 96005 | 95670 | 100%
S194200 | Test and Review Preproduction Sectors 1-12 with LEDs & cosmic rays | 255 | 24-Mar-20 A | 31-Mar-21 A | 67343 | 67108 | 100%
S194300 | Analyze and Review Test Results from Prepro Sectors 1-12 | 259 | 24-Mar-20 A | 05-Apr-21 A | 98355 | 98355 | 100%
S303000 | Magnet: Order Cable Tray and Supports M&S | 5 | 24-Mar-20 A | 31-Mar-20 A | 2276 | 2276 | 100%
S302901 | Magnet: Order Cable Tray and Supports_85% | 5 | 24-Mar-20 A | 31-Mar-20 A | 10014 | 10014 | 100%
S231300 | Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Prepare & Send Solicitation | 3 | 25-Mar-20 A | 30-Mar-20 A | 0 | 0 | 100%
S124800 | Procure TPC R1 Module Parts (Strongbacks) - Delivery Acceptance | 4 | 25-Mar-20 A | 31-Mar-20 A | 9349 | 9349 | 100%
S227300 | Fabricate SiPM Daughter Boards Sectors 13-64 - Vendor Selection | 4 | 25-Mar-20 A | 31-Mar-20 A | 0 | 0 | 100%
S198000 | Address Issues from Internal Review Support Structure | 47 | 25-Mar-20 A | 29-May-20 A | 4837 | 4697 | 100%
S194100 | Install cables and cooling system on Prepro Sectors 1-12 | 214 | 25-Mar-20 A | 01-Feb-21 A | 178526 | 177903 | 100%
S118000 | Procure TPC v2a Module Padplane Labor | 3 | 26-Mar-20 A | 31-Mar-20 A | 1826 | 1826 | 100%
S118300 | Procure TPC v2a Module GEMs Labor | 3 | 26-Mar-20 A | 31-Mar-20 A | 3652 | 3652 | 100%
S118100 | Procure TPC v2a Module Padplane M&S | 3 | 26-Mar-20 A | 31-Mar-20 A | 4210 | 4210 | 100%
S118400 | Procure TPC v2a Module GEMs M&S | 3 | 26-Mar-20 A | 31-Mar-20 A | 7397 | 7397 | 100%
S260100 | Procure DAQ Production Main Switches - Contract Award(s) | 0 | 30-Mar-20 A |  | 0 | 0 | 100%
S327501 | Gather Power Reqs for CRYO, Cooling and Lighting | 1 | 30-Mar-20 A | 31-Mar-20 A | 7343 | 7095 | 100%
S238900 | Fabricate HCal SiPM Boards - Contract Award(s) | 0 | 30-Mar-20 A |  | 0 | 0 | 100%
S239000 | Fabricate HCal SiPM Boards - Contract/PO - Leadtime | 129 | 30-Mar-20 A | 30-Sep-20 A | 0 | 0 | 100%
S171600 | Procure EMCAL Epoxy for Final Blocks- Contract Award(s) | 0 | 31-Mar-20 A |  | 0 | 0 | 100%
S172300 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Contract Award(s) | 0 | 31-Mar-20 A |  | 0 | 0 | 100%
S338900 | Design/Safety Reviews Complete, Beampipe/Vacuum components Released for Production | 0 |  | 31-Mar-20 A | 0 | 0 | 100%
S226700 | Production Readiness and Safety Review: EMCal Production Electronics | 17 | 31-Mar-20 A | 22-Apr-20 A | 8080 | 8080 | 100%
S260200 | Procure DAQ Production Main Switches - Contract/PO - Leadtime | 13 | 01-Apr-20 A | 20-Apr-20 A | 0 | 0 | 100%
S108600 | Design TPC Handling Cart | 21 | 01-Apr-20 A | 30-Apr-20 A | 17672 | 18175 | 100%
S108700 | Procure TPC Handling Cart Labor | 21 | 01-Apr-20 A | 30-Apr-20 A | 3737 | 3761 | 100%
S295800 | (Cryo Controls Hardware procurement) PLC I/O cards & expansion chassis Labor | 21 | 01-Apr-20 A | 30-Apr-20 A | 1898 | 1898 | 100%
S296000 | (Cryo Controls Hardware procurement) Rack components Labor | 21 | 01-Apr-20 A | 30-Apr-20 A | 506 | 506 | 100%
S295900 | (Cryo Controls Hardware procurement) PLC I/O cards & expansion chassis M&S | 21 | 01-Apr-20 A | 30-Apr-20 A | 8534 | 8534 | 100%
S296100 | (Cryo Controls Hardware procurement) Rack components M&S | 21 | 01-Apr-20 A | 30-Apr-20 A | 6828 | 6828 | 100%
S312000 | CC Drive & Alignment System - Assembly & Detail Drawings - Physics Resource(s) | 108 | 01-Apr-20 A | 01-Sep-20 A | 27389 | 27389 | 100%
S312010 | CC Drive & Alignment System - Assembly & Detail Drawings - CA-D Resource(s) | 108 | 01-Apr-20 A | 01-Sep-20 A | 58666 | 58666 | 100%
S243800 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Provide Requirements to Procurements | 188 | 01-Apr-20 A | 31-Dec-20 A | 19333 | 19333 | 100%
S108800 | Procure TPC Handling Cart M&S | 291 | 01-Apr-20 A | 28-May-21 A | 15022 | 15089 | 100%
S133100 | Procure TPC R3 Module Prod. Parts (Padplanes) - Contract Award(s) | 0 | 01-Apr-20 A |  | 0 | 0 | 100%
S225900 | Procure EMCal External Bias Power System: Sectors 1-12, Phase 1 - Contract Award(s) | 0 | 01-Apr-20 A |  | 0 | 0 | 100%
S226000 | Procure EMCal External Bias Power System: Sectors 1-12, Phase 2 - Contract Award(s) | 0 | 01-Apr-20 A |  | 0 | 0 | 100%
S311000 | Carriage Cradle - Contract Award(s) | 1 | 01-Apr-20 A | 01-Apr-20 A | 0 | 0 | 100%
S118500 | Test TPC v2a Module GEMS | 5 | 01-Apr-20 A | 07-Apr-20 A | 4565 | 4565 | 100%
S223900 | Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 1 - M&S | 5 | 01-Apr-20 A | 07-Apr-20 A | 11959 | 11959 | 100%
S224000 | Procure EMCal External LV/Bias Signal/Comm/Test Cables: Sectors 1-12, Phase 2 - M&S | 5 | 01-Apr-20 A | 07-Apr-20 A | 47838 | 47838 | 100%
S242300 | Fabricate HCal Interface Boards Production - Provide Requirements to Procurement | 5 | 01-Apr-20 A | 07-Apr-20 A | 0 | 0 | 100%
S241100 | Fabricate HCal LED Boards - Provide Requirements to Procurement | 5 | 01-Apr-20 A | 07-Apr-20 A | 8762 | 8762 | 100%
S240000 | Fabricate HCal Preamp Boards - Vendor Responses | 10 | 01-Apr-20 A | 14-Apr-20 A | 0 | 0 | 100%
S324300 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - Physics Resource(s) | 15 | 01-Apr-20 A | 21-Apr-20 A | 2971 | 2971 | 100%
S324310 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 15 | 01-Apr-20 A | 21-Apr-20 A | 11574 | 11574 | 100%
S204800 | Procure Outer HCAL Splice Plates - Vendor Selection | 20 | 01-Apr-20 A | 28-Apr-20 A | 0 | 0 | 100%
S109500 | Assemble TPC v2 Mandrel | 21 | 01-Apr-20 A | 30-Apr-20 A | 0 | 0 | 100%
S109400 | Procure TPC v2 Mandrel Parts M&S | 21 | 01-Apr-20 A | 30-Apr-20 A | 11872 | 11872 | 100%
S111500 | Procure TPC Field Cage Prototype v2 End Rings | 21 | 01-Apr-20 A | 30-Apr-20 A | 22759 | 22759 | 100%
S329406 | Send proposal packages for approvals (cable types, rack locations, and support components) | 21 | 01-Apr-20 A | 30-Apr-20 A | 2724 | 2724 | 100%
S224500 | Test Pulse Boards 1-12 - Labor | 41 | 01-Apr-20 A | 28-May-20 A | 9186 | 9186 | 100%
S137100 | v2 Fabricate TPC FEE preproduction prototype boards Labor | 42 | 01-Apr-20 A | 29-May-20 A | 2945 | 2945 | 100%
S137200 | v2 Fabricate TPC FEE preproduction prototype boards M&S | 42 | 01-Apr-20 A | 29-May-20 A | 1680 | 1680 | 100%
S133200 | Procure TPC R3 Module Prod. Parts (Padplanes) - Contract/PO - Leadtime | 52 | 01-Apr-20 A | 15-Jun-20 A | 0 | 0 | 100%
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | 137 | 01-Apr-20 A | 14-Oct-20 A | 37793 | 37793 | 100%
S324210 | End Caps/ Pole Tips - Assembly & Detail Drawing - CA-D Resource(s) | 137 | 01-Apr-20 A | 14-Oct-20 A | 84727 | 84727 | 100%
S324400 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 146 | 01-Apr-20 A | 28-Oct-20 A | 5478 | 5478 | 100%
S324410 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 146 | 01-Apr-20 A | 28-Oct-20 A | 13857 | 13857 | 100%
S325900 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - Physics Resource(s) | 147 | 01-Apr-20 A | 28-Oct-20 A | 5478 | 5642 | 100%
S325910 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 147 | 01-Apr-20 A | 28-Oct-20 A | 13857 | 14272 | 100%
S326000 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 147 | 01-Apr-20 A | 29-Oct-20 A | 5478 | 5642 | 100%
S326010 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 147 | 01-Apr-20 A | 29-Oct-20 A | 13857 | 14272 | 100%
S137000 | v2 Procure TPC FEE preproducion prototype components M&S | 149 | 01-Apr-20 A | 30-Oct-20 A | 6681 | 6681 | 100%
S324600 | End Caps/ Pole Tips - Prepare Procurement Package(s) - Physics Resource(s) | 166 | 01-Apr-20 A | 30-Nov-20 A | 13695 | 13695 | 100%
S324610 | End Caps/ Pole Tips - Prepare Procurement Package(s) - CA-D Resource(s) | 166 | 01-Apr-20 A | 30-Nov-20 A | 22306 | 22306 | 100%
S324100 | End Caps/ Pole Tips - Design Controls for Drive System - Physics Resource(s) | 188 | 01-Apr-20 A | 30-Dec-20 A | 22028 | 22028 | 100%
S324110 | End Caps/ Pole Tips - Design Controls for Drive System - CA-D Resource(s) | 188 | 01-Apr-20 A | 30-Dec-20 A | 6847 | 6847 | 100%
S325800 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - Physics Resource(s) | 208 | 01-Apr-20 A | 29-Jan-21 A | 40171 | 40261 | 100%
S325810 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - CA-D Resource(s) | 208 | 01-Apr-20 A | 29-Jan-21 A | 110854 | 111103 | 100%
S226100 | Procure EMCal External Bias Power System: Sectors 1-12, Phase 1 - Contract/PO - Leadtime | 223 | 01-Apr-20 A | 23-Feb-21 A | 0 | 0 | 100%
S226200 | Procure EMCal External Bias Power System: Sectors 1-12, Phase 2 - Contract/PO - Leadtime | 224 | 01-Apr-20 A | 24-Feb-21 A | 0 | 0 | 100%
S243900 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Prepare & Send Solicitation | 312 | 01-Apr-20 A | 29-Jun-21 A | 0 | 0 | 100%
S244000 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Vendor Responses | 312 | 01-Apr-20 A | 29-Jun-21 A | 0 | 0 | 100%
S244100 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Vendor Selection | 335 | 01-Apr-20 A | 2021-07-30 | 0 | 0 | 75%
S152100 | Procure TPC Gas System Equipment - Contract Award(s) | 0 | 02-Apr-20 A |  | 0 | 0 | 100%
S118800 | Assemble TPC v2a Module Prototype | 16 | 02-Apr-20 A | 24-Apr-20 A | 0 | 0 | 100%
S151900 | Procure TPC Gas System Equipment - Vendor Responses | 20 | 02-Apr-20 A | 30-Apr-20 A | 0 | 0 | 100%
S152000 | Procure TPC Gas System Equipment - Vendor Selection | 20 | 02-Apr-20 A | 30-Apr-20 A | 0 | 0 | 100%
S152200 | Procure TPC Gas System Equipment - Contract/PO - Leadtime | 246 | 02-Apr-20 A | 29-Mar-21 A | 0 | 0 | 100%
S233800 | Procure EMCal Bias Power System Sectors 13-64 - Contract Award(s) | 0 | 07-Apr-20 A |  | 0 | 0 | 100%
S233400 | Procure EMCal Bias Power System Sectors 13-64 - Provide Requirements to Procurement | 9 | 07-Apr-20 A | 20-Apr-20 A | 11382 | 11382 | 100%
S233500 | Procure EMCal Bias Power System Sectors 13-64 - Prepare & Send Solicitation | 9 | 07-Apr-20 A | 20-Apr-20 A | 0 | 0 | 100%
S233600 | Procure EMCal Bias Power System Sectors 13-64 - Vendor Responses | 9 | 07-Apr-20 A | 20-Apr-20 A | 0 | 0 | 100%
S233700 | Procure EMCal Bias Power System Sectors 13-64 - Vendor Selection | 9 | 07-Apr-20 A | 20-Apr-20 A | 0 | 0 | 100%
S233900 | Procure EMCal Bias Power System Sectors 13-64 - Contract/PO - Leadtime | 233 | 07-Apr-20 A | 15-Mar-21 A | 0 | 0 | 100%
S330610 | Radiation Test for Water Leak Detection System | 15 | 08-Apr-20 A | 29-Apr-20 A | 9625 | 9625 | 100%
S120500 | Select TPC Membrane HV Power Supply | 16 | 08-Apr-20 A | 30-Apr-20 A | 0 | 0 | 100%
S241500 | Fabricate HCal LED Boards - Contract Award(s) | 0 | 08-Apr-20 A |  | 0 | 0 | 100%
S118600 | Frame TPC v2a Module GEMs | 5 | 08-Apr-20 A | 14-Apr-20 A | 4565 | 4565 | 100%
S242400 | Fabricate HCal Interface Boards Production - Prepare & Send Solicitation | 5 | 08-Apr-20 A | 14-Apr-20 A | 0 | 0 | 100%
S241200 | Fabricate HCal LED Boards - Prepare & Send Solicitation | 14 | 08-Apr-20 A | 28-Apr-20 A | 0 | 0 | 100%
S241300 | Fabricate HCal LED Boards - Vendor Responses | 14 | 08-Apr-20 A | 28-Apr-20 A | 0 | 0 | 100%
S241400 | Fabricate HCal LED Boards - Vendor Selection | 14 | 08-Apr-20 A | 28-Apr-20 A | 0 | 0 | 100%
S241600 | Fabricate HCal LED Boards - Contract/PO - Leadtime | 23 | 08-Apr-20 A | 08-May-20 A | 0 | 0 | 100%
S151500 | Procure TPC Gas System mass flow meters Labor | 12 | 13-Apr-20 A | 29-Apr-20 A | 3534 | 3534 | 100%
S137600 | v2 Assemble and test TPC FEE preproduction prototype M&S | 135 | 13-Apr-20 A | 23-Oct-20 A | 6407 | 6407 | 100%
S137500 | v2 Assemble and test TPC FEE preproduction prototype | 283 | 13-Apr-20 A | 28-May-21 A | 92435 | 92435 | 100%
S137700 | Final Design Review, Production Readiness Review - TPC FEE | 325 | 13-Apr-20 A | 2021-07-28 | 1277 | 1277 | 95%
S151700 | Procure TPC Gas System Analyzers (2 for redundancy) - Provide Requirements to Procurement | 5 | 13-Apr-20 A | 17-Apr-20 A | 3534 | 3534 | 100%
S152400 | Procure TPC Gas System scrubbers Labor | 12 | 13-Apr-20 A | 29-Apr-20 A | 3534 | 3534 | 100%
S152600 | Procure TPC Gas System oxygen and water sensors Labor | 12 | 13-Apr-20 A | 29-Apr-20 A | 3534 | 3534 | 100%
S1005280 | AET submits FDR report to BNL for approval | 20 | 13-Apr-20 A | 08-May-20 A | 78600 | 78600 | 100%
S151600 | Procure TPC Gas System mass flow meters M&S | 55 | 13-Apr-20 A | 30-Jun-20 A | 7773 | 7773 | 100%
S152700 | Procure TPC Gas System oxygen and water sensors M&S | 140 | 13-Apr-20 A | 30-Oct-20 A | 12704 | 12704 | 100%
S152500 | Procure TPC Gas System scrubbers M&S | 240 | 13-Apr-20 A | 30-Mar-21 A | 8793 | 8793 | 100%
S138700 | Review the Test Result of the Full Chip (USP + BNL) | 4 | 14-Apr-20 A | 20-Apr-20 A | 0 | 0 | 100%
S110200 | Procure TPC v2 Outer Field Cage Parts - Contract/PO - Leadtime | 12 | 14-Apr-20 A | 30-Apr-20 A | 0 | 0 | 100%
S312100 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - Physics Resource(s) | 12 | 14-Apr-20 A | 30-Apr-20 A | 4565 | 4565 | 100%
S312110 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 12 | 14-Apr-20 A | 30-Apr-20 A | 23149 | 23149 | 100%
S186500 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Provide Requirements to Procurement | 32 | 14-Apr-20 A | 29-May-20 A | 6391 | 6391 | 100%
S186600 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Prepare & Send Solicitation | 32 | 14-Apr-20 A | 29-May-20 A | 0 | 0 | 100%
S194800 | Procure EMCAL Mechanical Parts for Final Sectors - Provide Requirements to Procurement | 11 | 15-Apr-20 A | 30-Apr-20 A | 6391 | 6391 | 100%
S352300 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - CA-D Resource(s) | 117 | 15-Apr-20 A | 30-Sep-20 A | 6067 | 6067 | 100%
S1003399 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | 117 | 15-Apr-20 A | 30-Sep-20 A | 35129 | 35129 | 100%
S118700 | Test TPC v2a Module Framed GEMs | 5 | 15-Apr-20 A | 21-Apr-20 A | 0 | 0 | 100%
S242500 | Fabricate HCal Interface Boards Production - Vendor Responses | 5 | 15-Apr-20 A | 21-Apr-20 A | 0 | 0 | 100%
S240100 | Fabricate HCal Preamp Boards - Vendor Selection | 11 | 15-Apr-20 A | 30-Apr-20 A | 0 | 0 | 100%
S308510 | Completed - Magnet Field Measurements: Fabricate NMR probe readout parts | 0 |  | 17-Apr-20 A | 0 | 0 | 100%
S187200 | Procure light guides for modules in Sectors 13-64 - Contract Award | 0 | 20-Apr-20 A |  | 0 | 0 | 100%
S151800 | Procure TPC Gas System Equipment - Prepare & Send Solicitation | 8 | 20-Apr-20 A | 30-Apr-20 A | 0 | 0 | 100%
S260300 | Procure DAQ Production Main Switches - Delivery Acceptance | 3 | 21-Apr-20 A | 24-Apr-20 A | 99994 | 99994 | 100%
S312200 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 123 | 21-Apr-20 A | 14-Oct-20 A | 4565 | 4565 | 100%
S312210 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 123 | 21-Apr-20 A | 14-Oct-20 A | 23149 | 23149 | 100%
S121200 | Procure TPC GEM HV Membrane Power Supply - Contract Award(s) | 0 | 22-Apr-20 A |  | 0 | 0 | 100%
S242600 | Fabricate HCal Interface Boards Production - Vendor Selection | 5 | 22-Apr-20 A | 28-Apr-20 A | 0 | 0 | 100%
S226800 | Production Readiness & Safety Review: EMCal Electronics | 0 |  | 22-Apr-20 A | 0 | 0 | 100%
S194900 | Procure EMCAL Mechanical Parts for Final Sectors - Prepare & Send Solicitation | 5 | 23-Apr-20 A | 30-Apr-20 A | 0 | 0 | 100%
S244300 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Contract/PO - Leadtime | 315 | 29-Apr-20 A | 2021-08-02 | 0 | 0 | 75%
S242700 | Fabricate HCal Interface Boards Production - Contract Award(s) | 0 | 29-Apr-20 A |  | 0 | 0 | 100%
S295910 | Completed - (Cryo Controls Hardware procurement) PLC I/O cards & expansion chassis M&S | 0 |  | 30-Apr-20 A | 0 | 0 | 100%
S242800 | Fabricate HCal Interface Boards Production - Contract/PO - Leadtime | 127 | 30-Apr-20 A | 30-Oct-20 A | 0 | 0 | 100%
S171700 | Procure EMCAL Epoxy for Final Blocks- Contract/PO - Leadtime | 61 | 01-May-20 A | 29-Jul-20 A | 0 | 0 | 100%
S172400 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Contract/PO - Leadtime | 63 | 01-May-20 A | 31-Jul-20 A | 0 | 0 | 100%
S240200 | Fabricate HCal Preamp Boards - Contract Award(s) | 0 | 01-May-20 A |  | 0 | 0 | 100%
S167700 | Pack and ship EMCAL blocks for Prepro sector 4 to BNL Purchased Services | 5 | 01-May-20 A | 07-May-20 A | 866 | 866 | 100%
S167800 | Pack and ship EMCAL blocks for Prepro sector 4 to BNL M&S | 5 | 01-May-20 A | 07-May-20 A | 1229 | 1229 | 100%
S243100 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Provide Requirements to Procurement | 5 | 01-May-20 A | 07-May-20 A | 19333 | 19333 | 100%
S171013 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 13 | 7 | 01-May-20 A | 12-May-20 A | 40858 | 40858 | 100%
S330601 | Analyze Detector Electronics Racks and Rack generic support systems Reqs | 10 | 01-May-20 A | 14-May-20 A | 0 | 0 | 100%
S241900 | Fabricate HCal Backplane Boards: Production - Labor | 18 | 01-May-20 A | 28-May-20 A | 15202 | 15202 | 100%
S242000 | Fabricate HCal Backplane Boards: Production - M&S | 18 | 01-May-20 A | 28-May-20 A | 17542 | 17542 | 100%
S308500 | Magnet Field Measurements: Fabricate NMR probe readout parts | 20 | 01-May-20 A | 29-May-20 A | 23369 | 23369 | 100%
S308610 | Magnet Field Measurements: Fabricate NMR probe mounts - CA-D Resource(s) | 20 | 01-May-20 A | 29-May-20 A | 2356 | 2356 | 100%
S240300 | Fabricate HCal Preamp Boards - Contract/PO - Leadtime | 85 | 01-May-20 A | 31-Aug-20 A | 0 | 0 | 100%
S348000 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - Physics Resourc | 105 | 01-May-20 A | 30-Sep-20 A | 25417 | 25328 | 100%
S348010 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s | 105 | 01-May-20 A | 30-Sep-20 A | 30995 | 30887 | 100%
S292700 | (Warm Piping System) Technical Specifications | 225 | 01-May-20 A | 29-Mar-21 A | 3075 | 3075 | 100%
S172850 | Supervise EMCal Final Block Production | 395 | 01-May-20 A | 2021-11-30 | 60986 | 60868 | 65%
S288600 | Procure LN2 supply transfer line system - Provide requirements to Procurement | 51 | 04-May-20 A | 15-Jul-20 A | 23056 | 23056 | 100%
S250900 | Procure EMCAL 7-Crate Digitizer - Assembly & Tests - Leadtime | 63 | 04-May-20 A | 31-Jul-20 A | 0 | 0 | 100%
S140900 | Procure TPC FEE Production Components - Provide Requirements to Procurement | 16 | 05-May-20 A | 28-May-20 A | 20911 | 20911 | 100%
S141000 | Procure TPC FEE Production Components - Prepare & Send Solicitation | 16 | 05-May-20 A | 28-May-20 A | 0 | 0 | 100%
S141100 | Procure TPC FEE Production Components - Vendor Responses | 16 | 05-May-20 A | 28-May-20 A | 0 | 0 | 100%
S121300 | Procure TPC GEM HV Power Supplies and Membrane Power Supply - Contract/PO - Leadtime | 103 | 05-May-20 A | 30-Sep-20 A | 0 | 0 | 100%
S166400 | Fabricate EMCAL Prepro blocks sector 6 | 30 | 06-May-20 A | 17-Jun-20 A | 9425 | 9425 | 100%
S119100 | Production Readiness Review - TPC Module | 1 | 06-May-20 A | 06-May-20 A | 1277 | 1277 | 100%
S311200 | Carriage Cradle - Vendor Leadtime | 83 | 06-May-20 A | 01-Sep-20 A | 0 | 0 | 100%
S311100 | Carriage Cradle - BNL Oversight - Physics Resource(s) | 180 | 06-May-20 A | 26-Jan-21 A | 5779 | 5779 | 100%
S311110 | Carriage Cradle - BNL Oversight - CA-D Resource(s) | 180 | 06-May-20 A | 26-Jan-21 A | 14012 | 14012 | 100%
S119700 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Contract Award(s) | 0 | 07-May-20 A |  | 0 | 0 | 100%
S119900 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Contract/PO - Leadtime | 5 | 07-May-20 A | 13-May-20 A | 0 | 0 | 100%
S120600 | Select TPC GEM HV Power Supplies | 10 | 07-May-20 A | 20-May-20 A | 0 | 0 | 100%
S243200 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Prepare & Send Solicitation | 5 | 08-May-20 A | 14-May-20 A | 0 | 0 | 100%
S241700 | Fabricate HCal LED Boards - Delivery Acceptance | 5 | 11-May-20 A | 15-May-20 A | 50145 | 50145 | 100%
S1005320 | AET begins material procurement | 5 | 11-May-20 A | 15-May-20 A | 0 | 0 | 100%
S231900 | Fabricate Test-pulse Boards 13 - 64 - Labor | 11 | 12-May-20 A | 28-May-20 A | 11382 | 11382 | 100%
S142600 | Procure TPC FEE Production Boards & Assembly - Provide Requirements to Procurement | 8 | 13-May-20 A | 26-May-20 A | 6480 | 6480 | 100%
S142700 | Procure TPC FEE Production Boards & Assembly - Prepare & Send Solicitation | 8 | 13-May-20 A | 26-May-20 A | 0 | 0 | 100%
S142800 | Procure TPC FEE Production Boards & Assembly - Vendor Responses | 8 | 13-May-20 A | 26-May-20 A | 0 | 0 | 100%
S198200 | Manufacture Inner HCAL Support Structure - Provide Requirements to Procurement | 8 | 13-May-20 A | 26-May-20 A | 9920 | 9631 | 100%
S171014 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 14 | 9 | 13-May-20 A | 27-May-20 A | 40858 | 40858 | 100%
S251700 | Procure Production Digitizer - Provide Requirements to Procurement | 9 | 13-May-20 A | 27-May-20 A | 23562 | 23562 | 100%
S251800 | Procure Production Digitizer - Prepare & Send Solicitation | 9 | 13-May-20 A | 27-May-20 A | 0 | 0 | 100%
S251900 | Procure Production Digitizer - Vendor Responses | 9 | 13-May-20 A | 27-May-20 A | 0 | 0 | 100%
S252000 | Procure Production Digitizer - Vendor Selection | 9 | 13-May-20 A | 27-May-20 A | 0 | 0 | 100%
S306800 | Magnet: Disconnect Quench Detector from Test System in 912 | 10 | 13-May-20 A | 28-May-20 A | 913 | 913 | 100%
S227600 | Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance | 11 | 13-May-20 A | 29-May-20 A | 38676 | 38676 | 100%
S227500 | Fabricate SiPM Daughter Boards Sectors 13-64 - Contract/PO - Leadtime | 11 | 13-May-20 A | 29-May-20 A | 0 | 0 | 100%
S317080 | Create Large Support Rings Supports Detailed Design Drawings | 125 | 13-May-20 A | 09-Nov-20 A | 58466 | 56929 | 100%
S316510 | Create Internal Detector Structural Support Assembly Drawings - CA-D Resource(s) | 178 | 13-May-20 A | 29-Jan-21 A | 9425 | 9425 | 100%
S316505 | Create Internal Detector Structural Support Assembly Drawings - Physics Resource(s) Split | 178 | 13-May-20 A | 29-Jan-21 A | 5478 | 5478 | 100%
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | 305 | 13-May-20 A | 2021-07-30 | 5953 | 5953 | 75%
S317050 | Create INTT Supports Detailed Design Drawings | 314 | 13-May-20 A | 2021-08-12 | 26061 | 24020 | 65%
S306900 | Magnet: Move Quench Detector to location | 117 | 14-May-20 A | 30-Oct-20 A | 2001 | 2001 | 100%
S311500 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - Physics Resource(s) | 117 | 14-May-20 A | 30-Oct-20 A | 9130 | 9130 | 100%
S311510 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - CA-D Resource(s) | 117 | 14-May-20 A | 30-Oct-20 A | 46297 | 46297 | 100%
S110100 | Procure TPC v2 Outer Field Cage Parts - Contract Award(s) | 0 | 14-May-20 A |  | 0 | 0 | 100%
S120000 | Procure Trained Technician to work in CERN Shop on TPC GEMs - Delivery Acceptance | 5 | 14-May-20 A | 20-May-20 A | 44470 | 44470 | 100%
S243300 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Vendor Responses | 5 | 15-May-20 A | 21-May-20 A | 0 | 0 | 100%
S330602 | Gather Power Reqs for Subsystem Racks on Detector | 9 | 15-May-20 A | 29-May-20 A | 28876 | 28876 | 100%
S317070 | Create MBD Supports Detailed Design Drawings | 321 | 18-May-20 A | 2021-08-26 | 18243 | 17222 | 70%
S1005360 | Fabricate Multiple Transfer Line Spool 4 & 5 | 56 | 18-May-20 A | 05-Aug-20 A | 0 | 0 | 100%
S227400 | Fabricate SiPM Daughter Boards Sectors 13-64 - Contract Award(s) | 0 | 19-May-20 A |  | 0 | 0 | 100%
S317060 | Create MVTX Supports Detailed Design Drawings | 257 | 19-May-20 A | 28-May-21 A | 26061 | 24020 | 100%
S119800 | Procure Production of TPC GEM foils (includes Technician fees) - Contract Award(s) | 0 | 20-May-20 A |  | 0 | 0 | 100%
S198600 | Address Issues from Internal Review of Inner HCAL Support Rings | 5 | 20-May-20 A | 28-May-20 A | 4837 | 4837 | 100%
S186700 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Vendor Responses | 6 | 20-May-20 A | 29-May-20 A | 0 | 0 | 100%
S227510 | 20% EMCal SiPM Daughter Boards Delivered: Production Sectors 13-64 | 6 | 20-May-20 A | 29-May-20 A | 0 | 0 | 100%
S227520 | 40% EMCal SiPM Daughter Boards Delivered: Production Sectors 13-64 | 6 | 20-May-20 A | 29-May-20 A | 0 | 0 | 100%
S302500 | Magnet: Order AC Power Distribution Parts Labor | 191 | 20-May-20 A | 26-Feb-21 A | 1213 | 1178 | 100%
S120700 | Procure TPC GEM HV Power Supplies and Membrane Power Supply - Provide Requirements to Procurement | 5 | 21-May-20 A | 28-May-20 A | 3652 | 3652 | 100%
S120100 | Procure Production of TPC GEM foils (includes Technician fees) - Delivery Acceptance | 226 | 21-May-20 A | 17-Apr-21 A | 152390 | 154002 | 100%
S243400 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Vendor Selection | 5 | 22-May-20 A | 29-May-20 A | 0 | 0 | 100%
S243500 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Contract Award(s) | 0 | 27-May-20 A |  | 0 | 0 | 100%
S244200 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Contract Award(s) | 0 | 27-May-20 A |  | 0 | 0 | 100%
S243700 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Delivery Acceptance | 2 | 27-May-20 A | 29-May-20 A | 92544 | 94395 | 100%
S243600 | Procure HCal Electronics Production Power & Signal Cables (Internal) - Contract/PO - Leadtime | 2 | 27-May-20 A | 29-May-20 A | 0 | 0 | 100%
S1005560 | BNL review for PDR approval | 5 | 27-May-20 A | 02-Jun-20 A | 34933 | 34933 | 100%
S231600 | Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Contract Award(s) | 0 | 28-May-20 A |  | 0 | 0 | 100%
S226600 | EMCal Electronics Preproduction Complete | 0 |  | 28-May-20 A | 0 | 0 | 100%
S140800 | SAMPA ASIC Performance Accepted | 0 |  | 29-May-20 A | 0 | 0 | 100%
S231700 | Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Contract PO / Leadtime | 183 | 29-May-20 A | 24-Feb-21 A | 0 | 0 | 100%
S226900 | Respond to Results of EMCal Production Readiness and Safety Review | 7 | 29-May-20 A | 08-Jun-20 A | 4778 | 4778 | 100%
S120800 | Procure TPC GEM HV Power Supplies and Membrane Power Supply - Prepare & Send Solicitation | 22 | 29-May-20 A | 30-Jun-20 A | 0 | 0 | 100%
S198100 | Inner HCAL Support Structure Design Complete | 0 |  | 29-May-20 A | 0 | 0 | 100%
S195000 | Procure EMCAL Mechanical Parts for Final Sectors - Vendor Responses | 21 | 01-Jun-20 A | 30-Jun-20 A | 0 | 0 | 100%
S195100 | Procure EMCAL Mechanical Parts for Final Sectors - Vendor Selection | 21 | 01-Jun-20 A | 30-Jun-20 A | 0 | 0 | 100%
S187300 | Procure light guides for modules in Sectors 13-64 - Contract/PO Leadtime | 145 | 01-Jun-20 A | 30-Dec-20 A | 0 | 0 | 100%
S167900 | Pack and ship EMCAL blocks for Prepro sector 5 to BNL Purchased Services | 5 | 01-Jun-20 A | 05-Jun-20 A | 866 | 866 | 100%
S168000 | Pack and ship EMCAL blocks for Prepro sector 5 to BNL M&S | 5 | 01-Jun-20 A | 05-Jun-20 A | 1229 | 1229 | 100%
S330604 | Power Distribution Conceptual Gesign for Subsystem Racks on Detector | 15 | 01-Jun-20 A | 19-Jun-20 A | 28876 | 28876 | 100%
S171015 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 15 | 20 | 01-Jun-20 A | 26-Jun-20 A | 40858 | 40858 | 100%
S262600 | Trigger Prototype v1: Test trigger systems | 184 | 01-Jun-20 A | 26-Feb-21 A | 0 | 0 | 100%
S110400 | Assemble TPC v2 Outer Field Cage | 287 | 01-Jun-20 A | 2021-07-22 | 0 | 0 | 98%
S111900 | Assemble TPC v2 Central Membrane | 287 | 01-Jun-20 A | 2021-07-22 | 0 | 0 | 90%
S229500 | Fabricate EMCAL Interface Board Sectors 13-64 - Provide Requirements to Fabricator | 3 | 02-Jun-20 A | 05-Jun-20 A | 12197 | 12197 | 100%
S297500 | (Cryo Controls Hardware procurement) 32 conductor cables, IP8 to 1008B racks Labor | 3 | 02-Jun-20 A | 05-Jun-20 A | 1518 | 1518 | 100%
S297400 | (Cryo Controls Hardware procurement) 32 conductor cables, IP8 to 1008B racks M&S | 3 | 02-Jun-20 A | 05-Jun-20 A | 18207 | 18207 | 100%
S209000 | Procure Outer HCAL Assembly & Testing Equipment - Provide Requirements to Procurement | 2 | 03-Jun-20 A | 05-Jun-20 A | 9568 | 9568 | 100%
S209100 | Procure Outer HCAL Assembly & Testing Equipment - Prepare & Send Solicitation | 2 | 03-Jun-20 A | 05-Jun-20 A | 0 | 0 | 100%
S209200 | Procure Outer HCAL Assembly & Testing Equipment - Vendor Responses | 2 | 03-Jun-20 A | 05-Jun-20 A | 0 | 0 | 100%
S209300 | Procure Outer HCAL Assembly & Testing Equipment - Vendor Selection | 2 | 03-Jun-20 A | 05-Jun-20 A | 0 | 0 | 100%
S1005600 | AET submits IDR to BNL for approval | 27 | 03-Jun-20 A | 10-Jul-20 A | 0 | 0 | 100%
S209400 | Procure Outer HCAL Assembly & Testing Equipment - Contract Award(s) | 0 | 05-Jun-20 A |  | 0 | 0 | 100%
S229600 | Fabricate EMCAL Interface Board Sectors 13-64 - Prepare & Send Solicitation | 1 | 08-Jun-20 A | 09-Jun-20 A | 0 | 0 | 100%
S209500 | Procure Outer HCAL Assembly & Testing Equipment - Contract/PO - Leadtime | 26 | 08-Jun-20 A | 15-Jul-20 A | 0 | 0 | 100%
S204900 | Procure Outer HCAL Splice Plates - Contract Award(s) | 0 | 09-Jun-20 A |  | 0 | 0 | 100%
S229700 | Fabricate EMCAL Interface Board Sectors 13-64 - Vendor Responses | 2 | 09-Jun-20 A | 11-Jun-20 A | 0 | 0 | 100%
S195500 | Procure EMCAL Cooling System for Final Sectors - Provide Requirements to Procurement | 4 | 09-Jun-20 A | 15-Jun-20 A | 8247 | 8247 | 100%
S195600 | Procure EMCAL Cooling System for Final Sectors - Prepare & Send Solicitation | 4 | 09-Jun-20 A | 15-Jun-20 A | 0 | 0 | 100%
S227530 | 60% EMCal SiPM Daughter Boards Delivered: Production Sectors 13-64 | 15 | 09-Jun-20 A | 30-Jun-20 A | 0 | 0 | 100%
S186800 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Vendor Selection | 5 | 10-Jun-20 A | 17-Jun-20 A | 0 | 0 | 100%
S1005620 | BNL review for IDR approval | 23 | 10-Jun-20 A | 13-Jul-20 A | 34933 | 34933 | 100%
S229800 | Fabricate EMCAL Interface Board Sectors 13-64 - Vendor Selection | 1 | 11-Jun-20 A | 12-Jun-20 A | 0 | 0 | 100%
S296800 | (Cryo Controls Hardware procurement) Pressure transmitters Labor | 1 | 12-Jun-20 A | 15-Jun-20 A | 1518 | 1518 | 100%
S296900 | (Cryo Controls Hardware procurement) Pressure transmitters M&S | 1 | 12-Jun-20 A | 15-Jun-20 A | 7283 | 7283 | 100%
S228190 | 5% EMCal SiPM Daughter Boards Tested: Production Sectors 13-64 | 0 |  | 12-Jun-20 A | 0 | 0 | 100%
S121100 | Procure TPC GEM HV Power Supplies - Contract Award(s) | 0 | 15-Jun-20 A |  | 0 | 0 | 100%
S229900 | Fabricate EMCAL Interface Board Sectors 13-64 - Contract Award(s) | 0 | 15-Jun-20 A |  | 0 | 0 | 100%
S298000 | (Cryo Controls Hardware procurement) Heater UL listed Control Panel Labor | 3 | 15-Jun-20 A | 18-Jun-20 A | 1824 | 1824 | 100%
S298100 | (Cryo Controls Hardware procurement) Heater UL listed Control Panel M&S | 3 | 15-Jun-20 A | 18-Jun-20 A | 20892 | 20892 | 100%
S208306 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 5&6 | 5 | 15-Jun-20 A | 22-Jun-20 A | 252582 | 252582 | 100%
S120900 | Procure TPC GEM HV Power Supplies and Membrane Power Supply - Vendor Responses | 7 | 15-Jun-20 A | 24-Jun-20 A | 0 | 0 | 100%
S121000 | Procure TPC GEM HV Power Supplies and Membrane Power Supply - Vendor Selection | 7 | 15-Jun-20 A | 24-Jun-20 A | 0 | 0 | 100%
S208400 | Outer HCAL Scintillating Tile Acceptance Testing | 130 | 15-Jun-20 A | 22-Dec-20 A | 11641 | 11583 | 100%
S170300 | EMCal W Powder Acquisition Complete | 0 |  | 15-Jun-20 A | 0 | 0 | 100%
S170210 | Procure EMCAL W Powder for Final Blocks - Sectors 39-64 - Delivery Acceptance | 9 | 15-Jun-20 A | 26-Jun-20 A | 540981 | 540981 | 100%
S133300 | Procure TPC R3 Module Prod. Parts (Padplanes) - Delivery Acceptance | 26 | 16-Jun-20 A | 22-Jul-20 A | 81669 | 81669 | 100%
S230000 | Fabricate EMCAL Interface Board Sectors 13-64 - Contract/PO - Leadtime | 96 | 16-Jun-20 A | 02-Nov-20 A | 0 | 0 | 100%
S147700 | Develop TPC DAM FPGA Algorithm - Round 3 | 238 | 16-Jun-20 A | 28-May-21 A | 39041 | 38987 | 100%
S337500 | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety | 95 | 17-Jun-20 A | 30-Oct-20 A | 3972 | 1324 | 100%
S1005640 | AET submits FDR report to BNL for approval | 28 | 17-Jun-20 A | 27-Jul-20 A | 78600 | 78600 | 100%
S151400 | Procurement Readiness Review - TPC Gas System | 256 | 22-Jun-20 A | 30-Jun-21 A | 1277 | 1277 | 100%
S330608 | Specify Power Controls Distribution Equipment | 110 | 22-Jun-20 A | 30-Nov-20 A | 28876 | 28876 | 100%
S208308 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 7&8 | 5 | 23-Jun-20 A | 30-Jun-20 A | 252582 | 252582 | 100%
S208310 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 9&10 | 48 | 23-Jun-20 A | 31-Aug-20 A | 235905 | 235905 | 100%
S187000 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Contract/PO - Leadtime | 107 | 24-Jun-20 A | 30-Nov-20 A | 0 | 0 | 100%
S195700 | Procure EMCAL Cooling System for Final Sectors - Vendor Responses | 24 | 25-Jun-20 A | 30-Jul-20 A | 0 | 0 | 100%
S195200 | Procure EMCAL Mechanical Parts for Final Sectors - Contract Award(s) | 0 | 30-Jun-20 A |  | 0 | 0 | 100%
S186900 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Contract Award(s) | 0 | 30-Jun-20 A |  | 0 | 0 | 100%
S198700 | Inner HCAL Support Rings Design Complete | 0 |  | 30-Jun-20 A | 0 | 0 | 100%
S257800 | Procure DAQ Production ATPs - Provide Requirements to Procurement | 39 | 30-Jun-20 A | 25-Aug-20 A | 26316 | 25550 | 100%
S195300 | Procure EMCAL Mechanical Parts for Final Sectors - Contract/PO - Leadtime | 104 | 30-Jun-20 A | 30-Nov-20 A | 0 | 0 | 100%
S311350 | Carriage Cradle - Delivery Acceptance - M&S | 1 | 01-Jul-20 A | 02-Jul-20 A | 233102 | 228531 | 100%
S339000 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation - Physics Resource(s) | 9 | 01-Jul-20 A | 15-Jul-20 A | 4232 | 1881 | 100%
S329408 | Conceptual Design for Cable Routing from Detector to Rack (TPC) | 249 | 01-Jul-20 A | 30-Jun-21 A | 14707 | 14707 | 100%
S128900 | Procure TPC R2 Module Prod. Parts (Padplanes) - Contract Award(s) | 0 | 01-Jul-20 A |  | 0 | 0 | 100%
S168100 | Pack and ship EMCAL blocks for Prepro sector 6 to BNL Purchased Services | 5 | 01-Jul-20 A | 08-Jul-20 A | 866 | 866 | 100%
S168200 | Pack and ship EMCAL blocks for Prepro sector 6 to BNL M&S | 5 | 01-Jul-20 A | 08-Jul-20 A | 1229 | 1229 | 100%
S166500 | Fabricate EMCAL Prepro blocks sector 7 | 10 | 01-Jul-20 A | 15-Jul-20 A | 9425 | 9425 | 100%
S171016 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 16 | 21 | 01-Jul-20 A | 30-Jul-20 A | 40858 | 40858 | 100%
S348100 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - M&S | 21 | 01-Jul-20 A | 31-Jul-20 A | 45699 | 45517 | 100%
S147800 | Procure TPC EDBC Computers & Peripherals - Provide Requirements to Procurement | 41 | 01-Jul-20 A | 28-Aug-20 A | 44708 | 44708 | 100%
S129000 | Procure TPC R2 Module Prod. Parts (Padplanes) - Contract/PO - Leadtime | 42 | 01-Jul-20 A | 31-Aug-20 A | 0 | 0 | 100%
S199400 | Manufacture Inner HCAL Support Rings - Provide Requirements to Procurement | 102 | 01-Jul-20 A | 30-Nov-20 A | 36951 | 36951 | 100%
S198800 | Manufacture Inner HCAL Support Structure - Prepare & Send Solicitation | 116 | 01-Jul-20 A | 18-Dec-20 A | 10806 | 10491 | 100%
S208410 | Outer HCAL Scintillating Tile Acceptance Testing - Contributed Labor | 118 | 01-Jul-20 A | 22-Dec-20 A | 47037 | 46803 | 100%
S205000 | Procure Outer HCAL Splice Plates - Contract/PO - Leadtime | 144 | 01-Jul-20 A | 01-Feb-21 A | 0 | 0 | 100%
S296200 | (Cryo Controls Hardware procurement) Lakeshore Temperature Controller/conditioners Labor | 18 | 07-Jul-20 A | 31-Jul-20 A | 1518 | 1518 | 100%
S296300 | (Cryo Controls Hardware procurement) Lakeshore Temperature Controller/conditioners M&S | 18 | 07-Jul-20 A | 31-Jul-20 A | 5690 | 5690 | 100%
S147900 | Procure TPC EDBC Computers & Peripherals - Prepare & Send Solicitation | 156 | 09-Jul-20 A | 25-Feb-21 A | 0 | 0 | 100%
S301000 | (Cryo Controls Hardware) PLC programming | 284 | 13-Jul-20 A | 2021-08-27 | 84816 | 88355 | 92%
S339100 | Evaluate & Process Beampipe/Vacuum Components Bids - Physics Resource(s) | 75 | 15-Jul-20 A | 30-Oct-20 A | 4232 | 1881 | 100%
S329450 | Conceptual Design for Routing Detector Cooling System | 264 | 15-Jul-20 A | 2021-08-03 | 36540 | 36540 | 35%
S339010 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation - CA-D Resource(s) | 11 | 16-Jul-20 A | 31-Jul-20 A | 5461 | 4854 | 100%
S339110 | Evaluate & Process Beampipe/Vacuum Components Bids - CA-D Resource(s) | 74 | 16-Jul-20 A | 30-Oct-20 A | 5461 | 4854 | 100%
S168300 | Pack and ship EMCAL blocks for Prepro sector 7 to BNL Purchased Services | 5 | 16-Jul-20 A | 22-Jul-20 A | 866 | 866 | 100%
S168400 | Pack and ship EMCAL blocks for Prepro sector 7 to BNL M&S | 5 | 16-Jul-20 A | 22-Jul-20 A | 1229 | 1229 | 100%
S166600 | Fabricate EMCAL Prepro blocks sector 8 | 10 | 16-Jul-20 A | 29-Jul-20 A | 9425 | 9425 | 100%
S209600 | Procure Outer HCAL Assembly & Testing Equipment- Delivery Acceptance | 8 | 20-Jul-20 A | 30-Jul-20 A | 85344 | 87051 | 100%
S258600 | DAQ Production: Procure jSEB Slow control computers | 259 | 20-Jul-20 A | 2021-07-30 | 26316 | 25550 | 50%
S298800 | (Cryo Controls Hardware Procurement) 32 conductor cable LN2 | 9 | 20-Jul-20 A | 31-Jul-20 A | 7397 | 7397 | 100%
S186400 | Production Readiness Review - EMCal Modules for Sectors 13-64 | 2 | 27-Jul-20 A | 29-Jul-20 A | 65379 | 65379 | 100%
S1005680 | AET begins material procurement | 45 | 28-Jul-20 A | 30-Sep-20 A | 0 | 0 | 100%
S312300 | CC Drive & Alignment System - Prepare Procurement Package - Physics Resource(s) | 60 | 28-Jul-20 A | 21-Oct-20 A | 2282 | 2282 | 100%
S312310 | CC Drive & Alignment System - Prepare Procurement Package - CA-D Resource(s) | 60 | 28-Jul-20 A | 21-Oct-20 A | 6588 | 6588 | 100%
S195800 | Procure EMCAL Cooling System for Final Sectors - Vendor Selection | 1 | 29-Jul-20 A | 30-Jul-20 A | 0 | 0 | 100%
S194500 | Revise sector assembly procedure based on preproduction Sector 1-12 fabrication | 0 | 30-Jul-20 A | 30-Jul-20 A | 21206 | 21206 | 100%
S194600 | Production Readiness Review - EMCal Sectors 13-63 | 0 | 30-Jul-20 A | 30-Jul-20 A | 29247 | 29247 | 100%
S194700 | EMCal Production Readiness Review Blocks/Modules/Sectors Complete | 0 |  | 30-Jul-20 A | 0 | 0 | 100%
S166700 | Fabricate EMCAL Prepro blocks sector 9 | 12 | 30-Jul-20 A | 14-Aug-20 A | 9425 | 9425 | 100%
S195900 | Procure EMCAL Cooling System for Final Sectors - Contract Award(s) | 0 | 31-Jul-20 A |  | 0 | 0 | 100%
S1005400 | Fabricate Multiple Transfer Line Spool 1, 2, 3, and Field Joint Sleeve | 35 | 31-Jul-20 A | 18-Sep-20 A | 0 | 0 | 100%
S1005440 | Delivery Multiple Transfer Line Spool 4 & 5 with Document Package | 42 | 31-Jul-20 A | 30-Sep-20 A | 0 | 0 | 100%
S255200 | DAQ Production: Design and layout the various types of front-end boards | 4 | 03-Aug-20 A | 07-Aug-20 A | 16199 | 15727 | 100%
S343814 | Start Track Modification - IR Assembly and Detail Drawings | 41 | 03-Aug-20 A | 30-Sep-20 A | 19074 | 18829 | 100%
S343812 | Start Track Modification - IR Prelim Design and Safety Review | 41 | 03-Aug-20 A | 30-Sep-20 A | 2967 | 3708 | 100%
S343818 | Start Track Modification - IR Address Action Items from D&S Review | 41 | 03-Aug-20 A | 30-Sep-20 A | 3966 | 3850 | 100%
S343816 | Start Track Modification - IR Final Design and Safety Review | 41 | 03-Aug-20 A | 30-Sep-20 A | 5179 | 5028 | 100%
S304500 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008B L | 157 | 03-Aug-20 A | 23-Mar-21 A | 8228 | 7989 | 100%
S304400 | Magnet Power Supply Installation: Cooling Water Installation 1008B | 201 | 03-Aug-20 A | 24-May-21 A | 8228 | 7989 | 100%
S304600 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008B M&S | 201 | 03-Aug-20 A | 24-May-21 A | 8925 | 8925 | 100%
S226901 | Completed: Production Readiness Review, Safety Review - EMCal FEE sectors 13-64 | 0 |  | 03-Aug-20 A | 0 | 0 | 100%
S168500 | Pack and ship EMCAL blocks for Prepro sector 8 to BNL Purchased Services | 5 | 03-Aug-20 A | 07-Aug-20 A | 866 | 866 | 100%
S168600 | Pack and ship EMCAL blocks for Prepro sector 8 to BNL M&S | 5 | 03-Aug-20 A | 07-Aug-20 A | 1229 | 1229 | 100%
S172900 | Production Readiness Review, Safety Review - EMCal Blocks | 5 | 03-Aug-20 A | 07-Aug-20 A | 1645 | 1580 | 100%
S228700 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Provide Requirements to Procure & Assem | 5 | 03-Aug-20 A | 07-Aug-20 A | 12197 | 12197 | 100%
S230400 | Fabricate Calorimeter Production Controller Boards - Provide Requirements to Procurement | 5 | 03-Aug-20 A | 07-Aug-20 A | 0 | 0 | 100%
S225300 | Test Pulse Boards 1-12 - M&S | 10 | 03-Aug-20 A | 14-Aug-20 A | 4804 | 4804 | 100%
S288700 | Procure LN2 supply transfer line system - Prepare & Send Solicitation | 15 | 03-Aug-20 A | 21-Aug-20 A | 0 | 0 | 100%
S299000 | (Cryo Controls Hardware Procurement) Acopian 24V power Supply | 17 | 03-Aug-20 A | 25-Aug-20 A | 2276 | 2276 | 100%
S299200 | (Cryo Controls Hardware Procurement) 72 inch enclosure | 17 | 03-Aug-20 A | 25-Aug-20 A | 1707 | 1707 | 100%
S171017 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 17 | 20 | 03-Aug-20 A | 31-Aug-20 A | 40858 | 40858 | 100%
S140500 | Populate v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip | 41 | 03-Aug-20 A | 30-Sep-20 A | 3414 | 3414 | 100%
S251200 | Procure EMCAL 7-Crate Digitizer (Assembly & Tests) - Delivery Acceptance | 41 | 03-Aug-20 A | 30-Sep-20 A | 90872 | 90872 | 100%
S300700 | (Cryo Controls Hardware) Control Logic eng document revision by Cryo process engineering | 41 | 03-Aug-20 A | 30-Sep-20 A | 66297 | 65706 | 100%
S1007320 | Delivery two male bayonets and one vapor return female bayonet | 81 | 03-Aug-20 A | 30-Nov-20 A | 89080 | 89080 | 100%
S293000 | (Warm Piping tie in bldg. 1010B compressor) General Arrangement Layout | 162 | 03-Aug-20 A | 30-Mar-21 A | 17464 | 17464 | 100%
S140605 | Test v2 Prototype TPC FEE Board with 80nsec Full SAMPA Chip | 205 | 03-Aug-20 A | 28-May-21 A | 56737 | 56737 | 100%
S171800 | Procure EMCAL Epoxy for Final Blocks - Delivery Acceptance | 240 | 03-Aug-20 A | 2021-07-19 | 104858 | 104592 | 55%
S172500 | Order parts and fabricate molds for EMCal Sectors 13-64 Blocks - Delivery Acceptance | 240 | 03-Aug-20 A | 2021-07-19 | 30340 | 30218 | 75%
S292800 | (Warm Piping tie in to WR header) General Arrangement Layout | 241 | 03-Aug-20 A | 2021-07-20 | 17970 | 17970 | 97%
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | 269 | 03-Aug-20 A | 2021-08-27 | 2190 | 2190 | 60%
S258000 | Procure DAQ Production ATPs - Vendor Responses | 15 | 04-Aug-20 A | 25-Aug-20 A | 0 | 0 | 100%
S295700 | (Controls Hardware) I/O list table | 240 | 07-Aug-20 A | 2021-07-23 | 11550 | 11550 | 90%
S255300 | Procure DAQ Production Boards - Provide Requirements to Procurement | 2 | 10-Aug-20 A | 12-Aug-20 A | 9708 | 9425 | 100%
S209700 | Prepare Outer HCal Assembly Area for Production | 10 | 10-Aug-20 A | 24-Aug-20 A | 58226 | 58226 | 100%
S258900 | Procure DAQ Production Buffer Boxes - Provide Requirements to Procurement | 11 | 10-Aug-20 A | 25-Aug-20 A | 13158 | 12775 | 100%
S259000 | Procure DAQ Production Buffer Boxes - Prepare & Send Solicitation | 11 | 10-Aug-20 A | 25-Aug-20 A | 0 | 0 | 100%
S259100 | Procure DAQ Production Buffer Boxes - Vendor Responses | 11 | 10-Aug-20 A | 25-Aug-20 A | 0 | 0 | 100%
S230800 | Fabricate Calorimeter Production Controller Boards - Contract Award(s) | 0 | 10-Aug-20 A |  | 0 | 0 | 100%
S230500 | Fabricate Calorimeter Production Controller Boards M&S - Prepare & Send Solicitation | 10 | 10-Aug-20 A | 21-Aug-20 A | 0 | 0 | 100%
S231100 | Test Calorimeter Controller Boards: Production Sectors 13-64 | 12 | 10-Aug-20 A | 26-Aug-20 A | 1973 | 1973 | 100%
S230600 | Fabricate Calorimeter Production Controller Boards - Vendor Responses | 12 | 10-Aug-20 A | 26-Aug-20 A | 0 | 0 | 100%
S230700 | Fabricate Calorimeter Production Controller Boards - Vendor Selection | 12 | 10-Aug-20 A | 26-Aug-20 A | 0 | 0 | 100%
S230900 | Fabricate Calorimeter Production Controller Boards - Contract/PO - Leadtime | 12 | 10-Aug-20 A | 26-Aug-20 A | 0 | 0 | 100%
S231000 | Fabricate Calorimeter Production Controller Boards - Delivery Acceptance | 12 | 10-Aug-20 A | 26-Aug-20 A | 92155 | 92155 | 100%
S231105 | Test Calorimeter Controller Boards: Production Sectors 13-64 - Contributed Labor | 12 | 10-Aug-20 A | 26-Aug-20 A | 23272 | 23272 | 100%
S240400 | Fabricate HCal Preamp Boards - Delivery Acceptance | 15 | 11-Aug-20 A | 31-Aug-20 A | 47069 | 48011 | 100%
S304100 | Magnet Power Supply Installation: Connect DC Cabling to Power Supply, Dump Resistor, Magnet | 127 | 11-Aug-20 A | 17-Feb-21 A | 10617 | 10308 | 100%
S255400 | Procure DAQ Production Boards - Prepare & Send Solicitation | 2 | 13-Aug-20 A | 17-Aug-20 A | 0 | 0 | 100%
S146900 | Procure TPC DAM Felix 2.0 Boards - Vendor Responses | 10 | 13-Aug-20 A | 26-Aug-20 A | 0 | 0 | 100%
S208312 | Procure Outer HCAL Scintillating Tiles (Prod) - Delivery Acceptance 11&12 | 70 | 17-Aug-20 A | 30-Nov-20 A | 235905 | 235905 | 100%
S209800 | Populate Outer HCAL sectors with scintillating tiles | 152 | 17-Aug-20 A | 30-Mar-21 A | 15509 | 15509 | 100%
S209810 | Populate Outer HCAL sectors with scintillating tiles - Contributed Labor | 152 | 17-Aug-20 A | 30-Mar-21 A | 199251 | 199251 | 100%
S166800 | Fabricate EMCAL Prepro blocks sector 10 | 19 | 17-Aug-20 A | 11-Sep-20 A | 9425 | 9425 | 100%
S327800 | Size Conductors for Line Electric Power - CA-D Resource(s) | 31 | 17-Aug-20 A | 30-Sep-20 A | 4182 | 4182 | 100%
S1002039 | Size Conductors for Line Electric Power - Physics Resource(s) | 31 | 17-Aug-20 A | 30-Sep-20 A | 8364 | 8364 | 100%
S255500 | Procure DAQ Production Boards - Vendor Responses | 4 | 18-Aug-20 A | 24-Aug-20 A | 0 | 0 | 100%
S303900 | Magnet Power Supply Installation: Move Power Supply to location | 7 | 18-Aug-20 A | 27-Aug-20 A | 2061 | 2001 | 100%
S1005480 | Delivery Multiple Transfer Line Spool 1, 2, 3, and Field Joint Sleeve with Document Package | 28 | 20-Aug-20 A | 30-Sep-20 A | 0 | 0 | 100%
S257900 | Procure DAQ Production ATPs - Prepare & Send Solicitation | 2 | 21-Aug-20 A | 25-Aug-20 A | 0 | 0 | 100%
S148701 | Final Design Review - TPC Laser System | 2 | 24-Aug-20 A | 26-Aug-20 A | 1277 | 1240 | 100%
S151201 | Final Design Review - TPC Gas Handling System | 2 | 24-Aug-20 A | 26-Aug-20 A | 1277 | 1277 | 100%
S255100 | Production Readiness Review - DAQ | 2 | 24-Aug-20 A | 26-Aug-20 A | 2524 | 2524 | 100%
S288800 | Procure LN2 supply transfer line system - Vendor Responses & Selection | 55 | 24-Aug-20 A | 10-Nov-20 A | 0 | 0 | 100%
S141900 | Procure TPC FEE LV power supplies - Provide Requirements to Procurement | 2 | 25-Aug-20 A | 27-Aug-20 A | 4854 | 4712 | 100%
S209701 | Production Readiness Review - OHCal Sector Assembly 7-32 | 4 | 25-Aug-20 A | 31-Aug-20 A | 1370 | 1370 | 100%
S147100 | Procure TPC DAM Felix 2.0 Boards - Contract Award(s) | 0 | 27-Aug-20 A |  | 0 | 0 | 100%
S129100 | Procure TPC R2 Module Prod. Parts (Padplanes) - Delivery Acceptance | 44 | 27-Aug-20 A | 29-Oct-20 A | 60299 | 60299 | 100%
S147000 | Procure TPC DAM Felix 2.0 Boards - Vendor Selection | 44 | 27-Aug-20 A | 30-Oct-20 A | 0 | 0 | 100%
S327900 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - CA-D Resource(s) | 145 | 27-Aug-20 A | 31-Mar-21 A | 8364 | 8364 | 100%
S1002079 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - Physics Resource(s) | 145 | 27-Aug-20 A | 31-Mar-21 A | 8364 | 8364 | 100%
S154101 | Final Design Review - TPC Cooling System | 1 | 28-Aug-20 A | 31-Aug-20 A | 1277 | 1277 | 100%
S147200 | Procure TPC DAM Felix 2.0 Boards - Contract/PO - Leadtime | 162 | 28-Aug-20 A | 26-Apr-21 A | 0 | 0 | 100%
S234100 | EMCal Low Voltage Power System Sectors 13-64 - M&S | 206 | 31-Aug-20 A | 29-Jun-21 A | 39270 | 39270 | 100%
S240500 | 50% HCal Preamp Board Assembly complete: Production | 0 |  | 31-Aug-20 A | 0 | 0 | 100%
S240600 | Hcal Preamp Board Assembly Complete: Production | 0 |  | 31-Aug-20 A | 0 | 0 | 100%
S168700 | Pack and ship EMCAL blocks for Prepro sector 9 to BNL Purchased Services | 5 | 01-Sep-20 A | 08-Sep-20 A | 866 | 866 | 100%
S168800 | Pack and ship EMCAL blocks for Prepro sector 9 to BNL M&S | 5 | 01-Sep-20 A | 08-Sep-20 A | 1229 | 1229 | 100%
S228800 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Prepare & Send Solicitation | 8 | 01-Sep-20 A | 14-Sep-20 A | 0 | 0 | 100%
S258100 | Procure DAQ Production ATPs - Vendor Selection | 20 | 01-Sep-20 A | 29-Sep-20 A | 0 | 0 | 100%
S171018 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 18 | 21 | 01-Sep-20 A | 30-Sep-20 A | 40858 | 40858 | 100%
S311300 | Carriage Cradle - Delivery Acceptance - Physics Resource(s) - Labor | 80 | 02-Sep-20 A | 30-Dec-20 A | 10956 | 10956 | 100%
S311310 | Carriage Cradle - Delivery Acceptance - CA-D Resource(s) - Labor | 80 | 02-Sep-20 A | 30-Dec-20 A | 7899 | 7899 | 100%
S343850 | Start Track Modification - AH Prelim Design and Safety Review | 16 | 08-Sep-20 A | 30-Sep-20 A | 5033 | 4886 | 100%
S343854 | Start Track Modification - AH Final Design and Safety Review | 16 | 08-Sep-20 A | 30-Sep-20 A | 6393 | 6206 | 100%
S343852 | Start Track Modification - AH Assembly and Detail Drawings | 16 | 08-Sep-20 A | 30-Sep-20 A | 10431 | 20255 | 100%
S343856 | Start Track Modification - AH Address Action Items from D&S Review | 16 | 08-Sep-20 A | 30-Sep-20 A | 3196 | 6206 | 100%
S239100 | Fabricate HCal SiPM Boards - Delivery Acceptance | 12 | 14-Sep-20 A | 30-Sep-20 A | 110822 | 110822 | 100%
S335000 | Analyze Rack Room Modifications Requirements - CA-D Resource(s) | 111 | 14-Sep-20 A | 26-Feb-21 A | 303 | 303 | 100%
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | 111 | 14-Sep-20 A | 26-Feb-21 A | 21811 | 21811 | 100%
S195400 | Procure EMCAL Mechanical Parts for Final Sectors - Delivery Acceptance | 187 | 14-Sep-20 A | 14-Jun-21 A | 291746 | 291746 | 100%
S168900 | Pack and ship EMCAL blocks for Prepro sector 10 to BNL Purchased Services | 5 | 14-Sep-20 A | 18-Sep-20 A | 866 | 866 | 100%
S169000 | Pack and ship EMCAL blocks for Prepro sector 10 to BNL M&S | 5 | 14-Sep-20 A | 18-Sep-20 A | 1229 | 1229 | 100%
S166900 | Fabricate EMCAL Prepro blocks sector 11 | 10 | 14-Sep-20 A | 25-Sep-20 A | 9425 | 9425 | 100%
S239300 | Test HCal SiPM Boards: Production | 5 | 15-Sep-20 A | 22-Sep-20 A | 24536 | 24536 | 100%
S317020 | Create Magnet Supports Detailed Design Drawings | 72 | 15-Sep-20 A | 30-Dec-20 A | 67759 | 63310 | 100%
S344800 | Create Survey Plan | 89 | 15-Sep-20 A | 27-Jan-21 A | 14531 | 14107 | 100%
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | 110 | 16-Sep-20 A | 26-Feb-21 A | 9829 | 9543 | 100%
S303200 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution in 1008B to 1008IR | 245 | 16-Sep-20 A | 2021-09-08 | 40019 | 38853 | 30%
S307922 | Final Field Calculations Pre-measurement - Phys | 7 | 21-Sep-20 A | 30-Sep-20 A | 4242 | 4229 | 100%
S307923 | Final Field Calculations Pre-measurement - CAD | 7 | 21-Sep-20 A | 30-Sep-20 A | 9101 | 9073 | 100%
S239200 | HCal SiPM Boards Assembly Complete | 0 |  | 22-Sep-20 A | 0 | 0 | 100%
S239400 | 25% Hcal SiPM Board testing complete: Production | 0 |  | 22-Sep-20 A | 0 | 0 | 100%
S239500 | 50% Hcal SiPM Board testing complete: Production | 0 |  | 22-Sep-20 A | 0 | 0 | 100%
S239600 | 75% Hcal SiPM Board testing complete: Production | 0 |  | 22-Sep-20 A | 0 | 0 | 100%
S239700 | Hcal SiPM Board testing Complete: Production | 0 |  | 22-Sep-20 A | 0 | 0 | 100%
S142000 | Procure TPC FEE LV Power Supplies - Prepare & Send Solicitation | 6 | 22-Sep-20 A | 30-Sep-20 A | 0 | 0 | 100%
S297600 | (Cryo Controls Hardware procurement) 8 conductor cables, IP8 to 1008B racks Labor | 6 | 22-Sep-20 A | 30-Sep-20 A | 1564 | 1518 | 100%
S297700 | (Cryo Controls Hardware procurement) 8 conductor cables, IP8 to 1008B racks M&S | 6 | 22-Sep-20 A | 30-Sep-20 A | 7196 | 7055 | 100%
S1005840 | AET submits PDR report to BNL for approval of 1008B Cold Box Assembly | 6 | 22-Sep-20 A | 30-Sep-20 A | 0 | 0 | 100%
S1005720 | Fabricate Interconnect (S-Line, H-Line, U-Line), vacuum break, Field Joint Tee and Sleeve | 25 | 22-Sep-20 A | 28-Oct-20 A | 0 | 0 | 100%
S121400 | Procure TPC GEM HV Power Supplies - Delivery Acceptance | 28 | 22-Sep-20 A | 30-Oct-20 A | 125263 | 125263 | 100%
S287000 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Rigging in place | 36 | 22-Sep-20 A | 12-Nov-20 A | 25454 | 25454 | 100%
S287200 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: Rigging in place | 68 | 22-Sep-20 A | 31-Dec-20 A | 13023 | 12643 | 100%
S298600 | (Cryo Controls Hardware procurement) Cable tray and supports Labor | 105 | 22-Sep-20 A | 26-Feb-21 A | 5994 | 5819 | 100%
S298700 | (Cryo Controls Hardware procurement) Cable tray and supports M&S | 105 | 22-Sep-20 A | 26-Feb-21 A | 4643 | 4552 | 100%
S303100 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008B | 126 | 22-Sep-20 A | 29-Mar-21 A | 26679 | 25902 | 100%
S303400 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B | 126 | 22-Sep-20 A | 29-Mar-21 A | 49575 | 48131 | 100%
S199500 | Manufacture Inner HCAL Support Rings - Prepare & Send Solicitation | 44 | 23-Sep-20 A | 30-Nov-20 A | 0 | 0 | 100%
S240700 | Test HCal Preamp Boards: Production | 123 | 28-Sep-20 A | 30-Mar-21 A | 37473 | 37473 | 100%
S167000 | Fabricate EMCAL Prepro blocks sector 12 | 10 | 28-Sep-20 A | 09-Oct-20 A | 9623 | 9425 | 100%
S257400 | Procure DAQ Production SEBs - Contract Award(s) | 0 | 30-Sep-20 A |  | 0 | 0 | 100%
S251300 | Preprod Calorimeter Digitizer 7-Crate Complete | 0 |  | 30-Sep-20 A | 0 | 0 | 100%
S288300 | (LN2 supply transfer line system) Bid package LN2 System Completed | 0 |  | 30-Sep-20 A | 0 | 0 | 100%
S343820 | Start Track Modification - IR Design Complete | 0 |  | 30-Sep-20 A | 0 | 0 | 100%
S258200 | Procure DAQ Production ATPs - Contract Award(s) | 0 | 30-Sep-20 A |  | 0 | 0 | 100%
S101015 | FY21 funding available | 0 | 01-Oct-20 A |  | 0 | 0 | 100%
S276900 | 2021 Facility Support Systems L3 Project Management | 250 | 01-Oct-20 A | 2021-09-30 | 36427 | 36335 | 74.4%
S119000 | TPC Module Safety Review | 1 | 01-Oct-20 A | 01-Oct-20 A | 1316 | 1277 | 100%
S169100 | Pack and ship EMCAL blocks for Prepro sector 11 to BNL Purchased Services | 5 | 01-Oct-20 A | 07-Oct-20 A | 892 | 866 | 100%
S169200 | Pack and ship EMCAL blocks for Prepro sector 11 to BNL M&S | 5 | 01-Oct-20 A | 07-Oct-20 A | 1254 | 1229 | 100%
S312400 | CC Drive & Alignment System - Procurement Readiness Review - Physics Resource(s) | 5 | 01-Oct-20 A | 07-Oct-20 A | 2351 | 2282 | 100%
S312410 | CC Drive & Alignment System - Procurement Readiness Review - CA-D Resource(s) | 5 | 01-Oct-20 A | 07-Oct-20 A | 6786 | 6588 | 100%
S343822 | Start Track Modification - IR Prepare Procur. Package | 10 | 01-Oct-20 A | 15-Oct-20 A | 5846 | 5741 | 100%
S1005880 | BNL review for PDR approval | 10 | 01-Oct-20 A | 15-Oct-20 A | 26200 | 26200 | 100%
S299100 | (Cryo Controls Hardware Procurement) +/- 15 volt Power Supply | 17 | 01-Oct-20 A | 26-Oct-20 A | 580 | 569 | 100%
S348200 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | 20 | 01-Oct-20 A | 29-Oct-20 A | 10807 | 10492 | 100%
S348210 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - CA-D Resource(s) | 20 | 01-Oct-20 A | 29-Oct-20 A | 8758 | 8502 | 100%
S258300 | Procure DAQ Production ATPs - Contract/PO - Leadtime | 20 | 01-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S298900 | (Cryo Controls Hardware Procurement) Plastic general 32 conductor connectors (pairs) | 20 | 01-Oct-20 A | 30-Oct-20 A | 348 | 341 | 100%
S171019 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 19 | 21 | 01-Oct-20 A | 30-Oct-20 A | 40858 | 40858 | 100%
S308611 | Specify and test probes for field monitoring | 61 | 01-Oct-20 A | 31-Dec-20 A | 8247 | 8247 | 100%
S339600 | Model IR HVAC Thermal Requirements | 80 | 01-Oct-20 A | 29-Jan-21 A | 4782 | 17269 | 100%
S275300 | 2021 Cryo L3 Project Management | 164 | 01-Oct-20 A | 31-May-21 A | 46714 | 46714 | 100%
S296600 | (Cryo Controls Hardware procurement) SC level probes Labor | 227 | 01-Oct-20 A | 2021-08-27 | 1564 | 1518 | 50%
S296700 | (Cryo Controls Hardware procurement) SC level probes M&S | 227 | 01-Oct-20 A | 2021-08-27 | 3482 | 3414 | 50%
S308621 | Conceptual design of mapping campaign | 249 | 01-Oct-20 A | 2021-09-29 | 6787 | 6787 | 60%
S104200 | Travel FY21 | 250 | 01-Oct-20 A | 2021-09-30 | 6905 | 6905 | 74.4%
S103200 | Mgmt Labor - A - MIE - FY21 | 250 | 01-Oct-20 A | 30-Sep-21* | 170568 | 170568 | 74.4%
S103310 | Mgmt labor - B - BNL Contributed Labor - FY21 - CA-D Resource(s) | 250 | 01-Oct-20 A | 30-Sep-21* | 154145 | 154145 | 74.3%
S103300 | Mgmt labor - B - BNL Contributed Labor - FY21 - Physics Resource(s) | 250 | 01-Oct-20 A | 30-Sep-21* | 1589056 | 1589056 | 74.3%
S274700 | 2021 Magnet Project Management | 250 | 01-Oct-20 A | 2021-09-30 | 155997 | 155997 | 74.4%
S275800 | 2021 PS & Quench Protection L3 Project Management | 250 | 01-Oct-20 A | 2021-09-30 | 61658 | 61658 | 74.4%
S276300 | 2021 Infrastructure Project Management | 250 | 01-Oct-20 A | 2021-09-30 | 256639 | 256639 | 74.4%
S277500 | 2021 Detector Support Systems L3 Project Management | 250 | 01-Oct-20 A | 2021-09-30 | 128399 | 112608 | 74.4%
S278100 | 2021 Integration & Installation Project Management | 249 | 02-Oct-20 A | 2021-09-30 | 289512 | 289478 | 74.4%
S337600 | Address Action Items from Cryo Structural Support in IR Detail Design & Safety Reviews | 4 | 06-Oct-20 A | 13-Oct-20 A | 3941 | 2126 | 100%
S149600 | Procure TPC Lasers - Delivery Acceptance | 215 | 06-Oct-20 A | 2021-08-16 | 169274 | 165955 | 50%
S121500 | Procure TPC GEM HV Membrane Power Supply - Delivery Acceptance | 5 | 06-Oct-20 A | 13-Oct-20 A | 12245 | 12245 | 100%
S133700 | Build TPC R3a Modules | 192 | 06-Oct-20 A | 2021-07-14 | 0 | 0 | 85%
S133900 | Build TPC R3b Modules | 192 | 06-Oct-20 A | 2021-07-14 | 0 | 0 | 85%
S317030 | Create EMCal Supports Detailed Design Drawings | 13 | 08-Oct-20 A | 28-Oct-20 A | 28667 | 27136 | 100%
S317031 | Review Design and Safety EMCal Supports | 13 | 08-Oct-20 A | 28-Oct-20 A | 104 | 104 | 100%
S317032 | Address Action Items for EMCal Supports | 13 | 08-Oct-20 A | 28-Oct-20 A | 104 | 104 | 100%
S312500 | CC Drive & Alignment System - Provide Requirement to Procurement | 5 | 08-Oct-20 A | 15-Oct-20 A | 1401 | 1361 | 100%
S343858 | Start Track Modification - AH Design Complete | 0 |  | 13-Oct-20 A | 0 | 0 | 100%
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | 52 | 13-Oct-20 A | 29-Dec-20 A | 72842 | 72842 | 100%
S150100 | Procure TPC Optics with Mirrors - Contract Award(s) | 0 | 13-Oct-20 A |  | 0 | 0 | 100%
S149000 | Procure TPC Laser(s) - Provide Requirements to Procurement | 5 | 13-Oct-20 A | 19-Oct-20 A | 7281 | 7028 | 100%
S149700 | Procure TPC Optics with mirrors - Provide Requirements to Procurement | 5 | 13-Oct-20 A | 19-Oct-20 A | 3640 | 3514 | 100%
S149800 | Procure TPC Optics with Mirrors - Prepare & Send Solicitation | 5 | 13-Oct-20 A | 19-Oct-20 A | 0 | 0 | 100%
S149900 | Procure TPC Optics with Mirrors - Vendor Responses | 5 | 13-Oct-20 A | 19-Oct-20 A | 0 | 0 | 100%
S150000 | Procure TPC Optics with Mirrors - Vendor Selection | 5 | 13-Oct-20 A | 19-Oct-20 A | 0 | 0 | 100%
S169300 | Pack and ship EMCAL blocks for Prepro sector 12 to BNL Purchased Services | 5 | 13-Oct-20 A | 19-Oct-20 A | 892 | 866 | 100%
S169400 | Pack and ship EMCAL blocks for Prepro sector 12 to BNL M&S | 5 | 13-Oct-20 A | 19-Oct-20 A | 1254 | 1229 | 100%
S173000 | Fabricate final blocks sector 13 | 6 | 13-Oct-20 A | 20-Oct-20 A | 5163 | 5012 | 100%
S150200 | Procure TPC Optics with Mirrors - Contract/PO - Leadtime | 13 | 13-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S150300 | Procure TPC Optics with Mirrors - Delivery Acceptance | 209 | 13-Oct-20 A | 2021-08-12 | 68248 | 66910 | 50%
S229100 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Contract Award(s) | 0 | 14-Oct-20 A |  | 0 | 0 | 100%
S228900 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Vendor Responses | 4 | 14-Oct-20 A | 20-Oct-20 A | 0 | 0 | 100%
S229000 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Vendor Selection | 4 | 14-Oct-20 A | 20-Oct-20 A | 0 | 0 | 100%
S259200 | Procure DAQ Production Buffer Boxes - Vendor Selection | 12 | 14-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S311600 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - Physics Resource(s) | 12 | 14-Oct-20 A | 30-Oct-20 A | 9404 | 9130 | 100%
S311700 | Carriage Cradle - Fabricate Fixtures & Tooling | 12 | 14-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S311610 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - CA-D Resource(s) | 12 | 14-Oct-20 A | 30-Oct-20 A | 47686 | 46297 | 100%
S242900 | Fabricate HCal Interface Boards Production - Delivery Acceptance | 22 | 14-Oct-20 A | 16-Nov-20 A | 33996 | 33330 | 100%
S337200 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fab incl) - M&S | 68 | 14-Oct-20 A | 26-Jan-21 A | 58034 | 57892 | 100%
S337900 | Evaluate & Process Magnet Cryo, Electrical & Control Structural Support in IR Components Bids | 72 | 14-Oct-20 A | 29-Jan-21 A | 8183 | 7945 | 100%
S338000 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fab incl) - Labor | 72 | 14-Oct-20 A | 29-Jan-21 A | 21822 | 21734 | 100%
S257500 | Procure DAQ Production SEBs - Contract/PO - Leadtime | 11 | 15-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S243000 | Test HCal Interface Boards: Production | 21 | 15-Oct-20 A | 16-Nov-20 A | 15259 | 14814 | 100%
S187100 | Procure EMCAL Mechanical Parts for Final Modules Sectors 13-64 - Delivery Acceptance | 29 | 15-Oct-20 A | 30-Nov-20 A | 61145 | 61145 | 100%
S242100 | Test Hcal Backplane Boards: Production | 31 | 15-Oct-20 A | 01-Dec-20 A | 66341 | 66341 | 100%
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | 71 | 15-Oct-20 A | 29-Jan-21 A | 15002 | 14565 | 100%
S154200 | TPC Cooling System Safety Review | 1 | 15-Oct-20 A | 15-Oct-20 A | 1316 | 1277 | 100%
S316000 | Steel Track Modifications - Finish Track Work M&S | 219 | 15-Oct-20 A | 2021-08-30 | 23214 | 23214 | 95%
S316005 | Steel Track Modifications - Finish Track Work Labor | 219 | 15-Oct-20 A | 2021-08-30 | 8280 | 8039 | 95%
S343824 | Start Track Modification - IR Procur. Readiness Review | 5 | 16-Oct-20 A | 22-Oct-20 A | 5179 | 5028 | 100%
S1005920 | AET to procure long lead items | 5 | 16-Oct-20 A | 22-Oct-20 A | 0 | 0 | 100%
S312600 | CC Drive & Alignment System - Prepare & Send Solicitation | 8 | 16-Oct-20 A | 28-Oct-20 A | 0 | 0 | 100%
S141200 | Procure TPC FEE Production Components - Vendor Selection | 8 | 20-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S142100 | Procure TPC FEE LV Power Supplies - Vendor Responses | 8 | 20-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S142200 | Procure TPC FEE LV Power Supplies - Vendor Selection | 8 | 20-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S148000 | Procure TPC EDBC Computers & Peripherals - Vendor Responses | 86 | 20-Oct-20 A | 26-Feb-21 A | 0 | 0 | 100%
S148100 | Procure TPC EDBC Computers & Peripherals - Vendor Selection | 131 | 20-Oct-20 A | 30-Apr-21 A | 0 | 0 | 100%
S149400 | Procure TPC Lasers - Contract Award(s) | 0 | 20-Oct-20 A |  | 0 | 0 | 100%
S149100 | Procure TPC Lasers - Prepare & Send Solicitation | 8 | 20-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S149200 | Procure TPC Lasers - Vendor Responses | 8 | 20-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S149300 | Procure TPC Lasers - Vendor Selection | 8 | 20-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S149500 | Procure TPC Lasers - Contract/PO - Leadtime | 8 | 20-Oct-20 A | 30-Oct-20 A | 0 | 0 | 100%
S147330 | Procure TPC DAM Felix 2.0 Optical Components - Vendor Responses | 6 | 21-Oct-20 A | 29-Oct-20 A | 0 | 0 | 100%
S147340 | Procure TPC DAM Felix 2.0 Optical Components - Vendor Selection | 6 | 21-Oct-20 A | 29-Oct-20 A | 0 | 0 | 100%
S173300 | Fabricate final blocks sector 16 | 18 | 21-Oct-20 A | 16-Nov-20 A | 5163 | 5012 | 100%
S173100 | Fabricate final blocks sector 14 | 6 | 21-Oct-20 A | 28-Oct-20 A | 5163 | 5012 | 100%
S133800 | Test TPC R3a Modules | 182 | 21-Oct-20 A | 2021-07-14 | 0 | 0 | 85%
S134000 | Test TPC R3b Modules | 182 | 21-Oct-20 A | 2021-07-14 | 0 | 0 | 85%
S302800 | Magnet: Fabricate DC flags | 4 | 22-Oct-20 A | 28-Oct-20 A | 5153 | 5003 | 100%
S173200 | Fabricate final blocks sector 15 | 6 | 22-Oct-20 A | 30-Oct-20 A | 5163 | 5012 | 100%
S178300 | Pack and ship final blocks for sectors 13-16 to BNL - Purchased Services | 22 | 22-Oct-20 A | 23-Nov-20 A | 1223 | 1187 | 100%
S178310 | Pack and ship final blocks for sectors 13-16 to BNL - M&S | 22 | 22-Oct-20 A | 23-Nov-20 A | 3761 | 3687 | 100%
S258400 | Procure DAQ Production ATPs - Delivery Acceptance | 25 | 22-Oct-20 A | 30-Nov-20 A | 113803 | 113803 | 100%
S329420 | Conceptual Design for Cable Routing from Detector to Rack (MBD) | 170 | 23-Oct-20 A | 30-Jun-21 A | 11386 | 11254 | 100%
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | 180 | 23-Oct-20 A | 2021-07-14 | 18052 | 18052 | 40%
S329440 | Conceptual Design for Routing Rack Cooling System | 192 | 23-Oct-20 A | 2021-07-30 | 25776 | 25776 | 30%
S154300 | Procurement Readiness Review - TPC Cooling System | 1 | 23-Oct-20 A | 23-Oct-20 A | 1316 | 1277 | 100%
S312800 | CC Drive & Alignment System - Vendor Selection - Physics Resource(s) | 3 | 23-Oct-20 A | 28-Oct-20 A | 6347 | 6163 | 100%
S312700 | CC Drive & Alignment System - Vendor Responses - Physics Resource(s) | 3 | 23-Oct-20 A | 28-Oct-20 A | 2116 | 2054 | 100%
S312810 | CC Drive & Alignment System - Vendor Selection - CA-D Resource(s) | 3 | 23-Oct-20 A | 28-Oct-20 A | 6247 | 6065 | 100%
S312710 | CC Drive & Alignment System - Vendor Responses - CA-D Resource(s) | 3 | 23-Oct-20 A | 28-Oct-20 A | 6247 | 6065 | 100%
S343826 | Start Track Modification - IR Provide Requirements to Procurements | 5 | 23-Oct-20 A | 29-Oct-20 A | 2085 | 2024 | 100%
S348300 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resou | 4 | 26-Oct-20 A | 29-Oct-20 A | 2154 | 2091 | 100%
S348400 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design&Safety Reviews-PO | 4 | 26-Oct-20 A | 29-Oct-20 A | 2154 | 2116 | 100%
S348310 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource | 4 | 26-Oct-20 A | 29-Oct-20 A | 2896 | 2812 | 100%
S348410 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design&Safety Reviews-AD | 4 | 26-Oct-20 A | 29-Oct-20 A | 1213 | 1192 | 100%
S230100 | Fabricate EMCAL Interface Board Sectors 13-64 - Delivery Acceptance | 44 | 26-Oct-20 A | 31-Dec-20 A | 217849 | 217849 | 100%
S234200 | EMCal Crates for Controllers - M&S | 147 | 26-Oct-20 A | 28-May-21 A | 5948 | 5948 | 100%
S141600 | Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Contract Award(s) | 0 | 28-Oct-20 A |  | 0 | 0 | 100%
S259300 | Procure DAQ Production Buffer Boxes - Contract Award(s) | 0 | 28-Oct-20 A |  | 0 | 0 | 100%
S317033 | EMCal Supports Released for Production (Milestone) | 0 |  | 28-Oct-20 A | 0 | 0 | 100%
S257600 | Procure DAQ Production SEBs - Delivery Acceptance | 20 | 28-Oct-20 A | 30-Nov-20 A | 47634 | 47634 | 100%
S259400 | Procure DAQ Production Buffer Boxes - Contract/PO - Leadtime | 20 | 28-Oct-20 A | 30-Nov-20 A | 0 | 0 | 100%
S348500 | Design/Safety Reviews Complete, Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Ready for service | 0 |  | 29-Oct-20 A | 0 | 0 | 100%
S337700 | Design/Safety Reviews Complete, Magnet Cryo, Electrical & Control Structural Support in IR Components Released for Produ | 0 |  | 30-Oct-20 A | 0 | 0 | 100%
S324500 | End Caps/ Pole Tips - Design & Safety Reviews Complete Released for Production | 0 |  | 30-Oct-20 A | 0 | 0 | 100%
S326100 | CC Bridge, Mid Platforms & Access - Design & Safety Reviews Complete Released for Production | 0 |  | 30-Oct-20 A | 0 | 0 | 100%
S141700 | Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Leadtime | 18 | 30-Oct-20 A | 30-Nov-20 A | 0 | 0 | 100%
S308615 | Develop readout electronics | 210 | 30-Oct-20 A | 2021-09-01 | 13651 | 13651 | 90%
S308623 | Develop mapping plan with Vendor | 269 | 30-Oct-20 A | 2021-11-30 | 21208 | 21208 | 50%
S252100 | Procure Production Digitizer (Parts) Contract Award(s) | 0 | 02-Nov-20 A |  | 0 | 0 | 100%
S252200 | Procure Production Digitizer (Boards) Contract Award(s) | 0 | 02-Nov-20 A |  | 0 | 0 | 100%
S252300 | Procure Production Digitizer (Assembly & Tests) - Contract Award(s) | 0 | 02-Nov-20 A |  | 0 | 0 | 100%
S141800 | Procure TPC FEE Production Components, Phase 2 (All except Optical and SAMPA) - Delivery Acceptance | 186 | 02-Nov-20 A | 2021-07-30 | 309548 | 309548 | 85%
S288900 | Procure LN2 supply transfer line system, Phase 1 (Preliminary Design Review) - Contract Award | 0 | 02-Nov-20 A |  | 0 | 0 | 100%
S289000 | Procure LN2 supply transfer line system, Phase 2 (Long lead items) - Contract Award | 0 | 02-Nov-20 A |  | 0 | 0 | 100%
S289100 | Procure LN2 supply transfer line system, Phase 3 (Final Design Review) - Contract Award | 0 | 02-Nov-20 A |  | 0 | 0 | 100%
S289200 | Procure LN2 supply transfer line system, Phase 4 (Raw Material) - Contract Award | 0 | 02-Nov-20 A |  | 0 | 0 | 100%
S289300 | Procure LN2 supply transfer line system - Contract Award - Phase 5 - Shipping | 0 | 02-Nov-20 A |  | 0 | 0 | 100%
S1005760 | Delivery Interconnect (S-Line, H-Line, U-Line), vacuum break, Field Joint Tee and Sleeve | 5 | 02-Nov-20 A | 06-Nov-20 A | 104800 | 104800 | 100%
S343828 | Start Track Modification - IR Prepare and Send Solicitations | 10 | 02-Nov-20 A | 16-Nov-20 A | 1042 | 1012 | 100%
S171020 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 20 | 17 | 02-Nov-20 A | 27-Nov-20 A | 40858 | 40858 | 100%
S129500 | Build TPC R2 Modules | 180 | 02-Nov-20 A | 2021-07-22 | 0 | 0 | 85%
S313000 | CC Drive & Alignment System - BNL Oversight - Physics Resource(s) | 110 | 03-Nov-20 A | 15-Apr-21 A | 5877 | 5820 | 100%
S313100 | CC Drive & Alignment System - Vendor Leadtime | 110 | 03-Nov-20 A | 15-Apr-21 A | 0 | 0 | 100%
S313010 | CC Drive & Alignment System - BNL Oversight - CA-D Resource(s) | 110 | 03-Nov-20 A | 15-Apr-21 A | 7712 | 7638 | 100%
S266700 | GL1 Prototype: evaluate performance, Final Design and Production Readiness Review | 206 | 03-Nov-20 A | 2021-08-30 | 24606 | 23889 | 60%
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | 37 | 04-Nov-20 A | 31-Dec-20 A | 69731 | 68106 | 100%
S308613 | Purchase probes for Magnetic Field Measurements | 37 | 04-Nov-20 A | 31-Dec-20 A | 8125 | 8125 | 100%
S257700 | Production SEBs - Setup Machines | 12 | 09-Nov-20 A | 30-Nov-20 A | 7091 | 7091 | 100%
S329410 | Conceptual Design for Cable Routing from Detector to Rack (MVTX) | 159 | 09-Nov-20 A | 30-Jun-21 A | 10446 | 10142 | 100%
S258500 | Production ATPs - Setup Machines | 11 | 10-Nov-20 A | 30-Nov-20 A | 7091 | 7091 | 100%
S317081 | Review Design and Safety Large Support Rings Supports | 10 | 10-Nov-20 A | 24-Nov-20 A | 6255 | 5775 | 100%
S178400 | Pack and ship final blocks for sectors 17-24 to BNL - Purchased Services | 90 | 16-Nov-20 A | 30-Mar-21 A | 2561 | 2502 | 100%
S178410 | Pack and ship final blocks for sectors 17-24 to BNL - M&S | 90 | 16-Nov-20 A | 30-Mar-21 A | 7521 | 7403 | 100%
S252400 | Procure Production Digitizer - Contract/PO - Leadtime for Parts | 134 | 16-Nov-20 A | 31-May-21 A | 0 | 0 | 100%
S252500 | Procure Production Digitizer - Contract/PO - Leadtime for Boards | 178 | 16-Nov-20 A | 2021-08-02 | 0 | 0 | 50%
S260600 | DAQ Production: DAQ Software development | 259 | 16-Nov-20 A | 2021-11-30 | 290832 | 282058 | 90%
S328000 | Review Line Electric Distribution Design/Safety - CA-D Resource(s) | 7 | 17-Nov-20 A | 27-Nov-20 A | 3640 | 3534 | 100%
S328100 | Address Action Items from Line Electric Distribution Design & Safety Reviews | 7 | 17-Nov-20 A | 27-Nov-20 A | 12010 | 11905 | 100%
S1002119 | Review Line Electric Distribution Design/Safety - Physics Resource(s) | 7 | 17-Nov-20 A | 27-Nov-20 A | 3034 | 2945 | 100%
S154400 | Procure TPC Cooling System equipment (pumps, heat exchanger, PH control, manifolds, tanks…) - Provide Requirements to Pr | 92 | 17-Nov-20 A | 02-Apr-21 A | 12923 | 12547 | 100%
S317040 | Create TPC Supports Detailed Design Drawings | 181 | 17-Nov-20 A | 2021-08-06 | 31273 | 29232 | 95%
S173400 | Fabricate final blocks sector 17 | 6 | 17-Nov-20 A | 24-Nov-20 A | 5163 | 5012 | 100%
S343830 | Start Track Modification - IR Vendor Responses | 49 | 17-Nov-20 A | 29-Jan-21 A | 1042 | 1012 | 100%
S129600 | Test TPC R2 Modules | 170 | 17-Nov-20 A | 2021-07-22 | 0 | 0 | 85%
S292900 | (Warm Piping tie in to WR header) Detailed drawing package with weld map | 170 | 17-Nov-20 A | 2021-07-22 | 5265 | 5112 | 82%
S241800 | Test HCal LED Boards: Production | 26 | 20-Nov-20 A | 31-Dec-20 A | 58523 | 58182 | 100%
S203600 | Outer HCAL Sector Transportation to Storage Area (Preproduction) | 39 | 23-Nov-20 A | 22-Jan-21 A | 7594 | 7373 | 100%
S229200 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Contract/PO - Leadtime | 63 | 23-Nov-20 A | 26-Feb-21 A | 0 | 0 | 100%
S302010 | Magnet: Design Cable Tray and Supports for Power and Signal Distribution Split | 63 | 23-Nov-20 A | 26-Feb-21 A | 9101 | 8836 | 100%
S302400 | Magnet: Delivery Power Supply, Magnet, Dump Resistor DC Cabling and Interconnects M&S | 108 | 23-Nov-20 A | 30-Apr-21 A | 24374 | 23896 | 100%
S308629 | Complete mechanical and electrical design for mapping | 216 | 23-Nov-20 A | 2021-10-01 | 12646 | 12627 | 35%
S259500 | Procure DAQ Production Buffer Boxes - Delivery Acceptance | 235 | 23-Nov-20 A | 2021-10-29 | 259459 | 259459 | 18%
S259600 | Production Buffer Boxes - Setup Machines | 240 | 23-Nov-20 A | 2021-11-05 | 7091 | 7091 | 16%
S187500 | Receive, unpack, log & inspect final blocks | 295 | 23-Nov-20 A | 2022-01-31 | 179682 | 178031 | 58%
S187800 | Install reflectors on final blocks Labor | 295 | 23-Nov-20 A | 2022-01-31 | 179723 | 178148 | 38%
S187900 | Install reflectors on final blocks M&S | 295 | 23-Nov-20 A | 2022-01-31 | 0 | 0 | 38%
S173500 | Fabricate final blocks sector 18 | 8 | 25-Nov-20 A | 08-Dec-20 A | 5163 | 5012 | 100%
S317082 | Address Action Items for Large Support Rings Supports | 44 | 25-Nov-20 A | 01-Feb-21 A | 2606 | 2530 | 100%
S312900 | CC Drive & Alignment System - Contract Award(s) | 0 | 30-Nov-20 A |  | 0 | 0 | 100%
S113050 | TPC Module technical Support | 104 | 01-Dec-20 A | 30-Apr-21 A | 92855 | 92855 | 100%
S172870 | EMCal Block Production QA | 208 | 01-Dec-20 A | 2021-09-27 | 533915 | 533915 | 70%
S289400 | (LN2 supply transfer line system) Kick off meeting | 1 | 01-Dec-20 A | 01-Dec-20 A | 1590 | 1544 | 100%
S317021 | Review Design and Safety Magnet Supports | 2 | 01-Dec-20 A | 02-Dec-20 A | 1042 | 1042 | 100%
S251400 | Production Readiness & Safety Review: Calorimeter Digitizers | 5 | 01-Dec-20 A | 07-Dec-20 A | 24269 | 23562 | 100%
S1005960 | AET submits IDR to BNL for approval | 10 | 01-Dec-20 A | 14-Dec-20 A | 0 | 0 | 100%
S199600 | Manufacture Inner HCAL Support Rings - Vendor Responses | 20 | 01-Dec-20 A | 29-Dec-20 A | 0 | 0 | 100%
S230200 | Test EMCal Interface Boards: Production Sectors 13-64 | 20 | 01-Dec-20 A | 30-Dec-20 A | 6313 | 6313 | 100%
S230205 | Test EMCal Interface Boards: Production Sectors 13-64 - Contributed Labor | 20 | 01-Dec-20 A | 30-Dec-20 A | 31221 | 31221 | 100%
S299400 | (Cryo Controls Hardware Procurement) Turbo pump and Controller | 40 | 01-Dec-20 A | 28-Jan-21 A | 29017 | 28448 | 100%
S297000 | (Cryo Controls Hardware procurement) Flowmeters Labor | 41 | 01-Dec-20 A | 29-Jan-21 A | 1564 | 1518 | 100%
S297100 | (Cryo Controls Hardware procurement) Flowmeters M&S | 41 | 01-Dec-20 A | 29-Jan-21 A | 5339 | 5234 | 100%
S227605 | Fabricate SiPM Daughter Boards Sectors 13-64 - Delivery Acceptance | 105 | 01-Dec-20 A | 30-Apr-21 A | 23206 | 23206 | 100%
S228100 | Test SiPM Daughter Boards Production Sectors 13-64 | 160 | 01-Dec-20 A | 2021-07-20 | 2893 | 2888 | 60%
S228110 | Test SiPM Daughter Boards Production Sectors 13-64 - Contributed Labor | 160 | 01-Dec-20 A | 2021-07-20 | 65413 | 65282 | 60%
S147300 | Procure TPC DAM Felix 2.0 Boards - Delivery Acceptance | 166 | 02-Dec-20 A | 2021-07-29 | 151309 | 151309 | 80%
S256900 | DAQ Production: Selecting the right technology and brands | 20 | 02-Dec-20 A | 31-Dec-20 A | 31579 | 30660 | 100%
S289600 | (LN2 supply transfer line system) Preliminary Design Review Labor | 37 | 02-Dec-20 A | 27-Jan-21 A | 1590 | 1544 | 100%
S289700 | Procure LN2 supply transfer line system, Phase 1 (Preliminary Design Review) - Leadtime | 37 | 02-Dec-20 A | 27-Jan-21 A | 0 | 0 | 100%
S289500 | Engineering Support for Procure LN2 supply transfer line system | 178 | 02-Dec-20 A | 2021-08-16 | 7156 | 6948 | 88%
S317022 | Address Action Items for Magnet Supports | 58 | 03-Dec-20 A | 26-Feb-21 A | 1042 | 1042 | 100%
S256800 | DAQ Production: Crate installation | 259 | 07-Dec-20 A | 2021-12-17 | 75794 | 74832 | 30%
S251500 | Complete: Procurement Readiness Review, Safety Review - Calorimeter Digitizer Final Order | 0 |  | 07-Dec-20 A | 0 | 0 | 100%
S233300 | Assemble Power Cables | 14 | 08-Dec-20 A | 29-Dec-20 A | 11723 | 11723 | 100%
S331730 | Design Coolin Manifolds for INTT | 152 | 08-Dec-20 A | 2021-07-15 | 4035 | 3917 | 75%
S331770 | Conceptual Design for Cooling Tube Routing from Detector to EMCal manifold | 152 | 08-Dec-20 A | 2021-07-15 | 4035 | 3988 | 20%
S331780 | Conceptual Design for Cooling Tube Routing from Detector to TPC manifold | 152 | 08-Dec-20 A | 2021-07-15 | 4035 | 4035 | 60%
S251600 | Review Calorimeter Electronics Readiness & Safety Review Report | 10 | 08-Dec-20 A | 21-Dec-20 A | 20629 | 20028 | 100%
S173600 | Fabricate final blocks sector 19 | 6 | 09-Dec-20 A | 16-Dec-20 A | 5163 | 5012 | 100%
S331790 | Conceptual Design for Cooling Tube Routing from Detector to INTT, MVTX manifold | 148 | 14-Dec-20 A | 2021-07-15 | 8069 | 8069 | 5%
S341800 | Analyze IR/AH Safety Subsystems Requirements - Physics Resource(s) | 159 | 14-Dec-20 A | 2021-07-30 | 532 | 532 | 25%
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 159 | 14-Dec-20 A | 2021-07-30 | 21111 | 21111 | 25%
S244400 | HCal Electronics Prod Pwr & Sig Cables & LV/Bias Supplies & Controller (External) - Delivery Acceptance | 179 | 14-Dec-20 A | 2021-08-27 | 101939 | 101939 | 50%
S324800 | End Caps/ Pole Tips - Provide Requirement to Procurement | 5 | 15-Dec-20 A | 22-Dec-20 A | 2803 | 2721 | 100%
S1003639 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics | 28 | 15-Dec-20 A | 27-Jan-21 A | 3094 | 3094 | 100%
S226300 | Procure EMCal External Bias Power System: Sectors 1-12, Phase 1 - Delivery Acceptance | 47 | 15-Dec-20 A | 24-Feb-21 A | 8837 | 8663 | 100%
S226400 | Procure EMCal External Bias Power System: Sectors 1-12, Phase 2 - Delivery Acceptance | 47 | 15-Dec-20 A | 24-Feb-21 A | 35347 | 34654 | 100%
S209900 | Populate Outer HCAL sectors with electronics | 71 | 15-Dec-20 A | 30-Mar-21 A | 15509 | 15509 | 100%
S210000 | Outer HCAL Sector LED testing and Light Tighting | 71 | 15-Dec-20 A | 30-Mar-21 A | 15509 | 15509 | 100%
S210200 | Outer HCAL Cosmics testing and initial calibration | 71 | 15-Dec-20 A | 30-Mar-21 A | 15509 | 15509 | 100%
S210100 | Procure Outer HCAL LED Testing & Light Tighting M&S | 71 | 15-Dec-20 A | 30-Mar-21 A | 22285 | 22285 | 100%
S209910 | Populate Outer HCAL sectors with electronics - Contributed Labor | 71 | 15-Dec-20 A | 30-Mar-21 A | 199251 | 199251 | 100%
S210010 | Outer HCAL Sector LED testing and Light Tighting - Contributed Labor | 71 | 15-Dec-20 A | 30-Mar-21 A | 199251 | 199251 | 100%
S210210 | Outer HCAL Cosmics testing and initial calibration - Contributed Labor | 71 | 15-Dec-20 A | 30-Mar-21 A | 44326 | 44326 | 100%
S302700 | Magnet: Order Power Supply, Magnet, Dump Resistor DC Cabling and Interconnects Labor | 94 | 15-Dec-20 A | 30-Apr-21 A | 2427 | 2356 | 100%
S1006000 | BNL review for IDR approval | 10 | 15-Dec-20 A | 29-Dec-20 A | 26200 | 26200 | 100%
S173700 | Fabricate final blocks sector 20 | 16 | 17-Dec-20 A | 11-Jan-21 A | 5163 | 5012 | 100%
S332710 | Conceptual Design for Routing N2 Line from Gas House to N2/Air Manifolds | 146 | 18-Dec-20 A | 2021-07-19 | 3094 | 3094 | 80%
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | 146 | 18-Dec-20 A | 2021-07-19 | 3094 | 3094 | 30%
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | 146 | 18-Dec-20 A | 2021-07-19 | 3094 | 3094 | 30%
S198900 | Manufacture Inner HCAL Support Structure - Vendor Responses | 2 | 21-Dec-20 A | 23-Dec-20 A | 0 | 0 | 100%
S324700 | End Caps/ Pole Tips - Procurement Readiness Review - Physics Resource(s) | 2 | 21-Dec-20 A | 23-Dec-20 A | 5172 | 5021 | 100%
S324710 | End Caps/ Pole Tips - Procurement Readiness Review - CA-D Resource(s) | 2 | 21-Dec-20 A | 23-Dec-20 A | 8794 | 8538 | 100%
S317061 | Review Design and Safety MVTX Supports | 7 | 21-Dec-20 A | 31-Dec-20 A | 2085 | 2085 | 100%
S311355 | Carriage Cradle - Delivery Acceptance Two - M&S | 7 | 21-Dec-20 A | 31-Dec-20 A | 1278686 | 1229033 | 100%
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | 145 | 21-Dec-20 A | 2021-07-19 | 4195 | 5593 | 50%
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | 145 | 21-Dec-20 A | 2021-07-19 | 11518 | 11518 | 80%
S196000 | Procure EMCAL Cooling System for Final Sectors - Contract/PO - Leadtime | 44 | 22-Dec-20 A | 26-Feb-21 A | 0 | 0 | 100%
S329430 | Conceptual Design for Routing Fiber Optic Cables from Rack to Patch Panel | 131 | 22-Dec-20 A | 30-Jun-21 A | 12327 | 12327 | 100%
S329409 | Conceptual Design for Cable Routing from Detector to Rack (INTT) | 131 | 22-Dec-20 A | 30-Jun-21 A | 11386 | 11055 | 100%
S332730 | Conceptual Design for Gas Tube Routing from Det to Operating Gas Manifolds (TPC) | 144 | 22-Dec-20 A | 2021-07-19 | 3094 | 3094 | 50%
S187400 | Procure light guides for modules in Sectors 13-64 - Delivery Acceptance | 153 | 22-Dec-20 A | 2021-07-30 | 240129 | 240129 | 74%
S199000 | Manufacture Inner HCAL Support Structure - Vendor Selection | 1 | 24-Dec-20 A | 28-Dec-20 A | 16712 | 16225 | 100%
S199700 | Manufacture Inner HCAL Support Rings - Vendor Selection | 2 | 28-Dec-20 A | 30-Dec-20 A | 0 | 0 | 100%
S287110 | Completed - Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | 0 |  | 29-Dec-20 A | 0 | 0 | 100%
S199800 | Manufacture Inner HCAL Support Rings - Contract Award(s) | 0 | 30-Dec-20 A |  | 0 | 0 | 100%
S199100 | Manufacture Inner HCAL Support Structure - Contract Award(s) | 0 | 31-Dec-20 A |  | 0 | 0 | 100%
S293700 | (Warm Piping System Materials Procurement) Reliefs Labor | 83 | 31-Dec-20 A | 30-Apr-21 A | 23694 | 23004 | 100%
S293900 | (Warm Piping System Materials Procurement) Warm Valves | 83 | 31-Dec-20 A | 30-Apr-21 A | 7156 | 6948 | 100%
S293600 | (Warm Piping System Materials Procurement) Reliefs M&S | 83 | 31-Dec-20 A | 30-Apr-21 A | 9285 | 9103 | 100%
S293800 | (Warm Piping System Materials Procurement) Warm Valves M&S | 83 | 31-Dec-20 A | 30-Apr-21 A | 17410 | 17069 | 100%
S231800 | Procure Internal EMCal Signal/Test/Comm and LV/Bias: Production - Delivery Acceptance | 103 | 31-Dec-20 A | 28-May-21 A | 288193 | 288193 | 100%
S196910 | Technical support labor for EMCal assembly | 257 | 04-Jan-21 A | 2022-01-12 | 281618 | 281000 | 50%
S208500 | Completion of Outer HCAL Scintillating Tile Testing | 0 |  | 04-Jan-21 A | 0 | 0 | 100%
S324900 | End Caps/ Pole Tips - Prepare & Send Solicitation | 5 | 04-Jan-21 A | 08-Jan-21 A | 0 | 0 | 100%
S171021 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 21 | 10 | 04-Jan-21 A | 18-Jan-21 A | 40858 | 40858 | 100%
S1006040 | AET submits FDR report to BNL for approval | 16 | 04-Jan-21 A | 27-Jan-21 A | 104800 | 104800 | 100%
S297200 | (Cryo Controls Hardware procurement) Vacuum gages and cables Labor | 19 | 04-Jan-21 A | 29-Jan-21 A | 1564 | 1518 | 100%
S297300 | (Cryo Controls Hardware procurement) Vacuum gages and cables M&S | 19 | 04-Jan-21 A | 29-Jan-21 A | 6964 | 6828 | 100%
S125000 | Procure TPC R1 Module Parts (Padplanes) - Contract/PO - Leadtime | 60 | 04-Jan-21 A | 31-Mar-21 A | 0 | 0 | 100%
S199900 | Manufacture Inner HCAL Support Rings - Contract lead time | 76 | 04-Jan-21 A | 22-Apr-21 A | 0 | 0 | 100%
S342900 | Analyze Assembly Hall Modification Requirements | 99 | 04-Jan-21 A | 25-May-21 A | 25106 | 25106 | 100%
S339200 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) - Physics Resource(s) | 103 | 04-Jan-21 A | 31-May-21 A | 4232 | 7523 | 100%
S339210 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) - CA-D Resource(s) | 103 | 04-Jan-21 A | 31-May-21 A | 5461 | 19415 | 100%
S149650 | TPC Diffuse Lasers | 147 | 04-Jan-21 A | 2021-08-02 | 232137 | 232137 | 50%
S338300 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) - M&S | 102 | 05-Jan-21 A | 31-May-21 A | 58034 | 58034 | 100%
S316600 | Create Internal Detector Structural Support Detail Drawings - Physics Resource(s) | 5 | 11-Jan-21 A | 18-Jan-21 A | 5877 | 5706 | 100%
S316610 | Create Internal Detector Structural Support Detail Drawings - CA-D Resource(s) | 5 | 11-Jan-21 A | 18-Jan-21 A | 7281 | 7069 | 100%
S135900 | Procure TPC FEE Cooling System - Provide Requirements to Procurement | 10 | 11-Jan-21 A | 26-Jan-21 A | 3076 | 2986 | 100%
S136200 | Procure TPC FEE Cooling System - Vendor Selection | 10 | 11-Jan-21 A | 26-Jan-21 A | 0 | 0 | 100%
S136000 | Procure TPC FEE Cooling System - Prepare & Send Solicitation | 10 | 11-Jan-21 A | 26-Jan-21 A | 0 | 0 | 100%
S136100 | Procure TPC FEE Cooling System - Vendor Responses | 10 | 11-Jan-21 A | 26-Jan-21 A | 0 | 0 | 100%
S343834 | Start Track Modification - IR Contract Award | 14 | 11-Jan-21 A | 29-Jan-21 A | 0 | 0 | 100%
S343832 | Start Track Modification - IR Vendor Selection | 14 | 11-Jan-21 A | 29-Jan-21 A | 1042 | 1012 | 100%
S343836 | Start Track Modification - IR Develop and Submit Safety Plan | 24 | 11-Jan-21 A | 16-Feb-21 A | 3127 | 3036 | 100%
S210300 | Outer HCAL Sector Transportation to Temp Storage | 77 | 11-Jan-21 A | 30-Apr-21 A | 39020 | 39020 | 100%
S125500 | Build TPC R1 Modules | 166 | 11-Jan-21 A | 2021-09-03 | 63173 | 63130 | 85%
S125505 | Build TPC R1 Modules - Contributed Labor | 166 | 11-Jan-21 A | 2021-09-03 | 0 | 0 | 85%
S125600 | Test TPC R1 Modules | 176 | 11-Jan-21 A | 2021-09-20 | 63173 | 63173 | 85%
S125605 | Test TPC R1 Modules - Contributed Labor | 176 | 11-Jan-21 A | 2021-09-20 | 0 | 0 | 85%
S325000 | End Caps/ Pole Tips - Vendor Responses - Physics Resource(s) | 12 | 11-Jan-21 A | 28-Jan-21 A | 1175 | 1141 | 100%
S325010 | End Caps/ Pole Tips - Vendor Responses - CA-D Resource(s) | 12 | 11-Jan-21 A | 28-Jan-21 A | 6405 | 6218 | 100%
S1006240 | AET submits PDR report to BNL for approval of IP8 Cold Box Assembly | 130 | 11-Jan-21 A | 2021-07-15 | 0 | 0 | 90%
S345000 | Review Integration and Installation Plan Design/Safety | 10 | 12-Jan-21 A | 27-Jan-21 A | 8930 | 8670 | 100%
S345100 | Review Cable Management Plan | 10 | 12-Jan-21 A | 27-Jan-21 A | 5726 | 5559 | 100%
S345200 | Review Survey Plan | 10 | 12-Jan-21 A | 27-Jan-21 A | 3868 | 3755 | 100%
S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey P | 10 | 12-Jan-21 A | 27-Jan-21 A | 3868 | 3755 | 100%
S344900 | Create Installation Plan | 10 | 12-Jan-21 A | 27-Jan-21 A | 30041 | 30041 | 100%
S307000 | Magnet: Connect AC Power to Quench Detector | 18 | 12-Jan-21 A | 05-Feb-21 A | 3092 | 3002 | 100%
S301800 | Magnet: 1008 IR Design Quench Detector AC Power Hook-up | 31 | 12-Jan-21 A | 26-Feb-21 A | 2427 | 2356 | 100%
S301710 | Magnet: 1008 IR Design Power Supply AC Power Hook-up Split | 31 | 12-Jan-21 A | 26-Feb-21 A | 2730 | 2651 | 100%
S301910 | Magnet: 1008 IR Design Power Supply, Magnet, Dump Resistor DC Cabling Split | 31 | 12-Jan-21 A | 26-Feb-21 A | 1820 | 1767 | 100%
S152300 | Procure TPC Gas System Equipment - Contract/PO - Delivery Acceptance | 139 | 12-Jan-21 A | 2021-07-29 | 38343 | 37591 | 70%
S173800 | Fabricate final blocks sector 21 | 6 | 12-Jan-21 A | 20-Jan-21 A | 5163 | 5012 | 100%
S196200 | Build mechanical enclosures for final sectors | 128 | 12-Jan-21 A | 2021-07-14 | 84633 | 84633 | 33%
S196300 | Build mechanical fixtures for final sectors | 128 | 12-Jan-21 A | 2021-07-14 | 84633 | 84017 | 45%
S196400 | Build cooling system for final sectors | 128 | 12-Jan-21 A | 2021-07-14 | 27303 | 27303 | 33%
S332705 | Conceptual Design for Routing Operating gas Line from Gas House to TPC Manifold | 4 | 13-Jan-21 A | 20-Jan-21 A | 3094 | 3094 | 100%
S289800 | Procure LN2 supply transfer line system, Phase 1 (Preliminary Design Review) - Delivery Acceptance | 9 | 13-Jan-21 A | 27-Jan-21 A | 25535 | 25535 | 100%
S150400 | Procure TPC mirror bundles with supports Labor | 161 | 13-Jan-21 A | 2021-08-31 | 3640 | 3533 | 50%
S150500 | Procure TPC mirror bundles with supports M&S | 161 | 13-Jan-21 A | 2021-08-31 | 17410 | 17060 | 50%
S289900 | (LN2 supply transfer line system) Detail dwg package | 72 | 18-Jan-21 A | 30-Apr-21 A | 9542 | 9542 | 100%
S196100 | Procure EMCAL Cooling System for Final Sectors - Delivery Acceptance | 124 | 18-Jan-21 A | 2021-07-14 | 82284 | 82284 | 42%
S171022 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 22 | 7 | 19-Jan-21 A | 28-Jan-21 A | 40858 | 40858 | 100%
S316700 | Review Internal Detector Structural Support Safety - Physics Resource(s) | 7 | 19-Jan-21 A | 28-Jan-21 A | 940 | 913 | 100%
S316800 | Review Internal Detector Structural Support Design - Physics Resource(s) | 7 | 19-Jan-21 A | 28-Jan-21 A | 1411 | 1369 | 100%
S316710 | Review Internal Detector Structural Support Safety - CA-D Resource(s) | 7 | 19-Jan-21 A | 28-Jan-21 A | 1213 | 1178 | 100%
S316810 | Review Internal Detector Structural Support Design - CA-D Resource(s) | 7 | 19-Jan-21 A | 28-Jan-21 A | 2427 | 2356 | 100%
S338100 | Perform Magnet Cryo, Electrical & Control Structural Support in IR Components Acceptance | 8 | 19-Jan-21 A | 29-Jan-21 A | 2592 | 2592 | 100%
S1006080 | AET begins material procurement | 27 | 19-Jan-21 A | 26-Feb-21 A | 0 | 0 | 100%
S1006120 | Fabricate the 1008B Cold Box | 92 | 19-Jan-21 A | 28-May-21 A | 0 | 0 | 100%
S142300 | Procure TPC FEE LV Power Supplies - Contract Award(s) | 0 | 20-Jan-21 A |  | 0 | 0 | 100%
S142400 | Procure TPC FEE LV Power Supplies - Contract/PO - Leadtime | 48 | 21-Jan-21 A | 31-Mar-21 A | 0 | 0 | 100%
S173900 | Fabricate final blocks sector 22 | 13 | 21-Jan-21 A | 08-Feb-21 A | 5163 | 5012 | 100%
S187600 | Install light guides on final blocks Labor | 257 | 21-Jan-21 A | 2022-01-31 | 180018 | 178070 | 35%
S187700 | Install light guides on final blocks M&S | 257 | 21-Jan-21 A | 2022-01-31 | 1926 | 1912 | 35%
S188000 | Install SiPMs daughterboards on final blocks Labor | 259 | 22-Jan-21 A | 2022-02-03 | 180039 | 178304 | 35%
S188200 | Glue final blocks together into modules | 259 | 22-Jan-21 A | 2022-02-03 | 180039 | 178382 | 33%
S188100 | Install SiPMs daughterboards on final blocks M&S | 259 | 22-Jan-21 A | 2022-02-03 | 350 | 348 | 35%
S302300 | Magnet: Delivery Power Supply and Quench Detector AC Power Cables and Interconnects M&S | 23 | 25-Jan-21 A | 26-Feb-21 A | 4643 | 4552 | 100%
S142500 | Procure TPC FEE LV Power Supplies - Delivery Acceptance | 132 | 25-Jan-21 A | 2021-07-30 | 220595 | 220595 | 80.2%
S196500 | Install modules in final sectors | 257 | 26-Jan-21 A | 2022-02-03 | 234726 | 232867 | 33%
S289810 | Completed - Procure LN2 supply transfer line system, Phase 1 (Preliminary Design Review) - Delivery Acceptance | 0 |  | 27-Jan-21 A | 0 | 0 | 100%
S345400 | Design/Safety Reviews Complete, Ready to Begin Installation | 0 |  | 27-Jan-21 A | 0 | 0 | 100%
S124900 | Procure TPC R1 Module Parts (Padplanes) - Contract Award(s) | 0 | 29-Jan-21 A |  | 0 | 0 | 100%
S240800 | 25% HCal Preamp Boards testing complete: Production | 0 |  | 29-Jan-21 A | 0 | 0 | 100%
S338200 | Magnet cryo, electrical and control structural support components Ready for Installation | 0 |  | 29-Jan-21 A | 0 | 0 | 100%
S326200 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - Physics Resource(s) | 11 | 29-Jan-21 A | 12-Feb-21 A | 12225 | 12225 | 100%
S326210 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - CA-D Resource(s) | 11 | 29-Jan-21 A | 12-Feb-21 A | 18274 | 18274 | 100%
S316900 | Address Action Items from Internal Detector Structural Support Design & Safety Reviews - Physics Resource(s) | 19 | 29-Jan-21 A | 26-Feb-21 A | 2351 | 2282 | 100%
S316910 | Address Action Items from Internal Detector Structural Support Design & Safety Reviews - CA-D Resource(s) | 19 | 29-Jan-21 A | 26-Feb-21 A | 6067 | 5891 | 100%
S325100 | End Caps/ Pole Tips - Vendor Selection - Physics Resource(s) | 20 | 29-Jan-21 A | 26-Feb-21 A | 1175 | 1141 | 100%
S325110 | End Caps/ Pole Tips - Vendor Selection - CA-D Resource(s) | 20 | 29-Jan-21 A | 26-Feb-21 A | 6405 | 6218 | 100%
S294300 | Procure Warm Piping and fittings - Contract award | 0 | 01-Feb-21 A |  | 0 | 0 | 100%
S294000 | Procure Warm Piping and fittings - Provide Requirements to Procurement | 17 | 01-Feb-21 A | 25-Feb-21 A | 3640 | 3534 | 100%
S294100 | Procure Warm Piping and fittings - Prepare and Send Solicitation | 17 | 01-Feb-21 A | 25-Feb-21 A | 0 | 0 | 100%
S294200 | Procure Warm Piping and fittings - Vendor Response and Selection | 17 | 01-Feb-21 A | 25-Feb-21 A | 0 | 0 | 100%
S294400 | Procure Warm Piping and fittings - Leadtime | 17 | 01-Feb-21 A | 25-Feb-21 A | 0 | 0 | 100%
S274310 | RHIC FY21 Run | 111 | 01-Feb-21 A | 2021-07-08 | 0 | 0 | 60%
S143270 | TPC FEE Electrical Engineering Support 1 | 229 | 01-Feb-21 A | 2021-12-29 | 120026 | 119731 | 46.52%
S143271 | TPC FEE Electrical Engineering Support 2 | 229 | 01-Feb-21 A | 2021-12-29 | 0 | 0 | 46.52%
S147380 | TPC DAM Electrical Engineering Support | 230 | 01-Feb-21 A | 2021-12-30 | 48446 | 48327 | 45%
S121605 | TPC Assembly Mechanical Engineering Support | 243 | 01-Feb-21 A | 2022-01-20 | 156597 | 156234 | 43.62%
S296400 | (Cryo Controls Hardware procurement) Lakeshore Temperature sensors Labor | 16 | 01-Feb-21 A | 24-Feb-21 A | 1564 | 1518 | 100%
S296500 | (Cryo Controls Hardware procurement) Lakeshore Temperature sensors M&S | 16 | 01-Feb-21 A | 24-Feb-21 A | 25535 | 25034 | 100%
S299300 | (Cryo Controls Hardware Procurement) LN2 Conduit/couplings | 17 | 01-Feb-21 A | 24-Feb-21 A | 3946 | 3869 | 100%
S171023 | Procure EMCAL Fibers for Final Blocks - Delivery Acceptance 23 | 17 | 01-Feb-21 A | 25-Feb-21 A | 38234 | 38234 | 100%
S343860 | Start Track Modification - AH Fabricate Track Plates Labor - Internal | 39 | 01-Feb-21 A | 29-Mar-21 A | 4297 | 7417 | 100%
S290300 | (LN2 supply transfer line system) Final Design Review Labor | 40 | 01-Feb-21 A | 30-Mar-21 A | 1590 | 1590 | 100%
S290400 | Procure LN2 supply transfer line system, Phase 3 (Final Design Review) - Leadtime | 40 | 01-Feb-21 A | 30-Mar-21 A | 0 | 0 | 100%
S290000 | Long lead items Support Labor for LN2 supply transfer line system | 41 | 01-Feb-21 A | 31-Mar-21 A | 4771 | 4771 | 100%
S343862 | Start Track Modification - AH Install Track Plates and Blocks - Internal | 41 | 01-Feb-21 A | 31-Mar-21 A | 14836 | 45650 | 100%
S343861 | Start Track Modification - AH Fabricate Track Plates M&S - Internal | 41 | 01-Feb-21 A | 31-Mar-21 A | 58034 | 56896 | 100%
S290100 | Procure LN2 supply transfer line system, Phase 2 (Long lead items) - Leadtime | 42 | 01-Feb-21 A | 01-Apr-21 A | 0 | 0 | 100%
S343864 | Start Track Modification - AH Survey and Grout Plates Labor - External | 63 | 01-Feb-21 A | 30-Apr-21 A | 44742 | 44742 | 100%
S343865 | Start Track Modification - AH Survey and Grout Plates M&S - External | 63 | 01-Feb-21 A | 30-Apr-21 A | 11607 | 11607 | 100%
S357500 | Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | 127 | 01-Feb-21 A | 2021-07-30 | 28546 | 28546 | 40%
S357600 | Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - M&S | 127 | 01-Feb-21 A | 2021-07-30 | 34821 | 34821 | 40%
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | 137 | 01-Feb-21 A | 2021-08-13 | 17777 | 17777 | 40%
S317083 | Large Support Rings Supports Released for Production (Milestone) | 0 |  | 01-Feb-21 A | 0 | 0 | 100%
S317180 | Prepare Procurement Package for Large Support Rings | 40 | 02-Feb-21 A | 31-Mar-21 A | 30252 | 29371 | 100%
S290500 | Procure LN2 supply transfer line system, Phase 3 (Final Design Review) - Delivery Acceptance | 62 | 02-Feb-21 A | 30-Apr-21 A | 58034 | 58034 | 100%
S154500 | Procure TPC Cooling System Equipment - Prepare & Send Solicitation | 41 | 03-Feb-21 A | 02-Apr-21 A | 0 | 0 | 100%
S331740 | Design Coolin Manifolds for MVTX | 9 | 08-Feb-21 A | 22-Feb-21 A | 4035 | 3917 | 100%
S352600 | Prepare SC Magnet Integration/Installation Procedures - CA-D Resource(s) | 10 | 08-Feb-21 A | 23-Feb-21 A | 11974 | 11974 | 100%
S1003559 | Prepare SC Magnet Integration/Installation Procedures - Physics Resource(s) | 10 | 08-Feb-21 A | 23-Feb-21 A | 4209 | 4209 | 100%
S355200 | Transport assembled Inner HCal Sectors to AH - Labor - CA-D Resource(s) | 11 | 08-Feb-21 A | 24-Feb-21 A | 1213 | 1213 | 100%
S355300 | Transport assembled Inner HCal Sectors to AH - M&S | 11 | 08-Feb-21 A | 24-Feb-21 A | 580 | 580 | 100%
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | 11 | 08-Feb-21 A | 24-Feb-21 A | 39025 | 39025 | 100%
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | 194 | 08-Feb-21 A | 2021-11-12 | 16836 | 16714 | 75%
S174000 | Fabricate final blocks sector 23 | 6 | 09-Feb-21 A | 17-Feb-21 A | 5163 | 5012 | 100%
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 208 | 10-Feb-21 A | 2021-12-08 | 9359 | 9359 | 50%
S260400 | DAQ Production: Setting up the switches | 118 | 12-Feb-21 A | 2021-07-30 | 29266 | 29266 | 80%
S224100 | Assemble EMCal External Power Cables: Sectors 1-12 | 8 | 15-Feb-21 A | 26-Feb-21 A | 9462 | 9186 | 100%
S199200 | Manufacture Inner HCAL Support Structure - Contract lead time | 73 | 15-Feb-21 A | 28-May-21 A | 0 | 0 | 100%
S155000 | Procure TPC Cooling System Equipment - Delivery Acceptance | 74 | 15-Feb-21 A | 31-May-21 A | 51464 | 50454 | 100%
S332715 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (MBD) | 108 | 15-Feb-21 A | 2021-07-19 | 3094 | 3094 | 60%
S332712 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (IHCal) | 108 | 15-Feb-21 A | 2021-07-19 | 3094 | 3094 | 30%
S143250 | TPC Front End Electronics Protection Components | 117 | 15-Feb-21 A | 2021-07-30 | 174103 | 174103 | 33.2%
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 156 | 15-Feb-21 A | 2021-09-24 | 25846 | 25846 | 30%
S295600 | (Controls Hardware) Power distribution drawings | 178 | 15-Feb-21 A | 2021-10-27 | 4765 | 4565 | 25%
S317230 | Evaluate and Process Bid for EMCal Supports | 7 | 16-Feb-21 A | 25-Feb-21 A | 2606 | 2606 | 100%
S293100 | (Warm Piping tie in bldg. 1010B compressor) Detailed drawing package with weld map | 30 | 16-Feb-21 A | 30-Mar-21 A | 17987 | 17464 | 100%
S326300 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - Physics Resource(s) | 5 | 16-Feb-21 A | 22-Feb-21 A | 5172 | 5172 | 100%
S326310 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - CA-D Resource(s) | 5 | 16-Feb-21 A | 22-Feb-21 A | 8794 | 8794 | 100%
S174100 | Fabricate final blocks sector 24 | 2 | 18-Feb-21 A | 22-Feb-21 A | 5163 | 5012 | 100%
S317130 | Prepare Procurement Package for EMCal Supports | 6 | 18-Feb-21 A | 26-Feb-21 A | 3782 | 3782 | 100%
F317050 | CC Bridge, Mid Platforms & Access - Prepare & Send Solicitation | 3 | 22-Feb-21 A | 25-Feb-21 A | 0 | 0 | 100%
S262900 | Trigger LL1 Preproduction Prototype: Electrical Safety and Final Design Review | 4 | 22-Feb-21 A | 26-Feb-21 A | 0 | 0 | 100%
S263000 | Procure Trigger Preproduction Prototype LL1 - Provide Requirements to Procurement | 4 | 22-Feb-21 A | 26-Feb-21 A | 0 | 0 | 100%
S263100 | Procure Trigger Preproduction Prototype LL1 - Prepare & Send Solicitation | 4 | 22-Feb-21 A | 26-Feb-21 A | 0 | 0 | 100%
S263200 | Procure Trigger Preproduction Prototype LL1 - Vendor Responses | 4 | 22-Feb-21 A | 26-Feb-21 A | 0 | 0 | 100%
S346500 | Install Cryogenics Supply Structural Support - Labor - Physics Resource(s) | 4 | 22-Feb-21 A | 26-Feb-21 A | 23419 | 23419 | 100%
S346600 | Install Cryogenics Supply Structural Support - M&S | 4 | 22-Feb-21 A | 26-Feb-21 A | 580 | 580 | 100%
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | 4 | 22-Feb-21 A | 26-Feb-21 A | 44718 | 44718 | 100%
S317930 | Procure EMCal Supports - M&S | 4 | 22-Feb-21 A | 26-Feb-21 A | 20939 | 20939 | 100%
S234000 | Procure EMCal Bias Power System Sectors 13-64 - Delivery Acceptance | 15 | 22-Feb-21 A | 15-Mar-21 A | 155680 | 155680 | 100%
S205100 | Procure Outer HCAL Splice Plates - Delivery Acceptance | 24 | 22-Feb-21 A | 26-Mar-21 A | 309392 | 303325 | 100%
S232600 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Provide Requirements to Procurement | 90 | 22-Feb-21 A | 29-Jun-21 A | 11723 | 11382 | 100%
S331800 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas | 102 | 22-Feb-21 A | 2021-07-15 | 25846 | 25093 | 33%
S308625 | Complete MOU with Vendor | 159 | 22-Feb-21 A | 2021-10-05 | 1748 | 1697 | 20%
S196700 | Install readout electronics on final sectors | 240 | 22-Feb-21 A | 2022-02-04 | 235148 | 232976 | 31%
S196800 | Install cables & cooling system on final sectors | 240 | 22-Feb-21 A | 2022-02-04 | 500103 | 495600 | 31%
S174200 | Fabricate final blocks sector 25 | 3 | 23-Feb-21 A | 26-Feb-21 A | 5163 | 5062 | 100%
S262800 | Trigger Prototype v1: Preproduction Readiness Review and Design Specifications Update | 3 | 23-Feb-21 A | 26-Feb-21 A | 5673 | 5507 | 100%
S262801 | Preliminary Design Review - DAQ Local Level-1 | 3 | 23-Feb-21 A | 26-Feb-21 A | 2079 | 2018 | 100%
S318130 | Perform EMCal Supports Acceptance | 3 | 23-Feb-21 A | 26-Feb-21 A | 2479 | 2479 | 100%
S331750 | Conceptual Design for Routing Detector Cooling Chiller Systems to Det Manifolds | 101 | 23-Feb-21 A | 2021-07-15 | 4035 | 3917 | 50%
S196900 | Test final sectors with LEDs & cosmic rays | 239 | 23-Feb-21 A | 2022-02-04 | 125693 | 124632 | 10%
S326400 | CC Bridge, Mid Platforms & Access - Provide Requirement to Procurement | 3 | 23-Feb-21 A | 26-Feb-21 A | 2803 | 2803 | 100%
S136300 | Procure TPC FEE Cooling System - Contract Award(s) | 0 | 25-Feb-21 A |  | 0 | 0 | 100%
S171100 | EMCal Scintillating Fiber Acquisition Complete | 0 |  | 25-Feb-21 A | 0 | 0 | 100%
S210400 | First Outer HCAL Sector and Splice Plates Ready to Install | 0 |  | 25-Feb-21 A | 0 | 0 | 100%
S240900 | 50% HCal Preamp Boards testing complete: Production | 0 |  | 25-Feb-21 A | 0 | 0 | 100%
S343838 | Start Track Modification - IR Notice to Proceed | 0 |  | 25-Feb-21 A | 0 | 0 | 100%
S272800 | Procure Min/Bias Electronics - Provide Requirements to Procurement | 1 | 25-Feb-21 A | 26-Feb-21 A | 19854 | 19276 | 100%
S272900 | Procure Min/Bias Electronics - Prepare & Send Solicitation | 1 | 25-Feb-21 A | 26-Feb-21 A | 0 | 0 | 100%
S273000 | Procure Min/Bias Electronics - Vendor Responses | 1 | 25-Feb-21 A | 26-Feb-21 A | 0 | 0 | 100%
S273100 | Procure Min/Bias Electronics - Vendor Selection | 1 | 25-Feb-21 A | 26-Feb-21 A | 0 | 0 | 100%
S272701 | Final Design Review, Procurement Readiness Review - MBD (Discriminator/Shaper board) | 1 | 25-Feb-21 A | 26-Feb-21 A | 3309 | 3213 | 100%
S273200 | Procure Min/Bias Electronics - sPHENIX Production Digitizers - Contract Award(s) | 0 | 26-Feb-21 A |  | 0 | 0 | 100%
S262700 | Trigger Prototype v1: Preprod complete | 0 |  | 26-Feb-21 A | 0 | 0 | 100%
S317000 | Design/Safety Reviews Complete, Internal Detector Structural Support Released for Production | 0 |  | 26-Feb-21 A | 0 | 0 | 100%
S325200 | End Caps/ Pole Tips - Contract Award(s) | 0 | 26-Feb-21 A |  | 0 | 0 | 100%
S174300 | Fabricate final blocks sector 26 | 20 | 26-Feb-21 A | 26-Mar-21 A | 5163 | 5163 | 100%
S136400 | Procure TPC FEE Cooling System - Contract/PO - Leadtime | 23 | 26-Feb-21 A | 31-Mar-21 A | 0 | 0 | 100%
S229300 | Fabricate EMCAL Production Preamp Boards Sectors 13-64 - Delivery Acceptance | 65 | 26-Feb-21 A | 28-May-21 A | 549642 | 549642 | 100%
S229400 | Test EMCal Preamp Boards: Production Sectors 13-64 | 97 | 26-Feb-21 A | 2021-07-14 | 6313 | 6313 | 40%
S325300 | End Caps/ Pole Tips - Contract lead Time | 127 | 26-Feb-21 A | 2021-08-25 | 0 | 0 | 11%
S343840 | Start Track Modification - IR Leadtime | 130 | 26-Feb-21 A | 2021-08-31 | 0 | 0 | 10%
S317023 | Magnet Supports Released for Production (Milestone) | 0 |  | 26-Feb-21 A | 0 | 0 | 100%
S304110 | Completed - Magnet Power Supply Installation: Connect DC Cabling to Power Supply, Dump Resistor, Magnet | 0 |  | 01-Mar-21 A | 0 | 0 | 100%
S210310 | Technical support labor for HCal | 22 | 01-Mar-21 A | 31-Mar-21 A | 0 | 0 | 100%
S263400 | Procure Trigger Preproduction Prototype LL1 - Contract Award(s) | 0 | 01-Mar-21 A |  | 0 | 0 | 100%
S263300 | Procure Trigger Preproduction Prototype LL1 - Vendor Selection | 1 | 01-Mar-21 A | 01-Mar-21 A | 0 | 0 | 100%
S112400 | Design TPC v2 Field Cage Modifications | 15 | 08-Mar-21 A | 29-Mar-21 A | 4308 | 4182 | 100%
S154700 | Procure TPC Cooling System Equipment - Vendor Selection | 19 | 08-Mar-21 A | 02-Apr-21 A | 0 | 0 | 100%
S294700 | (Warm Piping System Materials Procurement) Piping supports Labor | 59 | 08-Mar-21 A | 28-May-21 A | 4771 | 4632 | 100%
S294600 | (Warm Piping System Materials Procurement) Piping supports M&S | 59 | 08-Mar-21 A | 28-May-21 A | 11607 | 11379 | 100%
S147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | 105 | 08-Mar-21 A | 2021-08-03 | 70146 | 70146 | 10%
S153700 | Procure TPC Gas System Components for Installation - Delivery Acceptance | 125 | 08-Mar-21 A | 2021-08-31 | 40354 | 39563 | 70%
S307100 | Magnet: Connect Signal Interconnections | 125 | 08-Mar-21 A | 2021-08-31 | 9404 | 9130 | 30%
S300900 | (Cryo Controls Hardware) Built HMI operator screens | 138 | 08-Mar-21 A | 2021-09-20 | 85977 | 85977 | 45%
S308633 | Construct mapping support (mechanical and electrical) | 160 | 08-Mar-21 A | 2021-10-21 | 3874 | 3761 | 5%
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 292 | 08-Mar-21 A | 2022-05-04 | 7447 | 7447 | 50%
S153500 | Procure TPC Gas System Components for Installation - Contract Award(s) | 0 | 11-Mar-21 A |  | 0 | 0 | 100%
S153100 | Procure TPC Gas System Components for Installation - Provide Requirements to Procurement | 13 | 11-Mar-21 A | 30-Mar-21 A | 8342 | 8099 | 100%
S153200 | Procure TPC Gas System Components for Installation - Prepare & Send Solicitation | 13 | 11-Mar-21 A | 30-Mar-21 A | 0 | 0 | 100%
S153300 | Procure TPC Gas System Components for Installation - Vendor Responses | 13 | 11-Mar-21 A | 30-Mar-21 A | 0 | 0 | 100%
S153400 | Procure TPC Gas System Components for Installation - Vendor Selection | 13 | 11-Mar-21 A | 30-Mar-21 A | 0 | 0 | 100%
S153600 | Procure TPC Gas System Components for Installation - Contract/PO - Leadtime | 13 | 11-Mar-21 A | 30-Mar-21 A | 0 | 0 | 100%
S350200 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource(s) | 6 | 15-Mar-21 A | 23-Mar-21 A | 1020 | 990 | 100%
S350300 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - C | 6 | 15-Mar-21 A | 23-Mar-21 A | 1020 | 990 | 100%
S1002279 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resource(s) | 6 | 15-Mar-21 A | 23-Mar-21 A | 3094 | 3004 | 100%
S1002359 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - P | 6 | 15-Mar-21 A | 23-Mar-21 A | 3094 | 3004 | 100%
S264300 | Procure Production LL1 System - Provide Requirements to Procurement | 11 | 15-Mar-21 A | 30-Mar-21 A | 0 | 0 | 100%
S264400 | Procure Production LL1 System - Prepare & Send Solicitation | 11 | 15-Mar-21 A | 30-Mar-21 A | 0 | 0 | 100%
S264500 | Procure Production LL1 System - Vendor Responses | 11 | 15-Mar-21 A | 30-Mar-21 A | 0 | 0 | 100%
S264600 | Procure Production LL1 System - Vendor Selection | 11 | 15-Mar-21 A | 30-Mar-21 A | 0 | 0 | 100%
S326600 | CC Bridge, Mid Platforms & Access - Vendor Responses - Physics Resource(s) | 27 | 15-Mar-21 A | 21-Apr-21 A | 7053 | 7053 | 100%
S326610 | CC Bridge, Mid Platforms & Access - Vendor Responses - CA-D Resource(s) | 27 | 15-Mar-21 A | 21-Apr-21 A | 10881 | 10881 | 100%
S136500 | Procure TPC FEE Cooling System - Delivery Acceptance | 98 | 15-Mar-21 A | 2021-07-30 | 69821 | 69821 | 17.8%
S141500 | Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Delivery Acceptance | 98 | 15-Mar-21 A | 2021-07-30 | 34429 | 34429 | 33.2%
S270500 | Timing System Production: final firmware updates | 109 | 15-Mar-21 A | 2021-08-16 | 84316 | 81860 | 60%
S270510 | Timing System Production: final firmware updates IO | 109 | 15-Mar-21 A | 2021-08-16 | 41958 | 40736 | 60%
S147500 | TPC DAM Felix 2.0 Bandwidth test in 1008 | 120 | 15-Mar-21 A | 2021-08-31 | 60416 | 60416 | 40%
S152900 | Set up TPC Gas System computer control Labor | 150 | 15-Mar-21 A | 2021-10-14 | 3668 | 3543 | 25%
S317120 | Prepare Procurement Package for Magnet Supports | 7 | 16-Mar-21 A | 25-Mar-21 A | 15126 | 15126 | 100%
S290200 | Procure LN2 supply transfer line system, Phase 2 (Long lead items) - Delivery Acceptance | 10 | 16-Mar-21 A | 30-Mar-21 A | 58034 | 58034 | 100%
S153800 | Assemble and Plumb TPC Gas System | 179 | 16-Mar-21 A | 2021-11-30 | 53272 | 51720 | 30%
S197000 | Repair or rework any sectors as required | 224 | 16-Mar-21 A | 2022-02-04 | 252651 | 250055 | 31%
S174400 | Fabricate final blocks sector 27 | 10 | 16-Mar-21 A | 29-Mar-21 A | 5163 | 5163 | 100%
S256100 | Procure DAQ Production Crates - Provide Requirements to Procurement | 14 | 16-Mar-21 A | 05-Apr-21 A | 26316 | 25550 | 100%
S291900 | (LN2 supply transfer line system) Piping supports procure materials Labor | 2 | 17-Mar-21 A | 19-Mar-21 A | 1564 | 1518 | 100%
S291800 | (LN2 supply transfer line system) Piping supports procure materials M&S | 2 | 17-Mar-21 A | 19-Mar-21 A | 15089 | 14793 | 100%
S352400 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s) | 95 | 17-Mar-21 A | 2021-07-29 | 1517 | 1517 | 75%
S352500 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - M&S | 95 | 17-Mar-21 A | 2021-07-29 | 34821 | 34821 | 75%
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | 95 | 17-Mar-21 A | 2021-07-29 | 6901 | 6901 | 75%
S174500 | Fabricate final blocks sector 28 | 10 | 18-Mar-21 A | 31-Mar-21 A | 5163 | 5163 | 100%
S154600 | Procure TPC Cooling System Equipment - Vendor Responses | 11 | 18-Mar-21 A | 02-Apr-21 A | 0 | 0 | 100%
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 4 | 22-Mar-21 A | 26-Mar-21 A | 3094 | 3094 | 100%
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 4 | 22-Mar-21 A | 26-Mar-21 A | 3094 | 3094 | 100%
S352700 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification- CA-D | 4 | 22-Mar-21 A | 26-Mar-21 A | 1145 | 1145 | 100%
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 4 | 22-Mar-21 A | 26-Mar-21 A | 3094 | 3094 | 100%
S125100 | Procure TPC R1 Module Parts (Padplanes) - Delivery Acceptance | 5 | 22-Mar-21 A | 29-Mar-21 A | 51115 | 50113 | 100%
S304000 | Magnet Power Supply Installation: Connect AC Power to Power Supply | 7 | 22-Mar-21 A | 31-Mar-21 A | 4881 | 4739 | 100%
S317280 | Evaluate and Process Bid for Large Support Rings | 7 | 22-Mar-21 A | 31-Mar-21 A | 5212 | 5098 | 100%
S329470 | Conceptual Design for Power Distribution / Controls Cable Routing | 7 | 22-Mar-21 A | 31-Mar-21 A | 24847 | 24847 | 100%
S297800 | (Cryo Controls Hardware procurement) Heaters 480VAC Labor | 29 | 22-Mar-21 A | 30-Apr-21 A | 1879 | 1824 | 100%
S297900 | (Cryo Controls Hardware procurement) Heaters 480VAC M&S | 29 | 22-Mar-21 A | 30-Apr-21 A | 20126 | 19732 | 100%
S178500 | Pack and ship final blocks for sectors 25-32 to BNL - Purchased Services | 35 | 22-Mar-21 A | 07-May-21 A | 2561 | 2561 | 100%
S178510 | Pack and ship final blocks for sectors 25-32 to BNL - M&S | 35 | 22-Mar-21 A | 07-May-21 A | 7521 | 7521 | 100%
S148800 | TPC Laser System Safety Review | 87 | 22-Mar-21 A | 2021-07-22 | 1316 | 1240 | 20%
S148900 | Procurement Readiness Review - TPC Laser System | 93 | 22-Mar-21 A | 2021-07-30 | 1316 | 1240 | 50%
S152800 | Assemble TPC Gas System controls | 110 | 22-Mar-21 A | 2021-08-24 | 63703 | 61847 | 10%
S174600 | Fabricate final blocks sector 29 | 6 | 26-Mar-21 A | 02-Apr-21 A | 5163 | 5163 | 100%
S210500 | Last Outer HCAL Sector Ready to Install | 0 |  | 29-Mar-21 A | 0 | 0 | 100%
S229405 | Test EMCal Preamp Boards: Production Sectors 13-64 - Contributed Labor | 76 | 29-Mar-21 A | 2021-07-14 | 31221 | 31221 | 40%
S290210 | Completed - Procure LN2 supply transfer line system, Phase 2 (Long lead items) - Delivery Acceptance | 0 |  | 30-Mar-21 A | 0 | 0 | 100%
S358000 | Design/Safety Reviews Complete, EMCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | 0 |  | 30-Mar-21 A | 0 | 0 | 100%
S112700 | Procure TPC v2 Field Cage Modification Parts Labor | 1 | 30-Mar-21 A | 31-Mar-21 A | 3761 | 3652 | 100%
S112900 | Modify TPC v2 Field Cage | 1 | 30-Mar-21 A | 31-Mar-21 A | 0 | 0 | 100%
S113000 | Benchtest TPC Final Field Cage | 1 | 30-Mar-21 A | 31-Mar-21 A | 0 | 0 | 100%
S112800 | Procure TPC v2 Field Cage Modification Parts M&S | 1 | 30-Mar-21 A | 31-Mar-21 A | 6964 | 6828 | 100%
S112500 | TPC Field Cage Safety Review | 1 | 30-Mar-21 A | 31-Mar-21 A | 1316 | 1277 | 100%
S112600 | Procurement Readiness Review - TPC Field Cage | 1 | 30-Mar-21 A | 31-Mar-21 A | 1316 | 1277 | 100%
S264700 | Procure Production LL1 System - Contract Award(s) | 0 | 31-Mar-21 A |  | 0 | 0 | 100%
S241000 | 75% HCal Preamp Boards testing complete: Production | 0 |  | 31-Mar-21 A | 0 | 0 | 100%
S350400 | Design/Safety Reviews Complete, Outer HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | 0 |  | 31-Mar-21 A | 0 | 0 | 100%
S263500 | Procure Trigger Preproduction Prototype LL1 - Contract/PO - Leadtime | 86 | 31-Mar-21 A | 2021-07-30 | 0 | 0 | 50%
S264800 | Procure Production LL1 System - Contract/PO - Leadtime | 152 | 31-Mar-21 A | 2021-11-03 | 0 | 0 | 15%
S350500 | Outer HCal Sectors Ready for Installation | 0 |  | 31-Mar-21 A | 0 | 0 | 100%
S269700 | Timing System Production (FPGA Boards) - Provide Requirements to Procurement | 4 | 01-Apr-21 A | 07-Apr-21 A | 19394 | 18829 | 100%
S255600 | Procure DAQ Production Boards - Vendor Selection | 21 | 01-Apr-21 A | 30-Apr-21 A | 0 | 0 | 100%
S227550 | 100% EMCal SiPM Daughter Boards Delivered: Production Sectors 13-64 | 21 | 01-Apr-21 A | 30-Apr-21 A | 0 | 0 | 100%
S333900 | Analyze Gas Mixing House & Gas Pad Components Requirements - CA-D Resource(s) | 61 | 01-Apr-21 A | 28-Jun-21 A | 2458 | 2427 | 100%
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | 61 | 01-Apr-21 A | 28-Jun-21 A | 17793 | 17564 | 100%
S334000 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents C | 147 | 01-Apr-21 A | 2021-10-28 | 1250 | 1213 | 60%
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents P | 147 | 01-Apr-21 A | 2021-10-28 | 16825 | 16335 | 60%
S273300 | Procure Shaper/Disc Board 128 Channels - Contract Award(s) | 0 | 01-Apr-21 A |  | 0 | 0 | 100%
S228200 | 20% EMCal SiPM Daughter Boards Tested: Production Sectors 13-64 | 0 |  | 01-Apr-21 A | 0 | 0 | 100%
S228300 | 40% EMCal SiPM Daughter Boards Tested: Production Sectors 13-64 | 0 |  | 01-Apr-21 A | 0 | 0 | 100%
S328200 | Design/Safety Reviews Complete, Line Electric Power Distribution Released for Production | 0 |  | 01-Apr-21 A | 0 | 0 | 100%
S330616 | Prelim Design/Safety Reviews Complete for Det El Racks and Rack generic support systems | 0 |  | 01-Apr-21 A | 0 | 0 | 100%
S227540 | 80% EMCal SiPM Daughter Boards Delivered: Production Sectors 13-64 | 21 | 01-Apr-21 A | 30-Apr-21 A | 0 | 0 | 100%
S328550 | Prepare Line Electric Power Distribution Components Procurement Package(s) | 21 | 01-Apr-21 A | 30-Apr-21 A | 7818 | 7818 | 100%
S328500 | Procure Line Electric Power Distribution Components - Provide Requirements to Procurement | 21 | 01-Apr-21 A | 30-Apr-21 A | 6255 | 6255 | 100%
S154800 | Procure TPC Cooling System Equipment - Contract Award(s) | 0 | 02-Apr-21 A |  | 0 | 0 | 100%
S267000 | Procure Production GL1 Components - Provide Requirements to Procurement | 4 | 02-Apr-21 A | 08-Apr-21 A | 6382 | 6196 | 100%
S256300 | Procure DAQ Production Crates - Vendor Responses | 4 | 05-Apr-21 A | 09-Apr-21 A | 0 | 0 | 100%
S256400 | Procure DAQ Production Crates - Vendor Selection | 4 | 05-Apr-21 A | 09-Apr-21 A | 0 | 0 | 100%
S174700 | Fabricate final blocks sector 30 | 6 | 05-Apr-21 A | 12-Apr-21 A | 5163 | 5163 | 100%
S194400 | Completion of EMCal Prepro Sectors 1-12 | 0 |  | 05-Apr-21 A | 0 | 0 | 100%
S256200 | Procure DAQ Production Crates - Prepare & Send Solicitation | 18 | 06-Apr-21 A | 30-Apr-21 A | 0 | 0 | 100%
S269800 | Timing System Production (FPGA Boards) - Prepare & Send Solicitation | 4 | 08-Apr-21 A | 14-Apr-21 A | 0 | 0 | 100%
S267100 | Procure Production GL1 Components - Prepare & Send Solicitation | 4 | 09-Apr-21 A | 15-Apr-21 A | 0 | 0 | 100%
S313200 | CC Drive & Alignment System - Delivery Acceptance - Physics Resource(s) - Labor | 3 | 12-Apr-21 A | 15-Apr-21 A | 11284 | 11284 | 100%
S313210 | CC Drive & Alignment System - Delivery Acceptance - CA-D Resource(s) - Labor | 3 | 12-Apr-21 A | 15-Apr-21 A | 7435 | 7435 | 100%
S313250 | CC Drive & Alignment System - Delivery Acceptance - M&S | 3 | 12-Apr-21 A | 15-Apr-21 A | 65672 | 65672 | 100%
S142900 | Procure TPC FEE Production Boards & Assembly - Vendor Selection | 14 | 12-Apr-21 A | 30-Apr-21 A | 0 | 0 | 100%
S174800 | Fabricate final blocks sector 31 | 6 | 13-Apr-21 A | 20-Apr-21 A | 5163 | 5163 | 100%
S232800 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Vendor Responses | 53 | 14-Apr-21 A | 29-Jun-21 A | 0 | 0 | 100%
S311400 | Carriage Cradle - Components Ready for Installation | 0 |  | 15-Apr-21 A | 0 | 0 | 100%
S313255 | Completed - CC Drive & Alignment System - Delivery Acceptance - M&S | 0 |  | 15-Apr-21 A | 0 | 0 | 100%
S269900 | Timing System Production (FPGA Boards) - Vendor Responses | 4 | 15-Apr-21 A | 21-Apr-21 A | 0 | 0 | 100%
S317100 | Prepare Procurement Package(s) for Inner HCal Support Tabs - Physics Resource(s) | 53 | 15-Apr-21 A | 30-Jun-21 A | 5642 | 5478 | 100%
S317110 | Prepare Procurement Package(s) for Inner HCal Support Tabs - CA-D Resource(s) | 53 | 15-Apr-21 A | 30-Jun-21 A | 18202 | 17672 | 100%
S317980 | Procure Large Support Rings - M&S | 93 | 15-Apr-21 A | 2021-08-25 | 348205 | 348205 | 25%
S1008520 | (LN2 supply transfer line system) LOE Supervision Labor | 50 | 15-Apr-21 A | 25-Jun-21 A | 27830 | 27830 | 100%
S267200 | Procure Production GL1 Components - Vendor Responses | 4 | 16-Apr-21 A | 22-Apr-21 A | 0 | 0 | 100%
S120200 | GEM Production Complete | 0 |  | 17-Apr-21 A | 0 | 0 | 100%
S295500 | (Controls Hardware) Wire diagram drawings | 114 | 19-Apr-21 A | 2021-09-28 | 15046 | 14608 | 25%
S290700 | (LN2 supply transfer line system) Raw Material procurement Labor | 46 | 21-Apr-21 A | 25-Jun-21 A | 0 | 0 | 100%
S291000 | (LN2 supply transfer line system) Main fabrication items | 46 | 21-Apr-21 A | 25-Jun-21 A | 0 | 0 | 100%
S290900 | Procure LN2 supply transfer line system, Phase 4 (Raw Material) - Delivery Acceptance | 46 | 21-Apr-21 A | 25-Jun-21 A | 0 | 0 | 100%
S290800 | Procure LN2 supply transfer line system, Phase 4 (Raw Material) - Leadtime | 46 | 21-Apr-21 A | 25-Jun-21 A | 0 | 0 | 100%
S1006160 | Witness test 1008B Cold Box Assembly | 5 | 21-Apr-21 A | 27-Apr-21 A | 0 | 0 | 100%
S174900 | Fabricate final blocks sector 32 | 6 | 21-Apr-21 A | 28-Apr-21 A | 5163 | 5163 | 100%
S270000 | Timing System Production (FPGA Boards) - Vendor Selection | 4 | 22-Apr-21 A | 28-Apr-21 A | 0 | 0 | 100%
S267300 | Procure Production GL1 Components - Vendor Selection | 4 | 23-Apr-21 A | 29-Apr-21 A | 0 | 0 | 100%
S232700 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Prepare & Send Solicitation | 46 | 23-Apr-21 A | 29-Jun-21 A | 0 | 0 | 100%
S290600 | (LN2 supply transfer line system) Drawings approvals | 4 | 26-Apr-21 A | 30-Apr-21 A | 0 | 0 | 100%
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | 46 | 26-Apr-21 A | 30-Jun-21 A | 19999 | 19999 | 100%
S332800 | Analyze Detector Safety Subsystems Requirements - CA-D Resource(s) | 46 | 26-Apr-21 A | 30-Jun-21 A | 1213 | 1213 | 100%
S260500 | DAQ Production: Modify and Debug event builder software | 86 | 26-Apr-21 A | 2021-08-25 | 105265 | 105265 | 90%
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 128 | 26-Apr-21 A | 2021-10-26 | 14084 | 14318 | 50%
S340600 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - M&S | 179 | 26-Apr-21 A | 2022-01-12 | 76953 | 76953 | 50%
S1006200 | Delivery of the 1008B Cold Box and Document Package | 23 | 28-Apr-21 A | 31-May-21 A | 104800 | 104800 | 100%
S175100 | Fabricate final blocks sector 34 | 1 | 29-Apr-21 A | 30-Apr-21 A | 5163 | 5163 | 100%
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 127 | 29-Apr-21 A | 2021-10-28 | 7243 | 7243 | 35%
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 137 | 29-Apr-21 A | 2021-11-12 | 8418 | 8418 | 20%
S175000 | Fabricate final blocks sector 33 | 1 | 29-Apr-21 A | 30-Apr-21 A | 5163 | 5163 | 100%
S154900 | Procure TPC Cooling System Equipment - Contract/PO - Leadtime | 22 | 29-Apr-21 A | 31-May-21 A | 0 | 0 | 100%
S143000 | Procure TPC FEE Production Boards & Assembly - Contract Award(s) | 0 | 30-Apr-21 A |  | 0 | 0 | 100%
S148200 | Procure TPC EDBC Computers & Peripherals - Contract Award(s) | 0 | 30-Apr-21 A |  | 0 | 0 | 100%
S228600 | EMCal SiPM Boards Production Complete | 0 |  | 30-Apr-21 A | 0 | 0 | 100%
S290510 | Completed - Procure LN2 supply transfer line system, Phase 3 (Final Design Review) - Delivery Acceptance | 0 |  | 30-Apr-21 A | 0 | 0 | 100%
S343866 | Start Track Modification - AH Finish AH Installation | 0 |  | 30-Apr-21 A | 0 | 0 | 100%
S175200 | Fabricate final blocks sector 35 | 6 | 30-Apr-21 A | 07-May-21 A | 5163 | 5163 | 100%
S330800 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - CA-D Resource(s) | 62 | 30-Apr-21 A | 2021-07-28 | 1213 | 1213 | 60%
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | 62 | 30-Apr-21 A | 2021-07-28 | 6017 | 6017 | 85%
S252700 | Procure Production Digitizer (Parts) - Delivery Acceptance | 70 | 30-Apr-21 A | 2021-08-09 | 678538 | 678538 | 37%
S143100 | Procure TPC FEE Production Boards & Assembly - Contract/PO - Leadtime | 105 | 30-Apr-21 A | 2021-09-28 | 0 | 0 | 10%
S292910 | Completed - (Warm Piping tie in to WR header) Detailed drawing package with weld map | 0 |  | 30-Apr-21 A | 0 | 0 | 100%
S317220 | Evaluate and Process Bid for Magnet Supports | 10 | 03-May-21 A | 17-May-21 A | 5212 | 5212 | 100%
S298400 | (Cryo Controls Hardware procurement) Network switch and Ethernet fiber drop Labor | 15 | 03-May-21 A | 24-May-21 A | 652 | 633 | 100%
S298500 | (Cryo Controls Hardware procurement) Network switch and Ethernet fiber drop M&S | 15 | 03-May-21 A | 24-May-21 A | 4062 | 3983 | 100%
S348600 | Ready to Assemble Cradle Carriage in AH | 0 |  | 03-May-21 A | 0 | 0 | 100%
S348700 | Assemble base, carriage alignment and carriage roller supports - Labor - Physics Resource(s) | 41 | 03-May-21 A | 30-Jun-21 A | 60730 | 60730 | 100%
S348800 | Assemble base, carriage alignment and carriage roller supports - M&S | 41 | 03-May-21 A | 30-Jun-21 A | 2902 | 2902 | 100%
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | 41 | 03-May-21 A | 30-Jun-21 A | 46728 | 46728 | 100%
S328700 | Procure Line Electric Power Distribution Components - Prepare and Send Solicitation | 56 | 10-May-21 A | 2021-07-28 | 0 | 0 | 90%
S317920 | Procure Magnet Supports - M&S | 62 | 10-May-21 A | 2021-08-05 | 58034 | 58034 | 50%
S175300 | Fabricate final blocks sector 36 | 6 | 10-May-21 A | 17-May-21 A | 5163 | 5163 | 100%
S112000 | Assemble TPC v2 Field Cage Prototype | 57 | 11-May-21 A | 2021-07-30 | 0 | 0 | 15%
S304510 | Completed - Magnet Power Supply Installation: Water Cooled Bus Termination 1008B L | 0 |  | 17-May-21 A | 0 | 0 | 100%
S200000 | Manufacture Inner HCAL Support Rings - Delivery Acceptance | 3 | 17-May-21 A | 20-May-21 A | 141886 | 141886 | 100%
S232500 | Fabricate Test-pulse Boards 13 - 64 - M&S | 9 | 17-May-21 A | 28-May-21 A | 8183 | 8022 | 100%
S148300 | Procure TPC EDBC Computers & Peripherals - Contract/PO - Leadtime | 28 | 17-May-21 A | 25-Jun-21 A | 0 | 0 | 100%
S178600 | Pack and ship final blocks for sectors 33-40 to BNL - Purchased Services | 30 | 17-May-21 A | 28-Jun-21 A | 2561 | 2561 | 100%
S178610 | Pack and ship final blocks for sectors 33-40 to BNL - M&S | 30 | 17-May-21 A | 28-Jun-21 A | 7521 | 7521 | 100%
S140700 | Review Results of SAMPA 80 nsec Full Chip Performance with v2 Prototype TPC FEE Board | 31 | 17-May-21 A | 30-Jun-21 A | 45869 | 44533 | 100%
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | 45 | 17-May-21 A | 2021-07-20 | 10956 | 10637 | 3%
S121650 | Procure Piping Fittings | 81 | 17-May-21 A | 2021-09-09 | 1279 | 1279 | 50%
S175400 | Fabricate final blocks sector 37 | 6 | 18-May-21 A | 25-May-21 A | 5163 | 5163 | 100%
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | 70 | 24-May-21 A | 2021-08-31 | 4823 | 4683 | 10%
S175500 | Fabricate final blocks sector 38 | 6 | 26-May-21 A | 03-Jun-21 A | 5163 | 5163 | 100%
S228400 | 60% EMCal SiPM Daughter Boards Tested: Production Sectors 13-64 | 0 |  | 31-May-21 A | 0 | 0 | 100%
S327200 | Deleted CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor - Physics Resource(s) | 1 | 01-Jun-21 A | 02-Jun-21 A | 0 | 1411 | 100%
S327210 | Deleted CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor - CA-D Resource(s) | 1 | 01-Jun-21 A | 02-Jun-21 A | 0 | 6730 | 100%
S148400 | Procure TPC EDBC Computers & Peripherals - Delivery Acceptance | 9 | 01-Jun-21 A | 14-Jun-21 A | 244769 | 244769 | 100%
S348900 | Assemble HCal cradle onto base - Labor - Physics Resource(s) | 21 | 01-Jun-21 A | 30-Jun-21 A | 13711 | 13711 | 100%
S348910 | Assemble HCal cradle onto base - Labor - CA-D Resource(s) | 21 | 01-Jun-21 A | 30-Jun-21 A | 14312 | 14312 | 100%
S348915 | Assemble HCal cradle onto base - M&S | 21 | 01-Jun-21 A | 30-Jun-21 A | 3482 | 3482 | 100%
S121950 | TPC Assembly technical Support | 78 | 01-Jun-21 A | 2021-09-20 | 23334 | 23254 | 33%
S175600 | Fabricate final blocks sector 39 | 6 | 04-Jun-21 A | 11-Jun-21 A | 5163 | 5163 | 100%
S331900 | Review Detector Gas and Cooling Services Systems Design/Safety - CA-D Resource(s) | 60 | 08-Jun-21 A | 2021-08-31 | 2485 | 2356 | 50%
S326700 | CC Bridge, Mid Platforms & Access - Vendor Selection - Physics Resource(s) | 6 | 14-Jun-21 A | 22-Jun-21 A | 9874 | 9874 | 100%
S326710 | CC Bridge, Mid Platforms & Access - Vendor Selection - CA-D Resource(s) | 6 | 14-Jun-21 A | 22-Jun-21 A | 12282 | 12282 | 100%
S294500 | Procure Warm Piping and fittings - Delivery acceptance | 37 | 14-Jun-21 A | 2021-08-04 | 37142 | 37142 | 50%
S175700 | Fabricate final blocks sector 40 | 6 | 14-Jun-21 A | 21-Jun-21 A | 5163 | 5163 | 100%
S151300 | TPC Gas System Safety Review | 3 | 15-Jun-21 A | 18-Jun-21 A | 1316 | 1277 | 100%
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | 55 | 15-Jun-21 A | 2021-08-31 | 5855 | 5552 | 50%
S178700 | Pack and ship final blocks for sectors 41-48 to BNL - Purchased Services | 58 | 15-Jun-21 A | 2021-09-03 | 2561 | 2561 | 5%
S178710 | Pack and ship final blocks for sectors 41-48 to BNL - M&S | 58 | 15-Jun-21 A | 2021-09-03 | 7521 | 7521 | 5%
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 115 | 15-Jun-21 A | 2021-11-30 | 3187 | 3094 | 25%
S300100 | (Cryo Controls Hardware) Heater Control Panel Install | 145 | 15-Jun-21 A | 2022-01-13 | 4246 | 4122 | 50%
S300300 | (Cryo Controls Hardware) Insulating vacuum roughing pumps 480VAC Breaker install and 480V wiring to roughing pumps | 190 | 15-Jun-21 A | 2022-03-21 | 1062 | 1062 | 50%
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | 29 | 21-Jun-21 A | 2021-07-30 | 6017 | 6017 | 25%
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | 54 | 21-Jun-21 A | 2021-09-03 | 84290 | 83986 | 8%
S350900 | Install Partial Outer HCal (Prior to SC Magnet Install) - M&S | 54 | 21-Jun-21 A | 2021-09-03 | 582 | 580 | 8%
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 54 | 21-Jun-21 A | 2021-09-03 | 152827 | 152827 | 8%
S232900 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Vendor Selection | 27 | 22-Jun-21 A | 2021-07-29 | 0 | 0 | 20%
S175800 | Fabricate final blocks sector 41 | 6 | 22-Jun-21 A | 29-Jun-21 A | 5163 | 5163 | 100%
S326800 | CC Bridge, Mid Platforms & Access - Contract Award(s) | 0 | 23-Jun-21 A |  | 0 | 0 | 100%
S290910 | Completed - Procure LN2 supply transfer line system, Phase 4 (Raw Material) - Delivery Acceptance | 0 |  | 25-Jun-21 A | 0 | 0 | 100%
S199300 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 1 | 2 | 28-Jun-21 A | 30-Jun-21 A | 264958 | 264958 | 100%
S141300 | Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Contract Award(s) | 0 | 29-Jun-21 A |  | 0 | 0 | 100%
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | 0 | 29-Jun-21 A | 29-Jun-21 A | 50178 | 50178 | 100%
S141400 | Procure TPC FEE Production Components, Phase 1 (Optical Transceiver Components) - Leadtime | 1 | 29-Jun-21 A | 30-Jun-21 A | 0 | 0 | 100%
S350600 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - CA-D Resource(s) | 1 | 29-Jun-21 A | 30-Jun-21 A | 826 | 826 | 100%
S350700 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - M&S | 1 | 29-Jun-21 A | 30-Jun-21 A | 580 | 580 | 100%
S244500 | HCal Electronics Complete: Production | 0 |  | 30-Jun-21 A | 0 | 0 | 100%
S348920 | Completed - Assemble HCal cradle onto base | 0 |  | 30-Jun-21 A | 0 | 0 | 100%
S175900 | Fabricate final blocks sector 42 | 6 | 30-Jun-21 A | 2021-07-08 | 5163 | 5163 | 88%
S147350 | Procure TPC DAM Felix 2.0 Optical Components - Contract Award(s) | 0 | 2021-07-01 |  | 0 | 0 | 0%
S255700 | Procure DAQ Production Boards - Contract Award(s) | 0 | 2021-07-01 |  | 0 | 0 | 0%
S256500 | Procure DAQ Production Crates - Contract Award(s) | 0 | 2021-07-01 |  | 0 | 0 | 0%
S228500 | 100% EMCal SiPM Daughter Boards Tested: Production Sectors 13-64 | 0 |  | 2021-07-01 | 0 | 0 | 0%
S228450 | 80% EMCal SiPM Daughter Boards Tested: Production Sectors 13-64 | 0 |  | 2021-07-01 | 0 | 0 | 0%
S140701 | Production Readiness Review for TPC FEE full production | 1 | 2021-07-01 | 2021-07-01 | 3674 | 3567 | 0%
S266701 | Final Design Review - DAQ Global Level-1 | 1 | 2021-07-01 | 2021-07-01 | 3121 | 3030 | 0%
S266702 | Procurement Readiness Review - DAQ Global Level-1 | 1 | 2021-07-01 | 2021-07-01 | 3121 | 3030 | 0%
S155100 | Install TPC Cooling System pumps | 3 | 2021-07-01 | 2021-07-06 | 2821 | 2739 | 0%
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 5 | 2021-07-01 | 2021-07-08 | 11700 | 11700 | 0%
S331760 | Conceptual Design for Cooling Tube Routing from Detector to IHCal manifold | 5 | 2021-07-01 | 2021-07-08 | 4035 | 3917 | 0%
S1006640 | Draft PDR of three Manifold Jumper Transfer Lines | 10 | 01-Jul-21* | 2021-07-15 | 0 | 0 | 0%
S331905 | Review Detector Cooling Services Systems Design/Safety | 10 | 01-Jul-21* | 2021-07-15 | 2427 | 2427 | 0%
S302101 | Magnet: Design DC Flags 50% | 19 | 01-Jul-21* | 2021-07-28 | 758 | 736 | 0%
S317200 | Evaluate & Process Bid for Inner HCal Support Tabs - Physics Resource(s) | 20 | 2021-07-01 | 2021-07-29 | 3761 | 3652 | 0%
S317210 | Evaluate & Process Bid for IHCal Support Tabs - CA-D Resource(s) | 20 | 2021-07-01 | 2021-07-29 | 4854 | 4712 | 0%
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | 30 | 2021-07-01 | 2021-08-12 | 11217 | 11217 | 0%
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | 40 | 2021-07-01 | 2021-08-26 | 5794 | 5920 | 0%
S255800 | Procure DAQ Production Boards - Contract/PO - Leadtime | 80 | 2021-07-01 | 2021-10-25 | 0 | 0 | 0%
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | 85 | 2021-07-01 | 2021-11-01 | 12789 | 12695 | 0%
S327000 | CC Bridge, Mid Platforms & Access - Vendor Leadtime | 85 | 2021-07-01 | 2021-11-01 | 0 | 0 | 0%
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 85 | 2021-07-01 | 2021-11-01 | 18725 | 18588 | 0%
S256600 | Procure DAQ Production Crates - Contract/PO - Leadtime | 100 | 2021-07-01 | 2021-11-23 | 0 | 0 | 0%
S273700 | Oversight of sPHENIX MBD Digitizers Procurement | 105 | 2021-07-01 | 2021-12-02 | 2870 | 2762 | 0%
S273400 | Procure Min/Bias Electronics - Contract/PO - Leadtime | 105 | 2021-07-01 | 2021-12-02 | 0 | 0 | 0%
S327150 | Access stairs for upper platforms | 144 | 01-Jul-21* | 2022-01-31 | 50203 | 50203 | 0%
S339300 | Perform Beampipe/vacuum Acceptance - Physics Resource(s) NEG coating | 200 | 2021-07-01 | 2022-04-20 | 4318 | 965 | 0%
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) NEG coating | 200 | 2021-07-01 | 2022-04-20 | 4676 | 7314 | 0%
S275400 | 2022 Cryo L3 Project Management | 250 | 2021-07-01 | 2022-06-30 | 0 | 0 | 0%
S339350 | NEG Re-coating of beryllium beampipe | 260 | 01-Jul-21* | 2022-07-15 | 111561 | 111561 | 0%
S266800 | GL1 Prototype: Update design specifications; incorporate final design choice | 20 | 2021-07-02 | 2021-07-30 | 21770 | 21136 | 0%
S147360 | Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Leadtime | 75 | 2021-07-02 | 2021-10-19 | 0 | 0 | 0%
S155200 | Install TPC Cooling System heat exchanger | 3 | 2021-07-07 | 2021-07-09 | 2821 | 2739 | 0%
S176000 | Fabricate final blocks sector 43 | 6 | 2021-07-09 | 2021-07-16 | 5163 | 5163 | 0%
S332740 | Review Detector Gas Service Systems Design/Safety | 10 | 2021-07-09 | 2021-07-22 | 3094 | 3094 | 0%
S294840 | (Warm Piping System) Phase 2: Welding of piping, vent lines and install of piping supports, after coldbox/magnet install | 30 | 2021-07-09 | 2021-08-19 | 31002 | 31002 | 0%
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 30 | 2021-07-09 | 2021-08-19 | 78105 | 78105 | 0%
S155300 | Install TPC Cooling System PH control | 3 | 2021-07-12 | 2021-07-14 | 2821 | 2739 | 0%
S134100 | TPC R3 GEM Modules Production Ends | 0 |  | 2021-07-14 | 0 | 0 | 0%
S155400 | Install TPC Cooling System end cap manifolds | 10 | 2021-07-15 | 2021-07-28 | 9404 | 9130 | 0%
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 90 | 2021-07-15 | 2021-11-22 | 11585 | 11452 | 0%
S359800 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - M&S | 90 | 2021-07-15 | 2021-11-22 | 35091 | 34821 | 0%
S1006280 | BNL review for PDR approval | 10 | 2021-07-16 | 2021-07-29 | 34933 | 34933 | 0%
S1006660 | AET submits PDR report to BNL for approval of three Manifold Jumper Transfer Lines | 10 | 16-Jul-21* | 2021-07-29 | 0 | 0 | 0%
S313500 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - Physics Resource(s) | 5 | 2021-07-19 | 2021-07-23 | 2351 | 2282 | 0%
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 5 | 2021-07-19 | 2021-07-23 | 8418 | 8173 | 0%
S176100 | Fabricate final blocks sector 44 | 6 | 2021-07-19 | 2021-07-26 | 5163 | 5163 | 0%
S339800 | Review IR HVAC Design/Safety | 5 | 2021-07-20 | 2021-07-26 | 4434 | 1971 | 0%
S340900 | Review IR Electronics cooling water System Design/Safety | 10 | 2021-07-20 | 2021-08-02 | 3334 | 3334 | 0%
S354500 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - Labor | 60 | 2021-07-21 | 2021-10-14 | 23007 | 22237 | 0%
S354600 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - M&S | 60 | 21-Jul-21* | 2021-10-14 | 93133 | 91034 | 0%
S129700 | TPC R2 GEM Modules Production Ends | 0 |  | 2021-07-22 | 0 | 0 | 0%
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 10 | 2021-07-23 | 2021-08-05 | 4914 | 4914 | 0%
S313600 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 5 | 2021-07-26 | 2021-07-30 | 2351 | 2282 | 0%
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 5 | 2021-07-26 | 2021-07-30 | 11922 | 11574 | 0%
S298200 | (Cryo Controls Hardware procurement) Switch, 480 VAC Labor | 25 | 2021-07-26 | 2021-08-27 | 652 | 633 | 0%
S298300 | (Cryo Controls Hardware procurement) Switch, 480 VAC M&S | 25 | 2021-07-26 | 2021-08-27 | 1416 | 1388 | 0%
S176200 | Fabricate final blocks sector 45 | 6 | 2021-07-27 | 2021-08-03 | 5163 | 5163 | 0%
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | 10 | 2021-07-27 | 2021-08-09 | 3941 | 3941 | 0%
S155500 | Install TPC Cooling System tanks | 3 | 2021-07-29 | 2021-08-02 | 2821 | 2739 | 0%
S317091 | Review Design and Safety Beampipe Supports | 5 | 2021-07-29 | 2021-08-04 | 5212 | 4813 | 0%
S328850 | Evaluate & Process Line Electric Power Distribution Components Bid | 60 | 2021-07-29 | 2021-10-22 | 5251 | 5212 | 0%
S328800 | Procure Line Electric Power Distribution Components - Vendor Responses and Selection | 60 | 2021-07-29 | 2021-10-22 | 0 | 0 | 0%
S352900 | Design/Safety Reviews Complete, sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Ready for Service | 0 |  | 2021-07-29 | 0 | 0 | 0%
S353000 | Ready to Install SC Magnet | 0 |  | 2021-07-29 | 0 | 0 | 0%
S233000 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Contract Award(s) | 0 | 2021-07-30 |  | 0 | 0 | 0%
S269502 | Procurement Readiness Review - DAQ Timing System | 1 | 2021-07-30 | 2021-07-30 | 3121 | 3030 | 0%
S317400 | Procure IHCal Support Tabs - Provide Requirements to Procurement | 5 | 2021-07-30 | 2021-08-05 | 4170 | 4048 | 0%
S1006320 | AET to procure long lead items | 5 | 2021-07-30 | 2021-08-05 | 0 | 0 | 0%
S1006680 | BNL review for PDR approval | 5 | 2021-07-30 | 2021-08-05 | 26200 | 26200 | 0%
S1006360 | AET submits IDR to BNL for approval | 10 | 2021-07-30 | 2021-08-12 | 0 | 0 | 0%
S233100 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Contract/PO - Leadtime | 100 | 2021-07-30 | 2021-12-23 | 0 | 0 | 0%
S233250 | Trunk Signal Cables - EMCal | 100 | 2021-07-30 | 2021-12-23 | 786556 | 777844 | 0%
S244450 | Trunk Signal Cables - OuterHCal | 100 | 2021-07-30 | 2021-12-23 | 150983 | 149310 | 0%
S331000 | Design/Safety Reviews Complete, Detector Electronics Racks and Rack generic support systems Components Released for Prod | 0 |  | 2021-07-30 | 0 | 0 | 0%
S267400 | Procure Production GL1 Components - Contract Award(s) | 0 | 2021-08-02 |  | 0 | 0 | 0%
S269501 | Final Design Review - DAQ Timing System | 1 | 2021-08-02 | 2021-08-02 | 3121 | 3030 | 0%
S112100 | Benchtest TPC v2 Field Cage | 5 | 2021-08-02 | 2021-08-06 | 1316 | 1277 | 0%
S258700 | Procure DAQ Production jSEB Slow control computers - Delivery Acceptance | 5 | 2021-08-02 | 2021-08-06 | 19564 | 19181 | 0%
S263600 | Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance | 5 | 2021-08-02 | 2021-08-06 | 69641 | 69641 | 0%
S313700 | CC Seismic Restraints - Prepare Procurement Package - Physics Resource(s) | 5 | 2021-08-02 | 2021-08-06 | 2351 | 2282 | 0%
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 5 | 2021-08-02 | 2021-08-06 | 6786 | 6588 | 0%
S269600 | Update design specifications; incorporate final design choice | 10 | 2021-08-02 | 2021-08-13 | 2127 | 2065 | 0%
S332900 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - CA-D Resource(s) | 25 | 2021-08-02 | 2021-09-03 | 1820 | 1820 | 0%
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | 25 | 2021-08-02 | 2021-09-03 | 10102 | 10102 | 0%
S267500 | Procure Production GL1 Components - Contract/PO - Leadtime | 30 | 2021-08-02 | 2021-09-13 | 0 | 0 | 0%
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 30 | 2021-08-02 | 2021-09-13 | 19194 | 19194 | 0%
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | 40 | 2021-08-02 | 2021-09-27 | 12975 | 12975 | 0%
S266900 | GL1 Production: final firmware updates | 60 | 2021-08-02 | 2021-10-26 | 64795 | 62378 | 0%
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 60 | 2021-08-02 | 2021-10-26 | 6960 | 6901 | 0%
S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - M&S | 60 | 2021-08-02 | 2021-10-26 | 11673 | 11607 | 0%
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | 60 | 2021-08-02 | 2021-10-26 | 11549 | 11452 | 0%
S362200 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - M&S | 60 | 2021-08-02 | 2021-10-26 | 35018 | 34821 | 0%
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 60 | 2021-08-02 | 2021-10-26 | 13920 | 13803 | 0%
S364500 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - M&S | 60 | 2021-08-02 | 2021-10-26 | 35018 | 34821 | 0%
S343847 | Addition of ReBar plus Concrete Forming and Placement for IR Tracks - Leadtime | 96 | 02-Aug-21* | 2021-12-20 | 0 | 0 | 0%
S252800 | Procure Production Digitizer (Boards) - Delivery Acceptance | 5 | 2021-08-03 | 2021-08-09 | 149785 | 149785 | 0%
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 10 | 2021-08-03 | 2021-08-16 | 3031 | 3031 | 0%
S155600 | Install TPC Cooling System plumbing Labor | 30 | 2021-08-03 | 2021-09-14 | 28211 | 27453 | 0%
S329460 | Design Package for Detector Cooling System | 30 | 2021-08-03 | 2021-09-15 | 43848 | 43848 | 0%
S176300 | Fabricate final blocks sector 46 | 6 | 2021-08-04 | 2021-08-11 | 5163 | 5163 | 0%
S148500 | Test Full TPC DAM System | 90 | 2021-08-04 | 2021-12-14 | 227266 | 224141 | 0%
S294510 | Completed - Procure Warm Piping and fittings - Delivery acceptance | 0 |  | 2021-08-04 | 0 | 0 | 0%
S317092 | Address Action Items for Beampipe Supports | 2 | 2021-08-05 | 2021-08-06 | 1042 | 1042 | 0%
S332750 | Design/Safety Reviews complete (MS) for Detector Gas Service Systems | 0 |  | 2021-08-05 | 0 | 0 | 0%
S317500 | Procure IHCal Support Tabs - Prepare and Send Solicitation | 5 | 2021-08-06 | 2021-08-12 | 0 | 0 | 0%
S1006720 | AET submits IDR to BNL for approval | 5 | 2021-08-06 | 2021-08-12 | 0 | 0 | 0%
S318120 | Perform Magnet Supports Acceptance | 10 | 2021-08-06 | 2021-08-19 | 4957 | 4957 | 0%
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 90 | 2021-08-06 | 2021-12-16 | 13544 | 13317 | 0%
S317093 | Beampipe Supports Released for Production (Milestone) | 0 |  | 2021-08-06 | 0 | 0 | 0%
S258800 | Production jSEB Slow control computers - Setup Machines | 5 | 2021-08-09 | 2021-08-13 | 7091 | 6884 | 0%
S313800 | CC Seismic Restraints - Procurement Readiness Review - Physics Resource(s) | 5 | 2021-08-09 | 2021-08-13 | 2351 | 2282 | 0%
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 5 | 2021-08-09 | 2021-08-13 | 6786 | 6588 | 0%
S317041 | Review Design and Safety TPC Supports | 5 | 2021-08-09 | 2021-08-13 | 2085 | 2085 | 0%
S317190 | Prepare Procurement Package for Beampipe Supports | 10 | 2021-08-09 | 2021-08-20 | 15126 | 15126 | 0%
S263700 | Trigger LL1 Preproduction Prototype: Test trigger systems | 15 | 2021-08-09 | 2021-08-27 | 0 | 0 | 0%
S340000 | Design/Safety Reviews Complete, IR HVAC Components Released for Production | 0 |  | 2021-08-09 | 0 | 0 | 0%
S340100 | Prepare IR HVAC Components Procurement Package(s) | 20 | 2021-08-10 | 2021-09-07 | 6062 | 6062 | 0%
S252600 | Procure Production Digitizer - Contract/PO - Leadtime for Assembly & Tests | 55 | 2021-08-10 | 2021-10-27 | 0 | 0 | 0%
S176400 | Fabricate final blocks sector 47 | 6 | 2021-08-12 | 2021-08-19 | 5163 | 5163 | 0%
S317062 | Address Action Items for MVTX Supports | 2 | 2021-08-13 | 2021-08-16 | 2085 | 2085 | 0%
S317600 | Procure IHCal Support Tabs - Vendor Response and Selection | 5 | 2021-08-13 | 2021-08-19 | 4170 | 4048 | 0%
S317051 | Review Design and Safety INTT Supports | 5 | 2021-08-13 | 2021-08-19 | 6255 | 5744 | 0%
S1006400 | BNL review for IDR approval | 5 | 2021-08-13 | 2021-08-19 | 34933 | 34933 | 0%
S1006760 | BNL review for IDR approval | 5 | 2021-08-13 | 2021-08-19 | 26200 | 26200 | 0%
S343100 | Review Assembly Hall Modifications Design/Safety | 10 | 2021-08-13 | 2021-08-26 | 3486 | 3486 | 0%
S270100 | Timing System Production (FPGA Boards) - Contract Award(s) | 0 | 2021-08-16 |  | 0 | 0 | 0%
S317042 | Address Action Items for TPC Supports | 2 | 2021-08-16 | 2021-08-17 | 2085 | 2085 | 0%
S112200 | TPC Field Cage Safety Review | 3 | 2021-08-16 | 2021-08-18 | 1316 | 1277 | 0%
S313900 | CC Seismic Restraints - Provide Requirement to Procurement | 5 | 2021-08-16 | 2021-08-20 | 1401 | 1361 | 0%
S199310 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 2 | 5 | 16-Aug-21* | 2021-08-20 | 264958 | 264958 | 0%
S270200 | Timing System Production (FPGA Boards) - Contract/PO) - Leadtime | 50 | 2021-08-16 | 2021-10-26 | 0 | 0 | 0%
S341100 | Design/Safety Reviews Complete, IR Electronics Cooling Water Distribution System Components Released for Production | 0 |  | 2021-08-16 | 0 | 0 | 0%
S317063 | MVTX Supports Released for Production (Milestone) | 0 |  | 2021-08-16 | 0 | 0 | 0%
S150600 | Install & Test TPC lasers | 3 | 2021-08-17 | 2021-08-19 | 2821 | 2739 | 0%
S317160 | Prepare Procurement Package for MVTX Supports | 10 | 2021-08-17 | 2021-08-30 | 7563 | 7563 | 0%
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 20 | 2021-08-17 | 2021-09-14 | 6062 | 6062 | 0%
S291100 | (LN2 supply transfer line system) Final assemblies | 30 | 2021-08-17 | 2021-09-28 | 0 | 0 | 0%
S317043 | TPC Supports Released for Production (Milestone) | 0 |  | 2021-08-17 | 0 | 0 | 0%
S317140 | Prepare Procurement Package for TPC Supports | 20 | 2021-08-18 | 2021-09-15 | 15126 | 15126 | 0%
S112300 | Final Design Review - TPC Field Cage | 3 | 2021-08-19 | 2021-08-23 | 1316 | 1277 | 0%
S317700 | Procure IHCal Support Tabs - Contract Award | 0 | 2021-08-20 |  | 0 | 0 | 0%
S317052 | Address Action Items for INTT Supports | 2 | 2021-08-20 | 2021-08-23 | 2085 | 2085 | 0%
S176500 | Fabricate final blocks sector 48 | 6 | 2021-08-20 | 2021-08-27 | 5163 | 5163 | 0%
S150700 | Install &Test TPC Laser safety interlocks Labor | 8 | 2021-08-20 | 2021-08-31 | 21053 | 20440 | 0%
S150900 | Install &Test TPC Laser optics with mounts | 8 | 2021-08-20 | 2021-08-31 | 7523 | 7304 | 0%
S150800 | Install &Test TPC Laser safety interlocks M&S | 8 | 2021-08-20 | 2021-08-31 | 2321 | 2276 | 0%
S1006800 | AET submits FDR report to BNL for approval | 10 | 2021-08-20 | 2021-09-02 | 104800 | 104800 | 0%
S1006440 | AET submits FDR report to BNL for approval | 20 | 2021-08-20 | 2021-09-17 | 139734 | 139734 | 0%
S317800 | Procure IHCal Support Tabs - Leadtime | 48 | 2021-08-20 | 2021-10-28 | 0 | 0 | 0%
S314000 | CC Seismic Restraints - Prepare & Send Solicitation | 5 | 2021-08-23 | 2021-08-27 | 0 | 0 | 0%
S317290 | Evaluate and Process Bid for Beampipe Supports | 20 | 2021-08-23 | 2021-09-20 | 5212 | 5212 | 0%
S317053 | INTT Supports Released for Production (Milestone) | 0 |  | 2021-08-23 | 0 | 0 | 0%
S121600 | Production Readiness Review for TPC Final Assembly | 1 | 2021-08-24 | 2021-08-24 | 0 | 0 | 0%
S317150 | Prepare Procurement Package for INTT Supports | 10 | 2021-08-24 | 2021-09-07 | 7563 | 7563 | 0%
S121601 | Final Design Review and Production Readiness Review - TPC Final Assembly | 0 |  | 2021-08-24 | 0 | 0 | 0%
S153000 | Procure TPC Gas System Computer Controller M&S | 35 | 2021-08-25 | 2021-10-14 | 21468 | 20975 | 0%
S121610 | Install TPC Modules into Field Cage | 36 | 25-Aug-21* | 2021-10-15 | 0 | 0 | 0%
S325400 | End Caps/ Pole Tips - Delivery Acceptance | 0 | 2021-08-26 | 2021-08-26 | 993188 | 993188 | 0%
S325410 | Completed - End Caps/ Pole Tips - Delivery Acceptance | 0 |  | 2021-08-26 | 0 | 0 | 0%
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | 10 | 2021-08-26 | 2021-09-09 | 9874 | 9874 | 0%
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 10 | 2021-08-26 | 2021-09-09 | 19365 | 19365 | 0%
S318180 | Perform Large Support Rings Acceptance | 10 | 2021-08-26 | 2021-09-09 | 14616 | 14616 | 0%
S317071 | Review Design and Safety MBD Supports | 2 | 2021-08-27 | 2021-08-30 | 1042 | 1042 | 0%
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 10 | 2021-08-27 | 2021-09-10 | 3486 | 3486 | 0%
S335200 | Review Rack Room Modifications Components Design/Safety | 10 | 2021-08-27 | 2021-09-10 | 2632 | 2711 | 0%
S263800 | Final Design Review - DAQ Local Level-1 | 4 | 2021-08-30 | 2021-09-02 | 5673 | 5673 | 0%
S176600 | Fabricate final blocks sector 49 | 6 | 2021-08-30 | 2021-09-07 | 5163 | 5163 | 0%
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | 20 | 2021-08-30 | 2021-09-27 | 39167 | 38027 | 0%
S314100 | CC Seismic Restraints - Vendor Responses - Physics Resource(s) | 30 | 2021-08-30 | 2021-10-12 | 2131 | 2054 | 0%
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 30 | 2021-08-30 | 2021-10-12 | 6291 | 6065 | 0%
S292610 | Completed - (Warm Piping System) Mechanical Engineering Tasks | 0 |  | 2021-08-30 | 0 | 0 | 0%
S316010 | Completed - Steel Track Modifications | 0 |  | 2021-08-30 | 0 | 0 | 0%
S317072 | Address Action Items for MBD Supports | 2 | 2021-08-31 | 2021-09-01 | 1042 | 1042 | 0%
S317260 | Evaluate and Process Bid for MVTX Supports | 20 | 2021-08-31 | 2021-09-28 | 5212 | 5212 | 0%
S343842 | Start Track Modification - IR BNL Oversight of Construction | 29 | 2021-08-31 | 2021-10-12 | 17247 | 17197 | 0%
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | 90 | 2021-08-31 | 2022-01-12 | 94083 | 91998 | 0%
S147600 | TPC DAM Felix 2.0 Production Complete | 0 |  | 2021-08-31 | 0 | 0 | 0%
S151000 | Install &Test TPC mirror bundles and supports | 3 | 2021-09-01 | 2021-09-03 | 2821 | 2739 | 0%
S332000 | Address Action Items from Detector Gas and Cooling Services Systems Design & Safety Reviews | 10 | 2021-09-01 | 2021-09-15 | 6795 | 6795 | 0%
S274320 | RHIC FY22 Run | 81 | 01-Sep-21* | 2021-12-30 | 0 | 0 | 0%
S317073 | MBD Supports Released for Production (Milestone) | 0 |  | 2021-09-01 | 0 | 0 | 0%
S317170 | Prepare Procurement Package for MBD Supports | 10 | 2021-09-02 | 2021-09-16 | 3782 | 3782 | 0%
S308617 | Calibrate probes | 60 | 2021-09-02 | 2021-12-01 | 11783 | 11552 | 0%
S263900 | Trigger LL1 Preproduction complete | 0 |  | 2021-09-02 | 0 | 0 | 0%
S1006840 | AET begins material procurement | 5 | 2021-09-03 | 2021-09-10 | 0 | 0 | 0%
S264000 | Trigger LL1 Production: Updates to trigger board: Production | 17 | 2021-09-03 | 2021-09-28 | 0 | 0 | 0%
S151100 | TPC Laser System Complete | 0 |  | 2021-09-03 | 0 | 0 | 0%
S350910 | Completed - Install Partial Outer HCal (Prior to SC Magnet Install) | 0 |  | 2021-09-03 | 0 | 0 | 0%
S349100 | Install magnet mounting feet - Labor - CA-D Resource(s) | 10 | 2021-09-07 | 2021-09-20 | 607 | 607 | 0%
S349200 | Install magnet mounting feet - M&S | 10 | 2021-09-07 | 2021-09-20 | 3482 | 3482 | 0%
S333000 | Review Detector Safety Subsystems Design/Safety - CA-D Resource(s) | 10 | 2021-09-07 | 2021-09-20 | 1213 | 1213 | 0%
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | 10 | 2021-09-07 | 2021-09-20 | 21265 | 21265 | 0%
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | 10 | 2021-09-07 | 2021-09-20 | 3367 | 3367 | 0%
S176700 | Fabricate final blocks sector 50 | 6 | 2021-09-08 | 2021-09-15 | 5163 | 5163 | 0%
S340200 | Evaluate & Process IR HVAC Components Bids | 20 | 2021-09-08 | 2021-10-05 | 6089 | 6062 | 0%
S317250 | Evaluate and Process Bid for INTT Supports | 20 | 2021-09-08 | 2021-10-05 | 5236 | 5212 | 0%
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 15 | 2021-09-09 | 2021-09-29 | 75959 | 73747 | 0%
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | 15 | 2021-09-09 | 2021-09-29 | 40019 | 38853 | 0%
S325600 | End Caps/ Pole Tips - Ready for Installation | 0 |  | 2021-09-09 | 0 | 0 | 0%
S318182 | Assemble Large Support Rings | 15 | 2021-09-10 | 2021-09-30 | 20683 | 20683 | 0%
S343300 | Design/Safety Reviews Complete, Assembly Hall Modifications Components Released for Production | 0 |  | 2021-09-10 | 0 | 0 | 0%
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 10 | 2021-09-13 | 2021-09-24 | 6393 | 6585 | 0%
S1006880 | Fabricate all three Manifold Jumper Transfer Lines | 20 | 2021-09-13 | 2021-10-08 | 0 | 0 | 0%
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 30 | 2021-09-13 | 2021-10-25 | 15490 | 15246 | 0%
S267600 | Procure Production GL1 Components - final hardware - Delivery Acceptance | 5 | 2021-09-14 | 2021-09-20 | 32673 | 32673 | 0%
S342000 | Review IR/AH Safety Subsystems Design/Safety | 10 | 2021-09-14 | 2021-09-27 | 5593 | 5593 | 0%
S155700 | Procure TPC Plumbing - Contract/PO M&S | 20 | 2021-09-15 | 2021-10-13 | 13650 | 13542 | 0%
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 20 | 2021-09-15 | 2021-10-13 | 6135 | 6062 | 0%
S329600 | Review Detector Support Services Systems Design/Safety - CA-D Resource(s) | 12 | 2021-09-15 | 2021-10-01 | 3037 | 3034 | 0%
S1002399 | Review Detector Support Services Systems Design/Safety - Physics Resource(s) | 12 | 2021-09-15 | 2021-10-01 | 2157 | 1983 | 0%
S332100 | Design/Safety Reviews Complete, Detector Gas and Cooling Services Systems Components Released for Production | 0 |  | 2021-09-15 | 0 | 0 | 0%
S176800 | Fabricate final blocks sector 51 | 6 | 2021-09-16 | 2021-09-23 | 5163 | 5163 | 0%
S317240 | Evaluate and Process Bid for TPC Supports | 20 | 2021-09-16 | 2021-10-14 | 5283 | 5212 | 0%
S332200 | Prepare Detector Gas and Cooling Services Systems Components Procurement Package(s) | 50 | 2021-09-16 | 2021-11-30 | 13629 | 13317 | 0%
S317270 | Evaluate and Process Bid for MBD Supports | 20 | 2021-09-17 | 2021-10-15 | 2645 | 2606 | 0%
S1006480 | AET begins material procurement | 5 | 2021-09-20 | 2021-09-24 | 0 | 0 | 0%
S125700 | TPC R1 GEM Modules Production Ends | 0 |  | 2021-09-20 | 0 | 0 | 0%
S300910 | Completed - (Cryo Controls Hardware) Built HMI operator screens | 0 |  | 2021-09-20 | 0 | 0 | 0%
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | 2 | 2021-09-21 | 2021-09-22 | 6659 | 6659 | 0%
S353200 | Transport SC Magnet from 912 to AH - M&S | 2 | 2021-09-21 | 2021-09-22 | 1741 | 1741 | 0%
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | 2 | 2021-09-21 | 2021-09-22 | 13099 | 13099 | 0%
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | 10 | 2021-09-21 | 2021-10-04 | 3387 | 3367 | 0%
S317990 | Procure Beampipe Supports - M&S | 20 | 2021-09-21 | 2021-10-19 | 29365 | 29017 | 0%
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | 2 | 2021-09-23 | 2021-09-24 | 6423 | 6423 | 0%
S353400 | Install SC Magnet on Cradle - M&S | 2 | 2021-09-23 | 2021-09-24 | 1741 | 1741 | 0%
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | 2 | 2021-09-23 | 2021-09-24 | 13099 | 13099 | 0%
S199320 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 3 | 5 | 24-Sep-21* | 2021-09-30 | 264958 | 264958 | 0%
S176900 | Fabricate final blocks sector 52 | 6 | 2021-09-24 | 2021-10-01 | 5189 | 5163 | 0%
S353410 | Completed - Install SC Magnet on Cradle | 0 |  | 2021-09-24 | 0 | 0 | 0%
S335400 | Design/Safety Reviews Complete, Rack Room Modifications Components Released for Production | 0 |  | 2021-09-24 | 0 | 0 | 0%
S353500 | Align/Survey SC Magnet to Cradle - Labor - Physics Resource(s) | 10 | 2021-09-27 | 2021-10-08 | 9573 | 9404 | 0%
S353600 | Align/Survey SC Magnet to Cradle - M&S | 10 | 2021-09-27 | 2021-10-08 | 4111 | 4062 | 0%
S353510 | Align/Survey SC Magnet to Cradle - Labor - CA-D Resource(s) | 10 | 2021-09-27 | 2021-10-08 | 49702 | 48823 | 0%
S336100 | Analyze Control Room and Offices Modifications Requirements - CA-D Resource(s) | 10 | 2021-09-27 | 2021-10-08 | 618 | 625 | 0%
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 10 | 2021-09-27 | 2021-10-08 | 5551 | 5616 | 0%
S335500 | Prepare Rack Room Modifications Components Procurement Package(s) - CA-D Resource(s) | 30 | 2021-09-27 | 2021-11-08 | 311 | 312 | 0%
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 30 | 2021-09-27 | 2021-11-08 | 9524 | 9561 | 0%
S1006520 | Fabricate the IP8 Cold Box Assembly | 60 | 2021-09-27 | 2021-12-23 | 0 | 0 | 0%
S299700 | (Cryo Controls Hardware) Rack install | 5 | 2021-09-28 | 2021-10-04 | 2074 | 1990 | 0%
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 10 | 2021-09-28 | 2021-10-12 | 5091 | 4986 | 0%
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | 40 | 2021-09-28 | 2021-11-24 | 31307 | 30462 | 0%
S291200 | (LN2 supply transfer line system) BNL Holdpoint witness | 1 | 2021-09-29 | 2021-09-29 | 0 | 0 | 0%
S143200 | Procure TPC FEE Production Boards & Assembly - Delivery Acceptance | 5 | 2021-09-29 | 2021-10-05 | 177347 | 175244 | 0%
S264100 | Trigger LL1 Production: final updates to trigger crate requirements | 10 | 2021-09-29 | 2021-10-13 | 0 | 0 | 0%
S291210 | Completed - (LN2 supply transfer line system) BNL Holdpoint witness | 0 |  | 2021-09-29 | 0 | 0 | 0%
S303310 | Completed - Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | 0 |  | 2021-09-29 | 0 | 0 | 0%
S308631 | Review mapping plan | 5 | 2021-09-30 | 2021-10-06 | 6583 | 6429 | 0%
S291400 | Procure LN2 supply transfer line system - Phase 5 - Shipping - Leadtime | 10 | 2021-09-30 | 2021-10-14 | 0 | 0 | 0%
S291300 | (LN2 supply transfer line system) Shipping Labor | 13 | 2021-09-30 | 2021-10-19 | 0 | 0 | 0%
S317960 | Procure MVTX Supports - M&S | 40 | 2021-09-30 | 2021-11-30 | 59166 | 58034 | 0%
S308627 | Place contract with Vendor (Procurement string, $70K obligated at Contract award, paid when mapped?) | 100 | 2021-09-30 | 2022-02-28 | 74571 | 73123 | 0%
S101016 | FY22 funding available | 0 | 01-Oct-21* |  | 0 | 0 | 0%
S103400 | Mgmt labor - A - MIE - FY22 | 63 | 01-Oct-21* | 2022-01-05 | 11361 | 11361 | 0%
S103510 | Mgmt labor - B - BNL Contributed Labor - FY22 - CA-D Resource(s) | 63 | 01-Oct-21* | 2022-01-05 | 6351 | 6351 | 0%
S103500 | Mgmt labor - B - BNL Contributed Labor - FY22 - Physics Resource(s) | 63 | 01-Oct-21* | 2022-01-05 | 65205 | 65205 | 0%
S274800 | 2022 Magnet Project Management | 250 | 2021-10-01 | 2022-09-30 | 160676 | 160676 | 0%
S275900 | 2022 PS & Quench Protection L3 Project Management | 250 | 2021-10-01 | 2022-09-30 | 63508 | 63508 | 0%
S278200 | 2022 Integration & Installation Project Management | 250 | 2021-10-01 | 2022-09-30 | 158770 | 158770 | 0%
S276400 | 2022 Infrastructure Project Management | 250 | 2021-10-01 | 2022-09-30 | 107371 | 107371 | 0%
S277000 | 2022 Facility Support Systems L3 Project Management | 250 | 2021-10-01 | 2022-09-30 | 37426 | 37426 | 0%
S277600 | 2022 Detector Support Systems L3 Project Management | 250 | 01-Oct-21* | 2022-09-30 | 63508 | 47243 | 0%
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | 12 | 2021-10-01 | 2021-10-20 | 15935 | 14616 | 0%
S177000 | Fabricate final blocks sector 53 | 6 | 2021-10-04 | 2021-10-12 | 5318 | 5163 | 0%
S333200 | Design/Safety Reviews Complete, Detector Safety Subsystems Components Released for Production | 0 |  | 2021-10-04 | 0 | 0 | 0%
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | 10 | 2021-10-05 | 2021-10-19 | 2218 | 2154 | 0%
S299800 | (Cryo Controls Hardware) Cable pulling | 50 | 2021-10-05 | 2021-12-17 | 26199 | 25332 | 0%
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | 60 | 2021-10-06 | 2022-01-05 | 16857 | 16366 | 0%
S339500 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - M&S | 60 | 2021-10-06 | 2022-01-05 | 41436 | 40624 | 0%
S143300 | Perform QA Testing on TPC FEE | 69 | 2021-10-06 | 2022-01-19 | 88065 | 85500 | 0%
S317950 | Procure INTT Supports - M&S | 40 | 2021-10-07 | 2021-12-07 | 59195 | 58034 | 0%
S336200 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents C | 5 | 2021-10-12 | 2021-10-18 | 312 | 312 | 0%
S350950 | Install Large Support Rings and Cross Braces | 5 | 2021-10-12 | 2021-10-18 | 11092 | 10898 | 0%
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | 5 | 2021-10-12 | 2021-10-18 | 1594 | 1594 | 0%
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | 20 | 2021-10-12 | 2021-11-08 | 6374 | 6346 | 0%
S353800 | Prep SC Magnet for Run (Cryo) - M&S | 20 | 2021-10-12 | 2021-11-08 | 4144 | 4131 | 0%
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | 20 | 2021-10-12 | 2021-11-08 | 48268 | 48057 | 0%
S281400 | Magnet and Solenoid Valvebox - Reinstall | 25 | 2021-10-12 | 2021-11-16 | 54678 | 54487 | 0%
S1006920 | Delivery of all three Manifold Jumper Transfer Lines and Document package | 30 | 12-Oct-21* | 2021-11-23 | 0 | 0 | 0%
S342200 | Design/Safety Reviews Complete, IR/AH Safety Subsystems Components Released for Production | 0 |  | 2021-10-12 | 0 | 0 | 0%
S343844 | Start Track Modification - IR Delivery Acceptance Labor | 5 | 2021-10-13 | 2021-10-19 | 3397 | 3202 | 0%
S343845 | Start Track Modification - IR Delivery Acceptance M&S Outside BOA contractor | 5 | 2021-10-13 | 2021-10-19 | 165746 | 162496 | 0%
S177100 | Fabricate final blocks sector 54 | 6 | 2021-10-13 | 2021-10-20 | 5318 | 5163 | 0%
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 10 | 2021-10-13 | 2021-10-26 | 3434 | 3334 | 0%
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | 30 | 2021-10-13 | 2021-11-24 | 6538 | 6163 | 0%
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 30 | 2021-10-13 | 2021-11-24 | 6435 | 6065 | 0%
S155800 | Set up TPC Cooling System computer controls Labor | 5 | 2021-10-14 | 2021-10-20 | 4843 | 4702 | 0%
S155900 | Set up TPC Cooling System computer controls M&S | 5 | 2021-10-14 | 2021-10-20 | 12423 | 12179 | 0%
S264200 | Production Readiness Review - DAQ Local Level-1 | 10 | 2021-10-14 | 2021-10-27 | 5843 | 5673 | 0%
S121700 | Install TPC Electronics | 10 | 2021-10-18 | 2021-10-29 | 19372 | 18807 | 0%
S317970 | Procure MBD Supports - M&S | 20 | 2021-10-18 | 2021-11-15 | 11839 | 11607 | 0%
S317940 | Procure TPC Supports - M&S | 40 | 2021-10-18 | 2021-12-15 | 59195 | 58034 | 0%
S336300 | Review Control Room and Offices Modifications Design/Safety | 5 | 2021-10-19 | 2021-10-25 | 1355 | 1355 | 0%
S351000 | Transport Remainder of Outer Hcal Sectors to AH - Labor - CA-D Resource(s) | 10 | 2021-10-19 | 2021-11-01 | 851 | 851 | 0%
S351100 | Transport Remainder of Outer Hcal Sectors to AH - M&S | 10 | 2021-10-19 | 2021-11-01 | 592 | 592 | 0%
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 10 | 2021-10-19 | 2021-11-01 | 51684 | 51684 | 0%
S343846 | Start Track Modification - IR Complete | 0 |  | 2021-10-19 | 0 | 0 | 0%
S291500 | Procure LN2 supply transfer line system - Phase 5 - Shipping - Delivery Acceptance | 0 | 20-Oct-21* | 2021-10-20 | 119662 | 119662 | 0%
S291510 | Completed - Procure LN2 supply transfer line system - Phase 5 - Shipping - Delivery Acceptance | 0 |  | 2021-10-20 | 0 | 0 | 0%
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | 1 | 2021-10-20 | 2021-10-20 | 2794 | 2713 | 0%
S147370 | Procure TPC DAM Felix 2.0 Optical Components - Contract/PO - Delivery Acceptance | 5 | 2021-10-20 | 2021-10-26 | 95594 | 93719 | 0%
S318190 | Perform Beampipe Supports Acceptance | 10 | 2021-10-20 | 2021-11-02 | 10211 | 9914 | 0%
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | 30 | 2021-10-20 | 2021-12-03 | 6655 | 6461 | 0%
S329800 | Design/Safety Reviews Complete, Detector Support Services Systems Components Released for Production | 0 |  | 2021-10-20 | 0 | 0 | 0%
S329900 | Prepare Detector Support Services Systems Components Procurement Package(s) - CA-D Resource(s) | 20 | 2021-10-20 | 2021-11-18 | 3125 | 3034 | 0%
S1002479 | Prepare Detector Support Services Systems Components Procurement Package(s) - Physics Resource(s) | 20 | 2021-10-20 | 2021-11-18 | 20423 | 19828 | 0%
S291700 | (LN2 supply transfer line system) Inspection | 1 | 2021-10-21 | 2021-10-21 | 205 | 199 | 0%
S156000 | Set up and Test TPC Cooling System & Interlocks | 5 | 2021-10-21 | 2021-10-27 | 4843 | 4702 | 0%
S177200 | Fabricate final blocks sector 55 | 6 | 2021-10-21 | 2021-10-28 | 5318 | 5163 | 0%
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 10 | 2021-10-22 | 2021-11-04 | 33328 | 32357 | 0%
S328900 | Procure Line Electric Power Distribution Components - Contract Award | 0 | 2021-10-25 |  | 0 | 0 | 0%
S329000 | Procure Line Electric Power Distribution Components - Leadtime | 60 | 2021-10-25 | 2022-01-24 | 0 | 0 | 0%
S255900 | Procure DAQ Production Boards - Delivery Acceptance | 5 | 2021-10-26 | 2021-11-01 | 123933 | 121503 | 0%
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 10 | 2021-10-26 | 2021-11-08 | 5616 | 5616 | 0%
S1006940 | Draft PDR of three Solenoid Valve Box Transfer Lines | 10 | 2021-10-26 | 2021-11-08 | 0 | 0 | 0%
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 20 | 2021-10-26 | 2021-11-23 | 69879 | 69879 | 0%
S351300 | Install Remainder of Outer HCal Sectors - M&S | 20 | 2021-10-26 | 2021-11-23 | 592 | 592 | 0%
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 20 | 2021-10-26 | 2021-11-23 | 143427 | 143427 | 0%
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 30 | 2021-10-26 | 2021-12-09 | 15391 | 14943 | 0%
S270300 | Timing System Production (FPGA Boards) - Delivery Acceptance | 5 | 2021-10-27 | 2021-11-02 | 49250 | 48284 | 0%
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 10 | 2021-10-27 | 2021-11-09 | 8671 | 8418 | 0%
S267900 | GL1 Production: install GL1 system | 25 | 2021-10-27 | 2021-12-03 | 49480 | 48039 | 0%
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 30 | 2021-10-27 | 2021-12-10 | 9054 | 8790 | 0%
S156100 | TPC Cooling System Complete | 0 |  | 2021-10-27 | 0 | 0 | 0%
S295610 | Completed - (Controls Hardware) Power distribution drawings | 0 |  | 2021-10-27 | 0 | 0 | 0%
S252900 | Procure Production Digitizer (Assembly & Tests) - Delivery Acceptance | 5 | 2021-10-28 | 2021-11-03 | 235687 | 231066 | 0%
S177300 | Fabricate final blocks sector 56 | 5 | 2021-10-29 | 2021-11-04 | 5318 | 5163 | 0%
S317900 | Procure IHCal Support Tabs - Delivery Acceptance | 5 | 2021-10-29 | 2021-11-04 | 54282 | 53217 | 0%
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 10 | 2021-10-29 | 2021-11-12 | 3187 | 3094 | 0%
S334100 | Review Gas Mixing House & Gas Pad Components Design/Safety - CA-D Resource(s) | 10 | 2021-10-29 | 2021-11-12 | 1250 | 1213 | 0%
S1003119 | Review Gas Mixing House & Gas Pad Components Design/Safety - Physics Resource(s) | 10 | 2021-10-29 | 2021-11-12 | 2218 | 2154 | 0%
S121800 | Test TPC Prior to Installation | 62 | 2021-11-01 | 2022-02-02 | 0 | 0 | 0%
S256000 | DAQ Production Boards: Firmware updates | 50 | 2021-11-02 | 2022-01-18 | 140531 | 136438 | 0%
S270600 | Timing System Production: install timing system | 25 | 2021-11-03 | 2021-12-10 | 56784 | 55130 | 0%
S270610 | Timing System Production: install timing system | 25 | 2021-11-03 | 2021-12-10 | 21474 | 20849 | 0%
S253000 | Calorimeter Digitizer Production Complete | 0 |  | 2021-11-03 | 0 | 0 | 0%
S264900 | Procure Production LL1 System - Delivery Acceptance | 5 | 2021-11-04 | 2021-11-10 | 138516 | 135800 | 0%
S292110 | Completed - (LN2 supply transfer line system) Rigging in place onto piping supports | 0 |  | 2021-11-04 | 0 | 0 | 0%
S317910 | Completed - Procure IHCal Structural Support - Delivery Acceptance | 0 |  | 2021-11-04 | 0 | 0 | 0%
S178800 | Pack and ship final blocks for sectors 49-56 to BNL - Purchased Services | 5 | 2021-11-05 | 2021-11-12 | 2638 | 2561 | 0%
S178910 | Pack and ship final blocks for sectors 49-56 to BNL - M&S | 5 | 2021-11-05 | 2021-11-12 | 7672 | 7521 | 0%
S177400 | Fabricate final blocks sector 57 | 5 | 2021-11-05 | 2021-11-12 | 5318 | 5163 | 0%
S292120 | Welding LN2 Segment #1 to LN2 Dewar | 10 | 2021-11-05 | 2021-11-19 | 10615 | 10306 | 0%
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | 15 | 2021-11-05 | 2021-11-30 | 14844 | 14412 | 0%
S318000 | Perform Inner HCal Support Tabs Acceptance - Physics Resource(s) | 25 | 2021-11-05 | 2021-12-14 | 3390 | 3291 | 0%
S318010 | Perform Inner HCal Support Tabs Acceptance - CA-D Resource(s) | 25 | 2021-11-05 | 2021-12-14 | 2500 | 2427 | 0%
S336500 | Design/Safety Reviews Complete, Control Room and Offices Modifications Components Released for Production | 0 |  | 2021-11-08 | 0 | 0 | 0%
S1006960 | AET submits PDR report to BNL for approval of three Solenoid Valve Box Transfer Lines | 10 | 09-Nov-21* | 2021-11-23 | 0 | 0 | 0%
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | 20 | 2021-11-09 | 2021-12-09 | 23808 | 23808 | 0%
S354000 | Prep SC Magnet for Run (Electric) - M&S | 20 | 2021-11-09 | 2021-12-09 | 4144 | 4144 | 0%
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | 20 | 2021-11-09 | 2021-12-09 | 28897 | 28897 | 0%
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 20 | 2021-11-09 | 2021-12-09 | 7343 | 7343 | 0%
S336600 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - CA-D Resource(s) | 30 | 2021-11-09 | 2021-12-23 | 312 | 312 | 0%
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 30 | 2021-11-09 | 2021-12-23 | 9561 | 9561 | 0%
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 10 | 2021-11-10 | 2021-11-24 | 3187 | 3094 | 0%
S265000 | Trigger LL1 Production: Program and commission trigger boards | 15 | 2021-11-12 | 2021-12-06 | 0 | 0 | 0%
S177500 | Fabricate final blocks sector 58 | 5 | 2021-11-15 | 2021-11-19 | 5318 | 5163 | 0%
S199330 | Manufacture Inner HCAL Support Structure - Delivery Acceptance 4 | 5 | 15-Nov-21* | 2021-11-19 | 264958 | 264958 | 0%
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 10 | 2021-11-15 | 2021-11-30 | 3187 | 3094 | 0%
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 10 | 2021-11-15 | 2021-11-30 | 3187 | 3094 | 0%
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | 10 | 2021-11-15 | 2021-11-30 | 2218 | 2154 | 0%
S318170 | Perform MBD Supports Acceptance | 10 | 2021-11-16 | 2021-12-01 | 2553 | 2479 | 0%
S281410 | Completed - Magnet and Solenoid Valvebox - Reinstall | 0 |  | 2021-11-16 | 0 | 0 | 0%
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | 10 | 2021-11-17 | 2021-12-02 | 21871 | 21871 | 0%
S330000 | Evaluate & Process Detector Support Services Systems Components Bids - CA-D Resource(s) | 20 | 2021-11-18 | 2021-12-20 | 1562 | 1517 | 0%
S1002559 | Evaluate & Process Detector Support Services Systems Components Bids - Physics Resource(s) | 20 | 2021-11-18 | 2021-12-20 | 4085 | 3966 | 0%
S200100 | Inner HCAL Support Structure Ready for Installation | 0 |  | 2021-11-19 | 0 | 0 | 0%
S177600 | Fabricate final blocks sector 59 | 5 | 2021-11-22 | 2021-11-30 | 5318 | 5163 | 0%
S351310 | Completed - Install Remainder of Outer HCal Sectors | 0 |  | 2021-11-23 | 0 | 0 | 0%
S256700 | Procure DAQ Production Crates - Delivery Acceptance | 5 | 2021-11-24 | 2021-12-02 | 75769 | 74284 | 0%
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | 5 | 2021-11-24 | 2021-12-02 | 2906 | 2906 | 0%
S351500 | Align/Survey Outer Hcal to Centerline - M&S | 5 | 2021-11-24 | 2021-12-02 | 592 | 592 | 0%
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | 5 | 2021-11-24 | 2021-12-02 | 17879 | 17879 | 0%
S1007000 | BNL review for PDR approval | 5 | 2021-11-24 | 2021-12-02 | 26200 | 26200 | 0%
S314300 | CC Seismic Restraints - Contract Award(s) | 0 | 2021-11-29 |  | 0 | 0 | 0%
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 10 | 2021-11-29 | 2021-12-10 | 3187 | 3094 | 0%
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 50 | 2021-11-29 | 2022-02-09 | 31376 | 31361 | 0%
S331400 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - M&S | 50 | 2021-11-29 | 2022-02-09 | 108919 | 108883 | 0%
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | 180 | 2021-11-30 | 2022-08-16 | 6054 | 5802 | 0%
S314500 | CC Seismic Restraints - Vendor Leadtime | 180 | 2021-11-30 | 2022-08-16 | 0 | 0 | 0%
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 180 | 2021-11-30 | 2022-08-16 | 9290 | 8905 | 0%
S364900 | Design/Safety Reviews Complete, MVTX Integration/Installation Tooling/Fixtures/Procedures Ready for Service | 0 |  | 2021-11-30 | 0 | 0 | 0%
S334300 | Design/Safety Reviews Complete, Gas Mixing House & Gas Pad Components Released for Production | 0 |  | 2021-11-30 | 0 | 0 | 0%
S153900 | Install and Test TPC Gas System Interlocks | 5 | 2021-12-01 | 2021-12-07 | 6249 | 6067 | 0%
S177700 | Fabricate final blocks sector 60 | 5 | 2021-12-01 | 2021-12-07 | 5318 | 5163 | 0%
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | 10 | 2021-12-01 | 2021-12-14 | 10433 | 10129 | 0%
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 10 | 2021-12-01 | 2021-12-14 | 3187 | 3094 | 0%
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 10 | 2021-12-01 | 2021-12-14 | 3187 | 3094 | 0%
S327100 | CC Bridge, Mid Platforms & Access - Delivery Acceptance | 10 | 01-Dec-21* | 2021-12-14 | 419903 | 372184 | 0%
S318160 | Perform MVTX Supports Acceptance | 10 | 2021-12-01 | 2021-12-14 | 5106 | 4957 | 0%
S334400 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - CA-D Resource(s) | 30 | 2021-12-01 | 2022-01-13 | 312 | 303 | 0%
S332300 | Evaluate & Process Detector Gas and Cooling Services Systems Components Bids | 30 | 2021-12-01 | 2022-01-13 | 6655 | 6461 | 0%
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 30 | 2021-12-01 | 2022-01-13 | 12467 | 12104 | 0%
S281600 | Magnet - Solenoid Valvebox - Complete, Ready for Cryo Connections | 0 |  | 2021-12-02 | 0 | 0 | 0%
S273500 | Procure Min/Bias Electronics (sPHENIX Production Digitizers) - Delivery Acceptance | 5 | 2021-12-03 | 2021-12-09 | 17486 | 17143 | 0%
S273600 | Procure MBD Shaper/Disc Board 128 Channels - Delivery Acceptance | 5 | 2021-12-03 | 2021-12-09 | 54957 | 53879 | 0%
S1007040 | AET submits IDR to BNL for approval | 5 | 2021-12-03 | 2021-12-09 | 0 | 0 | 0%
S351600 | Install Outer HCal Cables and Services - Labor | 20 | 2021-12-03 | 2022-01-03 | 41556 | 41556 | 0%
S351700 | Install Outer HCal Cables and Services - M&S | 20 | 2021-12-03 | 2022-01-03 | 592 | 592 | 0%
S268000 | GL1 Production: commission GL1 system | 30 | 2021-12-06 | 2022-01-19 | 27641 | 26836 | 0%
S268010 | GL1 Production: commission GL1 system Instr | 30 | 2021-12-06 | 2022-01-19 | 14495 | 14073 | 0%
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | 60 | 2021-12-06 | 2022-03-03 | 13311 | 13240 | 0%
S333600 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) - M&S | 60 | 2021-12-06 | 2022-03-03 | 14207 | 14156 | 0%
S265100 | Trigger LL1 Production: Assemble trigger system | 5 | 2021-12-07 | 2021-12-13 | 0 | 0 | 0%
S154000 | TPC Gas System Complete | 0 |  | 2021-12-07 | 0 | 0 | 0%
S177800 | Fabricate final blocks sector 61 | 5 | 2021-12-08 | 2021-12-14 | 5318 | 5163 | 0%
S318150 | Perform INTT Supports Acceptance | 10 | 2021-12-08 | 2021-12-21 | 5106 | 4957 | 0%
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 10 | 2021-12-09 | 2021-12-22 | 3187 | 3094 | 0%
S1007080 | BNL review for IDR approval | 5 | 2021-12-10 | 2021-12-16 | 26200 | 26200 | 0%
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 10 | 2021-12-10 | 2021-12-23 | 3187 | 3187 | 0%
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 10 | 2021-12-10 | 2021-12-23 | 3856 | 3856 | 0%
S273800 | Test Full Min/Bias Electronics | 25 | 2021-12-10 | 2022-01-18 | 10912 | 10594 | 0%
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 60 | 2021-12-10 | 2022-03-09 | 22028 | 22028 | 0%
S335800 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - M&S | 60 | 2021-12-10 | 2022-03-09 | 23678 | 23678 | 0%
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 90 | 2021-12-10 | 2022-04-20 | 26536 | 25763 | 0%
S342800 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - M&S | 90 | 2021-12-10 | 2022-04-20 | 11839 | 11607 | 0%
S362600 | Design/Safety Reviews Complete, INTT Integration/Installation Tooling/Fixtures/Procedures Ready for Service | 0 |  | 2021-12-10 | 0 | 0 | 0%
S270700 | Timing System Production: commission timing system | 20 | 2021-12-13 | 2022-01-11 | 66320 | 64388 | 0%
S270710 | Timing System Production: commission timing system | 20 | 2021-12-13 | 2022-01-11 | 25769 | 25019 | 0%
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 60 | 2021-12-13 | 2022-03-10 | 17170 | 16670 | 0%
S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - M&S | 60 | 2021-12-13 | 2022-03-10 | 37885 | 37142 | 0%
S265200 | Trigger LL1 Production: Commission trigger systems | 5 | 2021-12-14 | 2021-12-20 | 0 | 0 | 0%
S148600 | TPC DAM Production Complete | 0 |  | 2021-12-14 | 0 | 0 | 0%
S292310 | Completed - (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | 0 |  | 2021-12-14 | 0 | 0 | 0%
S368300 | Design/Safety Reviews Complete, Min Bias Integration/Installation Tooling/Fixtures/Procedures Ready for Service | 0 |  | 2021-12-14 | 0 | 0 | 0%
S355000 | Design/Safety Reviews Complete, Inner HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | 0 |  | 2021-12-14 | 0 | 0 | 0%
S355100 | Inner HCal Sectors Ready for Installation | 0 |  | 2021-12-14 | 0 | 0 | 0%
S318100 | Inner HCal Support Tabs Components Ready for Installation | 0 |  | 2021-12-14 | 0 | 0 | 0%
S327300 | CC Bridge, Mid Platforms & Access - Ready for Installation | 0 |  | 2021-12-14 | 0 | 0 | 0%
S327110 | Completed - CC Bridge, Mid Platforms & Access - Delivery Acceptance | 0 |  | 2021-12-14 | 0 | 0 | 0%
S355400 | Install Inner Hcal Assembly Insertion Fixture - Labor | 4 | 2021-12-15 | 2021-12-20 | 10795 | 10481 | 0%
S355500 | Install Inner Hcal Assembly Insertion Fixture - M&S | 4 | 2021-12-15 | 2021-12-20 | 592 | 580 | 0%
S177900 | Fabricate final blocks sector 62 | 5 | 2021-12-15 | 2021-12-21 | 5318 | 5163 | 0%
S349300 | Install platforms & access - Labor - Physics Resource(s) | 12 | 2021-12-15 | 2022-01-03 | 33494 | 33494 | 0%
S349400 | Install platforms & access - M&S | 12 | 2021-12-15 | 2022-01-03 | 1184 | 1184 | 0%
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 12 | 2021-12-15 | 2022-01-03 | 47298 | 47298 | 0%
S318140 | Perform TPC Supports Acceptance | 10 | 2021-12-16 | 2021-12-30 | 10211 | 9914 | 0%
S1007120 | AET submits FDR report to BNL for approval | 5 | 2021-12-17 | 2021-12-23 | 104800 | 104800 | 0%
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 30 | 2021-12-17 | 2022-02-01 | 6655 | 6474 | 0%
S299810 | Completed - (Cryo Controls Hardware) Cable pulling | 0 |  | 2021-12-17 | 0 | 0 | 0%
S330100 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor C | 50 | 2021-12-20 | 2022-03-04 | 312 | 308 | 0%
S330200 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) M&S | 50 | 2021-12-20 | 2022-03-04 | 37885 | 37528 | 0%
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | 50 | 2021-12-20 | 2022-03-04 | 11092 | 10069 | 0%
S265300 | LL1 Trigger Production Complete | 0 |  | 2021-12-20 | 0 | 0 | 0%
S265400 | LL1 Ready to Operate | 0 |  | 2021-12-20 | 0 | 0 | 0%
S343849 | Addition of ReBar plus Concrete Forming and Placement for IR Tracks - Acceptance | 0 | 2021-12-21 | 2021-12-21 | 613587 | 613587 | 0%
S355600 | Install Inner HCal assembly on Insertion Fixture - Labor | 4 | 2021-12-21 | 2021-12-27 | 79737 | 77414 | 0%
S355700 | Install Inner HCal assembly on Insertion Fixture - M&S | 4 | 2021-12-21 | 2021-12-27 | 592 | 580 | 0%
S178000 | Fabricate final blocks sector 63 | 5 | 2021-12-22 | 2021-12-29 | 5318 | 5163 | 0%
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 10 | 2021-12-23 | 2022-01-07 | 3187 | 3094 | 0%
S233200 | Procure EMCal External LV/Bias Signal/Comm/Test Cables Sectors 13-64 - Delivery Acceptance | 5 | 2021-12-27 | 2022-01-03 | 209971 | 205854 | 0%
S1006560 | Witness test IP8 Cold Box Assembly | 5 | 2021-12-27 | 2022-01-03 | 0 | 0 | 0%
S1007160 | AET begins material procurement | 5 | 2021-12-27 | 2022-01-03 | 0 | 0 | 0%
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 10 | 2021-12-27 | 2022-01-10 | 3187 | 3187 | 0%
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 10 | 2021-12-27 | 2022-01-10 | 3856 | 3856 | 0%
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 10 | 2021-12-27 | 2022-01-10 | 4156 | 4156 | 0%
S355800 | Install 1st Inner HCal Support Ring - Labor | 2 | 2021-12-28 | 2021-12-29 | 5366 | 5366 | 0%
S355900 | Install 1st Inner HCal Support Ring - M&S | 2 | 2021-12-28 | 2021-12-29 | 592 | 592 | 0%
S356000 | Install Inner HCal - Labor - CA-D Resource(s) | 2 | 2021-12-30 | 2022-01-03 | 17251 | 17251 | 0%
S356100 | Install Inner HCal - M&S | 2 | 2021-12-30 | 2022-01-03 | 592 | 592 | 0%
S1003799 | Install Inner HCal - Labor - Physics Resource(s) | 2 | 2021-12-30 | 2022-01-03 | 5366 | 5366 | 0%
S178100 | Fabricate final blocks sector 64 | 5 | 2021-12-30 | 2022-01-06 | 5318 | 5163 | 0%
S253100 | Calorimeter Electronics Complete | 0 |  | 2022-01-03 | 0 | 0 | 0%
S234300 | EMCal Electronics Complete | 0 |  | 2022-01-03 | 0 | 0 | 0%
S349410 | Completed - Install platforms & access | 0 |  | 2022-01-03 | 0 | 0 | 0%
S356200 | Install 2nd Inner HCal Support Ring - Labor | 2 | 2022-01-04 | 2022-01-05 | 5366 | 5366 | 0%
S356300 | Install 2nd Inner HCal Support Ring - M&S | 2 | 2022-01-04 | 2022-01-05 | 592 | 592 | 0%
S1006600 | Delivery of the IP8 Cold Box Assembly and Document Package | 5 | 2022-01-04 | 2022-01-10 | 0 | 0 | 0%
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 10 | 2022-01-04 | 2022-01-18 | 54812 | 54812 | 0%
S351800 | Review Outer HCal for Operational Readiness (ORR) | 10 | 2022-01-04 | 2022-01-18 | 4156 | 4156 | 0%
S294860 | (Warm Piping System) Assembly hall work on Platform | 15 | 2022-01-04 | 2022-01-25 | 15966 | 15966 | 0%
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 20 | 2022-01-04 | 2022-02-01 | 18994 | 18994 | 0%
S347810 | Install IR Electronics Cooling Water On Detector - M&S | 20 | 2022-01-04 | 2022-02-01 | 592 | 592 | 0%
S1007200 | Fabricate three Solenoid Valve Box Transfer Lines and two 4" & 5" NPS Field Joint Sleeves | 20 | 2022-01-04 | 2022-02-01 | 0 | 0 | 0%
S356310 | Completed - Install 2nd Inner HCal Support Ring | 0 |  | 2022-01-05 | 0 | 0 | 0%
S356400 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - Physics Resource(s) | 5 | 2022-01-06 | 2022-01-12 | 2906 | 2906 | 0%
S356500 | Align/Survey Inner HCal to SC Magnet Centerline - M&S | 5 | 2022-01-06 | 2022-01-12 | 592 | 592 | 0%
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 5 | 2022-01-06 | 2022-01-12 | 26192 | 26192 | 0%
S340400 | Perform IR HVAC Components Acceptance | 10 | 2022-01-06 | 2022-01-20 | 7965 | 7733 | 0%
S178200 | EMCal Block fabrication is complete | 0 |  | 2022-01-06 | 0 | 0 | 0%
S178900 | Pack and ship final blocks for sectors 57-64 to BNL - Purchased Services | 1 | 2022-01-07 | 2022-01-07 | 2638 | 2561 | 0%
S176010 | Pack and ship final blocks for sectors 57-64 to BNL - M&S | 1 | 2022-01-07 | 2022-01-07 | 7672 | 7521 | 0%
S179000 | EMCal final blocks arrive at BNL | 0 |  | 2022-01-07 | 0 | 0 | 0%
S360200 | Design/Safety Reviews Complete, TPC Integration/Installation Tooling/Fixtures/Procedures Ready for Service | 0 |  | 2022-01-07 | 0 | 0 | 0%
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | 20 | 2022-01-11 | 2022-02-08 | 8910 | 8910 | 0%
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 30 | 2022-01-11 | 2022-02-23 | 15373 | 15373 | 0%
S270800 | Timing System Production: additional firmware updates | 17 | 2022-01-12 | 2022-02-04 | 19327 | 18764 | 0%
S336900 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - M&S | 30 | 2022-01-12 | 2022-02-24 | 59195 | 59195 | 0%
S294810 | Completed - (Warm Piping System) Phase 1: Welding of piping and install of piping supports | 0 |  | 2022-01-12 | 0 | 0 | 0%
S357210 | Completed - Install Inner HCal | 0 |  | 2022-01-12 | 0 | 0 | 0%
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 5 | 2022-01-13 | 2022-01-20 | 4451 | 4451 | 0%
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 20 | 2022-01-13 | 2022-02-10 | 41556 | 41556 | 0%
S356700 | Install Inner HCal Cables and Services (if instrumented) - M&S | 20 | 2022-01-13 | 2022-02-10 | 592 | 592 | 0%
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 25 | 2022-01-13 | 2022-02-17 | 1250 | 1250 | 0%
S358300 | Transport Assembled EMCal Sectors to AH - M&S | 25 | 2022-01-13 | 2022-02-17 | 592 | 592 | 0%
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 25 | 2022-01-13 | 2022-02-17 | 23671 | 23671 | 0%
S358400 | Install EMCal Sectors - Labor | 16 | 2022-01-14 | 2022-02-07 | 79737 | 79737 | 0%
S358500 | Install EMCal Sectors - M&S | 16 | 2022-01-14 | 2022-02-07 | 592 | 592 | 0%
S334500 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - CA-D Resource(s) | 30 | 2022-01-14 | 2022-02-28 | 312 | 303 | 0%
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 30 | 2022-01-14 | 2022-02-28 | 12467 | 12104 | 0%
S332400 | Procure & Deliver Detector Gas and Cooling Services Systems Components (leadtime and fabrication included) L | 90 | 2022-01-14 | 2022-05-23 | 26621 | 26415 | 0%
S332500 | Procure & Deliver Detector Gas and Cooling Services Systems Components (leadtime and fabrication included) M&S | 90 | 2022-01-14 | 2022-05-23 | 62747 | 62419 | 0%
S273900 | MBD Production Complete | 0 |  | 2022-01-18 | 0 | 0 | 0%
S303610 | Completed - Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 0 |  | 2022-01-18 | 0 | 0 | 0%
S274000 | Bench Test Min/Bias Detector | 5 | 2022-01-19 | 2022-01-25 | 14607 | 14182 | 0%
S260700 | DAQ Production: Internal Readiness Review | 10 | 2022-01-19 | 2022-02-01 | 56320 | 54679 | 0%
S351900 | Address Action Items from Outer Hcal ORR | 10 | 2022-01-19 | 2022-02-01 | 4156 | 4156 | 0%
S143400 | TPC FEE Production Complete | 0 |  | 2022-01-19 | 0 | 0 | 0%
S268100 | GL1 Production: additional firmware improvements | 12 | 2022-01-20 | 2022-02-04 | 20937 | 20328 | 0%
S340500 | IR HVAC components Ready for Installation | 0 |  | 2022-01-20 | 0 | 0 | 0%
S341600 | IR Electronics Cooling Water Distribution System Components Ready for Installation | 0 |  | 2022-01-20 | 0 | 0 | 0%
S345500 | Install IR HVAC - Labor - C-AD Resources | 10 | 2022-01-21 | 2022-02-03 | 23837 | 23143 | 0%
S345600 | Install IR HVAC - M&S | 10 | 2022-01-21 | 2022-02-03 | 592 | 580 | 0%
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 20 | 2022-01-21 | 2022-02-17 | 23677 | 23677 | 0%
S347800 | Install IR Electronics Cooling Water Off Detector - M&S | 20 | 2022-01-21 | 2022-02-17 | 592 | 592 | 0%
S329200 | Perform Line Electric Power Distribution Components Acceptance | 20 | 2022-01-25 | 2022-02-22 | 15054 | 14616 | 0%
S329100 | Procure Line Electric Power Distribution Components - Delivery Acceptance | 20 | 2022-01-25 | 2022-02-22 | 59195 | 58034 | 0%
S274100 | MinBias Detector Ready to Install | 0 |  | 2022-01-25 | 0 | 0 | 0%
S368400 | Min Bias Ready for Installation | 0 |  | 2022-01-25 | 0 | 0 | 0%
S295300 | (Warm Piping System) Vacuum Pumping System installation | 5 | 2022-01-26 | 2022-02-01 | 5674 | 5674 | 0%
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | 10 | 2022-01-26 | 2022-02-08 | 10433 | 10433 | 0%
S260800 | DAQ Production: DAQ Ready for Operation | 0 |  | 2022-02-01 | 0 | 0 | 0%
S295310 | Completed - (Warm Piping System) Vacuum Pumping System installation | 0 |  | 2022-02-01 | 0 | 0 | 0%
S1007240 | Delivery of all three Solenoid Valve Box Transfer Lines and two 4" & 5" NPS Field Joint Sleeves | 5 | 2022-02-02 | 2022-02-08 | 240966 | 240966 | 0%
S352000 | Commission Outer HCal - Labor | 20 | 2022-02-02 | 2022-03-02 | 140571 | 140571 | 0%
S352200 | Commission Outer HCal - M&S | 20 | 2022-02-02 | 2022-03-02 | 592 | 592 | 0%
S352100 | Commission Outer HCal - Labor | 20 | 2022-02-02 | 2022-03-02 | 0 | 0 | 0%
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 120 | 2022-02-02 | 2022-07-22 | 26621 | 26621 | 0%
S332770 | Procure & Deliver Detector Gas Services Systems Components - M&S | 120 | 2022-02-02 | 2022-07-22 | 63930 | 63930 | 0%
S121900 | TPC Ready to Install (Assembly Complete) | 0 |  | 2022-02-02 | 0 | 0 | 0%
S360300 | TPC Ready for Installation (Installation Sequence Can Commence) | 0 |  | 2022-02-02 | 0 | 0 | 0%
S308619 | Install probes and readout on TPC | 10 | 2022-02-03 | 2022-02-16 | 4843 | 4843 | 0%
S196600 | EMCal Modules Complete | 0 |  | 2022-02-03 | 0 | 0 | 0%
S197300 | EMCal Ready to Install | 0 |  | 2022-02-04 | 0 | 0 | 0%
S197100 | EMCal Sectors Complete | 0 |  | 2022-02-04 | 0 | 0 | 0%
S270900 | Timing System Production: Timing system ready to operate | 0 |  | 2022-02-04 | 0 | 0 | 0%
S268200 | GL1 Ready to Operate | 0 |  | 2022-02-04 | 0 | 0 | 0%
S358100 | EMCal Sectors Ready for Installation | 0 |  | 2022-02-04 | 0 | 0 | 0%
S101020 | Internal Project Float | 0 | 2022-02-07 | 07-Feb-22* | 0 | 0 | 0%
S101022 | Early Project Completion | 0 |  | 2022-02-07 | 0 | 0 | 0%
S101030 | WBS 1X Schedule Contingency | 225 | 2022-02-07 | 2022-12-29 | 0 | 0 | 0%
S358510 | Completed - Install EMCal Sectors | 0 |  | 2022-02-07 | 0 | 0 | 0%
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 7 | 2022-02-08 | 2022-02-16 | 2421 | 2421 | 0%
S358700 | Align/Survey EMCal to SC Magnet Centerline - M&S | 7 | 2022-02-08 | 2022-02-16 | 592 | 592 | 0%
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 7 | 2022-02-08 | 2022-02-16 | 26192 | 26192 | 0%
S287410 | Completed - (Helium System: 1008B Coldbox/Transferlines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | 0 |  | 2022-02-08 | 0 | 0 | 0%
S300200 | (Cryo Controls Hardware) Heater 480VAC wiring | 5 | 2022-02-09 | 2022-02-15 | 63690 | 63690 | 0%
S1007280 | Approval of all Data/Documentation/ Reports | 5 | 2022-02-09 | 2022-02-15 | 87334 | 87334 | 0%
S299900 | (Cryo Controls Hardware) Cable termination | 20 | 2022-02-09 | 2022-03-09 | 19372 | 19372 | 0%
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 10 | 2022-02-10 | 2022-02-24 | 9104 | 9104 | 0%
S356800 | Inner HCal - Operational Readiness Review (ORR) | 10 | 2022-02-11 | 2022-02-25 | 5405 | 5405 | 0%
S285300 | Milestone - RHIC Helium Interface Contract Complete | 0 |  | 2022-02-15 | 0 | 0 | 0%
S358800 | Install EMCal Cables and Services - Labor | 13 | 2022-02-17 | 2022-03-08 | 78454 | 78454 | 0%
S358900 | Install EMCal Cables and Services - M&S | 13 | 2022-02-17 | 2022-03-08 | 592 | 592 | 0%
S329300 | Line Electric Power Distribution Components Ready for Installation | 0 |  | 2022-02-22 | 0 | 0 | 0%
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 20 | 2022-02-23 | 2022-03-22 | 4999 | 4961 | 0%
S346200 | Install Line Electric Power Distribution Off Detector - M&S | 20 | 2022-02-23 | 2022-03-22 | 592 | 589 | 0%
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 20 | 2022-02-23 | 2022-03-22 | 28298 | 28079 | 0%
S331600 | Detector Electronics Racks and Rack generic support systems Components Ready for Installation | 0 |  | 2022-02-24 | 0 | 0 | 0%
S337000 | Perform Control Room and Offices Modifications Components Acceptance - CA-D Resource(s) | 10 | 2022-02-25 | 2022-03-10 | 312 | 312 | 0%
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 10 | 2022-02-25 | 2022-03-10 | 5132 | 5132 | 0%
S347100 | Install Electronics Racks Rackroom - Labor | 60 | 2022-02-25 | 2022-05-19 | 111108 | 111108 | 0%
S347300 | Install Electronics Racks Rackroom - M&S | 60 | 2022-02-25 | 2022-05-19 | 592 | 592 | 0%
S356900 | Address Action Items from Inner Hcal ORR | 10 | 2022-02-28 | 2022-03-11 | 5405 | 5405 | 0%
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 50 | 2022-03-01 | 2022-05-09 | 37400 | 37255 | 0%
S334700 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - M&S | 50 | 2022-03-01 | 2022-05-09 | 11839 | 11808 | 0%
S300400 | (Cryo Controls Hardware) Heater I/O wiring, temp sensors | 5 | 2022-03-03 | 2022-03-09 | 1937 | 1937 | 0%
S333700 | Perform Detector Safety Subsystems Components Acceptance | 10 | 2022-03-04 | 2022-03-17 | 2703 | 2703 | 0%
S330300 | Perform Detector Support Services Systems Components Acceptance - CA-D Resource(s) | 5 | 2022-03-04 | 2022-03-11 | 625 | 625 | 0%
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 5 | 2022-03-04 | 2022-03-11 | 3531 | 3443 | 0%
S359000 | EMCal - Operational Readiness Review (ORR) | 5 | 2022-03-09 | 2022-03-15 | 4156 | 4156 | 0%
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 10 | 2022-03-09 | 2022-03-22 | 9967 | 9967 | 0%
S349600 | Install Pole Tips - M&S | 10 | 2022-03-09 | 2022-03-22 | 3552 | 3552 | 0%
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 10 | 2022-03-09 | 2022-03-22 | 48254 | 48254 | 0%
S300500 | (Cryo Controls Hardware) Wire up instruments and control valves | 15 | 2022-03-10 | 2022-03-30 | 11623 | 11623 | 0%
S337100 | Control Room and Offices Modifications Components Ready for Installation | 0 |  | 2022-03-10 | 0 | 0 | 0%
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 10 | 2022-03-11 | 2022-03-24 | 14518 | 14095 | 0%
S330350 | Procure Fiber Optics Trunk Cables and Accessories - Labor - CA-D Resource(s) | 60 | 2022-03-11 | 2022-06-06 | 625 | 625 | 0%
S330355 | Procure Fiber Optics Trunk Cables and Accessories - M&S | 60 | 2022-03-11 | 2022-06-06 | 26046 | 26046 | 0%
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | 60 | 2022-03-11 | 2022-06-06 | 25344 | 25344 | 0%
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 5 | 2022-03-14 | 2022-03-18 | 106671 | 106671 | 0%
S357200 | Commission Inner HCal - M&S | 5 | 2022-03-14 | 2022-03-18 | 592 | 592 | 0%
S357100 | Commission Inner HCal (labor - if instrumented) - Labor | 5 | 2022-03-14 | 2022-03-18 | 0 | 0 | 0%
S359100 | Address Action Items from EMCal ORR | 10 | 2022-03-16 | 2022-03-29 | 4156 | 4156 | 0%
S365000 | MVTX Ready for Installation | 0 |  | 2022-03-17 | 0 | 0 | 0%
EXT101400 | [External Activity] MVTX Complete and ready for installation | 0 |  | 17-Mar-22* | 0 | 0 | 0%
S333800 | Detector Safety Subsystems Components Ready for Installation | 0 |  | 2022-03-17 | 0 | 0 | 0%
S365100 | Installation Prep | 5 | 2022-03-18 | 2022-03-24 | 0 | 0 | 0%
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 2022-03-18 | 2022-04-14 | 20778 | 20778 | 0%
S345900 | Install On Detector Safety Subsystems - M&S | 20 | 2022-03-18 | 2022-04-14 | 592 | 592 | 0%
S349610 | Completed - Install Pole Tips | 0 |  | 2022-03-22 | 0 | 0 | 0%
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 5 | 2022-03-23 | 2022-03-29 | 7642 | 7642 | 0%
S370100 | Move Full sPHENIX to IR - M&S | 5 | 2022-03-23 | 2022-03-29 | 1184 | 1184 | 0%
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 5 | 2022-03-23 | 2022-03-29 | 21590 | 21590 | 0%
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 20 | 2022-03-23 | 2022-04-19 | 5818 | 5818 | 0%
S346210 | Install Line Electric Power Distribution On Detector - M&S | 20 | 2022-03-23 | 2022-04-19 | 592 | 592 | 0%
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 20 | 2022-03-23 | 2022-04-19 | 16864 | 16864 | 0%
S342700 | IR/AH Safety Subsystems Components Ready for Installation | 0 |  | 2022-03-24 | 0 | 0 | 0%
S365200 | Installation Review | 1 | 2022-03-25 | 2022-03-25 | 0 | 0 | 0%
S345700 | Install Off Detector Safety Subsystems - Labor - C-AD Resources | 20 | 2022-03-25 | 2022-04-21 | 19623 | 19051 | 0%
S345910 | Install Off Detector Safety Subsystems - M&S | 20 | 2022-03-25 | 2022-04-21 | 592 | 580 | 0%
S365300 | Transport Assembled MVTX Sections to IR - Labor | 5 | 2022-03-28 | 2022-04-01 | 5124 | 5124 | 0%
S365400 | Transport Assembled MVTX Sections to IR - M&S | 5 | 2022-03-28 | 2022-04-01 | 592 | 592 | 0%
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 5 | 2022-03-30 | 2022-04-05 | 8475 | 8475 | 0%
S304800 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR M&S | 5 | 2022-03-30 | 2022-04-05 | 3500 | 3500 | 0%
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | 10 | 2022-03-30 | 2022-04-12 | 41645 | 41645 | 0%
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 15 | 2022-03-30 | 2022-04-19 | 15966 | 15966 | 0%
S359200 | Commission EMCal - Labor | 25 | 2022-03-30 | 2022-05-03 | 100062 | 100062 | 0%
S359400 | Commission EMCal - M&S | 25 | 2022-03-30 | 2022-05-03 | 592 | 592 | 0%
S359300 | Commission EMCal - Labor | 25 | 2022-03-30 | 2022-05-03 | 0 | 0 | 0%
S300000 | (Cryo Controls Hardware) Check out continuity | 10 | 2022-03-31 | 2022-04-13 | 4843 | 4843 | 0%
S304710 | Completed - Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 0 |  | 2022-04-05 | 0 | 0 | 0%
S306700 | Magnet: Install Quench Detector Cabling | 5 | 06-Apr-22* | 2022-04-12 | 0 | 0 | 0%
S305000 | Magnet Power Supply Installation: Power Supply Testing | 10 | 2022-04-06 | 2022-04-19 | 22184 | 22184 | 0%
S295000 | (Warm Piping System) Pressure and leak check | 5 | 2022-04-13 | 2022-04-19 | 8169 | 8169 | 0%
S307200 | Magnet: Quench Detector Testing | 5 | 2022-04-13 | 2022-04-19 | 24119 | 23417 | 0%
S287600 | RHIC Helium Interface - Final pump and purge | 10 | 2022-04-13 | 2022-04-26 | 18569 | 18569 | 0%
S300600 | (Cryo Controls Hardware) Hardware Installed | 0 |  | 2022-04-13 | 0 | 0 | 0%
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 10 | 2022-04-14 | 2022-04-27 | 34384 | 34384 | 0%
S294910 | Completed - (Warm Piping System) Phase 2: Welding of piping, vent lines & install of piping supports | 0 |  | 2022-04-19 | 0 | 0 | 0%
S305010 | Completed - Magnet Power Supply Installation: Power Supply Testing | 0 |  | 2022-04-19 | 0 | 0 | 0%
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | 5 | 2022-04-20 | 2022-04-26 | 8169 | 8169 | 0%
S339400 | Beampipe/Vacuum components Ready for Installation | 0 |  | 2022-04-20 | 0 | 0 | 0%
S343700 | Perform Assembly Hall Modifications Components Acceptance | 10 | 2022-04-21 | 2022-05-04 | 5026 | 4880 | 0%
S287700 | RHIC Helium Interface - Installation complete | 0 |  | 2022-04-26 | 0 | 0 | 0%
S278900 | LESHC Review Magnet Overall System Safety Review | 1 | 2022-04-28 | 2022-04-28 | 7447 | 7447 | 0%
S279000 | ASSRC REVIEW and Full Walkthrough | 1 | 2022-04-29 | 2022-04-29 | 6197 | 6197 | 0%
S359410 | Completed - Commission EMCal | 0 |  | 2022-05-03 | 0 | 0 | 0%
S343800 | Assembly Hall Components Ready for Installation | 0 |  | 2022-05-04 | 0 | 0 | 0%
S335900 | Perform Rack Room Modifications Components Acceptance | 10 | 2022-05-05 | 2022-05-18 | 5132 | 5132 | 0%
S279100 | Cooldown | 15 | 2022-05-05 | 2022-05-25 | 27602 | 27602 | 0%
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 20 | 2022-05-09 | 2022-06-06 | 28540 | 28540 | 0%
S334800 | Perform Gas Mixing House & Gas Pad Components Acceptance - CA-D Resource(s) | 10 | 2022-05-10 | 2022-05-23 | 312 | 312 | 0%
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 10 | 2022-05-10 | 2022-05-23 | 4156 | 4156 | 0%
S336000 | Rack Room Modifications Components Ready for Installation | 0 |  | 2022-05-18 | 0 | 0 | 0%
S347200 | Install Electronics Racks On Carriage - Labor | 60 | 2022-05-20 | 2022-08-15 | 111108 | 111108 | 0%
S347310 | Install Electronics Racks On Carriage - M&S | 60 | 2022-05-20 | 2022-08-15 | 592 | 592 | 0%
S334900 | Gas Mixing House & Gas Pad Components Ready for Installation | 0 |  | 2022-05-23 | 0 | 0 | 0%
S332600 | Perform Detector Gas and Cooling Services Systems Components Acceptance | 20 | 2022-05-24 | 2022-06-21 | 5405 | 5405 | 0%
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 35 | 2022-05-24 | 2022-07-13 | 68583 | 68583 | 0%
S346800 | Install Non-IR Infrastructure - M&S | 35 | 2022-05-24 | 2022-07-13 | 592 | 592 | 0%
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 35 | 2022-05-24 | 2022-07-13 | 43978 | 43978 | 0%
S362700 | INTT Ready for Installation | 0 |  | 2022-05-25 | 0 | 0 | 0%
EXT327600 | [External Activity] INTT Assembly Complete and Ready for Installation | 0 |  | 25-May-22* | 0 | 0 | 0%
S279200 | 4.5K Static Heat Load test | 2 | 2022-05-26 | 2022-05-27 | 3680 | 3680 | 0%
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 10 | 2022-05-26 | 2022-06-09 | 74746 | 74746 | 0%
S279300 | 4.5K Low power test | 5 | 2022-05-31 | 2022-06-06 | 43357 | 43357 | 0%
S330400 | Detector Support Services Systems Components Ready for Installation | 0 |  | 2022-06-06 | 0 | 0 | 0%
S346900 | Install Detector Support Services Systems - Labor - CA-D Resource(s) | 20 | 2022-06-06 | 2022-07-05 | 4253 | 4253 | 0%
S347000 | Install Detector Support Services Systems - M&S | 20 | 2022-06-06 | 2022-07-05 | 592 | 592 | 0%
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 20 | 2022-06-06 | 2022-07-05 | 91339 | 91339 | 0%
S370510 | Review of Safety System Design by CAD ESRC | 3 | 2022-06-07 | 2022-06-09 | 12125 | 12125 | 0%
S279400 | 4.5K High Power Test | 5 | 2022-06-07 | 2022-06-13 | 43357 | 43357 | 0%
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 2022-06-10 | 2022-07-08 | 41494 | 41494 | 0%
S279500 | Magnet is operational | 0 |  | 2022-06-13 | 0 | 0 | 0%
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 15 | 2022-06-14 | 2022-07-05 | 74746 | 74746 | 0%
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 15 | 2022-06-14 | 2022-07-05 | 74746 | 74746 | 0%
S332700 | Detector Gas and Cooling Services Systems Components Ready for Installation | 0 |  | 2022-06-21 | 0 | 0 | 0%
S347400 | Install Gas and Cooling System Services - Labor | 40 | 2022-06-22 | 2022-08-17 | 117543 | 117543 | 0%
S347500 | Install Gas and Cooling System Services - M&S | 40 | 2022-06-22 | 2022-08-17 | 592 | 592 | 0%
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 5 | 2022-06-30 | 2022-07-07 | 5124 | 5124 | 0%
S360500 | Transport Assembled TPC Sections to AH - M&S | 5 | 2022-06-30 | 2022-07-07 | 592 | 592 | 0%
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 5 | 2022-06-30 | 2022-07-07 | 1250 | 1250 | 0%
S309010 | Completed - Magnet Field Measurements: Map Magnetic Field of SC Magnet | 0 |  | 2022-07-05 | 0 | 0 | 0%
S309100 | Magnet Field Measurements: Remove Field Mapping Equipment | 2 | 2022-07-06 | 2022-07-07 | 14529 | 14529 | 0%
S360600 | Open SC Magnet Pole Tip Doors | 1 | 2022-07-08 | 2022-07-08 | 2562 | 2562 | 0%
S309110 | Receive report from CERN, incorporate into analysis | 20 | 08-Jul-22* | 2022-08-04 | 3495 | 3495 | 0%
S370530 | Review and approve procedures | 2 | 2022-07-11 | 2022-07-12 | 17579 | 17579 | 0%
S360700 | Install TPC Support - Labor | 5 | 2022-07-11 | 2022-07-15 | 12248 | 12248 | 0%
S360800 | Install TPC Support - M&S | 5 | 2022-07-11 | 2022-07-15 | 592 | 592 | 0%
S370540 | Magnet Checkout After Power Testing | 5 | 2022-07-13 | 2022-07-19 | 9084 | 9084 | 0%
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 5 | 2022-07-18 | 2022-07-22 | 851 | 851 | 0%
S361000 | Install TPC (Mechanical) - M&S | 5 | 2022-07-18 | 2022-07-22 | 592 | 592 | 0%
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 5 | 2022-07-18 | 2022-07-22 | 14603 | 14603 | 0%
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 5 | 2022-07-20 | 2022-07-26 | 11898 | 11898 | 0%
S361010 | Completed - Install TPC | 0 |  | 2022-07-22 | 0 | 0 | 0%
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 5 | 2022-07-25 | 2022-07-29 | 2421 | 2421 | 0%
S361200 | Align/Survey TPC to SC Magnet Centerline - M&S | 5 | 2022-07-25 | 2022-07-29 | 592 | 592 | 0%
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 5 | 2022-07-25 | 2022-07-29 | 26192 | 26192 | 0%
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 20 | 2022-07-25 | 2022-08-19 | 5405 | 5405 | 0%
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 10 | 2022-07-27 | 2022-08-09 | 9084 | 9084 | 0%
S346300 | Install Beampipe/Vacuum/Bakeout - Labor - Physics Resource(s) | 7 | 2022-08-01 | 2022-08-09 | 9905 | 9905 | 0%
S346400 | Install Beampipe/Vacuum/Bakeout - M&S | 7 | 2022-08-01 | 2022-08-09 | 592 | 592 | 0%
S346310 | Install Beampipe/Vacuum/Bakeout - Labor - CA-D Resource(s) | 7 | 2022-08-01 | 2022-08-09 | 27347 | 27347 | 0%
S346410 | Completed - Install Beampipe | 0 |  | 2022-08-09 | 0 | 0 | 0%
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 1 | 2022-08-10 | 2022-08-10 | 2218 | 2218 | 0%
S368600 | Transport Assembled Min Bias Sections to AH - M&S | 1 | 2022-08-10 | 2022-08-10 | 592 | 592 | 0%
S362800 | Transport Assembled INTT Sections to AH - Labor | 2 | 2022-08-10 | 2022-08-11 | 5124 | 5124 | 0%
S362900 | Transport Assembled INTT Sections to AH - M&S | 2 | 2022-08-10 | 2022-08-11 | 592 | 592 | 0%
S370570 | Preparation for Full Operation - Verify Global Safety System | 5 | 2022-08-10 | 2022-08-16 | 12369 | 12369 | 0%
S361300 | Install TPC Cables and Services - Labor | 15 | 2022-08-10 | 2022-08-30 | 60293 | 60293 | 0%
S361400 | Install TPC Cables and Services - M&S | 15 | 2022-08-10 | 2022-08-30 | 592 | 592 | 0%
S368700 | Install Min Bias Support - Labor | 8 | 2022-08-11 | 2022-08-22 | 4156 | 4156 | 0%
S368800 | Install Min Bias Support - M&S | 8 | 2022-08-11 | 2022-08-22 | 592 | 592 | 0%
S363000 | Install INTT Support - Labor | 2 | 2022-08-12 | 2022-08-15 | 9483 | 9483 | 0%
S363100 | Install INTT Support - M&S | 2 | 2022-08-12 | 2022-08-15 | 592 | 592 | 0%
S365500 | Install MVTX Support - Labor | 3 | 2022-08-12 | 2022-08-16 | 9483 | 9483 | 0%
S365600 | Install MVTX Support - M&S | 3 | 2022-08-12 | 2022-08-16 | 592 | 592 | 0%
S363200 | Install INTT (mechanical) - Labor | 3 | 2022-08-16 | 2022-08-18 | 9483 | 9483 | 0%
S363300 | Install INTT (mechanical) - M&S | 3 | 2022-08-16 | 2022-08-18 | 592 | 592 | 0%
S365700 | Install FELIX | 2 | 2022-08-17 | 2022-08-18 | 2147 | 2147 | 0%
S365900 | Install Optical fibers | 2 | 2022-08-17 | 2022-08-18 | 4843 | 4843 | 0%
S366000 | Install RU | 2 | 2022-08-17 | 2022-08-18 | 5369 | 5369 | 0%
S366200 | Install Samtec Cables | 2 | 2022-08-17 | 2022-08-18 | 4843 | 4843 | 0%
S365800 | Install FELIX | 2 | 2022-08-17 | 2022-08-18 | 0 | 0 | 0%
S366100 | Install RU | 2 | 2022-08-17 | 2022-08-18 | 0 | 0 | 0%
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | 5 | 2022-08-17 | 2022-08-23 | 2906 | 2821 | 0%
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 5 | 2022-08-17 | 2022-08-23 | 1518 | 1474 | 0%
S314650 | CC Seismic Restraints - Delivery Acceptance - M&S | 5 | 2022-08-17 | 2022-08-23 | 149171 | 146246 | 0%
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 5 | 2022-08-17 | 2022-08-23 | 20889 | 20889 | 0%
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 5 | 2022-08-19 | 2022-08-25 | 2421 | 2421 | 0%
S363500 | Align/Survey INTT to SC Magnet Centerline - M&S | 5 | 2022-08-19 | 2022-08-25 | 592 | 592 | 0%
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 5 | 2022-08-19 | 2022-08-25 | 17879 | 17879 | 0%
S366300 | Install Half-Barrel 1 | 6 | 2022-08-19 | 2022-08-26 | 20423 | 20423 | 0%
S366400 | Install Half-Barrel 1 | 6 | 2022-08-19 | 2022-08-26 | 0 | 0 | 0%
S332780 | Detector Gas Services Systems Components Ready for Installation | 0 |  | 2022-08-19 | 0 | 0 | 0%
S368900 | Install Min Bias (mechanical) - Labor | 5 | 2022-08-23 | 2022-08-29 | 4156 | 4156 | 0%
S369000 | Install Min Bias (mechanical) - M&S | 5 | 2022-08-23 | 2022-08-29 | 592 | 592 | 0%
S314655 | Completed - CC Seismic Restraints - Delivery Acceptance - M&S | 0 |  | 2022-08-23 | 0 | 0 | 0%
S370200 | Align Full sPHENIX to Nominal Beamline and IP - Labor - Physics Resource(s) | 5 | 2022-08-24 | 2022-08-30 | 1937 | 1937 | 0%
S370300 | Align Full sPHENIX to Nominal Beamline and IP - M&S | 5 | 2022-08-24 | 2022-08-30 | 1184 | 1184 | 0%
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 5 | 2022-08-24 | 2022-08-30 | 19870 | 19870 | 0%
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 5 | 2022-08-24 | 2022-08-30 | 3495 | 3495 | 0%
S363600 | Install INTT Cables and Services - Labor | 5 | 2022-08-26 | 2022-09-01 | 71307 | 71307 | 0%
S363700 | Install INTT Cables and Services - M&S | 5 | 2022-08-26 | 2022-09-01 | 592 | 592 | 0%
S366500 | Install Half-Barrel 2 | 5 | 2022-08-29 | 2022-09-02 | 20423 | 20423 | 0%
S366600 | Install Half-Barrel 2 | 5 | 2022-08-29 | 2022-09-02 | 0 | 0 | 0%
S369010 | Completed - Install Min Bias | 0 |  | 2022-08-29 | 0 | 0 | 0%
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 5 | 2022-08-30 | 2022-09-06 | 969 | 969 | 0%
S369200 | Align/Survey Min Bias to SC Magnet Centerline - M&S | 5 | 2022-08-30 | 2022-09-06 | 592 | 592 | 0%
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 5 | 2022-08-30 | 2022-09-06 | 8885 | 8885 | 0%
S361500 | TPC - Operational Readiness Review (ORR) | 5 | 2022-08-31 | 2022-09-07 | 4261 | 4261 | 0%
S363800 | INTT - Operational Readiness Review (ORR) | 5 | 2022-09-02 | 2022-09-09 | 4156 | 4156 | 0%
S366700 | Align/Survey MVTX to SC Magnet Centerline - Labor - Physics Resource(s) | 2 | 2022-09-06 | 2022-09-07 | 2421 | 2421 | 0%
S366800 | Align/Survey MVTX to SC Magnet Centerline - M&S | 2 | 2022-09-06 | 2022-09-07 | 592 | 592 | 0%
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 2 | 2022-09-06 | 2022-09-07 | 17879 | 17879 | 0%
S369300 | Install Min Bias Cables and Services - Labor | 5 | 2022-09-07 | 2022-09-13 | 71307 | 71307 | 0%
S369400 | Install Min Bias Cables and Services - M&S | 5 | 2022-09-07 | 2022-09-13 | 592 | 592 | 0%
S366900 | Install MVTX Remaining Cables and Services - Labor | 3 | 2022-09-08 | 2022-09-12 | 51007 | 51007 | 0%
S367000 | Install MVTX Remaining Cables and Services - M&S | 3 | 2022-09-08 | 2022-09-12 | 592 | 592 | 0%
S361600 | Address Action Items from TPC ORR | 5 | 2022-09-08 | 2022-09-14 | 4261 | 4261 | 0%
S363900 | Address Action Items from INTT ORR | 5 | 2022-09-12 | 2022-09-16 | 4156 | 4156 | 0%
S367100 | MVTX - Operational Readiness Review (ORR) | 5 | 2022-09-13 | 2022-09-19 | 4156 | 4156 | 0%
S367200 | MVTX - Operational Readiness Review (ORR) | 5 | 2022-09-13 | 2022-09-19 | 0 | 0 | 0%
S370400 | sPHENIX Installation Complete Ready for ORR | 0 |  | 2022-09-13 | 0 | 0 | 0%
S369500 | Min Bias - Operational Readiness Review (ORR) | 5 | 2022-09-14 | 2022-09-20 | 4156 | 4156 | 0%
S370600 | Full sPHENIX Detector - Operational Readiness Review (ORR) | 5 | 2022-09-14 | 2022-09-20 | 19340 | 19340 | 0%
S361700 | Commission TPC - Labor Phys | 15 | 2022-09-15 | 2022-10-05 | 100662 | 100262 | 0%
S361900 | Commission TPC - M&S | 15 | 2022-09-15 | 2022-10-05 | 594 | 593 | 0%
S361800 | Commission TPC - Labor Students | 15 | 2022-09-15 | 2022-10-05 | 0 | 0 | 0%
S364000 | Commission INTT - Labor | 10 | 2022-09-19 | 2022-09-30 | 100062 | 100062 | 0%
S364200 | Commission INTT - M&S | 10 | 2022-09-19 | 2022-09-30 | 592 | 592 | 0%
S364100 | Commission INTT - Labor | 10 | 2022-09-19 | 2022-09-30 | 0 | 0 | 0%
S367300 | Address Action Items from MVTX ORR | 5 | 2022-09-20 | 2022-09-26 | 4156 | 4156 | 0%
S367400 | Address Action Items from MVTX ORR | 5 | 2022-09-20 | 2022-09-26 | 0 | 0 | 0%
S369600 | Address Action Items from Min Bias ORR | 5 | 2022-09-21 | 2022-09-27 | 4156 | 4156 | 0%
S370700 | Address Action Items from Full sPHENIX Detector ORR | 15 | 2022-09-21 | 2022-10-12 | 19611 | 19534 | 0%
S367500 | Commission MVTX - Labor | 5 | 2022-09-27 | 2022-10-03 | 0 | 0 | 0%
S367600 | Commission MVTX - M&S | 5 | 2022-09-27 | 2022-10-03 | 594 | 592 | 0%
S369700 | Commission Min Bias - Labor | 5 | 2022-09-28 | 2022-10-04 | 101263 | 100062 | 0%
S369900 | Commission Min Bias - M&S | 5 | 2022-09-28 | 2022-10-04 | 597 | 592 | 0%
S369800 | Commission Min Bias - Labor | 5 | 2022-09-28 | 2022-10-04 | 0 | 0 | 0%
S364210 | Completed - Install INTT | 0 |  | 2022-09-30 | 0 | 0 | 0%
S277700 | 2023 Detector Support Systems L3 Project Management | 2 | 03-Oct-22* | 2022-10-04 | 20999 | 15621 | 0%
S278300 | 2023 Integration & Installation Project Management | 3 | 2022-10-03 | 2022-10-05 | 52405 | 52405 | 0%
S276500 | 2023 Infrastructure Project Management | 5 | 2022-10-03 | 2022-10-07 | 5530 | 5530 | 0%
S277100 | 2023 Facility Support Systems L3 Project Management | 5 | 2022-10-03 | 2022-10-07 | 12375 | 12375 | 0%
S367610 | Completed - Install MVTX | 0 |  | 2022-10-03 | 0 | 0 | 0%
S370800 | sPHENIX Ready for Operations | 0 |  | 2022-10-12 | 0 | 0 | 0%
S370850 | WBS 2X Schedule Contingency | 71 | 2022-10-13 | 2023-01-27 | 0 | 0 | 0%
S101040 | Approve Project Closeout PD-4 | 0 |  | 29-Dec-22* | 0 | 0 | 0%
S370900 | Start of RHIC Run 30-Jan-23 | 0 | 30-Jan-23* |  | 0 | 0 | 0%
S999999 | Completed: sPHENIX MIE and Support Projects | 0 |  | 2023-01-30 | 0 | 0 | 0%