## Slide 1: INTT Material Production Status
 | Batch-1 | Batch-2 | Batch-3 | Batch-4 | Total | Status
Silicon | 150* (2019) | 120* (2020) |  |  | 135 (270*) | completed
HDI | 180* (2020) | 90* (2020) | 83* (2021) |  | 176.5 (353*) | completed
Stave | 75 (2020) | 75 (2021) | 27 (2021) | 27 (2021) | 204 | completed
Bus Extender | 20 (2021-22) | 40 (2022) | 70 (2022) |  | 120 | ongoing
Conversion Cable |  |  |  |  |  | Prototyping
Beam Clock Distribution Board |  |  |  |  |  | Prototyping
* Quantity in ½ ladder unit
The production for the ladder components had been completed by the end of 2021.
The readout cables are in production and under prototyping.
CC
BEX
HDI
SSS
ROC
SSS
HDI
BEX
CC
SSS
SSS
ROC
Silicon module
Silicon module
Data
Data
completed
production
prototype
モンスターストライク
モンスターストライク

## Slide 2: FPHX Production Statistics
Year | 2016 | 2018 | Total
Quantity* | 5,829 | 7,560 | 12,885
Total FPHX Needed for 56 Ladders |  |  | 2,912
Total Number of Spare FPHX |  |  | 9,973
*Only good chips
We produced >12k good FPHX Chips.
This amount is equivalent for 247 ladders. (52 Chips/Ladder)
Sufficient enough spares.

## Slide 3: Conversion Cable
Design work by Dan Cacace (2021/July)
FVTX FPC Bus Extenders
INTT FPC Conversion Cable
(prototype-I)
INTTmCoax Conversion Cable
(prototype-II)
14~20 different FPC designs needed for INTT if we follow the FVTX way ➜ Not affordable.
Started prototyping using the m-coax technology. Requires only 1 design thanks to its flexibility in transverse direction.
Expected similar signal transmission performance with the FPC solution.
Prototype-II test is ongoing.
Preproduction and Production in 2022.
m-coax Cable : AWG44-UL11130 (Hitachi)
Connector : XSL series (KEL)

## Slide 4: Beam Clock Distribution Board (BCDB)
IR
B
FEM
FEM
FEM-IB
BCO
START
Twisted pair
6 feet (1.8m)
FVTX
ROC
ROC
ROC
ROC
BCDB
FEM
FEM
FEM-IB
BCO
<1 feet
INTT
ROC
ROC
ROC
ROC
START
BCFO
BCDB
BCDB
BCDB
BCDB
IR
FVTX
FVTX
INTT
FVTX Packet Drop
FVTX lost packet during data taking issue has been unresolved.
Long twisted pair cable is considered as the biggest suspect.
BCDB
INTT Solution : get rid of the long twisted pair cable.
Prototyping new BCDB is now underway
Beam clock fan-out
10Base-t

## Slide 5: Voltage Drop for FPHX Power in Cable Chain
 | @ROC | HDI | Bus Ext. | Conv. Cable | Volt. Drop | @FPHX
 | V [V] | Resistance (1 way) [mW] |  |  | DV [V] | V [V]
INTT | 2.5 | 135 ~ 185 | 145 | 185 | 0.20 ~ 0.25 | 2.30 ~ 2.25
FVTX |  | 70 | 70 | N/A | ~ 0.1 | 2.4
DV
Bus extender
Conversion cable
INTT Half Ladder
FVTX Ladder
FVTX Bus Extender
2.5 V
ROC Regulator
HDI
Bus Ext.
Conv. Cable
DV@FPHX
V@FPHX

## Slide 6: DV for FPHX Power Solution
FPHX regulators
(total 32/ROC)
 |  | V@ROC [V] | DV [V] /way | DV @FPHX [V]
INTT | Digital | 3.0 V | 0.20 ~ 0.25 | 2.50 ~ 2.60
 | Analogue | 2.8 V | 0.1 | 2.6
FVTX |  | 2.5 V | ~0.1 | 2.3~2.4
16 ROCs were upgraded from 2.5V regulators to 3.0V and 2.8V ones.
Full ROC boards tests are to be carried out this winter in RIKEN. (2 boards have been tested so far)

## Slide 7: backup