## Slide 1: Steps Beyond DPAP: Project Updates
Jim Yeck, EIC ALD and Project Director
ATHENA Bi-weekly Meeting
24 February 2022

## Slide 2: Project Schedule Priorities
Technical Progress with the Resources Available
  Conventional Construction
    Establish Requirements for Preliminary Design
    Secure NYS Funding
    Award A/E Contract
  Accelerator Design Maturity & Risk Reduction
    Prepare and Complete Technical Reviews and Requirements Definition
    R&D, Strong Hadron Cooling
  Detector
    Decision on Project Detector and Promoting Collaboration
    Prepare Detailed Plan for CD-2/3A
Preparing for CD-2/3A
  DOE Meeting in April and Status Review in June to assess progress and plans

## Slide 3: Issues
Funding: DOE ONP Funding Uncertainties, Growth Needed
RHIC to EIC Transition: Funding Re-directed to EIC, Staffing Plans, Conclusion of RHIC ops/Access to Accelerator Complex
Launching Project Detector: Collaboration Strength and Path to CD-2/3A
……

## Slide 4: Current Planning Assumptions Due to Impact of Continuing Resolution
Critical Decisions +6 months due to CR Impacts
  CD-2/3A: October 2023 (Originally April 2023)
  CD-3: January 2025
  CD-4A EF: January 2031
  CD-4: January 2032
  CD-4 EF: January 2032
  CD-4: January 2034
These dates are for our planning purposes only. We will adjust when DOE ONP FY2022 budget is final - March 11, and the DOE ONP Budget Request for FY2023 is released.

## Slide 5: Key Project Challenges
Cost: affordability, funding profile, in-kind, escalation
  Project cost control must remain a top priority
Accelerator Science & Technology
  Complex machine (high luminosity, polarization,…) requiring a collaborative approach to identify and address the technical issues
  BNL and JLab are working to engage international and domestic partners in these efforts
Infrastructure Schedule
  Initial pacing scope for the project with significant NYS funding
  Requires EIC technical teams to deliver timely requirements
Project Detector Baseline
  Need commitment to engage the EIC user community and clarity in the next six months on the detector scope, cost, schedule, collaboration and institutional responsibilities

## Slide 6: Summary
CD-1 approval was a major accomplishment
CD-2 and CD-3A approval will be an even bigger challenge
  Highly dependent on funding
  Overall design maturity at preliminary design level, detailed for CD-3A long lead procurements
  Organization clarified including partners
  Plan for the project detector including collaboration, in-kind plans
EIC technical progress currently constrained by the lack of funding, both NYS (pending grant) and DOE (FY2022 Continuing Resolution).