## Slide 1: 60% Design/Engineering for EIC Detector Solenoid Magnet Renuka Rajput-Ghoshal (JLab) On Behalf of EIC Detector Magnet team
Team Introduction and Project Status
Mid-Project Review
2022-06-27

## Slide 2: Outline
Team Members
Magnet Specification
Design of 1.5 T magnet
Current Status
What Next
Summary

## Slide 3: JLab- Technical Team Members
RENUKA RAJPUT-GHOSHAL
L3 CAM, JLab Project Lead, Conductor R&D, Electromagnetic design, Conductor Stability, Quench, interface between JLab and CEA, Saclay
PROBIR K. GHOSHAL Risk Analysis, FMEA, Quench, Power Supply, C&I
ERIC SUN Mechanical and Thermal Analysis
SANDESH GOPINATH, Thermal Analysis and , interface between CEA, Saclay Engineers and JLab Designers
DAN YOUNG
Designer
Catherine Hall
Designer

## Slide 4: CEA- Technical Team Members

## Slide 5: Other Team Members
JLab
  Rolf Ent- Co-Associate Director for the Experimental Program, Detector Management
  Mitch Laney, Procurement
  Giuseppina (Jessie) Tenbusch, Procurement
  Walter Wittmer, Project office
CEA, Saclay
  Lionel Quettier- Resource manager and Expert Engineer
BNL
  Elke Aschenauer- Co-Associate Director for the Experimental Program, Detector Management
  Roberto Than- Cryogenic interface
  Alexander Kiselev- HCal integration and material
  Rahul Sharma-Infrastructure interface
  Roland Wimmer- System Integration

## Slide 6: Detector Solenoid Magnet Specifications
Accelerator fringe field requirements, under further study.

## Slide 7: Design of 1.5T Magnet
The design will be divided in 60% and 90% design phase.
Conductor Quality Assessment
In parallel:
    Continue monitoring sPHENIX magnet run
    Update risk analysis based on the sPHENIX run (Details in Probir’s talk) (Sandesh’s talk on Mechanical aspects of the magnet)
    Update the Risk analysis document
    Review the results
    Make a decision about the magnet choice (existing vs replacement new)
  Prepare document for RFQ

## Slide 8: Design of 1.5 T Magnet (60% milestones)
Complete 60% design including the following:
  Complete conductor stability calculation (100%)
  Finalize the conductor E&D plan (100%)
  Start preparing conductor samples (after finalizing the vendor) (100%) ,
  Preliminary quench calculation on the selected conductor (100%) ,
  Finalize the conductor (100%)
  Finalize power supply, current leads and quench protection scheme (100%)
  Request for Information (RFI) to magnet and power supply vendors (100%)
  Detailed electromagnetic Design (60%)
  Detailed mechanical (60%)
  Thermal Analysis (60%)
  Quench Analysis (60%)
  Cryogenic Design (30%)
  I&C (10%)
  System and sub-system drawings (60%)
  Vendor search for conductor, magnet, power supply, current leads and other subsystems (60%)

## Slide 9: Work with CEA and Task List
CEA, Saclay is our collaborator for the design phase.
The existing contract is for 60% design work,
This work will be a collaborating work between JLab and CEA, Saclay.
The following tasks will be complete and delivered at the end of 60% design
Conductor stability calculations and conductor selection In Progress (Francesco’s talk)
  This task will result in finalizing the conductor.
Preliminary quench analysis (will start after finalizing the conductor)
  This task will result in a preliminary quench report. This will also help in finalizing the power supply including the current leads.
Electromagnetic design (60%) In Progress (Valerio’s talk)
  In this subcontract the following tasks will be completed for the electromagnetic design:
    Magnet design fulfills all the physics requirements including the stray field requirement (if stray field requirement is not fulfilled, an agreement has to be reached with the accelerator group for the acceptable limits of the stray field)
    The turns and layers layout are complete based on conductor dimensions
    Magnet operating parameters finalized
    Conductor length and possible piece size finalized
    Winding technique discussed and if possible finalized
    Magnetic forces calculated and given as input for the mechanical analysis

## Slide 10: Work with CEA and task list-contd.
Mechanical design (60%) In Progress (Michel and Hugo’s talk)
  In this subcontract 3-d analysis will be done using ANSYS software, showing that the main mechanical parts and stress level in all the parts are within the design limit and system is in safe operational limits. In this subcontract the following tasks will be completed for the mechanical design:
    Standard 3-d mechanical analysis using ANSYS
    Stress analysis using the gravitational load, winding, electromagnetic and thermal loads
    Make sure all the stresses are with-in the safe design and operating limits
    Material selection for all the supports and vessels
    Considered all thermal contractions and drawing adjusted to that
    Winding tension to be used on the conductor
Thermal Design (60%) will start after mechanical design
  In this subcontract 3-d analysis will be done using ANSYS software, showing the temperature distribution in the cold mass and stress while cool down the system to liquid Helium temperature. In this contract following tasks will be completed for the thermal design:
    Standard 3-d thermal analysis using ANSYS
    Thermal distribution for the mechanical analysis
    Thermal distribution for current and temperature margin
    Thermal distribution across the whole cold mass
    Decide about the rate of cooldown and warm up the cold mass
    Stress during cooldown and warm up, any limit to set on these in the controls

## Slide 11: Work with CEA and task list-contd.
Quench Analysis (60%) will start after finalizing the conductor
  The final quench analysis will be done using the standard multi-physics equations and OPERA 3-d quench modeling. The quench analysis will take input from thermal analysis, electromagnetic design. In this subcontract the following tasks will be completed for the quench analysis:
    Standard 3-d quench analysis in OPERA
    Quench validation using standard multi-physics equations
    Make sure all the temperatures in the event of quench are within the safe limits
    Make sure that the magnet stored energy is dissipated in the safe manner in the event of quench
Cryogenic design (30%) will start after this visit
  In this subcontract preliminary 3-d analysis will be done using ANSYS software, this will include the 4-K circuit design, thermal shield design, vacuum vessel design. This will also include cryo-flex and cryocan design. In this subcontract, the following tasks will be completed for the cryogenic design:
    Finalize the cooling scheme and cooling layout
    Calculated all the heat loads
    Input for thermal and mechanical design
    Input for quench analysis
Instrumentation and controls design (10%) not yet started
  This will take input from all the above sub-system designs and make a list of all the instruments to be used in the system and how to control all of these. The following tasks will be done:
    Prepare a list of all the instrumentation and control
    Preliminary electrical drawing
    Discussion with the project control person to plan the control strategy
Components, sub-systems and system drawing (60%)
Interface and Infrastructure- Damien’s talk

## Slide 12: Current Status
JLab and CEA teams are working together and collaboration is going well.
The interaction with the BNL team started and this visit will really help the project.
We are on trach to achieve 60% design by September end.
Discussions with the vendors for conductor is going on, changing Al-stabilizer to Cu- stabilizer has helped project significantly.
Working on conductor selection process.
Working on EM, Mechanical, Thermal, and quench analysis.
Cryogenic design and instrumentation and controls design will start soon.
Magnet and infrastructure discussions just started.

## Slide 13: What Next
Finalize the magnet specification.
Update BaBAR magnet risk assessment.
Complete 60% design including the following:
  Complete conductor stability calculation, finalize the conductor R&D plan, start preparing conductor samples (after finalizing the vendor), preliminary quench calculation on the selected conductor, finalize the conductor.
  Finalize power supply, current leads and quench protection scheme.
  Complete the detailed electromagnetic, mechanical, thermal and cryogenic analysis of the magnet
  Start working on I&C
  Start working on the system and sub-system drawings
Vendor search for conductor, magnet, power supply, current leads and other subsystems

## Slide 14: Summary
The design work is progressing well.
A good progress is made towards the Mid-project review,
Work is on track for the 60% design completion by end of September.

## Slide 15: Back up Slides