## Slide 1: sPHENIX Estimate At Completion MIE and I&F from May 2022 Progress Data
Glenn Young
June 23, 2022
BNL

## Slide 2: Elements Needed for the EAC
The Estimate at Completion, EAC, is an estimate of the total spending of the project
We separate the MIE and the I&F for the estimate shown here
EAC = ETC + ACWP
  ETC is Estimate to Complete i.e. estimated cost of everything we have not yet paid for, whether it is incomplete work in P6, or an unpaid invoice, or necessary work that is outside the baseline
  ACWP is Actual Cost of Work Performed and is updated monthly via P6 and COBRA, and corresponds e.g. to invoices & wages paid
If things go well, the EAC is stable from month to month

## Slide 3: Elements in the ETC
We include in the ETC:
  BCWR – the Budgeted Cost of Work Remaining
  Known must-have Additions outside the P6 scope
  Expected Value of remaining Risk Elements
  Estimate Uncertainty (EU) for remaining work
  Adjustment for unpaid invoices and known cost increases

## Slide 4: BCWR
The BCWR is developed directly from P6 EVMS data after each month’s status reporting
It is a sum over incomplete activities of the budgeted cost for that activity times the unfinished percentage of that activity
The first two tabs of the spreadsheet on the Indico PMG page cover this
We have been reporting this on the CPR spreadsheets since sPHENIX was baselined
It decreases each month if we are progressing…

## Slide 5: Known Additions
We had two known must-have additions in the MIE
  JACK board needed as an ancillary board for the TPC FEE
  Diffuse & Line Laser support items – optics, fiber links, controls
  We formally included these in the P6 baseline via PCR-030 in January 2022
We have one new addition/subtraction for the I&F
  The loss of the sPHENIX beampipe and subsequent decision to re-use the existing START pipe from their Heavy Flavor Tracker means we do not need to NEG-coat its interior (we think)

## Slide 6: Expected Value of Risk Elements
We take these from the full review of risk elements at the December 2021 Level-2 Managers meeting and updated them at the end of March 2022. Next L2 update is in late June 2022.
Risk Elements are updated monthly by the CAMs and slowly are retired as activities are completed

## Slide 7: Estimate Uncertainty
EU is updated each month as activities are completed and as items move from estimated to ordered status
For the MIE we have mostly M&S elements, with the Cat-A labor being handled as LOE
For the I&F we are including the EU only for the M&S items
EU will trend towards zero as work remaining trends towards zero

## Slide 8: Adjustments
We keep a table of adjustments that have to be made to the ETC. These total 3-5% of the EAC.
We use the monthly Budget and Expenses report as input
  The B&E report groups items by the Account #, which corresponds to WBS #
  Every active order with non-zero commitment is included
Some of these are due to unpaid invoices which have not been accrued – an issue in particular for university contracts
  These are pursued each month; some vendors are more responsive than others
Some are due to contracts which were placed well past the scheduled date in P6 and have cost changes (increases, mostly)
  In these cases we did not do a PCR to adjust the P6 baseline
Some are due to items already on order which were not included in the P6 baseline

## Slide 9: Have Chosen Not to Use Formulae
Have not used formulae, e.g. involving SPI and CPI, to project the ETC by modifying the BCWR based on prior performance
Instead add up the cost of known needed procurements using best price information
The MIE involves only M&S and fixed amounts of labor
  The apparent positive CV mostly derives from late invoices that have not been accrued. Actual CPI is likely close to 1.0
The I&F does involve labor and M&S both. CV is negative for labor

## Slide 10: Fraction of BCWR M&S To-Be-Ordered
MIE BCWR is $1.260M as of May 2022 (4.6% of $27M total)
  3% of this BCWR covers the one Baseline M&S order yet to be placed
  We added $323K labor in PCR-030 – techs and engineers not in Physics plus allowance for block completion at U Illinois
I&F BCWR is $4.156M as of May 2022 (12% of $33.4M total)
  Of this BCWR, some $0.999M is for M&S (3% of $33.4M total)
  40% of this latter amount consists of Baseline M&S orders yet to be placed
  Removed beampipe, non-scientist commissioning labor from BNL

## Slide 11: EAC for MIE

## Slide 12: EAC for I&F

## Slide 13: Tracking EAC for MIE

## Slide 14: Tracking EAC for I&F

## Slide 15: MIE M&S Items to Be Ordered

## Slide 16: I&F M&S Items to Be Ordered

## Slide 17: BCWR by Subsystem