## Slide 1: TPC Completion Schedule
TK Hemmick

## Slide 2: Overview: Time Saving Assembly
Five Pieces: Wheel 1, Wheel 2, Outer FC, Inner FC, Central Membrane
Ancillary: Gas (complexity off detector), Cooling, High Voltage, FEE (optical, LV)
Process:
  5 pieces assembled vertically
  Moved to Assembly Cart
  Ancillary Added
  System Test
  Deliver fully cabled to disconnects @ TPC outer perimeter.
Install Populated Wagon Wheels
Installation Frame
Rigging Plan (Rich Ruggiero)

## Slide 3: Schedule Overview
Philosophy:
  Marathon not sprint
  Each Day is filled with a half-day doable task.
  Any additional float is weekend.
  Google Calendars accessible and editable by group.
FEE Drives the Schedule
  FEE installation driven by rework completion.
June
July

## Slide 4
Present Schedule Completes all KPP by Sept 30.
  IBF: Done (from Xray tests)
  Crosstalk: from FEE characterization
  Live channels: pulser on detector
  Efficiency: 3 weeks running time
August
September

## Slide 5: High Level Overview
June
July
August
Sept
Oct
Testing
Central membrane
Outer field cage
Main Assembly
Float
ship
Nov
 | Start | End | Milestone | Milestone | Milestone | Milestone | Milestone | Milestone
Central Membrane | ongoing | August 1 | Petal Survey 1 July 13 | Petal Survey 2 July 19 | Side 1 Setup July 20 | Side 2 Setup July 27 | Delivery August 1 | 
Outer FC | ongoing | August 5 | Kapton Done July 12 | Honeycomb August 3 | Delivery August 5 |  |  | 
Main Assembly | July 27 | September 30 | WW1 Up August 3 | Field Cages August 9 | Membrane August 15 | WW2 August 15 | Cart move August 17 | Cooling August 23
Testing | August 26 | September 30 | Pulser Test 1 Sept 9 | Pulser Test 2 Sept 30 | MIP Sept 30 |  |  | 
Red means KPP