## Slide 1: TPC Completion Schedule
TK Hemmick

## Slide 2: Outer Field Cage Completion
Using weekends to keep weekly schedule.
Henry Klest reconfigured tensioner to meet first deadline early.
Early Finish by two days
Early Start by two days
Two Seams at Once
Tensioner Work

## Slide 3: Central Membrane
Mediation for Schedule Slip:
  Machined Petal Holder on a Saturday.
  Add Prakhar Garg to BNL Team.
  Petal Programming is shorter than estimated
    Not CODE.
    Machine memorizes Joystick.
Jig Assembled and In Use
Petal Holder Design
No picture (sorry)
Holder already at BNL
Programming Today

## Slide 4: Not Yet Scheduled to be Started.
CM slip has not pushed the completion (yet) due to 11 days float