## Slide 1: TPC Completion Schedule
TK Hemmick

## Slide 2: TPC Non-Electrical Services (Done)
Where we left off
Cooling fully installed and leak free (wide hoses temporary)
Wide Tubes
Narrow Tubes
Laser Port
Gas Fittings in Clean Room
Close Up
Leak Down
Gas Flows 24/7
Ar/CF4

## Slide 3: TPC Electrical Services
HV cards:
  75% = “chain”, 25% = “mirror”
  Mirror on hand, chain promised 10/21.
  Company claims COVID delay.
  Maybe Friday, but not promised.
DC Low Voltage
MirrorCards
Pedestals Read (SBU…not BNL)
FEE cards:
  All cards exist
  require burn-in, test, FPGA
  50% done.
Tension between goals:
  Can do “live channels” test before HV cards.
  Would require disassembly of FEE when HV arrives.
Mini TPC Tracks
Mitigation (enhanced readiness):
  MIP & Laser tracks in MiniTPC at BNL
  Pedestals at SBU