## Slide 1: sPHENIX Estimate At Completion MIE and I&F from September 2022 Progress Data
Glenn Young
October 27, 2022
BNL

## Slide 2: Elements Needed for the EAC
The Estimate at Completion, EAC, is an estimate of the total spending of the project
We separate the MIE and the I&F for the estimate shown here
EAC = ETC + ACWP
  ETC is Estimate to Complete i.e. estimated cost of everything we have not yet paid for, whether it is incomplete work in P6, or an unpaid invoice, or necessary work that is outside the baseline
  ACWP is Actual Cost of Work Performed and is updated monthly via P6 and COBRA, and corresponds e.g. to invoices & wages paid
If things go well, the EAC is stable from month to month

## Slide 3: Elements in the ETC
We include in the ETC:
  BCWR – the Budgeted Cost of Work Remaining
  Known must-have Additions outside the P6 scope
  Expected Value of remaining Risk Elements
  Estimate Uncertainty (EU) for remaining work
  Adjustment for unpaid invoices and known cost increases

## Slide 4: BCWR
The BCWR is developed directly from P6 EVMS data after each month’s status reporting
It is a sum over incomplete activities of the budgeted cost for that activity times the unfinished percentage of that activity
The first two tabs of the spreadsheet on the Indico PMG page cover this
We have been reporting this on the CPR spreadsheets since sPHENIX was baselined
It decreases each month if we are progressing…

## Slide 5: Known Additions/Subtractions
We had three subtractions in the MIE
  Diffuse lasers and associated fiber-bundles (for the TPC)
  Extra DCM-II modules (from DAQ)
We had two subtractions for the I&F
  The loss of the sPHENIX beampipe and subsequent decision to re-use the existing STAR pipe from their Heavy Flavor Tracker means we do not need to NEG-coat its interior
  We have removed the procurement of the seismic restraints

## Slide 6: Expected Value of Risk Elements
We take these from the full review of risk elements at the December 2021 Level-2 Managers meeting and updated them at the end of March 2022. L2 update in late June 2022 yielded no changes to the risk elements at that time
Risk Elements are updated monthly by the CAMs and slowly are retired as activities are completed

## Slide 7: Estimate Uncertainty
EU is updated each month as activities are completed and as items move from estimated to ordered status
For the MIE we have mostly M&S elements, with the Cat-A labor being handled as LOE
For the I&F we are including the EU only for the M&S items
EU will trend towards zero as work remaining trends towards zero

## Slide 8: Adjustments
We keep a table of adjustments that have to be made to the ETC. These total 2-3% of the EAC.
We use the monthly Budget and Expenses report as input
  The B&E report groups items by the Account #, which corresponds to WBS #
  Every active order with non-zero commitment is included
Some of these are due to unpaid invoices which have not been accrued – an issue in particular for university contracts
  These are pursued each month; some vendors are more responsive than others
Some are due to contracts which were placed well past the scheduled date in P6 and have cost changes (increases, mostly)
  In these cases we did not do a PCR to adjust the P6 baseline
Some are due to items already on order which were not included in the P6 baseline

## Slide 9: Have Chosen Not to Use Formulae
Have not used formulae, e.g. involving SPI and CPI, to project the ETC by modifying the BCWR based on prior performance
Instead add up the cost of known needed procurements using best price information
The MIE involves only M&S and fixed amounts of labor.
  The labor is now complete. Only one M&S item will be open after taking October 2022 progress
The I&F does involve labor and M&S both. CV is negative for labor

## Slide 10: Fraction of BCWR M&S To-Be-Ordered
MIE BCWR is $0.198M as of August 2022 (0.7% of $27M total)
  0% of this BCWR covers Baseline M&S orders yet to be placed
I&F BCWR is $1.829M as of August 2022 (5.5% of $33.4M total)
  Of this BCWR, some $0.110M is for M&S (0.3% of $33.4M total)
  75% of this latter amount consists of Baseline M&S orders yet to be placed
  Removed beampipe, seismic restraints

## Slide 11: EAC for MIE

## Slide 12: Remark on EAC for MIE
We have done a PCR to remove the Diffuse Lasers, their Fiber Optic splitters, and the DCM-II boards from the P6 plan for the MIE
At present, this just removes them from the P6 plan, leaving the BA alone (thus increasing the apparent MIE contingency)
We also still have them as commitments, i.e. as ”live” POs. As far as the EAC, this means they “null out” on the EAC
A forthcoming B&R change from DOE HQ will remove the funds from the MIE, at which point the open POs will also be assigned to a corresponding new non-MIE account

## Slide 13: EAC for I&F

## Slide 14: Tracking EAC for MIE

## Slide 15: Tracking EAC for I&F

## Slide 16: MIE M&S Items to Be Ordered

## Slide 17: I&F M&S Items to Be Ordered

## Slide 18: BCWR by Subsystem

## Slide 19: ReCharge Hours Aug 21 – Sept 30 2022
Cat A 120 ends after Sept – TPC FEE work
Cat B 902.5 TPC FEE work – ends once JACK boards done
Cat C 579.5 Infrastructure fabrication & installation
All from AM and IO divisions