## Slide 1: sPHENIX End Game Review Project Organization and Resources
Glenn R. Young
October 13, 2022
BNL

## Slide 2
DOE- Office of Nuclear Physics
T. Hallman
Associate Director of the Office of Science for Nuclear Physics
E. Bartosz
Federal Program Manager
BNL Director’s Office
D. Gibbs
Laboratory Director
BNL Nuclear and Particle Physics Directorate
H. Gao
Associate Lab Director for Nuclear & Particle Physics
M. Chamizo-Llatas
Deputy Assoc. Lab Director for Strategic Planning
sPHENIX Project Office
E. O’Brien Project Director
G. Young Project Manager
J. Haggerty Project Scientist
J. Mills Project Engineer
R. Feder Chief Mechanical Engineer
I. Sourikova Project Controls Manager
Project Management Office
WBS 1.1
I. Sourikova
R. Gutta
BNL Physics Dept
H. Ma
J. Dunlop
sPHENIX Collaboration
Co-Spokespersons
D. Morrison
G. Roland
MIE Level-2 Managers
T. Hemmick 1.2 Time Projection Chamber
C. Woody 1.3 EM Calorimeter
J. Lajoie 1.4 Hadronic Calorimeter
E. Mannel 1.5 Calorimeter Electronics
M. Purschke 1.6 DAQ/Trigger
M. Chiu 1.7 Minimum Bias Detector
Project Support Office
L. Stiegler ES&H
M. Romero QA
Project Management Group
Project Office of System Integration
R. Feder Chief System/Integration Engineer
BNL Collider Accelerator Dept
W. Fischer
DOE –Brookhaven Site Office
R. Gordon
Site Manager
R. Caradonna
BHSO Point of Contact
I&F Level-2 Managers
K. Yip 2.2 SC-Magnet
C. Pontieri 2.3 Carriage & Structural Comps
J. Vasquez 2.4 Infrastructure
R. Feder 2.5 Installation & Integration
Silicon Detector Level-2 Managers
R. Nouicer/I. Nakagawa 3.1 INTT
M. Liu 3.2 MVTX

## Slide 3: sPHENIX MIE L2 and L3 Management Structure
1.01 sPHENIX Project Management I. Sourikova (BNL)
1.02 sPHENIX TPC T. Hemmick (SBU)
1.02.01 TPC Mechanics K. Dehmelt (SBU)
1.02.02 TPC R1 Modules W. Llope (WSU)
1.02.03 TPC R2 Modules V. Greene (Vanderbilt)
1.02.04 TPC R3 Modules S. Milov (WIS) M. Posik (Temple)
1.02.05 TPC FEE T. Sakaguchi (BNL)
1.02.06 TPC DAM J. Huang (BNL)
1.02.07 TPC Support Systems R. Pisani (BNL)
1.03 sPHENIX EMCal C. Woody (BNL)
1.03.01 EMCAL Block Production C. Riedl (UIUC)
1.03.02 EMCAL Module Production and Sector Assembly S. Stoll (BNL)
1.04 sPHENIX HCal J. Lajoie (ISU)
1.04.01 Inner HCal Frame J. Lajoie (ISU)
1.04.02 Outer HCal Mech Structure C. Pontieri (BNL)
1.05 sPHENIX Cal Electronics E. Mannel (BNL)(BNL)
1.05.01 Optical Sensors C. Aidala (UM)
1.05.02 Calorimeter Front End Electronics S. Boose (BNL)
1.05.03 Calorimeter Digitizer System CY Chi (Columbia)
1.06 sPHENIX DAQ & Trigger M. Purschke(BNL)
1.06.01 DAQ M. Purschke (BNL)
1.06.02 Trigger (LL1) J. Nagle (UCol)
1.06.03 Global Level 1 (GL1) M. Purschke (BNL)
1.06.04 Timing System M. Purschke (BNL)
1.07 sPHENIX MinBias Trigger Detector M. Chiu (BNL)
1.04.03
Outer HCal Scintillating Tiles
M. Connors (GSU)
1.04.04
Outer HCal Assembly & Testing
S. Bathe (CUNY-Baruch)
WBS Code WBS Name Owner
WBS Code WBS Name Owner
Level 2: Level 3:
Key:
All Control Accounts are Managed at Level 2

## Slide 4: 1008 I&F Management Structure
2.01 I&F Management I. Sourikova
2.02 SC-Magnet K. Yip
2.02.01 Reviews & Tests K. Yip
2.02.02 Transport & Assembly M. Anerella
2.02.03 Cryogenics P. Orfin
2.02.04 PS, Controls, Quench Protection C. Shultheiss
2.02.05 Magnet Mapping J. Haggerty
2.03 Carriage & Structural Components C. Pontieri
2.03.01
Carriage/Cradle J. Mills
2.03.03 Magnet Barrel Steel C. Pontieri
2.04 Infrastructure J. Vasquez
2.04.01 Detector Support Services J. Vasquez
2.04.02 Facility Support Services M. Albanese
2.05
Installation Integration
R. Feder
2.03.04
End Caps/Pole tips
J. Mills
2.03.02
Inner Rings
C. Pontieri
2.03.05 Bridge, Platforms & Access J. Mills
All Control Account Managers are at L2

## Slide 5: I&F Upgrade Project Management
I&F Upgrade Project Management at BNL, staffed by BNL
  Includes Project Director, Project Manager, Project Scientist, Project Engineer, ES&H rep, QA rep, Chief Mechanical Engineer, Project Controls Manager and staff, Integration
  Significant experience – core of scientific and engineering group that built PHENIX and operated it for 16 years; project controls group experienced on several other completed DOE-413-type projects
L2 Managers/CAMs, L3 Managers: BNL staff
Charge Question #8

## Slide 6: I&F Upgrade Project Organization
BNL Staff direct, engineer, design, and perform the Infrastructure and Facilities work
  Superconducting Magnet and all support systems
  Cradle/Carriage, Inner Detector Supports, Platforms
  Magnet Steel: yoke and pole tips
  Infrastructure upgrades
    Detector - AC Power, Cabling/Fiber Optics and tray systems, Racks, Gas & Cooling Systems, Assembly Hall, Counting House
    Facility - Supports for Electrical & Cryogenic Services, AC power, HVAC, IR Cooling Water Supply, Safety Systems, Track Modifications
  Installation
    BNL handles mechanical rigging-in; designs and has fabricated all installation tooling & fixturing
    University and all Lab groups all participate in the in-situ testing step
Charge Question #3

## Slide 7: I&F Upgrade Labor Resources
Engineering and Design Staff from
  Physics
  Collider-Accelerator (CAD)
  Advanced Technology Research Organization (ATRO)
  Superconducting Magnet (SMD)
Installation phase is led by BNL staff (Physics, Collider-Accelerator)
Cabling and later in-situ testing work depends upon outside contributions in addition to BNL staff
  University staff
  Staff from other Laboratories: RIKEN/LANL/LBNL/MIT-LNS/Columbia-Nevis
Charge Question #3

## Slide 8: I&F Upgrade MOAs
Memoranda of Agreement between sPHENIX and these other BNL organizations address
  activities and personnel involved
  amounts and duration of the planned effort
All five are complete, updated, (posted on Indico page at top):
  Physics
  C-AD for Magnet and Carriage/Cradle
  Advanced Technology Research Organization (ATRO) for TPC and DAQ including installation
  SMD for Engineering/FEA
  C-AD for Infrastructure improvements
Charge Question #3

## Slide 9: Labor Needs going forward
Experience of past 7 months is that our actual labor use is running twice the baseline estimate – dominated as expected by Magnet, Infrastructure, Installation efforts
Reviewed remaining task list in ResourceLoadedSchedule (“P6”) – resulting estimates are now double the baseline number
  Excel file attached to Indico page
Actual use is 39.9K hours over past 7 months (38.9 FTE)
Estimate 31.1K hours of remaining effort (35.3 FTE for 6 months)
  Physics – 15.7K hours
  CAD – 7.2K hours
  Collaborators – 8.2K hours (note: this expands the prior labor pool)

## Slide 10
Need to Fully Staff Five Parallel Workstreams
Parallel Work Streams | Parallel Work Streams | sPHENIX Staff | C-AD Staff | Collab staff
Detectors | sPHENIX detector install Detector services On-carriage water and gas Gas lines and gas house Electronics fab and testing in 510 | 12.5 |  | 9.5
On-carriage Infrastructure | Racks, rack plumbing and wiring Electrical work on and off carriage DAC and Control Room | 4 |  | 
Off-carriage Infrastructure | ECW up to racks and panels Chiller platform, chilled lines to carriage Chiller units install (new scope) Beam pipe install, bake Shield wall and run prep |  | 3 | 
Magnet | Magnet electrical systems Magnet cryo systems |  | 2.5 | 
Manage | Supervision Project engineering Work planning Reviews and reporting | 3 |  | 

## Slide 11: Tasks and Resource Needs
Existing incomplete tasks from P6 were listed with resources by type.
A review with the CAMs was done to expand the detail of remaining work and estimate the needed resources and any changes in durations, with reference to Russ’ schedule
Next slide shows a small sample of existing P6 incomplete tasks ( cells in pink-orange) and added effort (cells in blue)
There are some 200 tasks remaining with these revisions. Further detailed breakdown will be done for daily work planning

## Slide 12: Tasks Listed with Resource Needs

## Slide 13: Recommendation #1 – Resources vs Time
The hours for various resource types (e.g. Sci, Prof, Tech, Electrician) for task groups were spread evenly over an assumed duration, with a start time and duration taken from Russ’ overall schedule.
A typical task group would be “Install TPC and Services” or “Install EMCal Services”
We did not include management, magnet work or the current effort to install the first 23 pairs of EMCal sectors. These efforts are staffed with known persons. We included all the rest, including the safety and procedure work.
Working copy of Excel file is on Indico page

## Slide 14: Typical Task Group Resources vs. Week #

## Slide 15: Total Resources vs Time
The hours for each skillset were summed over all task groups as a function of week number
This was then converted to persons/week of a given skillset by dividing by 40 hours/week
Cases where more than 3 or 5 persons of a given skillset are planned for a given week are highlighted in blue (≥3) or green (≥5)
This gives a rough initial guess – “EXCEL block schedule”
The better-detailed version is being done in P6

## Slide 16: Number of Persons for a Skillset vs Week #

## Slide 17: Total Hours by Personnel Category

## Slide 18: P6 Progress File Version
All added tasks and resource changes to existing tasks are added to a copy of the sPHENIX P6 Progress file, with data date Nov 1, 2022
Links are added. Most tasks are expansions of the P6 workflow already present, although installing the TPOT and sEPD are new. Russ’ schedule has been consulted heavily
BNL resources have been loaded. Collaboration resources are being added today. Some tweaks are being made also
We can then project task resource needs on a week-by-week basis
  A test-run example is on the Indico page
Normal “progressing” of P6 yields remaining resource needs with time as work is completed and marked off

## Slide 19: Remarks on Skillset vs Time (1)
There is a particular demand for Tech M through January. A particular push is to prepare cooling and gas panels and distribution lines, which effort comprises over 15% of the remaining total effort. These Techs tend to be listed as from Physics (Tech PO M) but can as well come from CAD (Tech AD M).
Electricians are critical for the next 2-3 months because rack power and thus detector testing and seeing data in the Control Room depend on this.
There is a “lull” in the schedule starting Feb 20 to allow for beampipe installation and INTT support installation (these two items are co-dependent) and beampipe bakeout. It is reasonable to expect some activities for TPC and TPot services hookup and tests to extend into this period, relieving resource pressure earlier and helping with load-leveling the resource needs over time.

## Slide 20: Remarks on Skillset vs Time (2)
There is a likely an underestimate on Tech E. Some tasks assigned to Tech M may well be better done by Tech E. There is time pressure on EMCal to finish their services, especially on the top sectors, due to their need for scaffolding that interferes with TPC installation.
I regard the sPHENIX Collaboration as a “heat bath” when it comes to staffing all calls for SCI, PD, GS and the like. A collaboration of over 400 persons can easily have over a dozen scientific persons in residence at BNL at any given time. This in fact is already in progress. The Calibration and Commissioning task force headed by J. Haggerty (BNL) and C. Riedl (U. Illinois) is already organizing this. This is an essential step in the “tech transfer” from the DAQ and Slow Controls experts to the Collaboration membership at large in anticipation of starting up full subsystems and keeping them “live” for e.g. cosmic data.

## Slide 21: Back Up

## Slide 22: I&F Upgrade Large Procurements - DONE
Infrastructure/Facilities has four major >$1M procurements
  Barrel Steel (2.3.3) – placed ($5.6M) – completed August 2019, installed
  Cradle/Carriage (2.3.1) – placed ($1.1M) - completed December 2020, installed
  Helium Interface for cryogenics (2.2.3) – placed ($1.56M); completed July 2022, installed
  Track strengthening (2.4.2) - placed ($1.0M); completed in-situ Nov 2021
Eight other procurements over $100K
  Pole tips (2.3.4) – placed ($880K), completed February 2022, installed
  Bridge/Platforms (2.3.5) – placed ($320K), completed April 2022, installed
  Large Support Rings (2.3.2) – placed ($300K), completed October 2021, installed
  LN2 transfer system (2.2.3) – placed ($229K), completed March 2022, installed
  Cryogenics controls (2.2.3) – placed ($160K), completed July 2022, installed
  Cooling Services (2.4.1) - placed ($100K), completed September 2022
  Inner HCal insertion fixture (2.5.6) – placed ($297K), completed March 2022, used to install IHCal June 2022
Charge Question #1

## Slide 23: Issues and Concerns
Skillsets at BNL – Schedule
  Skilled trade work remaining, particularly electrician work
  Must coordinate with other parts of BNL due to limited resource pool at the Lab
Scheduling Collaborating Groups - Schedule
  Detector checkout after installation is complex and involves several groups
  BNL techs for work at heights on cable installation
  BNL techs for critical gas and cooling system hookup
  BNL sPHENIX DAQ group for general test system operation, plus ‘tech-transfer’ to collaborators on each subsystem
  Collaborating groups on checking correctness of cabling, detector element performance, recording of test results
  Time for iterating the tests and checking results

## Slide 24: Summary
We have the team and plans in place to install and test sPHENIX
Collaboration groups have made plans for testing in-situ
Major fabrication is finished
Installation is advanced
Time is approaching for early live operation of detector subsystems

## Slide 25: I&F Upgrade Project Scope
Superconducting Magnet and support systems
  associated cryogenics (LHe, LN2, warm piping), links to RHIC cryogen lines
  power supply and quench detection system
  controls
Cradle/Carriage to support all parts of the experiment
  Internal detector supports, upgrades to rail system (twice mass of old PHENIX)
  Platforms, bridge, access items, stairs, motion control, seismic restraints
Magnet steel: Barrel Yoke (doubles as Outer HCal absorber) and Pole Tips
Infrastructure improvements to Building 1008 complex
Installation of all items
Testing in-situ of all items

## Slide 26: I&F Upgrade Internal Reviews
All construction underwent a series of reviews
  Design: conceptual, intermediate, final
  Performance evaluation after prototyping step
  Procurement (or production) readiness
  ESHQ check
A series of reviews of the installation plans has been held
  Reports on the Indico sites of the various reviews
  Interfaces check to other systems
  Schedule dependencies & installation order
    Quite detailed for the tracking/silicon/beampipe installation
Charge Questions #2,4,5

## Slide 27: Homework Question #7 (from 4/2021)
Elaborate the reasons behind the reduction of schedule float and how much it is reduced by.
The I&F Upgrade Baseline schedule of October 2019 was prepared using the then-current RHIC run schedule from mid-CY2019. This had RHIC Run 22 ending on 12/31/2021. The I&F Upgrade baseline plan used the ensuing 3 months to prepare items on the platforms, in particular cryogenics and power supply/quench detector items associated with the BaBar magnet and complete the installation of the EMCal.
Roll-in of sPHENIX to the 1008 IR for the baseline plan was set to be complete by April 4, 2022. The shield wall removal was planned to happen during March 2022, prior to roll-in.
RHIC had to suspend operations in March 2020 due to COVID-19. In order to operate for the agreed-upon number of cryoweeks, the ongoing RHIC Run 21 had to be extended to end July 2021, meaning RHIC Run 22 had to be pushed back 3 months to end on April 4, 2022.
The shield wall opening thus cannot start until April 4, 2022 and requires 20 days for wall-removal and sPHENIX roll-in. This has been recently estimated under two scenarios addressing specifics of the tracks (whether a grout-line will have to be broken).
Key activities immediately after roll-in center upon completing and testing the magnet’s cryogenic circuits and their controls, power supply connection and quench detector operation. These can only be done once sPHENIX is in the 1008 IR and can make contact with the needed linkages for these circuits on the West Wall of 1008IR.
The I&C schedule contingency (float) is thus expected to be reduced by these 20 days.

## Slide 28: sPHENIX Project Team Experience
John Haggerty
Project Scientist
Senior Scientist, Physics Department, BNL
Relevant Experience BNL AGS/E-787 1986-1996, DAQ and 500 MHz waveform digitizers; PHENIX Deputy Project Manager, 1997-2001; PHENIX Data Acquisition Coordinator, 2001-2007; PHENIX Deputy Operations Director, 2008-2016; PHENIX Run Coordinator 2009-2010; sPHENIX management 2012-present. Design, construction, implementation, and software support for PHENIX timing system, slow controls of front end electronics, high speed PCI interface to DAQ. Managed BaBar solenoid move to BNL. Lead Scientist for Fermilab T1044, the prototype sPHENIX Calorimeter test, 2014-2018.
Edward O’Brien
Project Director
Senior Scientist, Physics Department, BNL
Relevant Experience
Seven years as sPHENIX Project Director. Thirteen years as PHENIX Operations Director during which time he coordinated the addition of $25M in upgrade detectors to PHENIX and managed a staff of 25-30 FTEs. Four years as project manager of the $10M PHENIX Central Tracking system. Eight years as head of the PHENIX Central Tracking group and Project Manager of the $4M Time Expansion Chamber. Designed and built major components of the E814/E877 Tracking System, a BNL AGS fixed-target HI experiment.
Glenn Young
Project Manager
Senior Scientist, Physics Department, BNL
Relevant Experience
Glenn Young was at Oak Ridge National Laboratory from 1978 until 2009, serving in many capacities, including Physics Division Director. He led ORNL’s work on a series of heavy ion experiments at CERN (WA80, WA93, WA98). He was one of the founders of the PHENIX experiment in 1991 and led contributions by the Oak Ridge group to many PHENIX systems, and served as the experiment’s Deputy Spokesperson. He went to Thomas Jefferson National Accelerator Facility in 2009, and led the experimental program for the 12 GeV upgrade. He joined sPHENIX as Project Manager in 2017.
Charge Question # 8

## Slide 29: sPHENIX Project Team Experience
Irina Sourikova, PMP
Project Controls
Physics Department, BNL
Advanced Applications Engineer
Relevant Experience Sixteen years as PHENIX software Engineer, database developer and database administrator. Designed, implemented and supported PHENIX calibrations and collaboration databases providing legacy data migration, data archival and replication. SIx years as sPHENIX Project Controls. Certified Project Management Professional.
James Mills, P.E.
Project Engineer
Senior Project Engineer, Collider-Accelerator Department, BNL
Relevant Experience Over 39 years of Engineering and Project Management experience at Brookhaven National Laboratory. 8 years as Manager of the Modernization Project Office Engineering and Design Group (2006-2014) with overall responsibility for the successful completion of a portfolio of projects in excess of $15 million annually; 6 years as Project Engineer for conventional construction in support of facility operations at Brookhaven (2000-2006); managing projects up to $6 million in total scope. 4 years of experience as Head of the Facility and Experimental Support Group, RHIC Project (1996-2000). Responsible for approximately $13 million dollars of conventional construction in support of experiments at RHIC. 6 years as Project Engineer for the STAR Magnet (1990-1996), providing engineering analysis and design of the 0.5 Tesla solenoidal magnet.
Russ Feder, P.E., PMP
Chief Mechanical Engineer
Mechanical Engineer, Physics Department, BNL
Relevant Experience
Twenty eight years as a Mechanical Engineer including nineteen years at Princeton Plasma Physics Lab (PPPL). Most recently served as Project Manager for the NSTX-U Recovery Project and before that spent seven years as Chief Mechanical Engineer and WBS Manager for US ITER diagnostic systems contributions to ITER. M.S. in Nuclear and Mechanical Engineering and has experience in structural analysis, nuclear shielding, optical design and various aspects of engineering management.
The sPHENIX team has decades of experience managing DOE (NP, BES, HEP, FES and ASRC) projects, including sPHENIX, PHENIX, JLab 12-GeV, STAR, BNL F&O, ITER, NSTX-U…
Charge Question # 8