## Task vs Skillset
Task | JOB GROUP | Task Sum | SCI PO | PROF PO | TECH PO M | TECH PO E | SCI AD | PROF AD | TECH AD M | TECH AD E | Electrician | Rigger | Surveyor | SCI Labs | TECH Labs | PD Labs | SCI UNIV | PD UNIV | GS UNIV | US UNIV
Infrastructure management | 0 | 40 |  | 40
Detector Support systems management | 0 | 113 |  | 113
Facility Support systems management | 0 | 113 | [5 empty] | 113
Installation management | 0 | 282 |  | 282
Magnet Safety Reviews | 4 | 16 |  |  |  |  | 8 | 8
Magnet PSU Work - cabling, WCB, testing | 4 | 241 | [5 empty] | 52 | 123 |  |  |  | 66
Magnet Cryo Ops - Cooldown | 4 | 171 | [5 empty] | 114 | 57
Magnet Cryo Ops - test at 4.5K (heat load, lo power, hi power) | 4 | 544 |  |  |  |  | 160 | 216 | 168
Magnet Mapping preparations - Hall Probes | 4 | 97 | 19 | 19 |  | 59
Magnet Mapping preparations - construct support | 4 | 13 |  |  | 13
Magnet Mapping preparations - install and test mapper | 4 | 480 | 160 | 80 | 80 | 160
Magnet Field Mapping | 4 | 560 | 160 | 80 | 240 | 80
Removal of mapper (listed under TPC installation) | 4 | 0
Acceptance TPC Supports | 0 | 80 |  | 40 | 40
Acceptance MBD Supports | 0 | 20 |  | 10 | 10
Acceptance Beamline Supports | 0 | 72 |  | 36 | 36
Rack Assembly - Lower East | 2 | 6 |  |  |  | 6
Rack Assembly - Upper Platform | 2 | 40 |  |  |  | 40
ADDED RACK ASSEMBLY EFFORT, BASED ON EFFORT TO DATE | 2 | 500 |  |  |  | 500
Design, procure, test remaining cooling system items | 1 | 180 |  | 100 | 80
Cooling System Panel Fabrication - TPC | 1 | 138 |  | 8 | 130
Cooling System Panel Fabrication - TPot | 1 | 64 |  | 4 | 60
Cooling System Panel Fabrication - EMCal SiPM | 1 | 290 |  |  | 290
Cooling System Panel Fabrication - EMCal PreAmp | 1 | 290 |  |  | 290
Cooling System Panel Fabrication - INTT ROC | 1 | 120 |  |  | 120
Cooling System Panel Fabrication - INTT Stave | 1 | 120 |  |  | 120
Cooling System Panel Fabrication - MVTX | 1 | 80 |  |  | 80
Cooling System Platform Manifolding | 1 | 124 |  | 24 | 100
Design, procure, test remaining gas system items | 1 | 270 |  | 120 | 150
Gas Distribution Panel Fabrication - TPC Ar-CF4 | 1 | 100 |  |  | 100
Gas Distribution Panel Fabrication - TPC Laser N2 | 1 | 40 |  |  | 40
Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 1 | 84 |  | 4 | 80
Gas Distribution Panel Fabrication - EMCal SiPM N2 | 1 | 40 |  |  | 40
Gas Distribution Panel Fabrication - INTT Stave N2 | 1 | 40 |  |  | 40
Gas Distribution Panel Fabrication - MVTX N2 | 1 | 8 |  |  | 8
Gas Distribution Panel Fabrication - MBD dry compressed air | 1 | 40 |  |  | 40
Fabricate Detector Safety Systems | 1 | 120 |  |  | 60 | 60
Design IR/AH Safety Systems | 2 | 120 |  | 80 | 40
Procure IR/AH Safety Systems | 3 | 229 | [5 empty] | 115 | 114
INSTALLATION AFTER THIS POINT
Install Line Electric Power - off detector | 3 | 24 |  | 4 |  |  |  | 4 |  |  | 16
Install Line Electric Power - on detector | 2 | 120 |  | 34 |  |  |  | 18 |  |  | 68
Install Off-detector Safety Systems, inc VESDA | 3 | 120 | [5 empty] | 42 | 60 | 0 | 18
Install On-detector Safety Systems | 2 | 144 |  | 36 | 36 | 72
Install On-detector Cooling water supply lines | 2 | 133 |  | 18 | 86 | [6 empty] | 29
General support for gas and cooling systems for detectors | 2 | 936 |  | 120 | 816
HVAC work | 3 | 18 | [5 empty] | 8 | 4 |  | 6
Install non-IR Infrastructure | 3 | 250 |  | 40 | 40 | 40 |  | 10 | 40 | 40 |  | 40
Install Racks on All Carriage Platforms | 2 | 568 |  | 160 | 220 | 188
Install AC power to Racks - Lower platforms | 2 | 120 | [8 empty] | 120
Install AC power to Racks - Middle platforms | 2 | 120 | [8 empty] | 120
Install AC power to Racks - Upper platforms | 2 | 480 | [8 empty] | 480
Complete lighting and convenience power | 2 | 80 | [8 empty] | 80
Complete wiring of chiller platform | 2 | 40 | [8 empty] | 40
Complete wiring of N & S Pole Tip doors and motors | 2 | 80 | [8 empty] | 80
Complete on-detector 24V-DC distribution system | 2 | 120 | [7 empty] | 80 | 40
Complete global interlock system | 2 | 80 | [7 empty] | 80
Complete ODH, crash, sweeps - CAD PASS | 2 | 40 | [7 empty] | 40
Complete rack interlock system (36 racks) | 2 | 160 | [7 empty] | 160
Complete FAP and HSSP - Fire Alarm group | 2 | 40 | [7 empty] | 40
Complete network installation | 2 | 80 | [7 empty] | 80
Complete ECW water leak detection | 2 | 80 | [7 empty] | 80
Complete contactor boxes for interlock system | 2 | 120 | [7 empty] | 120
Complete VESDA north/south solenoid - piping (sEPD area) | 2 | 120 | [6 empty] | 80 | 40
Complete I/O terminations Rack 3B1 | 2 | 240 | [7 empty] | 240
Test rack interlock system | 2 | 120 |  | 80 | [5 empty] | 40
Test global interlock system | 2 | 120 |  | 80 | [5 empty] | 40
Control system programming | 2 | 120 |  | 120
Control system HMI and usage testing | 2 | 120 |  | 120
Off Carriage Water Lines & Flow Control - Sill & Labyrinth area | 3 | 80 | [6 empty] | 80
Off Carriage Water Lines & Flow Control - Chiller Platforms | 3 | 80 | [6 empty] | 80
Off Carriage Water - ECW to 'brass block' | 3 | 40 | [6 empty] | 40
Off Carriage Water - Brass block to chillers | 3 | 40 |  |  | 40
Off Carriage Water - Chiller panels to cooling lines | 3 | 80 | [6 empty] | 80
Off Carriage Water - Bridge lines | 3 | 40 | [6 empty] | 40
Off Carriage Water - Bridges to on-carriage panels | 3 | 80 | [6 empty] | 80
Off Carriage Water - Carriage ECW to on-carriage panels | 2 | 80 |  |  | 80
Install Rack Cooling water - Lower platforms | 3 | 80 | [6 empty] | 80
Install Rack Cooling water - Middle platforms | 3 | 80 | [6 empty] | 80
Install Rack Cooling water - Upper platforms | 3 | 320 | [6 empty] | 320
Install Rack Protection systems - Lower platform | 2 | 40 |  |  |  | 40
Install Rack Protection systems - Middle platform | 2 | 40 |  |  |  | 40
Install Rack Protection systems - Upper platform | 2 | 160 |  |  |  | 160
Build North and South Work platforms | 1 | 21 |  |  | 21
Install remaining OHCal cables - LV, bias, signal, control | 1 | 32 |  | 8 | 8 | 16
Check OHCal operation during cabling | 1 | 200 | 40 | [13 empty] | 80 | 80
Install OHCal gas distribution panels and route lines | 1 | 40 |  |  | 40
Check OHCal operation with slow controls (LV, bias, temp) | 1 | 200 | 40 | [13 empty] | 80 | 80
Check OHCal operation with DAQ in counting house | 1 | 200 | 40 | [13 empty] | 80 | 80
Install IHCal cables - LV, bias, signal, control | 1 | 320 |  | 80 | 80 | 160
Check IHCal operation during cabling | 1 | 200 | 40 | [13 empty] | 80 | 80
Install IHCal gas distribution panels and route lines | 1 | 40 |  |  | 40
Check IHCal operation with slow controls (LV, bias, temp) | 1 | 200 | 40 | [13 empty] | 80 | 80
Check IHCal operation with DAQ in counting house | 1 | 200 | 40 | [13 empty] | 80 | 80
Check EMCal sectors 24-32 prior to leaving Bldg 510 | 1 | 160 |  |  |  | 80 | [11 empty] | 80
Transport EMCal sectors 24-32 to 1008 AH | 1 | 85 |  | 4 | 28 | [6 empty] | 53
Open magnet pole tips | 1 | 20 |  | 4 | 16
Remove magnet mapping apparatus | 1 | 136 | 16 |  | 40 | 80
Install EMCal Sectors 24 - 32 | 1 | 320 |  | 32 | 288
Align EMCal sectors 24-32 | 1 | 110 |  |  | 10 |  |  |  | 60 |  |  |  | 40
Install EMCal cables - LV, bias, signal, control | 1 | 608 |  | 32 | 96 | 160 |  |  |  | 320
Check EMCal operation during cabling | 1 | 940 | 200 | 40 | 40 | 20 | [10 empty] | 320 | 320
Install EMCal cooling panels and route lines | 1 | 80 |  |  | 80
Install EMCal gas distribution panels and route lines | 1 | 80 |  |  | 80
Check EMCal operation with slow controls (LV, bias, temp) | 1 | 800 | 160 | [13 empty] | 320 | 320
Check EMCal operation with DAQ in counting house | 1 | 800 | 160 | [13 empty] | 320 | 320
Transport TPot from Stony Brook to 1008 AH | 1 | 16 |  |  | 8 | [8 empty] | 8
Install TPot Installation fixtures and test | 1 | 36 |  | 16 | 20
Install TPot support system | 1 | 24 |  | 4 | 20
Install TPot | 1 | 92 |  | 4 | 80 | [8 empty] | 8
Align TPot | 1 | 48 |  |  | 20 | [7 empty] | 20 | 8
Install TPot cables - LV, bias, signal, control | 1 | 132 |  | 24 | 20 | 40 |  |  |  | 40 |  |  |  | 8
Check TPot operation during cabling | 1 | 88 | 16 | [10 empty] | 24 |  |  | 24 | 24
Install TPot cooling panels and route lines | 1 | 40 |  |  | 40
Install TPot gas distribution panels and route lines | 1 | 40 |  |  | 40
Check TPot operation with slow controls (LV, bias, temp) | 1 | 88 | 16 | [10 empty] | 24 |  |  | 24 | 24
Check TPot operation with DAQ in counting house | 1 | 88 | 16 | [10 empty] | 24 |  |  | 24 | 24
Fab TPC insertion tooling/review procedures | 1 | 35 |  | 15 | 20
Transport TPC from Stony Brook to 1008 AH | 1 | 48 |  | 8 | 24 | 8 |  | 8
Install TPC Installation fixtures and test | 1 | 80 |  | 40 | 40
Install TPC support system | 1 | 100 |  | 4 | 96
Install TPC | 1 | 124 |  | 4 | 76 |  |  | 8 |  |  |  | 36
Align TPC | 1 | 220 |  |  | 20 |  |  |  | 120 |  |  |  | 80
Install North and South Line Lasers | 1 | 96 | 16 |  | 40 | 40
Install TPC cables - LV, bias, signal, control | 1 | 468 |  | 24 | 84 | 120 |  |  |  | 240
Check TPC operation during cabling | 1 | 480 | 160 | [13 empty] | 160 | 160
Install TPC cooling panels and route lines | 1 | 80 |  |  | 80
Install TPC gas distribution panels and route lines | 1 | 80 |  |  | 80
Install TPC Diffuse Lasers | 1 | 60 | 12 |  | 24 | 24
Check TPC operation with slow controls (LV, bias, temp) | 1 | 480 | 160 | [13 empty] | 160 | 160
Check TPC operation with DAQ in counting house | 1 | 480 | 160 | [13 empty] | 160 | 160
Erect 1008 IR Shield Wall | 3 | 160 | [6 empty] | 80 |  |  | 80
Fab INTT insertion fixture/review procedures | 1 | 108 |  | 56 | 52
Install INTT Installation fixtures and test | 1 | 40 |  | 20 | 20
Install Beampipe Temporary Support | 3 | 300 |  | 20 | 56 |  |  | 120 | 104
Install INTT support system | 1 | 76 |  | 8 | 68
Install Beampipe | 3 | 40 | [6 empty] | 40
Install Beampipe vacuum system | 3 | 40 | [6 empty] | 40
Pump down beampipe | 3 | 40 | [6 empty] | 40
Perform Beampipe Bakeout | 3 | 80 | [7 empty] | 80
Transport INTT from 510 to 1008 AH | 1 | 40 |  | 8 | 24 | 8
Install INTT | 1 | 76 |  | 8 | 68
Align INTT | 1 | 160 |  |  | 20 |  |  |  | 60 |  |  |  | 80
Install beampipe permanent support | 3 | 40 | [6 empty] | 40
Remove beampipe Temporary Support | 3 | 40 | [6 empty] | 40
Install INTT cables - LV, bias, signal, control | 1 | 552 |  | 48 | 144 | 120 |  |  |  | 240
Check INTT operation during cabling | 1 | 360 | 40 | [13 empty] | 160 | 160
Install INTT cooling panels and route lines | 1 | 40 |  |  | 40
Install INTT gas distribution panels and route lines | 1 | 40 |  |  | 40
Check INTT operation with slow controls (LV, bias, temp) | 1 | 360 | 40 | [13 empty] | 160 | 160
Check INTT operation with DAQ in counting house | 1 | 360 | 40 | [13 empty] | 160 | 160
Prepare MVTX insertion procedures/review procedures | 1 | 58 |  | 25 | 33
Transport MVTX from 510 to 1008 AH | 1 | 40 |  | 8 | 24 | 8
Install MVTX Installation fixtures and test | 1 | 120 |  |  | 40 | [8 empty] | 40 | 40
Install MVTX support system | 1 | 76 |  | 8 | 68
Install FELIX, optical fibers, RU, Samtec cables | 1 | 136 |  | 56 |  | 80
(both half-barrels) | 1 | 320 |  | 160 | 160
Align MVTX | 1 | 40 | [10 empty] | 40
Install MVTX cables - LV, bias, signal, control | 1 | 392 |  | 48 | 104 | 80 |  |  |  | 160
Check MVTX operation during cabling | 1 | 680 | 40 | [10 empty] | 160 | 160 |  | 160 | 160
Install MVTX cooling panels and route lines | 1 | 120 |  |  | 120
Install MVTX gas distribution panels and route lines | 1 | 40 |  |  | 40
Check MVTX operation with slow controls (LV, bias, temp) | 1 | 680 | 40 | [10 empty] | 160 | 160 |  | 160 | 160
Check MVTX operation with DAQ in counting house | 1 | 680 | 40 | [10 empty] | 160 | 160 |  | 160 | 160
Fab MBD insertion fixture/review procedures | 1 | 88 |  | 41 | 47
Transport MBD from 510 to 1008 AH | 1 | 16 |  | 8 | 8
Install MBD Installation fixtures and test | 1 | 20 |  | 10 | 10
Install MBD support system | 1 | 32 |  | 8 | 24
Install MBD | 1 | 32 |  | 8 | 24
Align MBD | 1 | 40 |  |  | 20 | [7 empty] | 20
Install MBD cables - LV, bias, signal, control | 1 | 80 |  |  | 40 | 40
Check MBD operation during cabling | 1 | 200 | 40 | [15 empty] | 160
Install MBD cooling panels and route lines | 1 | 40 |  |  | 40
Install MBD gas distribution panels and route lines | 1 | 40 |  |  | 40
Check MBD operation with slow controls (LV, bias, temp) | 1 | 200 | 40 | [15 empty] | 160
Check MBD operation with DAQ in counting house | 1 | 200 | 40 | [15 empty] | 160
Transport sEPD from 510 to 1008 AH | 1 | 40 |  |  | 40
Install sEPD Installation fixtures and test | 1 | 40 |  |  | 40
Install sEPD support system | 1 | 40 |  |  | 40
Install sEPD | 1 | 40 |  |  | 40
Align sEPD | 1 | 60 |  |  | 40 | [7 empty] | 20
Install sEPD cables - LV, bias, signal, control | 1 | 120 |  |  | 20 | 20 | [10 empty] | 40 | 40
Check sEPD operation during cabling | 1 | 200 | 40 | [13 empty] | 80 | 80
Check sEPD operation with slow controls (LV, bias, temp) | 1 | 200 | 40 | [13 empty] | 80 | 80
Check sEPD operation with DAQ in counting house | 1 | 200 | 40 | [13 empty] | 80 | 80
Prepare for review of sPHENIX Safety System by CAD; review | 0 | 224 | 128 | 96
Prepare procedures for sPHENIX (blue sheet, pink sheet) | 0 | 240 | 80 | 80 |  |  |  | 80
Review and approve sPHENIX procedures | 0 | 96 | 32 | 32 |  |  |  | 32
Prepare for sPHENIX IRR | 0 | 320 | 160 | 160
Prepare for sPHENIX ARR | 0 | 320 | 160 | 160
Magnet final checkout before cooldown for ops under RHIC ASE | 0 | 48 |  |  |  |  | 16 | 32
Preparation for full operation - In-rack safety sytems | 0 | 72 | 24 | 24 | 24
Preparation for full operation - Magnet re-check | 0 | 48 |  |  |  |  | 16 | 32
Preparation for full operation - Verify global safety systems | 0 | 80 | 16 | 32 | 32
Preparation for full operation - Final safety walkthrus | 0 | 128 | 32 | 32 | 32 |  | 8 | 24
Grand Total Hours | (all) | 31071 | 2783 | 3359 | 6986 | 2549 | 208 | 1036 | 2150 | 2160 | 1068 | 238 | 366 | 624 | 520 | 0 | 3232 | 3312 | 480 | 0
Job Group Key
Management, Procurement & Reviews | 0 | 2296 | 632 | 1137 | 174 | 0 | 40 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Detector work | 1 | 18985 | 1812 | 1131 | 5065 | 1164 | 0 | 16 | 240 | 1000 | 0 | 89 | 300 | 624 | 520 | 0 | 3232 | 3312 | 480 | 0
On-Carriage Infrasatructure | 2 | 5367 | 0 | 848 | 1278 | 1046 | 0 | 18 | 80 | 1040 | 1028 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Off-Carriage Infrastructure | 3 | 2301 | 0 | 64 | 136 | 40 | 0 | 299 | 1482 | 120 | 40 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Magnet Work | 4 | 2122 | 339 | 179 | 333 | 299 | 168 | 390 | 348 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FTE over 6 months | (all) | 35.308 | 3.1625 | 3.817 | 7.9386 | 2.8966 | 0.23636 | 1.1773 | 2.4432 | 2.4545 | 1.2136 | 0.27045 | 0.41591 | 0.70909 | 0.59091 | 0 | 3.6727 | 3.7636 | 0.54545 | 0
Management, Procurement & Reviews | 0 | 2.6091 | 0.71818 | 1.292 | 0.19773 | 0 | 0.045455 | 0.35568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Detector work | 1 | 21.5739 | 2.0591 | 1.2852 | 5.7557 | 1.3227 | 0 | 0.018182 | 0.27273 | 1.1364 | 0 | 0.10114 | 0.34091 | 0.70909 | 0.59091 | 0 | 3.6727 | 3.7636 | 0.54545 | 0
On-Carriage Infrasatructure | 2 | 6.0989 | 0 | 0.96364 | 1.4523 | 1.1886 | 0 | 0.020455 | 0.090909 | 1.1818 | 1.1682 | 0.032955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Off-Carriage Infrastructure | 3 | 2.6148 | 0 | 0.072727 | 0.15455 | 0.045455 | 0 | 0.33977 | 1.6841 | 0.13636 | 0.045455 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Magnet Work | 4 | 2.4114 | 0.38523 | 0.20341 | 0.37841 | 0.33977 | 0.19091 | 0.44318 | 0.39545 | 0 | 0 | 0 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL FTE SCIentists | 7.7807 |  |  |  |  | Spreadsheet Keys
|  | TOTAL FTE PROFessionals | 4.9943 |  |  |  |  | Labor Hours in P6
|  | TOTAL FTE TECHnicians | 16.3239 |  |  |  |  | Labor Hours added after Fall 2002 review
|  | TOTAL FTE CRAFTspersons | 1.9
|  | TOTAL FTE PostDocs | 3.7636 |  |  |  |  | Job Group Key | Job Group
|  | TOTAL FTE GraduateStudents | 0.54545 |  |  |  |  | Management, Procurement & Reviews | 0
|  | TOATL FTE UndergraduateStudents | 0 |  |  |  |  | Detector work | 1
[8 empty] | On-Carriage Infrasatructure | 2
[8 empty] | Off-Carriage Infrastructure | 3
|  | Category | TOTAL HOURS |  |  |  |  | Magnet Work | 4
|  | Sci PO | 2783
|  | Prof PO | 3359
|  | Tech PO M | 6986
|  | Tech PO E | 2549
|  | Sci AD | 208
|  | Prof AD | 1036
|  | Tech AD M | 2150
|  | Tech AD E | 2160
|  | Electrician | 1068
|  | Rigger | 238
|  | Surveyor | 366
|  | Sci Labs | 624
|  | Tech Labs | 520
|  | PD Labs | 0
|  | Sci Univ | 3232
|  | PD Univ | 3312
|  | GS Univ | 480
|  | US Univ | 0

## Skillset vs Time
[6 empty] | Date | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24
Task group | Start | Duration (weeks) | Skill | Total hours | Hours / week | Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Rack Assembly | 2022-10-17 | 8 | Tech PO E | 546 | 68.25 |  | 1: 68.3; 2: 68.3; 3: 68.3; 4: 68.3; 5: 68.3; 6: 68.3; 7: 68.3; 8: 68.3
Off-Carriage Water Distribution | 2022-10-17 | 16 | Tech PO M | 120 | 7.5 |  | 1: 7.5; 2: 7.5; 3: 7.5; 4: 7.5; 5: 7.5; 6: 7.5; 7: 7.5; 8: 7.5; 9: 7.5; 10: 7.5; 11: 7.5; 12: 7.5; 13: 7.5; 14: 7.5; 15: 7.5; 16: 7.5
Off-Carriage Water Distribution | 2022-10-17 | 16 | Tech AD M | 400 | 25 |  | 1: 25; 2: 25; 3: 25; 4: 25; 5: 25; 6: 25; 7: 25; 8: 25; 9: 25; 10: 25; 11: 25; 12: 25; 13: 25; 14: 25; 15: 25; 16: 25
Cooling System Panel Fabrication | 2022-10-17 | 16 | Prof PO | 274 | 17.125 |  | 1: 17.1; 2: 17.1; 3: 17.1; 4: 17.1; 5: 17.1; 6: 17.1; 7: 17.1; 8: 17.1; 9: 17.1; 10: 17.1; 11: 17.1; 12: 17.1; 13: 17.1; 14: 17.1; 15: 17.1; 16: 17.1
Cooling System Panel Fabrication | 2022-10-17 | 16 | Tech PO M | 2172 | 135.75 |  | 1: 135.8; 2: 135.8; 3: 135.8; 4: 135.8; 5: 135.8; 6: 135.8; 7: 135.8; 8: 135.8; 9: 135.8; 10: 135.8; 11: 135.8; 12: 135.8; 13: 135.8; 14: 135.8; 15: 135.8; 16: 135.8
Cooling System Panel Fabrication | 2022-11-21 | 2 | Rigger | 29 | 14.5 |  | 6: 14.5; 7: 14.5
Gas Panel Fabrication | 2022-10-17 | 16 | Prof PO | 124 | 7.75 |  | 1: 7.8; 2: 7.8; 3: 7.8; 4: 7.8; 5: 7.8; 6: 7.8; 7: 7.8; 8: 7.8; 9: 7.8; 10: 7.8; 11: 7.8; 12: 7.8; 13: 7.8; 14: 7.8; 15: 7.8; 16: 7.8
Gas Panel Fabrication | 2022-10-17 | 16 | Tech PO M | 498 | 31.125 |  | 1: 31.1; 2: 31.1; 3: 31.1; 4: 31.1; 5: 31.1; 6: 31.1; 7: 31.1; 8: 31.1; 9: 31.1; 10: 31.1; 11: 31.1; 12: 31.1; 13: 31.1; 14: 31.1; 15: 31.1; 16: 31.1
Various Safety System Fab/installs | 2022-10-17 | 16 | Prof PO | 116 | 7.25 |  | 1: 7.3; 2: 7.3; 3: 7.3; 4: 7.3; 5: 7.3; 6: 7.3; 7: 7.3; 8: 7.3; 9: 7.3; 10: 7.3; 11: 7.3; 12: 7.3; 13: 7.3; 14: 7.3; 15: 7.3; 16: 7.3
Various Safety System Fab/installs | 2022-10-17 | 16 | Tech PO M | 136 | 8.5 |  | 1: 8.5; 2: 8.5; 3: 8.5; 4: 8.5; 5: 8.5; 6: 8.5; 7: 8.5; 8: 8.5; 9: 8.5; 10: 8.5; 11: 8.5; 12: 8.5; 13: 8.5; 14: 8.5; 15: 8.5; 16: 8.5
Various Safety System Fab/installs | 2022-10-17 | 16 | Tech PO E | 132 | 8.25 |  | 1: 8.3; 2: 8.3; 3: 8.3; 4: 8.3; 5: 8.3; 6: 8.3; 7: 8.3; 8: 8.3; 9: 8.3; 10: 8.3; 11: 8.3; 12: 8.3; 13: 8.3; 14: 8.3; 15: 8.3; 16: 8.3
Various Safety System Fab/installs | 2022-10-17 | 16 | Prof AD | 157 | 9.8125 |  | 1: 9.8; 2: 9.8; 3: 9.8; 4: 9.8; 5: 9.8; 6: 9.8; 7: 9.8; 8: 9.8; 9: 9.8; 10: 9.8; 11: 9.8; 12: 9.8; 13: 9.8; 14: 9.8; 15: 9.8; 16: 9.8
Various Safety System Fab/installs | 2022-10-17 | 16 | Tech AD M | 174 | 10.875 |  | 1: 10.9; 2: 10.9; 3: 10.9; 4: 10.9; 5: 10.9; 6: 10.9; 7: 10.9; 8: 10.9; 9: 10.9; 10: 10.9; 11: 10.9; 12: 10.9; 13: 10.9; 14: 10.9; 15: 10.9; 16: 10.9
Various Safety System Fab/installs | 2022-10-17 | 16 | Electrician | 18 | 1.125 |  | 1: 1.1; 2: 1.1; 3: 1.1; 4: 1.1; 5: 1.1; 6: 1.1; 7: 1.1; 8: 1.1; 9: 1.1; 10: 1.1; 11: 1.1; 12: 1.1; 13: 1.1; 14: 1.1; 15: 1.1; 16: 1.1
HVAC completion | 2022-10-31 | 2 | Prof AD | 8 | 4 |  | 3: 4; 4: 4
HVAC completion | 2022-10-31 | 2 | Tech AD M | 4 | 2 |  | 3: 2; 4: 2
HVAC completion | 2022-10-31 | 2 | Electrician | 6 | 3 |  | 3: 3; 4: 3
Install non-IR Infrastructure | 2022-10-31 | 4 | Prof PO | 40 | 10 |  | 3: 10; 4: 10; 5: 10; 6: 10
Install non-IR Infrastructure | 2022-10-31 | 4 | Tech PO M | 40 | 10 |  | 3: 10; 4: 10; 5: 10; 6: 10
Install non-IR Infrastructure | 2022-10-31 | 4 | Tech PO E | 40 | 10 |  | 3: 10; 4: 10; 5: 10; 6: 10
Install non-IR Infrastructure | 2022-10-31 | 4 | Prof AD | 10 | 2.5 |  | 3: 2.5; 4: 2.5; 5: 2.5; 6: 2.5
Install non-IR Infrastructure | 2022-10-31 | 4 | Tech AD M | 40 | 10 |  | 3: 10; 4: 10; 5: 10; 6: 10
Install non-IR Infrastructure | 2022-10-31 | 4 | Tech AD E | 40 | 10 |  | 3: 10; 4: 10; 5: 10; 6: 10
Install non-IR Infrastructure | 2022-10-31 | 4 | Rigger | 40 | 10 |  | 3: 10; 4: 10; 5: 10; 6: 10
Line AC Power | 2022-10-17 | 16 | Prof PO | 60 | 3.75 |  | 1: 3.8; 2: 3.8; 3: 3.8; 4: 3.8; 5: 3.8; 6: 3.8; 7: 3.8; 8: 3.8; 9: 3.8; 10: 3.8; 11: 3.8; 12: 3.8; 13: 3.8; 14: 3.8; 15: 3.8; 16: 3.8
Line AC Power | 2022-10-17 | 16 | Electrician | 84 | 5.25 |  | 1: 5.3; 2: 5.3; 3: 5.3; 4: 5.3; 5: 5.3; 6: 5.3; 7: 5.3; 8: 5.3; 9: 5.3; 10: 5.3; 11: 5.3; 12: 5.3; 13: 5.3; 14: 5.3; 15: 5.3; 16: 5.3
Install Racks | 2022-10-17 | 11 | Prof PO | 160 | 14.5455 |  | 1: 14.5; 2: 14.5; 3: 14.5; 4: 14.5; 5: 14.5; 6: 14.5; 7: 14.5; 8: 14.5; 9: 14.5; 10: 14.5; 11: 14.5
Install Racks | 2022-10-17 | 11 | Tech PO M | 220 | 20 |  | 1: 20; 2: 20; 3: 20; 4: 20; 5: 20; 6: 20; 7: 20; 8: 20; 9: 20; 10: 20; 11: 20
Install Racks | 2022-10-17 | 11 | Tech PO E | 188 | 17.0909 |  | 1: 17.1; 2: 17.1; 3: 17.1; 4: 17.1; 5: 17.1; 6: 17.1; 7: 17.1; 8: 17.1; 9: 17.1; 10: 17.1; 11: 17.1
AC Power to Racks | 2022-10-17 | 11 | Electrician | 720 | 65.4545 |  | 1: 65.5; 2: 65.5; 3: 65.5; 4: 65.5; 5: 65.5; 6: 65.5; 7: 65.5; 8: 65.5; 9: 65.5; 10: 65.5; 11: 65.5
Cooling to Racks | 2023-01-02 | 5 | Tech AD M | 480 | 96 |  | 12: 96; 13: 96; 14: 96; 15: 96; 16: 96
Rack Protection Systems | 2023-01-02 | 5 | Tech PO E | 240 | 48 |  | 12: 48; 13: 48; 14: 48; 15: 48; 16: 48
Platforms | 2022-10-31 | 2 | Tech PO M | 21 | 10.5 |  | 3: 10.5; 4: 10.5
Control Distribution & Pgm | 2022-12-12 | 2 | Prof PO | 400 | 200 |  | 9: 200; 10: 200
Control Distribution & Pgm | 2022-10-31 | 6 | Tech AD M | 80 | 13.3333 |  | 3: 13.3333; 4: 13.3333; 5: 13.3333; 6: 13.3333; 7: 13.3333; 8: 13.3333
Control Distribution & Pgm | 2022-10-31 | 6 | Tech AD E | 1040 | 173.3333 |  | 3: 173.3333; 4: 173.3333; 5: 173.3333; 6: 173.3333; 7: 173.3333; 8: 173.3333
Control Distribution & Pgm | 2022-10-31 | 6 | Electrician | 240 | 40 |  | 3: 40; 4: 40; 5: 40; 6: 40; 7: 40; 8: 40
Install OHCal Cables, tests | 2022-11-21 | 2 | Sci PO | 120 | 60 |  | 6: 60; 7: 60
Install OHCal Cables, tests | 2022-11-21 | 2 | Prof PO | 8 | 4 |  | 6: 4; 7: 4
Install OHCal Cables, tests | 2022-11-21 | 2 | Tech PO M | 48 | 24 |  | 6: 24; 7: 24
Install OHCal Cables, tests | 2022-11-21 | 2 | Tech PO E | 16 | 8 |  | 6: 8; 7: 8
Install OHCal Cables, tests | 2022-11-21 | 2 | Sci Univ | 240 | 120 |  | 6: 120; 7: 120
Install OHCal Cables, tests | 2022-11-21 | 2 | PD Univ | 240 | 120 |  | 6: 120; 7: 120
Install IHCal Cables, tests | 2022-11-21 | 2 | Sci PO | 120 | 60 |  | 6: 60; 7: 60
Install IHCal Cables, tests | 2022-11-21 | 2 | Prof PO | 80 | 40 |  | 6: 40; 7: 40
Install IHCal Cables, tests | 2022-11-21 | 2 | Tech PO M | 120 | 60 |  | 6: 60; 7: 60
Install IHCal Cables, tests | 2022-11-21 | 2 | Tech PO E | 160 | 80 |  | 6: 80; 7: 80
Install IHCal Cables, tests | 2022-11-21 | 2 | Sci Univ | 240 | 120 |  | 6: 120; 7: 120
Install IHCal Cables, tests | 2022-11-21 | 2 | PD Univ | 240 | 120 |  | 6: 120; 7: 120
Install EMCal 24-32 | 2022-11-21 | 2 | Sci PO | 16 | 8 |  | 6: 8; 7: 8
Install EMCal 24-32 | 2022-11-21 | 2 | Prof PO | 40 | 20 |  | 6: 20; 7: 20
Install EMCal 24-32 | 2022-11-21 | 2 | Tech PO M | 382 | 191 |  | 6: 191; 7: 191
Install EMCal 24-32 | 2022-11-21 | 2 | Tech PO E | 160 | 80 |  | 6: 80; 7: 80
Install EMCal 24-32 | 2022-11-21 | 2 | Tech AD M | 60 | 30 |  | 6: 30; 7: 30
Install EMCal 24-32 | 2022-11-21 | 2 | Rigger | 53 | 26.5 |  | 6: 26.5; 7: 26.5
Install EMCal 24-32 | 2022-11-21 | 2 | Surveyor | 40 | 20 |  | 6: 20; 7: 20
Install EMCal 24-32 | 2022-11-21 | 2 | PD Univ | 80 | 40 |  | 6: 40; 7: 40
Install EMCal services | 2022-12-05 | 6 | Sci PO | 520 | 86.6667 |  | 8: 86.7; 9: 86.7; 10: 86.7; 11: 86.7; 12: 86.7; 13: 86.7
Install EMCal services | 2022-12-05 | 6 | Prof PO | 72 | 12 |  | 8: 12; 9: 12; 10: 12; 11: 12; 12: 12; 13: 12
Install EMCal services | 2022-12-05 | 6 | Tech PO M | 296 | 49.3333 |  | 8: 49.3; 9: 49.3; 10: 49.3; 11: 49.3; 12: 49.3; 13: 49.3
Install EMCal services | 2022-12-05 | 6 | Tech PO E | 180 | 30 |  | 8: 30; 9: 30; 10: 30; 11: 30; 12: 30; 13: 30
Install EMCal services | 2022-12-05 | 6 | Electrician | 0 | 0 |  | 8: 53.3; 9: 53.3; 10: 53.3; 11: 53.3; 12: 53.3; 13: 53.3
Install EMCal services | 2022-12-05 | 6 | Sci Univ | 960 | 160 |  | 8: 160; 9: 160; 10: 160; 11: 160; 12: 160; 13: 160
Install EMCal services | 2022-12-05 | 6 | PD Univ | 960 | 160 |  | 8: 160; 9: 160; 10: 160; 11: 160; 12: 160; 13: 160
TPot, services | 2022-12-05 | 6 | Sci PO | 48 | 8 |  | 8: 8; 9: 8; 10: 8; 11: 8; 12: 8; 13: 8
TPot, services | 2022-12-05 | 6 | Prof PO | 48 | 8 |  | 8: 8; 9: 8; 10: 8; 11: 8; 12: 8; 13: 8
TPot, services | 2022-12-05 | 6 | Tech PO M | 248 | 41.3333 |  | 8: 41.3; 9: 41.3; 10: 41.3; 11: 41.3; 12: 41.3; 13: 41.3
TPot, services | 2022-12-05 | 6 | Tech PO E | 40 | 6.6667 |  | 8: 6.7; 9: 6.7; 10: 6.7; 11: 6.7; 12: 6.7; 13: 6.7
TPot, services | 2022-12-05 | 6 | Electrician | 0 | 0 |  | 8: 6.7; 9: 6.7; 10: 6.7; 11: 6.7; 12: 6.7; 13: 6.7
TPot, services | 2022-12-05 | 6 | Surveyor | 20 | 3.3333 |  | 8: 3.3; 9: 3.3; 10: 3.3; 11: 3.3; 12: 3.3; 13: 3.3
TPot, services | 2022-12-05 | 6 | Sci Labs | 104 | 17.3333 |  | 8: 17.3; 9: 17.3; 10: 17.3; 11: 17.3; 12: 17.3; 13: 17.3
TPot, services | 2022-12-05 | 6 | Sci Univ | 72 | 12 |  | 8: 12; 9: 12; 10: 12; 11: 12; 12: 12; 13: 12
TPot, services | 2022-12-05 | 6 | PD Univ | 72 | 12 |  | 8: 12; 9: 12; 10: 12; 11: 12; 12: 12; 13: 12
Install TPC & Services | 2023-01-09 | 6 | Sci PO | 508 | 84.6667 |  | 13: 80; 14: 80; 15: 80; 16: 80; 17: 80; 18: 80
Install TPC & Services | 2023-01-09 | 6 | Prof PO | 95 | 15.8333 |  | 13: 15.8; 14: 15.8; 15: 15.8; 16: 15.8; 17: 15.8; 18: 15.8
Install TPC & Services | 2023-01-09 | 6 | Tech PO M | 584 | 97.3333 |  | 13: 86.7; 14: 86.7; 15: 86.7; 16: 86.7; 17: 86.7; 18: 86.7
Install TPC & Services | 2023-01-09 | 6 | Tech PO E | 192 | 32 |  | 13: 21.3; 14: 21.3; 15: 21.3; 16: 21.3; 17: 21.3; 18: 21.3
Install TPC & Services | 2023-01-09 | 6 | Prof AD | 16 | 2.6667 |  | 13: 2.7; 14: 2.7; 15: 2.7; 16: 2.7; 17: 2.7; 18: 2.7
Install TPC & Services | 2023-01-09 | 6 | Tech AD M | 120 | 20 |  | 13: 20; 14: 20; 15: 20; 16: 20; 17: 20; 18: 20
Install TPC & Services | 2023-01-09 | 6 | Electrician | 0 | 0 |  | 13: 40; 14: 40; 15: 40; 16: 40; 17: 40; 18: 40
Install TPC & Services | 2023-01-09 | 6 | Rigger | 36 | 6 |  | 13: 6; 14: 6; 15: 6; 16: 6; 17: 6; 18: 6
Install TPC & Services | 2023-01-09 | 6 | Surveyor | 80 | 13.3333 |  | 13: 13.3; 14: 13.3; 15: 13.3; 16: 13.3; 17: 13.3; 18: 13.3
Install TPC & Services | 2023-01-09 | 6 | Sci Univ | 480 | 80 |  | 13: 80; 14: 80; 15: 80; 16: 80; 17: 80; 18: 80
Install TPC & Services | 2023-01-09 | 6 | PD Univ | 480 | 80 |  | 13: 80; 14: 80; 15: 80; 16: 80; 17: 80; 18: 80
Install Beampipe& INTT Support | 2023-02-20 | 3 | Prof PO | 104 | 34.6667 |  | 19: 34.7; 20: 34.7; 21: 34.7
Install Beampipe& INTT Support | 2023-02-20 | 3 | Tech PO M | 196 | 65.3333 |  | 19: 65.3; 20: 65.3; 21: 65.3
Install Beampipe& INTT Support | 2023-02-20 | 3 | Prof AD | 120 | 40 |  | 19: 40; 20: 40; 21: 40
Install Beampipe& INTT Support | 2023-02-20 | 3 | Tech AD M | 224 | 74.6667 |  | 19: 74.7; 20: 74.7; 21: 74.7
Install Beampipe& INTT Support | 2023-02-20 | 3 | Electrician | 80 | 26.6667 |  | 19: 26.7; 20: 26.7; 21: 26.7
Erect 1008 IR Shield Wall | 2023-02-20 | 2 | Tech AD M | 80 | 40
Erect 1008 IR Shield Wall | 2023-02-20 | 2 | Rigger | 80 | 40
Install INTT & Services | 2023-03-13 | 3 | Sci PO | 120 | 40 |  | 22: 40; 23: 40; 24: 40
Install INTT & Services | 2023-03-13 | 3 | Prof PO | 64 | 21.3333 |  | 22: 21.3; 23: 21.3; 24: 21.3
Install INTT & Services | 2023-03-13 | 3 | Tech PO M | 336 | 112 |  | 22: 112; 23: 112; 24: 112
Install INTT & Services | 2023-03-13 | 3 | Tech PO E | 128 | 42.6667 |  | 22: 42.7; 23: 42.7; 24: 42.7
Install INTT & Services | 2023-03-13 | 3 | Tech AD M | 140 | 46.6667 |  | 22: 46.7; 23: 46.7; 24: 46.7
Install INTT & Services | 2023-03-13 | 3 | Surveyor | 80 | 26.6667 |  | 22: 106.7; 23: 106.7; 24: 106.7
Install INTT & Services | 2023-03-13 | 3 | Sci Univ | 480 | 160 |  | 22: 160; 23: 160; 24: 160
Install INTT & Services | 2023-03-13 | 3 | PD Univ | 480 | 160 |  | 22: 160; 23: 160; 24: 160
Install MVTX & Services | 2023-03-27 | 3 | Sci PO | 120 | 40 |  | 24: 40; 25: 40; 26: 40
Install MVTX & Services | 2023-03-27 | 3 | Prof PO | 305 | 101.6667 |  | 24: 93.3; 25: 93.3; 26: 93.3
Install MVTX & Services | 2023-03-27 | 3 | Tech PO M | 589 | 196.3333 |  | 24: 185.3; 25: 185.3; 26: 185.3
Install MVTX & Services | 2023-03-27 | 3 | Tech PO E | 168 | 56 |  | 24: 56; 25: 56; 26: 56
Install MVTX & Services | 2023-03-27 | 3 | Electrician | 0 | 0 |  | 24: 53.3; 25: 53.3; 26: 53.3
Install MVTX & Services | 2023-03-27 | 3 | Surveyor | 40 | 13.3333 |  | 24: 13.3; 25: 13.3; 26: 13.3
Install MVTX & Services | 2023-03-27 | 3 | Sci Labs | 520 | 173.3333 |  | 24: 173.3; 25: 173.3; 26: 173.3
Install MVTX & Services | 2023-03-27 | 3 | Tech Labs | 520 | 173.3333 |  | 24: 173.3; 25: 173.3; 26: 173.3
Install MVTX & Services | 2023-03-27 | 3 | Sci Univ | 480 | 160 |  | 24: 160; 25: 160; 26: 160
Install MVTX & Services | 2023-03-27 | 3 | PD Univ | 480 | 160 |  | 24: 160; 25: 160; 26: 160
Install MBD & Services | 2023-04-03 | 2 | Sci PO | 120 | 60 |  | 25: 60; 26: 60
Install MBD & Services | 2023-04-03 | 2 | Prof PO | 75 | 37.5 |  | 25: 37.5; 26: 37.5
Install MBD & Services | 2023-04-03 | 2 | Tech PO M | 253 | 126.5 |  | 25: 126.5; 26: 126.5
Install MBD & Services | 2023-04-03 | 2 | Tech PO E | 40 | 20 |  | 25: 20; 26: 20
Install MBD & Services | 2023-04-03 | 2 | Surveyor | 20 | 10 |  | 25: 10; 26: 10
Install MBD & Services | 2023-04-03 | 2 | GS Univ | 480 | 240 |  | 25: 240; 26: 240
Install sEPD & Services | 2023-04-17 | 2 | Sci PO | 120 | 60 |  | 27: 60; 28: 60
Install sEPD & Services | 2023-04-17 | 2 | Tech PO M | 220 | 110 |  | 27: 110; 28: 110
Install sEPD & Services | 2023-04-17 | 2 | Tech PO E | 20 | 10 |  | 27: 10; 28: 10
Install sEPD & Services | 2023-04-17 | 2 | Surveyor | 20 | 10 |  | 27: 10; 28: 10
Install sEPD & Services | 2023-04-17 | 2 | Sci Univ | 280 | 140 |  | 27: 140; 28: 140
Install sEPD & Services | 2023-04-17 | 2 | PD Univ | 280 | 140 |  | 27: 140; 28: 140
Reviews prep | 2023-10-17 | 24 | Sci PO | 632 | 26.3333 |  | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.3
Reviews prep | 2023-10-17 | 24 | Prof PO | 616 | 25.6667 |  | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7 | 25.7
Reviews prep | 2023-10-17 | 24 | Tech PO M | 88 | 3.6667 |  | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7
Reviews prep | 2023-10-17 | 24 | Sci AD | 40 | 1.6667 |  | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7
Reviews prep | 2023-10-17 | 24 | Prof AD | 200 | 8.3333 |  | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3
|  |  | Hours Sum | 27229
Hours per week |  |  | Sci PO |  |  |  | 26.3 | 26.3 | 26.3 | 26.3 | 26.3 | 154.3 | 154.3 | 121 | 121 | 121 | 121 | 121 | 201 | 106.3 | 106.3 | 106.3 | 106.3 | 106.3 | 26.3 | 26.3 | 26.3 | 66.3 | 66.3 | 106.3 | 100 | 100 | 60 | 60
Hours per week |  |  | Prof PO |  |  |  | 76.2 | 76.2 | 86.2 | 86.2 | 86.2 | 150.2 | 140.2 | 96.2 | 296.2 | 296.2 | 96.2 | 81.7 | 97.5 | 77.5 | 77.5 | 77.5 | 41.5 | 41.5 | 60.4 | 60.4 | 60.4 | 47 | 47 | 140.3 | 130.8 | 130.8 | 0 | 0
Hours per week |  |  | Tech PO M |  |  |  | 206.6 | 206.6 | 227.1 | 227.1 | 216.6 | 491.6 | 481.6 | 297.2 | 297.2 | 297.2 | 297.2 | 277.2 | 363.9 | 273.3 | 273.3 | 273.3 | 90.4 | 90.4 | 69 | 69 | 69 | 115.7 | 115.7 | 301 | 311.8 | 311.8 | 110 | 110
Hours per week |  |  | Tech PO E |  |  |  | 93.7 | 93.7 | 103.7 | 103.7 | 103.7 | 271.7 | 261.7 | 130.4 | 62.1 | 62.1 | 62.1 | 93 | 114.3 | 77.6 | 77.6 | 77.6 | 21.3 | 21.3 | 0 | 0 | 0 | 42.7 | 42.7 | 98.7 | 76 | 76 | 10 | 10
Hours per week |  |  | Prof AD |  |  |  | 18.1 | 18.1 | 24.6 | 24.6 | 20.6 | 20.6 | 18.1 | 18.1 | 18.1 | 18.1 | 18.1 | 18.1 | 20.8 | 20.8 | 20.8 | 20.8 | 11 | 11 | 48.3 | 48.3 | 48.3 | 8.3 | 8.3 | 8.3 | 0 | 0 | 0 | 0
Hours per week |  |  | Tech AD M |  |  |  | 35.9 | 35.9 | 61.2333 | 61.2333 | 59.2333 | 89.2333 | 79.2333 | 49.2333 | 35.9 | 35.9 | 35.9 | 131.9 | 151.9 | 151.9 | 151.9 | 151.9 | 20 | 20 | 74.7 | 74.7 | 74.7 | 46.7 | 46.7 | 46.7 | 0 | 0 | 0 | 0
Hours per week |  |  | Tech AD E |  |  |  | 0 | 0 | 183.3333 | 183.3333 | 183.3333 | 183.3333 | 173.3333 | 173.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours per week |  |  | Electrician |  |  |  | 71.9 | 71.9 | 114.9 | 114.9 | 111.9 | 111.9 | 111.9 | 171.9 | 131.9 | 131.9 | 131.9 | 66.4 | 106.4 | 46.4 | 46.4 | 46.4 | 40 | 40 | 26.7 | 26.7 | 26.7 | 0 | 0 | 53.3 | 53.3 | 53.3 | 0 | 0
Hours per week |  |  | Rigger |  |  |  | 0 | 0 | 10 | 10 | 10 | 51 | 41 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours per week |  |  | Surveyor |  |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 16.6 | 13.3 | 13.3 | 13.3 | 13.3 | 13.3 | 0 | 0 | 0 | 106.7 | 106.7 | 120 | 23.3 | 23.3 | 10 | 10
Hours per week |  |  | Sci Labs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3 | 173.3 | 173.3 | 0 | 0
Hours per week |  |  | Tech Labs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3 | 173.3 | 173.3 | 0 | 0
Hours per week |  |  | PD Labs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours per week |  |  | Sci Univ |  |  |  | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 172 | 172 | 172 | 172 | 172 | 252 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 160 | 160 | 320 | 160 | 160 | 140 | 140
Hours per week |  |  | PD Univ |  |  |  | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 172 | 172 | 172 | 172 | 172 | 252 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 160 | 160 | 320 | 160 | 160 | 140 | 140
Hours per week |  |  | GS Univ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | 0
|  |  |  | Total Hours/week |  |  | 528.7 | 528.7 | 837.3667 | 837.3667 | 817.8667 | 2063.8667 | 2001.3667 | 1421.9667 | 1327 | 1327 | 1127 | 1153.9 | 1599.7 | 933.1 | 933.1 | 933.1 | 509.8 | 509.8 | 305.4 | 305.4 | 305.4 | 753.4 | 753.4 | 1861.2 | 1601.8 | 1601.8 | 470 | 470
Persons/week |  |  | Sci PO |  |  |  | 0.6575 | 0.6575 | 0.6575 | 0.6575 | 0.6575 | 3.8575 | 3.8575 | 3.025 | 3.025 | 3.025 | 3.025 | 3.025 | 5.025 | 2.6575 | 2.6575 | 2.6575 | 2.6575 | 2.6575 | 0.6575 | 0.6575 | 0.6575 | 1.6575 | 1.6575 | 2.6575 | 2.5 | 2.5 | 1.5 | 1.5
Persons/week |  |  | Prof PO |  |  |  | 1.905 | 1.905 | 2.155 | 2.155 | 2.155 | 3.755 | 3.505 | 2.405 | 7.405 | 7.405 | 2.405 | 2.0425 | 2.4375 | 1.9375 | 1.9375 | 1.9375 | 1.0375 | 1.0375 | 1.51 | 1.51 | 1.51 | 1.175 | 1.175 | 3.5075 | 3.27 | 3.27 | 0 | 0
Persons/week |  |  | Tech PO M |  |  |  | 5.165 | 5.165 | 5.6775 | 5.6775 | 5.415 | 12.29 | 12.04 | 7.43 | 7.43 | 7.43 | 7.43 | 6.93 | 9.0975 | 6.8325 | 6.8325 | 6.8325 | 2.26 | 2.26 | 1.725 | 1.725 | 1.725 | 2.8925 | 2.8925 | 7.525 | 7.795 | 7.795 | 2.75 | 2.75
Persons/week |  |  | Tech PO E |  |  |  | 2.3425 | 2.3425 | 2.5925 | 2.5925 | 2.5925 | 6.7925 | 6.5425 | 3.26 | 1.5525 | 1.5525 | 1.5525 | 2.325 | 2.8575 | 1.94 | 1.94 | 1.94 | 0.5325 | 0.5325 | 0 | 0 | 0 | 1.0675 | 1.0675 | 2.4675 | 1.9 | 1.9 | 0.25 | 0.25
Persons/week |  |  | Prof AD |  |  |  | 0.4525 | 0.4525 | 0.615 | 0.615 | 0.515 | 0.515 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.52 | 0.52 | 0.52 | 0.52 | 0.275 | 0.275 | 1.2075 | 1.2075 | 1.2075 | 0.2075 | 0.2075 | 0.2075 | 0 | 0 | 0 | 0
Persons/week |  |  | Tech AD M |  |  |  | 0.8975 | 0.8975 | 1.5308 | 1.5308 | 1.4808 | 2.2308 | 1.9808 | 1.2308 | 0.8975 | 0.8975 | 0.8975 | 3.2975 | 3.7975 | 3.7975 | 3.7975 | 3.7975 | 0.5 | 0.5 | 1.8675 | 1.8675 | 1.8675 | 1.1675 | 1.1675 | 1.1675 | 0 | 0 | 0 | 0
Persons/week |  |  | Tech AD E |  |  |  | 0 | 0 | 4.5833 | 4.5833 | 4.5833 | 4.5833 | 4.3333 | 4.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Persons/week |  |  | Electrician |  |  |  | 1.7975 | 1.7975 | 2.8725 | 2.8725 | 2.7975 | 2.7975 | 2.7975 | 4.2975 | 3.2975 | 3.2975 | 3.2975 | 1.66 | 2.66 | 1.16 | 1.16 | 1.16 | 1 | 1 | 0.6675 | 0.6675 | 0.6675 | 0 | 0 | 1.3325 | 1.3325 | 1.3325 | 0 | 0
Persons/week |  |  | Rigger |  |  |  | 0 | 0 | 0.25 | 0.25 | 0.25 | 1.275 | 1.025 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Persons/week |  |  | Surveyor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.0825 | 0.0825 | 0.0825 | 0.0825 | 0.0825 | 0.415 | 0.3325 | 0.3325 | 0.3325 | 0.3325 | 0.3325 | 0 | 0 | 0 | 2.6675 | 2.6675 | 3 | 0.5825 | 0.5825 | 0.25 | 0.25
Persons/week |  |  | Sci Labs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4325 | 0.4325 | 0.4325 | 0.4325 | 0.4325 | 0.4325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3325 | 4.3325 | 4.3325 | 0 | 0
Persons/week |  |  | Tech Labs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3325 | 4.3325 | 4.3325 | 0 | 0
Persons/week |  |  | PD Labs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Persons/week |  |  | Sci Univ |  |  |  | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 6.3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 4 | 4 | 8 | 4 | 4 | 3.5 | 3.5
Persons/week |  |  | PD Univ |  |  |  | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 6.3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 4 | 4 | 8 | 4 | 4 | 3.5 | 3.5
Persons/week |  |  | GS Univ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0
3 or more/week for this skillset
| 5 or more/week for this skillset |  |  | Total persons/week |  |  | 13.2175 | 13.2175 | 20.9342 | 20.9342 | 20.4467 | 51.5967 | 50.0342 | 35.5492 | 33.175 | 33.175 | 28.175 | 28.8475 | 39.9925 | 23.3275 | 23.3275 | 23.3275 | 12.745 | 12.745 | 7.635 | 7.635 | 7.635 | 18.835 | 18.835 | 46.53 | 40.045 | 40.045 | 11.75 | 11.75
over 30 people/week

## Example TPC Install
[6 empty] | Date | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24
Task group | Start | Duration (weeks) | Skill | Total hours | Hours / week | Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Install TPC & Services | 2023-01-09 | 6 | Sci PO | 508 | 84.6667 |  | 13: 80; 14: 80; 15: 80; 16: 80; 17: 80; 18: 80
Install TPC & Services | 2023-01-09 | 6 | Prof PO | 95 | 15.8333 |  | 13: 15.8; 14: 15.8; 15: 15.8; 16: 15.8; 17: 15.8; 18: 15.8
Install TPC & Services | 2023-01-09 | 6 | Tech PO M | 584 | 97.3333 |  | 13: 86.7; 14: 86.7; 15: 86.7; 16: 86.7; 17: 86.7; 18: 86.7
Install TPC & Services | 2023-01-09 | 6 | Tech PO E | 192 | 32 |  | 13: 21.3; 14: 21.3; 15: 21.3; 16: 21.3; 17: 21.3; 18: 21.3
Install TPC & Services | 2023-01-09 | 6 | Prof AD | 16 | 2.6667 |  | 13: 2.7; 14: 2.7; 15: 2.7; 16: 2.7; 17: 2.7; 18: 2.7
Install TPC & Services | 2023-01-09 | 6 | Tech AD M | 120 | 20 |  | 13: 20; 14: 20; 15: 20; 16: 20; 17: 20; 18: 20
Install TPC & Services | 2023-01-09 | 6 | Electrician | 0 | 0 |  | 13: 40; 14: 40; 15: 40; 16: 40; 17: 40; 18: 40
Install TPC & Services | 2023-01-09 | 6 | Rigger | 36 | 6 |  | 13: 6; 14: 6; 15: 6; 16: 6; 17: 6; 18: 6
Install TPC & Services | 2023-01-09 | 6 | Surveyor | 80 | 13.3333 |  | 13: 13.3; 14: 13.3; 15: 13.3; 16: 13.3; 17: 13.3; 18: 13.3
Install TPC & Services | 2023-01-09 | 6 | Sci Univ | 480 | 80 |  | 13: 80; 14: 80; 15: 80; 16: 80; 17: 80; 18: 80
Install TPC & Services | 2023-01-09 | 6 | PD Univ | 480 | 80 |  | 13: 80; 14: 80; 15: 80; 16: 80; 17: 80; 18: 80

## Total Skillset vs Time
[6 empty] | Date | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24
Task group | Start | Duration (weeks) | Skill | Total hours | Hours / week | Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Persons/week |  |  | Sci PO |  |  |  | 0.6575 | 0.6575 | 0.6575 | 0.6575 | 0.6575 | 3.8575 | 3.8575 | 3.025 | 3.025 | 3.025 | 3.025 | 3.025 | 5.025 | 2.6575 | 2.6575 | 2.6575 | 2.6575 | 2.6575 | 0.6575 | 0.6575 | 0.6575 | 1.6575 | 1.6575 | 2.6575 | 2.5 | 2.5 | 1.5 | 1.5
Persons/week |  |  | Prof PO |  |  |  | 0.6575 | 1.81 | 1.81 | 1.81 | 1.81 | 3.41 | 3.41 | 2.31 | 2.31 | 2.31 | 2.31 | 1.9475 | 2.3425 | 1.8425 | 1.8425 | 1.8425 | 1.0375 | 1.0375 | 1.51 | 1.51 | 1.51 | 1.175 | 1.175 | 3.5075 | 3.27 | 3.27 | 0 | 0
Persons/week |  |  | Tech PO M |  |  |  | 0.6575 | 5.165 | 5.165 | 5.165 | 5.165 | 12.04 | 12.04 | 7.43 | 7.43 | 7.43 | 7.43 | 6.93 | 9.0975 | 6.8325 | 6.8325 | 6.8325 | 2.26 | 2.26 | 1.725 | 1.725 | 1.725 | 2.8925 | 2.8925 | 7.525 | 7.795 | 7.795 | 2.75 | 2.75
Persons/week |  |  | Tech PO E |  |  |  | 0.6575 | 2.3425 | 2.3425 | 2.3425 | 2.3425 | 6.5425 | 6.5425 | 3.26 | 1.5525 | 1.5525 | 1.5525 | 2.325 | 2.8575 | 1.94 | 1.94 | 1.94 | 0.5325 | 0.5325 | 0 | 0 | 0 | 1.0675 | 1.0675 | 2.4675 | 1.9 | 1.9 | 0.25 | 0.25
Persons/week |  |  | Prof AD |  |  |  | 0.6575 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.4525 | 0.52 | 0.52 | 0.52 | 0.52 | 0.275 | 0.275 | 1.2075 | 1.2075 | 1.2075 | 0.2075 | 0.2075 | 0.2075 | 0 | 0 | 0 | 0
Persons/week |  |  | Tech AD M |  |  |  | 0.6575 | 0.8975 | 0.8975 | 0.8975 | 0.8975 | 1.6475 | 1.6475 | 0.8975 | 0.8975 | 0.8975 | 0.8975 | 3.2975 | 3.7975 | 3.7975 | 3.7975 | 3.7975 | 0.5 | 0.5 | 1.8675 | 1.8675 | 1.8675 | 1.1675 | 1.1675 | 1.1675 | 0 | 0 | 0 | 0
Persons/week |  |  | Tech AD E |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Persons/week |  |  | Electrician |  |  |  | 0.6575 | 1.7975 | 1.7975 | 1.7975 | 1.7975 | 1.7975 | 1.7975 | 3.2975 | 3.2975 | 3.2975 | 3.2975 | 1.66 | 2.66 | 1.16 | 1.16 | 1.16 | 1 | 1 | 0.6675 | 0.6675 | 0.6675 | 0 | 0 | 1.3325 | 1.3325 | 1.3325 | 0 | 0
Persons/week |  |  | Rigger |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 0.6625 | 0.6625 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Persons/week |  |  | Surveyor |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.0825 | 0.0825 | 0.0825 | 0.0825 | 0.0825 | 0.415 | 0.3325 | 0.3325 | 0.3325 | 0.3325 | 0.3325 | 0 | 0 | 0 | 2.6675 | 2.6675 | 3 | 0.5825 | 0.5825 | 0.25 | 0.25
Persons/week |  |  | Sci Labs |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4325 | 0.4325 | 0.4325 | 0.4325 | 0.4325 | 0.4325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3325 | 4.3325 | 4.3325 | 0 | 0
Persons/week |  |  | Tech Labs |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3325 | 4.3325 | 4.3325 | 0 | 0
Persons/week |  |  | PD Labs |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Persons/week |  |  | Sci Univ |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 6 | 6 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 6.3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 4 | 4 | 8 | 4 | 4 | 3.5 | 3.5
Persons/week |  |  | PD Univ |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 7 | 7 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 6.3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 4 | 4 | 8 | 4 | 4 | 3.5 | 3.5
Persons/week |  |  | GS Univ |  |  |  | 0.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0
3 or more/week for this skillset
|  | 5 or more/week for this skillset |  |  | Total persons/week |  | 13.1225 | 13.1225 | 13.1225 | 13.1225 | 13.1225 | 43.91 | 43.91 | 29.7875 | 28.08 | 28.08 | 28.08 | 28.7525 | 39.8975 | 23.2325 | 23.2325 | 23.2325 | 12.745 | 12.745 | 7.635 | 7.635 | 7.635 | 18.835 | 18.835 | 46.53 | 40.045 | 40.045 | 11.75 | 11.75
over 30 people/week

## P6 Modifications
Task | JOB GROUP | Task Sum Hours | Existing or NEW activity? | Activity Number | Predecessor | Start Date | Duration (days) | SCI PO | PROF PO | TECH PO M | TECH PO E | SCI AD | PROF AD | TECH AD M | TECH AD E | Electrician | Rigger | Surveyor | SCI Labs | TECH Labs | PD Labs | SCI UNIV | PD UNIV | GS UNIV | US UNIV
Infrastructure management | 0 | 40 | Existing | [5 empty] | 40
Detector Support systems management | 0 | 113 | Existing | [5 empty] | 113
Facility Support systems management | 0 | 113 | Existing | [9 empty] | 113
Installation management | 0 | 282 | Existing | [5 empty] | 282
WBS 2.2
Magnet Safety Reviews | 4 | 16 | Existing | [8 empty] | 8 | 8
Magnet PSU Work - cabling, WCB, testing | 4 | 241 | Existing | [9 empty] | 52 | 123 |  |  |  | 66
Magnet Cryo Ops - Cooldown | 4 | 171 | Existing | [9 empty] | 114 | 57
Magnet Cryo Ops - test at 4.5K (heat load, lo power, hi power) | 4 | 544 | Existing | [8 empty] | 160 | 216 | 168
Magnet Mapping preparations - Hall Probes | 4 | 97 | Existing |  |  |  |  | 19 | 19 |  | 59
Magnet Mapping preparations - construct support | 4 | 13 | Existing | [6 empty] | 13
Magnet Mapping preparations - install and test mapper | 4 | 480 | Existing |  |  |  |  | 160 | 80 | 80 | 160
Magnet Field Mapping | 4 | 560 | Existing |  |  |  |  | 160 | 80 | 240 | 80
Removal of mapper (listed under TPC installation) | 4 | 0
WBS 2.3.2
Acceptance TPC Supports | 0 | 80 | Existing | [5 empty] | 40 | 40
Acceptance MBD Supports | 0 | 20 | Existing | [5 empty] | 10 | 10
Acceptance Beamline Supports | 0 | 72 | Existing | [5 empty] | 36 | 36
WBS 2.4.1.3
Rack Assembly - Lower East | 2 | 6 | Existing | [7 empty] | 6
Rack Assembly - Upper Platform | 2 | 40 | Existing | [7 empty] | 40
ADDED RACK ASSEMBLY EFFORT, BASED ON EFFORT TO DATE | 2 | 500 | NEW | S331496 | (n.a.) | 2022-11-01 | 20 |  |  |  | 500
WBS 2.4.1.4
Design, procure, test remaining cooling system items | 1 | 180 | NEW | S332781 | (n.a.) | 2022-11-01 | 2 |  | 100 | 80
Cooling System Panel Fabrication - TPC | 1 | 138 | NEW | S332782 | S332781 SS 2d |  | 2 |  | 8 | 130
Cooling System Panel Fabrication - TPot | 1 | 64 | NEW | S332783 | S332782 |  | 2 |  | 4 | 60
Cooling System Panel Fabrication - EMCal SiPM | 1 | 290 | NEW | S332784 | S332783 |  | 2 |  |  | 290
Cooling System Panel Fabrication - EMCal PreAmp | 1 | 290 | NEW | S332785 | S332784 |  | 2 |  |  | 290
Cooling System Panel Fabrication - INTT ROC | 1 | 120 | NEW | S332786 | S332785 |  | 2 |  |  | 120
Cooling System Panel Fabrication - INTT Stave | 1 | 120 | NEW | S332787 | S332786 |  | 2 |  |  | 120
Cooling System Panel Fabrication - MVTX | 1 | 80 | NEW | S332788 | S332787 |  | 2 |  |  | 80
Cooling System Platform Manifolding | 1 | 124 | NEW | S332789 | S332788 |  | 2 |  | 24 | 100
Design, procure, test remaining gas system items | 1 | 270 | Existing | [5 empty] | 120 | 150
Gas Distribution Panel Fabrication - TPC Ar-CF4 | 1 | 100 | NEW | S332790 | (n.a.) | 2022-11-01 | 2 |  |  | 100
Gas Distribution Panel Fabrication - TPC Laser N2 | 1 | 40 | NEW | S332791 | S332790 |  | 2 |  |  | 40
Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 1 | 84 | NEW | S332792 | S332791 |  | 2 |  | 4 | 80
Gas Distribution Panel Fabrication - EMCal SiPM N2 | 1 | 40 | NEW | S332793 | S332792 |  | 2 |  |  | 40
Gas Distribution Panel Fabrication - INTT Stave N2 | 1 | 40 | NEW | S332794 | S332793 |  | 2 |  |  | 40
Gas Distribution Panel Fabrication - MVTX N2 | 1 | 8 | NEW | S332795 | S332794 |  | 2 |  |  | 8
Gas Distribution Panel Fabrication - MBD dry compressed air | 1 | 40 | NEW | S332796 | S332795 |  | 2 |  |  | 40
WBS 2.4.1.5 | [6 empty] | 2
Fabricate Detector Safety Systems | 1 | 120 | NEW | S333720 | (n.a.) | 2022-11-01 | 20 |  |  | 60 | 60
WBS 2.4.2.5
Design IR/AH Safety Systems | 2 | 120 | NEW | S342390 | (n.a.) | 2022-11-01 | 40 |  | 80 | 40
Procure IR/AH Safety Systems | 3 | 229 | Existing | [9 empty] | 115 | 114
INSTALLATION AFTER THIS POINT
WBS 2.5.2
Install Line Electric Power - off detector | 3 | 24 | Existing | [5 empty] | 4 |  |  |  | 4 |  |  | 16
Install Line Electric Power - on detector | 2 | 120 | Existing | [5 empty] | 34 |  |  |  | 18 |  |  | 68
Install Off-detector Safety Systems, inc VESDA | 3 | 120 | Existing | [9 empty] | 42 | 60 |  | 18
Install On-detector Safety Systems | 2 | 144 | Existing | [5 empty] | 36 | 36 | 72
Install On-detector Cooling water supply lines | 2 | 133 | Existing | [5 empty] | 18 | 86 | [6 empty] | 29
General support for gas and cooling systems for detectors | 2 | 936 | Existing | [5 empty] | 120 | 816
HVAC work | 3 | 18 | Existing | [9 empty] | 8 | 4 |  | 6
Install non-IR Infrastructure | 3 | 250 | Existing | [5 empty] | 40 | 40 | 40 |  | 10 | 40 | 40 |  | 40
Install Racks on All Carriage Platforms | 2 | 568 | Existing | [5 empty] | 160 | 220 | 188
Install AC power to Racks - Lower platforms | 2 | 120 | NEW | S346220 | (n.a.) | 2022-11-01 | 20 | [8 empty] | 120
Install AC power to Racks - Middle platforms | 2 | 120 | NEW | S346221 | S346220 FS | (n.a.) | 20 | [8 empty] | 120
Install AC power to Racks - Upper platforms | 2 | 480 | NEW | S346222 | S346230 FS | (n.a.) | 20 | [8 empty] | 480
Complete lighting and convenience power | 2 | 80 | NEW | S346223 | (n.a.) | 2022-11-01 | 20 | [8 empty] | 80
Complete wiring of chiller platform | 2 | 40 | NEW | S346224 | (n.a.) | 2022-11-01 | 40 | [8 empty] | 40
Complete wiring of N & S Pole Tip doors and motors | 2 | 80 | NEW | S346226 | (n.a.) | 2022-11-01 | 10 | [8 empty] | 80
Complete on-detector 24V-DC distribution system | 2 | 120 | NEW | S346228 | (n.a.) | 2022-11-01 | 20 | [7 empty] | 80 | 40
Complete global interlock system | 2 | 80 | NEW | S346232 | (n.a.) | 2022-11-01 | 20 | [7 empty] | 80
Complete ODH, crash, sweeps - CAD PASS | 2 | 40 | NEW | S346234 | (n.a.) | 2022-11-01 | 20 | [7 empty] | 40
Complete rack interlock system (36 racks) | 2 | 160 | NEW | S346235 | (n.a.) | 2022-11-01 | 20 | [7 empty] | 160
Complete FAP and HSSP - Fire Alarm group | 2 | 40 | NEW | S346236 | (n.a.) | 2022-11-01 | 20 | [7 empty] | 40
Complete network installation | 2 | 80 | NEW | S346238 | (n.a.) | 2022-11-01 | 40 | [7 empty] | 80
Complete ECW water leak detection | 2 | 80 | NEW | S346242 | (n.a.) | 2022-11-01 | 40 | [7 empty] | 80
Complete contactor boxes for interlock system | 2 | 120 | NEW | S346244 | (n.a.) | 2022-11-01 | 20 | [7 empty] | 120
Complete VESDA north/south solenoid - piping (sEPD area) | 2 | 120 | NEW | S346245 | (n.a.) | 2023-01-30 | 20 | [6 empty] | 80 | 40
Complete I/O terminations Rack 3B1 | 2 | 240 | NEW | S346246 | (n.a.) | 2022-11-01 | 40 | [7 empty] | 240
Test rack interlock system | 2 | 120 | NEW | S346248 | (n.a.) | 2022-11-01 | 40 |  | 80 | [5 empty] | 40
Test global interlock system | 2 | 120 | NEW | S346250 | (n.a.) | 2022-11-01 | 40 |  | 80 | [5 empty] | 40
Control system programming | 2 | 120 | NEW | S356252 | (n.a.) | 2022-11-01 | 40 |  | 120
Control system HMI and usage testing | 2 | 120 | NEW | S356255 | (n.a.) | 2022-11-01 | 40 |  | 120
Off Carriage Water Lines & Flow Control - Sill & Labyrinth area | 3 | 80 | NEW | S347610 | (n.a.) | 2022-11-01 | 2 | [6 empty] | 80
Off Carriage Water Lines & Flow Control - Chiller Platforms | 3 | 80 | NEW | S347620 | S347610 SS | (n.a.) | 2 | [6 empty] | 80
Off Carriage Water - ECW to 'brass block' | 3 | 40 | NEW | S347630 | S347620 SS | (n.a.) | 2 | [6 empty] | 40
Off Carriage Water - Brass block to chillers | 3 | 40 | NEW | S347640 | S347630 SS | (n.a.) | 2 |  |  | 40
Off Carriage Water - Chiller panels to cooling lines | 3 | 80 | NEW | S347650 | S347640 SS | (n.a.) | 2 | [6 empty] | 80
Off Carriage Water - Bridge lines | 3 | 40 | NEW | S347660 | S347650 SS | (n.a.) | 2 | [6 empty] | 40
Off Carriage Water - Bridges to on-carriage panels | 3 | 80 | NEW | S347670 | S347660 SS | (n.a.) | 2 | [6 empty] | 80
Off Carriage Water - Carriage ECW to on-carriage panels | 2 | 80 | NEW | S347680 | S347670 SS | (n.a.) | 2 |  |  | 80
Install Rack Cooling water - Lower platforms | 3 | 80 | NEW | S347820 | (n.a.) | 2022-11-01 | 20 | [6 empty] | 80
Install Rack Cooling water - Middle platforms | 3 | 80 | NEW | S347830 | S347820 FS | (n.a.) | 20 | [6 empty] | 80
Install Rack Cooling water - Upper platforms | 3 | 320 | NEW | S347840 | S347830 FS | (n.a.) | 20 | [6 empty] | 320
Install Rack Protection systems - Lower platform | 2 | 40 | NEW | S345920 | (n.a.) | 2022-11-01 | 20 |  |  |  | 40
Install Rack Protection systems - Middle platform | 2 | 40 | NEW | S345930 | S345920 FS | (n.a.) | 20 |  |  |  | 40
Install Rack Protection systems - Upper platform | 2 | 160 | NEW | S345940 | S345930 FS | (n.a.) | 20 |  |  |  | 160
Build North and South Work platforms | 1 | 21 | Existing | S346298 | [5 empty] | 21
WBS 2.5.4
Install remaining OHCal cables - LV, bias, signal, control | 1 | 32 | Existing | S351600 |  |  |  |  | 8 | 8 | 16
Check OHCal operation during cabling | 1 | 200 | NEW | S351710 | S351600 SS | 2022-11-21 | 10 | 40 | [13 empty] | 80 | 80
Install OHCal gas distribution panels and route lines | 1 | 40 | NEW | S351720 | S351600 SS | 2022-11-21 | 5 |  |  | 40
Check OHCal operation with slow controls (LV, bias, temp) | 1 | 200 | NEW | S351730 | S351600 SS | 2022-11-21 | 10 | 40 | [13 empty] | 80 | 80
Check OHCal operation with DAQ in counting house | 1 | 200 | NEW | S351740 | S351600 SS | 2022-11-21 | 10 | 40 | [13 empty] | 80 | 80
WBS 2.5.6
Install IHCal cables - LV, bias, signal, control | 1 | 320 | Existing | S356600 |  |  |  |  | 80 | 80 | 160
Check IHCal operation during cabling | 1 | 200 | NEW | S356710 | S356600 SS | 2022-11-21 | 10 | 40 | [13 empty] | 80 | 80
Install IHCal gas distribution panels and route lines | 1 | 40 | NEW | S356720 | S356600 SS | 2022-11-21 | 5 |  |  | 40
Check IHCal operation with slow controls (LV, bias, temp) | 1 | 200 | NEW | S356730 | S356600 SS | 2022-11-21 | 10 | 40 | [13 empty] | 80 | 80
Check IHCal operation with DAQ in counting house | 1 | 200 | NEW | S356740 | S356600 SS | 2022-11-21 | 10 | 40 | [13 empty] | 80 | 80
WBS 2.5.7
Check EMCal sectors 24-32 prior to leaving Bldg 510 | 1 | 160 | NEW | S358190 | (n.a.) | 2022-11-01 | 5 |  |  |  | 80 | [11 empty] | 80
Transport EMCal sectors 24-32 to 1008 AH | 1 | 85 | Existing | S358200 |  |  |  |  | 4 | 28 | [6 empty] | 53
Open magnet pole tips (currently under TPC, wrong place) | 1 | 20 | Existing | S360600 |  |  |  |  | 4 | 16
Remove magnet mapping appr. (currently under Magnet WBS) | 1 | 136 | Existing | S309100 |  |  |  | 16 |  | 40 | 80
Install EMCal Sectors 24 - 32 | 1 | 320 | Existing | S358400 |  |  |  |  | 32 | 288
Align EMCal sectors 24-32 | 1 | 110 | Existing | S358600 | [5 empty] | 10 |  |  |  | 60 |  |  |  | 40
Install EMCal cables - LV, bias, signal, control | 1 | 608 | Existing | S358800 |  |  |  |  | 32 | 96 | 160 |  |  |  | 320 | 0
Check EMCal operation during cabling | 1 | 940 | Existing | S359200 |  |  |  | 200 | 40 | 40 | 20 | [10 empty] | 320 | 320
Install EMCal cooling panels and route lines | 1 | 80 | NEW | S359402 | S358400 SS |  | 2 |  |  | 80
Install EMCal gas distribution panels and route lines | 1 | 80 | NEW | S359404 | S358400 SS |  | 2 |  |  | 80
Check EMCal operation with slow controls (LV, bias, temp) | 1 | 800 | NEW | S359406 | S358800 SS |  | 10 | 160 | [13 empty] | 320 | 320
Check EMCal operation with DAQ in counting house | 1 | 800 | NEW | S359408 | S358800 SS |  | 10 | 160 | [13 empty] | 320 | 320
WBS 2.5.7 (addition thereto, for TPOT)
Transport TPot from Stony Brook to 1008 AH | 1 | 16 | NEW | S359510 |  | 2022-12-01 | 1 |  |  | 8 | [8 empty] | 8
Install TPot Installation fixtures and test | 1 | 36 | NEW | S359520 | S358510 SS |  | 2 |  | 16 | 20
Install TPot support system | 1 | 24 | NEW | S359530 | S359520 FS |  | 1 |  | 4 | 20
Install TPot | 1 | 92 | NEW | S359540 | S359530 FS |  | 2 |  | 4 | 80 | [8 empty] | 8
Align TPot | 1 | 48 | NEW | S359550 | S359540 FS |  | 1 |  |  | 20 | [7 empty] | 20 | 8
Install TPot cables - LV, bias, signal, control | 1 | 132 | NEW | S359560 | S359550 FS |  | 2 |  | 24 | 20 | 40 |  |  |  | 40 | 0 |  |  | 8
Check TPot operation during cabling | 1 | 88 | NEW | S359570 | S259560 SS |  | 2 | 16 | [10 empty] | 24 |  |  | 24 | 24
Install TPot cooling panels and route lines | 1 | 40 | NEW | S359580 | S359530 SS |  | 2 |  |  | 40
Install TPot gas distribution panels and route lines | 1 | 40 | NEW | S359590 | S359530 SS |  | 2 |  |  | 40
Check TPot operation with slow controls (LV, bias, temp) | 1 | 88 | NEW | S359595 | S359560 SS |  | 2 | 16 | [10 empty] | 24 |  |  | 24 | 24
Check TPot operation with DAQ in counting house | 1 | 88 | NEW | S359597 | S359560 SS |  | 2 | 16 | [10 empty] | 24 |  |  | 24 | 24
WBS 2.5.8
Fab TPC insertion tooling/review procedures | 1 | 35 | Existing | [5 empty] | 15 | 20
Transport TPC from Stony Brook to 1008 AH | 1 | 48 | Existing | S360400 |  |  |  |  | 8 | 24 | 8 |  | 8
Install TPC Installation fixtures and test | 1 | 80 | NEW | S360620 | S360600 FS | (n.a.) | 1 |  | 40 | 40
Install TPC support system | 1 | 100 | Existing | S360700 |  |  |  |  | 4 | 96
Install TPC | 1 | 124 | Existing | S360900 |  |  |  |  | 4 | 76 |  |  | 8 |  |  |  | 36
Align TPC | 1 | 220 | Existing | S361100 | [5 empty] | 20 |  |  |  | 120 | 0 |  |  | 80
Install North and South Line Lasers | 1 | 96 | NEW | S361111 | S361100 FS | (n.a.) | 4 | 16 |  | 40 | 40
Install TPC cables - LV, bias, signal, control | 1 | 468 | Existing | S361300 |  |  |  |  | 24 | 84 | 120 |  |  |  | 240 | 0
Check TPC operation during cabling | 1 | 480 | NEW | S361420 | S361300 SS | (n.a.) | 15 | 160 | [13 empty] | 160 | 160
Install TPC cooling panels and route lines | 1 | 80 | NEW | S361440 | S360700 SS | (n.a.) | 2 |  |  | 80
Install TPC gas distribution panels and route lines | 1 | 80 | NEW | S361460 | S360700 SS | (n.a.) | 2 |  |  | 80
Install TPC Diffuse Lasers | 1 | 60 | NEW | S361465 | S361300 FS | (n.a.) | 2 | 12 |  | 24 | 24
Check TPC operation with slow controls (LV, bias, temp) | 1 | 480 | NEW | S361470 | S361300 SS | (n.a.) | 15 | 160 | [13 empty] | 160 | 160
Check TPC operation with DAQ in counting house | 1 | 480 | NEW | S361480 | S361300 SS | (n.a.) | 15 | 160 | [13 empty] | 160 | 160
Erect 1008 IR Shield Wall | 3 | 160 | NEW | S361950 | S3261480 FS | (n.a.) | 5 | [6 empty] | 80 |  |  | 80
WBS 2.5.9 (mostly)
Fab INTT insertion fixture/review procedures | 1 | 108 | Existing | [5 empty] | 56 | 52
Install INTT Installation fixtures and test | 1 | 40 | NEW | S362920 | S362800 SS | (n.a.) | 2 |  | 20 | 20
Install Beampipe Temporary Support | 3 | 300 | Existing | [5 empty] | 20 | 56 |  |  | 120 | 104
Install INTT support system | 1 | 76 | Existing | [5 empty] | 8 | 68
Install Beampipe | 3 | 40 | NEW | S363120 | S363000 FS | (n.a.) | 1 | [6 empty] | 40
Install Beampipe vacuum system | 3 | 40 | NEW | S363140 | S363120 | (n.a.) | 1 | [6 empty] | 40
Pump down beampipe | 3 | 40 | NEW | S363160 | S363140 | (n.a.) | 1 | [6 empty] | 40
Perform Beampipe Bakeout | 3 | 80 | NEW | S363180 | S363160 | (n.a.) | 5 | [7 empty] | 80
Transport INTT from 510 to 1008 AH | 1 | 40 | Existing | [5 empty] | 8 | 24 | 8
Install INTT | 1 | 76 | Existing | S363200 | S363180 |  |  |  | 8 | 68
Align INTT | 1 | 160 | Existing | S363400 | [5 empty] | 20 |  |  |  | 60 |  |  |  | 80
Install beampipe permanent support | 3 | 40 | NEW | S363520 | S363400 | n.a.) | 1 | [6 empty] | 40
Remove beampipe Temporary Support | 3 | 40 | NEW | S363540 | S363520 | (n.a.) | 1 | [6 empty] | 40
Install INTT cables - LV, bias, signal, control | 1 | 552 | Existing | S363600 |  |  |  |  | 48 | 144 | 120 |  |  |  | 240 | 0
Check INTT operation during cabling | 1 | 360 | NEW | S363720 | S363600 SS | (n.a.) | 5 | 40 | [13 empty] | 160 | 160
Install INTT cooling panels and route lines | 1 | 40 | NEW | S363740 | S363540 | (n.a.) | 1 |  |  | 40
Install INTT gas distribution panels and route lines | 1 | 40 | NEW | S363760 | S363540 | (n.a.) | 1 |  |  | 40
Check INTT operation with slow controls (LV, bias, temp) | 1 | 360 | NEW | S363770 | S363720 SS | (n.a.) | 5 | 40 | [13 empty] | 160 | 160
Check INTT operation with DAQ in counting house | 1 | 360 | NEW | S363780 | S363720 SS | (n.a.) | 5 | 40 | [13 empty] | 160 | 160
WBS 2.5.10
Prepare MVTX insertion procedures/review procedures | 1 | 58 | Existing | [5 empty] | 25 | 33
Transport MVTX from 510 to 1008 AH | 1 | 40 | Existing | [5 empty] | 8 | 24 | 8
Install MVTX Installation fixtures and test | 1 | 120 | NEW | S365450 | S365300 SS | (n.a.) | 1 |  |  | 40 | [8 empty] | 40 | 40
Install MVTX support system | 1 | 76 | Existing | [5 empty] | 8 | 68
Install FELIX, optical fibers, RU, Samtec cables | 1 | 136 | Existing | [5 empty] | 56 |  | 80
(both half-barrels) | 1 | 320 | Existing | [5 empty] | 160 | 160
Align MVTX | 1 | 40 | Existing | S366700/710 |  |  | 1 | [10 empty] | 40
Install MVTX cables - LV, bias, signal, control | 1 | 392 | Existing | S366900 |  |  |  |  | 48 | 104 | 80 |  |  |  | 160 | 0
Check MVTX operation during cabling | 1 | 680 | NEW | S367010 | S366900 SS | (n.a.) | 2 | 40 | [10 empty] | 160 | 160 |  | 160 | 160
Install MVTX cooling panels and route lines | 1 | 120 | NEW | S367020 | S366900 SS | (n.a.) | 1 |  |  | 120
Install MVTX gas distribution panels and route lines | 1 | 40 | NEW | S367030 | S366900 SS | (n.a.) | 1 |  |  | 40
Check MVTX operation with slow controls (LV, bias, temp) | 1 | 680 | NEW | S367040 | S366900 SS | (n.a.) | 2 | 40 | [10 empty] | 160 | 160 |  | 160 | 160
Check MVTX operation with DAQ in counting house | 1 | 680 | NEW | S367050 | S366900 SS | (n.a.) | 2 | 40 | [10 empty] | 160 | 160 |  | 160 | 160
WBS 2.5.11
Fab MBD insertion fixture/review procedures | 1 | 88 | Existing | [5 empty] | 41 | 47
Transport MBD from 510 to 1008 AH | 1 | 16 | Existing | [5 empty] | 8 | 8
Install MBD Installation fixtures and test | 1 | 20 | NEW | S368650 | S368600 | (n.a.) | 1 |  | 10 | 10
Install MBD support system | 1 | 32 | Existing | [5 empty] | 8 | 24
Install MBD | 1 | 32 | Existing | [5 empty] | 8 | 24
Align MBD | 1 | 40 | Existing | S369100/110 |  |  | 1 |  |  | 20 | [7 empty] | 20
Install MBD cables - LV, bias, signal, control | 1 | 80 | Existing | [6 empty] | 40 | 40
Check MBD operation during cabling | 1 | 200 | NEW | S369450 | S369300 SS | (n.a.) | 1 | 40 | [15 empty] | 160
Install MBD cooling panels and route lines | 1 | 40 | NEW | S369460 | S369700 SS | (n.a.) | 1 |  |  | 40
Install MBD gas distribution panels and route lines | 1 | 40 | NEW | S369470 | S369700 SS | (n.a.) | 1 |  |  | 40
Check MBD operation with slow controls (LV, bias, temp) | 1 | 200 | NEW | S369480 | S369450 SS | (n.a.) | 5 | 40 | [15 empty] | 160
Check MBD operation with DAQ in counting house | 1 | 200 | NEW | S369490 | S369450 SS | (n.a.) | 5 | 40 | [15 empty] | 160
add to WBS 2.5.11
Transport sEPD from 510 to 1008 AH | 1 | 40 | NEW | S370105 | S368500 | (n.a.) | 1 |  |  | 40
Install sEPD Installation fixtures and test | 1 | 40 | NEW | S370120 | S368650 | (n.a.) | 1 |  |  | 40
Install sEPD support system | 1 | 40 | NEW | S370140 | S368700 | (n.a.) | 1 |  |  | 40
Install sEPD | 1 | 40 | NEW | S370160 | S370140 | (n.a.) | 1 |  |  | 40
Align sEPD | 1 | 60 | NEW | S370180 | S370160 | (n.a.) | 1 |  |  | 40 | [7 empty] | 20
Install sEPD cables - LV, bias, signal, control | 1 | 120 | NEW | S370205 | S370180 | (n.a.) | 1 |  |  | 20 | 20 | [10 empty] | 40 | 40
Check sEPD operation during cabling | 1 | 200 | NEW | S370220 | S370200 SS | (n.a.) | 5 | 40 | [13 empty] | 80 | 80
Check sEPD operation with slow controls (LV, bias, temp) | 1 | 200 | NEW | S370240 | S370200 SS | (n.a.) | 5 | 40 | [13 empty] | 80 | 80
Check sEPD operation with DAQ in counting house | 1 | 200 | NEW | S370260 | S370200 SS | (n.a.) | 5 | 40 | [13 empty] | 80 | 80
WBS 2.5.12
Prepare for review of sPHENIX Safety System by CAD; review | 0 | 224 | Existing |  |  |  |  | 128 | 96
Prepare procedures for sPHENIX (blue sheet, pink sheet) | 0 | 240 | Existing |  |  |  |  | 80 | 80 |  |  |  | 80
Review and approve sPHENIX procedures | 0 | 96 | Existing |  |  |  |  | 32 | 32 |  |  |  | 32
Prepare for sPHENIX IRR | 0 | 320 | NEW | S370595 | (n.a.) | 2022-11-01 | 60 | 160 | 160
Prepare for sPHENIX ARR | 0 | 320 | NEW | S370597 | (n.a.) | 2022-11-01 | 60 | 160 | 160
Magnet final checkout before cooldown for ops under RHIC ASE | 0 | 48 | Existing | [8 empty] | 16 | 32
Preparation for full operation - In-rack safety sytems | 0 | 72 | Existing |  |  |  |  | 24 | 24 | 24
Preparation for full operation - Magnet re-check | 0 | 48 | Existing | [8 empty] | 16 | 32
Preparation for full operation - Verify global safety systems | 0 | 80 | Existing |  |  |  |  | 16 | 32 | 32
Preparation for full operation - Final safety walkthrus | 0 | 128 | Existing |  |  |  |  | 32 | 32 | 32 |  | 8 | 24
Grand Total Hours | (all) | 31071 | [5 empty] | 2783 | 3359 | 6986 | 2549 | 208 | 1036 | 2150 | 2160 | 1068 | 238 | 366 | 624 | 520 | 0 | 3232 | 3312 | 480 | 0
Job Group Key
Management, Procurement & Reviews | 0 | 2296 | [5 empty] | 632 | 1137 | 174 | 0 | 40 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Detector work | 1 | 18985 | [5 empty] | 1812 | 1131 | 5065 | 1164 | 0 | 16 | 240 | 1000 | 0 | 89 | 300 | 624 | 520 | 0 | 3232 | 3312 | 480 | 0
On-Carriage Infrasatructure | 2 | 5367 | [5 empty] | 0 | 848 | 1278 | 1046 | 0 | 18 | 80 | 1040 | 1028 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Off-Carriage Infrastructure | 3 | 2301 | [5 empty] | 0 | 64 | 136 | 40 | 0 | 299 | 1482 | 120 | 40 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Magnet Work | 4 | 2122 | [5 empty] | 339 | 179 | 333 | 299 | 168 | 390 | 348 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FTE over 6 months | (all) | 35.308 | [5 empty] | 3.1625 | 3.817 | 7.9386 | 2.8966 | 0.23636 | 1.1773 | 2.4432 | 2.4545 | 1.2136 | 0.27045 | 0.41591 | 0.70909 | 0.59091 | 0 | 3.6727 | 3.7636 | 0.54545 | 0
Management, Procurement & Reviews | 0 | 2.6091 | [5 empty] | 0.71818 | 1.292 | 0.19773 | 0 | 0.045455 | 0.35568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Detector work | 1 | 21.5739 | [5 empty] | 2.0591 | 1.2852 | 5.7557 | 1.3227 | 0 | 0.018182 | 0.27273 | 1.1364 | 0 | 0.10114 | 0.34091 | 0.70909 | 0.59091 | 0 | 3.6727 | 3.7636 | 0.54545 | 0
On-Carriage Infrasatructure | 2 | 6.0989 | [5 empty] | 0 | 0.96364 | 1.4523 | 1.1886 | 0 | 0.020455 | 0.090909 | 1.1818 | 1.1682 | 0.032955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Off-Carriage Infrastructure | 3 | 2.6148 | [5 empty] | 0 | 0.072727 | 0.15455 | 0.045455 | 0 | 0.33977 | 1.6841 | 0.13636 | 0.045455 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Magnet Work | 4 | 2.4114 | [5 empty] | 0.38523 | 0.20341 | 0.37841 | 0.33977 | 0.19091 | 0.44318 | 0.39545 | 0 | 0 | 0 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL FTE SCIentists | [5 empty] | 7.7807
|  | TOTAL FTE PROFessionals | [5 empty] | 4.9943
|  | TOTAL FTE TECHnicians | [5 empty] | 16.3239
|  | TOTAL FTE CRAFTspersons | [5 empty] | 1.9
|  | TOTAL FTE PostDocs | [5 empty] | 3.7636
|  | TOTAL FTE GraduateStudents | [5 empty] | 0.54545
|  | TOATL FTE UndergraduateStudents | [5 empty] | 0
Spreadsheet Keys
Labor Hours in P6
Labor Hours added after Fall 2002 review
| Job Group Key | Job Group
| Management, Procurement & Reviews | 0
| Detector work | 1
| On-Carriage Infrasatructure | 2
| Off-Carriage Infrastructure | 3
| Magnet Work | 4