## ETC
Baseline Data |  |  |  | Forecast Data (Sep2022 status file)
Activity ID | Activity Name | Budgeted Units | Budgeted Cost | Forecast Start | Forecast Finish | % Complete | Resource ID Name | Calc ETC Units | Updated ETC Units | Potential PCR? | Calc ETC Cost | Updated ETC Cost | EAC Growth
CAT C
POM02-13.02.01.04 Infrastructure Management |  | 153 | 17904.51 | 2022-10-03 | 2022-10-07 |  |  | 153 |  |  | 17904.51 | 17904.51 | 0
S276500 | 2023 Infrastructure Project Management | 40 | 5529.62 | 2022-10-03 | 2022-10-07 | 0% | PROF3 PO E | 40 |  |  | 5529.62 | 5529.62 | 0
S277100 | 2023 Facility Support Systems L3 Project Management | 113 | 12374.89 | 2022-10-03 | 2022-10-07 | 0% | PROF2 AD | 113 |  |  | 12374.89 | 12374.89 | 0
POM02-13.02.01.05 Installation Management |  | 282 | 52404.77 | 2022-10-03 | 2022-10-05 |  |  | 282 |  |  | 52404.77 | 52404.77 | 0
S278300 | 2023 Integration & Installation Project Management | 282 | 52404.77 | 2022-10-03 | 2022-10-05 | 0% | PROF5 PO M | 282 |  |  | 52404.77 | 52404.77 | 0
POM02-13.02.02.01.01 Safety Reviews |  | 32 | 6383.25 | 16-Sep-22 A | 2022-10-07 |  |  | 32 |  |  | 6383.25 | 6383.25 | 0
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 3009.03 | 16-Sep-22 A | 2022-10-07 | 50% | SCI3 AD | 8 |  |  | 1504.515 | 1504.515 | 0
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 3374.22 | 16-Sep-22 A | 2022-10-07 | 50% | PROF6 AD | 8 |  |  | 1687.11 | 1687.11 | 0
POM02-13.02.02.01.02 Cooldown & Power Tests |  | 724 | 118823.66 | 17-Aug-22 A | 2022-10-27 |  |  | 724 |  |  | 118823.66 | 118823.66 | 0
S279100 | Cooldown | 60 | 8294.42 | 17-Aug-22 A | 2022-10-17 | 5% | PROF3 AD | 57 |  |  | 7879.699 | 7879.699 | 0
S279100 | Cooldown | 60 | 7482.26 | 17-Aug-22 A | 2022-10-17 | 5% | TECH3 AD | 57 |  |  | 7108.147 | 7108.147 | 0
S279100 | Cooldown | 60 | 12653.32 | 17-Aug-22 A | 2022-10-17 | 5% | PROF6 AD | 57 |  |  | 12020.654 | 12020.654 | 0
S279200 | 4.5K Static Heat Load test | 8 | 1073.71 | 2022-10-18 | 2022-10-19 | 0% | PROF3 AD | 8 |  |  | 1073.71 | 1073.71 | 0
S279200 | 4.5K Static Heat Load test | 8 | 968.58 | 2022-10-18 | 2022-10-19 | 0% | TECH3 AD | 8 |  |  | 968.58 | 968.58 | 0
S279200 | 4.5K Static Heat Load test | 8 | 1637.97 | 2022-10-18 | 2022-10-19 | 0% | PROF6 AD | 8 |  |  | 1637.97 | 1637.97 | 0
S279300 | 4.5K Low power test | 20 | 2684.28 | 2022-10-20 | 2022-10-24 | 0% | PROF3 AD | 20 |  |  | 2684.28 | 2684.28 | 0
S279300 | 4.5K Low power test | 80 | 14606.95 | 2022-10-20 | 2022-10-24 | 0% | SCI3 AD | 80 |  |  | 14606.95 | 14606.95 | 0
S279300 | 4.5K Low power test | 80 | 9685.77 | 2022-10-20 | 2022-10-24 | 0% | TECH3 AD | 80 |  |  | 9685.77 | 9685.77 | 0
S279300 | 4.5K Low power test | 80 | 16379.7 | 2022-10-20 | 2022-10-24 | 0% | PROF6 AD | 80 |  |  | 16379.7 | 16379.7 | 0
S279400 | 4.5K High Power Test | 20 | 2684.28 | 2022-10-25 | 2022-10-27 | 0% | PROF3 AD | 20 |  |  | 2684.28 | 2684.28 | 0
S279400 | 4.5K High Power Test | 80 | 14606.95 | 2022-10-25 | 2022-10-27 | 0% | SCI3 AD | 80 |  |  | 14606.95 | 14606.95 | 0
S279400 | 4.5K High Power Test | 80 | 9685.77 | 2022-10-25 | 2022-10-27 | 0% | TECH3 AD | 80 |  |  | 9685.77 | 9685.77 | 0
S279400 | 4.5K High Power Test | 80 | 16379.7 | 2022-10-25 | 2022-10-27 | 0% | PROF6 AD | 80 |  |  | 16379.7 | 16379.7 | 0
POM02-13.02.02.04.01.03 Install PS AC/DC Cabling |  | 420 | 54812.28 | 01-Jul-22 A | 2022-10-07 |  |  | 420 |  |  | 54812.28 | 54812.28 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 40 | 6249.34 | 01-Jul-22 A | 2022-10-07 | 70% | PROF4 AD | 12 |  |  | 1874.802 | 1874.802 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 160 | 19371.55 | 01-Jul-22 A | 2022-10-07 | 70% | TECH3 AD | 48 |  |  | 5811.465 | 5811.465 | 0
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 220 | 29191.39 | 01-Jul-22 A | 2022-10-07 | 70% | CRAFT3 | 66 |  |  | 8757.417 | 8757.417 | 0
POM02-13.02.02.04.02.01 Install Power Supply |  | 230 | 31179.97 | 10-Aug-22 A | 2022-10-19 |  |  | 230 |  |  | 31179.97 | 31179.97 | 0
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 70 | 8729.3 | 10-Aug-22 A | 2022-10-11 | 50% | TECH3 AD | 35 |  |  | 4364.65 | 4364.65 | 0
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 12648.66 | 23-Sep-22 A | 2022-10-19 | 50% | PROF4 AD | 40 |  |  | 6324.33 | 6324.33 | 0
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 9802 | 23-Sep-22 A | 2022-10-19 | 50% | TECH3 AD | 40 |  |  | 4901 | 4901 | 0
POM02-13.02.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication |  | 112 | 17097.9 | 01-Sep-22 A | 2023-01-17 |  |  | 112 |  |  | 17097.9 | 17097.9 | 0
S308617 | Calibrate probes | 24 | 5400.02 | 01-Sep-22 A | 2022-12-30 | 20% | SCI4 PO | 19.2 |  |  | 4320.016 | 4320.016 | 0
S308617 | Calibrate probes | 24 | 3862.09 | 01-Sep-22 A | 2022-12-30 | 20% | PROF4 PO E | 19.2 |  |  | 3089.672 | 3089.672 | 0
S308617 | Calibrate probes | 24 | 2992.9 | 01-Sep-22 A | 2022-12-30 | 20% | TECH3 PO E | 19.2 |  |  | 2394.32 | 2394.32 | 0
S308619 | Install probes and readout on TPC | 40 | 4842.89 | 2023-01-03 | 2023-01-17 | 0% | TECH3 PO E | 40 |  |  | 4842.89 | 4842.89 | 0
POM02-13.02.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis |  | 1208 | 186391.94 | 08-Mar-21 A | 2022-12-22 |  |  | 1208 |  |  | 186391.94 | 186391.94 | 0
S308633 | Construct mapping support (mechanical and electrical) | 32 | 3874.31 | 08-Mar-21 A | 2022-11-01 | 60% | TECH3 PO M | 12.8 |  |  | 1549.724 | 1549.724 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 9976.35 | 2022-10-18 | 2022-10-31 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 19952.7 | 2022-10-18 | 2022-10-31 | 0% | TECH3 PO E | 160 |  |  | 19952.7 | 19952.7 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 11059.23 | 2022-10-18 | 2022-10-31 | 0% | PROF3 PO E | 80 |  |  | 11059.23 | 11059.23 | 0
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 36000.1 | 2022-10-18 | 2022-10-31 | 0% | SCI4 PO | 160 |  |  | 36000.1 | 36000.1 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9976.35 | 2022-11-01 | 2022-11-15 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 36000.1 | 2022-11-01 | 2022-11-15 | 0% | SCI4 PO | 160 |  |  | 36000.1 | 36000.1 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 11059.23 | 2022-11-01 | 2022-11-15 | 0% | PROF3 PO E | 80 |  |  | 11059.23 | 11059.23 | 0
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 19952.7 | 2022-11-01 | 2022-11-15 | 0% | TECH3 PO E | 160 |  |  | 19952.7 | 19952.7 | 0
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9976.35 | 2022-11-01 | 2022-11-15 | 0% | TECH3 PO E | 80 |  |  | 9976.35 | 9976.35 | 0
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 40 | 4988.17 | 2022-11-16 | 2022-11-22 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 80 | 9976.35 | 2022-11-16 | 2022-11-22 | 0% | TECH3 PO E | 80 |  |  | 9976.35 | 9976.35 | 0
S309110 | Receive report from CERN, incorporate into analysis | 16 | 3600.01 | 2022-11-23 | 2022-12-22 | 0% | SCI4 PO | 16 |  |  | 3600.01 | 3600.01 | 0
POM02-13.02.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports |  | 60180 | 94315.98 | 31-Mar-22 A | 2022-11-14 |  |  | 60180 |  |  | 94315.98 | 94315.98 | 0
S317940 | Procure TPC Supports - M&S | 50000 | 59194.9 | 31-Mar-22 A | 2022-10-28 | 85% | Purch 1st $2M | 7500 |  |  | 8879.235 | 8879.235 | 0
S317970 | Procure MBD Supports - M&S | 10000 | 11838.98 | 01-Jul-22 A | 2022-10-28 | 50% | Purch 1st $2M | 5000 |  |  | 5919.49 | 5919.49 | 0
S318140 | Perform TPC Supports Acceptance | 40 | 4842.89 | 2022-10-31 | 2022-11-14 | 0% | TECH3 PO M | 40 |  |  | 4842.89 | 4842.89 | 0
S318140 | Perform TPC Supports Acceptance | 40 | 5368.56 | 2022-10-31 | 2022-11-14 | 0% | PROF3 PO E | 40 |  |  | 5368.56 | 5368.56 | 0
S318170 | Perform MBD Supports Acceptance | 10 | 1210.72 | 2022-10-31 | 2022-11-14 | 0% | TECH3 PO M | 10 |  |  | 1210.72 | 1210.72 | 0
S318170 | Perform MBD Supports Acceptance | 10 | 1342.14 | 2022-10-31 | 2022-11-14 | 0% | PROF3 PO E | 10 |  |  | 1342.14 | 1342.14 | 0
S318190 | Perform Beampipe Supports Acceptance | 40 | 4988.17 | 26-Sep-22 A | 2022-10-17 | 10% | TECH3 PO M | 36 |  |  | 4489.353 | 4489.353 | 0
S318190 | Perform Beampipe Supports Acceptance | 40 | 5529.62 | 26-Sep-22 A | 2022-10-17 | 10% | PROF3 PO E | 36 |  |  | 4976.658 | 4976.658 | 0
POM02-13.02.04.01.03 Detector Electronics Racks and Rack generic support systems |  | 780 | 96252.38 | 13-Sep-21 A | 2022-11-10 |  |  | 780 |  |  | 96252.38 | 96252.38 | 0
S331470 | Assemble Racks for Lower East Platform | 80 | 9685.77 | 15-Nov-21 A | 2022-10-31 | 92% | TECH3 PO E | 6.4 |  |  | 774.8616 | 774.8616 | 0
S331490 | Assemble Racks for Main Upper Platform | 200 | 24214.44 | 13-Sep-21 A | 2022-10-31 | 80% | TECH3 PO E | 40 |  |  | 4842.888 | 4842.888 | 0
S331496 | ADDED RACK ASSEMBLY EFFORT, BASED ON EFFORT TO DATE | 500 | 62352.17 | 2022-11-01 | 2022-11-10 | 0% | TECH3 PO E | 500 |  |  | 62352.17 | 62352.17 | 0
POM02-13.02.04.01.04 Detector Gas and Cooling Services Systems |  | 56334 | 366297.65 | 15-Feb-21 A | 2023-02-09 |  |  | 56334 |  |  | 366297.65 | 366297.65 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 96 | 14561.56 | 15-Feb-21 A | 2022-10-31 | 80% | PROF4 PO M | 19.2 |  |  | 2912.312 | 2912.312 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642.2 | 15-Feb-21 A | 2022-10-31 | 80% | TECH3 PO D | 9.6 |  |  | 1128.44 | 1128.44 | 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642.2 | 15-Feb-21 A | 2022-10-31 | 80% | TECH3 PO M | 9.6 |  |  | 1128.44 | 1128.44 | 0
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 32 | 5004.47 | 22-Jul-22 A | 2022-10-31 | 40% | PROF4 PO M | 19.2 |  |  | 3002.682 | 3002.682 | 0
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 72 | 8725.91 | 22-Jul-22 A | 2022-10-31 | 40% | TECH3 PO D | 43.2 |  |  | 5235.546 | 5235.546 | 0
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 3862.09 | 05-Sep-22 A | 2022-11-02 | 40% | PROF4 PO M | 14.4 |  |  | 2317.254 | 2317.254 | 0
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 2992.9 | 05-Sep-22 A | 2022-11-02 | 40% | TECH3 PO D | 14.4 |  |  | 1795.74 | 1795.74 | 0
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 15448.36 | 03-Sep-22 A | 2023-02-02 | 40% | PROF4 PO M | 57.6 |  |  | 9269.016 | 9269.016 | 0
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 11971.62 | 03-Sep-22 A | 2023-02-02 | 40% | TECH3 PO D | 57.6 |  |  | 7182.972 | 7182.972 | 0
S332770 | Procure & Deliver Detector Gas Services Systems Components - M&S | 54000 | 65209.09 | 03-Sep-22 A | 2023-02-02 | 40% | Purch 1st $2M | 32400 |  |  | 39125.454 | 39125.454 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 2574.73 | 12-Sep-22 A | 2023-02-09 | 40% | PROF4 PO M | 9.6 |  |  | 1544.838 | 1544.838 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 1995.27 | 12-Sep-22 A | 2023-02-09 | 40% | TECH3 PO D | 9.6 |  |  | 1197.162 | 1197.162 | 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 8 | 997.63 | 12-Sep-22 A | 2023-02-09 | 40% | TECH3 PO M | 4.8 |  |  | 598.578 | 598.578 | 0
S332781 | Design, procure, test remaining cooling system items | 100 | 13824.04 | 2022-11-01 | 2022-11-02 | 0% | PROF3 PO E | 100 |  |  | 13824.04 | 13824.04 | 0
S332781 | Design, procure, test remaining cooling system items | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S332782 | Cooling System Panel Fabrication - TPC | 8 | 1105.92 | 2022-11-03 | 2022-11-04 | 0% | PROF3 PO E | 8 |  |  | 1105.92 | 1105.92 | 0
S332782 | Cooling System Panel Fabrication - TPC | 130 | 16211.57 | 2022-11-03 | 2022-11-04 | 0% | TECH3 PO M | 130 |  |  | 16211.57 | 16211.57 | 0
S332783 | Cooling System Panel Fabrication - TPot | 4 | 552.96 | 2022-11-07 | 2022-11-08 | 0% | PROF3 PO E | 4 |  |  | 552.96 | 552.96 | 0
S332783 | Cooling System Panel Fabrication - TPot | 60 | 7482.26 | 2022-11-07 | 2022-11-08 | 0% | TECH3 PO M | 60 |  |  | 7482.26 | 7482.26 | 0
S332784 | Cooling System Panel Fabrication - EMCal SiPM | 290 | 36164.26 | 2022-11-09 | 2022-11-10 | 0% | TECH3 PO M | 290 |  |  | 36164.26 | 36164.26 | 0
S332785 | Cooling System Panel Fabrication - EMCal PreAmp | 290 | 36164.26 | 2022-11-14 | 2022-11-15 | 0% | TECH3 PO M | 290 |  |  | 36164.26 | 36164.26 | 0
S332786 | Cooling System Panel Fabrication - INTT ROC | 120 | 14964.52 | 2022-11-16 | 2022-11-17 | 0% | TECH3 PO M | 120 |  |  | 14964.52 | 14964.52 | 0
S332787 | Cooling System Panel Fabrication - INTT Stave | 120 | 14964.52 | 2022-11-18 | 2022-11-21 | 0% | TECH3 PO M | 120 |  |  | 14964.52 | 14964.52 | 0
S332788 | Cooling System Panel Fabrication - MVTX | 80 | 9976.35 | 2022-11-22 | 2022-11-23 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S332789 | Cooling System Platform Manifolding | 24 | 3862.09 | 2022-11-28 | 2022-11-29 | 0% | PROF4 PO M | 24 |  |  | 3862.09 | 3862.09 | 0
S332789 | Cooling System Platform Manifolding | 100 | 12470.43 | 2022-11-28 | 2022-11-29 | 0% | TECH3 PO M | 100 |  |  | 12470.43 | 12470.43 | 0
S332790 | Gas Distribution Panel Fabrication - TPC Ar-CF4 | 100 | 12470.43 | 2022-10-03 | 2022-10-04 | 0% | TECH3 PO M | 100 |  |  | 12470.43 | 12470.43 | 0
S332791 | Gas Distribution Panel Fabrication - TPC Laser N2 | 40 | 4988.17 | 2022-10-05 | 2022-10-06 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 4 | 552.96 | 2022-10-07 | 2022-10-11 | 0% | PROF3 PO E | 4 |  |  | 552.96 | 552.96 | 0
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 80 | 9976.35 | 2022-10-07 | 2022-10-11 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S332793 | Gas Distribution Panel Fabrication - EMCal SiPM N2 | 40 | 4988.17 | 2022-10-12 | 2022-10-13 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S332794 | Gas Distribution Panel Fabrication - INTT Stave N2 | 40 | 4988.17 | 2022-10-14 | 2022-10-17 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S332795 | Gas Distribution Panel Fabrication - MVTX N2 | 8 | 997.63 | 2022-10-18 | 2022-10-19 | 0% | TECH3 PO M | 8 |  |  | 997.63 | 997.63 | 0
S332796 | Gas Distribution Panel Fabrication - MBD dry compressed air | 40 | 4988.17 | 2022-10-20 | 2022-10-21 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
POM02-13.02.04.01.05 Detector Safety Subsystems |  | 120 | 14964.52 | 2022-11-01 | 2022-12-01 |  |  | 120 |  |  | 14964.52 | 14964.52 | 0
S333720 | Fabricate Detector Safety Systems | 60 | 7482.26 | 2022-11-01 | 2022-12-01 | 0% | TECH3 PO M | 60 |  |  | 7482.26 | 7482.26 | 0
S333720 | Fabricate Detector Safety Systems | 60 | 7482.26 | 2022-11-01 | 2022-12-01 | 0% | TECH3 PO E | 60 |  |  | 7482.26 | 7482.26 | 0
POM02-13.02.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR |  | 113 | 20999.07 | 2022-10-03 | 2022-10-04 |  |  | 113 |  |  | 20999.07 | 20999.07 | 0
S277700 | 2023 Detector Support Systems L3 Project Management | 113 | 20999.07 | 2022-10-03 | 2022-10-04 | 0% | PROF5 PO M | 113 |  |  | 20999.07 | 20999.07 | 0
POM02-13.02.04.02.05 IR/AH Safety Subsystems |  | 32450 | 96653.71 | 04-Jul-22 A | 2023-01-06 |  |  | 32450 |  |  | 96653.71 | 96653.71 | 0
S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - M&S | 32000 | 38642.42 | 04-Jul-22 A | 2022-12-21 | 25% | Purch 1st $2M | 24000 |  |  | 28981.815 | 28981.815 | 0
S342390 | Design IR/AH Safety Systems | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S342390 | Design IR/AH Safety Systems | 80 | 11059.23 | 2022-11-01 | 2022-12-30 | 0% | PROF3 PO E | 80 |  |  | 11059.23 | 11059.23 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 24 | 3424.91 | 03-Sep-22 A | 2022-10-17 | 50% | TECH4 AD | 12 |  |  | 1712.455 | 1712.455 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 48 | 5256.59 | 03-Sep-22 A | 2022-10-17 | 50% | PROF2 AD | 24 |  |  | 2628.295 | 2628.295 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 4 | 643.68 | 03-Sep-22 A | 2022-10-17 | 50% | PROF4 AD | 2 |  |  | 321.84 | 321.84 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 48 | 6849.81 | 18-Sep-22 A | 2022-11-15 | 25% | TECH4 AD | 36 |  |  | 5137.3575 | 5137.3575 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 96 | 10513.18 | 18-Sep-22 A | 2022-11-15 | 25% | PROF2 AD | 72 |  |  | 7884.885 | 7884.885 | 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 2 | 321.84 | 18-Sep-22 A | 2022-11-15 | 25% | PROF4 AD | 1.5 |  |  | 241.38 | 241.38 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 88 | 12557.99 | 22-Sep-22 A | 2023-01-06 | 25% | TECH4 AD | 66 |  |  | 9418.4925 | 9418.4925 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 16 | 1752.2 | 22-Sep-22 A | 2023-01-06 | 25% | PROF2 AD | 12 |  |  | 1314.15 | 1314.15 | 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 4 | 643.68 | 22-Sep-22 A | 2023-01-06 | 25% | PROF4 AD | 3 |  |  | 482.76 | 482.76 | 0
POM02-13.02.05.02 Infrastructure Installation |  | 13128 | 956788.33 | 09-Sep-21 A | 2023-03-10 |  |  | 13128 |  |  | 956788.33 | 956788.33 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 160 | 21230.1 | 09-Sep-21 A | 2022-10-28 | 90% | CRAFT3 | 16 |  |  | 2123.01 | 2123.01 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 40 | 6249.34 | 09-Sep-21 A | 2022-10-28 | 90% | PROF4 PO E | 4 |  |  | 624.934 | 624.934 | 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 4 | 818.98 | 09-Sep-21 A | 2022-10-28 | 90% | PROF6 AD | 0.4 |  |  | 81.898 | 81.898 | 0
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 80 | 10933.5 | 30-Aug-22 A | 2022-10-31 | 50% | CRAFT3 | 40 |  |  | 5466.75 | 5466.75 | 0
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 40 | 6436.82 | 30-Aug-22 A | 2022-10-31 | 50% | PROF4 PO E | 20 |  |  | 3218.41 | 3218.41 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4842.89 | 03-Jan-22 A | 2022-10-28 | 95% | TECH3 AD | 2 |  |  | 242.1445 | 242.1445 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 64 | 8492.04 | 03-Jan-22 A | 2022-10-28 | 95% | CRAFT3 | 3.2 |  |  | 424.602 | 424.602 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4252.91 | 03-Jan-22 A | 2022-10-28 | 95% | PROF2 AD | 2 |  |  | 212.6455 | 212.6455 | 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 6249.34 | 03-Jan-22 A | 2022-10-28 | 95% | PROF4 AD | 2 |  |  | 312.467 | 312.467 | 0
S345600 | Install IR HVAC - M&S | 250 | 295.97 | 03-Jan-22 A | 2022-10-28 | 95% | Purch 1st $2M | 12.5 |  |  | 14.7985 | 14.7985 | 0
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 80 | 9976.35 | 01-Apr-22 A | 2023-02-06 | 25% | TECH3 AD | 60 |  |  | 7482.2625 | 7482.2625 | 0
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 16 | 2574.73 | 01-Apr-22 A | 2023-02-06 | 25% | PROF4 AD | 12 |  |  | 1931.0475 | 1931.0475 | 0
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 24 | 3280.05 | 01-Apr-22 A | 2023-02-06 | 25% | CRAFT3 | 18 |  |  | 2460.0375 | 2460.0375 | 0
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 40 | 4380.49 | 01-Apr-22 A | 2023-02-06 | 25% | PROF2 AD | 30 |  |  | 3285.3675 | 3285.3675 | 0
S345800 | Install On Detector Safety Subsystems - Labor | 80 | 9976.35 | 14-Sep-22 A | 2022-12-15 | 10% | TECH3 PO E | 72 |  |  | 8978.715 | 8978.715 | 0
S345800 | Install On Detector Safety Subsystems - Labor | 40 | 4988.17 | 14-Sep-22 A | 2022-12-15 | 10% | TECH3 PO M | 36 |  |  | 4489.353 | 4489.353 | 0
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3218.41 | 14-Sep-22 A | 2022-12-15 | 10% | PROF4 PO E | 18 |  |  | 2896.569 | 2896.569 | 0
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3218.41 | 14-Sep-22 A | 2022-12-15 | 10% | PROF4 PO M | 18 |  |  | 2896.569 | 2896.569 | 0
S345900 | Install On Detector Safety Subsystems - M&S | 500 | 603.79 | 14-Sep-22 A | 2022-12-15 | 10% | Purch 1st $2M | 450 |  |  | 543.411 | 543.411 | 0
S345910 | Install Off Detector Safety Subsystems inc Vesda - M&S | 500 | 603.79 | 01-Apr-22 A | 2023-02-06 | 25% | Purch 1st $2M | 375 |  |  | 452.8425 | 452.8425 | 0
S345920 | Install Rack Protection systems - Lower platform | 40 | 4988.17 | 2022-11-01 | 2022-12-01 | 0% | TECH3 PO E | 40 |  |  | 4988.17 | 4988.17 | 0
S345930 | Install Rack Protection systems - Middle platform | 40 | 4988.17 | 2022-12-02 | 2022-12-30 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S345940 | Install Rack Protection systems - Upper platform | 160 | 19952.7 | 2023-01-03 | 2023-01-31 | 0% | TECH3 PO E | 160 |  |  | 19952.7 | 19952.7 | 0
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 32 | 4999.47 | 09-Sep-21 A | 2022-10-28 | 90% | PROF4 AD | 3.2 |  |  | 499.947 | 499.947 | 0
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 32 | 4999.47 | 30-Aug-22 A | 2022-10-31 | 50% | PROF4 AD | 16 |  |  | 2499.735 | 2499.735 | 0
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 4 | 818.98 | 30-Aug-22 A | 2022-10-31 | 50% | PROF6 AD | 2 |  |  | 409.49 | 409.49 | 0
S346200 | Install Line Electric Power Distribution Off Detector - M&S | 500 | 591.95 | 09-Sep-21 A | 2022-10-28 | 90% | Purch 1st $2M | 50 |  |  | 59.195 | 59.195 | 0
S346210 | Install Line Electric Power Distribution On Detector - M&S | 500 | 597.46 | 30-Aug-22 A | 2022-10-31 | 50% | Purch 1st $2M | 250 |  |  | 298.73 | 298.73 | 0
S346220 | Install AC power to Racks - Lower platforms | 120 | 14964.52 | 2022-11-01 | 2022-12-01 | 0% | TECH3 PO E | 120 |  |  | 14964.52 | 14964.52 | 0
S346222 | Complete lighting and convenience power | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | 0% | TECH3 PO E | 80 |  |  | 9976.35 | 9976.35 | 0
S346224 | Complete wiring of chiller platform | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | 0% | TECH3 PO E | 40 |  |  | 4988.17 | 4988.17 | 0
S346226 | Complete wiring of N & S Ploe Tip doors and motors | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | 0% | TECH3 PO E | 80 |  |  | 9976.35 | 9976.35 | 0
S346228 | Complete on-detector 24V-DC distribution system | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | 0% | TECH3 PO E | 40 |  |  | 4988.17 | 4988.17 | 0
S346228 | Complete on-detector 24V-DC distribution system | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S346230 | Install AC power to Racks - Middle platforms | 120 | 14964.52 | 2022-12-02 | 2022-12-30 | 0% | TECH3 PO E | 120 |  |  | 14964.52 | 14964.52 | 0
S346232 | Complete global interlock system | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S346234 | Complete ODH, crash, sweeps - CAD PASS | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S346235 | Complete rack interlock system (36 racks) | 160 | 19952.7 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 160 |  |  | 19952.7 | 19952.7 | 0
S346236 | Complete FAP and HSSP - Fire Alarm group | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S346238 | Complete network installation | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S346240 | Install AC power to Racks - Upper platforms | 480 | 59858.09 | 2023-01-03 | 2023-01-31 | 0% | TECH3 PO E | 480 |  |  | 59858.09 | 59858.09 | 0
S346242 | Complete ECW water leak detection | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S346244 | Complete contactor boxes for interlock system | 120 | 14964.52 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 120 |  |  | 14964.52 | 14964.52 | 0
S346245 | Complete VESDA north/south solenoid - piping (sEPD area) | 120 | 14964.52 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 120 |  |  | 14964.52 | 14964.52 | 0
S346246 | Complete I/O terminations Rack 3B1 | 240 | 29929.04 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 240 |  |  | 29929.04 | 29929.04 | 0
S346248 | Test rack interlock system | 80 | 11059.23 | 2022-11-01 | 2022-12-30 | 0% | PROF3 PO E | 80 |  |  | 11059.23 | 11059.23 | 0
S346248 | Test rack interlock system | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S346250 | Test global interlock system | 80 | 11059.23 | 2022-11-01 | 2022-12-30 | 0% | PROF3 PO E | 80 |  |  | 11059.23 | 11059.23 | 0
S346250 | Test global interlock system | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S346298 | Build North and South work platforms | 30 | 3741.13 | 17-Aug-22 A | 2023-01-27 | 30% | TECH3 PO M | 21 |  |  | 2618.791 | 2618.791 | 0
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 20 | 3218.41 | 2023-01-30 | 2023-02-03 | 0% | PROF4 PO M | 20 |  |  | 3218.41 | 3218.41 | 0
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 40 | 4988.17 | 2023-01-30 | 2023-02-03 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 16 | 1995.27 | 2023-01-30 | 2023-02-03 | 0% | TECH3 PO D | 16 |  |  | 1995.27 | 1995.27 | 0
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 104 | 12969.25 | 2023-01-30 | 2023-02-03 | 0% | TECH3 AD | 104 |  |  | 12969.25 | 12969.25 | 0
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 80 | 8760.98 | 2023-01-30 | 2023-02-03 | 0% | PROF2 AD | 80 |  |  | 8760.98 | 8760.98 | 0
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 40 | 6436.82 | 2023-01-30 | 2023-02-03 | 0% | PROF4 AD | 40 |  |  | 6436.82 | 6436.82 | 0
S346400 | Install Beampipe Temp Support M&S | 500 | 603.79 | 2023-01-30 | 2023-02-03 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S346402 | Beampipe bakeout | 500 | 603.79 | 2023-02-06 | 2023-02-17 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S346404 | Install permanent Beampipe support | 500 | 603.79 | 2023-03-10 | 2023-03-10 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 9793.39 | 01-Apr-22 A | 2022-10-17 | 50% | TECH3 PO E | 40 |  |  | 4896.695 | 4896.695 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 9793.39 | 01-Apr-22 A | 2022-10-17 | 50% | TECH3 PO M | 40 |  |  | 4896.695 | 4896.695 | 0
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 12637.55 | 01-Apr-22 A | 2022-10-17 | 50% | PROF4 PO E | 40 |  |  | 6318.775 | 6318.775 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 160 | 19586.79 | 01-Apr-22 A | 2022-10-17 | 50% | TECH3 AD | 80 |  |  | 9793.395 | 9793.395 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 80 | 10733 | 01-Apr-22 A | 2022-10-17 | 50% | CRAFT3 | 40 |  |  | 5366.5 | 5366.5 | 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 20 | 2150.08 | 01-Apr-22 A | 2022-10-17 | 50% | PROF2 AD | 10 |  |  | 1075.04 | 1075.04 | 0
S346800 | Install Non-IR Infrastructure - M&S | 500 | 600.95 | 01-Apr-22 A | 2022-12-21 | 50% | Purch 1st $2M | 250 |  |  | 300.475 | 300.475 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18860.5 | 01-Apr-22 A | 2022-11-30 | 33% | PROF4 PO M | 80.4 |  |  | 12636.535 | 12636.535 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 34103.61 | 01-Apr-22 A | 2022-11-30 | 33% | TECH3 PO E | 187.6 |  |  | 22849.4187 | 22849.4187 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 34103.61 | 01-Apr-22 A | 2022-11-30 | 33% | TECH3 PO M | 187.6 |  |  | 22849.4187 | 22849.4187 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 48 | 5846.33 | 01-Apr-22 A | 2022-11-30 | 33% | TECH3 PO D | 32.16 |  |  | 3917.0411 | 3917.0411 | 0
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18860.5 | 01-Apr-22 A | 2022-11-30 | 33% | PROF4 PO E | 80.4 |  |  | 12636.535 | 12636.535 | 0
S347310 | Install Electronics Racks On Carriage - M&S | 500 | 594.32 | 01-Apr-22 A | 2022-11-30 | 33% | Purch 1st $2M | 335 |  |  | 398.1944 | 398.1944 | 0
S347400 | Install Gas and Cooling System Services - Labor | 120 | 19310.45 | 2022-10-03 | 2022-12-01 | 0% | PROF4 PO M | 120 |  |  | 19310.45 | 19310.45 | 0
S347400 | Install Gas and Cooling System Services - Labor | 720 | 89787.13 | 2022-10-03 | 2022-12-01 | 0% | TECH3 PO M | 720 |  |  | 89787.13 | 89787.13 | 0
S347400 | Install Gas and Cooling System Services - Labor | 96 | 11971.62 | 2022-10-03 | 2022-12-01 | 0% | TECH3 PO D | 96 |  |  | 11971.62 | 11971.62 | 0
S347500 | Install Gas and Cooling System Services - M&S | 500 | 603.79 | 2022-10-03 | 2022-12-01 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S347610 | Off Carriage Water Lines & Flow Control - Sill & Labyrinth area | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S347620 | Off Carriage Water Lines & Flow Control - Chiller Platforms | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S347630 | Off Carriage Water - ECW to 'brass block' | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S347640 | Off Carriage Water - Brass block to chillers | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S347650 | Off Carriage Water - Chiller panels to cooling lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S347660 | Off Carriage Water - Bridge lines | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S347670 | Off Carriage Water - Bridges to on-carriage panels | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S347680 | Off Carriage Water - Carriage ECW to on-carriage panels | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 80 | 9685.77 | 01-Aug-22 A | 2023-01-18 | 10% | TECH3 PO M | 72 |  |  | 8717.193 | 8717.193 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 16 | 1937.15 | 01-Aug-22 A | 2023-01-18 | 10% | TECH3 PO D | 14.4 |  |  | 1743.435 | 1743.435 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 32 | 4246.02 | 01-Aug-22 A | 2023-01-18 | 10% | CRAFT3 | 28.8 |  |  | 3821.418 | 3821.418 | 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 20 | 3124.67 | 01-Aug-22 A | 2023-01-18 | 10% | PROF4 PO E | 18 |  |  | 2812.203 | 2812.203 | 0
S347810 | Install IR Electronics Cooling Water On Detector - M&S | 500 | 591.95 | 01-Aug-22 A | 2023-01-18 | 10% | Purch 1st $2M | 450 |  |  | 532.755 | 532.755 | 0
S347820 | Install Rack Cooling water - Lower platforms | 80 | 9976.35 | 2022-11-01 | 2022-12-01 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S347830 | Install Rack Cooling water - Middle platforms | 80 | 9976.35 | 2022-12-02 | 2022-12-30 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S347840 | Install Rack Cooling water - Upper platforms | 320 | 39905.39 | 2023-01-03 | 2023-01-31 | 0% | TECH3 AD | 320 |  |  | 39905.39 | 39905.39 | 0
S356252 | Control system programming | 120 | 16588.85 | 2022-11-01 | 2022-12-30 | 0% | PROF3 PO E | 120 |  |  | 16588.85 | 16588.85 | 0
S356255 | Control system HMI and usage testing | 120 | 16588.85 | 2022-11-01 | 2022-12-30 | 0% | PROF3 PO E | 120 |  |  | 16588.85 | 16588.85 | 0
POM02-13.02.05.04 Outer Hcal Installation |  | 980 | 69703.86 | 01-Mar-22 A | 2022-12-06 |  |  | 980 |  |  | 69703.86 | 69703.86 | 0
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 9685.77 | 01-Mar-22 A | 2022-10-28 | 90% | TECH3 PO M | 8 |  |  | 968.577 | 968.577 | 0
S351600 | Install Outer HCal Cables and Services - Labor | 160 | 19371.55 | 01-Mar-22 A | 2022-10-28 | 90% | TECH3 PO E | 16 |  |  | 1937.155 | 1937.155 | 0
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 12498.68 | 01-Mar-22 A | 2022-10-28 | 90% | PROF4 PO E | 8 |  |  | 1249.868 | 1249.868 | 0
S351700 | Install Outer HCal Cables and Services - M&S | 500 | 591.95 | 01-Mar-22 A | 2022-10-28 | 90% | Purch 1st $2M | 50 |  |  | 59.195 | 59.195 | 0
S351710 | Check OHCal operation during cabling | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S351720 | Install OHCal gas distribution panels and route lines | 40 | 4988.17 | 2022-11-21 | 2022-11-29 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S351740 | Check OHCal operation with DAQ in counting house | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
POM02-13.02.05.06 Inner Hcal Installation |  | 980 | 69703.86 | 2022-10-03 | 2022-12-06 |  |  | 980 |  |  | 69703.86 | 69703.86 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 9685.77 | 2022-10-03 | 2022-10-31 | 0% | TECH3 PO M | 80 |  |  | 9685.77 | 9685.77 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 160 | 19371.55 | 2022-10-03 | 2022-10-31 | 0% | TECH3 PO E | 160 |  |  | 19371.55 | 19371.55 | 0
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 12498.68 | 2022-10-03 | 2022-10-31 | 0% | PROF4 PO E | 80 |  |  | 12498.68 | 12498.68 | 0
S356700 | Install Inner HCal Cables and Services (if instrumented) - M&S | 500 | 591.95 | 2022-11-01 | 2022-12-01 | 0% | Purch 1st $2M | 500 |  |  | 591.95 | 591.95 | 0
S356710 | Check IHCal operation during cabling | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S356720 | Install IHCal gas distribution panels and route lines | 40 | 4988.17 | 2022-11-21 | 2022-11-29 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S356740 | Check IHCal operation with DAQ in counting house | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
POM02-13.02.05.07 EMCal Installation |  | 5764 | 469131.25 | 01-Jul-22 A | 2023-02-10 |  |  | 5764 |  |  | 469131.25 | 469131.25 | 0
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 120 | 15922.58 | 01-Jul-22 A | 2022-12-09 | 56% | CRAFT3 | 52.8 |  |  | 7005.9352 | 7005.9352 | 0
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 64 | 7748.62 | 01-Jul-22 A | 2022-12-09 | 56% | TECH3 PO M | 28.16 |  |  | 3409.3928 | 3409.3928 | 0
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 80 | 9976.35 | 2022-11-01 | 2022-11-07 | 0% | TECH3 PO E | 80 |  |  | 9976.35 | 9976.35 | 0
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 8 | 1249.87 | 01-Jul-22 A | 2022-12-09 | 56% | PROF4 AD | 3.52 |  |  | 549.9428 | 549.9428 | 0
S358300 | Transport Assembled EMCal Sectors to AH - M&S | 500 | 591.95 | 01-Jul-22 A | 2022-12-09 | 56% | Purch 1st $2M | 220 |  |  | 260.458 | 260.458 | 0
S358400 | Install EMCal Sectors - Labor | 64 | 9998.94 | 01-Aug-22 A | 2022-12-09 | 50% | PROF4 PO M | 32 |  |  | 4999.47 | 4999.47 | 0
S358400 | Install EMCal Sectors - Labor | 64 | 7748.62 | 01-Aug-22 A | 2022-12-09 | 50% | TECH3 PO D | 32 |  |  | 3874.31 | 3874.31 | 0
S358400 | Install EMCal Sectors - Labor | 512 | 61988.96 | 01-Aug-22 A | 2022-12-09 | 50% | TECH3 PO M | 256 |  |  | 30994.48 | 30994.48 | 0
S358500 | Install EMCal Sectors - M&S | 500 | 591.95 | 01-Aug-22 A | 2022-12-09 | 50% | Purch 1st $2M | 250 |  |  | 295.975 | 295.975 | 0
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 17-Aug-22 A | 2022-12-12 | 50% | TECH3 PO M | 10 |  |  | 1247.045 | 1247.045 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10933.5 | 17-Aug-22 A | 2022-12-12 | 50% | CRAFT3 | 40 |  |  | 5466.75 | 5466.75 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 17-Aug-22 A | 2022-12-12 | 50% | TECH3 AD | 30 |  |  | 3741.13 | 3741.13 | 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8562.26 | 17-Aug-22 A | 2022-12-12 | 50% | TECH4 AD | 30 |  |  | 4281.13 | 4281.13 | 0
S358700 | Align/Survey EMCal to SC Magnet Centerline - M&S | 500 | 603.79 | 17-Aug-22 A | 2022-12-12 | 50% | Purch 1st $2M | 250 |  |  | 301.895 | 301.895 | 0
S358800 | Install EMCal Cables and Services - Labor | 160 | 19698.44 | 2022-12-13 | 2023-01-05 | 0% | TECH3 PO E | 160 |  |  | 19698.44 | 19698.44 | 0
S358800 | Install EMCal Cables and Services - Labor | 64 | 7879.38 | 2022-12-13 | 2023-01-05 | 0% | TECH3 PO M | 64 |  |  | 7879.38 | 7879.38 | 0
S358800 | Install EMCal Cables and Services - Labor | 32 | 5083.84 | 2022-12-13 | 2023-01-05 | 0% | PROF4 PO M | 32 |  |  | 5083.84 | 5083.84 | 0
S358800 | Install EMCal Cables and Services - Labor | 32 | 3939.69 | 2022-12-13 | 2023-01-05 | 0% | TECH3 PO D | 32 |  |  | 3939.69 | 3939.69 | 0
S358800 | Install EMCal Cables and Services - Labor | 320 | 43176.72 | 2022-12-13 | 2023-01-05 | 0% | CRAFT3 | 320 |  |  | 43176.72 | 43176.72 | 0
S358900 | Install EMCal Cables and Services - M&S | 500 | 598.61 | 2022-12-13 | 2023-01-05 | 0% | Purch 1st $2M | 500 |  |  | 598.61 | 598.61 | 0
S359200 | Commission EMCal - Labor | 400 | 75225.81 | 01-Aug-22 A | 2023-02-10 | 50% | SCI3 PO | 200 |  |  | 37612.905 | 37612.905 | 0
S359200 | Commission EMCal - Labor | 40 | 6436.82 | 01-Aug-22 A | 2023-02-10 | 50% | PROF4 PO E | 20 |  |  | 3218.41 | 3218.41 | 0
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | 50% | TECH3 PO E | 20 |  |  | 2494.085 | 2494.085 | 0
S359200 | Commission EMCal - Labor | 40 | 6436.82 | 01-Aug-22 A | 2023-02-10 | 50% | PROF4 PO M | 20 |  |  | 3218.41 | 3218.41 | 0
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | 50% | TECH3 PO D | 20 |  |  | 2494.085 | 2494.085 | 0
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | 50% | TECH3 PO M | 20 |  |  | 2494.085 | 2494.085 | 0
S359400 | Commission EMCal - M&S | 500 | 603.79 | 01-Aug-22 A | 2023-02-10 | 50% | Purch 1st $2M | 250 |  |  | 301.895 | 301.895 | 0
S359402 | Install EMCal cooling panels and route lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S359404 | Install EMCal gas distribution panels and route lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 160 | 30090.32 | 2022-12-13 | 2022-12-27 | 0% | SCI3 | 160 |  |  | 30090.32 | 30090.32 | 0
S359408 | Check EMCal operation with DAQ in counting house | 160 | 30090.32 | 2022-12-13 | 2022-12-27 | 0% | SCI3 | 160 |  |  | 30090.32 | 30090.32 | 0
S359510 | Transport TPot from Stony Brook to 1008 AH | 8 | 997.63 | 2022-12-01 | 2022-12-01 | 0% | TECH3 PO M | 8 |  |  | 997.63 | 997.63 | 0
S359520 | Install TPot Installation fixtures and test | 16 | 2211.85 | 2022-10-03 | 2022-10-04 | 0% | PROF3 PO M | 16 |  |  | 2211.85 | 2211.85 | 0
S359520 | Install TPot Installation fixtures and test | 20 | 2494.09 | 2022-10-03 | 2022-10-04 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S359530 | Install TPot support system | 4 | 552.96 | 2022-12-02 | 2022-12-02 | 0% | PROF3 PO M | 4 |  |  | 552.96 | 552.96 | 0
S359530 | Install TPot support system | 20 | 2494.09 | 2022-12-02 | 2022-12-02 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S359540 | Install TPot | 4 | 552.96 | 2022-10-05 | 2022-10-06 | 0% | PROF3 PO M | 4 |  |  | 552.96 | 552.96 | 0
S359540 | Install TPot | 80 | 9976.35 | 2022-10-05 | 2022-10-06 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S359550 | Align TPot | 20 | 2494.09 | 2022-12-05 | 2022-12-05 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S359550 | Align TPot | 20 | 2494.09 | 2022-12-05 | 2022-12-05 | 0% | TECH3 AD | 20 |  |  | 2494.09 | 2494.09 | 0
S359560 | Install TPot cables - LV, bias, signal, control | 24 | 3317.77 | 2022-10-07 | 2022-10-11 | 0% | PROF3 PO M | 24 |  |  | 3317.77 | 3317.77 | 0
S359560 | Install TPot cables - LV, bias, signal, control | 80 | 9976.35 | 2022-10-07 | 2022-10-11 | 0% | TECH3 PO E | 80 |  |  | 9976.35 | 9976.35 | 0
S359560 | Install TPot cables - LV, bias, signal, control | 20 | 2494.09 | 2022-10-07 | 2022-10-11 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S359570 | Check TPot operation during cabling | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | 0% | SCI3 | 16 |  |  | 3009.03 | 3009.03 | 0
S359580 | Install TPot cooling panels and route lines | 40 | 4988.17 | 2022-10-03 | 2022-10-04 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S359590 | Install TPot gas distribution panels and route lines | 40 | 4988.17 | 2022-10-03 | 2022-10-04 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | 0% | SCI3 | 16 |  |  | 3009.03 | 3009.03 | 0
S359597 | Check TPot operation with DAQ in counting house | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | 0% | SCI3 | 16 |  |  | 3009.03 | 3009.03 | 0
POM02-13.02.05.08 TPC Installation |  | 34644 | 348738.55 | 03-Jan-22 A | 2023-03-06 |  |  | 34644 |  |  | 348738.55 | 348738.55 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 4 | 643.68 | 2022-12-29 | 2023-01-05 | 0% | PROF4 PO M | 4 |  |  | 643.68 | 643.68 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 16 | 1995.27 | 2022-12-29 | 2023-01-05 | 0% | TECH3 PO D | 16 |  |  | 1995.27 | 1995.27 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 60 | 7482.26 | 2022-12-29 | 2023-01-05 | 0% | TECH3 PO M | 60 |  |  | 7482.26 | 7482.26 | 0
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 36 | 4920.08 | 2022-12-29 | 2023-01-05 | 0% | CRAFT3 | 36 |  |  | 4920.08 | 4920.08 | 0
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 60 | 9374.01 | 03-Jan-22 A | 2022-10-20 | 90% | PROF4 PO M | 6 |  |  | 937.401 | 937.401 | 0
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 20 | 2421.44 | 03-Jan-22 A | 2022-10-20 | 90% | TECH3 PO D | 2 |  |  | 242.144 | 242.144 | 0
S359800 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - M&S | 30000 | 35516.94 | 03-Jan-22 A | 2022-10-20 | 90% | Purch 1st $2M | 3000 |  |  | 3551.694 | 3551.694 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 25-Jan-22 A | 2022-11-02 | 90% | PROF4 PO M | 0.8 |  |  | 124.987 | 124.987 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 25-Jan-22 A | 2022-11-02 | 90% | TECH3 PO M | 0.8 |  |  | 96.858 | 96.858 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 25-Jan-22 A | 2022-11-02 | 90% | TECH3 PO D | 0.8 |  |  | 96.858 | 96.858 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1287.36 | 2022-11-03 | 2022-11-17 | 0% | PROF4 PO M | 8 |  |  | 1287.36 | 1287.36 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 997.63 | 2022-11-03 | 2022-11-17 | 0% | TECH3 PO M | 8 |  |  | 997.63 | 997.63 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 997.63 | 2022-11-03 | 2022-11-17 | 0% | TECH3 PO D | 8 |  |  | 997.63 | 997.63 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 1249.87 | 2022-12-13 | 2022-12-19 | 0% | PROF4 PO M | 8 |  |  | 1249.87 | 1249.87 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 24 | 2905.73 | 2022-12-13 | 2022-12-19 | 0% | TECH3 PO M | 24 |  |  | 2905.73 | 2905.73 | 0
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 968.58 | 2022-12-13 | 2022-12-19 | 0% | TECH3 PO E | 8 |  |  | 968.58 | 968.58 | 0
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 8 | 1249.87 | 2022-12-13 | 2022-12-19 | 0% | PROF4 AD | 8 |  |  | 1249.87 | 1249.87 | 0
S360500 | Transport Assembled TPC Sections to AH - M&S | 500 | 591.95 | 2022-12-13 | 2022-12-19 | 0% | Purch 1st $2M | 500 |  |  | 591.95 | 591.95 | 0
S360600 | Open SC Magnet Pole Tip Doors | 4 | 643.68 | 2022-12-20 | 2022-12-20 | 0% | PROF4 PO M | 4 |  |  | 643.68 | 643.68 | 0
S360600 | Open SC Magnet Pole Tip Doors | 16 | 1995.27 | 2022-12-20 | 2022-12-20 | 0% | TECH3 PO M | 16 |  |  | 1995.27 | 1995.27 | 0
S360620 | Install TPC Installation fixtures and test | 40 | 6436.82 | 2022-12-21 | 2022-12-21 | 0% | PROF4 PO M | 40 |  |  | 6436.82 | 6436.82 | 0
S360620 | Install TPC Installation fixtures and test | 40 | 4988.17 | 2022-12-21 | 2022-12-21 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S360700 | Install TPC Support - Labor | 4 | 643.68 | 2022-12-21 | 2022-12-28 | 0% | PROF4 PO M | 4 |  |  | 643.68 | 643.68 | 0
S360700 | Install TPC Support - Labor | 16 | 1995.27 | 2022-12-21 | 2022-12-28 | 0% | TECH3 PO D | 16 |  |  | 1995.27 | 1995.27 | 0
S360700 | Install TPC Support - Labor | 80 | 9976.35 | 2022-12-21 | 2022-12-28 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S360800 | Install TPC Support - M&S | 500 | 603.79 | 2022-12-21 | 2022-12-28 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 8 | 876.1 | 2022-12-29 | 2023-01-12 | 0% | PROF2 AD | 8 |  |  | 876.1 | 876.1 | 0
S361000 | Install TPC (Mechanical) - M&S | 500 | 603.79 | 2022-12-29 | 2023-01-12 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-01-13 | 2023-01-20 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10933.5 | 2023-01-13 | 2023-01-20 | 0% | CRAFT3 | 80 |  |  | 10933.5 | 10933.5 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 2023-01-13 | 2023-01-20 | 0% | TECH3 AD | 60 |  |  | 7482.26 | 7482.26 | 0
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8562.26 | 2023-01-13 | 2023-01-20 | 0% | TECH4 AD | 60 |  |  | 8562.26 | 8562.26 | 0
S361111 | Install North and South Line Lasers | 16 | 3009.03 | 2023-01-23 | 2023-01-26 | 0% | SCI3 | 16 |  |  | 3009.03 | 3009.03 | 0
S361111 | Install North and South Line Lasers | 40 | 4988.17 | 2023-01-23 | 2023-01-26 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S361111 | Install North and South Line Lasers | 40 | 4988.17 | 2023-01-23 | 2023-01-26 | 0% | TECH3 PO E | 40 |  |  | 4988.17 | 4988.17 | 0
S361200 | Align/Survey TPC to SC Magnet Centerline - M&S | 500 | 603.79 | 2023-01-13 | 2023-01-20 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S361300 | Install TPC Cables and Services - Labor | 120 | 14964.52 | 2023-02-06 | 2023-02-27 | 0% | TECH3 PO E | 120 |  |  | 14964.52 | 14964.52 | 0
S361300 | Install TPC Cables and Services - Labor | 60 | 7482.26 | 2023-02-06 | 2023-02-27 | 0% | TECH3 PO M | 60 |  |  | 7482.26 | 7482.26 | 0
S361300 | Install TPC Cables and Services - Labor | 24 | 3862.09 | 2023-02-06 | 2023-02-27 | 0% | PROF4 PO M | 24 |  |  | 3862.09 | 3862.09 | 0
S361300 | Install TPC Cables and Services - Labor | 24 | 2992.9 | 2023-02-06 | 2023-02-27 | 0% | TECH3 PO D | 24 |  |  | 2992.9 | 2992.9 | 0
S361300 | Install TPC Cables and Services - Labor | 240 | 32800.51 | 2023-02-06 | 2023-02-27 | 0% | CRAFT3 | 240 |  |  | 32800.51 | 32800.51 | 0
S361400 | Install TPC Cables and Services - M&S | 500 | 603.79 | 2023-02-06 | 2023-02-27 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S361420 | Check TPC operation during cabling | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | 0% | SCI3 | 160 |  |  | 30090.32 | 30090.32 | 0
S361440 | Install TPC cooling panels and route lines | 80 | 9976.35 | 2022-12-21 | 2022-12-22 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S361460 | Install TPC gas distribution panels and route lines | 80 | 9976.35 | 2022-12-21 | 2022-12-22 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S361465 | Install TPC Diffuse Lasers | 12 | 2256.77 | 2023-02-28 | 2023-03-01 | 0% | SCI3 | 12 |  |  | 2256.77 | 2256.77 | 0
S361465 | Install TPC Diffuse Lasers | 24 | 2992.9 | 2023-02-28 | 2023-03-01 | 0% | TECH3 PO M | 24 |  |  | 2992.9 | 2992.9 | 0
S361465 | Install TPC Diffuse Lasers | 24 | 2992.9 | 2023-02-28 | 2023-03-01 | 0% | TECH3 PO E | 24 |  |  | 2992.9 | 2992.9 | 0
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | 0% | SCI3 | 160 |  |  | 30090.32 | 30090.32 | 0
S361480 | Check TPC operation with DAQ in counting house | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | 0% | SCI3 | 160 |  |  | 30090.32 | 30090.32 | 0
S361950 | Erect 1008 IR Shield Wall | 80 | 9976.35 | 2023-02-28 | 2023-03-06 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S361950 | Erect 1008 IR Shield Wall | 80 | 9976.35 | 2023-02-28 | 2023-03-06 | 0% | TECH3 PO E | 80 |  |  | 9976.35 | 9976.35 | 0
POM02-13.02.05.09 INTT Installation |  | 4032 | 208995.72 | 2022-10-03 | 2023-03-09 |  |  | 4032 |  |  | 208995.72 | 208995.72 | 0
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 40 | 6249.34 | 2022-10-03 | 2022-10-17 | 0% | PROF4 PO M | 40 |  |  | 6249.34 | 6249.34 | 0
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 20 | 2421.44 | 2022-10-03 | 2022-10-17 | 0% | TECH3 PO D | 20 |  |  | 2421.44 | 2421.44 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-10-18 | 2022-10-31 | 0% | PROF4 PO M | 8 |  |  | 1249.87 | 1249.87 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-18 | 2022-10-31 | 0% | TECH3 PO M | 8 |  |  | 968.58 | 968.58 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-18 | 2022-10-31 | 0% | TECH3 PO D | 8 |  |  | 968.58 | 968.58 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 1249.87 | 2022-11-01 | 2022-11-15 | 0% | PROF4 PO M | 8 |  |  | 1249.87 | 1249.87 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 968.58 | 2022-11-01 | 2022-11-15 | 0% | TECH3 PO M | 8 |  |  | 968.58 | 968.58 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 968.58 | 2022-11-01 | 2022-11-15 | 0% | TECH3 PO D | 8 |  |  | 968.58 | 968.58 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 1287.36 | 2023-02-06 | 2023-02-07 | 0% | PROF4 PO M | 8 |  |  | 1287.36 | 1287.36 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | 24 | 2992.9 | 2023-02-06 | 2023-02-07 | 0% | TECH3 PO M | 24 |  |  | 2992.9 | 2992.9 | 0
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 997.63 | 2023-02-06 | 2023-02-07 | 0% | TECH3 PO E | 8 |  |  | 997.63 | 997.63 | 0
S362900 | Transport Assembled INTT Sections to AH - M&S | 500 | 603.79 | 2023-02-06 | 2023-02-07 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S362920 | Install INTT Installation fixtures and test | 20 | 2764.81 | 2023-02-06 | 2023-02-07 | 0% | PROF3 PO M | 20 |  |  | 2764.81 | 2764.81 | 0
S362920 | Install INTT Installation fixtures and test | 20 | 2494.09 | 2023-02-06 | 2023-02-07 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S363000 | Install INTT Support - Labor | 8 | 1287.36 | 2023-02-08 | 2023-02-17 | 0% | PROF4 PO M | 8 |  |  | 1287.36 | 1287.36 | 0
S363000 | Install INTT Support - Labor | 8 | 997.63 | 2023-02-08 | 2023-02-17 | 0% | TECH3 PO D | 8 |  |  | 997.63 | 997.63 | 0
S363000 | Install INTT Support - Labor | 60 | 7482.26 | 2023-02-08 | 2023-02-17 | 0% | TECH3 PO M | 60 |  |  | 7482.26 | 7482.26 | 0
S363100 | Install INTT Support - M&S | 500 | 603.79 | 2023-02-08 | 2023-02-17 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S363120 | Install Beampipe | 40 | 4988.17 | 2023-02-21 | 2023-02-21 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S363140 | Install Beampipe vacuum system | 40 | 4988.17 | 2023-02-22 | 2023-02-22 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S363160 | Pump down beampipe | 40 | 4988.17 | 2023-02-23 | 2023-02-23 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S363180 | Perform Beampipe Bakeout | 80 | 9976.35 | 2023-02-24 | 2023-03-02 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S363200 | Install INTT (mechanical) - Labor | 8 | 1287.36 | 2023-02-21 | 2023-03-02 | 0% | PROF4 PO M | 8 |  |  | 1287.36 | 1287.36 | 0
S363200 | Install INTT (mechanical) - Labor | 8 | 997.63 | 2023-02-21 | 2023-03-02 | 0% | TECH3 PO D | 8 |  |  | 997.63 | 997.63 | 0
S363200 | Install INTT (mechanical) - Labor | 60 | 7482.26 | 2023-02-21 | 2023-03-02 | 0% | TECH3 PO M | 60 |  |  | 7482.26 | 7482.26 | 0
S363300 | Install INTT (mechanical) - M&S | 500 | 603.79 | 2023-02-21 | 2023-03-02 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-02-21 | 2023-03-02 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 9976.35 | 2023-02-21 | 2023-03-02 | 0% | TECH3 AD | 80 |  |  | 9976.35 | 9976.35 | 0
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 2023-02-21 | 2023-03-02 | 0% | TECH3 AD | 60 |  |  | 7482.26 | 7482.26 | 0
S363500 | Align/Survey INTT to SC Magnet Centerline - M&S | 500 | 603.79 | 2023-02-21 | 2023-03-02 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S363520 | Install beampipe permanent support | 40 | 4988.17 | 2023-03-03 | 2023-03-03 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S363540 | Remove beampipe Temporary Support | 40 | 4988.17 | 2023-03-06 | 2023-03-06 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S363600 | Install INTT Cables and Services - Labor | 120 | 14964.52 | 2023-03-03 | 2023-03-09 | 0% | TECH3 PO E | 120 |  |  | 14964.52 | 14964.52 | 0
S363600 | Install INTT Cables and Services - Labor | 120 | 14964.52 | 2023-03-03 | 2023-03-09 | 0% | TECH3 PO M | 120 |  |  | 14964.52 | 14964.52 | 0
S363600 | Install INTT Cables and Services - Labor | 24 | 3862.09 | 2023-03-03 | 2023-03-09 | 0% | PROF4 PO E | 24 |  |  | 3862.09 | 3862.09 | 0
S363600 | Install INTT Cables and Services - Labor | 24 | 3862.09 | 2023-03-03 | 2023-03-09 | 0% | PROF4 PO M | 24 |  |  | 3862.09 | 3862.09 | 0
S363600 | Install INTT Cables and Services - Labor | 24 | 2992.9 | 2023-03-03 | 2023-03-09 | 0% | TECH3 PO D | 24 |  |  | 2992.9 | 2992.9 | 0
S363600 | Install INTT Cables and Services - Labor | 240 | 32800.51 | 2023-03-03 | 2023-03-09 | 0% | CRAFT3 | 240 |  |  | 32800.51 | 32800.51 | 0
S363700 | Install INTT Cables and Services - M&S | 500 | 603.79 | 2023-03-03 | 2023-03-09 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S363720 | Check INTT operation during cabling | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S363740 | Install INTT cooling panels and route lines | 40 | 4988.17 | 2023-03-07 | 2023-03-07 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S363760 | Install INTT gas distribution panels and route lines | 40 | 4988.17 | 2023-03-07 | 2023-03-07 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S363780 | Check INTT operation with DAQ in counting house | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
POM02-13.02.05.10 MVTX Installation |  | 2922 | 195130.32 | 29-Apr-21 A | 2023-03-22 |  |  | 2922 |  |  | 195130.32 | 195130.32 | 0
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 29-Apr-21 A | 2022-10-28 | 75% | PROF4 PO M | 10 |  |  | 1516.83 | 1516.83 | 0
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 10 | 1175.46 | 29-Apr-21 A | 2022-10-28 | 75% | TECH3 PO D | 2.5 |  |  | 293.865 | 293.865 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 26-Jul-22 A | 2022-11-14 | 10% | PROF4 PO M | 7.2 |  |  | 1124.883 | 1124.883 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 26-Jul-22 A | 2022-11-14 | 10% | TECH3 PO D | 7.2 |  |  | 871.722 | 871.722 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 26-Jul-22 A | 2022-11-14 | 10% | TECH3 PO M | 7.2 |  |  | 871.722 | 871.722 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-11-15 | 2022-11-30 | 0% | PROF4 PO M | 8 |  |  | 1249.87 | 1249.87 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | 0% | TECH3 PO D | 8 |  |  | 968.58 | 968.58 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | 0% | TECH3 PO M | 8 |  |  | 968.58 | 968.58 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 1249.87 | 2022-12-09 | 2022-12-15 | 0% | PROF4 PO M | 8 |  |  | 1249.87 | 1249.87 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | 24 | 2905.73 | 2022-12-09 | 2022-12-15 | 0% | TECH3 PO M | 24 |  |  | 2905.73 | 2905.73 | 0
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 968.58 | 2022-12-09 | 2022-12-15 | 0% | TECH3 PO E | 8 |  |  | 968.58 | 968.58 | 0
S365400 | Transport Assembled MVTX Sections to IR - M&S | 500 | 591.95 | 2022-12-09 | 2022-12-15 | 0% | Purch 1st $2M | 500 |  |  | 591.95 | 591.95 | 0
S365450 | Install MVTX Installation fixtures and test | 40 | 4988.17 | 2022-12-09 | 2022-12-09 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S365500 | Install MVTX Support - Labor | 8 | 1287.36 | 2023-03-09 | 2023-03-09 | 0% | PROF4 PO M | 8 |  |  | 1287.36 | 1287.36 | 0
S365500 | Install MVTX Support - Labor | 8 | 997.63 | 2023-03-09 | 2023-03-09 | 0% | TECH3 PO D | 8 |  |  | 997.63 | 997.63 | 0
S365500 | Install MVTX Support - Labor | 60 | 7482.26 | 2023-03-09 | 2023-03-09 | 0% | TECH3 PO M | 60 |  |  | 7482.26 | 7482.26 | 0
S365600 | Install MVTX Support - M&S | 500 | 603.79 | 2023-03-09 | 2023-03-09 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S365700 | Install FELIX | 16 | 2211.85 | 2023-03-10 | 2023-03-13 | 0% | PROF3 IO E | 16 |  |  | 2211.85 | 2211.85 | 0
S365900 | Install Optical fibers | 40 | 4988.17 | 2023-03-10 | 2023-03-13 | 0% | TECH3 PO E | 40 |  |  | 4988.17 | 4988.17 | 0
S366000 | Install RU | 40 | 5529.62 | 2023-03-10 | 2023-03-13 | 0% | PROF3 IO E | 40 |  |  | 5529.62 | 5529.62 | 0
S366200 | Install Samtec Cables | 40 | 4988.17 | 2023-03-10 | 2023-03-10 | 0% | TECH3 PO E | 40 |  |  | 4988.17 | 4988.17 | 0
S366300 | Install Half-Barrel 1 | 80 | 11059.23 | 2023-03-13 | 2023-03-14 | 0% | PROF3 PO M | 80 |  |  | 11059.23 | 11059.23 | 0
S366300 | Install Half-Barrel 1 | 80 | 9976.35 | 2023-03-13 | 2023-03-14 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S366500 | Install Half-Barrel 2 | 80 | 9976.35 | 2023-03-15 | 2023-03-16 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S366500 | Install Half-Barrel 2 | 80 | 11059.23 | 2023-03-15 | 2023-03-16 | 0% | PROF3 PO M | 80 |  |  | 11059.23 | 11059.23 | 0
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 40 | 4988.17 | 2023-03-17 | 2023-03-20 | 0% | TECH3 AD | 40 |  |  | 4988.17 | 4988.17 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9976.35 | 2023-03-20 | 2023-03-21 | 0% | TECH3 PO M | 80 |  |  | 9976.35 | 9976.35 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3862.09 | 2023-03-20 | 2023-03-21 | 0% | PROF4 PO E | 24 |  |  | 3862.09 | 3862.09 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9976.35 | 2023-03-20 | 2023-03-21 | 0% | TECH3 PO E | 80 |  |  | 9976.35 | 9976.35 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 2992.9 | 2023-03-20 | 2023-03-21 | 0% | TECH3 PO D | 24 |  |  | 2992.9 | 2992.9 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3862.09 | 2023-03-20 | 2023-03-21 | 0% | PROF4 PO M | 24 |  |  | 3862.09 | 3862.09 | 0
S366900 | Install MVTX Remaining Cables and Services - Labor | 160 | 21867.01 | 2023-03-20 | 2023-03-21 | 0% | CRAFT3 | 160 |  |  | 21867.01 | 21867.01 | 0
S367000 | Install MVTX Remaining Cables and Services - M&S | 500 | 603.79 | 2023-03-20 | 2023-03-21 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S367010 | Check MVTX operation during cabling | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S367020 | Install MVTX cooling panels and route lines | 120 | 14964.52 | 2023-03-20 | 2023-03-21 | 0% | TECH3 PO M | 120 |  |  | 14964.52 | 14964.52 | 0
S367030 | Install MVTX gas distribution panels and route lines | 40 | 4988.17 | 2023-03-20 | 2023-03-21 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S367050 | Check MVTX operation with DAQ in counting house | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
POM02-13.02.05.11 Min Bias Installation |  | 12998 | 157174.37 | 29-Apr-21 A | 2023-03-29 |  |  | 12998 |  |  | 157174.37 | 157174.37 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 30 | 4724.5 | 01-Jul-22 A | 2022-10-25 | 50% | PROF4 PO M | 15 |  |  | 2362.25 | 2362.25 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1220.41 | 01-Jul-22 A | 2022-10-25 | 50% | TECH3 PO D | 5 |  |  | 610.205 | 610.205 | 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1220.41 | 01-Jul-22 A | 2022-10-25 | 50% | TECH3 PO M | 5 |  |  | 610.205 | 610.205 | 0
S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - M&S | 10000 | 11838.98 | 01-Jul-22 A | 2022-10-25 | 50% | Purch 1st $2M | 5000 |  |  | 5919.49 | 5919.49 | 0
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 29-Apr-21 A | 2022-10-28 | 75% | PROF4 PO M | 10 |  |  | 1516.83 | 1516.83 | 0
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 20 | 2350.92 | 29-Apr-21 A | 2022-10-28 | 75% | TECH3 PO D | 5 |  |  | 587.73 | 587.73 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-10-31 | 2022-11-14 | 0% | PROF4 PO M | 8 |  |  | 1249.87 | 1249.87 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-31 | 2022-11-14 | 0% | TECH3 PO D | 8 |  |  | 968.58 | 968.58 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-31 | 2022-11-14 | 0% | TECH3 PO M | 8 |  |  | 968.58 | 968.58 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-11-15 | 2022-11-30 | 0% | PROF4 PO M | 8 |  |  | 1249.87 | 1249.87 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | 0% | TECH3 PO D | 8 |  |  | 968.58 | 968.58 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | 0% | TECH3 PO M | 8 |  |  | 968.58 | 968.58 | 0
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 1287.36 | 2023-03-13 | 2023-03-13 | 0% | PROF4 PO M | 8 |  |  | 1287.36 | 1287.36 | 0
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 997.63 | 2023-03-13 | 2023-03-13 | 0% | TECH3 PO M | 8 |  |  | 997.63 | 997.63 | 0
S368600 | Transport Assembled Min Bias Sections to AH - M&S | 500 | 603.79 | 2023-03-13 | 2023-03-13 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S368650 | Install MBD Installation fixtures and test | 10 | 1382.4 | 2023-03-14 | 2023-03-14 | 0% | PROF3 PO M | 10 |  |  | 1382.4 | 1382.4 | 0
S368650 | Install MBD Installation fixtures and test | 10 | 1247.04 | 2023-03-14 | 2023-03-14 | 0% | TECH3 PO M | 10 |  |  | 1247.04 | 1247.04 | 0
S368700 | Install Min Bias Support - Labor | 8 | 1287.36 | 2023-03-14 | 2023-03-14 | 0% | PROF4 PO M | 8 |  |  | 1287.36 | 1287.36 | 0
S368700 | Install Min Bias Support - Labor | 8 | 997.63 | 2023-03-14 | 2023-03-14 | 0% | TECH3 PO D | 8 |  |  | 997.63 | 997.63 | 0
S368700 | Install Min Bias Support - Labor | 16 | 1995.27 | 2023-03-14 | 2023-03-14 | 0% | TECH3 PO M | 16 |  |  | 1995.27 | 1995.27 | 0
S368800 | Install Min Bias Support - M&S | 500 | 603.79 | 2023-03-14 | 2023-03-14 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S368900 | Install Min Bias (mechanical) - Labor | 8 | 1287.36 | 2023-03-15 | 2023-03-15 | 0% | PROF4 PO M | 8 |  |  | 1287.36 | 1287.36 | 0
S368900 | Install Min Bias (mechanical) - Labor | 8 | 997.63 | 2023-03-15 | 2023-03-15 | 0% | TECH3 PO D | 8 |  |  | 997.63 | 997.63 | 0
S368900 | Install Min Bias (mechanical) - Labor | 16 | 1995.27 | 2023-03-15 | 2023-03-15 | 0% | TECH3 PO M | 16 |  |  | 1995.27 | 1995.27 | 0
S369000 | Install Min Bias (mechanical) - M&S | 500 | 603.79 | 2023-03-15 | 2023-03-15 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-22 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-22 | 0% | TECH3 AD | 20 |  |  | 2494.09 | 2494.09 | 0
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-17 | 0% | TECH3 AD | 20 |  |  | 2494.09 | 2494.09 | 0
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-20 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S369300 | Install Min Bias Cables and Services - Labor | 40 | 4988.17 | 2023-03-23 | 2023-03-23 | 0% | TECH3 PO E | 40 |  |  | 4988.17 | 4988.17 | 0
S369300 | Install Min Bias Cables and Services - Labor | 40 | 4988.17 | 2023-03-23 | 2023-03-23 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S369400 | Install Min Bias Cables and Services - M&S | 500 | 603.79 | 2023-03-23 | 2023-03-23 | 0% | Purch 1st $2M | 500 |  |  | 603.79 | 603.79 | 0
S369450 | Check MBD operation during cabling | 40 | 7522.58 | 2023-03-23 | 2023-03-23 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S369460 | Install MBD cooling panels and route lines | 40 | 4988.17 | 2023-03-24 | 2023-03-24 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S369470 | Install MBD gas distribution panels and route lines | 40 | 4988.17 | 2023-03-24 | 2023-03-24 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-23 | 2023-03-29 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S369490 | Check MBD operation with DAQ in counting house | 40 | 7522.58 | 2023-03-23 | 2023-03-29 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S370105 | Install MBD cooling panels and route lines | 40 | 4988.17 | 2023-03-14 | 2023-03-14 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S370120 | Install sEPD Installation fixtures and test | 40 | 4988.17 | 2023-03-15 | 2023-03-15 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S370140 | Install sEPD support system | 40 | 4988.17 | 2023-03-15 | 2023-03-15 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S370160 | Install sEPD | 40 | 4988.17 | 2023-03-16 | 2023-03-16 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S370180 | Align sEPD | 40 | 4988.17 | 2023-03-17 | 2023-03-17 | 0% | TECH3 PO M | 40 |  |  | 4988.17 | 4988.17 | 0
S370180 | Align sEPD | 20 | 2494.09 | 2023-03-17 | 2023-03-17 | 0% | TECH3 AD | 20 |  |  | 2494.09 | 2494.09 | 0
S370205 | Install sEPD cables - LV, bias, signal, control | 20 | 2494.09 | 2023-03-20 | 2023-03-20 | 0% | TECH3 PO M | 20 |  |  | 2494.09 | 2494.09 | 0
S370205 | Install sEPD cables - LV, bias, signal, control | 20 | 2494.09 | 2023-03-20 | 2023-03-20 | 0% | TECH3 PO E | 20 |  |  | 2494.09 | 2494.09 | 0
S370220 | Check sEPD operation during cabling | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | 0% | SCI3 | 40 |  |  | 7522.58 | 7522.58 | 0
POM02-13.02.05.12 Full System Integration and ORR |  | 1592 | 270974.3 | 2022-10-03 | 2023-01-31 |  |  | 1592 |  |  | 270974.3 | 270974.3 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249.34 | 2022-10-03 | 2022-10-31 | 0% | PROF4 PO M | 40 |  |  | 6249.34 | 6249.34 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249.34 | 2022-10-03 | 2022-10-31 | 0% | PROF4 PO E | 40 |  |  | 6249.34 | 6249.34 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 7303.48 | 2022-10-03 | 2022-10-31 | 0% | SCI3 PO | 40 |  |  | 7303.48 | 7303.48 | 0
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 8737.89 | 2022-10-03 | 2022-10-31 | 0% | SCI4 PO | 40 |  |  | 8737.89 | 8737.89 | 0
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1249.87 | 2022-11-01 | 2022-11-03 | 0% | PROF4 PO M | 8 |  |  | 1249.87 | 1249.87 | 0
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1249.87 | 2022-11-01 | 2022-11-03 | 0% | PROF4 PO E | 8 |  |  | 1249.87 | 1249.87 | 0
S370510 | Review of Safety System Design by CAD ESRC | 24 | 5242.73 | 2022-11-01 | 2022-11-03 | 0% | SCI4 PO | 24 |  |  | 5242.73 | 5242.73 | 0
S370510 | Review of Safety System Design by CAD ESRC | 24 | 4382.09 | 2022-11-01 | 2022-11-03 | 0% | SCI3 PO | 24 |  |  | 4382.09 | 4382.09 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249.34 | 2022-11-04 | 2022-12-06 | 0% | PROF4 PO M | 40 |  |  | 6249.34 | 6249.34 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249.34 | 2022-11-04 | 2022-12-06 | 0% | PROF4 PO E | 40 |  |  | 6249.34 | 6249.34 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 7303.48 | 2022-11-04 | 2022-12-06 | 0% | SCI3 PO | 40 |  |  | 7303.48 | 7303.48 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 8737.89 | 2022-11-04 | 2022-12-06 | 0% | SCI4 PO | 40 |  |  | 8737.89 | 8737.89 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3608.4 | 2022-11-04 | 2022-12-06 | 0% | PROF5 AD | 20 |  |  | 3608.4 | 3608.4 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 4094.92 | 2022-11-04 | 2022-12-06 | 0% | PROF6 AD | 20 |  |  | 4094.92 | 4094.92 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 2126.45 | 2022-11-04 | 2022-12-06 | 0% | PROF2 AD | 20 |  |  | 2126.45 | 2126.45 | 0
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3124.67 | 2022-11-04 | 2022-12-06 | 0% | PROF4 AD | 20 |  |  | 3124.67 | 3124.67 | 0
S370530 | Review and approve procedures | 16 | 2499.74 | 2022-12-07 | 2022-12-08 | 0% | PROF4 PO M | 16 |  |  | 2499.74 | 2499.74 | 0
S370530 | Review and approve procedures | 16 | 2499.74 | 2022-12-07 | 2022-12-08 | 0% | PROF4 PO E | 16 |  |  | 2499.74 | 2499.74 | 0
S370530 | Review and approve procedures | 16 | 2921.39 | 2022-12-07 | 2022-12-08 | 0% | SCI3 PO | 16 |  |  | 2921.39 | 2921.39 | 0
S370530 | Review and approve procedures | 16 | 3495.16 | 2022-12-07 | 2022-12-08 | 0% | SCI4 PO | 16 |  |  | 3495.16 | 3495.16 | 0
S370530 | Review and approve procedures | 16 | 2886.72 | 2022-12-07 | 2022-12-08 | 0% | PROF5 AD | 16 |  |  | 2886.72 | 2886.72 | 0
S370530 | Review and approve procedures | 16 | 3275.94 | 2022-12-07 | 2022-12-08 | 0% | PROF6 AD | 16 |  |  | 3275.94 | 3275.94 | 0
S370540 | Magnet Checkout After Power Testing | 16 | 2921.39 | 2022-12-09 | 2022-12-15 | 0% | SCI3 AD | 16 |  |  | 2921.39 | 2921.39 | 0
S370540 | Magnet Checkout After Power Testing | 16 | 3275.94 | 2022-12-09 | 2022-12-15 | 0% | PROF6 AD | 16 |  |  | 3275.94 | 3275.94 | 0
S370540 | Magnet Checkout After Power Testing | 16 | 2886.72 | 2022-12-09 | 2022-12-15 | 0% | PROF5 AD | 16 |  |  | 2886.72 | 2886.72 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 2905.73 | 2022-12-16 | 2022-12-22 | 0% | TECH3 PO E | 24 |  |  | 2905.73 | 2905.73 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 3749.6 | 2022-12-16 | 2022-12-22 | 0% | PROF4 PO E | 24 |  |  | 3749.6 | 3749.6 | 0
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 5242.73 | 2022-12-16 | 2022-12-22 | 0% | SCI4 PO | 24 |  |  | 5242.73 | 5242.73 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2921.39 | 2022-12-23 | 2023-01-09 | 0% | SCI3 AD | 16 |  |  | 2921.39 | 2921.39 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2886.72 | 2022-12-23 | 2023-01-09 | 0% | PROF5 AD | 16 |  |  | 2886.72 | 2886.72 | 0
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 3275.94 | 2022-12-23 | 2023-01-09 | 0% | PROF6 AD | 16 |  |  | 3275.94 | 3275.94 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2499.74 | 44936 | 44943 | 0% | PROF4 PO M | 16 |  |  | 2499.74 | 2499.74 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937.15 | 44936 | 44943 | 0% | TECH3 PO E | 16 |  |  | 1937.15 | 1937.15 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937.15 | 44936 | 44943 | 0% | TECH3 PO M | 16 |  |  | 1937.15 | 1937.15 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2499.74 | 44936 | 44943 | 0% | PROF4 PO E | 16 |  |  | 2499.74 | 2499.74 | 0
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 3495.16 | 44936 | 44943 | 0% | SCI4 PO | 16 |  |  | 3495.16 | 3495.16 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2499.74 | 44944 | 44950 | 0% | PROF4 PO M | 16 |  |  | 2499.74 | 2499.74 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937.15 | 44944 | 44950 | 0% | TECH3 PO E | 16 |  |  | 1937.15 | 1937.15 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937.15 | 44944 | 44950 | 0% | TECH3 PO M | 16 |  |  | 1937.15 | 1937.15 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2499.74 | 44944 | 44950 | 0% | PROF4 PO E | 16 |  |  | 2499.74 | 2499.74 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 3495.16 | 44944 | 44950 | 0% | SCI4 PO | 16 |  |  | 3495.16 | 3495.16 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2921.39 | 44944 | 44950 | 0% | SCI3 PO | 16 |  |  | 2921.39 | 2921.39 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1460.7 | 44944 | 44950 | 0% | SCI3 AD | 8 |  |  | 1460.7 | 1460.7 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1249.87 | 44944 | 44950 | 0% | PROF4 AD | 8 |  |  | 1249.87 | 1249.87 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1249.87 | 44944 | 44950 | 0% | PROF4 AD | 8 |  |  | 1249.87 | 1249.87 | 0
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1637.97 | 44944 | 44950 | 0% | PROF6 AD | 8 |  |  | 1637.97 | 1637.97 | 0
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 16 | 3495.16 | 44951 | 44957 | 0% | SCI4 PO | 16 |  |  | 3495.16 | 3495.16 | 0
S370595 | Prepare for sPHENIX IRR | 160 | 30090.32 | 44866 | 44957 | 0% | SCI3 | 160 |  |  | 30090.32 | 30090.32 | 0
S370595 | Prepare for sPHENIX IRR | 160 | 22118.46 | 44866 | 44957 | 0% | PROF3 PO M | 160 |  |  | 22118.46 | 22118.46 | 0
S370597 | Prepare for sPHENIX ARR | 160 | 22118.46 | 44866 | 44957 | 0% | PROF3 PO M | 160 |  |  | 22118.46 | 22118.46 | 0
S370597 | Prepare for sPHENIX ARR | 160 | 30090.32 | 44866 | 44957 | 0% | SCI3 | 160 |  |  | 30090.32 | 30090.32 | 0

## Data Dump (hidden)
Activity ID | Activity Name | Budgeted Units | Budgeted Cost | Start | Finish | Remaining Units | Resource ID | Spreadsheet Field | FY21 | FY22 | FY23
POM02-13.02.01.04 Infrastructure Management |  | 153 | 17904.51 | 2022-10-03 | 2022-10-07 | 153 |  | Labor Hr/M&S Direct$ |  |  | 153
S276500 | 2023 Infrastructure Project Management | 40 | 5529.62 | 2022-10-03 | 2022-10-07 | 40 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 40
S277100 | 2023 Facility Support Systems L3 Project Management | 113 | 12374.89 | 2022-10-03 | 2022-10-07 | 113 | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 113
POM02-13.02.01.05 Installation Management |  | 282 | 52404.77 | 2022-10-03 | 2022-10-05 | 282 |  | Labor Hr/M&S Direct$ |  |  | 282
S278300 | 2023 Integration & Installation Project Management | 282 | 52404.77 | 2022-10-03 | 2022-10-05 | 282 | PROF5 PO M | Labor Hr/M&S Direct$ |  |  | 282
POM02-13.02.02.01.01 Safety Reviews |  | 32 | 6383.25 | 16-Sep-22 A | 2022-10-07 | 16 |  | Labor Hr/M&S Direct$ |  |  | 32
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 3009.03 | 16-Sep-22 A | 2022-10-07 | 8 | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 16
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 3374.22 | 16-Sep-22 A | 2022-10-07 | 8 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 16
POM02-13.02.02.01.02 Cooldown & Power Tests |  | 724 | 118823.66 | 17-Aug-22 A | 2022-10-27 | 715 |  | Labor Hr/M&S Direct$ |  |  | 724
S279100 | Cooldown | 60 | 8294.42 | 17-Aug-22 A | 2022-10-17 | 57 | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 60
S279100 | Cooldown | 60 | 7482.26 | 17-Aug-22 A | 2022-10-17 | 57 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 60
S279100 | Cooldown | 60 | 12653.32 | 17-Aug-22 A | 2022-10-17 | 57 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 60
S279200 | 4.5K Static Heat Load test | 8 | 1073.71 | 2022-10-18 | 2022-10-19 | 8 | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 8
S279200 | 4.5K Static Heat Load test | 8 | 968.58 | 2022-10-18 | 2022-10-19 | 8 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 8
S279200 | 4.5K Static Heat Load test | 8 | 1637.97 | 2022-10-18 | 2022-10-19 | 8 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 8
S279300 | 4.5K Low power test | 20 | 2684.28 | 2022-10-20 | 2022-10-24 | 20 | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 20
S279300 | 4.5K Low power test | 80 | 14606.95 | 2022-10-20 | 2022-10-24 | 80 | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 80
S279300 | 4.5K Low power test | 80 | 9685.77 | 2022-10-20 | 2022-10-24 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S279300 | 4.5K Low power test | 80 | 16379.7 | 2022-10-20 | 2022-10-24 | 80 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 80
S279400 | 4.5K High Power Test | 20 | 2684.28 | 2022-10-25 | 2022-10-27 | 20 | PROF3 AD | Labor Hr/M&S Direct$ |  |  | 20
S279400 | 4.5K High Power Test | 80 | 14606.95 | 2022-10-25 | 2022-10-27 | 80 | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 80
S279400 | 4.5K High Power Test | 80 | 9685.77 | 2022-10-25 | 2022-10-27 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S279400 | 4.5K High Power Test | 80 | 16379.7 | 2022-10-25 | 2022-10-27 | 80 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 80
POM02-13.02.02.04.01.03 Install PS AC/DC Cabling |  | 420 | 54812.28 | 01-Jul-22 A | 2022-10-07 | 126 |  | Labor Hr/M&S Direct$ |  | 420
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 40 | 6249.34 | 01-Jul-22 A | 2022-10-07 | 12 | PROF4 AD | Labor Hr/M&S Direct$ |  | 40
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 160 | 19371.55 | 01-Jul-22 A | 2022-10-07 | 48 | TECH3 AD | Labor Hr/M&S Direct$ |  | 160
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 220 | 29191.39 | 01-Jul-22 A | 2022-10-07 | 66 | CRAFT3 | Labor Hr/M&S Direct$ |  | 220
POM02-13.02.02.04.02.01 Install Power Supply |  | 230 | 31179.97 | 10-Aug-22 A | 2022-10-19 | 115 |  | Labor Hr/M&S Direct$ |  | 96 | 134
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 70 | 8729.3 | 10-Aug-22 A | 2022-10-11 | 35 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 70
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 12648.66 | 23-Sep-22 A | 2022-10-19 | 40 | PROF4 AD | Labor Hr/M&S Direct$ |  | 48 | 32
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 9802 | 23-Sep-22 A | 2022-10-19 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  | 48 | 32
POM02-13.02.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication |  | 112 | 17097.9 | 01-Sep-22 A | 2023-01-17 | 98 |  | Labor Hr/M&S Direct$ |  |  | 112
S308617 | Calibrate probes | 24 | 5400.02 | 01-Sep-22 A | 2022-12-30 | 19 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 24
S308617 | Calibrate probes | 24 | 3862.09 | 01-Sep-22 A | 2022-12-30 | 19 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 24
S308617 | Calibrate probes | 24 | 2992.9 | 01-Sep-22 A | 2022-12-30 | 19 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 24
S308619 | Install probes and readout on TPC | 40 | 4842.89 | 2023-01-03 | 2023-01-17 | 40 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 40
POM02-13.02.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis |  | 1208 | 186391.94 | 08-Mar-21 A | 2022-12-22 | 1189 |  | Labor Hr/M&S Direct$ |  | 32 | 1176
S308633 | Construct mapping support (mechanical and electrical) | 32 | 3874.31 | 08-Mar-21 A | 2022-11-01 | 13 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 32
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 9976.35 | 2022-10-18 | 2022-10-31 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 19952.7 | 2022-10-18 | 2022-10-31 | 160 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 160
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 11059.23 | 2022-10-18 | 2022-10-31 | 80 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 36000.1 | 2022-10-18 | 2022-10-31 | 160 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 160
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9976.35 | 2022-11-01 | 2022-11-15 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 36000.1 | 2022-11-01 | 2022-11-15 | 160 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 160
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 11059.23 | 2022-11-01 | 2022-11-15 | 80 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 19952.7 | 2022-11-01 | 2022-11-15 | 160 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 160
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9976.35 | 2022-11-01 | 2022-11-15 | 80 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 40 | 4988.17 | 2022-11-16 | 2022-11-22 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 80 | 9976.35 | 2022-11-16 | 2022-11-22 | 80 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S309110 | Receive report from CERN, incorporate into analysis | 16 | 3600.01 | 2022-11-23 | 2022-12-22 | 16 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 16
POM02-13.02.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports |  | 60180 | 94315.98 | 31-Mar-22 A | 2022-11-14 | 12672 |  | Labor Hr/M&S Direct$ |  | 60000 | 180
S317940 | Procure TPC Supports - M&S | 50000 | 59194.9 | 31-Mar-22 A | 2022-10-28 | 7500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 50000
S317970 | Procure MBD Supports - M&S | 10000 | 11838.98 | 01-Jul-22 A | 2022-10-28 | 5000 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 10000
S318140 | Perform TPC Supports Acceptance | 40 | 4842.89 | 2022-10-31 | 2022-11-14 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S318140 | Perform TPC Supports Acceptance | 40 | 5368.56 | 2022-10-31 | 2022-11-14 | 40 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 40
S318170 | Perform MBD Supports Acceptance | 10 | 1210.72 | 2022-10-31 | 2022-11-14 | 10 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 10
S318170 | Perform MBD Supports Acceptance | 10 | 1342.14 | 2022-10-31 | 2022-11-14 | 10 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 10
S318190 | Perform Beampipe Supports Acceptance | 40 | 4988.17 | 26-Sep-22 A | 2022-10-17 | 36 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S318190 | Perform Beampipe Supports Acceptance | 40 | 5529.62 | 26-Sep-22 A | 2022-10-17 | 36 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 40
POM02-13.02.04.01.03 Detector Electronics Racks and Rack generic support systems |  | 780 | 96252.38 | 13-Sep-21 A | 2022-11-10 | 546 |  | Labor Hr/M&S Direct$ |  | 280 | 500
S331470 | Assemble Racks for Lower East Platform | 80 | 9685.77 | 15-Nov-21 A | 2022-10-31 | 6 | TECH3 PO E | Labor Hr/M&S Direct$ |  | 80
S331490 | Assemble Racks for Main Upper Platform | 200 | 24214.44 | 13-Sep-21 A | 2022-10-31 | 40 | TECH3 PO E | Labor Hr/M&S Direct$ |  | 200
S331496 | ADDED RACK ASSEMBLY EFFORT, BASED ON EFFORT TO DATE | 500 | 62352.17 | 2022-11-01 | 2022-11-10 | 500 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 500
POM02-13.02.04.01.04 Detector Gas and Cooling Services Systems |  | 56334 | 366297.65 | 15-Feb-21 A | 2023-02-09 | 34427 |  | Labor Hr/M&S Direct$ | 192 | 101 | 56041
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 96 | 14561.56 | 15-Feb-21 A | 2022-10-31 | 19 | PROF4 PO M | Labor Hr/M&S Direct$ | 96
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642.2 | 15-Feb-21 A | 2022-10-31 | 10 | TECH3 PO D | Labor Hr/M&S Direct$ | 48
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642.2 | 15-Feb-21 A | 2022-10-31 | 10 | TECH3 PO M | Labor Hr/M&S Direct$ | 48
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 32 | 5004.47 | 22-Jul-22 A | 2022-10-31 | 19 | PROF4 PO M | Labor Hr/M&S Direct$ |  | 31 | 1
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 72 | 8725.91 | 22-Jul-22 A | 2022-10-31 | 43 | TECH3 PO D | Labor Hr/M&S Direct$ |  | 70 | 2
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 3862.09 | 05-Sep-22 A | 2022-11-02 | 14 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 24
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 2992.9 | 05-Sep-22 A | 2022-11-02 | 14 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 24
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 15448.36 | 03-Sep-22 A | 2023-02-02 | 58 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 96
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 11971.62 | 03-Sep-22 A | 2023-02-02 | 58 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 96
S332770 | Procure & Deliver Detector Gas Services Systems Components - M&S | 54000 | 65209.09 | 03-Sep-22 A | 2023-02-02 | 32400 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 54000
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 2574.73 | 12-Sep-22 A | 2023-02-09 | 10 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 16
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 1995.27 | 12-Sep-22 A | 2023-02-09 | 10 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 16
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 8 | 997.63 | 12-Sep-22 A | 2023-02-09 | 5 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S332781 | Design, procure, test remaining cooling system items | 100 | 13824.04 | 2022-11-01 | 2022-11-02 | 100 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 100
S332781 | Design, procure, test remaining cooling system items | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S332782 | Cooling System Panel Fabrication - TPC | 8 | 1105.92 | 2022-11-03 | 2022-11-04 | 8 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 8
S332782 | Cooling System Panel Fabrication - TPC | 130 | 16211.57 | 2022-11-03 | 2022-11-04 | 130 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 130
S332783 | Cooling System Panel Fabrication - TPot | 4 | 552.96 | 2022-11-07 | 2022-11-08 | 4 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 4
S332783 | Cooling System Panel Fabrication - TPot | 60 | 7482.26 | 2022-11-07 | 2022-11-08 | 60 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 60
S332784 | Cooling System Panel Fabrication - EMCal SiPM | 290 | 36164.26 | 2022-11-09 | 2022-11-10 | 290 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 290
S332785 | Cooling System Panel Fabrication - EMCal PreAmp | 290 | 36164.26 | 2022-11-14 | 2022-11-15 | 290 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 290
S332786 | Cooling System Panel Fabrication - INTT ROC | 120 | 14964.52 | 2022-11-16 | 2022-11-17 | 120 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 120
S332787 | Cooling System Panel Fabrication - INTT Stave | 120 | 14964.52 | 2022-11-18 | 2022-11-21 | 120 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 120
S332788 | Cooling System Panel Fabrication - MVTX | 80 | 9976.35 | 2022-11-22 | 2022-11-23 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S332789 | Cooling System Platform Manifolding | 24 | 3862.09 | 2022-11-28 | 2022-11-29 | 24 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 24
S332789 | Cooling System Platform Manifolding | 100 | 12470.43 | 2022-11-28 | 2022-11-29 | 100 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 100
S332790 | Gas Distribution Panel Fabrication - TPC Ar-CF4 | 100 | 12470.43 | 2022-10-03 | 2022-10-04 | 100 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 100
S332791 | Gas Distribution Panel Fabrication - TPC Laser N2 | 40 | 4988.17 | 2022-10-05 | 2022-10-06 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 4 | 552.96 | 2022-10-07 | 2022-10-11 | 4 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 4
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 80 | 9976.35 | 2022-10-07 | 2022-10-11 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S332793 | Gas Distribution Panel Fabrication - EMCal SiPM N2 | 40 | 4988.17 | 2022-10-12 | 2022-10-13 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S332794 | Gas Distribution Panel Fabrication - INTT Stave N2 | 40 | 4988.17 | 2022-10-14 | 2022-10-17 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S332795 | Gas Distribution Panel Fabrication - MVTX N2 | 8 | 997.63 | 2022-10-18 | 2022-10-19 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S332796 | Gas Distribution Panel Fabrication - MBD dry compressed air | 40 | 4988.17 | 2022-10-20 | 2022-10-21 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
POM02-13.02.04.01.05 Detector Safety Subsystems |  | 120 | 14964.52 | 2022-11-01 | 2022-12-01 | 120 |  | Labor Hr/M&S Direct$ |  |  | 120
S333720 | Fabricate Detector Safety Systems | 60 | 7482.26 | 2022-11-01 | 2022-12-01 | 60 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 60
S333720 | Fabricate Detector Safety Systems | 60 | 7482.26 | 2022-11-01 | 2022-12-01 | 60 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 60
POM02-13.02.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR |  | 113 | 20999.07 | 2022-10-03 | 2022-10-04 | 113 |  | Labor Hr/M&S Direct$ |  |  | 113
S277700 | 2023 Detector Support Systems L3 Project Management | 113 | 20999.07 | 2022-10-03 | 2022-10-04 | 113 | PROF5 PO M | Labor Hr/M&S Direct$ |  |  | 113
POM02-13.02.04.02.05 IR/AH Safety Subsystems |  | 32450 | 96653.71 | 04-Jul-22 A | 2023-01-06 | 24349 |  | Labor Hr/M&S Direct$ |  |  | 32450
S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - M&S | 32000 | 38642.42 | 04-Jul-22 A | 2022-12-21 | 24000 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 32000
S342390 | Design IR/AH Safety Systems | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S342390 | Design IR/AH Safety Systems | 80 | 11059.23 | 2022-11-01 | 2022-12-30 | 80 | PROF3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 24 | 3424.91 | 03-Sep-22 A | 2022-10-17 | 12 | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 24
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 48 | 5256.59 | 03-Sep-22 A | 2022-10-17 | 24 | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 48
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 4 | 643.68 | 03-Sep-22 A | 2022-10-17 | 2 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 4
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 48 | 6849.81 | 18-Sep-22 A | 2022-11-15 | 36 | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 48
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 96 | 10513.18 | 18-Sep-22 A | 2022-11-15 | 72 | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 96
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 2 | 321.84 | 18-Sep-22 A | 2022-11-15 | 2 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 2
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 88 | 12557.99 | 22-Sep-22 A | 2023-01-06 | 66 | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 88
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 16 | 1752.2 | 22-Sep-22 A | 2023-01-06 | 12 | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 16
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 4 | 643.68 | 22-Sep-22 A | 2023-01-06 | 3 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 4
POM02-13.02.05.02 Infrastructure Installation |  | 11368 | 731894.27 | 09-Sep-21 A | 2023-03-10 | 8716 |  | Labor Hr/M&S Direct$ |  | 3634 | 7734
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 160 | 21230.1 | 09-Sep-21 A | 2022-10-28 | 16 | CRAFT3 | Labor Hr/M&S Direct$ |  | 160
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 40 | 6249.34 | 09-Sep-21 A | 2022-10-28 | 4 | PROF4 PO E | Labor Hr/M&S Direct$ |  | 40
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 4 | 818.98 | 09-Sep-21 A | 2022-10-28 | 0 | PROF6 AD | Labor Hr/M&S Direct$ |  | 4
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 80 | 10933.5 | 30-Aug-22 A | 2022-10-31 | 40 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 80
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 40 | 6436.82 | 30-Aug-22 A | 2022-10-31 | 20 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 40
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4842.89 | 03-Jan-22 A | 2022-10-28 | 2 | TECH3 AD | Labor Hr/M&S Direct$ |  | 40
S345500 | Install IR HVAC - Labor - C-AD Resources | 64 | 8492.04 | 03-Jan-22 A | 2022-10-28 | 3 | CRAFT3 | Labor Hr/M&S Direct$ |  | 64
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4252.91 | 03-Jan-22 A | 2022-10-28 | 2 | PROF2 AD | Labor Hr/M&S Direct$ |  | 40
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 6249.34 | 03-Jan-22 A | 2022-10-28 | 2 | PROF4 AD | Labor Hr/M&S Direct$ |  | 40
S345600 | Install IR HVAC - M&S | 250 | 295.97 | 03-Jan-22 A | 2022-10-28 | 13 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 250
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 80 | 9976.35 | 01-Apr-22 A | 2023-02-06 | 60 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 16 | 2574.73 | 01-Apr-22 A | 2023-02-06 | 12 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 16
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 24 | 3280.05 | 01-Apr-22 A | 2023-02-06 | 18 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 24
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 40 | 4380.49 | 01-Apr-22 A | 2023-02-06 | 30 | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 40
S345800 | Install On Detector Safety Subsystems - Labor | 80 | 9976.35 | 14-Sep-22 A | 2022-12-15 | 72 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S345800 | Install On Detector Safety Subsystems - Labor | 40 | 4988.17 | 14-Sep-22 A | 2022-12-15 | 36 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3218.41 | 14-Sep-22 A | 2022-12-15 | 18 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 20
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3218.41 | 14-Sep-22 A | 2022-12-15 | 18 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 20
S345900 | Install On Detector Safety Subsystems - M&S | 500 | 603.79 | 14-Sep-22 A | 2022-12-15 | 450 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S345910 | Install Off Detector Safety Subsystems inc Vesda - M&S | 500 | 603.79 | 01-Apr-22 A | 2023-02-06 | 375 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S345920 | Install Rack Protection systems - Lower platform | 40 | 4988.17 | 2022-11-01 | 2022-12-01 | 40 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 40
S345930 | Install Rack Protection systems - Middle platform | 40 | 4988.17 | 2022-12-02 | 2022-12-30 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S345940 | Install Rack Protection systems - Upper platform | 160 | 19952.7 | 2023-01-03 | 2023-01-31 | 160 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 160
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 32 | 4999.47 | 09-Sep-21 A | 2022-10-28 | 3 | PROF4 AD | Labor Hr/M&S Direct$ |  | 32
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 32 | 4999.47 | 30-Aug-22 A | 2022-10-31 | 16 | PROF4 AD | Labor Hr/M&S Direct$ |  | 32
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 4 | 818.98 | 30-Aug-22 A | 2022-10-31 | 2 | PROF6 AD | Labor Hr/M&S Direct$ |  | 4
S346200 | Install Line Electric Power Distribution Off Detector - M&S | 500 | 591.95 | 09-Sep-21 A | 2022-10-28 | 50 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 500
S346210 | Install Line Electric Power Distribution On Detector - M&S | 500 | 597.46 | 30-Aug-22 A | 2022-10-31 | 250 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 267 | 233
S346220 | Install AC power to Racks - Lower platforms | 120 | 14964.52 | 2022-11-01 | 2022-12-01 | 120 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 120
S346230 | Install AC power to Racks - Middle platforms | 120 | 14964.52 | 2022-12-02 | 2022-12-30 | 120 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 120
S346240 | Install AC power to Racks - Upper platforms | 480 | 59858.09 | 2023-01-03 | 2023-01-31 | 480 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 480
S346298 | Build North and South work platforms | 30 | 3741.13 | 17-Aug-22 A | 2023-01-27 | 21 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 30
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 20 | 3218.41 | 2023-01-30 | 2023-02-03 | 20 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 20
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 40 | 4988.17 | 2023-01-30 | 2023-02-03 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 16 | 1995.27 | 2023-01-30 | 2023-02-03 | 16 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 16
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 104 | 12969.25 | 2023-01-30 | 2023-02-03 | 104 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 104
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 80 | 8760.98 | 2023-01-30 | 2023-02-03 | 80 | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 80
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 40 | 6436.82 | 2023-01-30 | 2023-02-03 | 40 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 40
S346400 | Install Beampipe Temp Support M&S | 500 | 603.79 | 2023-01-30 | 2023-02-03 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S346402 | Beampipe bakeout | 500 | 603.79 | 2023-02-06 | 2023-02-17 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S346404 | Install permanent Beampipe support | 500 | 603.79 | 2023-03-10 | 2023-03-10 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 9793.39 | 01-Apr-22 A | 2022-10-17 | 40 | TECH3 PO E | Labor Hr/M&S Direct$ |  | 50 | 30
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 9793.39 | 01-Apr-22 A | 2022-10-17 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 50 | 30
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 12637.55 | 01-Apr-22 A | 2022-10-17 | 40 | PROF4 PO E | Labor Hr/M&S Direct$ |  | 50 | 30
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 160 | 19586.79 | 01-Apr-22 A | 2022-10-17 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  | 101 | 59
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 80 | 10733 | 01-Apr-22 A | 2022-10-17 | 40 | CRAFT3 | Labor Hr/M&S Direct$ |  | 50 | 30
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 20 | 2150.08 | 01-Apr-22 A | 2022-10-17 | 10 | PROF2 AD | Labor Hr/M&S Direct$ |  | 13 | 7
S346800 | Install Non-IR Infrastructure - M&S | 500 | 600.95 | 01-Apr-22 A | 2022-12-21 | 250 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 120 | 380
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18860.5 | 01-Apr-22 A | 2022-11-30 | 114 | PROF4 PO M | Labor Hr/M&S Direct$ |  | 96 | 24
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 34103.61 | 01-Apr-22 A | 2022-11-30 | 114 | TECH3 PO E | Labor Hr/M&S Direct$ |  | 224 | 56
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 34103.61 | 01-Apr-22 A | 2022-11-30 | 114 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 224 | 56
S347200 | Install Electronics Racks On Carriage - Labor | 48 | 5846.33 | 01-Apr-22 A | 2022-11-30 | 114 | TECH3 PO D | Labor Hr/M&S Direct$ |  | 38 | 10
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18860.5 | 01-Apr-22 A | 2022-11-30 | 114 | PROF4 PO E | Labor Hr/M&S Direct$ |  | 96 | 24
S347310 | Install Electronics Racks On Carriage - M&S | 500 | 594.32 | 01-Apr-22 A | 2022-11-30 | 335 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 400 | 100
S347400 | Install Gas and Cooling System Services - Labor | 120 | 19310.45 | 2022-10-03 | 2022-12-01 | 120 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 120
S347400 | Install Gas and Cooling System Services - Labor | 720 | 89787.13 | 2022-10-03 | 2022-12-01 | 720 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 720
S347400 | Install Gas and Cooling System Services - Labor | 96 | 11971.62 | 2022-10-03 | 2022-12-01 | 96 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 96
S347500 | Install Gas and Cooling System Services - M&S | 500 | 603.79 | 2022-10-03 | 2022-12-01 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S347610 | Off Carriage Water Lines & Flow Control - Sill & Labyrinth area | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S347620 | Off Carriage Water Lines & Flow Control - Chiller Platforms | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S347630 | Off Carriage Water - ECW to 'brass block' | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 40
S347640 | Off Carriage Water - Brass block to chillers | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S347650 | Off Carriage Water - Chiller panels to cooling lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S347660 | Off Carriage Water - Bridge lines | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 40
S347670 | Off Carriage Water - Bridges to on-carriage panels | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S347680 | Off Carriage Water - Carriage ECW to on-carriage panels | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 80 | 9685.77 | 01-Aug-22 A | 2023-01-18 | 72 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 80
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 16 | 1937.15 | 01-Aug-22 A | 2023-01-18 | 14 | TECH3 PO D | Labor Hr/M&S Direct$ |  | 16
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 32 | 4246.02 | 01-Aug-22 A | 2023-01-18 | 29 | CRAFT3 | Labor Hr/M&S Direct$ |  | 32
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 20 | 3124.67 | 01-Aug-22 A | 2023-01-18 | 18 | PROF4 PO E | Labor Hr/M&S Direct$ |  | 20
S347810 | Install IR Electronics Cooling Water On Detector - M&S | 500 | 591.95 | 01-Aug-22 A | 2023-01-18 | 450 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 500
S347820 | Install Rack Cooling water - Lower platforms | 80 | 9976.35 | 2022-11-01 | 2022-12-01 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S347830 | Install Rack Cooling water - Middle platforms | 80 | 9976.35 | 2022-12-02 | 2022-12-30 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S347840 | Install Rack Cooling water - Upper platforms | 320 | 39905.39 | 2023-01-03 | 2023-01-31 | 320 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 320
POM02-13.02.05.04 Outer Hcal Installation |  | 980 | 69703.86 | 01-Mar-22 A | 2022-12-06 | 242 |  | Labor Hr/M&S Direct$ |  | 820 | 160
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 9685.77 | 01-Mar-22 A | 2022-10-28 | 11 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 80
S351600 | Install Outer HCal Cables and Services - Labor | 160 | 19371.55 | 01-Mar-22 A | 2022-10-28 | 11 | TECH3 PO E | Labor Hr/M&S Direct$ |  | 160
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 12498.68 | 01-Mar-22 A | 2022-10-28 | 11 | PROF4 PO E | Labor Hr/M&S Direct$ |  | 80
S351700 | Install Outer HCal Cables and Services - M&S | 500 | 591.95 | 01-Mar-22 A | 2022-10-28 | 50 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 500
S351710 | Check OHCal operation during cabling | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S351720 | Install OHCal gas distribution panels and route lines | 40 | 4988.17 | 2022-11-21 | 2022-11-29 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S351740 | Check OHCal operation with DAQ in counting house | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
POM02-13.02.05.06 Inner Hcal Installation |  | 980 | 69703.86 | 2022-10-03 | 2022-12-06 | 980 |  | Labor Hr/M&S Direct$ |  |  | 980
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 9685.77 | 2022-10-03 | 2022-10-31 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 160 | 19371.55 | 2022-10-03 | 2022-10-31 | 160 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 160
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 12498.68 | 2022-10-03 | 2022-10-31 | 80 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 80
S356700 | Install Inner HCal Cables and Services (if instrumented) - M&S | 500 | 591.95 | 2022-11-01 | 2022-12-01 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S356710 | Check IHCal operation during cabling | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S356720 | Install IHCal gas distribution panels and route lines | 40 | 4988.17 | 2022-11-21 | 2022-11-29 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S356740 | Check IHCal operation with DAQ in counting house | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
POM02-13.02.05.07 EMCal Installation |  | 5764 | 469131.25 | 01-Jul-22 A | 2023-02-10 | 3896 |  | Labor Hr/M&S Direct$ |  | 1832 | 3932
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 120 | 15922.58 | 01-Jul-22 A | 2022-12-09 | 53 | CRAFT3 | Labor Hr/M&S Direct$ |  | 120
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 64 | 7748.62 | 01-Jul-22 A | 2022-12-09 | 28 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 64
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 80 | 9976.35 | 2022-11-01 | 2022-11-07 | 80 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 8 | 1249.87 | 01-Jul-22 A | 2022-12-09 | 4 | PROF4 AD | Labor Hr/M&S Direct$ |  | 8
S358300 | Transport Assembled EMCal Sectors to AH - M&S | 500 | 591.95 | 01-Jul-22 A | 2022-12-09 | 220 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 500
S358400 | Install EMCal Sectors - Labor | 64 | 9998.94 | 01-Aug-22 A | 2022-12-09 | 32 | PROF4 PO M | Labor Hr/M&S Direct$ |  | 64
S358400 | Install EMCal Sectors - Labor | 64 | 7748.62 | 01-Aug-22 A | 2022-12-09 | 32 | TECH3 PO D | Labor Hr/M&S Direct$ |  | 64
S358400 | Install EMCal Sectors - Labor | 512 | 61988.96 | 01-Aug-22 A | 2022-12-09 | 256 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 512
S358500 | Install EMCal Sectors - M&S | 500 | 591.95 | 01-Aug-22 A | 2022-12-09 | 250 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 500
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 17-Aug-22 A | 2022-12-12 | 10 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10933.5 | 17-Aug-22 A | 2022-12-12 | 40 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 80
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 17-Aug-22 A | 2022-12-12 | 30 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 60
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8562.26 | 17-Aug-22 A | 2022-12-12 | 30 | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 60
S358700 | Align/Survey EMCal to SC Magnet Centerline - M&S | 500 | 603.79 | 17-Aug-22 A | 2022-12-12 | 250 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S358800 | Install EMCal Cables and Services - Labor | 160 | 19698.44 | 2022-12-13 | 2023-01-05 | 160 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 160
S358800 | Install EMCal Cables and Services - Labor | 64 | 7879.38 | 2022-12-13 | 2023-01-05 | 64 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 64
S358800 | Install EMCal Cables and Services - Labor | 32 | 5083.84 | 2022-12-13 | 2023-01-05 | 32 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 32
S358800 | Install EMCal Cables and Services - Labor | 32 | 3939.69 | 2022-12-13 | 2023-01-05 | 32 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 32
S358800 | Install EMCal Cables and Services - Labor | 320 | 43176.72 | 2022-12-13 | 2023-01-05 | 320 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 320
S358900 | Install EMCal Cables and Services - M&S | 500 | 598.61 | 2022-12-13 | 2023-01-05 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S359200 | Commission EMCal - Labor | 400 | 75225.81 | 01-Aug-22 A | 2023-02-10 | 200 | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 400
S359200 | Commission EMCal - Labor | 40 | 6436.82 | 01-Aug-22 A | 2023-02-10 | 20 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 40
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | 20 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 40
S359200 | Commission EMCal - Labor | 40 | 6436.82 | 01-Aug-22 A | 2023-02-10 | 20 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 40
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | 20 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 40
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S359400 | Commission EMCal - M&S | 500 | 603.79 | 01-Aug-22 A | 2023-02-10 | 250 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S359402 | Install EMCal cooling panels and route lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S359404 | Install EMCal gas distribution panels and route lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 160 | 30090.32 | 2022-12-13 | 2022-12-27 | 160 | SCI3 | Labor Hr/M&S Direct$ |  |  | 160
S359408 | Check EMCal operation with DAQ in counting house | 160 | 30090.32 | 2022-12-13 | 2022-12-27 | 160 | SCI3 | Labor Hr/M&S Direct$ |  |  | 160
S359510 | Transport TPot from Stony Brook to 1008 AH | 8 | 997.63 | 2022-12-01 | 2022-12-01 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S359520 | Install TPot Installation fixtures and test | 16 | 2211.85 | 2022-10-03 | 2022-10-04 | 16 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 16
S359520 | Install TPot Installation fixtures and test | 20 | 2494.09 | 2022-10-03 | 2022-10-04 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S359530 | Install TPot support system | 4 | 552.96 | 2022-12-02 | 2022-12-02 | 4 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 4
S359530 | Install TPot support system | 20 | 2494.09 | 2022-12-02 | 2022-12-02 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S359540 | Install TPot | 4 | 552.96 | 2022-10-05 | 2022-10-06 | 4 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 4
S359540 | Install TPot | 80 | 9976.35 | 2022-10-05 | 2022-10-06 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S359550 | Align TPot | 20 | 2494.09 | 2022-12-05 | 2022-12-05 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S359550 | Align TPot | 20 | 2494.09 | 2022-12-05 | 2022-12-05 | 20 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 20
S359560 | Install TPot cables - LV, bias, signal, control | 24 | 3317.77 | 2022-10-07 | 2022-10-11 | 24 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 24
S359560 | Install TPot cables - LV, bias, signal, control | 80 | 9976.35 | 2022-10-07 | 2022-10-11 | 80 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S359560 | Install TPot cables - LV, bias, signal, control | 20 | 2494.09 | 2022-10-07 | 2022-10-11 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S359570 | Check TPot operation during cabling | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | 16 | SCI3 | Labor Hr/M&S Direct$ |  |  | 16
S359580 | Install TPot cooling panels and route lines | 40 | 4988.17 | 2022-10-03 | 2022-10-04 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S359590 | Install TPot gas distribution panels and route lines | 40 | 4988.17 | 2022-10-03 | 2022-10-04 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | 16 | SCI3 | Labor Hr/M&S Direct$ |  |  | 16
S359597 | Check TPot operation with DAQ in counting house | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | 16 | SCI3 | Labor Hr/M&S Direct$ |  |  | 16
POM02-13.02.05.08 TPC Installation |  | 34644 | 348738.55 | 03-Jan-22 A | 2023-03-06 | 7550 |  | Labor Hr/M&S Direct$ |  | 30104 | 4540
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 4 | 643.68 | 2022-12-29 | 2023-01-05 | 4 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 4
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 16 | 1995.27 | 2022-12-29 | 2023-01-05 | 16 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 16
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 60 | 7482.26 | 2022-12-29 | 2023-01-05 | 60 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 60
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 36 | 4920.08 | 2022-12-29 | 2023-01-05 | 36 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 36
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 60 | 9374.01 | 03-Jan-22 A | 2022-10-20 | 6 | PROF4 PO M | Labor Hr/M&S Direct$ |  | 60
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 20 | 2421.44 | 03-Jan-22 A | 2022-10-20 | 2 | TECH3 PO D | Labor Hr/M&S Direct$ |  | 20
S359800 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - M&S | 30000 | 35516.94 | 03-Jan-22 A | 2022-10-20 | 3000 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 30000
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 25-Jan-22 A | 2022-11-02 | 1 | PROF4 PO M | Labor Hr/M&S Direct$ |  | 8
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 25-Jan-22 A | 2022-11-02 | 1 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 8
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 25-Jan-22 A | 2022-11-02 | 1 | TECH3 PO D | Labor Hr/M&S Direct$ |  | 8
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1287.36 | 2022-11-03 | 2022-11-17 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 997.63 | 2022-11-03 | 2022-11-17 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 997.63 | 2022-11-03 | 2022-11-17 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 1249.87 | 2022-12-13 | 2022-12-19 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 24 | 2905.73 | 2022-12-13 | 2022-12-19 | 24 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 24
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 968.58 | 2022-12-13 | 2022-12-19 | 8 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 8
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 8 | 1249.87 | 2022-12-13 | 2022-12-19 | 8 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 8
S360500 | Transport Assembled TPC Sections to AH - M&S | 500 | 591.95 | 2022-12-13 | 2022-12-19 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S360600 | Open SC Magnet Pole Tip Doors | 4 | 643.68 | 2022-12-20 | 2022-12-20 | 4 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 4
S360600 | Open SC Magnet Pole Tip Doors | 16 | 1995.27 | 2022-12-20 | 2022-12-20 | 16 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 16
S360620 | Install TPC Installation fixtures and test | 40 | 6436.82 | 2022-12-21 | 2022-12-21 | 40 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 40
S360620 | Install TPC Installation fixtures and test | 40 | 4988.17 | 2022-12-21 | 2022-12-21 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S360700 | Install TPC Support - Labor | 4 | 643.68 | 2022-12-21 | 2022-12-28 | 4 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 4
S360700 | Install TPC Support - Labor | 16 | 1995.27 | 2022-12-21 | 2022-12-28 | 16 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 16
S360700 | Install TPC Support - Labor | 80 | 9976.35 | 2022-12-21 | 2022-12-28 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S360800 | Install TPC Support - M&S | 500 | 603.79 | 2022-12-21 | 2022-12-28 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 8 | 876.1 | 2022-12-29 | 2023-01-12 | 8 | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 8
S361000 | Install TPC (Mechanical) - M&S | 500 | 603.79 | 2022-12-29 | 2023-01-12 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-01-13 | 2023-01-20 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10933.5 | 2023-01-13 | 2023-01-20 | 80 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 80
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 2023-01-13 | 2023-01-20 | 60 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 60
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8562.26 | 2023-01-13 | 2023-01-20 | 60 | TECH4 AD | Labor Hr/M&S Direct$ |  |  | 60
S361111 | Install North and South Line Lasers | 16 | 3009.03 | 2023-01-23 | 2023-01-26 | 16 | SCI3 | Labor Hr/M&S Direct$ |  |  | 16
S361111 | Install North and South Line Lasers | 40 | 4988.17 | 2023-01-23 | 2023-01-26 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S361111 | Install North and South Line Lasers | 40 | 4988.17 | 2023-01-23 | 2023-01-26 | 40 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 40
S361200 | Align/Survey TPC to SC Magnet Centerline - M&S | 500 | 603.79 | 2023-01-13 | 2023-01-20 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S361300 | Install TPC Cables and Services - Labor | 120 | 14964.52 | 2023-02-06 | 2023-02-27 | 120 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 120
S361300 | Install TPC Cables and Services - Labor | 60 | 7482.26 | 2023-02-06 | 2023-02-27 | 60 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 60
S361300 | Install TPC Cables and Services - Labor | 24 | 3862.09 | 2023-02-06 | 2023-02-27 | 24 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 24
S361300 | Install TPC Cables and Services - Labor | 24 | 2992.9 | 2023-02-06 | 2023-02-27 | 24 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 24
S361300 | Install TPC Cables and Services - Labor | 240 | 32800.51 | 2023-02-06 | 2023-02-27 | 240 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 240
S361400 | Install TPC Cables and Services - M&S | 500 | 603.79 | 2023-02-06 | 2023-02-27 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S361420 | Check TPC operation during cabling | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | 160 | SCI3 | Labor Hr/M&S Direct$ |  |  | 160
S361440 | Install TPC cooling panels and route lines | 80 | 9976.35 | 2022-12-21 | 2022-12-22 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S361460 | Install TPC gas distribution panels and route lines | 80 | 9976.35 | 2022-12-21 | 2022-12-22 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S361465 | Install TPC Diffuse Lasers | 12 | 2256.77 | 2023-02-28 | 2023-03-01 | 12 | SCI3 | Labor Hr/M&S Direct$ |  |  | 12
S361465 | Install TPC Diffuse Lasers | 24 | 2992.9 | 2023-02-28 | 2023-03-01 | 24 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 24
S361465 | Install TPC Diffuse Lasers | 24 | 2992.9 | 2023-02-28 | 2023-03-01 | 24 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 24
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | 160 | SCI3 | Labor Hr/M&S Direct$ |  |  | 160
S361480 | Check TPC operation with DAQ in counting house | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | 160 | SCI3 | Labor Hr/M&S Direct$ |  |  | 160
S361950 | Erect 1008 IR Shield Wall | 80 | 9976.35 | 2023-02-28 | 2023-03-06 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S361950 | Erect 1008 IR Shield Wall | 80 | 9976.35 | 2023-02-28 | 2023-03-06 | 80 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 80
POM02-13.02.05.09 INTT Installation |  | 4032 | 208995.72 | 2022-10-03 | 2023-03-09 | 4032 |  | Labor Hr/M&S Direct$ |  |  | 4032
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 40 | 6249.34 | 2022-10-03 | 2022-10-17 | 40 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 40
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 20 | 2421.44 | 2022-10-03 | 2022-10-17 | 20 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 20
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-10-18 | 2022-10-31 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-18 | 2022-10-31 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-18 | 2022-10-31 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 1249.87 | 2022-11-01 | 2022-11-15 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 968.58 | 2022-11-01 | 2022-11-15 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 968.58 | 2022-11-01 | 2022-11-15 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 1287.36 | 2023-02-06 | 2023-02-07 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S362800 | Transport Assembled INTT Sections to AH - Labor | 24 | 2992.9 | 2023-02-06 | 2023-02-07 | 24 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 24
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 997.63 | 2023-02-06 | 2023-02-07 | 8 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 8
S362900 | Transport Assembled INTT Sections to AH - M&S | 500 | 603.79 | 2023-02-06 | 2023-02-07 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S362920 | Install INTT Installation fixtures and test | 20 | 2764.81 | 2023-02-06 | 2023-02-07 | 20 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S362920 | Install INTT Installation fixtures and test | 20 | 2494.09 | 2023-02-06 | 2023-02-07 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S363000 | Install INTT Support - Labor | 8 | 1287.36 | 2023-02-08 | 2023-02-17 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S363000 | Install INTT Support - Labor | 8 | 997.63 | 2023-02-08 | 2023-02-17 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S363000 | Install INTT Support - Labor | 60 | 7482.26 | 2023-02-08 | 2023-02-17 | 60 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 60
S363100 | Install INTT Support - M&S | 500 | 603.79 | 2023-02-08 | 2023-02-17 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S363120 | Install Beampipe | 40 | 4988.17 | 2023-02-21 | 2023-02-21 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 40
S363140 | Install Beampipe vacuum system | 40 | 4988.17 | 2023-02-22 | 2023-02-22 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 40
S363160 | Pump down beampipe | 40 | 4988.17 | 2023-02-23 | 2023-02-23 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 40
S363180 | Perform Beampipe Bakeout | 80 | 9976.35 | 2023-02-24 | 2023-03-02 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S363200 | Install INTT (mechanical) - Labor | 8 | 1287.36 | 2023-02-21 | 2023-03-02 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S363200 | Install INTT (mechanical) - Labor | 8 | 997.63 | 2023-02-21 | 2023-03-02 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S363200 | Install INTT (mechanical) - Labor | 60 | 7482.26 | 2023-02-21 | 2023-03-02 | 60 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 60
S363300 | Install INTT (mechanical) - M&S | 500 | 603.79 | 2023-02-21 | 2023-03-02 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-02-21 | 2023-03-02 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 9976.35 | 2023-02-21 | 2023-03-02 | 80 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 80
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 2023-02-21 | 2023-03-02 | 60 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 60
S363500 | Align/Survey INTT to SC Magnet Centerline - M&S | 500 | 603.79 | 2023-02-21 | 2023-03-02 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S363520 | Install beampipe permanent support | 40 | 4988.17 | 2023-03-03 | 2023-03-03 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 40
S363540 | Remove beampipe Temporary Support | 40 | 4988.17 | 2023-03-06 | 2023-03-06 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 40
S363600 | Install INTT Cables and Services - Labor | 120 | 14964.52 | 2023-03-03 | 2023-03-09 | 120 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 120
S363600 | Install INTT Cables and Services - Labor | 120 | 14964.52 | 2023-03-03 | 2023-03-09 | 120 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 120
S363600 | Install INTT Cables and Services - Labor | 24 | 3862.09 | 2023-03-03 | 2023-03-09 | 24 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 24
S363600 | Install INTT Cables and Services - Labor | 24 | 3862.09 | 2023-03-03 | 2023-03-09 | 24 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 24
S363600 | Install INTT Cables and Services - Labor | 24 | 2992.9 | 2023-03-03 | 2023-03-09 | 24 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 24
S363600 | Install INTT Cables and Services - Labor | 240 | 32800.51 | 2023-03-03 | 2023-03-09 | 240 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 240
S363700 | Install INTT Cables and Services - M&S | 500 | 603.79 | 2023-03-03 | 2023-03-09 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S363720 | Check INTT operation during cabling | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S363740 | Install INTT cooling panels and route lines | 40 | 4988.17 | 2023-03-07 | 2023-03-07 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S363760 | Install INTT gas distribution panels and route lines | 40 | 4988.17 | 2023-03-07 | 2023-03-07 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S363780 | Check INTT operation with DAQ in counting house | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
POM02-13.02.05.10 MVTX Installation |  | 2922 | 195130.32 | 29-Apr-21 A | 2023-03-22 | 2882 |  | Labor Hr/M&S Direct$ | 50 | 24 | 2848
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 29-Apr-21 A | 2022-10-28 | 10 | PROF4 PO M | Labor Hr/M&S Direct$ | 40
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 10 | 1175.46 | 29-Apr-21 A | 2022-10-28 | 3 | TECH3 PO D | Labor Hr/M&S Direct$ | 10
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 26-Jul-22 A | 2022-11-14 | 7 | PROF4 PO M | Labor Hr/M&S Direct$ |  | 8
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 26-Jul-22 A | 2022-11-14 | 7 | TECH3 PO D | Labor Hr/M&S Direct$ |  | 8
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 26-Jul-22 A | 2022-11-14 | 7 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 8
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-11-15 | 2022-11-30 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 1249.87 | 2022-12-09 | 2022-12-15 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S365300 | Transport Assembled MVTX Sections to IR - Labor | 24 | 2905.73 | 2022-12-09 | 2022-12-15 | 24 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 24
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 968.58 | 2022-12-09 | 2022-12-15 | 8 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 8
S365400 | Transport Assembled MVTX Sections to IR - M&S | 500 | 591.95 | 2022-12-09 | 2022-12-15 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S365450 | Install MVTX Installation fixtures and test | 40 | 4988.17 | 2022-12-09 | 2022-12-09 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S365500 | Install MVTX Support - Labor | 8 | 1287.36 | 2023-03-09 | 2023-03-09 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S365500 | Install MVTX Support - Labor | 8 | 997.63 | 2023-03-09 | 2023-03-09 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S365500 | Install MVTX Support - Labor | 60 | 7482.26 | 2023-03-09 | 2023-03-09 | 60 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 60
S365600 | Install MVTX Support - M&S | 500 | 603.79 | 2023-03-09 | 2023-03-09 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S365700 | Install FELIX | 16 | 2211.85 | 2023-03-10 | 2023-03-13 | 16 | PROF3 IO E | Labor Hr/M&S Direct$ |  |  | 16
S365900 | Install Optical fibers | 40 | 4988.17 | 2023-03-10 | 2023-03-13 | 40 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 40
S366000 | Install RU | 40 | 5529.62 | 2023-03-10 | 2023-03-13 | 40 | PROF3 IO E | Labor Hr/M&S Direct$ |  |  | 40
S366200 | Install Samtec Cables | 40 | 4988.17 | 2023-03-10 | 2023-03-10 | 40 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 40
S366300 | Install Half-Barrel 1 | 80 | 11059.23 | 2023-03-13 | 2023-03-14 | 80 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S366300 | Install Half-Barrel 1 | 80 | 9976.35 | 2023-03-13 | 2023-03-14 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S366500 | Install Half-Barrel 2 | 80 | 9976.35 | 2023-03-15 | 2023-03-16 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S366500 | Install Half-Barrel 2 | 80 | 11059.23 | 2023-03-15 | 2023-03-16 | 80 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 40 | 4988.17 | 2023-03-17 | 2023-03-20 | 40 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 40
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9976.35 | 2023-03-20 | 2023-03-21 | 80 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 80
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3862.09 | 2023-03-20 | 2023-03-21 | 24 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 24
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9976.35 | 2023-03-20 | 2023-03-21 | 80 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 80
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 2992.9 | 2023-03-20 | 2023-03-21 | 24 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 24
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3862.09 | 2023-03-20 | 2023-03-21 | 24 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 24
S366900 | Install MVTX Remaining Cables and Services - Labor | 160 | 21867.01 | 2023-03-20 | 2023-03-21 | 160 | CRAFT3 | Labor Hr/M&S Direct$ |  |  | 160
S367000 | Install MVTX Remaining Cables and Services - M&S | 500 | 603.79 | 2023-03-20 | 2023-03-21 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S367010 | Check MVTX operation during cabling | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S367020 | Install MVTX cooling panels and route lines | 120 | 14964.52 | 2023-03-20 | 2023-03-21 | 120 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 120
S367030 | Install MVTX gas distribution panels and route lines | 40 | 4988.17 | 2023-03-20 | 2023-03-21 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S367050 | Check MVTX operation with DAQ in counting house | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
POM02-13.02.05.11 Min Bias Installation |  | 12998 | 157174.37 | 29-Apr-21 A | 2023-03-29 | 7928 |  | Labor Hr/M&S Direct$ | 60 | 10037 | 2901
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 30 | 4724.5 | 01-Jul-22 A | 2022-10-25 | 15 | PROF4 PO M | Labor Hr/M&S Direct$ |  | 22 | 8
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1220.41 | 01-Jul-22 A | 2022-10-25 | 5 | TECH3 PO D | Labor Hr/M&S Direct$ |  | 7 | 3
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1220.41 | 01-Jul-22 A | 2022-10-25 | 5 | TECH3 PO M | Labor Hr/M&S Direct$ |  | 7 | 3
S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - M&S | 10000 | 11838.98 | 01-Jul-22 A | 2022-10-25 | 5000 | Purch 1st $2M | Labor Hr/M&S Direct$ |  | 10000
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 29-Apr-21 A | 2022-10-28 | 10 | PROF4 PO M | Labor Hr/M&S Direct$ | 40
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 20 | 2350.92 | 29-Apr-21 A | 2022-10-28 | 5 | TECH3 PO D | Labor Hr/M&S Direct$ | 20
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-10-31 | 2022-11-14 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-31 | 2022-11-14 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-31 | 2022-11-14 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-11-15 | 2022-11-30 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 1287.36 | 2023-03-13 | 2023-03-13 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 997.63 | 2023-03-13 | 2023-03-13 | 8 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 8
S368600 | Transport Assembled Min Bias Sections to AH - M&S | 500 | 603.79 | 2023-03-13 | 2023-03-13 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S368650 | Install MBD Installation fixtures and test | 10 | 1382.4 | 2023-03-14 | 2023-03-14 | 10 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 10
S368650 | Install MBD Installation fixtures and test | 10 | 1247.04 | 2023-03-14 | 2023-03-14 | 10 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 10
S368700 | Install Min Bias Support - Labor | 8 | 1287.36 | 2023-03-14 | 2023-03-14 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S368700 | Install Min Bias Support - Labor | 8 | 997.63 | 2023-03-14 | 2023-03-14 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S368700 | Install Min Bias Support - Labor | 16 | 1995.27 | 2023-03-14 | 2023-03-14 | 16 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 16
S368800 | Install Min Bias Support - M&S | 500 | 603.79 | 2023-03-14 | 2023-03-14 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S368900 | Install Min Bias (mechanical) - Labor | 8 | 1287.36 | 2023-03-15 | 2023-03-15 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S368900 | Install Min Bias (mechanical) - Labor | 8 | 997.63 | 2023-03-15 | 2023-03-15 | 8 | TECH3 PO D | Labor Hr/M&S Direct$ |  |  | 8
S368900 | Install Min Bias (mechanical) - Labor | 16 | 1995.27 | 2023-03-15 | 2023-03-15 | 16 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 16
S369000 | Install Min Bias (mechanical) - M&S | 500 | 603.79 | 2023-03-15 | 2023-03-15 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-22 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-22 | 20 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 20
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-17 | 20 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 20
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-20 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S369300 | Install Min Bias Cables and Services - Labor | 40 | 4988.17 | 2023-03-23 | 2023-03-23 | 40 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 40
S369300 | Install Min Bias Cables and Services - Labor | 40 | 4988.17 | 2023-03-23 | 2023-03-23 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S369400 | Install Min Bias Cables and Services - M&S | 500 | 603.79 | 2023-03-23 | 2023-03-23 | 500 | Purch 1st $2M | Labor Hr/M&S Direct$ |  |  | 500
S369450 | Check MBD operation during cabling | 40 | 7522.58 | 2023-03-23 | 2023-03-23 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S369460 | Install MBD cooling panels and route lines | 40 | 4988.17 | 2023-03-24 | 2023-03-24 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S369470 | Install MBD gas distribution panels and route lines | 40 | 4988.17 | 2023-03-24 | 2023-03-24 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-23 | 2023-03-29 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S369490 | Check MBD operation with DAQ in counting house | 40 | 7522.58 | 2023-03-23 | 2023-03-29 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S370105 | Install MBD cooling panels and route lines | 40 | 4988.17 | 2023-03-14 | 2023-03-14 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S370120 | Install sEPD Installation fixtures and test | 40 | 4988.17 | 2023-03-15 | 2023-03-15 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S370140 | Install sEPD support system | 40 | 4988.17 | 2023-03-15 | 2023-03-15 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S370160 | Install sEPD | 40 | 4988.17 | 2023-03-16 | 2023-03-16 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S370180 | Align sEPD | 40 | 4988.17 | 2023-03-17 | 2023-03-17 | 40 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 40
S370180 | Align sEPD | 20 | 2494.09 | 2023-03-17 | 2023-03-17 | 20 | TECH3 AD | Labor Hr/M&S Direct$ |  |  | 20
S370205 | Install sEPD cables - LV, bias, signal, control | 20 | 2494.09 | 2023-03-20 | 2023-03-20 | 20 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 20
S370205 | Install sEPD cables - LV, bias, signal, control | 20 | 2494.09 | 2023-03-20 | 2023-03-20 | 20 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 20
S370220 | Check sEPD operation during cabling | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | 40 | SCI3 | Labor Hr/M&S Direct$ |  |  | 40
POM02-13.02.05.12 Full System Integration and ORR |  | 1592 | 270974.3 | 2022-10-03 | 2023-01-31 | 1592 |  | Labor Hr/M&S Direct$ |  |  | 1592
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249.34 | 2022-10-03 | 2022-10-31 | 40 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249.34 | 2022-10-03 | 2022-10-31 | 40 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 7303.48 | 2022-10-03 | 2022-10-31 | 40 | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 8737.89 | 2022-10-03 | 2022-10-31 | 40 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 40
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1249.87 | 2022-11-01 | 2022-11-03 | 8 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 8
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1249.87 | 2022-11-01 | 2022-11-03 | 8 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 8
S370510 | Review of Safety System Design by CAD ESRC | 24 | 5242.73 | 2022-11-01 | 2022-11-03 | 24 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 24
S370510 | Review of Safety System Design by CAD ESRC | 24 | 4382.09 | 2022-11-01 | 2022-11-03 | 24 | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 24
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249.34 | 2022-11-04 | 2022-12-06 | 40 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 40
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249.34 | 2022-11-04 | 2022-12-06 | 40 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 40
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 7303.48 | 2022-11-04 | 2022-12-06 | 40 | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 40
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 8737.89 | 2022-11-04 | 2022-12-06 | 40 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 40
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3608.4 | 2022-11-04 | 2022-12-06 | 20 | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 20
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 4094.92 | 2022-11-04 | 2022-12-06 | 20 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 20
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 2126.45 | 2022-11-04 | 2022-12-06 | 20 | PROF2 AD | Labor Hr/M&S Direct$ |  |  | 20
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3124.67 | 2022-11-04 | 2022-12-06 | 20 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 20
S370530 | Review and approve procedures | 16 | 2499.74 | 2022-12-07 | 2022-12-08 | 16 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 16
S370530 | Review and approve procedures | 16 | 2499.74 | 2022-12-07 | 2022-12-08 | 16 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 16
S370530 | Review and approve procedures | 16 | 2921.39 | 2022-12-07 | 2022-12-08 | 16 | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 16
S370530 | Review and approve procedures | 16 | 3495.16 | 2022-12-07 | 2022-12-08 | 16 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 16
S370530 | Review and approve procedures | 16 | 2886.72 | 2022-12-07 | 2022-12-08 | 16 | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 16
S370530 | Review and approve procedures | 16 | 3275.94 | 2022-12-07 | 2022-12-08 | 16 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 16
S370540 | Magnet Checkout After Power Testing | 16 | 2921.39 | 2022-12-09 | 2022-12-15 | 16 | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 16
S370540 | Magnet Checkout After Power Testing | 16 | 3275.94 | 2022-12-09 | 2022-12-15 | 16 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 16
S370540 | Magnet Checkout After Power Testing | 16 | 2886.72 | 2022-12-09 | 2022-12-15 | 16 | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 16
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 2905.73 | 2022-12-16 | 2022-12-22 | 24 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 24
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 3749.6 | 2022-12-16 | 2022-12-22 | 24 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 24
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 5242.73 | 2022-12-16 | 2022-12-22 | 24 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 24
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2921.39 | 2022-12-23 | 2023-01-09 | 16 | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 16
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2886.72 | 2022-12-23 | 2023-01-09 | 16 | PROF5 AD | Labor Hr/M&S Direct$ |  |  | 16
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 3275.94 | 2022-12-23 | 2023-01-09 | 16 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2499.74 | 2023-01-10 | 2023-01-17 | 16 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937.15 | 2023-01-10 | 2023-01-17 | 16 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937.15 | 2023-01-10 | 2023-01-17 | 16 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2499.74 | 2023-01-10 | 2023-01-17 | 16 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 3495.16 | 2023-01-10 | 2023-01-17 | 16 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2499.74 | 2023-01-18 | 2023-01-24 | 16 | PROF4 PO M | Labor Hr/M&S Direct$ |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937.15 | 2023-01-18 | 2023-01-24 | 16 | TECH3 PO E | Labor Hr/M&S Direct$ |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937.15 | 2023-01-18 | 2023-01-24 | 16 | TECH3 PO M | Labor Hr/M&S Direct$ |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2499.74 | 2023-01-18 | 2023-01-24 | 16 | PROF4 PO E | Labor Hr/M&S Direct$ |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 3495.16 | 2023-01-18 | 2023-01-24 | 16 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2921.39 | 2023-01-18 | 2023-01-24 | 16 | SCI3 PO | Labor Hr/M&S Direct$ |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1460.7 | 2023-01-18 | 2023-01-24 | 8 | SCI3 AD | Labor Hr/M&S Direct$ |  |  | 8
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1249.87 | 2023-01-18 | 2023-01-24 | 8 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 8
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1249.87 | 2023-01-18 | 2023-01-24 | 8 | PROF4 AD | Labor Hr/M&S Direct$ |  |  | 8
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1637.97 | 2023-01-18 | 2023-01-24 | 8 | PROF6 AD | Labor Hr/M&S Direct$ |  |  | 8
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 16 | 3495.16 | 2023-01-25 | 2023-01-31 | 16 | SCI4 PO | Labor Hr/M&S Direct$ |  |  | 16
S370595 | Prepare for sPHENIX IRR | 160 | 30090.32 | 2022-11-01 | 2023-01-31 | 160 | SCI3 | Labor Hr/M&S Direct$ |  |  | 160
S370595 | Prepare for sPHENIX IRR | 160 | 22118.46 | 2022-11-01 | 2023-01-31 | 160 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 160
S370597 | Prepare for sPHENIX ARR | 160 | 22118.46 | 2022-11-01 | 2023-01-31 | 160 | PROF3 PO M | Labor Hr/M&S Direct$ |  |  | 160
S370597 | Prepare for sPHENIX ARR | 160 | 30090.32 | 2022-11-01 | 2023-01-31 | 160 | SCI3 | Labor Hr/M&S Direct$ |  |  | 160

## 2.x-1 (hidden)
Activity ID | % | BNL_Fund Source
S342400 | 50% | C
S345500 | 95% | C
S345600 | 95% | C
S345700 | 25% | C
S345910 | 25% | C
S345800 | 10% | C
S345900 | 10% | C
S346220 | 0% | C
S346230 | 0% | C
S346240 | 0% | C
S347610 | 0% | C
S347620 | 0% | C
S347630 | 0% | C
S347640 | 0% | C
S347650 | 0% | C
S347660 | 0% | C
S347670 | 0% | C
S347680 | 0% | C
S370500 | 0% | C
S370510 | 0% | C
S370520 | 0% | C
S370530 | 0% | C
S370540 | 0% | C
S370550 | 0% | C
S370560 | 0% | C
S370570 | 0% | C
S370580 | 0% | C
S370590 | 0% | C
S370595 | 0% | C
S370597 | 0% | C
S1003679 | 90% | C
S346000 | 90% | C
S346200 | 90% | C
S1003759 | 50% | C
S346100 | 50% | C
S346210 | 50% | C
S345920 | 0% | C
S345930 | 0% | C
S345940 | 0% | C
S346222 | 0% | C
S346224 | 0% | C
S346226 | 0% | C
S346228 | 0% | C
S346232 | 0% | C
S346234 | 0% | C
S346235 | 0% | C
S346236 | 0% | C
S346238 | 0% | C
S346242 | 0% | C
S346244 | 0% | C
S346245 | 0% | C
S346246 | 0% | C
S346248 | 0% | C
S346250 | 0% | C
S346298 | 30% | C
S346300 | 0% | C
S346310 | 0% | C
S346400 | 0% | C
S346402 | 0% | C
S346404 | 0% | C
S346700 | 50% | C
S346710 | 50% | C
S346800 | 50% | C
S347820 | 0% | C
S347830 | 0% | C
S347840 | 0% | C
S356252 | 0% | C
S356255 | 0% | C
S347200 | 33% | C
S347310 | 33% | C
S347400 | 0% | C
S347500 | 0% | C
S342500 | 25% | C
S341700 | 25% | C
S342600 | 25% | C
S1003839 | 56% | C
S1003879 | 0% | C
S276500 | 0% | C
S277100 | 0% | C
S277700 | 0% | C
S278300 | 0% | C
S279000 | 50% | C
S279100 | 5% | C
S279200 | 0% | C
S279300 | 0% | C
S279400 | 0% | C
S303600 | 70% | C
S304700 | 50% | C
S305000 | 50% | C
S308617 | 20% | C
S308619 | 0% | C
S308633 | 60% | C
S308900 | 0% | C
S309000 | 0% | C
S309005 | 0% | C
S309100 | 0% | C
S309110 | 0% | C
S317940 | 85% | C
S317970 | 50% | C
S318140 | 0% | C
S318170 | 0% | C
S318190 | 10% | C
S331470 | 92% | C
S331490 | 80% | C
S331496 | 0% | C
S332735 | 80% | C
S332755 | 40% | C
S332760 | 40% | C
S332765 | 40% | C
S332770 | 40% | C
S332775 | 40% | C
S332781 | 0% | C
S332782 | 0% | C
S332783 | 0% | C
S332784 | 0% | C
S332785 | 0% | C
S332786 | 0% | C
S332787 | 0% | C
S332788 | 0% | C
S332789 | 0% | C
S332790 | 0% | C
S332791 | 0% | C
S332792 | 0% | C
S332793 | 0% | C
S332794 | 0% | C
S332795 | 0% | C
S332796 | 0% | C
S333720 | 0% | C
S342390 | 0% | C
S347700 | 10% | C
S347810 | 10% | C
S351600 | 90% | C
S351700 | 90% | C
S351710 | 0% | C
S351720 | 0% | C
S351730 | 0% | C
S351740 | 0% | C
S356600 | 0% | C
S356700 | 0% | C
S356710 | 0% | C
S356720 | 0% | C
S356730 | 0% | C
S356740 | 0% | C
S358190 | 0% | C
S358200 | 56% | C
S358300 | 56% | C
S358400 | 50% | C
S358500 | 50% | C
S358600 | 50% | C
S358610 | 50% | C
S358700 | 50% | C
S358800 | 0% | C
S358900 | 0% | C
S359200 | 50% | C
S359400 | 50% | C
S359402 | 0% | C
S359404 | 0% | C
S359406 | 0% | C
S359408 | 0% | C
S359510 | 0% | C
S359520 | 0% | C
S359530 | 0% | C
S359540 | 0% | C
S359550 | 0% | C
S359560 | 0% | C
S359570 | 0% | C
S359580 | 0% | C
S359590 | 0% | C
S359595 | 0% | C
S359597 | 0% | C
S359700 | 90% | C
S359800 | 90% | C
S360000 | 90% | C
S360100 | 0% | C
S360400 | 0% | C
S360410 | 0% | C
S360500 | 0% | C
S360600 | 0% | C
S360620 | 0% | C
S360700 | 0% | C
S360800 | 0% | C
S360900 | 0% | C
S361000 | 0% | C
S361100 | 0% | C
S361110 | 0% | C
S361111 | 0% | C
S361200 | 0% | C
S361300 | 0% | C
S361400 | 0% | C
S361420 | 0% | C
S361440 | 0% | C
S361460 | 0% | C
S361465 | 0% | C
S361470 | 0% | C
S361480 | 0% | C
S361950 | 0% | C
S362300 | 0% | C
S362400 | 0% | C
S362500 | 0% | C
S362800 | 0% | C
S362900 | 0% | C
S362920 | 0% | C
S363000 | 0% | C
S363100 | 0% | C
S363120 | 0% | C
S363140 | 0% | C
S363160 | 0% | C
S363180 | 0% | C
S363200 | 0% | C
S363300 | 0% | C
S363400 | 0% | C
S363410 | 0% | C
S363500 | 0% | C
S363520 | 0% | C
S363540 | 0% | C
S363600 | 0% | C
S363700 | 0% | C
S363720 | 0% | C
S363740 | 0% | C
S363760 | 0% | C
S363770 | 0% | C
S363780 | 0% | C
S364600 | 75% | C
S364700 | 10% | C
S364800 | 0% | C
S365300 | 0% | C
S365400 | 0% | C
S365450 | 0% | C
S365500 | 0% | C
S365600 | 0% | C
S365700 | 0% | C
S365900 | 0% | C
S366000 | 0% | C
S366200 | 0% | C
S366300 | 0% | C
S366500 | 0% | C
S366710 | 0% | C
S366900 | 0% | C
S367000 | 0% | C
S367010 | 0% | C
S367020 | 0% | C
S367030 | 0% | C
S367040 | 0% | C
S367050 | 0% | C
S367800 | 50% | C
S367900 | 50% | C
S368000 | 75% | C
S368100 | 0% | C
S368200 | 0% | C
S368500 | 0% | C
S368600 | 0% | C
S368650 | 0% | C
S368700 | 0% | C
S368800 | 0% | C
S368900 | 0% | C
S369000 | 0% | C
S369100 | 0% | C
S369110 | 0% | C
S369300 | 0% | C
S369400 | 0% | C
S369450 | 0% | C
S369460 | 0% | C
S369470 | 0% | C
S369480 | 0% | C
S369490 | 0% | C
S370105 | 0% | C
S370120 | 0% | C
S370140 | 0% | C
S370160 | 0% | C
S370180 | 0% | C
S370205 | 0% | C
S370220 | 0% | C
S370240 | 0% | C
S370260 | 0% | C

## 2.x-2 (hidden)
Activity ID | Activity Name | Budgeted Units | Budgeted Cost | Start | Finish | Resource ID
POM02-13.02.01.04 Infrastructure Management |  | 153 | 17904.51 | 2022-10-03 | 2022-10-07
S276500 | 2023 Infrastructure Project Management | 40 | 5529.62 | 2022-10-03 | 2022-10-07 | PROF3 PO E
S277100 | 2023 Facility Support Systems L3 Project Management | 113 | 12374.89 | 2022-10-03 | 2022-10-07 | PROF2 AD
POM02-13.02.01.05 Installation Management |  | 282 | 52404.77 | 2022-10-03 | 2022-10-05
S278300 | 2023 Integration & Installation Project Management | 282 | 52404.77 | 2022-10-03 | 2022-10-05 | PROF5 PO M
POM02-13.02.02.01.01 Safety Reviews |  | 32 | 6383.25 | 16-Sep-22 A | 2022-10-07
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 3009.03 | 16-Sep-22 A | 2022-10-07 | SCI3 AD
S279000 | ASSRC REVIEW and Full Walkthrough | 16 | 3374.22 | 16-Sep-22 A | 2022-10-07 | PROF6 AD
POM02-13.02.02.01.02 Cooldown & Power Tests |  | 724 | 118823.66 | 17-Aug-22 A | 2022-10-27
S279100 | Cooldown | 60 | 8294.42 | 17-Aug-22 A | 2022-10-17 | PROF3 AD
S279100 | Cooldown | 60 | 7482.26 | 17-Aug-22 A | 2022-10-17 | TECH3 AD
S279100 | Cooldown | 60 | 12653.32 | 17-Aug-22 A | 2022-10-17 | PROF6 AD
S279200 | 4.5K Static Heat Load test | 8 | 1073.71 | 2022-10-18 | 2022-10-19 | PROF3 AD
S279200 | 4.5K Static Heat Load test | 8 | 968.58 | 2022-10-18 | 2022-10-19 | TECH3 AD
S279200 | 4.5K Static Heat Load test | 8 | 1637.97 | 2022-10-18 | 2022-10-19 | PROF6 AD
S279300 | 4.5K Low power test | 20 | 2684.28 | 2022-10-20 | 2022-10-24 | PROF3 AD
S279300 | 4.5K Low power test | 80 | 14606.95 | 2022-10-20 | 2022-10-24 | SCI3 AD
S279300 | 4.5K Low power test | 80 | 9685.77 | 2022-10-20 | 2022-10-24 | TECH3 AD
S279300 | 4.5K Low power test | 80 | 16379.7 | 2022-10-20 | 2022-10-24 | PROF6 AD
S279400 | 4.5K High Power Test | 20 | 2684.28 | 2022-10-25 | 2022-10-27 | PROF3 AD
S279400 | 4.5K High Power Test | 80 | 14606.95 | 2022-10-25 | 2022-10-27 | SCI3 AD
S279400 | 4.5K High Power Test | 80 | 9685.77 | 2022-10-25 | 2022-10-27 | TECH3 AD
S279400 | 4.5K High Power Test | 80 | 16379.7 | 2022-10-25 | 2022-10-27 | PROF6 AD
POM02-13.02.02.04.01.03 Install PS AC/DC Cabling |  | 420 | 54812.28 | 01-Jul-22 A | 2022-10-07
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 40 | 6249.34 | 01-Jul-22 A | 2022-10-07 | PROF4 AD
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 160 | 19371.55 | 01-Jul-22 A | 2022-10-07 | TECH3 AD
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 220 | 29191.39 | 01-Jul-22 A | 2022-10-07 | CRAFT3
POM02-13.02.02.04.02.01 Install Power Supply |  | 230 | 31179.97 | 10-Aug-22 A | 2022-10-19
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 70 | 8729.3 | 10-Aug-22 A | 2022-10-11 | TECH3 AD
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 12648.66 | 23-Sep-22 A | 2022-10-19 | PROF4 AD
S305000 | Magnet Power Supply Installation: Power Supply Testing | 80 | 9802 | 23-Sep-22 A | 2022-10-19 | TECH3 AD
POM02-13.02.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication |  | 112 | 17097.9 | 01-Sep-22 A | 2023-01-17
S308617 | Calibrate probes | 24 | 5400.02 | 01-Sep-22 A | 2022-12-30 | SCI4 PO
S308617 | Calibrate probes | 24 | 3862.09 | 01-Sep-22 A | 2022-12-30 | PROF4 PO E
S308617 | Calibrate probes | 24 | 2992.9 | 01-Sep-22 A | 2022-12-30 | TECH3 PO E
S308619 | Install probes and readout on TPC | 40 | 4842.89 | 2023-01-03 | 2023-01-17 | TECH3 PO E
POM02-13.02.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis |  | 1208 | 186391.94 | 08-Mar-21 A | 2022-12-22
S308633 | Construct mapping support (mechanical and electrical) | 32 | 3874.31 | 08-Mar-21 A | 2022-11-01 | TECH3 PO M
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 9976.35 | 2022-10-18 | 2022-10-31 | TECH3 PO M
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 19952.7 | 2022-10-18 | 2022-10-31 | TECH3 PO E
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 80 | 11059.23 | 2022-10-18 | 2022-10-31 | PROF3 PO E
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 160 | 36000.1 | 2022-10-18 | 2022-10-31 | SCI4 PO
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9976.35 | 2022-11-01 | 2022-11-15 | TECH3 PO M
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 36000.1 | 2022-11-01 | 2022-11-15 | SCI4 PO
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 11059.23 | 2022-11-01 | 2022-11-15 | PROF3 PO E
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 160 | 19952.7 | 2022-11-01 | 2022-11-15 | TECH3 PO E
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 80 | 9976.35 | 2022-11-01 | 2022-11-15 | TECH3 PO E
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 40 | 4988.17 | 2022-11-16 | 2022-11-22 | TECH3 PO M
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 80 | 9976.35 | 2022-11-16 | 2022-11-22 | TECH3 PO E
S309110 | Receive report from CERN, incorporate into analysis | 16 | 3600.01 | 2022-11-23 | 2022-12-22 | SCI4 PO
POM02-13.02.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports |  | 60180 | 94315.98 | 31-Mar-22 A | 2022-11-14
S317940 | Procure TPC Supports - M&S | 50000 | 59194.9 | 31-Mar-22 A | 2022-10-28 | Purch 1st $2M
S317970 | Procure MBD Supports - M&S | 10000 | 11838.98 | 01-Jul-22 A | 2022-10-28 | Purch 1st $2M
S318140 | Perform TPC Supports Acceptance | 40 | 4842.89 | 2022-10-31 | 2022-11-14 | TECH3 PO M
S318140 | Perform TPC Supports Acceptance | 40 | 5368.56 | 2022-10-31 | 2022-11-14 | PROF3 PO E
S318170 | Perform MBD Supports Acceptance | 10 | 1210.72 | 2022-10-31 | 2022-11-14 | TECH3 PO M
S318170 | Perform MBD Supports Acceptance | 10 | 1342.14 | 2022-10-31 | 2022-11-14 | PROF3 PO E
S318190 | Perform Beampipe Supports Acceptance | 40 | 4988.17 | 26-Sep-22 A | 2022-10-17 | TECH3 PO M
S318190 | Perform Beampipe Supports Acceptance | 40 | 5529.62 | 26-Sep-22 A | 2022-10-17 | PROF3 PO E
POM02-13.02.04.01.03 Detector Electronics Racks and Rack generic support systems |  | 780 | 96252.38 | 13-Sep-21 A | 2022-11-10
S331470 | Assemble Racks for Lower East Platform | 80 | 9685.77 | 15-Nov-21 A | 2022-10-31 | TECH3 PO E
S331490 | Assemble Racks for Main Upper Platform | 200 | 24214.44 | 13-Sep-21 A | 2022-10-31 | TECH3 PO E
S331496 | ADDED RACK ASSEMBLY EFFORT, BASED ON EFFORT TO DATE | 500 | 62352.17 | 2022-11-01 | 2022-11-10 | TECH3 PO E
POM02-13.02.04.01.04 Detector Gas and Cooling Services Systems |  | 56334 | 366297.65 | 15-Feb-21 A | 2023-02-09
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 96 | 14561.56 | 15-Feb-21 A | 2022-10-31 | PROF4 PO M
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642.2 | 15-Feb-21 A | 2022-10-31 | TECH3 PO D
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 48 | 5642.2 | 15-Feb-21 A | 2022-10-31 | TECH3 PO M
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 32 | 5004.47 | 22-Jul-22 A | 2022-10-31 | PROF4 PO M
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 72 | 8725.91 | 22-Jul-22 A | 2022-10-31 | TECH3 PO D
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 3862.09 | 05-Sep-22 A | 2022-11-02 | PROF4 PO M
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 24 | 2992.9 | 05-Sep-22 A | 2022-11-02 | TECH3 PO D
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 15448.36 | 03-Sep-22 A | 2023-02-02 | PROF4 PO M
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 96 | 11971.62 | 03-Sep-22 A | 2023-02-02 | TECH3 PO D
S332770 | Procure & Deliver Detector Gas Services Systems Components - M&S | 54000 | 65209.09 | 03-Sep-22 A | 2023-02-02 | Purch 1st $2M
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 2574.73 | 12-Sep-22 A | 2023-02-09 | PROF4 PO M
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 16 | 1995.27 | 12-Sep-22 A | 2023-02-09 | TECH3 PO D
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 8 | 997.63 | 12-Sep-22 A | 2023-02-09 | TECH3 PO M
S332781 | Design, procure, test remaining cooling system items | 100 | 13824.04 | 2022-11-01 | 2022-11-02 | PROF3 PO E
S332781 | Design, procure, test remaining cooling system items | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | TECH3 PO M
S332782 | Cooling System Panel Fabrication - TPC | 8 | 1105.92 | 2022-11-03 | 2022-11-04 | PROF3 PO E
S332782 | Cooling System Panel Fabrication - TPC | 130 | 16211.57 | 2022-11-03 | 2022-11-04 | TECH3 PO M
S332783 | Cooling System Panel Fabrication - TPot | 4 | 552.96 | 2022-11-07 | 2022-11-08 | PROF3 PO E
S332783 | Cooling System Panel Fabrication - TPot | 60 | 7482.26 | 2022-11-07 | 2022-11-08 | TECH3 PO M
S332784 | Cooling System Panel Fabrication - EMCal SiPM | 290 | 36164.26 | 2022-11-09 | 2022-11-10 | TECH3 PO M
S332785 | Cooling System Panel Fabrication - EMCal PreAmp | 290 | 36164.26 | 2022-11-14 | 2022-11-15 | TECH3 PO M
S332786 | Cooling System Panel Fabrication - INTT ROC | 120 | 14964.52 | 2022-11-16 | 2022-11-17 | TECH3 PO M
S332787 | Cooling System Panel Fabrication - INTT Stave | 120 | 14964.52 | 2022-11-18 | 2022-11-21 | TECH3 PO M
S332788 | Cooling System Panel Fabrication - MVTX | 80 | 9976.35 | 2022-11-22 | 2022-11-23 | TECH3 PO M
S332789 | Cooling System Platform Manifolding | 24 | 3862.09 | 2022-11-28 | 2022-11-29 | PROF4 PO M
S332789 | Cooling System Platform Manifolding | 100 | 12470.43 | 2022-11-28 | 2022-11-29 | TECH3 PO M
S332790 | Gas Distribution Panel Fabrication - TPC Ar-CF4 | 100 | 12470.43 | 2022-10-03 | 2022-10-04 | TECH3 PO M
S332791 | Gas Distribution Panel Fabrication - TPC Laser N2 | 40 | 4988.17 | 2022-10-05 | 2022-10-06 | TECH3 PO M
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 4 | 552.96 | 2022-10-07 | 2022-10-11 | PROF3 PO E
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 80 | 9976.35 | 2022-10-07 | 2022-10-11 | TECH3 PO M
S332793 | Gas Distribution Panel Fabrication - EMCal SiPM N2 | 40 | 4988.17 | 2022-10-12 | 2022-10-13 | TECH3 PO M
S332794 | Gas Distribution Panel Fabrication - INTT Stave N2 | 40 | 4988.17 | 2022-10-14 | 2022-10-17 | TECH3 PO M
S332795 | Gas Distribution Panel Fabrication - MVTX N2 | 8 | 997.63 | 2022-10-18 | 2022-10-19 | TECH3 PO M
S332796 | Gas Distribution Panel Fabrication - MBD dry compressed air | 40 | 4988.17 | 2022-10-20 | 2022-10-21 | TECH3 PO M
POM02-13.02.04.01.05 Detector Safety Subsystems |  | 120 | 14964.52 | 2022-11-01 | 2022-12-01
S333720 | Fabricate Detector Safety Systems | 60 | 7482.26 | 2022-11-01 | 2022-12-01 | TECH3 PO M
S333720 | Fabricate Detector Safety Systems | 60 | 7482.26 | 2022-11-01 | 2022-12-01 | TECH3 PO E
POM02-13.02.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR |  | 113 | 20999.07 | 2022-10-03 | 2022-10-04
S277700 | 2023 Detector Support Systems L3 Project Management | 113 | 20999.07 | 2022-10-03 | 2022-10-04 | PROF5 PO M
POM02-13.02.04.02.05 IR/AH Safety Subsystems |  | 32450 | 96653.71 | 04-Jul-22 A | 2023-01-06
S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - M&S | 32000 | 38642.42 | 04-Jul-22 A | 2022-12-21 | Purch 1st $2M
S342390 | Design IR/AH Safety Systems | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | TECH3 PO M
S342390 | Design IR/AH Safety Systems | 80 | 11059.23 | 2022-11-01 | 2022-12-30 | PROF3 PO E
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 24 | 3424.91 | 03-Sep-22 A | 2022-10-17 | TECH4 AD
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 48 | 5256.59 | 03-Sep-22 A | 2022-10-17 | PROF2 AD
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 4 | 643.68 | 03-Sep-22 A | 2022-10-17 | PROF4 AD
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 48 | 6849.81 | 18-Sep-22 A | 2022-11-15 | TECH4 AD
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 96 | 10513.18 | 18-Sep-22 A | 2022-11-15 | PROF2 AD
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 2 | 321.84 | 18-Sep-22 A | 2022-11-15 | PROF4 AD
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 88 | 12557.99 | 22-Sep-22 A | 2023-01-06 | TECH4 AD
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 16 | 1752.2 | 22-Sep-22 A | 2023-01-06 | PROF2 AD
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 4 | 643.68 | 22-Sep-22 A | 2023-01-06 | PROF4 AD
POM02-13.02.05.02 Infrastructure Installation |  | 13128 | 956788.33 | 09-Sep-21 A | 2023-03-10
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 160 | 21230.1 | 09-Sep-21 A | 2022-10-28 | CRAFT3
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 40 | 6249.34 | 09-Sep-21 A | 2022-10-28 | PROF4 PO E
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 4 | 818.98 | 09-Sep-21 A | 2022-10-28 | PROF6 AD
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 80 | 10933.5 | 30-Aug-22 A | 2022-10-31 | CRAFT3
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 40 | 6436.82 | 30-Aug-22 A | 2022-10-31 | PROF4 PO E
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4842.89 | 03-Jan-22 A | 2022-10-28 | TECH3 AD
S345500 | Install IR HVAC - Labor - C-AD Resources | 64 | 8492.04 | 03-Jan-22 A | 2022-10-28 | CRAFT3
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 4252.91 | 03-Jan-22 A | 2022-10-28 | PROF2 AD
S345500 | Install IR HVAC - Labor - C-AD Resources | 40 | 6249.34 | 03-Jan-22 A | 2022-10-28 | PROF4 AD
S345600 | Install IR HVAC - M&S | 250 | 295.97 | 03-Jan-22 A | 2022-10-28 | Purch 1st $2M
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 80 | 9976.35 | 01-Apr-22 A | 2023-02-06 | TECH3 AD
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 16 | 2574.73 | 01-Apr-22 A | 2023-02-06 | PROF4 AD
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 24 | 3280.05 | 01-Apr-22 A | 2023-02-06 | CRAFT3
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 40 | 4380.49 | 01-Apr-22 A | 2023-02-06 | PROF2 AD
S345800 | Install On Detector Safety Subsystems - Labor | 80 | 9976.35 | 14-Sep-22 A | 2022-12-15 | TECH3 PO E
S345800 | Install On Detector Safety Subsystems - Labor | 40 | 4988.17 | 14-Sep-22 A | 2022-12-15 | TECH3 PO M
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3218.41 | 14-Sep-22 A | 2022-12-15 | PROF4 PO E
S345800 | Install On Detector Safety Subsystems - Labor | 20 | 3218.41 | 14-Sep-22 A | 2022-12-15 | PROF4 PO M
S345900 | Install On Detector Safety Subsystems - M&S | 500 | 603.79 | 14-Sep-22 A | 2022-12-15 | Purch 1st $2M
S345910 | Install Off Detector Safety Subsystems inc Vesda - M&S | 500 | 603.79 | 01-Apr-22 A | 2023-02-06 | Purch 1st $2M
S345920 | Install Rack Protection systems - Lower platform | 40 | 4988.17 | 2022-11-01 | 2022-12-01 | TECH3 PO E
S345930 | Install Rack Protection systems - Middle platform | 40 | 4988.17 | 2022-12-02 | 2022-12-30 | TECH3 PO M
S345940 | Install Rack Protection systems - Upper platform | 160 | 19952.7 | 2023-01-03 | 2023-01-31 | TECH3 PO E
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 32 | 4999.47 | 09-Sep-21 A | 2022-10-28 | PROF4 AD
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 32 | 4999.47 | 30-Aug-22 A | 2022-10-31 | PROF4 AD
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 4 | 818.98 | 30-Aug-22 A | 2022-10-31 | PROF6 AD
S346200 | Install Line Electric Power Distribution Off Detector - M&S | 500 | 591.95 | 09-Sep-21 A | 2022-10-28 | Purch 1st $2M
S346210 | Install Line Electric Power Distribution On Detector - M&S | 500 | 597.46 | 30-Aug-22 A | 2022-10-31 | Purch 1st $2M
S346220 | Install AC power to Racks - Lower platforms | 120 | 14964.52 | 2022-11-01 | 2022-12-01 | TECH3 PO E
S346222 | Complete lighting and convenience power | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | TECH3 PO E
S346224 | Complete wiring of chiller platform | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | TECH3 PO E
S346226 | Complete wiring of N & S Ploe Tip doors and motors | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | TECH3 PO E
S346228 | Complete on-detector 24V-DC distribution system | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | TECH3 PO E
S346228 | Complete on-detector 24V-DC distribution system | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346230 | Install AC power to Racks - Middle platforms | 120 | 14964.52 | 2022-12-02 | 2022-12-30 | TECH3 PO E
S346232 | Complete global interlock system | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346234 | Complete ODH, crash, sweeps - CAD PASS | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346235 | Complete rack interlock system (36 racks) | 160 | 19952.7 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346236 | Complete FAP and HSSP - Fire Alarm group | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346238 | Complete network installation | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346240 | Install AC power to Racks - Upper platforms | 480 | 59858.09 | 2023-01-03 | 2023-01-31 | TECH3 PO E
S346242 | Complete ECW water leak detection | 80 | 9976.35 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346244 | Complete contactor boxes for interlock system | 120 | 14964.52 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346245 | Complete VESDA north/south solenoid - piping (sEPD area) | 120 | 14964.52 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346246 | Complete I/O terminations Rack 3B1 | 240 | 29929.04 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346248 | Test rack interlock system | 80 | 11059.23 | 2022-11-01 | 2022-12-30 | PROF3 PO E
S346248 | Test rack interlock system | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346250 | Test global interlock system | 80 | 11059.23 | 2022-11-01 | 2022-12-30 | PROF3 PO E
S346250 | Test global interlock system | 40 | 4988.17 | 2022-11-01 | 2022-12-30 | TECH3 AD
S346298 | Build North and South work platforms | 30 | 3741.13 | 17-Aug-22 A | 2023-01-27 | TECH3 PO M
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 20 | 3218.41 | 2023-01-30 | 2023-02-03 | PROF4 PO M
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 40 | 4988.17 | 2023-01-30 | 2023-02-03 | TECH3 PO M
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 16 | 1995.27 | 2023-01-30 | 2023-02-03 | TECH3 PO D
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 104 | 12969.25 | 2023-01-30 | 2023-02-03 | TECH3 AD
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 80 | 8760.98 | 2023-01-30 | 2023-02-03 | PROF2 AD
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 40 | 6436.82 | 2023-01-30 | 2023-02-03 | PROF4 AD
S346400 | Install Beampipe Temp Support M&S | 500 | 603.79 | 2023-01-30 | 2023-02-03 | Purch 1st $2M
S346402 | Beampipe bakeout | 500 | 603.79 | 2023-02-06 | 2023-02-17 | Purch 1st $2M
S346404 | Install permanent Beampipe support | 500 | 603.79 | 2023-03-10 | 2023-03-10 | Purch 1st $2M
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 9793.39 | 01-Apr-22 A | 2022-10-17 | TECH3 PO E
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 9793.39 | 01-Apr-22 A | 2022-10-17 | TECH3 PO M
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 80 | 12637.55 | 01-Apr-22 A | 2022-10-17 | PROF4 PO E
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 160 | 19586.79 | 01-Apr-22 A | 2022-10-17 | TECH3 AD
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 80 | 10733 | 01-Apr-22 A | 2022-10-17 | CRAFT3
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 20 | 2150.08 | 01-Apr-22 A | 2022-10-17 | PROF2 AD
S346800 | Install Non-IR Infrastructure - M&S | 500 | 600.95 | 01-Apr-22 A | 2022-12-21 | Purch 1st $2M
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18860.5 | 01-Apr-22 A | 2022-11-30 | PROF4 PO M
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 34103.61 | 01-Apr-22 A | 2022-11-30 | TECH3 PO E
S347200 | Install Electronics Racks On Carriage - Labor | 280 | 34103.61 | 01-Apr-22 A | 2022-11-30 | TECH3 PO M
S347200 | Install Electronics Racks On Carriage - Labor | 48 | 5846.33 | 01-Apr-22 A | 2022-11-30 | TECH3 PO D
S347200 | Install Electronics Racks On Carriage - Labor | 120 | 18860.5 | 01-Apr-22 A | 2022-11-30 | PROF4 PO E
S347310 | Install Electronics Racks On Carriage - M&S | 500 | 594.32 | 01-Apr-22 A | 2022-11-30 | Purch 1st $2M
S347400 | Install Gas and Cooling System Services - Labor | 120 | 19310.45 | 2022-10-03 | 2022-12-01 | PROF4 PO M
S347400 | Install Gas and Cooling System Services - Labor | 720 | 89787.13 | 2022-10-03 | 2022-12-01 | TECH3 PO M
S347400 | Install Gas and Cooling System Services - Labor | 96 | 11971.62 | 2022-10-03 | 2022-12-01 | TECH3 PO D
S347500 | Install Gas and Cooling System Services - M&S | 500 | 603.79 | 2022-10-03 | 2022-12-01 | Purch 1st $2M
S347610 | Off Carriage Water Lines & Flow Control - Sill & Labyrinth area | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | TECH3 AD
S347620 | Off Carriage Water Lines & Flow Control - Chiller Platforms | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | TECH3 AD
S347630 | Off Carriage Water - ECW to 'brass block' | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | TECH3 AD
S347640 | Off Carriage Water - Brass block to chillers | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | TECH3 PO M
S347650 | Off Carriage Water - Chiller panels to cooling lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | TECH3 AD
S347660 | Off Carriage Water - Bridge lines | 40 | 4988.17 | 2022-11-01 | 2022-11-02 | TECH3 AD
S347670 | Off Carriage Water - Bridges to on-carriage panels | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | TECH3 AD
S347680 | Off Carriage Water - Carriage ECW to on-carriage panels | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | TECH3 PO M
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 80 | 9685.77 | 01-Aug-22 A | 2023-01-18 | TECH3 PO M
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 16 | 1937.15 | 01-Aug-22 A | 2023-01-18 | TECH3 PO D
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 32 | 4246.02 | 01-Aug-22 A | 2023-01-18 | CRAFT3
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 20 | 3124.67 | 01-Aug-22 A | 2023-01-18 | PROF4 PO E
S347810 | Install IR Electronics Cooling Water On Detector - M&S | 500 | 591.95 | 01-Aug-22 A | 2023-01-18 | Purch 1st $2M
S347820 | Install Rack Cooling water - Lower platforms | 80 | 9976.35 | 2022-11-01 | 2022-12-01 | TECH3 AD
S347830 | Install Rack Cooling water - Middle platforms | 80 | 9976.35 | 2022-12-02 | 2022-12-30 | TECH3 AD
S347840 | Install Rack Cooling water - Upper platforms | 320 | 39905.39 | 2023-01-03 | 2023-01-31 | TECH3 AD
S356252 | Control system programming | 120 | 16588.85 | 2022-11-01 | 2022-12-30 | PROF3 PO E
S356255 | Control system HMI and usage testing | 120 | 16588.85 | 2022-11-01 | 2022-12-30 | PROF3 PO E
POM02-13.02.05.04 Outer Hcal Installation |  | 980 | 69703.86 | 01-Mar-22 A | 2022-12-06
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 9685.77 | 01-Mar-22 A | 2022-10-28 | TECH3 PO M
S351600 | Install Outer HCal Cables and Services - Labor | 160 | 19371.55 | 01-Mar-22 A | 2022-10-28 | TECH3 PO E
S351600 | Install Outer HCal Cables and Services - Labor | 80 | 12498.68 | 01-Mar-22 A | 2022-10-28 | PROF4 PO E
S351700 | Install Outer HCal Cables and Services - M&S | 500 | 591.95 | 01-Mar-22 A | 2022-10-28 | Purch 1st $2M
S351710 | Check OHCal operation during cabling | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | SCI3
S351720 | Install OHCal gas distribution panels and route lines | 40 | 4988.17 | 2022-11-21 | 2022-11-29 | TECH3 PO M
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | SCI3
S351740 | Check OHCal operation with DAQ in counting house | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | SCI3
POM02-13.02.05.06 Inner Hcal Installation |  | 980 | 69703.86 | 2022-10-03 | 2022-12-06
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 9685.77 | 2022-10-03 | 2022-10-31 | TECH3 PO M
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 160 | 19371.55 | 2022-10-03 | 2022-10-31 | TECH3 PO E
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 80 | 12498.68 | 2022-10-03 | 2022-10-31 | PROF4 PO E
S356700 | Install Inner HCal Cables and Services (if instrumented) - M&S | 500 | 591.95 | 2022-11-01 | 2022-12-01 | Purch 1st $2M
S356710 | Check IHCal operation during cabling | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | SCI3
S356720 | Install IHCal gas distribution panels and route lines | 40 | 4988.17 | 2022-11-21 | 2022-11-29 | TECH3 PO M
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | SCI3
S356740 | Check IHCal operation with DAQ in counting house | 40 | 7522.58 | 2022-11-21 | 2022-12-06 | SCI3
POM02-13.02.05.07 EMCal Installation |  | 5764 | 469131.25 | 01-Jul-22 A | 2023-02-10
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 120 | 15922.58 | 01-Jul-22 A | 2022-12-09 | CRAFT3
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 64 | 7748.62 | 01-Jul-22 A | 2022-12-09 | TECH3 PO M
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 80 | 9976.35 | 2022-11-01 | 2022-11-07 | TECH3 PO E
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 8 | 1249.87 | 01-Jul-22 A | 2022-12-09 | PROF4 AD
S358300 | Transport Assembled EMCal Sectors to AH - M&S | 500 | 591.95 | 01-Jul-22 A | 2022-12-09 | Purch 1st $2M
S358400 | Install EMCal Sectors - Labor | 64 | 9998.94 | 01-Aug-22 A | 2022-12-09 | PROF4 PO M
S358400 | Install EMCal Sectors - Labor | 64 | 7748.62 | 01-Aug-22 A | 2022-12-09 | TECH3 PO D
S358400 | Install EMCal Sectors - Labor | 512 | 61988.96 | 01-Aug-22 A | 2022-12-09 | TECH3 PO M
S358500 | Install EMCal Sectors - M&S | 500 | 591.95 | 01-Aug-22 A | 2022-12-09 | Purch 1st $2M
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 17-Aug-22 A | 2022-12-12 | TECH3 PO M
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10933.5 | 17-Aug-22 A | 2022-12-12 | CRAFT3
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 17-Aug-22 A | 2022-12-12 | TECH3 AD
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8562.26 | 17-Aug-22 A | 2022-12-12 | TECH4 AD
S358700 | Align/Survey EMCal to SC Magnet Centerline - M&S | 500 | 603.79 | 17-Aug-22 A | 2022-12-12 | Purch 1st $2M
S358800 | Install EMCal Cables and Services - Labor | 160 | 19698.44 | 2022-12-13 | 2023-01-05 | TECH3 PO E
S358800 | Install EMCal Cables and Services - Labor | 64 | 7879.38 | 2022-12-13 | 2023-01-05 | TECH3 PO M
S358800 | Install EMCal Cables and Services - Labor | 32 | 5083.84 | 2022-12-13 | 2023-01-05 | PROF4 PO M
S358800 | Install EMCal Cables and Services - Labor | 32 | 3939.69 | 2022-12-13 | 2023-01-05 | TECH3 PO D
S358800 | Install EMCal Cables and Services - Labor | 320 | 43176.72 | 2022-12-13 | 2023-01-05 | CRAFT3
S358900 | Install EMCal Cables and Services - M&S | 500 | 598.61 | 2022-12-13 | 2023-01-05 | Purch 1st $2M
S359200 | Commission EMCal - Labor | 400 | 75225.81 | 01-Aug-22 A | 2023-02-10 | SCI3 PO
S359200 | Commission EMCal - Labor | 40 | 6436.82 | 01-Aug-22 A | 2023-02-10 | PROF4 PO E
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | TECH3 PO E
S359200 | Commission EMCal - Labor | 40 | 6436.82 | 01-Aug-22 A | 2023-02-10 | PROF4 PO M
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | TECH3 PO D
S359200 | Commission EMCal - Labor | 40 | 4988.17 | 01-Aug-22 A | 2023-02-10 | TECH3 PO M
S359400 | Commission EMCal - M&S | 500 | 603.79 | 01-Aug-22 A | 2023-02-10 | Purch 1st $2M
S359402 | Install EMCal cooling panels and route lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | TECH3 PO M
S359404 | Install EMCal gas distribution panels and route lines | 80 | 9976.35 | 2022-11-01 | 2022-11-02 | TECH3 PO M
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 160 | 30090.32 | 2022-12-13 | 2022-12-27 | SCI3
S359408 | Check EMCal operation with DAQ in counting house | 160 | 30090.32 | 2022-12-13 | 2022-12-27 | SCI3
S359510 | Transport TPot from Stony Brook to 1008 AH | 8 | 997.63 | 2022-12-01 | 2022-12-01 | TECH3 PO M
S359520 | Install TPot Installation fixtures and test | 16 | 2211.85 | 2022-10-03 | 2022-10-04 | PROF3 PO M
S359520 | Install TPot Installation fixtures and test | 20 | 2494.09 | 2022-10-03 | 2022-10-04 | TECH3 PO M
S359530 | Install TPot support system | 4 | 552.96 | 2022-12-02 | 2022-12-02 | PROF3 PO M
S359530 | Install TPot support system | 20 | 2494.09 | 2022-12-02 | 2022-12-02 | TECH3 PO M
S359540 | Install TPot | 4 | 552.96 | 2022-10-05 | 2022-10-06 | PROF3 PO M
S359540 | Install TPot | 80 | 9976.35 | 2022-10-05 | 2022-10-06 | TECH3 PO M
S359550 | Align TPot | 20 | 2494.09 | 2022-12-05 | 2022-12-05 | TECH3 PO M
S359550 | Align TPot | 20 | 2494.09 | 2022-12-05 | 2022-12-05 | TECH3 AD
S359560 | Install TPot cables - LV, bias, signal, control | 24 | 3317.77 | 2022-10-07 | 2022-10-11 | PROF3 PO M
S359560 | Install TPot cables - LV, bias, signal, control | 80 | 9976.35 | 2022-10-07 | 2022-10-11 | TECH3 PO E
S359560 | Install TPot cables - LV, bias, signal, control | 20 | 2494.09 | 2022-10-07 | 2022-10-11 | TECH3 PO M
S359570 | Check TPot operation during cabling | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | SCI3
S359580 | Install TPot cooling panels and route lines | 40 | 4988.17 | 2022-10-03 | 2022-10-04 | TECH3 PO M
S359590 | Install TPot gas distribution panels and route lines | 40 | 4988.17 | 2022-10-03 | 2022-10-04 | TECH3 PO M
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | SCI3
S359597 | Check TPot operation with DAQ in counting house | 16 | 3009.03 | 2022-12-05 | 2022-12-06 | SCI3
POM02-13.02.05.08 TPC Installation |  | 34644 | 348738.55 | 03-Jan-22 A | 2023-03-06
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 4 | 643.68 | 2022-12-29 | 2023-01-05 | PROF4 PO M
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 16 | 1995.27 | 2022-12-29 | 2023-01-05 | TECH3 PO D
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 60 | 7482.26 | 2022-12-29 | 2023-01-05 | TECH3 PO M
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 36 | 4920.08 | 2022-12-29 | 2023-01-05 | CRAFT3
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 60 | 9374.01 | 03-Jan-22 A | 2022-10-20 | PROF4 PO M
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 20 | 2421.44 | 03-Jan-22 A | 2022-10-20 | TECH3 PO D
S359800 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - M&S | 30000 | 35516.94 | 03-Jan-22 A | 2022-10-20 | Purch 1st $2M
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 25-Jan-22 A | 2022-11-02 | PROF4 PO M
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 25-Jan-22 A | 2022-11-02 | TECH3 PO M
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 25-Jan-22 A | 2022-11-02 | TECH3 PO D
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1287.36 | 2022-11-03 | 2022-11-17 | PROF4 PO M
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 997.63 | 2022-11-03 | 2022-11-17 | TECH3 PO M
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 997.63 | 2022-11-03 | 2022-11-17 | TECH3 PO D
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 1249.87 | 2022-12-13 | 2022-12-19 | PROF4 PO M
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 24 | 2905.73 | 2022-12-13 | 2022-12-19 | TECH3 PO M
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 8 | 968.58 | 2022-12-13 | 2022-12-19 | TECH3 PO E
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 8 | 1249.87 | 2022-12-13 | 2022-12-19 | PROF4 AD
S360500 | Transport Assembled TPC Sections to AH - M&S | 500 | 591.95 | 2022-12-13 | 2022-12-19 | Purch 1st $2M
S360600 | Open SC Magnet Pole Tip Doors | 4 | 643.68 | 2022-12-20 | 2022-12-20 | PROF4 PO M
S360600 | Open SC Magnet Pole Tip Doors | 16 | 1995.27 | 2022-12-20 | 2022-12-20 | TECH3 PO M
S360620 | Install TPC Installation fixtures and test | 40 | 6436.82 | 2022-12-21 | 2022-12-21 | PROF4 PO M
S360620 | Install TPC Installation fixtures and test | 40 | 4988.17 | 2022-12-21 | 2022-12-21 | TECH3 PO M
S360700 | Install TPC Support - Labor | 4 | 643.68 | 2022-12-21 | 2022-12-28 | PROF4 PO M
S360700 | Install TPC Support - Labor | 16 | 1995.27 | 2022-12-21 | 2022-12-28 | TECH3 PO D
S360700 | Install TPC Support - Labor | 80 | 9976.35 | 2022-12-21 | 2022-12-28 | TECH3 PO M
S360800 | Install TPC Support - M&S | 500 | 603.79 | 2022-12-21 | 2022-12-28 | Purch 1st $2M
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 8 | 876.1 | 2022-12-29 | 2023-01-12 | PROF2 AD
S361000 | Install TPC (Mechanical) - M&S | 500 | 603.79 | 2022-12-29 | 2023-01-12 | Purch 1st $2M
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-01-13 | 2023-01-20 | TECH3 PO M
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 10933.5 | 2023-01-13 | 2023-01-20 | CRAFT3
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 2023-01-13 | 2023-01-20 | TECH3 AD
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 8562.26 | 2023-01-13 | 2023-01-20 | TECH4 AD
S361111 | Install North and South Line Lasers | 16 | 3009.03 | 2023-01-23 | 2023-01-26 | SCI3
S361111 | Install North and South Line Lasers | 40 | 4988.17 | 2023-01-23 | 2023-01-26 | TECH3 PO M
S361111 | Install North and South Line Lasers | 40 | 4988.17 | 2023-01-23 | 2023-01-26 | TECH3 PO E
S361200 | Align/Survey TPC to SC Magnet Centerline - M&S | 500 | 603.79 | 2023-01-13 | 2023-01-20 | Purch 1st $2M
S361300 | Install TPC Cables and Services - Labor | 120 | 14964.52 | 2023-02-06 | 2023-02-27 | TECH3 PO E
S361300 | Install TPC Cables and Services - Labor | 60 | 7482.26 | 2023-02-06 | 2023-02-27 | TECH3 PO M
S361300 | Install TPC Cables and Services - Labor | 24 | 3862.09 | 2023-02-06 | 2023-02-27 | PROF4 PO M
S361300 | Install TPC Cables and Services - Labor | 24 | 2992.9 | 2023-02-06 | 2023-02-27 | TECH3 PO D
S361300 | Install TPC Cables and Services - Labor | 240 | 32800.51 | 2023-02-06 | 2023-02-27 | CRAFT3
S361400 | Install TPC Cables and Services - M&S | 500 | 603.79 | 2023-02-06 | 2023-02-27 | Purch 1st $2M
S361420 | Check TPC operation during cabling | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | SCI3
S361440 | Install TPC cooling panels and route lines | 80 | 9976.35 | 2022-12-21 | 2022-12-22 | TECH3 PO M
S361460 | Install TPC gas distribution panels and route lines | 80 | 9976.35 | 2022-12-21 | 2022-12-22 | TECH3 PO M
S361465 | Install TPC Diffuse Lasers | 12 | 2256.77 | 2023-02-28 | 2023-03-01 | SCI3
S361465 | Install TPC Diffuse Lasers | 24 | 2992.9 | 2023-02-28 | 2023-03-01 | TECH3 PO M
S361465 | Install TPC Diffuse Lasers | 24 | 2992.9 | 2023-02-28 | 2023-03-01 | TECH3 PO E
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | SCI3
S361480 | Check TPC operation with DAQ in counting house | 160 | 30090.32 | 2023-02-06 | 2023-02-27 | SCI3
S361950 | Erect 1008 IR Shield Wall | 80 | 9976.35 | 2023-02-28 | 2023-03-06 | TECH3 AD
S361950 | Erect 1008 IR Shield Wall | 80 | 9976.35 | 2023-02-28 | 2023-03-06 | TECH3 PO E
POM02-13.02.05.09 INTT Installation |  | 4032 | 208995.72 | 2022-10-03 | 2023-03-09
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 40 | 6249.34 | 2022-10-03 | 2022-10-17 | PROF4 PO M
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 20 | 2421.44 | 2022-10-03 | 2022-10-17 | TECH3 PO D
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-10-18 | 2022-10-31 | PROF4 PO M
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-18 | 2022-10-31 | TECH3 PO M
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-18 | 2022-10-31 | TECH3 PO D
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 1249.87 | 2022-11-01 | 2022-11-15 | PROF4 PO M
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 968.58 | 2022-11-01 | 2022-11-15 | TECH3 PO M
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 8 | 968.58 | 2022-11-01 | 2022-11-15 | TECH3 PO D
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 1287.36 | 2023-02-06 | 2023-02-07 | PROF4 PO M
S362800 | Transport Assembled INTT Sections to AH - Labor | 24 | 2992.9 | 2023-02-06 | 2023-02-07 | TECH3 PO M
S362800 | Transport Assembled INTT Sections to AH - Labor | 8 | 997.63 | 2023-02-06 | 2023-02-07 | TECH3 PO E
S362900 | Transport Assembled INTT Sections to AH - M&S | 500 | 603.79 | 2023-02-06 | 2023-02-07 | Purch 1st $2M
S362920 | Install INTT Installation fixtures and test | 20 | 2764.81 | 2023-02-06 | 2023-02-07 | PROF3 PO M
S362920 | Install INTT Installation fixtures and test | 20 | 2494.09 | 2023-02-06 | 2023-02-07 | TECH3 PO M
S363000 | Install INTT Support - Labor | 8 | 1287.36 | 2023-02-08 | 2023-02-17 | PROF4 PO M
S363000 | Install INTT Support - Labor | 8 | 997.63 | 2023-02-08 | 2023-02-17 | TECH3 PO D
S363000 | Install INTT Support - Labor | 60 | 7482.26 | 2023-02-08 | 2023-02-17 | TECH3 PO M
S363100 | Install INTT Support - M&S | 500 | 603.79 | 2023-02-08 | 2023-02-17 | Purch 1st $2M
S363120 | Install Beampipe | 40 | 4988.17 | 2023-02-21 | 2023-02-21 | TECH3 AD
S363140 | Install Beampipe vacuum system | 40 | 4988.17 | 2023-02-22 | 2023-02-22 | TECH3 AD
S363160 | Pump down beampipe | 40 | 4988.17 | 2023-02-23 | 2023-02-23 | TECH3 AD
S363180 | Perform Beampipe Bakeout | 80 | 9976.35 | 2023-02-24 | 2023-03-02 | TECH3 AD
S363200 | Install INTT (mechanical) - Labor | 8 | 1287.36 | 2023-02-21 | 2023-03-02 | PROF4 PO M
S363200 | Install INTT (mechanical) - Labor | 8 | 997.63 | 2023-02-21 | 2023-03-02 | TECH3 PO D
S363200 | Install INTT (mechanical) - Labor | 60 | 7482.26 | 2023-02-21 | 2023-03-02 | TECH3 PO M
S363300 | Install INTT (mechanical) - M&S | 500 | 603.79 | 2023-02-21 | 2023-03-02 | Purch 1st $2M
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-02-21 | 2023-03-02 | TECH3 PO M
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 80 | 9976.35 | 2023-02-21 | 2023-03-02 | TECH3 AD
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 60 | 7482.26 | 2023-02-21 | 2023-03-02 | TECH3 AD
S363500 | Align/Survey INTT to SC Magnet Centerline - M&S | 500 | 603.79 | 2023-02-21 | 2023-03-02 | Purch 1st $2M
S363520 | Install beampipe permanent support | 40 | 4988.17 | 2023-03-03 | 2023-03-03 | TECH3 AD
S363540 | Remove beampipe Temporary Support | 40 | 4988.17 | 2023-03-06 | 2023-03-06 | TECH3 AD
S363600 | Install INTT Cables and Services - Labor | 120 | 14964.52 | 2023-03-03 | 2023-03-09 | TECH3 PO E
S363600 | Install INTT Cables and Services - Labor | 120 | 14964.52 | 2023-03-03 | 2023-03-09 | TECH3 PO M
S363600 | Install INTT Cables and Services - Labor | 24 | 3862.09 | 2023-03-03 | 2023-03-09 | PROF4 PO E
S363600 | Install INTT Cables and Services - Labor | 24 | 3862.09 | 2023-03-03 | 2023-03-09 | PROF4 PO M
S363600 | Install INTT Cables and Services - Labor | 24 | 2992.9 | 2023-03-03 | 2023-03-09 | TECH3 PO D
S363600 | Install INTT Cables and Services - Labor | 240 | 32800.51 | 2023-03-03 | 2023-03-09 | CRAFT3
S363700 | Install INTT Cables and Services - M&S | 500 | 603.79 | 2023-03-03 | 2023-03-09 | Purch 1st $2M
S363720 | Check INTT operation during cabling | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | SCI3
S363740 | Install INTT cooling panels and route lines | 40 | 4988.17 | 2023-03-07 | 2023-03-07 | TECH3 PO M
S363760 | Install INTT gas distribution panels and route lines | 40 | 4988.17 | 2023-03-07 | 2023-03-07 | TECH3 PO M
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | SCI3
S363780 | Check INTT operation with DAQ in counting house | 40 | 7522.58 | 2023-03-03 | 2023-03-09 | SCI3
POM02-13.02.05.10 MVTX Installation |  | 2922 | 195130.32 | 29-Apr-21 A | 2023-03-22
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 29-Apr-21 A | 2022-10-28 | PROF4 PO M
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 10 | 1175.46 | 29-Apr-21 A | 2022-10-28 | TECH3 PO D
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 26-Jul-22 A | 2022-11-14 | PROF4 PO M
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 26-Jul-22 A | 2022-11-14 | TECH3 PO D
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 26-Jul-22 A | 2022-11-14 | TECH3 PO M
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-11-15 | 2022-11-30 | PROF4 PO M
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | TECH3 PO D
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | TECH3 PO M
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 1249.87 | 2022-12-09 | 2022-12-15 | PROF4 PO M
S365300 | Transport Assembled MVTX Sections to IR - Labor | 24 | 2905.73 | 2022-12-09 | 2022-12-15 | TECH3 PO M
S365300 | Transport Assembled MVTX Sections to IR - Labor | 8 | 968.58 | 2022-12-09 | 2022-12-15 | TECH3 PO E
S365400 | Transport Assembled MVTX Sections to IR - M&S | 500 | 591.95 | 2022-12-09 | 2022-12-15 | Purch 1st $2M
S365450 | Install MVTX Installation fixtures and test | 40 | 4988.17 | 2022-12-09 | 2022-12-09 | TECH3 PO M
S365500 | Install MVTX Support - Labor | 8 | 1287.36 | 2023-03-09 | 2023-03-09 | PROF4 PO M
S365500 | Install MVTX Support - Labor | 8 | 997.63 | 2023-03-09 | 2023-03-09 | TECH3 PO D
S365500 | Install MVTX Support - Labor | 60 | 7482.26 | 2023-03-09 | 2023-03-09 | TECH3 PO M
S365600 | Install MVTX Support - M&S | 500 | 603.79 | 2023-03-09 | 2023-03-09 | Purch 1st $2M
S365700 | Install FELIX | 16 | 2211.85 | 2023-03-10 | 2023-03-13 | PROF3 IO E
S365900 | Install Optical fibers | 40 | 4988.17 | 2023-03-10 | 2023-03-13 | TECH3 PO E
S366000 | Install RU | 40 | 5529.62 | 2023-03-10 | 2023-03-13 | PROF3 IO E
S366200 | Install Samtec Cables | 40 | 4988.17 | 2023-03-10 | 2023-03-10 | TECH3 PO E
S366300 | Install Half-Barrel 1 | 80 | 11059.23 | 2023-03-13 | 2023-03-14 | PROF3 PO M
S366300 | Install Half-Barrel 1 | 80 | 9976.35 | 2023-03-13 | 2023-03-14 | TECH3 PO M
S366500 | Install Half-Barrel 2 | 80 | 9976.35 | 2023-03-15 | 2023-03-16 | TECH3 PO M
S366500 | Install Half-Barrel 2 | 80 | 11059.23 | 2023-03-15 | 2023-03-16 | PROF3 PO M
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 40 | 4988.17 | 2023-03-17 | 2023-03-20 | TECH3 AD
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9976.35 | 2023-03-20 | 2023-03-21 | TECH3 PO M
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3862.09 | 2023-03-20 | 2023-03-21 | PROF4 PO E
S366900 | Install MVTX Remaining Cables and Services - Labor | 80 | 9976.35 | 2023-03-20 | 2023-03-21 | TECH3 PO E
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 2992.9 | 2023-03-20 | 2023-03-21 | TECH3 PO D
S366900 | Install MVTX Remaining Cables and Services - Labor | 24 | 3862.09 | 2023-03-20 | 2023-03-21 | PROF4 PO M
S366900 | Install MVTX Remaining Cables and Services - Labor | 160 | 21867.01 | 2023-03-20 | 2023-03-21 | CRAFT3
S367000 | Install MVTX Remaining Cables and Services - M&S | 500 | 603.79 | 2023-03-20 | 2023-03-21 | Purch 1st $2M
S367010 | Check MVTX operation during cabling | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | SCI3
S367020 | Install MVTX cooling panels and route lines | 120 | 14964.52 | 2023-03-20 | 2023-03-21 | TECH3 PO M
S367030 | Install MVTX gas distribution panels and route lines | 40 | 4988.17 | 2023-03-20 | 2023-03-21 | TECH3 PO M
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | SCI3
S367050 | Check MVTX operation with DAQ in counting house | 40 | 7522.58 | 2023-03-20 | 2023-03-22 | SCI3
POM02-13.02.05.11 Min Bias Installation |  | 12998 | 157174.37 | 29-Apr-21 A | 2023-03-29
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 30 | 4724.5 | 01-Jul-22 A | 2022-10-25 | PROF4 PO M
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1220.41 | 01-Jul-22 A | 2022-10-25 | TECH3 PO D
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 10 | 1220.41 | 01-Jul-22 A | 2022-10-25 | TECH3 PO M
S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - M&S | 10000 | 11838.98 | 01-Jul-22 A | 2022-10-25 | Purch 1st $2M
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 40 | 6067.32 | 29-Apr-21 A | 2022-10-28 | PROF4 PO M
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 20 | 2350.92 | 29-Apr-21 A | 2022-10-28 | TECH3 PO D
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 1249.87 | 2022-10-31 | 2022-11-14 | PROF4 PO M
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-31 | 2022-11-14 | TECH3 PO D
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 8 | 968.58 | 2022-10-31 | 2022-11-14 | TECH3 PO M
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 1249.87 | 2022-11-15 | 2022-11-30 | PROF4 PO M
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | TECH3 PO D
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 8 | 968.58 | 2022-11-15 | 2022-11-30 | TECH3 PO M
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 1287.36 | 2023-03-13 | 2023-03-13 | PROF4 PO M
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 8 | 997.63 | 2023-03-13 | 2023-03-13 | TECH3 PO M
S368600 | Transport Assembled Min Bias Sections to AH - M&S | 500 | 603.79 | 2023-03-13 | 2023-03-13 | Purch 1st $2M
S368650 | Install MBD Installation fixtures and test | 10 | 1382.4 | 2023-03-14 | 2023-03-14 | PROF3 PO M
S368650 | Install MBD Installation fixtures and test | 10 | 1247.04 | 2023-03-14 | 2023-03-14 | TECH3 PO M
S368700 | Install Min Bias Support - Labor | 8 | 1287.36 | 2023-03-14 | 2023-03-14 | PROF4 PO M
S368700 | Install Min Bias Support - Labor | 8 | 997.63 | 2023-03-14 | 2023-03-14 | TECH3 PO D
S368700 | Install Min Bias Support - Labor | 16 | 1995.27 | 2023-03-14 | 2023-03-14 | TECH3 PO M
S368800 | Install Min Bias Support - M&S | 500 | 603.79 | 2023-03-14 | 2023-03-14 | Purch 1st $2M
S368900 | Install Min Bias (mechanical) - Labor | 8 | 1287.36 | 2023-03-15 | 2023-03-15 | PROF4 PO M
S368900 | Install Min Bias (mechanical) - Labor | 8 | 997.63 | 2023-03-15 | 2023-03-15 | TECH3 PO D
S368900 | Install Min Bias (mechanical) - Labor | 16 | 1995.27 | 2023-03-15 | 2023-03-15 | TECH3 PO M
S369000 | Install Min Bias (mechanical) - M&S | 500 | 603.79 | 2023-03-15 | 2023-03-15 | Purch 1st $2M
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-22 | TECH3 PO M
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-22 | TECH3 AD
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-17 | TECH3 AD
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 20 | 2494.09 | 2023-03-16 | 2023-03-20 | TECH3 PO M
S369300 | Install Min Bias Cables and Services - Labor | 40 | 4988.17 | 2023-03-23 | 2023-03-23 | TECH3 PO E
S369300 | Install Min Bias Cables and Services - Labor | 40 | 4988.17 | 2023-03-23 | 2023-03-23 | TECH3 PO M
S369400 | Install Min Bias Cables and Services - M&S | 500 | 603.79 | 2023-03-23 | 2023-03-23 | Purch 1st $2M
S369450 | Check MBD operation during cabling | 40 | 7522.58 | 2023-03-23 | 2023-03-23 | SCI3
S369460 | Install MBD cooling panels and route lines | 40 | 4988.17 | 2023-03-24 | 2023-03-24 | TECH3 PO M
S369470 | Install MBD gas distribution panels and route lines | 40 | 4988.17 | 2023-03-24 | 2023-03-24 | TECH3 PO M
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2023-03-23 | 2023-03-29 | SCI3
S369490 | Check MBD operation with DAQ in counting house | 40 | 7522.58 | 2023-03-23 | 2023-03-29 | SCI3
S370105 | Install MBD cooling panels and route lines | 40 | 4988.17 | 2023-03-14 | 2023-03-14 | TECH3 PO M
S370120 | Install sEPD Installation fixtures and test | 40 | 4988.17 | 2023-03-15 | 2023-03-15 | TECH3 PO M
S370140 | Install sEPD support system | 40 | 4988.17 | 2023-03-15 | 2023-03-15 | TECH3 PO M
S370160 | Install sEPD | 40 | 4988.17 | 2023-03-16 | 2023-03-16 | TECH3 PO M
S370180 | Align sEPD | 40 | 4988.17 | 2023-03-17 | 2023-03-17 | TECH3 PO M
S370180 | Align sEPD | 20 | 2494.09 | 2023-03-17 | 2023-03-17 | TECH3 AD
S370205 | Install sEPD cables - LV, bias, signal, control | 20 | 2494.09 | 2023-03-20 | 2023-03-20 | TECH3 PO M
S370205 | Install sEPD cables - LV, bias, signal, control | 20 | 2494.09 | 2023-03-20 | 2023-03-20 | TECH3 PO E
S370220 | Check sEPD operation during cabling | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | SCI3
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | SCI3
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 40 | 7522.58 | 2022-10-03 | 2022-10-07 | SCI3
POM02-13.02.05.12 Full System Integration and ORR |  | 1592 | 270974.3 | 2022-10-03 | 2023-01-31
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249.34 | 2022-10-03 | 2022-10-31 | PROF4 PO M
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 6249.34 | 2022-10-03 | 2022-10-31 | PROF4 PO E
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 7303.48 | 2022-10-03 | 2022-10-31 | SCI3 PO
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 40 | 8737.89 | 2022-10-03 | 2022-10-31 | SCI4 PO
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1249.87 | 2022-11-01 | 2022-11-03 | PROF4 PO M
S370510 | Review of Safety System Design by CAD ESRC | 8 | 1249.87 | 2022-11-01 | 2022-11-03 | PROF4 PO E
S370510 | Review of Safety System Design by CAD ESRC | 24 | 5242.73 | 2022-11-01 | 2022-11-03 | SCI4 PO
S370510 | Review of Safety System Design by CAD ESRC | 24 | 4382.09 | 2022-11-01 | 2022-11-03 | SCI3 PO
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249.34 | 2022-11-04 | 2022-12-06 | PROF4 PO M
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 6249.34 | 2022-11-04 | 2022-12-06 | PROF4 PO E
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 7303.48 | 2022-11-04 | 2022-12-06 | SCI3 PO
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 40 | 8737.89 | 2022-11-04 | 2022-12-06 | SCI4 PO
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3608.4 | 2022-11-04 | 2022-12-06 | PROF5 AD
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 4094.92 | 2022-11-04 | 2022-12-06 | PROF6 AD
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 2126.45 | 2022-11-04 | 2022-12-06 | PROF2 AD
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 20 | 3124.67 | 2022-11-04 | 2022-12-06 | PROF4 AD
S370530 | Review and approve procedures | 16 | 2499.74 | 2022-12-07 | 2022-12-08 | PROF4 PO M
S370530 | Review and approve procedures | 16 | 2499.74 | 2022-12-07 | 2022-12-08 | PROF4 PO E
S370530 | Review and approve procedures | 16 | 2921.39 | 2022-12-07 | 2022-12-08 | SCI3 PO
S370530 | Review and approve procedures | 16 | 3495.16 | 2022-12-07 | 2022-12-08 | SCI4 PO
S370530 | Review and approve procedures | 16 | 2886.72 | 2022-12-07 | 2022-12-08 | PROF5 AD
S370530 | Review and approve procedures | 16 | 3275.94 | 2022-12-07 | 2022-12-08 | PROF6 AD
S370540 | Magnet Checkout After Power Testing | 16 | 2921.39 | 2022-12-09 | 2022-12-15 | SCI3 AD
S370540 | Magnet Checkout After Power Testing | 16 | 3275.94 | 2022-12-09 | 2022-12-15 | PROF6 AD
S370540 | Magnet Checkout After Power Testing | 16 | 2886.72 | 2022-12-09 | 2022-12-15 | PROF5 AD
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 2905.73 | 2022-12-16 | 2022-12-22 | TECH3 PO E
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 3749.6 | 2022-12-16 | 2022-12-22 | PROF4 PO E
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 24 | 5242.73 | 2022-12-16 | 2022-12-22 | SCI4 PO
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2921.39 | 2022-12-23 | 2023-01-09 | SCI3 AD
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 2886.72 | 2022-12-23 | 2023-01-09 | PROF5 AD
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 16 | 3275.94 | 2022-12-23 | 2023-01-09 | PROF6 AD
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2499.74 | 2023-01-10 | 2023-01-17 | PROF4 PO M
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937.15 | 2023-01-10 | 2023-01-17 | TECH3 PO E
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 1937.15 | 2023-01-10 | 2023-01-17 | TECH3 PO M
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 2499.74 | 2023-01-10 | 2023-01-17 | PROF4 PO E
S370570 | Preparation for Full Operation - Verify Global Safety System | 16 | 3495.16 | 2023-01-10 | 2023-01-17 | SCI4 PO
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2499.74 | 2023-01-18 | 2023-01-24 | PROF4 PO M
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937.15 | 2023-01-18 | 2023-01-24 | TECH3 PO E
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 1937.15 | 2023-01-18 | 2023-01-24 | TECH3 PO M
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2499.74 | 2023-01-18 | 2023-01-24 | PROF4 PO E
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 3495.16 | 2023-01-18 | 2023-01-24 | SCI4 PO
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 16 | 2921.39 | 2023-01-18 | 2023-01-24 | SCI3 PO
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1460.7 | 2023-01-18 | 2023-01-24 | SCI3 AD
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1249.87 | 2023-01-18 | 2023-01-24 | PROF4 AD
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1249.87 | 2023-01-18 | 2023-01-24 | PROF4 AD
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 8 | 1637.97 | 2023-01-18 | 2023-01-24 | PROF6 AD
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 16 | 3495.16 | 2023-01-25 | 2023-01-31 | SCI4 PO
S370595 | Prepare for sPHENIX IRR | 160 | 30090.32 | 2022-11-01 | 2023-01-31 | SCI3
S370595 | Prepare for sPHENIX IRR | 160 | 22118.46 | 2022-11-01 | 2023-01-31 | PROF3 PO M
S370597 | Prepare for sPHENIX ARR | 160 | 22118.46 | 2022-11-01 | 2023-01-31 | PROF3 PO M
S370597 | Prepare for sPHENIX ARR | 160 | 30090.32 | 2022-11-01 | 2023-01-31 | SCI3

## Timephased Schedule (hidden)
Activity ID | Activity Name | Start | Finish | Resource ID | Resource Name | Budgeted Units | Remaining Units | BNL_Fund Source | Spreadsheet Field | FY20 | FY21 | FY22 | FY23
POM02-13 POM02 sPHENIX WBS 1.x, 2.x October 2022- with Resources |  | 01-Oct-19 A | 2023-03-29 |  |  | 123278 | 30434 |  | Budgeted Units | 24609 | 31108 | 36477 | 31085
POM02-13.02 Infrastructure/Facility |  | 01-Oct-19 A | 2023-03-29 |  |  | 123278 | 30434 |  | Budgeted Units | 24609 | 31108 | 36477 | 31085
POM02-13.02.01 Infrastructure/Facility Management |  | 01-Oct-19 A | 2022-10-07 |  |  | 16078 | 435 |  | Budgeted Units | 6258 | 6084 | 3132 | 604
POM02-13.02.01.02 Magnet Management and Technical Oversight |  | 01-Oct-19 A | 30-Sep-22 A |  |  | 4283 | 0 |  | Budgeted Units | 1584 | 1467 | 1162 | 70
S275700 | 2020 PS & Quench Protection L3 Project Management | 01-Oct-19 A | 30-Sep-20 A | PROF5 AD | PROF5 AD | 352 | 0 | C | Budgeted Units | 352 | 0
S275800 | 2021 PS & Quench Protection L3 Project Management | 01-Oct-20 A | 30-Sep-21 A | PROF5 AD | PROF5 AD | 352 | 0 | C | Budgeted Units |  | 352
S275900 | 2022 PS & Quench Protection L3 Project Management | 01-Oct-21 A | 30-Sep-22 A | PROF5 AD | PROF5 AD | 352 | 0 | C | Budgeted Units |  |  | 352
S275200 | 2020 Cryo L3 Project Management | 01-Oct-19 A | 30-Sep-20 A | PROF6 AD | PROF6 AD | 352 | 0 | C | Budgeted Units | 352 | 0
S275300 | 2021 Cryo L3 Project Management | 01-Oct-20 A | 31-May-21 A | PROF6 AD | PROF6 AD | 235 | 0 | C | Budgeted Units |  | 235
S274600 | 2020 Magnet Project Management | 01-Oct-19 A | 30-Sep-20 A | SCI3 AD | SCI3 AD | 880 | 0 | C | Budgeted Units | 880
S274700 | 2021 Magnet Project Management | 01-Oct-20 A | 30-Sep-21 A | SCI3 AD | SCI3 AD | 880 | 0 | C | Budgeted Units |  | 880
S274800 | 2022 Magnet Project Management | 01-Oct-21 A | 30-Sep-22 A | SCI3 AD | SCI3 AD | 880 | 0 | C | Budgeted Units |  |  | 810 | 70
POM02-13.02.01.04 Infrastructure Management |  | 01-Oct-19 A | 2022-10-07 |  |  | 7113 | 153 |  | Budgeted Units | 2914 | 2864 | 1153 | 181
S276800 | 2020 Facility Support Systems L3 Project Management | 01-Oct-19 A | 30-Sep-20 A | PROF2 AD | PROF2 AD | 352 | 0 | C | Budgeted Units | 352 | 0
S276900 | 2021 Facility Support Systems L3 Project Management | 01-Oct-20 A | 30-Sep-21 A | PROF2 AD | PROF2 AD | 352 | 0 | C | Budgeted Units |  | 322 | 30
S277000 | 2022 Facility Support Systems L3 Project Management | 01-Oct-21 A | 30-Sep-22 A | PROF2 AD | PROF2 AD | 352 | 0 | C | Budgeted Units |  |  | 324 | 28
S277100 | 2023 Facility Support Systems L3 Project Management | 2022-10-03 | 2022-10-07 | PROF2 AD | PROF2 AD | 113 | 113 | C | Budgeted Units |  |  |  | 113
S277400 | 2020 Detector Support Systems L3 Project Management | 01-Oct-19 A | 30-Sep-20 A | PROF5 PO M | PROF5 PO M | 352 | 0 | C | Budgeted Units | 352 | 0
S277400 | 2020 Detector Support Systems L3 Project Management | 01-Oct-19 A | 30-Sep-20 A | PROF4 PO E | PROF4 PO E | 440 | 0 | C | Budgeted Units | 440
S277500 | 2021 Detector Support Systems L3 Project Management | 01-Oct-20 A | 30-Sep-21 A | PROF5 PO M | PROF5 PO M | 352 | 0 | C | Budgeted Units |  | 352
S277500 | 2021 Detector Support Systems L3 Project Management | 01-Oct-20 A | 30-Sep-21 A | PROF4 PO E | PROF4 PO E | 440 | 0 | C | Budgeted Units |  | 440
S276200 | 2020 Infrastructure Project Management | 01-Oct-19 A | 30-Sep-20 A | PM Spec - PS | Project Mgmt Specialist - Purchased Services | 890 | 0 | C | Budgeted Units | 890
S276300 | 2021 Infrastructure Project Management | 01-Oct-20 A | 30-Sep-21 A | PM Spec - PS | Project Mgmt Specialist - Purchased Services | 890 | 0 | C | Budgeted Units |  | 890
S276200 | 2020 Infrastructure Project Management | 01-Oct-19 A | 30-Sep-20 A | PROF3 PO E | PROF3 PO E | 880 | 0 | C | Budgeted Units | 880
S276300 | 2021 Infrastructure Project Management | 01-Oct-20 A | 30-Sep-21 A | PROF3 PO E | PROF3 PO E | 860 | 0 | C | Budgeted Units |  | 860
S276400 | 2022 Infrastructure Project Management | 01-Oct-21 A | 30-Sep-22 A | PROF3 PO E | PROF3 PO E | 800 | 0 | C | Budgeted Units |  |  | 800
S276500 | 2023 Infrastructure Project Management | 2022-10-03 | 2022-10-07 | PROF3 PO E | PROF3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
POM02-13.02.01.05 Installation Management |  | 01-Oct-19 A | 2022-10-05 |  |  | 4682 | 282 |  | Budgeted Units | 1760 | 1753 | 817 | 352
S278000 | 2020 Integration & Installation Project Management | 01-Oct-19 A | 30-Sep-20 A | PROF5 PO M | PROF5 PO M | 880 | 0 | C | Budgeted Units | 880
S278000 | 2020 Integration & Installation Project Management | 01-Oct-19 A | 30-Sep-20 A | PROF3 PO E | PROF3 PO E | 440 | 0 | C | Budgeted Units | 440
S278000 | 2020 Integration & Installation Project Management | 01-Oct-19 A | 30-Sep-20 A | SCI3 PO | SCI3 PO | 440 | 0 | C | Budgeted Units | 440
S278100 | 2021 Integration & Installation Project Management | 02-Oct-20 A | 30-Sep-21 A | PROF5 PO M | PROF5 PO M | 880 | 0 | C | Budgeted Units |  | 876 | 4
S278100 | 2021 Integration & Installation Project Management | 02-Oct-20 A | 30-Sep-21 A | PROF3 PO E | PROF3 PO E | 440 | 0 | C | Budgeted Units |  | 438 | 2
S278100 | 2021 Integration & Installation Project Management | 02-Oct-20 A | 30-Sep-21 A | SCI3 PO | SCI3 PO | 440 | 0 | C | Budgeted Units |  | 438 | 2
S278200 | 2022 Integration & Installation Project Management | 01-Oct-21 A | 30-Sep-22 A | PROF5 PO M | PROF5 PO M | 880 | 0 | C | Budgeted Units |  |  | 810 | 70
S278300 | 2023 Integration & Installation Project Management | 2022-10-03 | 2022-10-05 | PROF5 PO M | PROF5 PO M | 282 | 282 | C | Budgeted Units |  |  |  | 282
POM02-13.02.02 SC Magnet |  | 01-Oct-19 A | 2023-01-17 |  |  | 19071 | 2258 |  | Budgeted Units | 3921 | 6728 | 5980 | 2442
POM02-13.02.02.01 Safety Reviews, Cooldown, Power Tests |  | 08-Mar-21 A | 2022-10-27 |  |  | 836 | 731 |  | Budgeted Units |  |  | 80 | 756
POM02-13.02.02.01.01 Safety Reviews |  | 08-Mar-21 A | 2022-10-07 |  |  | 112 | 16 |  | Budgeted Units |  |  | 80 | 32
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 08-Mar-21 A | 19-Apr-22 A | PROF6 AD | PROF6 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S278900 | LESHC Review Magnet Overall System Safety Review | 15-Sep-22 A | 15-Sep-22 A | PROF6 AD | PROF6 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S279000 | ASSRC REVIEW and Full Walkthrough | 16-Sep-22 A | 2022-10-07 | PROF6 AD | PROF6 AD | 16 | 8 | C | Budgeted Units |  |  |  | 16
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 08-Mar-21 A | 19-Apr-22 A | SCI3 AD | SCI3 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S278900 | LESHC Review Magnet Overall System Safety Review | 15-Sep-22 A | 15-Sep-22 A | SCI3 AD | SCI3 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S279000 | ASSRC REVIEW and Full Walkthrough | 16-Sep-22 A | 2022-10-07 | SCI3 AD | SCI3 AD | 16 | 8 | C | Budgeted Units |  |  |  | 16
S278800 | LESHC-PSSC Review Cryogenic Safety Review | 08-Mar-21 A | 19-Apr-22 A | PROF4 AM | PROF4 AM | 8 | 0 | C | Budgeted Units |  |  | 8
S278900 | LESHC Review Magnet Overall System Safety Review | 15-Sep-22 A | 15-Sep-22 A | PROF4 AM | PROF4 AM | 8 | 0 | C | Budgeted Units |  |  | 8
POM02-13.02.02.01.02 Cooldown & Power Tests |  | 17-Aug-22 A | 2022-10-27 |  |  | 724 | 715 |  | Budgeted Units |  |  |  | 724
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | PROF3 AD | PROF3 AD | 60 | 57 | C | Budgeted Units |  |  |  | 60
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | PROF3 AD | PROF3 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | PROF3 AD | PROF3 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | PROF3 AD | PROF3 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | TECH3 AD | TECH3 AD | 60 | 57 | C | Budgeted Units |  |  |  | 60
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | TECH3 AD | TECH3 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | PROF6 AD | PROF6 AD | 60 | 57 | C | Budgeted Units |  |  |  | 60
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | PROF6 AD | PROF6 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | PROF6 AD | PROF6 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | PROF6 AD | PROF6 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | SCI3 AD | SCI3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | SCI3 AD | SCI3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
POM02-13.02.02.02 Magnet Transport & Assembly |  | 01-Oct-19 A | 29-Jul-22 A |  |  | 792 | 0 |  | Budgeted Units | 176 |  | 616
S281200 | Magnet - Prepare for Coil Shipment - Shipping Constraints and Tooling | 01-Oct-19 A | 30-Dec-19 A | TECH3 AM | TECH3 AM | 160 | 0 | C | Budgeted Units | 160
S281200 | Magnet - Prepare for Coil Shipment - Shipping Constraints and Tooling | 01-Oct-19 A | 30-Dec-19 A | PROF4 AM | PROF4 AM | 16 | 0 | C | Budgeted Units | 16
S281400 | Magnet and Solenoid Valvebox - Reinstall | 01-Jul-22 A | 22-Jul-22 A | TECH3 AM | TECH3 AM | 400 | 0 | C | Budgeted Units |  |  | 400
S281400 | Magnet and Solenoid Valvebox - Reinstall | 01-Jul-22 A | 22-Jul-22 A | PROF4 AM | PROF4 AM | 40 | 0 | C | Budgeted Units |  |  | 40
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | 25-Jul-22 A | 29-Jul-22 A | TECH3 AM | TECH3 AM | 160 | 0 | C | Budgeted Units |  |  | 160
S281500 | Magnet - Readjust Coil and Remove Shipping Tooling | 25-Jul-22 A | 29-Jul-22 A | PROF4 AM | PROF4 AM | 16 | 0 | C | Budgeted Units |  |  | 16
POM02-13.02.02.03 Magnet Cryogenic Systems |  | 01-Oct-19 A | 14-Sep-22 A |  |  | 11090 | 0 |  | Budgeted Units | 2483 | 4726 | 3617 | 264
POM02-13.02.02.03.01 Helium System: 1008BColdbox, Transferlines, & IR8 Coldbox |  | 18-Nov-19 A | 29-Jul-22 A |  |  | 3193 | 0 |  | Budgeted Units | 501 | 1802 | 890
POM02-13.02.02.03.01.04 Vendor Manufacturing - Helium System: 1008B Coldbox, Transferlines, & IR8 Coldbox |  | 18-Nov-19 A | 29-Jul-22 A |  |  | 501 | 0 |  | Budgeted Units | 501
POM02-13.02.02.03.01.04.04 Vendor Engineering and Design |  | 18-Nov-19 A | 29-Jul-22 A |  |  | 501 | 0 |  | Budgeted Units | 501
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 02-Dec-19 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 54 | 0 | C | Budgeted Units | 54
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 02-Dec-19 A | 29-Jul-22 A | PROF3 AD | PROF3 AD | 240 | 0 | C | Budgeted Units | 240
S284200 | Procure RHIC Helium Interface, MS1 (Manufacturing Program Plan) - Leadtime | 18-Nov-19 A | 25-Nov-19 A | PROF3 AD | PROF3 AD | 0 | 0 | C | Budgeted Units
S284100 | RHIC Helium Interface - Engineering supervision by BNL | 02-Dec-19 A | 29-Jul-22 A | PROF6 AD | PROF6 AD | 207 | 0 | C | Budgeted Units | 207
S284200 | Procure RHIC Helium Interface, MS1 (Manufacturing Program Plan) - Leadtime | 18-Nov-19 A | 25-Nov-19 A | PROF6 AD | PROF6 AD | 0 | 0 | C | Budgeted Units
POM02-13.02.02.03.01.06 Installation |  | 22-Sep-20 A | 26-Oct-21 A |  |  | 2692 | 0 |  | Budgeted Units |  | 1802 | 890
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 01-Jul-21 A | 30-Aug-21 A | PROF3 AD | PROF3 AD | 20 | 0 | C | Budgeted Units |  | 20
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 31-Aug-21 A | 26-Oct-21 A | PROF3 AD | PROF3 AD | 24 | 0 | C | Budgeted Units |  | 9 | 15
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | 04-Oct-21 A | 26-Oct-21 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units |  |  | 12
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | 04-Oct-21 A | 26-Oct-21 A | PROF3 AD | PROF3 AD | 80 | 0 | C | Budgeted Units |  |  | 80
S287600 | RHIC Helium Interface - Final pump and purge | 04-Oct-21 A | 26-Oct-21 A | PROF3 AD | PROF3 AD | 24 | 0 | C | Budgeted Units |  |  | 24
S287000 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Rigging in place | 22-Sep-20 A | 12-Nov-20 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units |  | 8
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | 13-Oct-20 A | 29-Dec-20 A | PROF3 AD | PROF3 AD | 40 | 0 | C | Budgeted Units |  | 40
S287200 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: Rigging in place | 22-Sep-20 A | 31-Dec-20 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units |  | 8
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | 04-Nov-20 A | 31-Dec-20 A | PROF3 AD | PROF3 AD | 40 | 0 | C | Budgeted Units |  | 40
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 01-Jul-21 A | 30-Aug-21 A | TECH3 AD | TECH3 AD | 20 | 0 | C | Budgeted Units |  | 20
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 31-Aug-21 A | 26-Oct-21 A | TECH3 AD | TECH3 AD | 360 | 0 | C | Budgeted Units |  | 132 | 228
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | 04-Oct-21 A | 26-Oct-21 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  |  | 40
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | 04-Oct-21 A | 26-Oct-21 A | TECH3 AD | TECH3 AD | 120 | 0 | C | Budgeted Units |  |  | 120
S287600 | RHIC Helium Interface - Final pump and purge | 04-Oct-21 A | 26-Oct-21 A | TECH3 AD | TECH3 AD | 120 | 0 | C | Budgeted Units |  |  | 120
S287000 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Rigging in place | 22-Sep-20 A | 12-Nov-20 A | TECH3 AD | TECH3 AD | 120 | 0 | C | Budgeted Units |  | 120
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | 13-Oct-20 A | 29-Dec-20 A | TECH3 AD | TECH3 AD | 320 | 0 | C | Budgeted Units |  | 320
S287200 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: Rigging in place | 22-Sep-20 A | 31-Dec-20 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  | 80
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | 04-Nov-20 A | 31-Dec-20 A | TECH3 AD | TECH3 AD | 320 | 0 | C | Budgeted Units |  | 320
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 31-Aug-21 A | 26-Oct-21 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  | 15 | 25
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | 13-Oct-20 A | 29-Dec-20 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  | 80
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | 04-Nov-20 A | 31-Dec-20 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  | 40
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 01-Jul-21 A | 30-Aug-21 A | PROF6 AD | PROF6 AD | 8 | 0 | C | Budgeted Units |  | 8
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 31-Aug-21 A | 26-Oct-21 A | PROF6 AD | PROF6 AD | 24 | 0 | C | Budgeted Units |  | 9 | 15
S287400 | (Helium System: 1008B Coldbox/Transfer lines / IR8 Coldbox) Installation/Rigging of IR8 Coldbox | 04-Oct-21 A | 26-Oct-21 A | PROF6 AD | PROF6 AD | 12 | 0 | C | Budgeted Units |  |  | 12
S287500 | RHIC Helium Interface - Final Bayonet jumpers lines install, pressure & leak check and valve check out | 04-Oct-21 A | 26-Oct-21 A | PROF6 AD | PROF6 AD | 80 | 0 | C | Budgeted Units |  |  | 80
S287600 | RHIC Helium Interface - Final pump and purge | 04-Oct-21 A | 26-Oct-21 A | PROF6 AD | PROF6 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | 04-Nov-20 A | 31-Dec-20 A | PROF6 AD | PROF6 AD | 8 | 0 | C | Budgeted Units |  | 8
S286800 | Helium System 1008B Coldbox INSTALLATION: Rigging | 01-Jul-21 A | 30-Aug-21 A | CRAFT3 | CRAFT3 | 40 | 0 | C | Budgeted Units |  | 40
S286900 | Helium System 1008B Coldbox INSTALLATION: Field Joint Welding and leak checking | 31-Aug-21 A | 26-Oct-21 A | CRAFT3 | CRAFT3 | 180 | 0 | C | Budgeted Units |  | 66 | 114
S287000 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Rigging in place | 22-Sep-20 A | 12-Nov-20 A | CRAFT3 | CRAFT3 | 80 | 0 | C | Budgeted Units |  | 80
S287100 | Helium System: Transfer lines BETWEEN 1008B and IR8 Hall INSTALLATION: Field Joint welding | 13-Oct-20 A | 29-Dec-20 A | CRAFT3 | CRAFT3 | 160 | 0 | C | Budgeted Units |  | 160
S287200 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: Rigging in place | 22-Sep-20 A | 31-Dec-20 A | CRAFT3 | CRAFT3 | 20 | 0 | C | Budgeted Units |  | 20
S287300 | Helium System Transfer lines : Along West wall of IR8 Hall INSTALLATION: field Joint welding | 04-Nov-20 A | 31-Dec-20 A | CRAFT3 | CRAFT3 | 160 | 0 | C | Budgeted Units |  | 160
POM02-13.02.02.03.02 LN2 Supply Transfer Line System |  | 01-Oct-19 A | 27-May-22 A |  |  | 1440 | 0 |  | Budgeted Units | 490 | 372 | 578
POM02-13.02.02.03.02.01 Engineering and Design, LN2 Supply Transfer Line System |  | 01-Oct-19 A | 01-May-20 A |  |  | 152 | 0 |  | Budgeted Units | 152
S288200 | (LN2 supply transfer line system) SOW & Technical Specifications | 22-Nov-19 A | 01-May-20 A | PROF3 AD | PROF3 AD | 36 | 0 | C | Budgeted Units | 36
S288100 | (LN2 supply transfer line system) Mechanical Engineering Tasks FY19 | 01-Oct-19 A | 01-May-20 A | PROF3 AD | PROF3 AD | 40 | 0 | C | Budgeted Units | 40
S288200 | (LN2 supply transfer line system) SOW & Technical Specifications | 22-Nov-19 A | 01-May-20 A | PROF6 AD | PROF6 AD | 36 | 0 | C | Budgeted Units | 36
S288100 | (LN2 supply transfer line system) Mechanical Engineering Tasks FY19 | 01-Oct-19 A | 01-May-20 A | PROF6 AD | PROF6 AD | 40 | 0 | C | Budgeted Units | 40
POM02-13.02.02.03.02.02 Design/Drafting, LN2 Supply Transfer Line System |  | 01-Oct-19 A | 10-Jul-20 A |  |  | 202 | 0 |  | Budgeted Units | 202
S288500 | (LN2 supply transfer line system) Detailed dwg package for Procurement | 10-Dec-19 A | 10-Jul-20 A | PROF3 AD | PROF3 AD | 120 | 0 | C | Budgeted Units | 120
S288410 | (LN2 supply transfer line system) LN2 supply transfer line detail layout Split | 01-Oct-19 A | 09-Dec-19 A | PROF3 AD | PROF3 AD | 17 | 0 | C | Budgeted Units | 17
S288500 | (LN2 supply transfer line system) Detailed dwg package for Procurement | 10-Dec-19 A | 10-Jul-20 A | PROF6 AD | PROF6 AD | 48 | 0 | C | Budgeted Units | 48
S288410 | (LN2 supply transfer line system) LN2 supply transfer line detail layout Split | 01-Oct-19 A | 09-Dec-19 A | PROF6 AD | PROF6 AD | 17 | 0 | C | Budgeted Units | 17
POM02-13.02.02.03.02.03 Procurement, LN2 Supply Transfer Line System |  | 04-May-20 A | 15-Jul-20 A |  |  | 136 | 0 |  | Budgeted Units | 136
S288600 | Procure LN2 supply transfer line system - Provide requirements to Procurement | 04-May-20 A | 15-Jul-20 A | PROF3 AD | PROF3 AD | 48 | 0 | C | Budgeted Units | 48
S288600 | Procure LN2 supply transfer line system - Provide requirements to Procurement | 04-May-20 A | 15-Jul-20 A | PROF6 AD | PROF6 AD | 88 | 0 | C | Budgeted Units | 88
POM02-13.02.02.03.02.04 Fabrication at Vendor, LN2 Supply Transfer Line System |  | 01-Dec-20 A | 29-Apr-22 A |  |  | 272 | 0 |  | Budgeted Units |  | 272
POM02-13.02.02.03.02.04.01 Vendor Engineering and Design |  | 01-Dec-20 A | 29-Apr-22 A |  |  | 132 | 0 |  | Budgeted Units |  | 132
S289400 | (LN2 supply transfer line system) Kick off meeting | 01-Dec-20 A | 01-Dec-20 A | PROF6 AD | PROF6 AD | 8 | 0 | C | Budgeted Units |  | 8
S289500 | Engineering Support for Procure LN2 supply transfer line system | 02-Dec-20 A | 29-Apr-22 A | PROF6 AD | PROF6 AD | 36 | 0 | C | Budgeted Units |  | 36
S289600 | (LN2 supply transfer line system) Preliminary Design Review Labor | 02-Dec-20 A | 27-Jan-21 A | PROF6 AD | PROF6 AD | 8 | 0 | C | Budgeted Units |  | 8
S289900 | (LN2 supply transfer line system) Detail dwg package | 18-Jan-21 A | 30-Apr-21 A | PROF6 AD | PROF6 AD | 48 | 0 | C | Budgeted Units |  | 48
S290300 | (LN2 supply transfer line system) Final Design Review Labor | 01-Feb-21 A | 30-Mar-21 A | PROF6 AD | PROF6 AD | 8 | 0 | C | Budgeted Units |  | 8
S290000 | Long lead items Support Labor for LN2 supply transfer line system | 01-Feb-21 A | 31-Mar-21 A | PROF6 AD | PROF6 AD | 24 | 0 | C | Budgeted Units |  | 24
S290600 | (LN2 supply transfer line system) Drawings approvals | 26-Apr-21 A | 30-Apr-21 A | PROF6 AD | PROF6 AD | 0 | 0 | C | Budgeted Units
POM02-13.02.02.03.02.04.02 Vendor Fabrication |  | 15-Apr-21 A | 28-Feb-22 A |  |  | 140 | 0 |  | Budgeted Units |  | 140
S290700 | (LN2 supply transfer line system) Raw Material procurement Labor | 21-Apr-21 A | 25-Jun-21 A | PROF6 AD | PROF6 AD | 0 | 0 | C | Budgeted Units
S291000 | (LN2 supply transfer line system) Main fabrication items | 21-Apr-21 A | 25-Jun-21 A | PROF6 AD | PROF6 AD | 0 | 0 | C | Budgeted Units
S291100 | (LN2 supply transfer line system) Final assemblies | 12-Jul-21 A | 28-Feb-22 A | PROF6 AD | PROF6 AD | 0 | 0 | C | Budgeted Units
S291200 | (LN2 supply transfer line system) BNL Holdpoint witness | 12-Jul-21 A | 29-Oct-21 A | PROF6 AD | PROF6 AD | 0 | 0 | C | Budgeted Units
S291300 | (LN2 supply transfer line system) Shipping Labor | 13-Jul-21 A | 30-Sep-21 A | PROF6 AD | PROF6 AD | 0 | 0 | C | Budgeted Units
S1008520 | (LN2 supply transfer line system) LOE Supervision Labor | 15-Apr-21 A | 25-Jun-21 A | PROF6 AD | PROF6 AD | 140 | 0 | C | Budgeted Units |  | 140
POM02-13.02.02.03.02.05 Delivery and receiving, LN2 Supply Transfer Line System |  | 13-Jul-21 A | 31-Mar-22 A |  |  | 22 | 0 |  | Budgeted Units |  |  | 22
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | 13-Jul-21 A | 31-Mar-22 A | PROF3 AD | PROF3 AD | 5 | 0 | C | Budgeted Units |  |  | 5
S291700 | (LN2 supply transfer line system) Inspection | 13-Jul-21 A | 31-Mar-22 A | PROF6 AD | PROF6 AD | 1 | 0 | C | Budgeted Units |  |  | 1
S291600 | (LN2 supply transfer line system) Rigging/Truck Unloading | 13-Jul-21 A | 31-Mar-22 A | CRAFT3 | CRAFT3 | 16 | 0 | C | Budgeted Units |  |  | 16
POM02-13.02.02.03.02.06 Installation, LN2 Supply Transfer Line System |  | 17-Mar-21 A | 27-May-22 A |  |  | 656 | 0 |  | Budgeted Units |  | 100 | 556
S291900 | (LN2 supply transfer line system) Piping supports procure materials Labor | 17-Mar-21 A | 19-Mar-21 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units |  | 12
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | 17-May-21 A | 27-Apr-22 A | PROF3 AD | PROF3 AD | 48 | 0 | C | Budgeted Units |  | 48
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 20-Jul-21 A | 29-Apr-22 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | 21-Jul-21 A | 20-May-22 A | PROF3 AD | PROF3 AD | 24 | 0 | C | Budgeted Units |  |  | 24
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | 16-May-22 A | 27-May-22 A | PROF3 AD | PROF3 AD | 20 | 0 | C | Budgeted Units |  |  | 20
S292000 | (LN2 supply transfer line system) Install piping supports (Outside pipe run) | 17-May-21 A | 27-Apr-22 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  | 40
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 20-Jul-21 A | 29-Apr-22 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
S292200 | (LN2 supply transfer line system) Install Instrumentation, reliefs and air supply to valves | 21-Jul-21 A | 20-May-22 A | TECH3 AD | TECH3 AD | 96 | 0 | C | Budgeted Units |  |  | 96
S292300 | (LN2 supply transfer line system) Final pressure. leak check and equipment shakedown | 16-May-22 A | 27-May-22 A | TECH3 AD | TECH3 AD | 64 | 0 | C | Budgeted Units |  |  | 64
S292100 | (LN2 supply transfer line system) Rigging in place onto piping supports | 20-Jul-21 A | 29-Apr-22 A | CRAFT3 | CRAFT3 | 16 | 0 | C | Budgeted Units |  |  | 16
S292120 | Welding LN2 Segment #1 to LN2 Dewar | 27-Apr-22 A | 27-May-22 A | CRAFT3 | CRAFT3 | 80 | 0 | C | Budgeted Units |  |  | 80
POM02-13.02.02.03.03 Warm Piping System |  | 02-Dec-19 A | 06-Sep-22 A |  |  | 2391 | 0 |  | Budgeted Units | 521 | 794 | 1076
POM02-13.02.02.03.03.01 Engineering and Design, Warm Piping System |  | 02-Dec-19 A | 31-Mar-22 A |  |  | 75 | 0 |  | Budgeted Units | 75
S292700 | (Warm Piping System) Technical Specifications | 01-May-20 A | 29-Mar-21 A | PROF3 AD | PROF3 AD | 6 | 0 | C | Budgeted Units | 6
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | 02-Dec-19 A | 31-Mar-22 A | PROF3 AD | PROF3 AD | 19 | 0 | C | Budgeted Units | 19
S292700 | (Warm Piping System) Technical Specifications | 01-May-20 A | 29-Mar-21 A | PROF6 AD | PROF6 AD | 12 | 0 | C | Budgeted Units | 12
S292602 | (Warm Piping System) Mechanical Engineering Tasks Split | 02-Dec-19 A | 31-Mar-22 A | PROF6 AD | PROF6 AD | 38 | 0 | C | Budgeted Units | 38
POM02-13.02.02.03.03.02 Design/Drafting, Warm Piping System |  | 09-Dec-19 A | 30-Jul-21 A |  |  | 574 | 0 |  | Budgeted Units | 446 | 128
POM02-13.02.02.03.03.02.01 Warm Piping tie in to WR header |  | 03-Aug-20 A | 22-Jul-21 A |  |  | 132 | 0 |  | Budgeted Units | 100 | 32
S292800 | (Warm Piping tie in to WR header) General Arrangement Layout | 03-Aug-20 A | 20-Jul-21 A | PROF3 AD | PROF3 AD | 20 | 0 | C | Budgeted Units | 20
S292900 | (Warm Piping tie in to WR header) Detailed drawing package with weld map | 17-Nov-20 A | 22-Jul-21 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  | 16
S292800 | (Warm Piping tie in to WR header) General Arrangement Layout | 03-Aug-20 A | 20-Jul-21 A | PROF6 AD | PROF6 AD | 80 | 0 | C | Budgeted Units | 80
S292900 | (Warm Piping tie in to WR header) Detailed drawing package with weld map | 17-Nov-20 A | 22-Jul-21 A | PROF6 AD | PROF6 AD | 16 | 0 | C | Budgeted Units |  | 16
POM02-13.02.02.03.03.02.02 Warm Piping tie in Bldg 1010B Compressor |  | 03-Aug-20 A | 30-Mar-21 A |  |  | 192 | 0 |  | Budgeted Units | 96 | 96
S293000 | (Warm Piping tie in bldg. 1010B compressor) General Arrangement Layout | 03-Aug-20 A | 30-Mar-21 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units | 16
S293100 | (Warm Piping tie in bldg. 1010B compressor) Detailed drawing package with weld map | 16-Feb-21 A | 30-Mar-21 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  | 16
S293000 | (Warm Piping tie in bldg. 1010B compressor) General Arrangement Layout | 03-Aug-20 A | 30-Mar-21 A | PROF6 AD | PROF6 AD | 80 | 0 | C | Budgeted Units | 80
S293100 | (Warm Piping tie in bldg. 1010B compressor) Detailed drawing package with weld map | 16-Feb-21 A | 30-Mar-21 A | PROF6 AD | PROF6 AD | 80 | 0 | C | Budgeted Units |  | 80
POM02-13.02.02.03.03.02.03 GN2 Vent Line from Platform Coldbox |  | 09-Dec-19 A | 15-Jul-20 A |  |  | 96 | 0 |  | Budgeted Units | 96
S293300 | (GN2 Vent Line from platform coldbox) Detailed drawing package with weld map | 09-Dec-19 A | 15-Jul-20 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units | 16
S293300 | (GN2 Vent Line from platform coldbox) Detailed drawing package with weld map | 09-Dec-19 A | 15-Jul-20 A | PROF6 AD | PROF6 AD | 80 | 0 | C | Budgeted Units | 80
POM02-13.02.02.03.03.02.04 Warm Piping for Summer 80K Hold Helium Compressor Loop |  | 16-Dec-19 A | 30-Jul-21 A |  |  | 154 | 0 |  | Budgeted Units | 154
S293500 | (Current Leads Warm Piping) Detailed drawing package with weld map | 16-Dec-19 A | 30-Jul-21 A | PROF3 AD | PROF3 AD | 26 | 0 | C | Budgeted Units | 26
S293500 | (Current Leads Warm Piping) Detailed drawing package with weld map | 16-Dec-19 A | 30-Jul-21 A | PROF6 AD | PROF6 AD | 128 | 0 | C | Budgeted Units | 128
POM02-13.02.02.03.03.03 Procurement of Materials, Warm Piping System |  | 31-Dec-20 A | 28-May-21 A |  |  | 228 | 0 |  | Budgeted Units |  | 228
S293700 | (Warm Piping System Materials Procurement) Reliefs Labor | 31-Dec-20 A | 30-Apr-21 A | PROF3 AD | PROF3 AD | 72 | 0 | C | Budgeted Units |  | 72
S294000 | Procure Warm Piping and fittings - Provide Requirements to Procurement | 01-Feb-21 A | 25-Feb-21 A | PROF4 AD | PROF4 AD | 24 | 0 | C | Budgeted Units |  | 24
S293700 | (Warm Piping System Materials Procurement) Reliefs Labor | 31-Dec-20 A | 30-Apr-21 A | PROF6 AD | PROF6 AD | 72 | 0 | C | Budgeted Units |  | 72
S293900 | (Warm Piping System Materials Procurement) Warm Valves | 31-Dec-20 A | 30-Apr-21 A | PROF6 AD | PROF6 AD | 36 | 0 | C | Budgeted Units |  | 36
S294700 | (Warm Piping System Materials Procurement) Piping supports Labor | 08-Mar-21 A | 28-May-21 A | PROF6 AD | PROF6 AD | 24 | 0 | C | Budgeted Units |  | 24
POM02-13.02.02.03.03.04 Installation: Warm Piping Systems |  | 09-Jul-21 A | 06-Sep-22 A |  |  | 1514 | 0 |  | Budgeted Units |  | 438 | 1076
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | 26-Jul-21 A | 29-Oct-21 A | PROF3 AD | PROF3 AD | 144 | 0 | C | Budgeted Units |  | 35 | 109
S294840 | (Warm Piping System) Phase 2: Welding of piping, vent lines and install of piping supports, after coldbox/magnet install | 09-Jul-21 A | 29-Oct-21 A | PROF3 AD | PROF3 AD | 36 | 0 | C | Budgeted Units |  | 36
S295000 | (Warm Piping System) Pressure and leak check | 25-Jul-22 A | 15-Aug-22 A | PROF3 AD | PROF3 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | 12-Aug-22 A | 26-Aug-22 A | PROF3 AD | PROF3 AD | 20 | 0 | C | Budgeted Units |  |  | 20
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | 01-Sep-22 A | 06-Sep-22 A | PROF3 AD | PROF3 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S295300 | (Warm Piping System) Vacuum Pumping System installation | 29-Jul-22 A | 26-Aug-22 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S294860 | (Warm Piping System) Assembly hall work on Platform | 29-Jul-22 A | 12-Aug-22 A | PROF3 AD | PROF3 AD | 18 | 0 | C | Budgeted Units |  |  | 18
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 19-Jul-22 A | 12-Aug-22 A | PROF3 AD | PROF3 AD | 18 | 0 | C | Budgeted Units |  |  | 18
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | 26-Jul-21 A | 29-Oct-21 A | TECH3 AD | TECH3 AD | 360 | 0 | C | Budgeted Units |  | 88 | 272
S294840 | (Warm Piping System) Phase 2: Welding of piping, vent lines and install of piping supports, after coldbox/magnet install | 09-Jul-21 A | 29-Oct-21 A | TECH3 AD | TECH3 AD | 180 | 0 | C | Budgeted Units |  | 180
S295000 | (Warm Piping System) Pressure and leak check | 25-Jul-22 A | 15-Aug-22 A | TECH3 AD | TECH3 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S295100 | (Warm Piping System) Install Instrumentation, reliefs and air supply to valves | 12-Aug-22 A | 26-Aug-22 A | TECH3 AD | TECH3 AD | 64 | 0 | C | Budgeted Units |  |  | 64
S295200 | (Warm Piping System) Final pressure. leak check and equipment shakedown | 01-Sep-22 A | 06-Sep-22 A | TECH3 AD | TECH3 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S295300 | (Warm Piping System) Vacuum Pumping System installation | 29-Jul-22 A | 26-Aug-22 A | TECH3 AD | TECH3 AD | 38 | 0 | C | Budgeted Units |  |  | 38
S294860 | (Warm Piping System) Assembly hall work on Platform | 29-Jul-22 A | 12-Aug-22 A | TECH3 AD | TECH3 AD | 90 | 0 | C | Budgeted Units |  |  | 90
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 19-Jul-22 A | 12-Aug-22 A | TECH3 AD | TECH3 AD | 90 | 0 | C | Budgeted Units |  |  | 90
S294800 | (Warm Piping System) Phase 1: Welding of piping and install of piping supports | 26-Jul-21 A | 29-Oct-21 A | CRAFT3 | CRAFT3 | 240 | 0 | C | Budgeted Units |  | 59 | 181
S294840 | (Warm Piping System) Phase 2: Welding of piping, vent lines and install of piping supports, after coldbox/magnet install | 09-Jul-21 A | 29-Oct-21 A | CRAFT3 | CRAFT3 | 40 | 0 | C | Budgeted Units |  | 40
S294860 | (Warm Piping System) Assembly hall work on Platform | 29-Jul-22 A | 12-Aug-22 A | CRAFT3 | CRAFT3 | 20 | 0 | C | Budgeted Units |  |  | 20
S294880 | (Warm Piping System) IR Hall work Jumper work between Platform and West Wall | 19-Jul-22 A | 12-Aug-22 A | CRAFT3 | CRAFT3 | 20 | 0 | C | Budgeted Units |  |  | 20
POM02-13.02.02.03.04 Cryo Controls Hardware |  | 01-Oct-19 A | 07-Sep-22 A |  |  | 2010 | 0 |  | Budgeted Units | 319 | 618 | 1073
POM02-13.02.02.03.04.01 Engineering and Design |  | 01-Oct-19 A | 30-Nov-21 A |  |  | 432 | 0 |  | Budgeted Units | 264 | 150 | 18
S295500 | (Controls Hardware) Wire diagram drawings | 19-Apr-21 A | 30-Nov-21 A | TECH3 AD | TECH3 AD | 128 | 0 | C | Budgeted Units |  | 128
S295600 | (Controls Hardware) Power distribution drawings | 15-Feb-21 A | 30-Nov-21 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  | 22 | 18
S295700 | (Controls Hardware) I/O list table | 07-Aug-20 A | 29-Oct-21 A | TECH3 AD | TECH3 AD | 48 | 0 | C | Budgeted Units | 48
S295401 | (Controls Hardware) Cryo instrument and equipment specifications 70% | 01-Oct-19 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 84 | 0 | C | Budgeted Units | 84
S295700 | (Controls Hardware) I/O list table | 07-Aug-20 A | 29-Oct-21 A | PROF3 AD | PROF3 AD | 48 | 0 | C | Budgeted Units | 48
S295401 | (Controls Hardware) Cryo instrument and equipment specifications 70% | 01-Oct-19 A | 30-Sep-21 A | PROF3 AD | PROF3 AD | 84 | 0 | C | Budgeted Units | 84
POM02-13.02.02.03.04.02 Procurement |  | 01-Apr-20 A | 31-Jan-22 A |  |  | 199 | 0 |  | Budgeted Units | 55 | 130 | 14
S295800 | (Cryo Controls Hardware procurement) PLC I/O cards & expansion chassis Labor | 01-Apr-20 A | 30-Apr-20 A | PROF3 AD | PROF3 AD | 15 | 0 | C | Budgeted Units | 15
S296000 | (Cryo Controls Hardware procurement) Rack components Labor | 01-Apr-20 A | 30-Apr-20 A | PROF3 AD | PROF3 AD | 4 | 0 | C | Budgeted Units | 4
S296200 | (Cryo Controls Hardware procurement) Lakeshore Temperature Controller/conditioners Labor | 07-Jul-20 A | 31-Jul-20 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units | 12
S296400 | (Cryo Controls Hardware procurement) Lakeshore Temperature sensors Labor | 01-Feb-21 A | 24-Feb-21 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units |  | 12
S296600 | (Cryo Controls Hardware procurement) SC level probes Labor | 01-Oct-20 A | 31-Jan-22 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units |  | 12
S296800 | (Cryo Controls Hardware procurement) Pressure transmitters Labor | 12-Jun-20 A | 15-Jun-20 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units | 12
S297000 | (Cryo Controls Hardware procurement) Flowmeters Labor | 01-Dec-20 A | 29-Jan-21 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units |  | 12
S297200 | (Cryo Controls Hardware procurement) Vacuum gages and cables Labor | 04-Jan-21 A | 29-Jan-21 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units |  | 12
S297500 | (Cryo Controls Hardware procurement) 32 conductor cables, IP8 to 1008B racks Labor | 02-Jun-20 A | 05-Jun-20 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units | 12
S297600 | (Cryo Controls Hardware procurement) 8 conductor cables, IP8 to 1008B racks Labor | 22-Sep-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 12 | 0 | C | Budgeted Units |  | 12
S297800 | (Cryo Controls Hardware procurement) Heaters 480VAC Labor | 22-Mar-21 A | 30-Apr-21 A | PROF3 AD | PROF3 AD | 14 | 0 | C | Budgeted Units |  |  | 14
S298000 | (Cryo Controls Hardware procurement) Heater UL listed Control Panel Labor | 15-Jun-20 A | 18-Jun-20 A | PROF3 AD | PROF3 AD | 14 | 0 | C | Budgeted Units |  | 14
S298200 | (Cryo Controls Hardware procurement) Switch, 480 VAC Labor | 19-Jul-21 A | 30-Jul-21 A | PROF3 AD | PROF3 AD | 5 | 0 | C | Budgeted Units |  | 5
S298400 | (Cryo Controls Hardware procurement) Network switch and Ethernet fiber drop Labor | 03-May-21 A | 24-May-21 A | PROF3 AD | PROF3 AD | 5 | 0 | C | Budgeted Units |  | 5
S298600 | (Cryo Controls Hardware procurement) Cable tray and supports Labor | 22-Sep-20 A | 26-Feb-21 A | PROF3 AD | PROF3 AD | 46 | 0 | C | Budgeted Units |  | 46
POM02-13.02.02.03.04.03 Installation: Cryo Controls Hardware |  | 15-Jun-21 A | 07-Sep-22 A |  |  | 1379 | 0 |  | Budgeted Units |  | 338 | 1041
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | 19-Jul-21 A | 27-Jun-22 A | TECH3 AD | TECH3 AD | 280 | 0 | C | Budgeted Units |  | 280
S299700 | (Cryo Controls Hardware) Rack install | 19-Jul-21 A | 22-Nov-21 A | TECH3 AD | TECH3 AD | 13 | 0 | C | Budgeted Units |  | 8 | 5
S299800 | (Cryo Controls Hardware) Cable pulling | 19-Jul-21 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 52 | 0 | C | Budgeted Units |  |  | 52
S299900 | (Cryo Controls Hardware) Cable termination | 20-Jul-21 A | 16-Aug-22 A | TECH3 AD | TECH3 AD | 160 | 0 | C | Budgeted Units |  |  | 160
S300000 | (Cryo Controls Hardware) Check out continuity | 26-Aug-22 A | 07-Sep-22 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  |  | 40
S300400 | (Cryo Controls Hardware) Heater I/O wiring, temp sensors | 01-Jul-22 A | 25-Jul-22 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S300500 | (Cryo Controls Hardware) Wire up instruments and control valves | 04-Jul-22 A | 23-Aug-22 A | TECH3 AD | TECH3 AD | 96 | 0 | C | Budgeted Units |  |  | 96
S299600 | (Cryo Controls Hardware) Rack built/rebuilt | 19-Jul-21 A | 27-Jun-22 A | PROF3 AD | PROF3 AD | 48 | 0 | C | Budgeted Units |  | 48
S299700 | (Cryo Controls Hardware) Rack install | 19-Jul-21 A | 22-Nov-21 A | PROF3 AD | PROF3 AD | 4 | 0 | C | Budgeted Units |  | 2 | 2
S299800 | (Cryo Controls Hardware) Cable pulling | 19-Jul-21 A | 29-Jul-22 A | CRAFT3 | CRAFT3 | 150 | 0 | C | Budgeted Units |  |  | 150
S300100 | (Cryo Controls Hardware) Heater Control Panel Install | 15-Jun-21 A | 30-Jul-21 A | CRAFT3 | CRAFT3 | 32 | 0 | C | Budgeted Units |  |  | 32
S300200 | (Cryo Controls Hardware) Heater 480VAC wiring | 18-Oct-21 A | 16-Aug-22 A | CRAFT3 | CRAFT3 | 480 | 0 | C | Budgeted Units |  |  | 480
S300300 | (Cryo Controls Hardware) Insulating vacuum roughing pumps 480VAC Breaker install and 480V wiring to roughing pumps | 15-Jun-21 A | 16-Aug-22 A | CRAFT3 | CRAFT3 | 8 | 0 | C | Budgeted Units |  |  | 8
POM02-13.02.02.03.05 Cryo Controls Software |  | 13-Jul-20 A | 14-Sep-22 A |  |  | 2056 | 0 |  | Budgeted Units | 652 | 1140 |  | 264
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 16-Aug-22 A | 14-Sep-22 A | TECH3 AD | TECH3 AD | 120 | 0 | C | Budgeted Units |  |  |  | 120
S300700 | (Cryo Controls Hardware) Control Logic eng document revision by Cryo process engineering | 03-Aug-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 240 | 0 | C | Budgeted Units | 168 | 72
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | 03-Aug-20 A | 15-Aug-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units | 8
S300900 | (Cryo Controls Hardware) Built HMI operator screens | 08-Mar-21 A | 27-Apr-22 A | PROF4 AD | PROF4 AD | 72 | 0 | C | Budgeted Units |  | 72
S301000 | (Cryo Controls Hardware) PLC programming | 13-Jul-20 A | 28-Apr-22 A | PROF4 AD | PROF4 AD | 72 | 0 | C | Budgeted Units | 33 | 39
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 16-Aug-22 A | 14-Sep-22 A | PROF4 AD | PROF4 AD | 24 | 0 | C | Budgeted Units |  |  |  | 24
S300700 | (Cryo Controls Hardware) Control Logic eng document revision by Cryo process engineering | 03-Aug-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 240 | 0 | C | Budgeted Units | 168 | 72
S300800 | (Cryo Controls Hardware) Interface document definition for variables to MCR and sPHENIX controls | 03-Aug-20 A | 15-Aug-22 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units | 8
S300900 | (Cryo Controls Hardware) Built HMI operator screens | 08-Mar-21 A | 27-Apr-22 A | PROF3 AD | PROF3 AD | 576 | 0 | C | Budgeted Units |  | 576
S301000 | (Cryo Controls Hardware) PLC programming | 13-Jul-20 A | 28-Apr-22 A | PROF3 AD | PROF3 AD | 576 | 0 | C | Budgeted Units | 267 | 309
S301100 | (Cryo Controls Hardware) Live I/O check out and control logic test | 16-Aug-22 A | 14-Sep-22 A | PROF3 AD | PROF3 AD | 120 | 0 | C | Budgeted Units |  |  |  | 120
POM02-13.02.02.04 Magnet Power Supplies/Controls/Quench Protection |  | 01-Oct-19 A | 2022-10-19 |  |  | 3894 | 241 |  | Budgeted Units | 613 | 1566 | 1581 | 134
POM02-13.02.02.04.01 AC/DC Power Distribution |  | 01-Oct-19 A | 2022-10-07 |  |  | 2497 | 126 |  | Budgeted Units | 106 | 1066 | 1325
POM02-13.02.02.04.01.01 Design AC/DC Power Distribution |  | 01-Oct-19 A | 29-Dec-21 A |  |  | 141 | 0 |  | Budgeted Units | 30 | 106 | 5
S301610 | Magnet: 1008 IR Design Power Supply AC and Quench Detector Power Distribution Split | 01-Oct-19 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 30 | 0 | C | Budgeted Units | 30
S301800 | Magnet: 1008 IR Design Quench Detector AC Power Hook-up | 12-Jan-21 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S301710 | Magnet: 1008 IR Design Power Supply AC Power Hook-up Split | 12-Jan-21 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 18 | 0 | C | Budgeted Units |  | 18
S301910 | Magnet: 1008 IR Design Power Supply, Magnet, Dump Resistor DC Cabling Split | 12-Jan-21 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 12 | 0 | C | Budgeted Units |  | 12
S302010 | Magnet: Design Cable Tray and Supports for Power and Signal Distribution Split | 23-Nov-20 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units |  | 60
S302101 | Magnet: Design DC Flags 50% | 20-Dec-21 A | 29-Dec-21 A | PROF4 AD | PROF4 AD | 5 | 0 | C | Budgeted Units |  |  | 5
POM02-13.02.02.04.01.02 Procure PS System Connections |  | 01-Nov-19 A | 30-Apr-21 A |  |  | 140 | 0 |  | Budgeted Units | 76 | 64
S302500 | Magnet: Order AC Power Distribution Parts Labor | 20-May-20 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S302700 | Magnet: Order Power Supply, Magnet, Dump Resistor DC Cabling and Interconnects Labor | 15-Dec-20 A | 30-Apr-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S302601 | Magnet: Order Power Supply and Quench Detector AC Power Cables and Interconnects Labor 95% | 01-Nov-19 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units | 8
S302901 | Magnet: Order Cable Tray and Supports_85% | 24-Mar-20 A | 31-Mar-20 A | PROF4 AD | PROF4 AD | 68 | 0 | C | Budgeted Units | 68
S302800 | Magnet: Fabricate DC flags | 22-Oct-20 A | 28-Oct-20 A | CRAFT3 | CRAFT3 | 40 | 0 | C | Budgeted Units |  | 40
POM02-13.02.02.04.01.03 Install PS AC/DC Cabling |  | 16-Sep-20 A | 2022-10-07 |  |  | 2216 | 126 |  | Budgeted Units |  | 896 | 1320
S303400 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B | 22-Sep-20 A | 29-Mar-21 A | TECH3 AD | TECH3 AD | 160 | 0 | C | Budgeted Units |  | 160
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 03-Jan-22 A | 31-May-22 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | TECH3 AD | TECH3 AD | 160 | 48 | C | Budgeted Units |  |  | 160
S303100 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008B | 22-Sep-20 A | 29-Mar-21 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units |  | 40
S303400 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B | 22-Sep-20 A | 29-Mar-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S303200 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution in 1008B to 1008IR | 16-Sep-20 A | 15-Nov-21 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units |  | 60
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 03-Jan-22 A | 31-May-22 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units |  |  | 60
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | 01-Jul-22 A | 31-Aug-22 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units |  |  | 60
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | PROF4 AD | PROF4 AD | 40 | 12 | C | Budgeted Units |  |  | 40
S303100 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008B | 22-Sep-20 A | 29-Mar-21 A | CRAFT3 | CRAFT3 | 160 | 0 | C | Budgeted Units |  | 160
S303400 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B | 22-Sep-20 A | 29-Mar-21 A | CRAFT3 | CRAFT3 | 220 | 0 | C | Budgeted Units |  | 220
S303200 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution in 1008B to 1008IR | 16-Sep-20 A | 15-Nov-21 A | CRAFT3 | CRAFT3 | 240 | 0 | C | Budgeted Units |  | 240
S303500 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008B to 1008IR | 03-Jan-22 A | 31-May-22 A | CRAFT3 | CRAFT3 | 300 | 0 | C | Budgeted Units |  |  | 300
S303300 | Magnet: Install Cable Tray and Supports for Power and Signal Distribution 1008IR | 01-Jul-22 A | 31-Aug-22 A | CRAFT3 | CRAFT3 | 240 | 0 | C | Budgeted Units |  |  | 240
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | CRAFT3 | CRAFT3 | 220 | 66 | C | Budgeted Units |  |  | 220
POM02-13.02.02.04.02 Power Supply |  | 01-Oct-19 A | 2022-10-19 |  |  | 1028 | 115 |  | Budgeted Units | 410 | 388 | 96 | 134
POM02-13.02.02.04.02.01 Install Power Supply |  | 01-Oct-19 A | 2022-10-19 |  |  | 1028 | 115 |  | Budgeted Units | 410 | 388 | 96 | 134
S305110 | Magnet Power Supply Installation: Documentation Split | 01-Oct-19 A | 31-Dec-19 A | PROF5 AD | PROF5 AD | 108 | 0 | C | Budgeted Units | 85 | 23
S304901 | Magnet Power Supply Installation: Design and Test Control Interface update software_50% | 13-Nov-19 A | 29-Nov-19 A | PROF5 AD | PROF5 AD | 30 | 0 | C | Budgeted Units | 30
S304100 | Magnet Power Supply Installation: Connect DC Cabling to Power Supply, Dump Resistor, Magnet | 11-Aug-20 A | 17-Feb-21 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  | 80
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | 24-May-21 A | 15-Sep-22 A | TECH3 AD | TECH3 AD | 32 | 0 | C | Budgeted Units |  | 32
S305000 | Magnet Power Supply Installation: Power Supply Testing | 23-Sep-22 A | 2022-10-19 | TECH3 AD | TECH3 AD | 80 | 40 | C | Budgeted Units |  |  | 48 | 32
S305110 | Magnet Power Supply Installation: Documentation Split | 01-Oct-19 A | 31-Dec-19 A | TECH3 AD | TECH3 AD | 216 | 0 | C | Budgeted Units | 171 | 45
S304000 | Magnet Power Supply Installation: Connect AC Power to Power Supply | 22-Mar-21 A | 31-Mar-21 A | PROF4 AD | PROF4 AD | 5 | 0 | C | Budgeted Units |  | 5
S304100 | Magnet Power Supply Installation: Connect DC Cabling to Power Supply, Dump Resistor, Magnet | 11-Aug-20 A | 17-Feb-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S304200 | Magnet Power Supply Installation: Connect Signal Interconnections 1008B | 24-May-21 A | 15-Sep-22 A | PROF4 AD | PROF4 AD | 7 | 0 | C | Budgeted Units |  | 7
S305000 | Magnet Power Supply Installation: Power Supply Testing | 23-Sep-22 A | 2022-10-19 | PROF4 AD | PROF4 AD | 80 | 40 | C | Budgeted Units |  |  | 48 | 32
S304400 | Magnet Power Supply Installation: Cooling Water Installation 1008B | 03-Aug-20 A | 24-May-21 A | TECH3 AD | TECH3 AD | 70 | 0 | C | Budgeted Units |  | 70
S304500 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008B L | 03-Aug-20 A | 23-Mar-21 A | TECH3 AD | TECH3 AD | 70 | 0 | C | Budgeted Units |  | 70
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 10-Aug-22 A | 2022-10-11 | TECH3 AD | TECH3 AD | 70 | 35 | C | Budgeted Units |  |  |  | 70
S304310 | Magnet Power Supply Installation: Cooling Water Design Split | 01-Nov-19 A | 28-Apr-21 A | PROF4 AD | PROF4 AD | 64 | 0 | C | Budgeted Units | 64
S304901 | Magnet Power Supply Installation: Design and Test Control Interface update software_50% | 13-Nov-19 A | 29-Nov-19 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units | 60
S303900 | Magnet Power Supply Installation: Move Power Supply to location | 18-Aug-20 A | 27-Aug-20 A | CRAFT3 | CRAFT3 | 16 | 0 | C | Budgeted Units |  | 16
S304000 | Magnet Power Supply Installation: Connect AC Power to Power Supply | 22-Mar-21 A | 31-Mar-21 A | CRAFT3 | CRAFT3 | 32 | 0 | C | Budgeted Units |  | 32
POM02-13.02.02.04.03 Quench Detector |  | 01-Oct-19 A | 30-Sep-22 A |  |  | 370 | 0 |  | Budgeted Units | 97 | 112 | 160
POM02-13.02.02.04.03.02 Procure Quench Detector System Connections |  | 01-Oct-19 A | 30-Sep-22 A |  |  | 370 | 0 |  | Budgeted Units | 97 | 112 | 160
POM02-13.02.02.04.03.02.01 Install Quench Detector |  | 01-Oct-19 A | 30-Sep-22 A |  |  | 370 | 0 |  | Budgeted Units | 97 | 112 | 160
S307200 | Magnet: Quench Detector Testing | 20-Jul-21 A | 30-Sep-22 A | PROF5 AD | PROF5 AD | 80 | 0 | C | Budgeted Units |  |  | 80
S307311 | Magnet: Quench Detector Documentation Split_85% | 01-Oct-19 A | 27-May-22 A | PROF5 AD | PROF5 AD | 27 | 0 | C | Budgeted Units | 24 | 3
S307100 | Magnet: Connect Signal Interconnections | 08-Mar-21 A | 15-Sep-22 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  | 80
S307200 | Magnet: Quench Detector Testing | 20-Jul-21 A | 30-Sep-22 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  |  | 80
S306800 | Magnet: Disconnect Quench Detector from Test System in 912 | 13-May-20 A | 28-May-20 A | TECH3 AD | TECH3 AD | 8 | 0 | C | Budgeted Units | 8
S307311 | Magnet: Quench Detector Documentation Split_85% | 01-Oct-19 A | 27-May-22 A | TECH3 AD | TECH3 AD | 54 | 0 | C | Budgeted Units | 49 | 6
S306900 | Magnet: Move Quench Detector to location | 14-May-20 A | 30-Oct-20 A | CRAFT3 | CRAFT3 | 16 | 0 | C | Budgeted Units | 16
S307000 | Magnet: Connect AC Power to Quench Detector | 12-Jan-21 A | 05-Feb-21 A | CRAFT3 | CRAFT3 | 24 | 0 | C | Budgeted Units |  | 24
POM02-13.02.02.05 Magnet Field Measurements |  | 01-Oct-19 A | 2023-01-17 |  |  | 2459 | 1286 |  | Budgeted Units | 649 | 435 | 87 | 1288
POM02-13.02.02.05.01 Magnet Field Measurements Engineering and Design, Field Studies and Stress Analysis |  | 01-Oct-19 A | 30-Sep-20 A |  |  | 245 | 0 |  | Budgeted Units | 165 | 80
S307610 | Magnet Field Measurements: Design mounts for probes to monitor field - CA-D Resource(s) | 03-Feb-20 A | 14-Feb-20 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units | 8
S307921 | Magnet Field Measurements: Perform Magnet Assembly Stress Analysis FY19 - CA-D Resource(s) Split_70% | 01-Oct-19 A | 31-Dec-19 A | PROF4 AD | PROF4 AD | 48 | 0 | C | Budgeted Units | 48
S307923 | Final Field Calculations Pre-measurement - CAD | 21-Sep-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units |  | 60
S307710 | Magnet Field Measurements: Design readout for probes to monitor field - CA-D Resource(s) | 18-Feb-20 A | 24-Feb-20 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units | 4
S307600 | Magnet Field Measurements: Design mounts for probes to monitor field - Physics Resource(s) | 03-Feb-20 A | 14-Feb-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S307700 | Magnet Field Measurements: Design readout for probes to monitor field - Physics Resource(s) | 18-Feb-20 A | 24-Feb-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S307511 | Magnet Field Measurements: Setup a detailed 3D model of the coil, return yoke and internal calorimeters FY19 Split_60% | 01-Oct-19 A | 31-Dec-19 A | SCI3 PO | SCI3 PO | 19 | 0 | C | Budgeted Units | 19
S307511 | Magnet Field Measurements: Setup a detailed 3D model of the coil, return yoke and internal calorimeters FY19 Split_60% | 01-Oct-19 A | 31-Dec-19 A | TECH3 PO D | TECH3 PO D | 6 | 0 | C | Budgeted Units | 6
S307922 | Final Field Calculations Pre-measurement - Phys | 21-Sep-20 A | 30-Sep-20 A | SCI4 PO | SCI 4 PO | 20 | 0 | C | Budgeted Units |  | 20
POM02-13.02.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication |  | 16-Jan-20 A | 2023-01-17 |  |  | 654 | 98 |  | Budgeted Units | 404 | 138 |  | 112
S308611 | Specify and test probes for field monitoring | 01-Oct-20 A | 31-Dec-20 A | SCI4 PO | SCI 4 PO | 16 | 0 | C | Budgeted Units |  | 16
S308611 | Specify and test probes for field monitoring | 01-Oct-20 A | 31-Dec-20 A | PROF4 PO E | PROF4 PO E | 16 | 0 | C | Budgeted Units |  | 16
S308611 | Specify and test probes for field monitoring | 01-Oct-20 A | 31-Dec-20 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  | 16
S308615 | Develop readout electronics | 30-Oct-20 A | 30-Jun-22 A | PROF4 PO E | PROF4 PO E | 90 | 0 | C | Budgeted Units |  | 90
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | SCI4 PO | SCI 4 PO | 24 | 19 | C | Budgeted Units |  |  |  | 24
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | PROF4 PO E | PROF4 PO E | 24 | 19 | C | Budgeted Units |  |  |  | 24
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | TECH3 PO E | TECH3 PO E | 24 | 19 | C | Budgeted Units |  |  |  | 24
S308619 | Install probes and readout on TPC | 2023-01-03 | 2023-01-17 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S308300 | Magnet Field Measurements: Procure NMR probe readout parts Labor | 24-Jan-20 A | 24-Apr-20 A | PROF4 PO M | PROF4 PO M | 10 | 0 | C | Budgeted Units | 10
S308100 | Magnet Field Measurements: Procure NMR probes Labor | 24-Jan-20 A | 20-Mar-20 A | PROF4 PO M | PROF4 PO M | 10 | 0 | C | Budgeted Units | 10
S308500 | Magnet Field Measurements: Fabricate NMR probe readout parts | 01-May-20 A | 29-May-20 A | SCI3 PO | SCI3 PO | 16 | 0 | C | Budgeted Units | 16
S308500 | Magnet Field Measurements: Fabricate NMR probe readout parts | 01-May-20 A | 29-May-20 A | TECH3 PO D | TECH3 PO D | 160 | 0 | C | Budgeted Units | 160
S308500 | Magnet Field Measurements: Fabricate NMR probe readout parts | 01-May-20 A | 29-May-20 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units | 16
S308600 | Magnet Field Measurements: Fabricate NMR probe mounts - Physics Resource(s) | 16-Jan-20 A | 24-Apr-20 A | TECH3 PO D | TECH3 PO D | 160 | 0 | C | Budgeted Units | 160
S308600 | Magnet Field Measurements: Fabricate NMR probe mounts - Physics Resource(s) | 16-Jan-20 A | 24-Apr-20 A | SCI3 PO | SCI3 PO | 16 | 0 | C | Budgeted Units | 16
S308610 | Magnet Field Measurements: Fabricate NMR probe mounts - CA-D Resource(s) | 01-May-20 A | 29-May-20 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units | 16
POM02-13.02.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis |  | 24-Jan-20 A | 2022-12-22 |  |  | 1560 | 1189 |  | Budgeted Units | 80 | 218 | 87 | 1176
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Budgeted Units |  |  |  | 160
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | SCI4 PO | SCI 4 PO | 160 | 160 | C | Budgeted Units |  |  |  | 160
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | SCI4 PO | SCI 4 PO | 160 | 160 | C | Budgeted Units |  |  |  | 160
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Budgeted Units |  |  |  | 160
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 2022-11-16 | 2022-11-22 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 2022-11-16 | 2022-11-22 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S308625 | Complete MOU with Vendor | 22-Feb-21 A | 13-Jul-22 A | SCI4 PO | SCI 4 PO | 8 | 0 | C | Budgeted Units |  |  | 8
S308621 | Conceptual design of mapping campaign | 01-Oct-20 A | 30-Jun-22 A | SCI4 PO | SCI 4 PO | 32 | 0 | C | Budgeted Units |  | 32
S308623 | Develop mapping plan with Vendor | 30-Oct-20 A | 30-Jun-22 A | SCI4 PO | SCI 4 PO | 100 | 0 | C | Budgeted Units |  | 100
S308629 | Complete mechanical and electrical design for mapping | 23-Nov-20 A | 31-Aug-22 A | PROF4 PO M | PROF4 PO M | 60 | 0 | C | Budgeted Units |  | 57 | 3
S308631 | Review mapping plan | 01-Jun-22 A | 27-Jun-22 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S309110 | Receive report from CERN, incorporate into analysis | 2022-11-23 | 2022-12-22 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Budgeted Units |  |  |  | 16
S308629 | Complete mechanical and electrical design for mapping | 23-Nov-20 A | 31-Aug-22 A | TECH3 PO D | TECH3 PO D | 30 | 0 | C | Budgeted Units |  | 29 | 2
S308631 | Review mapping plan | 01-Jun-22 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S308631 | Review mapping plan | 01-Jun-22 A | 27-Jun-22 A | SCI4 PO | SCI 4 PO | 10 | 0 | C | Budgeted Units |  |  | 10
S308633 | Construct mapping support (mechanical and electrical) | 08-Mar-21 A | 2022-11-01 | TECH3 PO M | TECH3 PO M | 32 | 13 | C | Budgeted Units |  |  | 32
S308700 | Magnet Field Measurements: Run 3D field simulations and construct field and force maps - Physics Resource(s) | 24-Jan-20 A | 24-Feb-20 A | SCI3 PO | SCI3 PO | 40 | 0 | C | Budgeted Units | 40
S308710 | Magnet Field Measurements: Run 3D field simulations and construct field and force maps - CA-D Resource(s) | 24-Jan-20 A | 24-Feb-20 A | SCI3 AD | SCI3 AD | 40 | 0 | C | Budgeted Units | 40
POM02-13.02.03 Carriage and Structural Components |  | 01-Oct-19 A | 2022-11-14 |  |  | 16166 | 172 |  | Budgeted Units | 8859 | 5584 | 1502 | 220
POM02-13.02.03.01 Cradle Carriage |  | 01-Oct-19 A | 29-Jul-22 A |  |  | 5198 | 0 |  | Budgeted Units | 4190 | 1008
S313300 | CC Seismic Restraints - Engineer & Analysis | 28-Oct-19 A | 31-Mar-20 A | PROF4 AD | PROF4 AD | 240 | 0 | C | Budgeted Units | 240
S310410 | Carriage Cradle - Prepare Procurement Package(s) - CA-D Resource(s) | 01-Oct-19 A | 15-Nov-19 A | PROF4 AD | PROF4 AD | 24 | 0 | C | Budgeted Units | 24
S310910 | Carriage Cradle - Vendor Selection - CA-D Resource(s) | 20-Mar-20 A | 25-Mar-20 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units | 20
S311110 | Carriage Cradle - BNL Oversight - CA-D Resource(s) | 06-May-20 A | 26-Jan-21 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units | 23 | 17
S311310 | Carriage Cradle - Delivery Acceptance - CA-D Resource(s) - Labor | 02-Sep-20 A | 30-Dec-20 A | PROF4 AD | PROF4 AD | 32 | 0 | C | Budgeted Units | 32
S310510 | Carriage Cradle - Procurement Readiness Review - CA-D Resource(s) | 18-Nov-19 A | 22-Nov-19 A | PROF4 AD | PROF4 AD | 24 | 0 | C | Budgeted Units | 24
S311510 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - CA-D Resource(s) | 14-May-20 A | 30-Oct-20 A | PROF4 AD | PROF4 AD | 160 | 0 | C | Budgeted Units | 160
S311610 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - CA-D Resource(s) | 14-Oct-20 A | 30-Oct-20 A | PROF4 AD | PROF4 AD | 160 | 0 | C | Budgeted Units |  | 160
S311810 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - CA-D Resource(s) | 18-Oct-19 A | 30-Apr-20 A | PROF4 AD | PROF4 AD | 30 | 0 | C | Budgeted Units | 30
S312010 | CC Drive & Alignment System - Assembly & Detail Drawings - CA-D Resource(s) | 01-Apr-20 A | 01-Sep-20 A | PROF4 AD | PROF4 AD | 120 | 0 | C | Budgeted Units | 120
S315010 | Steel Track Modifications - Final Design Reviews (Design & Safety) | 30-Oct-19 A | 31-Oct-19 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units | 8
S315110 | Steel Track Modifications - Address Action Items from Design & Safety Reviews | 01-Nov-19 A | 15-Nov-19 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units | 8
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 17-Dec-19 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 80 | 0 | C | Budgeted Units | 80
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 0 | 0 | C | Budgeted Units
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 0 | 0 | C | Budgeted Units
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 0 | 0 | C | Budgeted Units
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 0 | 0 | C | Budgeted Units
S310810 | Carriage Cradle - Vendor Responses - CA-D Resource(s) | 08-Jan-20 A | 19-Mar-20 A | PROF4 AD | PROF4 AD | 36 | 0 | C | Budgeted Units | 36
S312110 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 14-Apr-20 A | 30-Apr-20 A | PROF4 AD | PROF4 AD | 80 | 0 | C | Budgeted Units | 80
S312310 | CC Drive & Alignment System - Prepare Procurement Package - CA-D Resource(s) | 28-Jul-20 A | 21-Oct-20 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units | 20
S312410 | CC Drive & Alignment System - Procurement Readiness Review - CA-D Resource(s) | 01-Oct-20 A | 07-Oct-20 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units |  | 20
S312210 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 21-Apr-20 A | 14-Oct-20 A | PROF4 AD | PROF4 AD | 80 | 0 | C | Budgeted Units | 80
S312810 | CC Drive & Alignment System - Vendor Selection - CA-D Resource(s) | 23-Oct-20 A | 28-Oct-20 A | PROF4 AD | PROF4 AD | 18 | 0 | C | Budgeted Units |  | 18
S313010 | CC Drive & Alignment System - BNL Oversight - CA-D Resource(s) | 03-Nov-20 A | 15-Apr-21 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units |  | 20
S313210 | CC Drive & Alignment System - Delivery Acceptance - CA-D Resource(s) - Labor | 12-Apr-21 A | 15-Apr-21 A | PROF4 AD | PROF4 AD | 32 | 0 | C | Budgeted Units |  | 32
S312710 | CC Drive & Alignment System - Vendor Responses - CA-D Resource(s) | 23-Oct-20 A | 28-Oct-20 A | PROF4 AD | PROF4 AD | 18 | 0 | C | Budgeted Units |  | 18
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 0 | 0 | C | Budgeted Units
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 0 | 0 | C | Budgeted Units
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 01-Jul-22 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 0 | 0 | C | Budgeted Units
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 0 | 0 | C | Budgeted Units
S315910 | Steel Track Modifications - BNL Oversight Construction - CA-D Resource(s) | 18-Nov-19 A | 31-Jan-20 A | PROF4 AD | PROF4 AD | 120 | 0 | C | Budgeted Units | 120
S310016 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) Split_10% | 01-Oct-19 A | 29-Nov-19 A | PROF4 AD | PROF4 AD | 10 | 0 | C | Budgeted Units | 10
S310211 | Carriage Cradle - Address Action Items from Design & Safety Reviews - CA-D Resource(s)_75% | 01-Oct-19 A | 17-Oct-19 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units | 60
S310410 | Carriage Cradle - Prepare Procurement Package(s) - CA-D Resource(s) | 01-Oct-19 A | 15-Nov-19 A | TECH3 AD | TECH3 AD | 24 | 0 | C | Budgeted Units | 24
S310910 | Carriage Cradle - Vendor Selection - CA-D Resource(s) | 20-Mar-20 A | 25-Mar-20 A | TECH3 AD | TECH3 AD | 36 | 0 | C | Budgeted Units | 36
S311110 | Carriage Cradle - BNL Oversight - CA-D Resource(s) | 06-May-20 A | 26-Jan-21 A | TECH3 AD | TECH3 AD | 10 | 0 | C | Budgeted Units | 6 | 4
S311310 | Carriage Cradle - Delivery Acceptance - CA-D Resource(s) - Labor | 02-Sep-20 A | 30-Dec-20 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units | 16
S310510 | Carriage Cradle - Procurement Readiness Review - CA-D Resource(s) | 18-Nov-19 A | 22-Nov-19 A | TECH3 AD | TECH3 AD | 12 | 0 | C | Budgeted Units | 12
S311510 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - CA-D Resource(s) | 14-May-20 A | 30-Oct-20 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units | 80
S311610 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - CA-D Resource(s) | 14-Oct-20 A | 30-Oct-20 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  | 80
S311810 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - CA-D Resource(s) | 18-Oct-19 A | 30-Apr-20 A | TECH3 AD | TECH3 AD | 15 | 0 | C | Budgeted Units | 15
S312010 | CC Drive & Alignment System - Assembly & Detail Drawings - CA-D Resource(s) | 01-Apr-20 A | 01-Sep-20 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units | 240
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 17-Dec-19 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 120 | 0 | C | Budgeted Units | 120
S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S310810 | Carriage Cradle - Vendor Responses - CA-D Resource(s) | 08-Jan-20 A | 19-Mar-20 A | TECH3 AD | TECH3 AD | 36 | 0 | C | Budgeted Units | 36
S312110 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 14-Apr-20 A | 30-Apr-20 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units | 40
S312310 | CC Drive & Alignment System - Prepare Procurement Package - CA-D Resource(s) | 28-Jul-20 A | 21-Oct-20 A | TECH3 AD | TECH3 AD | 20 | 0 | C | Budgeted Units | 20
S312410 | CC Drive & Alignment System - Procurement Readiness Review - CA-D Resource(s) | 01-Oct-20 A | 07-Oct-20 A | TECH3 AD | TECH3 AD | 20 | 0 | C | Budgeted Units |  | 20
S312210 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 21-Apr-20 A | 14-Oct-20 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units | 40
S312810 | CC Drive & Alignment System - Vendor Selection - CA-D Resource(s) | 23-Oct-20 A | 28-Oct-20 A | TECH3 AD | TECH3 AD | 18 | 0 | C | Budgeted Units |  | 18
S313010 | CC Drive & Alignment System - BNL Oversight - CA-D Resource(s) | 03-Nov-20 A | 15-Apr-21 A | TECH3 AD | TECH3 AD | 10 | 0 | C | Budgeted Units |  | 10
S313210 | CC Drive & Alignment System - Delivery Acceptance - CA-D Resource(s) - Labor | 12-Apr-21 A | 15-Apr-21 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units |  | 16
S312710 | CC Drive & Alignment System - Vendor Responses - CA-D Resource(s) | 23-Oct-20 A | 28-Oct-20 A | TECH3 AD | TECH3 AD | 18 | 0 | C | Budgeted Units |  | 18
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 01-Jul-22 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S310016 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) Split_10% | 01-Oct-19 A | 29-Nov-19 A | TECH3 AD | TECH3 AD | 19 | 0 | C | Budgeted Units | 19
S310211 | Carriage Cradle - Address Action Items from Design & Safety Reviews - CA-D Resource(s)_75% | 01-Oct-19 A | 17-Oct-19 A | TECH3 AD | TECH3 AD | 45 | 0 | C | Budgeted Units | 45
S313300 | CC Seismic Restraints - Engineer & Analysis | 28-Oct-19 A | 31-Mar-20 A | PROF5 AD | PROF5 AD | 120 | 0 | C | Budgeted Units | 120
S310600 | Carriage Cradle - Provide Requirement to Procurement | 25-Nov-19 A | 31-Dec-19 A | PROF5 AD | PROF5 AD | 8 | 0 | C | Budgeted Units | 8
S312500 | CC Drive & Alignment System - Provide Requirement to Procurement | 08-Oct-20 A | 15-Oct-20 A | PROF5 AD | PROF5 AD | 8 | 0 | C | Budgeted Units |  | 8
S313900 | CC Seismic Restraints - Provide Requirement to Procurement | 01-Jul-22 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 0 | 0 | C | Budgeted Units
S310410 | Carriage Cradle - Prepare Procurement Package(s) - CA-D Resource(s) | 01-Oct-19 A | 15-Nov-19 A | PROF5 AD | PROF5 AD | 20 | 0 | C | Budgeted Units | 20
S310910 | Carriage Cradle - Vendor Selection - CA-D Resource(s) | 20-Mar-20 A | 25-Mar-20 A | PROF5 AD | PROF5 AD | 20 | 0 | C | Budgeted Units | 20
S311110 | Carriage Cradle - BNL Oversight - CA-D Resource(s) | 06-May-20 A | 26-Jan-21 A | PROF5 AD | PROF5 AD | 40 | 0 | C | Budgeted Units | 23 | 17
S311310 | Carriage Cradle - Delivery Acceptance - CA-D Resource(s) - Labor | 02-Sep-20 A | 30-Dec-20 A | PROF5 AD | PROF5 AD | 8 | 0 | C | Budgeted Units | 8
S311510 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - CA-D Resource(s) | 14-May-20 A | 30-Oct-20 A | PROF5 AD | PROF5 AD | 80 | 0 | C | Budgeted Units | 80
S311610 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - CA-D Resource(s) | 14-Oct-20 A | 30-Oct-20 A | PROF5 AD | PROF5 AD | 80 | 0 | C | Budgeted Units |  | 80
S311810 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - CA-D Resource(s) | 18-Oct-19 A | 30-Apr-20 A | PROF5 AD | PROF5 AD | 64 | 0 | C | Budgeted Units | 64
S312010 | CC Drive & Alignment System - Assembly & Detail Drawings - CA-D Resource(s) | 01-Apr-20 A | 01-Sep-20 A | PROF5 AD | PROF5 AD | 80 | 0 | C | Budgeted Units | 80
S313410 | CC Seismic Restraints - Assembly & Detail Drawings - CA-D Resource(s) | 17-Dec-19 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 40 | 0 | C | Budgeted Units | 40
S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 0 | 0 | C | Budgeted Units
S313710 | CC Seismic Restraints - Prepare Procurement Package - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 0 | 0 | C | Budgeted Units
S313810 | CC Seismic Restraints - Procurement Readiness Review - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 0 | 0 | C | Budgeted Units
S310810 | Carriage Cradle - Vendor Responses - CA-D Resource(s) | 08-Jan-20 A | 19-Mar-20 A | PROF5 AD | PROF5 AD | 36 | 0 | C | Budgeted Units | 36
S312110 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 14-Apr-20 A | 30-Apr-20 A | PROF5 AD | PROF5 AD | 40 | 0 | C | Budgeted Units | 40
S312310 | CC Drive & Alignment System - Prepare Procurement Package - CA-D Resource(s) | 28-Jul-20 A | 21-Oct-20 A | PROF5 AD | PROF5 AD | 8 | 0 | C | Budgeted Units | 8
S312410 | CC Drive & Alignment System - Procurement Readiness Review - CA-D Resource(s) | 01-Oct-20 A | 07-Oct-20 A | PROF5 AD | PROF5 AD | 8 | 0 | C | Budgeted Units |  | 8
S312210 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 21-Apr-20 A | 14-Oct-20 A | PROF5 AD | PROF5 AD | 40 | 0 | C | Budgeted Units | 40
S312810 | CC Drive & Alignment System - Vendor Selection - CA-D Resource(s) | 23-Oct-20 A | 28-Oct-20 A | PROF5 AD | PROF5 AD | 8 | 0 | C | Budgeted Units |  | 8
S313010 | CC Drive & Alignment System - BNL Oversight - CA-D Resource(s) | 03-Nov-20 A | 15-Apr-21 A | PROF5 AD | PROF5 AD | 20 | 0 | C | Budgeted Units |  | 20
S313210 | CC Drive & Alignment System - Delivery Acceptance - CA-D Resource(s) - Labor | 12-Apr-21 A | 15-Apr-21 A | PROF5 AD | PROF5 AD | 4 | 0 | C | Budgeted Units |  | 4
S312710 | CC Drive & Alignment System - Vendor Responses - CA-D Resource(s) | 23-Oct-20 A | 28-Oct-20 A | PROF5 AD | PROF5 AD | 8 | 0 | C | Budgeted Units |  | 8
S314210 | CC Seismic Restraints - Vendor Selection - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 0 | 0 | C | Budgeted Units
S314410 | CC Seismic Restraints - BNL Oversight - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 0 | 0 | C | Budgeted Units
S314610 | CC Seismic Restraints - Delivery Acceptance - CA-D Resource(s) - Labor | 01-Jul-22 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 0 | 0 | C | Budgeted Units
S314110 | CC Seismic Restraints - Vendor Responses - CA-D Resource(s) | 01-Jul-22 A | 29-Jul-22 A | PROF5 AD | PROF5 AD | 0 | 0 | C | Budgeted Units
S315925 | Steel Track Modifications - Inspection As-Builts and Punchlists CA-D | 03-Feb-20 A | 30-Oct-20 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units | 60
S316005 | Steel Track Modifications - Finish Track Work Labor | 15-Oct-20 A | 30-Jul-21 A | PROF3 AD | PROF3 AD | 24 | 0 | C | Budgeted Units |  | 24
S310016 | Carriage Cradle - Create Assembly & Detail Drawings - CA-D Resource(s) Split_10% | 01-Oct-19 A | 29-Nov-19 A | PROF5 AD | PROF5 AD | 10 | 0 | C | Budgeted Units | 10
S310211 | Carriage Cradle - Address Action Items from Design & Safety Reviews - CA-D Resource(s)_75% | 01-Oct-19 A | 17-Oct-19 A | PROF5 AD | PROF5 AD | 30 | 0 | C | Budgeted Units | 30
S311900 | CC Drive & Alignment System - Design Carriage Controls & Limits | 02-Dec-19 A | 01-Sep-20 A | PROF4 PO E | PROF4 PO E | 120 | 0 | C | Budgeted Units | 120
S315910 | Steel Track Modifications - BNL Oversight Construction - CA-D Resource(s) | 18-Nov-19 A | 31-Jan-20 A | CRAFT3 | CRAFT3 | 300 | 0 | C | Budgeted Units | 300
S316005 | Steel Track Modifications - Finish Track Work Labor | 15-Oct-20 A | 30-Jul-21 A | CRAFT3 | CRAFT3 | 40 | 0 | C | Budgeted Units |  | 40
S310400 | Carriage Cradle - Prepare Procurement Package(s) - Physics Resource(s) | 01-Oct-19 A | 15-Nov-19 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units | 24
S310400 | Carriage Cradle - Prepare Procurement Package(s) - Physics Resource(s) | 01-Oct-19 A | 15-Nov-19 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units | 24
S310900 | Carriage Cradle - Vendor Selection - Physics Resource(s) | 20-Mar-20 A | 25-Mar-20 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units | 36
S310900 | Carriage Cradle - Vendor Selection - Physics Resource(s) | 20-Mar-20 A | 25-Mar-20 A | TECH3 PO M | TECH3 PO M | 72 | 0 | C | Budgeted Units | 72
S311100 | Carriage Cradle - BNL Oversight - Physics Resource(s) | 06-May-20 A | 26-Jan-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units | 6 | 4
S311100 | Carriage Cradle - BNL Oversight - Physics Resource(s) | 06-May-20 A | 26-Jan-21 A | TECH3 PO M | TECH3 PO M | 40 | 0 | C | Budgeted Units | 23 | 17
S311300 | Carriage Cradle - Delivery Acceptance - Physics Resource(s) - Labor | 02-Sep-20 A | 30-Dec-20 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units | 16
S311300 | Carriage Cradle - Delivery Acceptance - Physics Resource(s) - Labor | 02-Sep-20 A | 30-Dec-20 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units | 80
S310500 | Carriage Cradle - Procurement Readiness Review - Physics Resource(s) | 18-Nov-19 A | 22-Nov-19 A | TECH3 PO D | TECH3 PO D | 12 | 0 | C | Budgeted Units | 12
S310500 | Carriage Cradle - Procurement Readiness Review - Physics Resource(s) | 18-Nov-19 A | 22-Nov-19 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units | 24
S311500 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering - Physics Resource(s) | 14-May-20 A | 30-Oct-20 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units | 80
S311600 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design - Physics Resource(s) | 14-Oct-20 A | 30-Oct-20 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units |  | 80
S311800 | CC Drive & Alignment System - Engineering (re-engineer & use STAR controller?) - Physics Resource(s) | 18-Oct-19 A | 30-Apr-20 A | TECH3 PO D | TECH3 PO D | 15 | 0 | C | Budgeted Units | 15
S312000 | CC Drive & Alignment System - Assembly & Detail Drawings - Physics Resource(s) | 01-Apr-20 A | 01-Sep-20 A | TECH3 PO D | TECH3 PO D | 240 | 0 | C | Budgeted Units | 240
S313400 | CC Seismic Restraints - Assembly & Detail Drawings - Physics Resource(s) | 17-Dec-19 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 120 | 0 | C | Budgeted Units | 120
S313500 | CC Seismic Restraints - Final Design Reviews (Design & Safety) - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S313600 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S313700 | CC Seismic Restraints - Prepare Procurement Package - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S313800 | CC Seismic Restraints - Procurement Readiness Review - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S310800 | Carriage Cradle - Vendor Responses - Physics Resource(s) | 08-Jan-20 A | 19-Mar-20 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units | 36
S312100 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) - Physics Resource(s) | 14-Apr-20 A | 30-Apr-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S312300 | CC Drive & Alignment System - Prepare Procurement Package - Physics Resource(s) | 28-Jul-20 A | 21-Oct-20 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units | 20
S312400 | CC Drive & Alignment System - Procurement Readiness Review - Physics Resource(s) | 01-Oct-20 A | 07-Oct-20 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  | 20
S312200 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 21-Apr-20 A | 14-Oct-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S312800 | CC Drive & Alignment System - Vendor Selection - Physics Resource(s) | 23-Oct-20 A | 28-Oct-20 A | TECH3 PO D | TECH3 PO D | 18 | 0 | C | Budgeted Units |  | 18
S312800 | CC Drive & Alignment System - Vendor Selection - Physics Resource(s) | 23-Oct-20 A | 28-Oct-20 A | TECH3 PO M | TECH3 PO M | 36 | 0 | C | Budgeted Units |  | 36
S313000 | CC Drive & Alignment System - BNL Oversight - Physics Resource(s) | 03-Nov-20 A | 15-Apr-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units |  | 10
S313000 | CC Drive & Alignment System - BNL Oversight - Physics Resource(s) | 03-Nov-20 A | 15-Apr-21 A | TECH3 PO M | TECH3 PO M | 40 | 0 | C | Budgeted Units |  | 40
S313200 | CC Drive & Alignment System - Delivery Acceptance - Physics Resource(s) - Labor | 12-Apr-21 A | 15-Apr-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S313200 | CC Drive & Alignment System - Delivery Acceptance - Physics Resource(s) - Labor | 12-Apr-21 A | 15-Apr-21 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units |  | 80
S312700 | CC Drive & Alignment System - Vendor Responses - Physics Resource(s) | 23-Oct-20 A | 28-Oct-20 A | TECH3 PO D | TECH3 PO D | 18 | 0 | C | Budgeted Units |  | 18
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S314200 | CC Seismic Restraints - Vendor Selection - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S314400 | CC Seismic Restraints - BNL Oversight - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S314600 | CC Seismic Restraints - Delivery Acceptance - Physics Resource(s) - Labor | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S314100 | CC Seismic Restraints - Vendor Responses - Physics Resource(s) | 01-Jul-22 A | 29-Jul-22 A | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S315900 | Steel Track Modifications - BNL Oversight Construction - Physics Resource(s) | 18-Nov-19 A | 31-Jan-20 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units | 80
S315915 | Steel Track Modifications - Inspection As-Builts and Punchlists Phys | 03-Feb-20 A | 30-Oct-20 A | TECH3 PO D | TECH3 PO D | 60 | 0 | C | Budgeted Units | 60
S310006 | Carriage Cradle - Create Assembly & Detail Drawings - Physics Resource(s) Split_10% | 01-Oct-19 A | 29-Nov-19 A | TECH3 PO D | TECH3 PO D | 19 | 0 | C | Budgeted Units | 19
S310006 | Carriage Cradle - Create Assembly & Detail Drawings - Physics Resource(s) Split_10% | 01-Oct-19 A | 29-Nov-19 A | TECH3 PO M | TECH3 PO M | 3 | 0 | C | Budgeted Units | 3
S310201 | Carriage Cradle - Address Action Items from Design & Safety Reviews - Physics Resource(s)_75% | 01-Oct-19 A | 17-Oct-19 A | TECH3 PO D | TECH3 PO D | 45 | 0 | C | Budgeted Units | 45
S310201 | Carriage Cradle - Address Action Items from Design & Safety Reviews - Physics Resource(s)_75% | 01-Oct-19 A | 17-Oct-19 A | SCI3 PO | SCI3 PO | 6 | 0 | C | Budgeted Units | 6
S310201 | Carriage Cradle - Address Action Items from Design & Safety Reviews - Physics Resource(s)_75% | 01-Oct-19 A | 17-Oct-19 A | TECH3 PO M | TECH3 PO M | 6 | 0 | C | Budgeted Units | 6
S314716 | Steel Track Modifications - Structural Analysis of Existing Steel Track System & Preliminary Design_85% | 01-Oct-19 A | 30-Oct-19 A | TECH3 PO D | TECH3 PO D | 34 | 0 | C | Budgeted Units | 34
POM02-13.02.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports |  | 01-Nov-19 A | 2022-11-14 |  |  | 5135 | 172 |  | Budgeted Units | 191 | 3615 | 1110 | 220
S316510 | Create Internal Detector Structural Support Assembly Drawings - CA-D Resource(s) | 13-May-20 A | 29-Jan-21 A | PROF4 AD | PROF4 AD | 64 | 0 | C | Budgeted Units | 64
S316610 | Create Internal Detector Structural Support Detail Drawings - CA-D Resource(s) | 11-Jan-21 A | 18-Jan-21 A | PROF4 AD | PROF4 AD | 48 | 0 | C | Budgeted Units |  | 48
S316710 | Review Internal Detector Structural Support Safety - CA-D Resource(s) | 19-Jan-21 A | 28-Jan-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S316810 | Review Internal Detector Structural Support Design - CA-D Resource(s) | 19-Jan-21 A | 28-Jan-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S316910 | Address Action Items from Internal Detector Structural Support Design & Safety Reviews - CA-D Resource(s) | 29-Jan-21 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units |  | 40
S317110 | Prepare Procurement Package(s) for Inner HCal Support Tabs - CA-D Resource(s) | 15-Apr-21 A | 30-Jun-21 A | PROF4 AD | PROF4 AD | 120 | 0 | C | Budgeted Units |  | 120
S317210 | Evaluate & Process Bid for IHCal Support Tabs - CA-D Resource(s) | 02-Jul-21 A | 27-Jul-21 A | PROF4 AD | PROF4 AD | 32 | 0 | C | Budgeted Units |  | 32
S318010 | Perform Inner HCal Support Tabs Acceptance - CA-D Resource(s) | 14-Sep-21 A | 29-Sep-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S316600 | Create Internal Detector Structural Support Detail Drawings - Physics Resource(s) | 11-Jan-21 A | 18-Jan-21 A | TECH3 PO D | TECH3 PO D | 50 | 0 | C | Budgeted Units |  | 50
S316700 | Review Internal Detector Structural Support Safety - Physics Resource(s) | 19-Jan-21 A | 28-Jan-21 A | TECH3 PO D | TECH3 PO D | 4 | 0 | C | Budgeted Units |  | 4
S316700 | Review Internal Detector Structural Support Safety - Physics Resource(s) | 19-Jan-21 A | 28-Jan-21 A | TECH3 PO M | TECH3 PO M | 4 | 0 | C | Budgeted Units |  | 4
S316800 | Review Internal Detector Structural Support Design - Physics Resource(s) | 19-Jan-21 A | 28-Jan-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S316800 | Review Internal Detector Structural Support Design - Physics Resource(s) | 19-Jan-21 A | 28-Jan-21 A | TECH3 PO M | TECH3 PO M | 4 | 0 | C | Budgeted Units |  | 4
S316900 | Address Action Items from Internal Detector Structural Support Design & Safety Reviews - Physics Resource(s) | 29-Jan-21 A | 26-Feb-21 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  | 20
S317100 | Prepare Procurement Package(s) for Inner HCal Support Tabs - Physics Resource(s) | 15-Apr-21 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 24
S317100 | Prepare Procurement Package(s) for Inner HCal Support Tabs - Physics Resource(s) | 15-Apr-21 A | 30-Jun-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  | 24
S317200 | Evaluate & Process Bid for Inner HCal Support Tabs - Physics Resource(s) | 02-Jul-21 A | 27-Jul-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S317200 | Evaluate & Process Bid for Inner HCal Support Tabs - Physics Resource(s) | 02-Jul-21 A | 27-Jul-21 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  | 16
S318000 | Perform Inner HCal Support Tabs Acceptance - Physics Resource(s) | 14-Sep-21 A | 29-Sep-21 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  |  | 20
S318000 | Perform Inner HCal Support Tabs Acceptance - Physics Resource(s) | 14-Sep-21 A | 29-Sep-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S317400 | Procure IHCal Support Tabs - Provide Requirements to Procurement | 12-Jul-21 A | 19-Jul-21 A | PROF3 PO M | PROF3 PO M | 32 | 0 | C | Budgeted Units |  | 32
S317600 | Procure IHCal Support Tabs - Vendor Response and Selection | 01-Jul-21 A | 23-Jul-21 A | PROF3 PO M | PROF3 PO M | 32 | 0 | C | Budgeted Units |  | 32
S316505 | Create Internal Detector Structural Support Assembly Drawings - Physics Resource(s) Split | 13-May-20 A | 29-Jan-21 A | TECH3 PO D | TECH3 PO D | 48 | 0 | C | Budgeted Units | 48
S317020 | Create Magnet Supports Detailed Design Drawings | 15-Sep-20 A | 30-Dec-20 A | PROF3 PO E | PROF3 PO E | 220 | 0 | C | Budgeted Units |  | 220
S317020 | Create Magnet Supports Detailed Design Drawings | 15-Sep-20 A | 30-Dec-20 A | PROF3 PO M | PROF3 PO M | 300 | 0 | C | Budgeted Units |  | 300
S317021 | Review Design and Safety Magnet Supports | 01-Dec-20 A | 02-Dec-20 A | PROF3 PO E | PROF3 PO E | 4 | 0 | C | Budgeted Units |  | 4
S317021 | Review Design and Safety Magnet Supports | 01-Dec-20 A | 02-Dec-20 A | PROF3 PO M | PROF3 PO M | 4 | 0 | C | Budgeted Units |  | 4
S317022 | Address Action Items for Magnet Supports | 03-Dec-20 A | 26-Feb-21 A | PROF3 PO E | PROF3 PO E | 4 | 0 | C | Budgeted Units |  | 4
S317022 | Address Action Items for Magnet Supports | 03-Dec-20 A | 26-Feb-21 A | PROF3 PO M | PROF3 PO M | 4 | 0 | C | Budgeted Units |  | 4
S317030 | Create EMCal Supports Detailed Design Drawings | 08-Oct-20 A | 28-Oct-20 A | PROF3 PO E | PROF3 PO E | 100 | 0 | C | Budgeted Units |  | 100
S317030 | Create EMCal Supports Detailed Design Drawings | 08-Oct-20 A | 28-Oct-20 A | PROF3 PO M | PROF3 PO M | 120 | 0 | C | Budgeted Units |  | 120
S317031 | Review Design and Safety EMCal Supports | 08-Oct-20 A | 28-Oct-20 A | PROF3 PO E | PROF3 PO E | 0 | 0 | C | Budgeted Units |  | 0
S317031 | Review Design and Safety EMCal Supports | 08-Oct-20 A | 28-Oct-20 A | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units |  | 0
S317032 | Address Action Items for EMCal Supports | 08-Oct-20 A | 28-Oct-20 A | PROF3 PO E | PROF3 PO E | 0 | 0 | C | Budgeted Units |  | 0
S317032 | Address Action Items for EMCal Supports | 08-Oct-20 A | 28-Oct-20 A | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units |  | 0
S317040 | Create TPC Supports Detailed Design Drawings | 17-Nov-20 A | 31-Jan-22 A | PROF3 PO E | PROF3 PO E | 80 | 0 | C | Budgeted Units |  | 80
S317040 | Create TPC Supports Detailed Design Drawings | 17-Nov-20 A | 31-Jan-22 A | PROF3 PO M | PROF3 PO M | 160 | 0 | C | Budgeted Units |  | 160
S317041 | Review Design and Safety TPC Supports | 22-Sep-21 A | 14-Jan-22 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S317041 | Review Design and Safety TPC Supports | 22-Sep-21 A | 14-Jan-22 A | PROF3 PO M | PROF3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S317042 | Address Action Items for TPC Supports | 14-Jan-22 A | 18-Jan-22 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S317042 | Address Action Items for TPC Supports | 14-Jan-22 A | 18-Jan-22 A | PROF3 PO M | PROF3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S317050 | Create INTT Supports Detailed Design Drawings | 13-May-20 A | 30-Nov-21 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  | 40
S317050 | Create INTT Supports Detailed Design Drawings | 13-May-20 A | 30-Nov-21 A | PROF3 PO M | PROF3 PO M | 160 | 0 | C | Budgeted Units |  | 160
S317051 | Review Design and Safety INTT Supports | 07-Sep-21 A | 30-Nov-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S317051 | Review Design and Safety INTT Supports | 07-Sep-21 A | 30-Nov-21 A | PROF3 PO M | PROF3 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S317052 | Address Action Items for INTT Supports | 18-Nov-21 A | 30-Nov-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S317052 | Address Action Items for INTT Supports | 18-Nov-21 A | 30-Nov-21 A | PROF3 PO M | PROF3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S317060 | Create MVTX Supports Detailed Design Drawings | 19-May-20 A | 28-May-21 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  | 40
S317060 | Create MVTX Supports Detailed Design Drawings | 19-May-20 A | 28-May-21 A | PROF3 PO M | PROF3 PO M | 160 | 0 | C | Budgeted Units |  | 160
S317061 | Review Design and Safety MVTX Supports | 21-Dec-20 A | 31-Dec-20 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  | 8
S317061 | Review Design and Safety MVTX Supports | 21-Dec-20 A | 31-Dec-20 A | PROF3 PO M | PROF3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S317062 | Address Action Items for MVTX Supports | 13-Jul-21 A | 22-Jul-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S317062 | Address Action Items for MVTX Supports | 13-Jul-21 A | 22-Jul-21 A | PROF3 PO M | PROF3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S317070 | Create MBD Supports Detailed Design Drawings | 18-May-20 A | 28-Apr-22 A | PROF3 PO E | PROF3 PO E | 60 | 0 | C | Budgeted Units |  | 60
S317070 | Create MBD Supports Detailed Design Drawings | 18-May-20 A | 28-Apr-22 A | PROF3 PO M | PROF3 PO M | 80 | 0 | C | Budgeted Units |  | 80
S317071 | Review Design and Safety MBD Supports | 01-Apr-22 A | 25-Apr-22 A | PROF3 PO E | PROF3 PO E | 4 | 0 | C | Budgeted Units |  |  | 4
S317071 | Review Design and Safety MBD Supports | 01-Apr-22 A | 25-Apr-22 A | PROF3 PO M | PROF3 PO M | 4 | 0 | C | Budgeted Units |  |  | 4
S317072 | Address Action Items for MBD Supports | 01-Apr-22 A | 27-Apr-22 A | PROF3 PO E | PROF3 PO E | 4 | 0 | C | Budgeted Units |  |  | 4
S317072 | Address Action Items for MBD Supports | 01-Apr-22 A | 27-Apr-22 A | PROF3 PO M | PROF3 PO M | 4 | 0 | C | Budgeted Units |  |  | 4
S317080 | Create Large Support Rings Supports Detailed Design Drawings | 13-May-20 A | 09-Nov-20 A | PROF3 PO E | PROF3 PO E | 100 | 0 | C | Budgeted Units | 10 | 90
S317080 | Create Large Support Rings Supports Detailed Design Drawings | 13-May-20 A | 09-Nov-20 A | PROF3 PO M | PROF3 PO M | 350 | 0 | C | Budgeted Units | 35 | 315
S317081 | Review Design and Safety Large Support Rings Supports | 10-Nov-20 A | 24-Nov-20 A | PROF3 PO E | PROF3 PO E | 24 | 0 | C | Budgeted Units |  | 24
S317081 | Review Design and Safety Large Support Rings Supports | 10-Nov-20 A | 24-Nov-20 A | PROF3 PO M | PROF3 PO M | 24 | 0 | C | Budgeted Units |  | 24
S317082 | Address Action Items for Large Support Rings Supports | 25-Nov-20 A | 01-Feb-21 A | PROF3 PO E | PROF3 PO E | 10 | 0 | C | Budgeted Units |  | 10
S317082 | Address Action Items for Large Support Rings Supports | 25-Nov-20 A | 01-Feb-21 A | PROF3 PO M | PROF3 PO M | 10 | 0 | C | Budgeted Units |  | 10
S317090 | Create Beampipe Supports and Beampipe Detailed Design Drawings | 12-Mar-20 A | 28-Feb-22 A | PROF3 PO E | PROF3 PO E | 240 | 0 | C | Budgeted Units |  | 240
S317090 | Create Beampipe Supports and Beampipe Detailed Design Drawings | 12-Mar-20 A | 28-Feb-22 A | PROF3 PO M | PROF3 PO M | 300 | 0 | C | Budgeted Units |  | 300
S317091 | Review Design and Safety Beampipe Supports | 30-Mar-22 A | 31-Mar-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  | 20
S317091 | Review Design and Safety Beampipe Supports | 30-Mar-22 A | 31-Mar-22 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317092 | Address Action Items for Beampipe Supports | 01-Apr-22 A | 27-Apr-22 A | PROF3 PO E | PROF3 PO E | 4 | 0 | C | Budgeted Units |  |  | 4
S317092 | Address Action Items for Beampipe Supports | 01-Apr-22 A | 27-Apr-22 A | PROF3 PO M | PROF3 PO M | 4 | 0 | C | Budgeted Units |  |  | 4
S317120 | Prepare Procurement Package for Magnet Supports | 16-Mar-21 A | 25-Mar-21 A | TECH3 PO M | TECH3 PO M | 40 | 0 | C | Budgeted Units |  | 40
S317120 | Prepare Procurement Package for Magnet Supports | 16-Mar-21 A | 25-Mar-21 A | PROF3 PO M | PROF3 PO M | 40 | 0 | C | Budgeted Units |  | 40
S317120 | Prepare Procurement Package for Magnet Supports | 16-Mar-21 A | 25-Mar-21 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  | 40
S317130 | Prepare Procurement Package for EMCal Supports | 18-Feb-21 A | 26-Feb-21 A | TECH3 PO M | TECH3 PO M | 10 | 0 | C | Budgeted Units |  | 10
S317130 | Prepare Procurement Package for EMCal Supports | 18-Feb-21 A | 26-Feb-21 A | PROF3 PO M | PROF3 PO M | 10 | 0 | C | Budgeted Units |  | 10
S317130 | Prepare Procurement Package for EMCal Supports | 18-Feb-21 A | 26-Feb-21 A | PROF3 PO E | PROF3 PO E | 10 | 0 | C | Budgeted Units |  | 10
S317140 | Prepare Procurement Package for TPC Supports | 18-Jan-22 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S317140 | Prepare Procurement Package for TPC Supports | 18-Jan-22 A | 28-Feb-22 A | PROF3 PO M | PROF3 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S317140 | Prepare Procurement Package for TPC Supports | 18-Jan-22 A | 28-Feb-22 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  |  | 40
S317150 | Prepare Procurement Package for INTT Supports | 18-Jan-22 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317150 | Prepare Procurement Package for INTT Supports | 18-Jan-22 A | 28-Feb-22 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317150 | Prepare Procurement Package for INTT Supports | 18-Jan-22 A | 28-Feb-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  | 20
S317160 | Prepare Procurement Package for MVTX Supports | 18-Jan-22 A | 31-Jan-22 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317160 | Prepare Procurement Package for MVTX Supports | 18-Jan-22 A | 31-Jan-22 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317160 | Prepare Procurement Package for MVTX Supports | 18-Jan-22 A | 31-Jan-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  | 20
S317170 | Prepare Procurement Package for MBD Supports | 13-Apr-22 A | 27-May-22 A | TECH3 PO M | TECH3 PO M | 10 | 0 | C | Budgeted Units |  |  | 10
S317170 | Prepare Procurement Package for MBD Supports | 13-Apr-22 A | 27-May-22 A | PROF3 PO M | PROF3 PO M | 10 | 0 | C | Budgeted Units |  |  | 10
S317170 | Prepare Procurement Package for MBD Supports | 13-Apr-22 A | 27-May-22 A | PROF3 PO E | PROF3 PO E | 10 | 0 | C | Budgeted Units |  |  | 10
S317180 | Prepare Procurement Package for Large Support Rings | 02-Feb-21 A | 31-Mar-21 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units |  | 80
S317180 | Prepare Procurement Package for Large Support Rings | 02-Feb-21 A | 31-Mar-21 A | PROF3 PO M | PROF3 PO M | 80 | 0 | C | Budgeted Units |  | 80
S317180 | Prepare Procurement Package for Large Support Rings | 02-Feb-21 A | 31-Mar-21 A | PROF3 PO E | PROF3 PO E | 80 | 0 | C | Budgeted Units |  | 80
S317190 | Prepare Procurement Package for Beampipe Supports | 04-Apr-22 A | 27-May-22 A | TECH3 PO M | TECH3 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S317190 | Prepare Procurement Package for Beampipe Supports | 04-Apr-22 A | 27-May-22 A | PROF3 PO M | PROF3 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S317190 | Prepare Procurement Package for Beampipe Supports | 04-Apr-22 A | 27-May-22 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  |  | 40
S317220 | Evaluate and Process Bid for Magnet Supports | 03-May-21 A | 17-May-21 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  | 20
S317220 | Evaluate and Process Bid for Magnet Supports | 03-May-21 A | 17-May-21 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  | 20
S317230 | Evaluate and Process Bid for EMCal Supports | 16-Feb-21 A | 25-Feb-21 A | PROF3 PO M | PROF3 PO M | 10 | 0 | C | Budgeted Units |  | 10
S317230 | Evaluate and Process Bid for EMCal Supports | 16-Feb-21 A | 25-Feb-21 A | PROF3 PO E | PROF3 PO E | 10 | 0 | C | Budgeted Units |  | 10
S317240 | Evaluate and Process Bid for TPC Supports | 18-Jan-22 A | 28-Feb-22 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317240 | Evaluate and Process Bid for TPC Supports | 18-Jan-22 A | 28-Feb-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  | 20
S317250 | Evaluate and Process Bid for INTT Supports | 18-Jan-22 A | 28-Feb-22 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317250 | Evaluate and Process Bid for INTT Supports | 18-Jan-22 A | 28-Feb-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  | 20
S317260 | Evaluate and Process Bid for MVTX Supports | 18-Jan-22 A | 31-Jan-22 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317260 | Evaluate and Process Bid for MVTX Supports | 18-Jan-22 A | 31-Jan-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  | 20
S317270 | Evaluate and Process Bid for MBD Supports | 25-May-22 A | 29-Jul-22 A | PROF3 PO M | PROF3 PO M | 10 | 0 | C | Budgeted Units |  |  | 10
S317270 | Evaluate and Process Bid for MBD Supports | 25-May-22 A | 29-Jul-22 A | PROF3 PO E | PROF3 PO E | 10 | 0 | C | Budgeted Units |  |  | 10
S317280 | Evaluate and Process Bid for Large Support Rings | 22-Mar-21 A | 31-Mar-21 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  | 20
S317280 | Evaluate and Process Bid for Large Support Rings | 22-Mar-21 A | 31-Mar-21 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  | 20
S317290 | Evaluate and Process Bid for Beampipe Supports | 25-May-22 A | 29-Jul-22 A | PROF3 PO M | PROF3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S317290 | Evaluate and Process Bid for Beampipe Supports | 25-May-22 A | 29-Jul-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  | 20
S318120 | Perform Magnet Supports Acceptance | 01-Sep-21 A | 15-Sep-21 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  | 20
S318120 | Perform Magnet Supports Acceptance | 01-Sep-21 A | 15-Sep-21 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  | 20
S318130 | Perform EMCal Supports Acceptance | 23-Feb-21 A | 26-Feb-21 A | TECH3 PO M | TECH3 PO M | 10 | 0 | C | Budgeted Units |  | 10
S318130 | Perform EMCal Supports Acceptance | 23-Feb-21 A | 26-Feb-21 A | PROF3 PO E | PROF3 PO E | 10 | 0 | C | Budgeted Units |  | 10
S318140 | Perform TPC Supports Acceptance | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S318140 | Perform TPC Supports Acceptance | 2022-10-31 | 2022-11-14 | PROF3 PO E | PROF3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S318150 | Perform INTT Supports Acceptance | 03-Aug-22 A | 31-Aug-22 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  |  |  | 20
S318150 | Perform INTT Supports Acceptance | 03-Aug-22 A | 31-Aug-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  |  | 20
S318160 | Perform MVTX Supports Acceptance | 14-Feb-22 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S318160 | Perform MVTX Supports Acceptance | 14-Feb-22 A | 28-Feb-22 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  |  | 20
S318170 | Perform MBD Supports Acceptance | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 10 | 10 | C | Budgeted Units |  |  |  | 10
S318170 | Perform MBD Supports Acceptance | 2022-10-31 | 2022-11-14 | PROF3 PO E | PROF3 PO E | 10 | 10 | C | Budgeted Units |  |  |  | 10
S318180 | Perform Large Support Rings Acceptance | 18-Oct-21 A | 22-Oct-21 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units |  |  | 80
S318180 | Perform Large Support Rings Acceptance | 18-Oct-21 A | 22-Oct-21 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  |  | 40
S318190 | Perform Beampipe Supports Acceptance | 26-Sep-22 A | 2022-10-17 | TECH3 PO M | TECH3 PO M | 40 | 36 | C | Budgeted Units |  |  |  | 40
S318190 | Perform Beampipe Supports Acceptance | 26-Sep-22 A | 2022-10-17 | PROF3 PO E | PROF3 PO E | 40 | 36 | C | Budgeted Units |  |  |  | 40
S316406 | Analyze and Evaluate Structural Support for Internal Detectors FY19 - Physics Resource(s) Split_75% | 01-Nov-19 A | 31-Jul-20 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units | 20
S316406 | Analyze and Evaluate Structural Support for Internal Detectors FY19 - Physics Resource(s) Split_75% | 01-Nov-19 A | 31-Jul-20 A | TECH3 PO M | TECH3 PO M | 14 | 0 | C | Budgeted Units | 14
S318182 | Assemble Large Support Rings | 25-Oct-21 A | 22-Nov-21 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units |  |  | 80
S318182 | Assemble Large Support Rings | 25-Oct-21 A | 22-Nov-21 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  |  | 40
S318182 | Assemble Large Support Rings | 25-Oct-21 A | 22-Nov-21 A | PROF4 PO M | PROF4 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
POM02-13.02.03.04 End Caps/ Pole Tips |  | 01-Nov-19 A | 28-Feb-22 A |  |  | 2670 | 0 |  | Budgeted Units | 2230 | 224 | 216
S324210 | End Caps/ Pole Tips - Assembly & Detail Drawing - CA-D Resource(s) | 01-Apr-20 A | 14-Oct-20 A | PROF4 AD | PROF4 AD | 245 | 0 | C | Budgeted Units | 245
S324310 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 01-Apr-20 A | 21-Apr-20 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units | 40
S324410 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Apr-20 A | 28-Oct-20 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units | 40
S324610 | End Caps/ Pole Tips - Prepare Procurement Package(s) - CA-D Resource(s) | 01-Apr-20 A | 30-Nov-20 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units | 40
S325110 | End Caps/ Pole Tips - Vendor Selection - CA-D Resource(s) | 29-Jan-21 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S324010 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - CA-D Resource(s) | 01-Nov-19 A | 31-Mar-20 A | PROF4 AD | PROF4 AD | 240 | 0 | C | Budgeted Units | 240
S324710 | End Caps/ Pole Tips - Procurement Readiness Review - CA-D Resource(s) | 21-Dec-20 A | 23-Dec-20 A | PROF4 AD | PROF4 AD | 24 | 0 | C | Budgeted Units |  | 24
S325010 | End Caps/ Pole Tips - Vendor Responses - CA-D Resource(s) | 11-Jan-21 A | 28-Jan-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 25-Feb-22 A | 28-Feb-22 A | PROF4 AD | PROF4 AD | 52 | 0 | C | Budgeted Units |  |  | 52
S324210 | End Caps/ Pole Tips - Assembly & Detail Drawing - CA-D Resource(s) | 01-Apr-20 A | 14-Oct-20 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units | 240
S324310 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 01-Apr-20 A | 21-Apr-20 A | TECH3 AD | TECH3 AD | 20 | 0 | C | Budgeted Units | 20
S324410 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Apr-20 A | 28-Oct-20 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units | 40
S324610 | End Caps/ Pole Tips - Prepare Procurement Package(s) - CA-D Resource(s) | 01-Apr-20 A | 30-Nov-20 A | TECH3 AD | TECH3 AD | 120 | 0 | C | Budgeted Units | 120
S325110 | End Caps/ Pole Tips - Vendor Selection - CA-D Resource(s) | 29-Jan-21 A | 26-Feb-21 A | TECH3 AD | TECH3 AD | 10 | 0 | C | Budgeted Units |  | 10
S324010 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - CA-D Resource(s) | 01-Nov-19 A | 31-Mar-20 A | TECH3 AD | TECH3 AD | 70 | 0 | C | Budgeted Units | 70
S324710 | End Caps/ Pole Tips - Procurement Readiness Review - CA-D Resource(s) | 21-Dec-20 A | 23-Dec-20 A | TECH3 AD | TECH3 AD | 20 | 0 | C | Budgeted Units |  | 20
S325010 | End Caps/ Pole Tips - Vendor Responses - CA-D Resource(s) | 11-Jan-21 A | 28-Jan-21 A | TECH3 AD | TECH3 AD | 10 | 0 | C | Budgeted Units |  | 10
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 25-Feb-22 A | 28-Feb-22 A | TECH3 AD | TECH3 AD | 44 | 0 | C | Budgeted Units |  |  | 44
S324110 | End Caps/ Pole Tips - Design Controls for Drive System - CA-D Resource(s) | 01-Apr-20 A | 30-Dec-20 A | TECH3 AD | TECH3 AD | 60 | 0 | C | Budgeted Units | 60
S324800 | End Caps/ Pole Tips - Provide Requirement to Procurement | 15-Dec-20 A | 22-Dec-20 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units |  | 16
S324210 | End Caps/ Pole Tips - Assembly & Detail Drawing - CA-D Resource(s) | 01-Apr-20 A | 14-Oct-20 A | PROF5 AD | PROF5 AD | 125 | 0 | C | Budgeted Units | 125
S324310 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 01-Apr-20 A | 21-Apr-20 A | PROF5 AD | PROF5 AD | 20 | 0 | C | Budgeted Units | 20
S324410 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Apr-20 A | 28-Oct-20 A | PROF5 AD | PROF5 AD | 20 | 0 | C | Budgeted Units | 20
S324610 | End Caps/ Pole Tips - Prepare Procurement Package(s) - CA-D Resource(s) | 01-Apr-20 A | 30-Nov-20 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units | 16
S325110 | End Caps/ Pole Tips - Vendor Selection - CA-D Resource(s) | 29-Jan-21 A | 26-Feb-21 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units |  | 16
S324010 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - CA-D Resource(s) | 01-Nov-19 A | 31-Mar-20 A | PROF5 AD | PROF5 AD | 140 | 0 | C | Budgeted Units | 140
S324710 | End Caps/ Pole Tips - Procurement Readiness Review - CA-D Resource(s) | 21-Dec-20 A | 23-Dec-20 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units |  | 16
S325010 | End Caps/ Pole Tips - Vendor Responses - CA-D Resource(s) | 11-Jan-21 A | 28-Jan-21 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units |  | 16
S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - CA-D Resource(s) | 25-Feb-22 A | 28-Feb-22 A | PROF5 AD | PROF5 AD | 36 | 0 | C | Budgeted Units |  |  | 36
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | 01-Apr-20 A | 14-Oct-20 A | PROF4 PO M | PROF4 PO M | 24 | 0 | C | Budgeted Units | 24
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | 01-Apr-20 A | 14-Oct-20 A | SCI3 PO | SCI3 PO | 24 | 0 | C | Budgeted Units | 24
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | 01-Apr-20 A | 14-Oct-20 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units | 24
S324200 | End Caps/ Pole Tips - Assembly & Detail Drawing - Physics Resource(s) | 01-Apr-20 A | 14-Oct-20 A | TECH3 PO D | TECH3 PO D | 240 | 0 | C | Budgeted Units | 240
S324300 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - Physics Resource(s) | 01-Apr-20 A | 21-Apr-20 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units | 20
S324300 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) - Physics Resource(s) | 01-Apr-20 A | 21-Apr-20 A | SCI3 PO | SCI3 PO | 4 | 0 | C | Budgeted Units | 4
S324400 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 01-Apr-20 A | 28-Oct-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S324400 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 01-Apr-20 A | 28-Oct-20 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units | 8
S324600 | End Caps/ Pole Tips - Prepare Procurement Package(s) - Physics Resource(s) | 01-Apr-20 A | 30-Nov-20 A | TECH3 PO D | TECH3 PO D | 120 | 0 | C | Budgeted Units | 120
S325100 | End Caps/ Pole Tips - Vendor Selection - Physics Resource(s) | 29-Jan-21 A | 26-Feb-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units |  | 10
S324000 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) - Physics Resource(s) | 01-Nov-19 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 70 | 0 | C | Budgeted Units | 70
S324100 | End Caps/ Pole Tips - Design Controls for Drive System - Physics Resource(s) | 01-Apr-20 A | 30-Dec-20 A | PROF3 PO E | PROF3 PO E | 120 | 0 | C | Budgeted Units | 120
S324100 | End Caps/ Pole Tips - Design Controls for Drive System - Physics Resource(s) | 01-Apr-20 A | 30-Dec-20 A | TECH3 PO D | TECH3 PO D | 60 | 0 | C | Budgeted Units | 60
S324700 | End Caps/ Pole Tips - Procurement Readiness Review - Physics Resource(s) | 21-Dec-20 A | 23-Dec-20 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  | 24
S324700 | End Caps/ Pole Tips - Procurement Readiness Review - Physics Resource(s) | 21-Dec-20 A | 23-Dec-20 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  | 20
S325000 | End Caps/ Pole Tips - Vendor Responses - Physics Resource(s) | 11-Jan-21 A | 28-Jan-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units |  | 10
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | 25-Feb-22 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S325500 | End Caps/ Pole Tips - Delivery Acceptance Support Labor - Physics Resource(s) | 25-Feb-22 A | 28-Feb-22 A | TECH3 PO D | TECH3 PO D | 44 | 0 | C | Budgeted Units |  |  | 44
POM02-13.02.03.05 CC Bridge, Mid Platforms and Access |  | 01-Nov-19 A | 31-Mar-22 A |  |  | 3162 | 0 |  | Budgeted Units | 2248 | 738 | 176
S325810 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - CA-D Resource(s) | 01-Apr-20 A | 29-Jan-21 A | PROF4 AD | PROF4 AD | 320 | 0 | C | Budgeted Units | 320
S325910 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 01-Apr-20 A | 28-Oct-20 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units | 40
S326010 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Apr-20 A | 29-Oct-20 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units | 40
S326210 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - CA-D Resource(s) | 29-Jan-21 A | 12-Feb-21 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units |  | 40
S326710 | CC Bridge, Mid Platforms & Access - Vendor Selection - CA-D Resource(s) | 14-Jun-21 A | 22-Jun-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 16-Aug-21 A | 31-Mar-22 A | PROF4 AD | PROF4 AD | 60 | 0 | C | Budgeted Units |  | 15 | 45
S325710 | CC Bridge, Mid Platforms & Access - Engineering Analysis - CA-D Resource(s) | 01-Nov-19 A | 31-Mar-20 A | PROF4 AD | PROF4 AD | 320 | 0 | C | Budgeted Units | 320
S326310 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - CA-D Resource(s) | 16-Feb-21 A | 22-Feb-21 A | PROF4 AD | PROF4 AD | 24 | 0 | C | Budgeted Units |  | 24
S326610 | CC Bridge, Mid Platforms & Access - Vendor Responses - CA-D Resource(s) | 15-Mar-21 A | 21-Apr-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S325810 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - CA-D Resource(s) | 01-Apr-20 A | 29-Jan-21 A | TECH3 AD | TECH3 AD | 320 | 0 | C | Budgeted Units | 320
S325910 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 01-Apr-20 A | 28-Oct-20 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units | 40
S326010 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Apr-20 A | 29-Oct-20 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units | 40
S326210 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - CA-D Resource(s) | 29-Jan-21 A | 12-Feb-21 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  | 80
S326710 | CC Bridge, Mid Platforms & Access - Vendor Selection - CA-D Resource(s) | 14-Jun-21 A | 22-Jun-21 A | TECH3 AD | TECH3 AD | 60 | 0 | C | Budgeted Units |  | 60
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 16-Aug-21 A | 31-Mar-22 A | TECH3 AD | TECH3 AD | 36 | 0 | C | Budgeted Units |  | 9 | 27
S325710 | CC Bridge, Mid Platforms & Access - Engineering Analysis - CA-D Resource(s) | 01-Nov-19 A | 31-Mar-20 A | TECH3 AD | TECH3 AD | 160 | 0 | C | Budgeted Units | 160
S326310 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - CA-D Resource(s) | 16-Feb-21 A | 22-Feb-21 A | TECH3 AD | TECH3 AD | 20 | 0 | C | Budgeted Units |  | 20
S326610 | CC Bridge, Mid Platforms & Access - Vendor Responses - CA-D Resource(s) | 15-Mar-21 A | 21-Apr-21 A | TECH3 AD | TECH3 AD | 60 | 0 | C | Budgeted Units |  | 60
S326400 | CC Bridge, Mid Platforms & Access - Provide Requirement to Procurement | 23-Feb-21 A | 26-Feb-21 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units |  | 16
S325810 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - CA-D Resource(s) | 01-Apr-20 A | 29-Jan-21 A | PROF5 AD | PROF5 AD | 160 | 0 | C | Budgeted Units | 160
S325910 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - CA-D Resource(s) | 01-Apr-20 A | 28-Oct-20 A | PROF5 AD | PROF5 AD | 20 | 0 | C | Budgeted Units | 20
S326010 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - CA-D Resource(s) | 01-Apr-20 A | 29-Oct-20 A | PROF5 AD | PROF5 AD | 20 | 0 | C | Budgeted Units | 20
S326210 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - CA-D Resource(s) | 29-Jan-21 A | 12-Feb-21 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units |  | 16
S326710 | CC Bridge, Mid Platforms & Access - Vendor Selection - CA-D Resource(s) | 14-Jun-21 A | 22-Jun-21 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units |  | 16
S326910 | CC Bridge, Mid Platforms & Access - BNL Oversight - CA-D Resource(s) | 16-Aug-21 A | 31-Mar-22 A | PROF5 AD | PROF5 AD | 30 | 0 | C | Budgeted Units |  | 7 | 23
S325710 | CC Bridge, Mid Platforms & Access - Engineering Analysis - CA-D Resource(s) | 01-Nov-19 A | 31-Mar-20 A | PROF5 AD | PROF5 AD | 160 | 0 | C | Budgeted Units | 160
S326310 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - CA-D Resource(s) | 16-Feb-21 A | 22-Feb-21 A | PROF5 AD | PROF5 AD | 16 | 0 | C | Budgeted Units |  | 16
S326610 | CC Bridge, Mid Platforms & Access - Vendor Responses - CA-D Resource(s) | 15-Mar-21 A | 21-Apr-21 A | PROF5 AD | PROF5 AD | 8 | 0 | C | Budgeted Units |  | 8
S325800 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - Physics Resource(s) | 01-Apr-20 A | 29-Jan-21 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units | 32
S325800 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings - Physics Resource(s) | 01-Apr-20 A | 29-Jan-21 A | TECH3 PO D | TECH3 PO D | 320 | 0 | C | Budgeted Units | 320
S325900 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - Physics Resource(s) | 01-Apr-20 A | 28-Oct-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S325900 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) - Physics Resource(s) | 01-Apr-20 A | 28-Oct-20 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units | 8
S326000 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 01-Apr-20 A | 29-Oct-20 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units | 8
S326000 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews - Physics Resource(s) | 01-Apr-20 A | 29-Oct-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S326200 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - Physics Resource(s) | 29-Jan-21 A | 12-Feb-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  | 24
S326200 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) - Physics Resource(s) | 29-Jan-21 A | 12-Feb-21 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units |  | 80
S326700 | CC Bridge, Mid Platforms & Access - Vendor Selection - Physics Resource(s) | 14-Jun-21 A | 22-Jun-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  | 24
S326700 | CC Bridge, Mid Platforms & Access - Vendor Selection - Physics Resource(s) | 14-Jun-21 A | 22-Jun-21 A | TECH3 PO D | TECH3 PO D | 60 | 0 | C | Budgeted Units |  | 60
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | 16-Aug-21 A | 31-Mar-22 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units |  | 9 | 27
S326900 | CC Bridge, Mid Platforms & Access - BNL Oversight - Physics Resource(s) | 16-Aug-21 A | 31-Mar-22 A | TECH3 PO M | TECH3 PO M | 72 | 0 | C | Budgeted Units |  | 18 | 54
S325700 | CC Bridge, Mid Platforms & Access - Engineering Analysis - Physics Resource(s) | 01-Nov-19 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 160 | 0 | C | Budgeted Units | 160
S326300 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - Physics Resource(s) | 16-Feb-21 A | 22-Feb-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  | 24
S326300 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review - Physics Resource(s) | 16-Feb-21 A | 22-Feb-21 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  | 20
S326600 | CC Bridge, Mid Platforms & Access - Vendor Responses - Physics Resource(s) | 15-Mar-21 A | 21-Apr-21 A | TECH3 PO D | TECH3 PO D | 60 | 0 | C | Budgeted Units |  | 60
POM02-13.02.04 Infrastructure |  | 01-Oct-19 A | 2023-02-09 |  |  | 20882 | 3155 |  | Budgeted Units | 3828 | 6090 | 7582 | 3382
POM02-13.02.04.01 Infrastructure Detector Support Systems |  | 01-Oct-19 A | 2023-02-09 |  |  | 14506 | 2693 |  | Budgeted Units | 2887 | 3288 | 5566 | 2766
POM02-13.02.04.01.01 Line Electric Power Distribution |  | 01-Nov-19 A | 30-Sep-22 A |  |  | 1220 | 0 |  | Budgeted Units | 456 | 281 | 455 | 28
S327700 | Calculate Power Transformer Requirements for Line Electric Power - CA-D Resource(s) | 09-Jan-20 A | 30-Jan-20 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units | 16
S327700 | Calculate Power Transformer Requirements for Line Electric Power - CA-D Resource(s) | 09-Jan-20 A | 30-Jan-20 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units | 16
S327800 | Size Conductors for Line Electric Power - CA-D Resource(s) | 17-Aug-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units | 16
S327800 | Size Conductors for Line Electric Power - CA-D Resource(s) | 17-Aug-20 A | 30-Sep-20 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units | 16
S327900 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - CA-D Resource(s) | 27-Aug-20 A | 31-Mar-21 A | PROF4 AD | PROF4 AD | 32 | 0 | C | Budgeted Units | 32
S327900 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - CA-D Resource(s) | 27-Aug-20 A | 31-Mar-21 A | TECH3 AD | TECH3 AD | 32 | 0 | C | Budgeted Units | 32
S328000 | Review Line Electric Distribution Design/Safety - CA-D Resource(s) | 17-Nov-20 A | 27-Nov-20 A | PROF4 AD | PROF4 AD | 24 | 0 | C | Budgeted Units |  | 24
S277600 | 2022 Detector Support Systems L3 Project Management | 01-Oct-21 A | 30-Sep-22 A | PROF5 PO M | PROF5 PO M | 352 | 0 | C | Budgeted Units |  |  | 324 | 28
S1001999 | Calculate Power Transformer Requirements for Line Electric Power - Physics Resource(s) | 09-Jan-20 A | 30-Jan-20 A | PROF4 PO E | PROF4 PO E | 40 | 0 | C | Budgeted Units | 40
S1002039 | Size Conductors for Line Electric Power - Physics Resource(s) | 17-Aug-20 A | 30-Sep-20 A | PROF4 PO E | PROF4 PO E | 32 | 0 | C | Budgeted Units | 32
S1002079 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - Physics Resource(s) | 27-Aug-20 A | 31-Mar-21 A | TECH3 PO D | TECH3 PO D | 32 | 0 | C | Budgeted Units | 32
S1002079 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power - Physics Resource(s) | 27-Aug-20 A | 31-Mar-21 A | PROF4 PO E | PROF4 PO E | 32 | 0 | C | Budgeted Units | 32
S1002119 | Review Line Electric Distribution Design/Safety - Physics Resource(s) | 17-Nov-20 A | 27-Nov-20 A | PROF4 PO E | PROF4 PO E | 20 | 0 | C | Budgeted Units |  | 20
S327600 | Evaluate Normal, Emergency and UPS Load Requirements for Line Electric Power | 02-Jan-20 A | 08-Jan-20 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units | 20
S328100 | Address Action Items from Line Electric Distribution Design & Safety Reviews | 17-Nov-20 A | 27-Nov-20 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units |  | 80
S328100 | Address Action Items from Line Electric Distribution Design & Safety Reviews | 17-Nov-20 A | 27-Nov-20 A | PROF3 PO E | PROF3 PO E | 20 | 0 | C | Budgeted Units |  | 20
S328550 | Prepare Line Electric Power Distribution Components Procurement Package(s) | 01-Apr-21 A | 30-Apr-21 A | PROF3 PO E | PROF3 PO E | 60 | 0 | C | Budgeted Units |  | 60
S328850 | Evaluate & Process Line Electric Power Distribution Components Bid | 02-Jul-21 A | 29-Jul-21 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  | 29 | 11
S328500 | Procure Line Electric Power Distribution Components - Provide Requirements to Procurement | 01-Apr-21 A | 30-Apr-21 A | PROF3 PO E | PROF3 PO E | 48 | 0 | C | Budgeted Units |  | 48
S329200 | Perform Line Electric Power Distribution Components Acceptance | 20-Dec-21 A | 27-May-22 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units |  |  | 40
S329200 | Perform Line Electric Power Distribution Components Acceptance | 20-Dec-21 A | 27-May-22 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units |  |  | 80
S327502 | Gather Design Requirements for All sPHENIX Subsystems for Line Electric Power Split | 01-Nov-19 A | 18-Dec-19 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units | 40
S1001999 | Calculate Power Transformer Requirements for Line Electric Power - Physics Resource(s) | 09-Jan-20 A | 30-Jan-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S1002039 | Size Conductors for Line Electric Power - Physics Resource(s) | 17-Aug-20 A | 30-Sep-20 A | TECH3 PO D | TECH3 PO D | 32 | 0 | C | Budgeted Units | 32
S327501 | Gather Power Reqs for CRYO, Cooling and Lighting | 30-Mar-20 A | 31-Mar-20 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units | 40
S327501 | Gather Power Reqs for CRYO, Cooling and Lighting | 30-Mar-20 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units | 20
POM02-13.02.04.01.02 Detector Support Services Systems (including Cables, Fibers, Cable Trays) |  | 01-Oct-19 A | 27-Jun-22 A |  |  | 2893 | 0 |  | Budgeted Units | 497 | 1096 | 1300
S329478 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp C | 02-Mar-20 A | 29-May-20 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S329500 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp C | 02-Mar-20 A | 29-May-20 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units | 4
S329600 | Review Detector Support Services Systems Design/Safety - CA-D Resource(s) | 02-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units |  |  | 20
S329900 | Prepare Detector Support Services Systems Components Procurement Package(s) - CA-D Resource(s) | 23-Aug-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units |  |  | 20
S330000 | Evaluate & Process Detector Support Services Systems Components Bids - CA-D Resource(s) | 23-Aug-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 10 | 0 | C | Budgeted Units |  |  | 10
S330100 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor C | 23-Aug-21 A | 30-Dec-21 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S330300 | Perform Detector Support Services Systems Components Acceptance - CA-D Resource(s) | 01-Sep-21 A | 30-Dec-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S330350 | Procure Fiber Optics Trunk Cables and Accessories - Labor - CA-D Resource(s) | 01-Apr-22 A | 25-Apr-22 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S329405 | Analyze Detector Support Services Systems Requirements Split - CA-D Resource(s) | 01-Oct-19 A | 31-Jul-20 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units | 16
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | 02-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | 02-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units |  |  | 80
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | 01-Oct-19 A | 31-Jul-20 A | PROF4 PO M | PROF4 PO M | 32 | 0 | C | Budgeted Units | 32
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | 01-Oct-19 A | 31-Jul-20 A | TECH3 PO M | TECH3 PO M | 26 | 0 | C | Budgeted Units | 26
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | 01-Oct-19 A | 31-Jul-20 A | TECH3 PO D | TECH3 PO D | 26 | 0 | C | Budgeted Units | 26
S1002199 | Analyze Detector Support Services Systems Requirements Split - Physics Resource(s) | 01-Oct-19 A | 31-Jul-20 A | SCI3 PO | SCI3 PO | 26 | 0 | C | Budgeted Units | 26
S1002319 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | 02-Mar-20 A | 29-May-20 A | PROF4 PO M | PROF4 PO M | 32 | 0 | C | Budgeted Units | 32
S1002319 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | 02-Mar-20 A | 29-May-20 A | TECH3 PO D | TECH3 PO D | 32 | 0 | C | Budgeted Units | 32
S1002399 | Review Detector Support Services Systems Design/Safety - Physics Resource(s) | 02-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1002399 | Review Detector Support Services Systems Design/Safety - Physics Resource(s) | 02-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S1002479 | Prepare Detector Support Services Systems Components Procurement Package(s) - Physics Resource(s) | 23-Aug-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units |  |  | 80
S1002559 | Evaluate & Process Detector Support Services Systems Components Bids - Physics Resource(s) | 23-Aug-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | 23-Aug-21 A | 30-Dec-21 A | PROF4 PO M | PROF4 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S1002639 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) - Labor P | 23-Aug-21 A | 30-Dec-21 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units |  |  | 40
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 01-Sep-21 A | 30-Dec-21 A | PROF4 PO M | PROF4 PO M | 4 | 0 | C | Budgeted Units |  |  | 4
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 01-Sep-21 A | 30-Dec-21 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S1002719 | Perform Detector Support Services Systems Components Acceptance - Physics Resource(s) | 01-Sep-21 A | 30-Dec-21 A | TECH3 PO D | TECH3 PO D | 4 | 0 | C | Budgeted Units |  |  | 4
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | 01-Apr-22 A | 25-Apr-22 A | SCI3 PO | SCI3 PO | 80 | 0 | C | Budgeted Units |  |  | 80
S1002759 | Procure Fiber Optics Trunk Cables and Accessories - Labor - Physics Resource(s) | 01-Apr-22 A | 25-Apr-22 A | PROF3 PO E | PROF3 PO E | 80 | 0 | C | Budgeted Units |  |  | 80
S329475 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | 02-Mar-20 A | 29-May-20 A | TECH3 PO D | TECH3 PO D | 200 | 0 | C | Budgeted Units |  |  | 200
S1002479 | Prepare Detector Support Services Systems Components Procurement Package(s) - Physics Resource(s) | 23-Aug-21 A | 30-Sep-21 A | PROF3 PO E | PROF3 PO E | 80 | 0 | C | Budgeted Units |  |  | 80
S1002559 | Evaluate & Process Detector Support Services Systems Components Bids - Physics Resource(s) | 23-Aug-21 A | 30-Sep-21 A | PROF3 PO E | PROF3 PO E | 16 | 0 | C | Budgeted Units |  |  | 16
S329410 | Conceptual Design for Cable Routing from Detector to Rack (MVTX) | 09-Nov-20 A | 30-Jun-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  | 8
S329410 | Conceptual Design for Cable Routing from Detector to Rack (MVTX) | 09-Nov-20 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units |  | 80
S329420 | Conceptual Design for Cable Routing from Detector to Rack (MBD) | 23-Oct-20 A | 30-Jun-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  | 8
S329420 | Conceptual Design for Cable Routing from Detector to Rack (MBD) | 23-Oct-20 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 88 | 0 | C | Budgeted Units |  | 88
S329430 | Conceptual Design for Routing Fiber Optic Cables from Rack to Patch Panel | 22-Dec-20 A | 30-Jun-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  | 8
S329430 | Conceptual Design for Routing Fiber Optic Cables from Rack to Patch Panel | 22-Dec-20 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 96 | 0 | C | Budgeted Units |  | 96
S329440 | Conceptual Design for Routing Rack Cooling System | 23-Oct-20 A | 29-Apr-22 A | PROF3 PO E | PROF3 PO E | 104 | 0 | C | Budgeted Units |  | 104
S329440 | Conceptual Design for Routing Rack Cooling System | 23-Oct-20 A | 29-Apr-22 A | TECH3 PO D | TECH3 PO D | 104 | 0 | C | Budgeted Units |  | 104
S329450 | Conceptual Design for Routing Detector Cooling System | 15-Jul-20 A | 27-Jun-22 A | PROF3 PO E | PROF3 PO E | 100 | 0 | C | Budgeted Units |  | 100
S329450 | Conceptual Design for Routing Detector Cooling System | 15-Jul-20 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 200 | 0 | C | Budgeted Units |  | 200
S329460 | Design Package for Detector Cooling System | 02-Sep-21 A | 30-Sep-21 A | PROF3 PO E | PROF3 PO E | 120 | 0 | C | Budgeted Units |  |  | 120
S329460 | Design Package for Detector Cooling System | 02-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 240 | 0 | C | Budgeted Units |  |  | 240
S329470 | Conceptual Design for Power Distribution / Controls Cable Routing | 22-Mar-21 A | 31-Mar-21 A | PROF3 PO E | PROF3 PO E | 68 | 0 | C | Budgeted Units |  | 68
S329470 | Conceptual Design for Power Distribution / Controls Cable Routing | 22-Mar-21 A | 31-Mar-21 A | TECH3 PO D | TECH3 PO D | 136 | 0 | C | Budgeted Units |  | 136
S329406 | Send proposal packages for approvals (cable types, rack locations, and support components) | 01-Apr-20 A | 30-Apr-20 A | TECH3 PO D | TECH3 PO D | 15 | 0 | C | Budgeted Units | 15
S329406 | Send proposal packages for approvals (cable types, rack locations, and support components) | 01-Apr-20 A | 30-Apr-20 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units | 8
S329407 | Conceptual Design for Cable Routing from Detector to Rack (HCal, EMCal) | 11-Mar-20 A | 30-Oct-20 A | TECH3 PO D | TECH3 PO D | 136 | 0 | C | Budgeted Units | 136
S329407 | Conceptual Design for Cable Routing from Detector to Rack (HCal, EMCal) | 11-Mar-20 A | 30-Oct-20 A | PROF3 PO E | PROF3 PO E | 16 | 0 | C | Budgeted Units | 16
S329408 | Conceptual Design for Cable Routing from Detector to Rack (TPC) | 01-Jul-20 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 120 | 0 | C | Budgeted Units | 120
S329408 | Conceptual Design for Cable Routing from Detector to Rack (TPC) | 01-Jul-20 A | 30-Jun-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units | 8
S329409 | Conceptual Design for Cable Routing from Detector to Rack (INTT) | 22-Dec-20 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 88 | 0 | C | Budgeted Units |  | 88
S329409 | Conceptual Design for Cable Routing from Detector to Rack (INTT) | 22-Dec-20 A | 30-Jun-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  | 8
S329475 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings - Detector Supp P | 02-Mar-20 A | 29-May-20 A | PROF3 PO E | PROF3 PO E | 80 | 0 | C | Budgeted Units |  |  | 80
POM02-13.02.04.01.03 Detector Electronics Racks and Rack generic support systems |  | 03-Feb-20 A | 2022-11-10 |  |  | 4017 | 546 |  | Budgeted Units | 1488 | 653 | 1376 | 500
S330800 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - CA-D Resource(s) | 30-Apr-21 A | 30-Jul-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | 23-Oct-20 A | 28-Oct-21 A | PROF4 PO M | PROF4 PO M | 24 | 0 | C | Budgeted Units |  | 24
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | 23-Oct-20 A | 28-Oct-21 A | TECH3 PO D | TECH3 PO D | 96 | 0 | C | Budgeted Units |  | 96
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | 21-Jun-21 A | 30-Jul-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | 21-Jun-21 A | 30-Jul-21 A | TECH3 PO D | TECH3 PO D | 32 | 0 | C | Budgeted Units |  | 32
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | 05-Jul-21 A | 30-Nov-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | 05-Jul-21 A | 30-Nov-21 A | TECH3 PO D | TECH3 PO D | 72 | 0 | C | Budgeted Units |  |  | 72
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | 05-Jul-21 A | 30-Nov-21 A | PROF4 PO M | PROF4 PO M | 48 | 0 | C | Budgeted Units |  |  | 48
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | 05-Jul-21 A | 30-Nov-21 A | TECH3 PO D | TECH3 PO D | 144 | 0 | C | Budgeted Units |  |  | 144
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 05-Jul-21 A | 29-Apr-22 A | PROF4 PO M | PROF4 PO M | 48 | 0 | C | Budgeted Units |  |  | 48
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 05-Jul-21 A | 29-Apr-22 A | TECH3 PO D | TECH3 PO D | 144 | 0 | C | Budgeted Units |  |  | 144
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 13-Dec-21 A | 29-Apr-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 13-Dec-21 A | 29-Apr-22 A | TECH3 PO M | TECH3 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 13-Dec-21 A | 29-Apr-22 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | 03-Feb-20 A | 28-Feb-20 A | PROF4 PO E | PROF4 PO E | 13 | 0 | C | Budgeted Units |  | 13
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | 03-Feb-20 A | 28-Feb-20 A | PROF4 PO M | PROF4 PO M | 13 | 0 | C | Budgeted Units |  | 13
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | 03-Feb-20 A | 28-Feb-20 A | SCI3 PO | SCI3 PO | 13 | 0 | C | Budgeted Units |  | 13
S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements FY19 | 03-Feb-20 A | 28-Feb-20 A | TECH3 PO D | TECH3 PO D | 54 | 0 | C | Budgeted Units |  | 54
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | 30-Apr-21 A | 26-Jul-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | 30-Apr-21 A | 26-Jul-21 A | TECH3 PO D | TECH3 PO D | 32 | 0 | C | Budgeted Units |  | 32
S330612 | Rack Interlock Conceptual Design | 13-Mar-20 A | 31-Jul-20 A | TECH3 PO D | TECH3 PO D | 240 | 0 | C | Budgeted Units | 240
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Elec | 23-Oct-20 A | 28-Oct-21 A | PROF3 PO E | PROF3 PO E | 24 | 0 | C | Budgeted Units |  | 24
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | 21-Jun-21 A | 30-Jul-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  | 8
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | 05-Jul-21 A | 30-Nov-21 A | PROF3 PO E | PROF3 PO E | 16 | 0 | C | Budgeted Units |  |  | 16
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | 05-Jul-21 A | 30-Nov-21 A | PROF3 PO E | PROF3 PO E | 48 | 0 | C | Budgeted Units |  |  | 48
S331300 | Procure & Deliver Detector Elec. Racks & Rack generic support systems Components (leadtime and fab incl.) - Labor | 05-Jul-21 A | 29-Apr-22 A | PROF3 PO E | PROF3 PO E | 48 | 0 | C | Budgeted Units |  |  | 48
S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | 13-Dec-21 A | 29-Apr-22 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S1002799 | Review Detector Electronics Racks and Rack generic support systems Design/Safety - Physics Resource(s) | 30-Apr-21 A | 26-Jul-21 A | PROF3 PO E | PROF3 PO E | 8 | 0 | C | Budgeted Units |  | 8
S330640 | Prototype System Development Labor | 16-Mar-20 A | 29-Jun-21 A | TECH3 PO D | TECH3 PO D | 180 | 0 | C | Budgeted Units | 24 | 156
S330640 | Prototype System Development Labor | 16-Mar-20 A | 29-Jun-21 A | PROF3 PO E | PROF3 PO E | 180 | 0 | C | Budgeted Units | 24 | 156
S330602 | Gather Power Reqs for Subsystem Racks on Detector | 15-May-20 A | 29-May-20 A | TECH3 PO D | TECH3 PO D | 120 | 0 | C | Budgeted Units | 120
S330602 | Gather Power Reqs for Subsystem Racks on Detector | 15-May-20 A | 29-May-20 A | PROF3 PO E | PROF3 PO E | 120 | 0 | C | Budgeted Units | 120
S330606 | Gather Rack Interlock Reqs and Specify Interlock Equipment | 11-Mar-20 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 80 | 0 | C | Budgeted Units | 80
S330606 | Gather Rack Interlock Reqs and Specify Interlock Equipment | 11-Mar-20 A | 31-Mar-20 A | PROF3 PO E | PROF3 PO E | 80 | 0 | C | Budgeted Units | 80
S330608 | Specify Power Controls Distribution Equipment | 22-Jun-20 A | 30-Nov-20 A | TECH3 PO D | TECH3 PO D | 120 | 0 | C | Budgeted Units | 120
S330608 | Specify Power Controls Distribution Equipment | 22-Jun-20 A | 30-Nov-20 A | PROF3 PO E | PROF3 PO E | 120 | 0 | C | Budgeted Units | 120
S330610 | Radiation Test for Water Leak Detection System | 08-Apr-20 A | 29-Apr-20 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S330610 | Radiation Test for Water Leak Detection System | 08-Apr-20 A | 29-Apr-20 A | PROF3 PO E | PROF3 PO E | 40 | 0 | C | Budgeted Units | 40
S330612 | Rack Interlock Conceptual Design | 13-Mar-20 A | 31-Jul-20 A | PROF3 PO E | PROF3 PO E | 240 | 0 | C | Budgeted Units | 240
S330604 | Power Distribution Conceptual Gesign for Subsystem Racks on Detector | 01-Jun-20 A | 19-Jun-20 A | TECH3 PO D | TECH3 PO D | 120 | 0 | C | Budgeted Units | 120
S330604 | Power Distribution Conceptual Gesign for Subsystem Racks on Detector | 01-Jun-20 A | 19-Jun-20 A | PROF3 PO E | PROF3 PO E | 120 | 0 | C | Budgeted Units | 120
S331450 | Assemble Racks for Lower West Platform | 13-Sep-21 A | 29-Apr-22 A | TECH3 PO E | TECH3 PO E | 80 | 0 | C | Budgeted Units |  |  | 80
S331460 | Assemble Racks for Middle West Platform | 13-Sep-21 A | 31-Mar-22 A | TECH3 PO E | TECH3 PO E | 80 | 0 | C | Budgeted Units |  |  | 80
S331470 | Assemble Racks for Lower East Platform | 15-Nov-21 A | 2022-10-31 | TECH3 PO E | TECH3 PO E | 80 | 6 | C | Budgeted Units |  |  | 80
S331480 | Assemble Racks for Middle East Platform | 13-Sep-21 A | 31-Mar-22 A | TECH3 PO E | TECH3 PO E | 80 | 0 | C | Budgeted Units |  |  | 80
S331490 | Assemble Racks for Main Upper Platform | 13-Sep-21 A | 2022-10-31 | TECH3 PO E | TECH3 PO E | 200 | 40 | C | Budgeted Units |  |  | 200
S331495 | Assemble Racks for Rack Room | 13-Sep-21 A | 27-Jun-22 A | TECH3 PO E | TECH3 PO E | 200 | 0 | C | Budgeted Units |  |  | 200
S331496 | ADDED RACK ASSEMBLY EFFORT, BASED ON EFFORT TO DATE | 2022-11-01 | 2022-11-10 | TECH3 PO E | TECH3 PO E | 500 | 500 | C | Budgeted Units |  |  |  | 500
POM02-13.02.04.01.04 Detector Gas and Cooling Services Systems |  | 01-Oct-19 A | 2023-02-09 |  |  | 3968 | 2027 |  | Budgeted Units | 446 | 820 | 620 | 2081
S331900 | Review Detector Cooling Services Systems Design/Safety - CA-D Resource(s) | 22-Sep-21 A | 23-Sep-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 3 | 13
S331705 | Analyze Detector Gas and Cooling Services Systems Requirements Split - CA-D Resource(s) | 01-Oct-19 A | 31-Jul-20 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units | 16
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assy & Detail Drawings for Det Cooling | 22-Feb-21 A | 27-Sep-21 A | PROF4 PO M | PROF4 PO M | 96 | 0 | C | Budgeted Units |  | 96
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assy & Detail Drawings for Det Cooling | 22-Feb-21 A | 27-Sep-21 A | TECH3 PO D | TECH3 PO D | 48 | 0 | C | Budgeted Units |  | 48
S331800 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assy & Detail Drawings for Det Cooling | 22-Feb-21 A | 27-Sep-21 A | TECH3 PO M | TECH3 PO M | 48 | 0 | C | Budgeted Units |  | 48
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | 22-Sep-21 A | 23-Sep-21 A | PROF4 PO M | PROF4 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | 22-Sep-21 A | 23-Sep-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S332000 | Address Action Items from Detector Cooling Services Systems Design & Safety Reviews | 22-Sep-21 A | 23-Sep-21 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S332200 | Prepare Detector Cooling Services Systems Components Procurement Package(s) | 03-Jan-22 A | 30-Sep-22 A | PROF4 PO M | PROF4 PO M | 32 | 0 | C | Budgeted Units |  |  | 32
S332200 | Prepare Detector Cooling Services Systems Components Procurement Package(s) | 03-Jan-22 A | 30-Sep-22 A | TECH3 PO D | TECH3 PO D | 72 | 0 | C | Budgeted Units |  |  | 72
S332300 | Evaluate & Process Detector Cooling Services Systems Components Bids | 03-Jan-22 A | 30-Sep-22 A | PROF4 PO M | PROF4 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S332300 | Evaluate & Process Detector Cooling Services Systems Components Bids | 03-Jan-22 A | 30-Sep-22 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  |  | 24
S332400 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) L | 17-Jan-22 A | 30-Sep-22 A | PROF4 PO M | PROF4 PO M | 96 | 0 | C | Budgeted Units |  |  | 96
S332400 | Procure & Deliver Detector Cooling Services Systems Components (leadtime and fabrication included) L | 17-Jan-22 A | 30-Sep-22 A | TECH3 PO D | TECH3 PO D | 96 | 0 | C | Budgeted Units |  |  | 96
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 18-Jul-22 A | 30-Sep-22 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  |  |  | 16
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 18-Jul-22 A | 30-Sep-22 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  |  | 16
S332600 | Perform Detector Cooling Services Systems Components Acceptance | 18-Jul-22 A | 30-Sep-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  |  | 8
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | 01-Oct-19 A | 31-Jul-20 A | PROF4 PO M | PROF4 PO M | 168 | 0 | C | Budgeted Units | 168
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | 01-Oct-19 A | 31-Jul-20 A | TECH3 PO M | TECH3 PO M | 66 | 0 | C | Budgeted Units | 66
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | 01-Oct-19 A | 31-Jul-20 A | TECH3 PO D | TECH3 PO D | 66 | 0 | C | Budgeted Units | 66
S1002839 | Analyze Detector Gas and Cooling Services Systems Requirements Split - Physics Resource(s) | 01-Oct-19 A | 31-Jul-20 A | SCI3 PO | SCI3 PO | 66 | 0 | C | Budgeted Units | 66
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | 15-Jun-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  | 3 | 13
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | 15-Jun-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  | 4 | 16
S1002879 | Review Detector Gas and Cooling Services Systems Design/Safety - Physics Resource(s) | 15-Jun-21 A | 30-Sep-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 2 | 6
S332705 | Conceptual Design for Routing Operating gas Line from Gas House to TPC Manifold | 13-Jan-21 A | 20-Jan-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S332705 | Conceptual Design for Routing Operating gas Line from Gas House to TPC Manifold | 13-Jan-21 A | 20-Jan-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S332710 | Conceptual Design for Routing N2 Line from Gas House to N2/Air Manifolds | 18-Dec-20 A | 29-Oct-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S332710 | Conceptual Design for Routing N2 Line from Gas House to N2/Air Manifolds | 18-Dec-20 A | 29-Oct-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S332715 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (MBD) | 15-Feb-21 A | 29-Oct-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S332715 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (MBD) | 15-Feb-21 A | 29-Oct-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | 18-Dec-20 A | 27-Jun-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S332720 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (INTT, MVTX) | 18-Dec-20 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | 18-Dec-20 A | 27-Jun-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S332725 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (EMCal) | 18-Dec-20 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S332730 | Conceptual Design for Gas Tube Routing from Det to Operating Gas Manifolds (TPC) | 22-Dec-20 A | 27-Sep-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S332730 | Conceptual Design for Gas Tube Routing from Det to Operating Gas Manifolds (TPC) | 22-Dec-20 A | 27-Sep-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | PROF4 PO M | PROF4 PO M | 96 | 19 | C | Budgeted Units |  | 96
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | TECH3 PO D | TECH3 PO D | 48 | 10 | C | Budgeted Units |  | 48
S332740 | Review Detector Gas Service Systems Design/Safety | 01-Jul-22 A | 08-Jul-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S332740 | Review Detector Gas Service Systems Design/Safety | 01-Jul-22 A | 08-Jul-22 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 08-Jul-22 A | 19-Jul-22 A | PROF4 PO M | PROF4 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 08-Jul-22 A | 19-Jul-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 22-Jul-22 A | 2022-10-31 | PROF4 PO M | PROF4 PO M | 32 | 19 | C | Budgeted Units |  |  | 31 | 1
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 22-Jul-22 A | 2022-10-31 | TECH3 PO D | TECH3 PO D | 72 | 43 | C | Budgeted Units |  |  | 70 | 2
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 05-Sep-22 A | 2022-11-02 | PROF4 PO M | PROF4 PO M | 24 | 14 | C | Budgeted Units |  |  |  | 24
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 05-Sep-22 A | 2022-11-02 | TECH3 PO D | TECH3 PO D | 24 | 14 | C | Budgeted Units |  |  |  | 24
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 03-Sep-22 A | 2023-02-02 | PROF4 PO M | PROF4 PO M | 96 | 58 | C | Budgeted Units |  |  |  | 96
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 03-Sep-22 A | 2023-02-02 | TECH3 PO D | TECH3 PO D | 96 | 58 | C | Budgeted Units |  |  |  | 96
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | PROF4 PO M | PROF4 PO M | 16 | 10 | C | Budgeted Units |  |  |  | 16
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | TECH3 PO D | TECH3 PO D | 16 | 10 | C | Budgeted Units |  |  |  | 16
S332712 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (IHCal) | 15-Feb-21 A | 30-Nov-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S332712 | Conceptual Design for Gas Tube Routing from Det to N2/Air Manifolds (IHCal) | 15-Feb-21 A | 30-Nov-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S332781 | Design, procure, test remaining cooling system items | 2022-11-01 | 2022-11-02 | PROF3 PO E | PROF3 PO E | 100 | 100 | C | Budgeted Units |  |  |  | 100
S332781 | Design, procure, test remaining cooling system items | 2022-11-01 | 2022-11-02 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332781 | Design, procure, test remaining cooling system items | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S332782 | Cooling System Panel Fabrication - TPC | 2022-11-03 | 2022-11-04 | PROF3 PO E | PROF3 PO E | 8 | 8 | C | Budgeted Units |  |  |  | 8
S332782 | Cooling System Panel Fabrication - TPC | 2022-11-03 | 2022-11-04 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332782 | Cooling System Panel Fabrication - TPC | 2022-11-03 | 2022-11-04 | TECH3 PO M | TECH3 PO M | 130 | 130 | C | Budgeted Units |  |  |  | 130
S332783 | Cooling System Panel Fabrication - TPot | 2022-11-07 | 2022-11-08 | PROF3 PO E | PROF3 PO E | 4 | 4 | C | Budgeted Units |  |  |  | 4
S332783 | Cooling System Panel Fabrication - TPot | 2022-11-07 | 2022-11-08 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332783 | Cooling System Panel Fabrication - TPot | 2022-11-07 | 2022-11-08 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Budgeted Units |  |  |  | 60
S332784 | Cooling System Panel Fabrication - EMCal SiPM | 2022-11-09 | 2022-11-10 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332784 | Cooling System Panel Fabrication - EMCal SiPM | 2022-11-09 | 2022-11-10 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332784 | Cooling System Panel Fabrication - EMCal SiPM | 2022-11-09 | 2022-11-10 | TECH3 PO M | TECH3 PO M | 290 | 290 | C | Budgeted Units |  |  |  | 290
S332785 | Cooling System Panel Fabrication - EMCal PreAmp | 2022-11-14 | 2022-11-15 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332785 | Cooling System Panel Fabrication - EMCal PreAmp | 2022-11-14 | 2022-11-15 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332785 | Cooling System Panel Fabrication - EMCal PreAmp | 2022-11-14 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 290 | 290 | C | Budgeted Units |  |  |  | 290
S332786 | Cooling System Panel Fabrication - INTT ROC | 2022-11-16 | 2022-11-17 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332786 | Cooling System Panel Fabrication - INTT ROC | 2022-11-16 | 2022-11-17 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332786 | Cooling System Panel Fabrication - INTT ROC | 2022-11-16 | 2022-11-17 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Budgeted Units |  |  |  | 120
S332787 | Cooling System Panel Fabrication - INTT Stave | 2022-11-18 | 2022-11-21 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332787 | Cooling System Panel Fabrication - INTT Stave | 2022-11-18 | 2022-11-21 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332787 | Cooling System Panel Fabrication - INTT Stave | 2022-11-18 | 2022-11-21 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Budgeted Units |  |  |  | 120
S332788 | Cooling System Panel Fabrication - MVTX | 2022-11-22 | 2022-11-23 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332788 | Cooling System Panel Fabrication - MVTX | 2022-11-22 | 2022-11-23 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332788 | Cooling System Panel Fabrication - MVTX | 2022-11-22 | 2022-11-23 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S332789 | Cooling System Platform Manifolding | 2022-11-28 | 2022-11-29 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S332789 | Cooling System Platform Manifolding | 2022-11-28 | 2022-11-29 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332789 | Cooling System Platform Manifolding | 2022-11-28 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 100 | 100 | C | Budgeted Units |  |  |  | 100
S332790 | Gas Distribution Panel Fabrication - TPC Ar-CF4 | 2022-10-03 | 2022-10-04 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332790 | Gas Distribution Panel Fabrication - TPC Ar-CF4 | 2022-10-03 | 2022-10-04 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332790 | Gas Distribution Panel Fabrication - TPC Ar-CF4 | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 100 | 100 | C | Budgeted Units |  |  |  | 100
S332791 | Gas Distribution Panel Fabrication - TPC Laser N2 | 2022-10-05 | 2022-10-06 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332791 | Gas Distribution Panel Fabrication - TPC Laser N2 | 2022-10-05 | 2022-10-06 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332791 | Gas Distribution Panel Fabrication - TPC Laser N2 | 2022-10-05 | 2022-10-06 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 2022-10-07 | 2022-10-11 | PROF3 PO E | PROF3 PO E | 4 | 4 | C | Budgeted Units |  |  |  | 4
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 2022-10-07 | 2022-10-11 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 2022-10-07 | 2022-10-11 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S332793 | Gas Distribution Panel Fabrication - EMCal SiPM N2 | 2022-10-12 | 2022-10-13 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332793 | Gas Distribution Panel Fabrication - EMCal SiPM N2 | 2022-10-12 | 2022-10-13 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332793 | Gas Distribution Panel Fabrication - EMCal SiPM N2 | 2022-10-12 | 2022-10-13 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S332794 | Gas Distribution Panel Fabrication - INTT Stave N2 | 2022-10-14 | 2022-10-17 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332794 | Gas Distribution Panel Fabrication - INTT Stave N2 | 2022-10-14 | 2022-10-17 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332794 | Gas Distribution Panel Fabrication - INTT Stave N2 | 2022-10-14 | 2022-10-17 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S332795 | Gas Distribution Panel Fabrication - MVTX N2 | 2022-10-18 | 2022-10-19 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332795 | Gas Distribution Panel Fabrication - MVTX N2 | 2022-10-18 | 2022-10-19 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332795 | Gas Distribution Panel Fabrication - MVTX N2 | 2022-10-18 | 2022-10-19 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S332796 | Gas Distribution Panel Fabrication - MBD dry compressed air | 2022-10-20 | 2022-10-21 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S332796 | Gas Distribution Panel Fabrication - MBD dry compressed air | 2022-10-20 | 2022-10-21 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S332796 | Gas Distribution Panel Fabrication - MBD dry compressed air | 2022-10-20 | 2022-10-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | TECH3 PO M | TECH3 PO M | 48 | 10 | C | Budgeted Units |  | 48
S332745 | Address Action items from Detector Gas Services Systems Design & Safety Reviews | 08-Jul-22 A | 19-Jul-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | TECH3 PO M | TECH3 PO M | 8 | 5 | C | Budgeted Units |  |  |  | 8
S331710 | Design Cooling Manifolds for EMCal | 18-Mar-20 A | 29-Apr-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units | 8
S331710 | Design Cooling Manifolds for EMCal | 18-Mar-20 A | 29-Apr-22 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units | 24
S331720 | Design Cooling Manifolds for TPC | 17-Mar-20 A | 16-Apr-21 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units | 8
S331720 | Design Cooling Manifolds for TPC | 17-Mar-20 A | 16-Apr-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units | 24
S331730 | Design Coolin Manifolds for INTT | 08-Dec-20 A | 27-Jun-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  | 8
S331730 | Design Coolin Manifolds for INTT | 08-Dec-20 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 24
S331740 | Design Coolin Manifolds for MVTX | 08-Feb-21 A | 22-Feb-21 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  | 8
S331740 | Design Coolin Manifolds for MVTX | 08-Feb-21 A | 22-Feb-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 24
S331750 | Conceptual Design for Routing Detector Cooling Chiller Systems to Det Manifolds | 23-Feb-21 A | 30-Sep-21 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  | 8
S331750 | Conceptual Design for Routing Detector Cooling Chiller Systems to Det Manifolds | 23-Feb-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 24
S331760 | Conceptual Design for Cooling Tube Routing from Detector to IHCal manifold | 12-Jul-21 A | 30-Jul-21 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  | 8
S331760 | Conceptual Design for Cooling Tube Routing from Detector to IHCal manifold | 12-Jul-21 A | 30-Jul-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 24
S331770 | Conceptual Design for Cooling Tube Routing from Detector to EMCal manifold | 08-Dec-20 A | 30-Sep-21 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  | 8
S331770 | Conceptual Design for Cooling Tube Routing from Detector to EMCal manifold | 08-Dec-20 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 24
S331780 | Conceptual Design for Cooling Tube Routing from Detector to TPC manifold | 08-Dec-20 A | 30-Sep-21 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  | 8
S331780 | Conceptual Design for Cooling Tube Routing from Detector to TPC manifold | 08-Dec-20 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 24
S331790 | Conceptual Design for Cooling Tube Routing from Detector to INTT, MVTX manifold | 14-Dec-20 A | 30-Sep-21 A | PROF4 PO E | PROF4 PO E | 16 | 0 | C | Budgeted Units |  | 16
S331790 | Conceptual Design for Cooling Tube Routing from Detector to INTT, MVTX manifold | 14-Dec-20 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 48 | 0 | C | Budgeted Units |  | 48
S331905 | Review Detector Cooling Services Systems Design/Safety | 22-Sep-21 A | 23-Sep-21 A | PROF4 PO E | PROF4 PO E | 16 | 0 | C | Budgeted Units |  |  | 16
POM02-13.02.04.01.05 Detector Safety Subsystems |  | 26-Apr-21 A | 2022-12-01 |  |  | 592 | 120 |  | Budgeted Units |  | 152 | 320 | 120
S332900 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - CA-D Resource(s) | 05-Jul-21 A | 27-Dec-21 A | PROF4 AD | PROF4 AD | 12 | 0 | C | Budgeted Units |  |  | 12
S333000 | Review Detector Safety Subsystems Design/Safety - CA-D Resource(s) | 06-Dec-21 A | 14-Dec-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S332800 | Analyze Detector Safety Subsystems Requirements - CA-D Resource(s) | 26-Apr-21 A | 30-Jun-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | 26-Apr-21 A | 30-Jun-21 A | PROF4 PO E | PROF4 PO E | 48 | 0 | C | Budgeted Units |  | 48
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | 26-Apr-21 A | 30-Jun-21 A | SCI3 PO | SCI3 PO | 24 | 0 | C | Budgeted Units |  | 24
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | 26-Apr-21 A | 30-Jun-21 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  | 24
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | 26-Apr-21 A | 30-Jun-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  | 24
S1002919 | Analyze Detector Safety Subsystems Requirements - Physics Resource(s) | 26-Apr-21 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 24
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | 14-Feb-22 A | 28-Feb-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | 14-Feb-22 A | 28-Feb-22 A | PROF4 PO E | PROF4 PO E | 16 | 0 | C | Budgeted Units |  |  | 16
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | 21-Feb-22 A | 31-Aug-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | 21-Feb-22 A | 31-Aug-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | 21-Feb-22 A | 31-Aug-22 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  |  | 24
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | 21-Feb-22 A | 31-Aug-22 A | PROF4 PO E | PROF4 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | 14-Feb-22 A | 30-Sep-22 A | TECH3 PO D | TECH3 PO D | 48 | 0 | C | Budgeted Units |  |  | 48
S333500 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | 14-Feb-22 A | 30-Sep-22 A | PROF4 PO E | PROF4 PO E | 48 | 0 | C | Budgeted Units |  |  | 48
S333700 | Perform Detector Safety Subsystems Components Acceptance | 14-Feb-22 A | 30-Sep-22 A | TECH3 PO D | TECH3 PO D | 4 | 0 | C | Budgeted Units |  |  | 4
S333700 | Perform Detector Safety Subsystems Components Acceptance | 14-Feb-22 A | 30-Sep-22 A | TECH3 PO M | TECH3 PO M | 4 | 0 | C | Budgeted Units |  |  | 4
S333700 | Perform Detector Safety Subsystems Components Acceptance | 14-Feb-22 A | 30-Sep-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S333700 | Perform Detector Safety Subsystems Components Acceptance | 14-Feb-22 A | 30-Sep-22 A | TECH3 PO E | TECH3 PO E | 4 | 0 | C | Budgeted Units |  |  | 4
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | 05-Jul-21 A | 27-Dec-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  |  | 24
S1002959 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems - Physics Resource(s) | 05-Jul-21 A | 27-Dec-21 A | PROF4 PO E | PROF4 PO E | 48 | 0 | C | Budgeted Units |  |  | 48
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | 06-Dec-21 A | 14-Dec-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S1002999 | Review Detector Safety Subsystems Design/Safety - Physics Resource(s) | 06-Dec-21 A | 14-Dec-21 A | PROF4 PO E | PROF4 PO E | 16 | 0 | C | Budgeted Units |  |  | 16
S333720 | Fabricate Detector Safety Systems | 2022-11-01 | 2022-12-01 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S333720 | Fabricate Detector Safety Systems | 2022-11-01 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Budgeted Units |  |  |  | 60
S333720 | Fabricate Detector Safety Systems | 2022-11-01 | 2022-12-01 | PROF4 PO E | PROF4 PO E | 0 | 0 | C | Budgeted Units
S333720 | Fabricate Detector Safety Systems | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 60 | 60 | C | Budgeted Units |  |  |  | 60
POM02-13.02.04.01.06 Gas Mixing House & Gas Pad Components |  | 01-Apr-21 A | 30-Sep-21 A |  |  | 846 | 0 |  | Budgeted Units |  | 84 | 762
S333900 | Analyze Gas Mixing House & Gas Pad Components Requirements - CA-D Resource(s) | 01-Apr-21 A | 28-Jun-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 9 | 7
S334000 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specs Control Documents C | 01-Apr-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S334100 | Review Gas Mixing House & Gas Pad Components Design/Safety - CA-D Resource(s) | 01-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S334400 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - CA-D Resource(s) | 01-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S334500 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - CA-D Resource(s) | 01-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S334800 | Perform Gas Mixing House & Gas Pad Components Acceptance - CA-D Resource(s) | 01-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | 01-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | 01-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 01-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 72 | 0 | C | Budgeted Units |  |  | 72
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 01-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 72 | 0 | C | Budgeted Units |  |  | 72
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 01-Sep-21 A | 30-Sep-21 A | TECH3 PO M | TECH3 PO M | 72 | 0 | C | Budgeted Units |  |  | 72
S334600 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) - Labor | 01-Sep-21 A | 30-Sep-21 A | TECH3 PO E | TECH3 PO E | 72 | 0 | C | Budgeted Units |  |  | 72
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | 01-Apr-21 A | 28-Jun-21 A | PROF4 PO M | PROF4 PO M | 60 | 0 | C | Budgeted Units |  | 34 | 26
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | 01-Apr-21 A | 28-Jun-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  | 14 | 10
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | 01-Apr-21 A | 28-Jun-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  | 14 | 10
S1003039 | Analyze Gas Mixing House & Gas Pad Components Requirements - Physics Resource(s) | 01-Apr-21 A | 28-Jun-21 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  | 14 | 10
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specs Control Documents P | 01-Apr-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specs Control Documents P | 01-Apr-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 60 | 0 | C | Budgeted Units |  |  | 60
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specs Control Documents P | 01-Apr-21 A | 30-Sep-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S1003079 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specs Control Documents P | 01-Apr-21 A | 30-Sep-21 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S1003119 | Review Gas Mixing House & Gas Pad Components Design/Safety - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1003119 | Review Gas Mixing House & Gas Pad Components Design/Safety - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  |  | 24
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S1003159 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  |  | 24
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S1003199 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1003239 | Perform Gas Mixing House & Gas Pad Components Acceptance - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
POM02-13.02.04.01.07 Rack Room Modifications |  | 14-Sep-20 A | 27-Jun-22 A |  |  | 600 | 0 |  | Budgeted Units |  | 202 | 362 | 36
S335000 | Analyze Rack Room Modifications Requirements - CA-D Resource(s) | 14-Sep-20 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  | 2
S335500 | Prepare Rack Room Modifications Components Procurement Package(s) - CA-D Resource(s) | 10-Jan-22 A | 24-Jan-22 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | 02-Jul-21 A | 24-Jan-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | 02-Jul-21 A | 24-Jan-22 A | PROF4 PO E | PROF4 PO E | 32 | 0 | C | Budgeted Units |  | 32
S335200 | Review Rack Room Modifications Components Design/Safety | 10-Jan-22 A | 24-Jan-22 A | SCI3 PO | SCI3 PO | 8 | 0 | C | Budgeted Units |  |  | 8
S335200 | Review Rack Room Modifications Components Design/Safety | 10-Jan-22 A | 24-Jan-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 10-Jan-22 A | 24-Jan-22 A | SCI3 PO | SCI3 PO | 8 | 0 | C | Budgeted Units |  |  | 8
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 10-Jan-22 A | 24-Jan-22 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 10-Jan-22 A | 24-Jan-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 10-Jan-22 A | 24-Jan-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | 10-Jan-22 A | 24-Jan-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 14-Feb-22 A | 27-Jun-22 A | PROF4 PO E | PROF4 PO E | 16 | 0 | C | Budgeted Units |  |  | 16
S335600 | Evaluate & Process Rack Room Modifications Components Bids | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO E | TECH3 PO E | 16 | 0 | C | Budgeted Units |  |  | 16
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 24 | 0 | C | Budgeted Units |  |  | 24
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO M | TECH3 PO M | 48 | 0 | C | Budgeted Units |  |  | 48
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 14-Feb-22 A | 27-Jun-22 A | PROF4 PO E | PROF4 PO E | 48 | 0 | C | Budgeted Units |  |  | 48
S335700 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) - Labor | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO E | TECH3 PO E | 48 | 0 | C | Budgeted Units |  |  | 48
S335900 | Perform Rack Room Modifications Components Acceptance | 14-Feb-22 A | 27-Jun-22 A | SCI3 PO | SCI3 PO | 8 | 0 | C | Budgeted Units |  |  |  | 8
S335900 | Perform Rack Room Modifications Components Acceptance | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 4 | 0 | C | Budgeted Units |  |  |  | 4
S335900 | Perform Rack Room Modifications Components Acceptance | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  |  | 8
S335900 | Perform Rack Room Modifications Components Acceptance | 14-Feb-22 A | 27-Jun-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  |  | 8
S335900 | Perform Rack Room Modifications Components Acceptance | 14-Feb-22 A | 27-Jun-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  |  | 8
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | 14-Sep-20 A | 26-Feb-21 A | PROF4 PO E | PROF4 PO E | 32 | 0 | C | Budgeted Units |  | 32
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | 14-Sep-20 A | 26-Feb-21 A | SCI3 PO | SCI3 PO | 32 | 0 | C | Budgeted Units |  | 32
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | 14-Sep-20 A | 26-Feb-21 A | TECH3 PO E | TECH3 PO E | 32 | 0 | C | Budgeted Units |  | 32
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | 14-Sep-20 A | 26-Feb-21 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units |  | 32
S1003279 | Analyze Rack Room Modifications Requirements - Physics Resource(s) | 14-Sep-20 A | 26-Feb-21 A | TECH3 PO D | TECH3 PO D | 32 | 0 | C | Budgeted Units |  | 32
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 10-Jan-22 A | 24-Jan-22 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 10-Jan-22 A | 24-Jan-22 A | PROF4 PO E | PROF4 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S1003319 | Prepare Rack Room Modifications Components Procurement Package(s) - Physics Resource(s) | 10-Jan-22 A | 24-Jan-22 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
POM02-13.02.04.01.08 Control Room and Offices Modifications |  | 06-Sep-21 A | 26-Aug-22 A |  |  | 370 | 0 |  | Budgeted Units |  |  | 370
S336100 | Analyze Control Room and Offices Modifications Requirements - CA-D Resource(s) | 04-Oct-21 A | 25-Oct-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S336200 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents C | 06-Sep-21 A | 17-Jan-22 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S336600 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - CA-D Resource(s) | 14-Feb-22 A | 26-Aug-22 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S337000 | Perform Control Room and Offices Modifications Components Acceptance - CA-D Resource(s) | 14-Feb-22 A | 26-Aug-22 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S336300 | Review Control Room and Offices Modifications Design/Safety | 24-Jan-22 A | 31-Jan-22 A | SCI3 PO | SCI3 PO | 4 | 0 | C | Budgeted Units |  |  | 4
S336300 | Review Control Room and Offices Modifications Design/Safety | 24-Jan-22 A | 31-Jan-22 A | PROF4 PO E | PROF4 PO E | 4 | 0 | C | Budgeted Units |  |  | 4
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 24-Jan-22 A | 31-Jan-22 A | SCI3 PO | SCI3 PO | 8 | 0 | C | Budgeted Units |  |  | 8
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 24-Jan-22 A | 31-Jan-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 24-Jan-22 A | 31-Jan-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 24-Jan-22 A | 31-Jan-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S336400 | Address Action Items from Control Room and Offices Modifications Design & Safety Reviews | 24-Jan-22 A | 31-Jan-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 14-Feb-22 A | 26-Aug-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 14-Feb-22 A | 26-Aug-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 14-Feb-22 A | 26-Aug-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S336700 | Evaluate & Process Control Room and Offices Modifications Components Bids | 14-Feb-22 A | 26-Aug-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 06-Dec-21 A | 27-Dec-21 A | TECH3 PO D | TECH3 PO D | 48 | 0 | C | Budgeted Units |  |  | 48
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 06-Dec-21 A | 27-Dec-21 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 06-Dec-21 A | 27-Dec-21 A | PROF4 PO E | PROF4 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S336800 | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included) - Labor | 06-Dec-21 A | 27-Dec-21 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 04-Oct-21 A | 25-Oct-21 A | SCI3 PO | SCI3 PO | 8 | 0 | C | Budgeted Units |  |  | 8
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 04-Oct-21 A | 25-Oct-21 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 04-Oct-21 A | 25-Oct-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 04-Oct-21 A | 25-Oct-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S1003359 | Analyze Control Room and Offices Modifications Requirements - Physics Resource(s) | 04-Oct-21 A | 25-Oct-21 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | 06-Sep-21 A | 17-Jan-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S1003439 | Create Control Room and Offices Modifications Schematic Design and Specification Control Documents P | 06-Sep-21 A | 17-Jan-22 A | PROF4 PO E | PROF4 PO E | 4 | 0 | C | Budgeted Units |  |  | 4
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 10-Jan-22 A | 17-Jan-22 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  |  | 24
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 10-Jan-22 A | 17-Jan-22 A | PROF4 PO E | PROF4 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S1003519 | Prepare Control Room and Offices Modifications Components Procurement Package(s) - Physics Resource(s) | 10-Jan-22 A | 17-Jan-22 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 10-Jan-22 A | 17-Jan-22 A | SCI3 PO | SCI3 PO | 8 | 0 | C | Budgeted Units |  |  | 8
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 10-Jan-22 A | 17-Jan-22 A | TECH3 PO D | TECH3 PO D | 4 | 0 | C | Budgeted Units |  |  | 4
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 10-Jan-22 A | 17-Jan-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 10-Jan-22 A | 17-Jan-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S1003599 | Perform Control Room and Offices Modifications Components Acceptance - Physics Resource(s) | 10-Jan-22 A | 17-Jan-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
POM02-13.02.04.02 Infrastructure Facility Support Systems |  | 01-Oct-19 A | 2023-01-06 |  |  | 6376 | 462 |  | Budgeted Units | 941 | 2803 | 2016 | 616
POM02-13.02.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR |  | 01-Oct-19 A | 2022-10-04 |  |  | 785 | 113 |  | Budgeted Units | 216 | 456 |  | 113
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | 30-Oct-19 A | 31-Aug-20 A | TECH3 AD | TECH3 AD | 7 | 0 | C | Budgeted Units | 7
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | 15-Oct-20 A | 29-Jan-21 A | TECH4 AD | TECH4 AD | 20 | 0 | C | Budgeted Units |  | 20
S337310 | Create Cryo Routing in IR Layout Drawings - CA-D Resource(s) | 01-Oct-19 A | 31-Aug-20 A | TECH4 AD | TECH4 AD | 24 | 0 | C | Budgeted Units | 24
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | 30-Oct-19 A | 31-Aug-20 A | TECH3 AD | TECH3 AD | 7 | 0 | C | Budgeted Units | 7
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | 30-Oct-19 A | 31-Aug-20 A | TECH4 AD | TECH4 AD | 7 | 0 | C | Budgeted Units | 7
S337500 | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety | 17-Jun-20 A | 30-Oct-20 A | TECH4 AD | TECH4 AD | 12 | 0 | C | Budgeted Units | 12
S337600 | Address Action Items from Cryo Structural Support in IR Detail Design & Safety Reviews | 06-Oct-20 A | 13-Oct-20 A | TECH4 AD | TECH4 AD | 7 | 0 | C | Budgeted Units |  | 7
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | 15-Oct-20 A | 29-Jan-21 A | TECH4 AD | TECH4 AD | 24 | 0 | C | Budgeted Units |  | 24
S337900 | Evaluate & Process Magnet Cryo, Electrical & Control Structural Support in IR Components Bids | 14-Oct-20 A | 29-Jan-21 A | TECH4 AD | TECH4 AD | 24 | 0 | C | Budgeted Units |  | 24
S338000 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fab incl) - Labor | 14-Oct-20 A | 29-Jan-21 A | TECH4 AD | TECH4 AD | 64 | 0 | C | Budgeted Units |  | 64
S338100 | Perform Magnet Cryo, Electrical & Control Structural Support in IR Components Acceptance | 19-Jan-21 A | 29-Jan-21 A | TECH3 AD | TECH3 AD | 8 | 0 | C | Budgeted Units |  | 8
S337310 | Create Cryo Routing in IR Layout Drawings - CA-D Resource(s) | 01-Oct-19 A | 31-Aug-20 A | TECH4 AD | TECH4 AD | 16 | 0 | C | Budgeted Units | 16
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | 30-Oct-19 A | 31-Aug-20 A | PROF2 AD | PROF2 AD | 14 | 0 | C | Budgeted Units | 14
S337500 | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety | 17-Jun-20 A | 30-Oct-20 A | PROF2 AD | PROF2 AD | 24 | 0 | C | Budgeted Units | 24
S337600 | Address Action Items from Cryo Structural Support in IR Detail Design & Safety Reviews | 06-Oct-20 A | 13-Oct-20 A | PROF2 AD | PROF2 AD | 29 | 0 | C | Budgeted Units |  | 29
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | 15-Oct-20 A | 29-Jan-21 A | PROF2 AD | PROF2 AD | 88 | 0 | C | Budgeted Units |  | 88
S337900 | Evaluate & Process Magnet Cryo, Electrical & Control Structural Support in IR Components Bids | 14-Oct-20 A | 29-Jan-21 A | PROF2 AD | PROF2 AD | 48 | 0 | C | Budgeted Units |  | 48
S338000 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fab incl) - Labor | 14-Oct-20 A | 29-Jan-21 A | PROF2 AD | PROF2 AD | 128 | 0 | C | Budgeted Units |  | 128
S338100 | Perform Magnet Cryo, Electrical & Control Structural Support in IR Components Acceptance | 19-Jan-21 A | 29-Jan-21 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  | 16
S337310 | Create Cryo Routing in IR Layout Drawings - CA-D Resource(s) | 01-Oct-19 A | 31-Aug-20 A | PROF2 AD | PROF2 AD | 80 | 0 | C | Budgeted Units | 80
S337300 | Create Cryo Routing in IR Layout Drawings - Physics Resource(s) | 01-Oct-19 A | 31-Aug-20 A | PROF4 PO M | PROF4 PO M | 24 | 0 | C | Budgeted Units | 24
S277700 | 2023 Detector Support Systems L3 Project Management | 2022-10-03 | 2022-10-04 | PROF5 PO M | PROF5 PO M | 113 | 113 | C | Budgeted Units |  |  |  | 113
POM02-13.02.04.02.02 Beampipe/Vacuum |  | 02-Mar-20 A | 27-May-22 A |  |  | 1070 | 0 |  | Budgeted Units |  | 518 | 547 | 5
S338410 | Create Beampipe/Vacuum Layout - CA-D Resource(s) | 02-Mar-20 A | 31-Mar-20 A | PROF4 AD | PROF4 AD | 36 | 0 | C | Budgeted Units |  | 36
S338710 | Review Beampipe/Vacuum Design/Safety - CA-D Resource(s) | 02-Mar-20 A | 31-Mar-20 A | PROF4 AD | PROF4 AD | 30 | 0 | C | Budgeted Units |  | 30
S338710 | Review Beampipe/Vacuum Design/Safety - CA-D Resource(s) | 02-Mar-20 A | 31-Mar-20 A | TECH4 AD | TECH4 AD | 20 | 0 | C | Budgeted Units |  | 20
S338810 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews - CA-D Resource(s) | 02-Mar-20 A | 31-Mar-20 A | PROF4 AD | PROF4 AD | 36 | 0 | C | Budgeted Units |  | 36
S339010 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation - CA-D Resource(s) | 16-Jul-20 A | 31-Jul-20 A | PROF4 AD | PROF4 AD | 36 | 0 | C | Budgeted Units |  | 36
S339110 | Evaluate & Process Beampipe/Vacuum Components Bids - CA-D Resource(s) | 16-Jul-20 A | 30-Oct-20 A | PROF4 AD | PROF4 AD | 36 | 0 | C | Budgeted Units |  | 36
S339210 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) - CA-D Resource(s) | 04-Jan-21 A | 31-May-21 A | PROF4 AD | PROF4 AD | 36 | 0 | C | Budgeted Units |  | 36
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) NEG coating | 02-May-22 A | 27-May-22 A | PROF4 AD | PROF4 AD | 10 | 0 | C | Budgeted Units |  |  | 9 | 1
S339310 | Perform Beampipe/vacuum Acceptance - CA-D Resource(s) NEG coating | 02-May-22 A | 27-May-22 A | TECH3 AD | TECH3 AD | 26 | 0 | C | Budgeted Units |  |  | 22 | 4
S338400 | Create Beampipe/Vacuum Layout - Physics Resource(s) | 02-Mar-20 A | 31-Mar-20 A | PROF4 PO M | PROF4 PO M | 9 | 0 | C | Budgeted Units |  | 9
S338400 | Create Beampipe/Vacuum Layout - Physics Resource(s) | 02-Mar-20 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 18 | 0 | C | Budgeted Units |  | 18
S338400 | Create Beampipe/Vacuum Layout - Physics Resource(s) | 02-Mar-20 A | 31-Mar-20 A | SCI3 PO | SCI3 PO | 9 | 0 | C | Budgeted Units |  | 9
S338500 | Create Beampipe/Vacuum Envelope Drawing | 02-Mar-20 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units |  | 36
S338600 | Create Beampipe/Vacuum subassembly and detail Drawings | 02-Mar-20 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units |  | 36
S338700 | Review Beampipe/Vacuum Design/Safety - Physics Resource(s) | 02-Mar-20 A | 31-Mar-20 A | SCI3 PO | SCI3 PO | 18 | 0 | C | Budgeted Units |  | 18
S338700 | Review Beampipe/Vacuum Design/Safety - Physics Resource(s) | 02-Mar-20 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 18 | 0 | C | Budgeted Units |  | 18
S338800 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews - Physics Resource(s) | 02-Mar-20 A | 31-Mar-20 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units |  | 36
S339000 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation - Physics Resource(s) | 01-Jul-20 A | 15-Jul-20 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units |  | 36
S339100 | Evaluate & Process Beampipe/Vacuum Components Bids - Physics Resource(s) | 15-Jul-20 A | 30-Oct-20 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units |  | 36
S339200 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) - Physics Resource(s) | 04-Jan-21 A | 31-May-21 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units |  | 36
S339300 | Perform Beampipe/vacuum Acceptance - Physics Resource(s) NEG coating | 02-May-22 A | 27-May-22 A | TECH3 PO D | TECH3 PO D | 36 | 0 | C | Budgeted Units |  |  | 36
S339355 | NEG Re-coating of beryllium beampipe | 02-May-22 A | 27-May-22 A | PROF3 AD | PROF3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
S339355 | NEG Re-coating of beryllium beampipe | 02-May-22 A | 27-May-22 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
POM02-13.02.04.02.03 IR HVAC |  | 01-Oct-20 A | 29-Jul-22 A |  |  | 454 | 0 |  | Budgeted Units |  | 140 | 314
S339600 | Model IR HVAC Thermal Requirements | 01-Oct-20 A | 29-Jan-21 A | TECH4 AD | TECH4 AD | 7 | 0 | C | Budgeted Units |  | 7
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | 21-Dec-20 A | 30-Jul-21 A | TECH4 AD | TECH4 AD | 6 | 0 | C | Budgeted Units |  | 6
S339800 | Review IR HVAC Design/Safety | 02-Sep-21 A | 30-Sep-21 A | TECH4 AD | TECH4 AD | 9 | 0 | C | Budgeted Units |  | 9
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | 02-Sep-21 A | 30-Sep-21 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  | 8
S340100 | Prepare IR HVAC Components Procurement Package(s) | 02-Sep-21 A | 30-Sep-21 A | TECH4 AD | TECH4 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S340200 | Evaluate & Process IR HVAC Components Bids | 02-Sep-21 A | 27-May-22 A | TECH4 AD | TECH4 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | 16-Nov-21 A | 29-Jul-22 A | TECH4 AD | TECH4 AD | 48 | 0 | C | Budgeted Units |  |  | 48
S340400 | Perform IR HVAC Components Acceptance | 14-Dec-21 A | 29-Jul-22 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  |  | 40
S340400 | Perform IR HVAC Components Acceptance | 14-Dec-21 A | 29-Jul-22 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S339600 | Model IR HVAC Thermal Requirements | 01-Oct-20 A | 29-Jan-21 A | PROF2 AD | PROF2 AD | 13 | 0 | C | Budgeted Units |  | 13
S339600 | Model IR HVAC Thermal Requirements | 01-Oct-20 A | 29-Jan-21 A | PROF4 AD | PROF4 AD | 11 | 0 | C | Budgeted Units |  | 11
S339600 | Model IR HVAC Thermal Requirements | 01-Oct-20 A | 29-Jan-21 A | PROF6 AD | PROF6 AD | 3 | 0 | C | Budgeted Units |  | 3
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | 21-Dec-20 A | 30-Jul-21 A | PROF2 AD | PROF2 AD | 24 | 0 | C | Budgeted Units |  | 24
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | 21-Dec-20 A | 30-Jul-21 A | PROF4 AD | PROF4 AD | 6 | 0 | C | Budgeted Units |  | 6
S339800 | Review IR HVAC Design/Safety | 02-Sep-21 A | 30-Sep-21 A | PROF2 AD | PROF2 AD | 18 | 0 | C | Budgeted Units |  | 18
S339800 | Review IR HVAC Design/Safety | 02-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 9 | 0 | C | Budgeted Units |  | 9
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | 02-Sep-21 A | 30-Sep-21 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  | 16
S339900 | Address Action Items from IR HVAC Design & Safety Reviews | 02-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S340100 | Prepare IR HVAC Components Procurement Package(s) | 02-Sep-21 A | 30-Sep-21 A | PROF2 AD | PROF2 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S340100 | Prepare IR HVAC Components Procurement Package(s) | 02-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S340200 | Evaluate & Process IR HVAC Components Bids | 02-Sep-21 A | 27-May-22 A | PROF2 AD | PROF2 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S340200 | Evaluate & Process IR HVAC Components Bids | 02-Sep-21 A | 27-May-22 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S340300 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) - Labor | 16-Nov-21 A | 29-Jul-22 A | PROF2 AD | PROF2 AD | 96 | 0 | C | Budgeted Units |  |  | 96
S340400 | Perform IR HVAC Components Acceptance | 14-Dec-21 A | 29-Jul-22 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S340400 | Perform IR HVAC Components Acceptance | 14-Dec-21 A | 29-Jul-22 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S339600 | Model IR HVAC Thermal Requirements | 01-Oct-20 A | 29-Jan-21 A | CRAFT3 | CRAFT3 | 2 | 0 | C | Budgeted Units |  | 2
POM02-13.02.04.02.04 IR Electronics Cooling Water Distribution System |  | 01-Nov-19 A | 27-May-22 A |  |  | 690 | 0 |  | Budgeted Units | 274 | 181 | 235
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | 21-Dec-20 A | 28-Jul-21 A | TECH4 AD | TECH4 AD | 32 | 0 | C | Budgeted Units |  | 32
S340900 | Review IR Electronics cooling water System Design/Safety | 13-Dec-21 A | 20-Dec-21 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 20-Dec-21 A | 22-Dec-21 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 01-Dec-21 A | 24-Dec-21 A | TECH4 AD | TECH4 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 01-Dec-21 A | 24-Dec-21 A | TECH4 AD | TECH4 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 26-Apr-21 A | 27-May-22 A | TECH4 AD | TECH4 AD | 40 | 0 | C | Budgeted Units |  | 26 | 14
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 01-Dec-21 A | 27-May-22 A | TECH3 AD | TECH3 AD | 20 | 0 | C | Budgeted Units |  |  | 20
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 01-Dec-21 A | 27-May-22 A | TECH4 AD | TECH4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | 01-Nov-19 A | 25-Nov-19 A | TECH3 AD | TECH3 AD | 32 | 0 | C | Budgeted Units | 32
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | 01-Nov-19 A | 25-Nov-19 A | TECH4 AD | TECH4 AD | 32 | 0 | C | Budgeted Units | 32
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | 21-Dec-20 A | 28-Jul-21 A | PROF2 AD | PROF2 AD | 64 | 0 | C | Budgeted Units |  | 64
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | 21-Dec-20 A | 28-Jul-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  | 4
S340900 | Review IR Electronics cooling water System Design/Safety | 13-Dec-21 A | 20-Dec-21 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S340900 | Review IR Electronics cooling water System Design/Safety | 13-Dec-21 A | 20-Dec-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 20-Dec-21 A | 22-Dec-21 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | 20-Dec-21 A | 22-Dec-21 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 01-Dec-21 A | 24-Dec-21 A | PROF2 AD | PROF2 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | 01-Dec-21 A | 24-Dec-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 01-Dec-21 A | 24-Dec-21 A | PROF2 AD | PROF2 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | 01-Dec-21 A | 24-Dec-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 26-Apr-21 A | 27-May-22 A | PROF2 AD | PROF2 AD | 80 | 0 | C | Budgeted Units |  | 53 | 27
S341400 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) - Labor | 26-Apr-21 A | 27-May-22 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  | 1 | 1
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 01-Dec-21 A | 27-May-22 A | PROF2 AD | PROF2 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | 01-Dec-21 A | 27-May-22 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | 01-Nov-19 A | 25-Nov-19 A | PROF2 AD | PROF2 AD | 160 | 0 | C | Budgeted Units | 160
S340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements - CA-D Resource(s) | 01-Nov-19 A | 25-Nov-19 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units | 20
S340702 | Model IR Electronics Cooling Water Distribution Thermal Requirements - Physics Resource(s) Split | 01-Nov-19 A | 25-Nov-19 A | SCI3 PO | SCI3 PO | 30 | 0 | C | Budgeted Units | 30
POM02-13.02.04.02.05 IR/AH Safety Subsystems |  | 14-Dec-20 A | 2023-01-06 |  |  | 915 | 349 |  | Budgeted Units |  | 181 | 256 | 478
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 01-Apr-22 A | 30-Sep-22 A | TECH4 AD | TECH4 AD | 60 | 0 | C | Budgeted Units |  |  | 60
S342000 | Review IR/AH Safety Subsystems Design/Safety | 02-May-22 A | 30-Sep-22 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 02-May-22 A | 30-Sep-22 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 02-Sep-22 A | 30-Sep-22 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  |  |  | 8
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | TECH4 AD | TECH4 AD | 24 | 12 | C | Budgeted Units |  |  |  | 24
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | TECH4 AD | TECH4 AD | 48 | 36 | C | Budgeted Units |  |  |  | 48
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | TECH4 AD | TECH4 AD | 88 | 66 | C | Budgeted Units |  |  |  | 88
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 14-Dec-20 A | 28-Apr-22 A | TECH4 AD | TECH4 AD | 72 | 0 | C | Budgeted Units |  | 72
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 01-Apr-22 A | 30-Sep-22 A | PROF2 AD | PROF2 AD | 96 | 0 | C | Budgeted Units |  |  | 96
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | 01-Apr-22 A | 30-Sep-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S342000 | Review IR/AH Safety Subsystems Design/Safety | 02-May-22 A | 30-Sep-22 A | PROF2 AD | PROF2 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S342000 | Review IR/AH Safety Subsystems Design/Safety | 02-May-22 A | 30-Sep-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 02-May-22 A | 30-Sep-22 A | PROF2 AD | PROF2 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | 02-May-22 A | 30-Sep-22 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 02-Sep-22 A | 30-Sep-22 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  |  |  | 16
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | 02-Sep-22 A | 30-Sep-22 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  |  | 4
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | PROF2 AD | PROF2 AD | 48 | 24 | C | Budgeted Units |  |  |  | 48
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | PROF4 AD | PROF4 AD | 4 | 2 | C | Budgeted Units |  |  |  | 4
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | PROF2 AD | PROF2 AD | 96 | 72 | C | Budgeted Units |  |  |  | 96
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | PROF4 AD | PROF4 AD | 2 | 2 | C | Budgeted Units |  |  |  | 2
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | PROF2 AD | PROF2 AD | 16 | 12 | C | Budgeted Units |  |  |  | 16
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | PROF4 AD | PROF4 AD | 4 | 3 | C | Budgeted Units |  |  |  | 4
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 14-Dec-20 A | 28-Apr-22 A | PROF2 AD | PROF2 AD | 96 | 0 | C | Budgeted Units |  | 96
S341810 | Analyze IR/AH Safety Subsystems Requirements - CA-D Resource(s) | 14-Dec-20 A | 28-Apr-22 A | PROF4 AD | PROF4 AD | 10 | 0 | C | Budgeted Units |  | 10
S341800 | Analyze IR/AH Safety Subsystems Requirements - Physics Resource(s) | 14-Dec-20 A | 28-Apr-22 A | SCI3 PO | SCI3 PO | 3 | 0 | C | Budgeted Units |  | 3
S342390 | Design IR/AH Safety Systems | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S342390 | Design IR/AH Safety Systems | 2022-11-01 | 2022-12-30 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S342390 | Design IR/AH Safety Systems | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S342390 | Design IR/AH Safety Systems | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
POM02-13.02.04.02.06 Assembly Hall and Interaction Region Modifications |  | 18-Oct-19 A | 26-Sep-22 A |  |  | 2462 | 0 |  | Budgeted Units | 451 | 1327 | 664 | 20
S343814 | Start Track Modification - IR Assembly and Detail Drawings | 03-Aug-20 A | 30-Sep-20 A | TECH3 AD | TECH3 AD | 100 | 0 | C | Budgeted Units | 57 | 43
S343822 | Start Track Modification - IR Prepare Procur. Package | 01-Oct-20 A | 15-Oct-20 A | TECH3 AD | TECH3 AD | 32 | 0 | C | Budgeted Units |  | 32
S343818 | Start Track Modification - IR Address Action Items from D&S Review | 03-Aug-20 A | 30-Sep-20 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343816 | Start Track Modification - IR Final Design and Safety Review | 03-Aug-20 A | 30-Sep-20 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343824 | Start Track Modification - IR Procur. Readiness Review | 16-Oct-20 A | 22-Oct-20 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343854 | Start Track Modification - AH Final Design and Safety Review | 08-Sep-20 A | 30-Sep-20 A | TECH3 AD | TECH3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343852 | Start Track Modification - AH Assembly and Detail Drawings | 08-Sep-20 A | 30-Sep-20 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  | 40
S343856 | Start Track Modification - AH Address Action Items from D&S Review | 08-Sep-20 A | 30-Sep-20 A | TECH3 AD | TECH3 AD | 8 | 0 | C | Budgeted Units |  | 8
S342900 | Analyze Assembly Hall Modification Requirements | 04-Jan-21 A | 25-May-21 A | TECH4 AD | TECH4 AD | 72 | 0 | C | Budgeted Units |  | 72
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | 13-Sep-21 A | 26-Nov-21 A | TECH4 AD | TECH4 AD | 24 | 0 | C | Budgeted Units |  |  | 24
S343100 | Review Assembly Hall Modifications Design/Safety | 18-Oct-21 A | 26-Nov-21 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 14-Feb-22 A | 29-Apr-22 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 01-Apr-22 A | 27-Apr-22 A | TECH4 AD | TECH4 AD | 72 | 0 | C | Budgeted Units |  |  | 72
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 01-Apr-22 A | 28-Apr-22 A | TECH4 AD | TECH4 AD | 72 | 0 | C | Budgeted Units |  |  | 72
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 26-May-22 A | 25-Sep-22 A | TECH4 AD | TECH4 AD | 72 | 0 | C | Budgeted Units |  |  | 72
S343700 | Perform Assembly Hall Modifications Components Acceptance | 31-Aug-22 A | 26-Sep-22 A | TECH4 AD | TECH4 AD | 24 | 0 | C | Budgeted Units |  |  | 12 | 12
S342900 | Analyze Assembly Hall Modification Requirements | 04-Jan-21 A | 25-May-21 A | PROF2 AD | PROF2 AD | 120 | 0 | C | Budgeted Units |  | 120
S342900 | Analyze Assembly Hall Modification Requirements | 04-Jan-21 A | 25-May-21 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units |  | 20
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | 13-Sep-21 A | 26-Nov-21 A | PROF2 AD | PROF2 AD | 48 | 0 | C | Budgeted Units |  |  | 48
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | 13-Sep-21 A | 26-Nov-21 A | PROF4 AD | PROF4 AD | 20 | 0 | C | Budgeted Units |  |  | 20
S343100 | Review Assembly Hall Modifications Design/Safety | 18-Oct-21 A | 26-Nov-21 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S343100 | Review Assembly Hall Modifications Design/Safety | 18-Oct-21 A | 26-Nov-21 A | PROF4 AD | PROF4 AD | 5 | 0 | C | Budgeted Units |  |  | 5
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 14-Feb-22 A | 29-Apr-22 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | 14-Feb-22 A | 29-Apr-22 A | PROF4 AD | PROF4 AD | 5 | 0 | C | Budgeted Units |  |  | 5
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 01-Apr-22 A | 27-Apr-22 A | PROF2 AD | PROF2 AD | 48 | 0 | C | Budgeted Units |  |  | 48
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | 01-Apr-22 A | 27-Apr-22 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 01-Apr-22 A | 28-Apr-22 A | PROF2 AD | PROF2 AD | 48 | 0 | C | Budgeted Units |  |  | 48
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | 01-Apr-22 A | 28-Apr-22 A | PROF4 AD | PROF4 AD | 2 | 0 | C | Budgeted Units |  |  | 2
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 26-May-22 A | 25-Sep-22 A | PROF2 AD | PROF2 AD | 144 | 0 | C | Budgeted Units |  |  | 144
S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) - Labor | 26-May-22 A | 25-Sep-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S343700 | Perform Assembly Hall Modifications Components Acceptance | 31-Aug-22 A | 26-Sep-22 A | PROF2 AD | PROF2 AD | 16 | 0 | C | Budgeted Units |  |  | 8 | 8
S343810 | Start Track Modification - IR Structural Analysis of Existing Track System and Prelim Design | 18-Oct-19 A | 31-Aug-20 A | PROF3 AD | PROF3 AD | 120 | 0 | C | Budgeted Units | 120
S343810 | Start Track Modification - IR Structural Analysis of Existing Track System and Prelim Design | 18-Oct-19 A | 31-Aug-20 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units | 40
S343814 | Start Track Modification - IR Assembly and Detail Drawings | 03-Aug-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 40 | 0 | C | Budgeted Units | 23 | 17
S343814 | Start Track Modification - IR Assembly and Detail Drawings | 03-Aug-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units | 9 | 7
S343812 | Start Track Modification - IR Prelim Design and Safety Review | 03-Aug-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units | 16
S343812 | Start Track Modification - IR Prelim Design and Safety Review | 03-Aug-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 6 | 0 | C | Budgeted Units | 6
S343822 | Start Track Modification - IR Prepare Procur. Package | 01-Oct-20 A | 15-Oct-20 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343818 | Start Track Modification - IR Address Action Items from D&S Review | 03-Aug-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343816 | Start Track Modification - IR Final Design and Safety Review | 03-Aug-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343816 | Start Track Modification - IR Final Design and Safety Review | 03-Aug-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S343836 | Start Track Modification - IR Develop and Submit Safety Plan | 11-Jan-21 A | 16-Feb-21 A | PROF3 AD | PROF3 AD | 24 | 0 | C | Budgeted Units |  | 24
S343826 | Start Track Modification - IR Provide Requirements to Procurements | 23-Oct-20 A | 29-Oct-20 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343824 | Start Track Modification - IR Procur. Readiness Review | 16-Oct-20 A | 22-Oct-20 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343824 | Start Track Modification - IR Procur. Readiness Review | 16-Oct-20 A | 22-Oct-20 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S343832 | Start Track Modification - IR Vendor Selection | 11-Jan-21 A | 29-Jan-21 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units |  | 8
S343830 | Start Track Modification - IR Vendor Responses | 17-Nov-20 A | 29-Jan-21 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units |  | 8
S343828 | Start Track Modification - IR Prepare and Send Solicitations | 02-Nov-20 A | 16-Nov-20 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units |  | 8
S343842 | Start Track Modification - IR BNL Oversight of Construction | 02-Jul-21 A | 29-Oct-21 A | PROF3 AD | PROF3 AD | 104 | 0 | C | Budgeted Units |  | 104
S343842 | Start Track Modification - IR BNL Oversight of Construction | 02-Jul-21 A | 29-Oct-21 A | PROF4 AD | PROF4 AD | 23 | 0 | C | Budgeted Units |  | 23
S343850 | Start Track Modification - AH Prelim Design and Safety Review | 08-Sep-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 20 | 0 | C | Budgeted Units |  | 20
S343850 | Start Track Modification - AH Prelim Design and Safety Review | 08-Sep-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S343848 | Start Track Modification - AH Structural Analysis of Existing Track System and Prelim. Design | 18-Oct-19 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 100 | 0 | C | Budgeted Units | 100
S343848 | Start Track Modification - AH Structural Analysis of Existing Track System and Prelim. Design | 18-Oct-19 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 80 | 0 | C | Budgeted Units | 80
S343844 | Start Track Modification - IR Delivery Acceptance Labor | 11-Oct-21 A | 29-Oct-21 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S343844 | Start Track Modification - IR Delivery Acceptance Labor | 11-Oct-21 A | 29-Oct-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S343864 | Start Track Modification - AH Survey and Grout Plates Labor - External | 01-Feb-21 A | 30-Apr-21 A | PROF3 AD | PROF3 AD | 20 | 0 | C | Budgeted Units |  | 20
S343864 | Start Track Modification - AH Survey and Grout Plates Labor - External | 01-Feb-21 A | 30-Apr-21 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S343854 | Start Track Modification - AH Final Design and Safety Review | 08-Sep-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 16 | 0 | C | Budgeted Units |  | 16
S343854 | Start Track Modification - AH Final Design and Safety Review | 08-Sep-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 16 | 0 | C | Budgeted Units |  | 16
S343852 | Start Track Modification - AH Assembly and Detail Drawings | 08-Sep-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 30 | 0 | C | Budgeted Units |  | 30
S343852 | Start Track Modification - AH Assembly and Detail Drawings | 08-Sep-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 12 | 0 | C | Budgeted Units |  | 12
S343862 | Start Track Modification - AH Install Track Plates and Blocks - Internal | 01-Feb-21 A | 31-Mar-21 A | PROF3 AD | PROF3 AD | 26 | 0 | C | Budgeted Units |  | 26
S343862 | Start Track Modification - AH Install Track Plates and Blocks - Internal | 01-Feb-21 A | 31-Mar-21 A | PROF4 AD | PROF4 AD | 5 | 0 | C | Budgeted Units |  | 5
S343860 | Start Track Modification - AH Fabricate Track Plates Labor - Internal | 01-Feb-21 A | 29-Mar-21 A | PROF3 AD | PROF3 AD | 23 | 0 | C | Budgeted Units |  | 23
S343860 | Start Track Modification - AH Fabricate Track Plates Labor - Internal | 01-Feb-21 A | 29-Mar-21 A | PROF4 AD | PROF4 AD | 9 | 0 | C | Budgeted Units |  | 9
S343856 | Start Track Modification - AH Address Action Items from D&S Review | 08-Sep-20 A | 30-Sep-20 A | PROF3 AD | PROF3 AD | 8 | 0 | C | Budgeted Units |  | 8
S343856 | Start Track Modification - AH Address Action Items from D&S Review | 08-Sep-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S343864 | Start Track Modification - AH Survey and Grout Plates Labor - External | 01-Feb-21 A | 30-Apr-21 A | TECH3 AD | TECH3 AD | 180 | 0 | C | Budgeted Units |  | 180
S343862 | Start Track Modification - AH Install Track Plates and Blocks - Internal | 01-Feb-21 A | 31-Mar-21 A | TECH3 AD | TECH3 AD | 5 | 0 | C | Budgeted Units |  | 5
S343864 | Start Track Modification - AH Survey and Grout Plates Labor - External | 01-Feb-21 A | 30-Apr-21 A | CRAFT3 | CRAFT3 | 144 | 0 | C | Budgeted Units |  | 144
S343862 | Start Track Modification - AH Install Track Plates and Blocks - Internal | 01-Feb-21 A | 31-Mar-21 A | CRAFT3 | CRAFT3 | 78 | 0 | C | Budgeted Units |  | 78
POM02-13.02.05 Integration and Installation |  | 01-Oct-19 A | 2023-03-29 |  |  | 51082 | 24414 |  | Budgeted Units | 1743 | 6621 | 18280 | 24437
POM02-13.02.05.01 Subsystem Interface & Integration Plan |  | 02-Dec-19 A | 27-Jan-21 A |  |  | 664 | 0 |  | Budgeted Units | 392 | 272
S344700 | Create Services Management Plan | 02-Dec-19 A | 27-Jan-21 A | PROF4 PO M | PROF4 PO M | 80 | 0 | C | Budgeted Units | 80
S344700 | Create Services Management Plan | 02-Dec-19 A | 27-Jan-21 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units | 32
S344700 | Create Services Management Plan | 02-Dec-19 A | 27-Jan-21 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units | 40
S344800 | Create Survey Plan | 15-Sep-20 A | 27-Jan-21 A | PROF4 PO M | PROF4 PO M | 40 | 0 | C | Budgeted Units |  | 40
S344800 | Create Survey Plan | 15-Sep-20 A | 27-Jan-21 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units |  | 32
S344800 | Create Survey Plan | 15-Sep-20 A | 27-Jan-21 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units |  | 40
S345000 | Review Integration and Installation Plan Design/Safety | 12-Jan-21 A | 27-Jan-21 A | PROF4 PO M | PROF4 PO M | 20 | 0 | C | Budgeted Units |  | 20
S345000 | Review Integration and Installation Plan Design/Safety | 12-Jan-21 A | 27-Jan-21 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  | 20
S345000 | Review Integration and Installation Plan Design/Safety | 12-Jan-21 A | 27-Jan-21 A | SCI3 PO | SCI3 PO | 20 | 0 | C | Budgeted Units |  | 20
S345100 | Review Cable Management Plan | 12-Jan-21 A | 27-Jan-21 A | PROF4 PO M | PROF4 PO M | 20 | 0 | C | Budgeted Units |  | 20
S345100 | Review Cable Management Plan | 12-Jan-21 A | 27-Jan-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units |  | 10
S345100 | Review Cable Management Plan | 12-Jan-21 A | 27-Jan-21 A | PROF4 PO E | PROF4 PO E | 10 | 0 | C | Budgeted Units |  | 10
S345200 | Review Survey Plan | 12-Jan-21 A | 27-Jan-21 A | PROF4 PO M | PROF4 PO M | 10 | 0 | C | Budgeted Units |  | 10
S345200 | Review Survey Plan | 12-Jan-21 A | 27-Jan-21 A | TECH3 PO M | TECH3 PO M | 10 | 0 | C | Budgeted Units |  | 10
S345200 | Review Survey Plan | 12-Jan-21 A | 27-Jan-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units |  | 10
S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey P | 12-Jan-21 A | 27-Jan-21 A | PROF4 PO M | PROF4 PO M | 10 | 0 | C | Budgeted Units |  | 10
S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey P | 12-Jan-21 A | 27-Jan-21 A | TECH3 PO M | TECH3 PO M | 10 | 0 | C | Budgeted Units |  | 10
S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey P | 12-Jan-21 A | 27-Jan-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units |  | 10
S344900 | Create Installation Plan | 12-Jan-21 A | 27-Jan-21 A | PROF4 PO M | PROF4 PO M | 80 | 0 | C | Budgeted Units | 80
S344900 | Create Installation Plan | 12-Jan-21 A | 27-Jan-21 A | TECH3 PO D | TECH3 PO D | 160 | 0 | C | Budgeted Units | 160
POM02-13.02.05.02 Infrastructure Installation |  | 22-Feb-21 A | 2023-02-06 |  |  | 9702 | 6303 |  | Budgeted Units |  | 536 | 3385 | 5781
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | PROF4 AD | PROF4 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 AD | TECH3 AD | 104 | 104 | C | Budgeted Units |  |  |  | 104
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | PROF2 AD | PROF2 AD | 40 | 2 | C | Budgeted Units |  |  | 40
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | PROF4 AD | PROF4 AD | 40 | 2 | C | Budgeted Units |  |  | 40
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 01-Apr-22 A | 31-Aug-22 A | PROF2 AD | PROF2 AD | 20 | 0 | C | Budgeted Units |  |  | 20
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 01-Apr-22 A | 31-Aug-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S346900 | Install Detector Support Services Systems - Labor - CA-D Resource(s) | 01-Apr-22 A | 30-Sep-22 A | PROF2 AD | PROF2 AD | 40 | 0 | C | Budgeted Units |  |  | 40
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | PROF4 AD | PROF4 AD | 16 | 12 | C | Budgeted Units |  |  |  | 16
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | PROF2 AD | PROF2 AD | 40 | 30 | C | Budgeted Units |  |  |  | 40
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | 22-Feb-21 A | 26-Feb-21 A | PROF2 AD | PROF2 AD | 80 | 0 | C | Budgeted Units |  | 80
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | 22-Feb-21 A | 26-Feb-21 A | PROF4 AD | PROF4 AD | 32 | 0 | C | Budgeted Units |  | 32
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | 22-Feb-21 A | 26-Feb-21 A | PROF6 AD | PROF6 AD | 8 | 0 | C | Budgeted Units |  | 8
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | PROF2 AD | PROF2 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF4 AD | PROF4 AD | 32 | 3 | C | Budgeted Units |  |  | 32
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF4 AD | PROF4 AD | 32 | 16 | C | Budgeted Units |  |  | 32
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF6 AD | PROF6 AD | 4 | 2 | C | Budgeted Units |  |  | 4
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF6 AD | PROF6 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 01-Apr-22 A | 31-Aug-22 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  |  | 80
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | TECH3 AD | TECH3 AD | 80 | 60 | C | Budgeted Units |  |  |  | 80
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | TECH3 AD | TECH3 AD | 40 | 2 | C | Budgeted Units |  |  | 40
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | 22-Feb-21 A | 26-Feb-21 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  | 80
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 AD | TECH3 AD | 160 | 80 | C | Budgeted Units |  |  | 101 | 59
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | CRAFT3 | CRAFT3 | 64 | 3 | C | Budgeted Units |  |  | 64
S347600 | Install IR Electronics Cooling Water Off Detector - Labor - C-AD Resources | 01-Apr-22 A | 31-Aug-22 A | CRAFT3 | CRAFT3 | 80 | 0 | C | Budgeted Units |  |  | 80
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | CRAFT3 | CRAFT3 | 24 | 18 | C | Budgeted Units |  |  |  | 24
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | CRAFT3 | CRAFT3 | 32 | 29 | C | Budgeted Units |  |  | 32
S346510 | Install Cryogenics Supply Structural Support - Labor - CA-D Resource(s) | 22-Feb-21 A | 26-Feb-21 A | CRAFT3 | CRAFT3 | 160 | 0 | C | Budgeted Units |  | 160
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | CRAFT3 | CRAFT3 | 80 | 40 | C | Budgeted Units |  |  | 50 | 30
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 01-Apr-22 A | 30-Sep-22 A | CRAFT3 | CRAFT3 | 200 | 0 | C | Budgeted Units |  |  | 200
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | CRAFT3 | CRAFT3 | 160 | 16 | C | Budgeted Units |  |  | 160
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 30-Aug-22 A | 2022-10-31 | CRAFT3 | CRAFT3 | 80 | 40 | C | Budgeted Units |  |  |  | 80
S346500 | Install Cryogenics Supply Structural Support - Labor - Physics Resource(s) | 22-Feb-21 A | 26-Feb-21 A | PROF4 PO M | PROF4 PO M | 80 | 0 | C | Budgeted Units |  | 80
S346500 | Install Cryogenics Supply Structural Support - Labor - Physics Resource(s) | 22-Feb-21 A | 26-Feb-21 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units |  | 80
S346500 | Install Cryogenics Supply Structural Support - Labor - Physics Resource(s) | 22-Feb-21 A | 26-Feb-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | PROF4 PO M | PROF4 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Budgeted Units |  |  |  | 16
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | TECH3 PO E | TECH3 PO E | 80 | 72 | C | Budgeted Units |  |  |  | 80
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | TECH3 PO M | TECH3 PO M | 40 | 36 | C | Budgeted Units |  |  |  | 40
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | PROF4 PO E | PROF4 PO E | 20 | 18 | C | Budgeted Units |  |  |  | 20
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | PROF4 PO M | PROF4 PO M | 20 | 18 | C | Budgeted Units |  |  |  | 20
S347100 | Install Electronics Racks Rackroom - Labor | 13-Sep-21 A | 27-Jun-22 A | PROF4 PO M | PROF4 PO M | 120 | 0 | C | Budgeted Units |  |  | 120
S347100 | Install Electronics Racks Rackroom - Labor | 13-Sep-21 A | 27-Jun-22 A | TECH3 PO E | TECH3 PO E | 280 | 0 | C | Budgeted Units |  |  | 280
S347100 | Install Electronics Racks Rackroom - Labor | 13-Sep-21 A | 27-Jun-22 A | TECH3 PO M | TECH3 PO M | 280 | 0 | C | Budgeted Units |  |  | 280
S347100 | Install Electronics Racks Rackroom - Labor | 13-Sep-21 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 48 | 0 | C | Budgeted Units |  |  | 48
S347100 | Install Electronics Racks Rackroom - Labor | 13-Sep-21 A | 27-Jun-22 A | PROF4 PO E | PROF4 PO E | 120 | 0 | C | Budgeted Units |  |  | 120
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | PROF4 PO M | PROF4 PO M | 120 | 120 | C | Budgeted Units |  |  |  | 120
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 720 | 720 | C | Budgeted Units |  |  |  | 720
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | TECH3 PO D | TECH3 PO D | 96 | 96 | C | Budgeted Units |  |  |  | 96
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 PO E | TECH3 PO E | 80 | 40 | C | Budgeted Units |  |  | 50 | 30
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 PO M | TECH3 PO M | 80 | 40 | C | Budgeted Units |  |  | 50 | 30
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | PROF4 PO E | PROF4 PO E | 80 | 40 | C | Budgeted Units |  |  | 50 | 30
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | PROF4 PO M | PROF4 PO M | 120 | 114 | C | Budgeted Units |  |  | 96 | 24
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO E | TECH3 PO E | 280 | 114 | C | Budgeted Units |  |  | 224 | 56
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO M | TECH3 PO M | 280 | 114 | C | Budgeted Units |  |  | 224 | 56
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO D | TECH3 PO D | 48 | 114 | C | Budgeted Units |  |  | 38 | 10
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | PROF4 PO E | PROF4 PO E | 120 | 114 | C | Budgeted Units |  |  | 96 | 24
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | TECH3 PO M | TECH3 PO M | 80 | 72 | C | Budgeted Units |  |  | 80
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | TECH3 PO D | TECH3 PO D | 16 | 14 | C | Budgeted Units |  |  | 16
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | PROF4 PO E | PROF4 PO E | 20 | 18 | C | Budgeted Units |  |  | 20
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 01-Apr-22 A | 30-Sep-22 A | TECH3 PO D | TECH3 PO D | 32 | 0 | C | Budgeted Units |  |  | 32
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 01-Apr-22 A | 30-Sep-22 A | PROF4 PO E | PROF4 PO E | 80 | 0 | C | Budgeted Units |  |  | 80
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 01-Apr-22 A | 30-Sep-22 A | TECH3 PO E | TECH3 PO E | 200 | 0 | C | Budgeted Units |  |  | 200
S1002159 | Install Detector Support Services Systems - Labor - Physics Resource(s) | 01-Apr-22 A | 30-Sep-22 A | TECH3 PO M | TECH3 PO M | 200 | 0 | C | Budgeted Units |  |  | 200
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF4 PO E | PROF4 PO E | 40 | 4 | C | Budgeted Units |  |  | 40
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF4 PO E | PROF4 PO E | 40 | 20 | C | Budgeted Units |  |  |  | 40
S346298 | Build North and South work platforms | 17-Aug-22 A | 2023-01-27 | TECH3 PO M | TECH3 PO M | 30 | 21 | C | Budgeted Units |  |  |  | 30
S346220 | Install AC power to Racks - Lower platforms | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Budgeted Units |  |  |  | 120
S346230 | Install AC power to Racks - Middle platforms | 2022-12-02 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Budgeted Units |  |  |  | 120
S346240 | Install AC power to Racks - Upper platforms | 2023-01-03 | 2023-01-31 | TECH3 PO E | TECH3 PO E | 480 | 480 | C | Budgeted Units |  |  |  | 480
S347610 | Off Carriage Water Lines & Flow Control - Sill & Labyrinth area | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S347620 | Off Carriage Water Lines & Flow Control - Chiller Platforms | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S347630 | Off Carriage Water - ECW to 'brass block' | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S347640 | Off Carriage Water - Brass block to chillers | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S347650 | Off Carriage Water - Chiller panels to cooling lines | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S347660 | Off Carriage Water - Bridge lines | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S347670 | Off Carriage Water - Bridges to on-carriage panels | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S347680 | Off Carriage Water - Carriage ECW to on-carriage panels | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S347820 | Install Rack Cooling water - Lower platforms | 2022-11-01 | 2022-12-01 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S347830 | Install Rack Cooling water - Middle platforms | 2022-12-02 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S347840 | Install Rack Cooling water - Upper platforms | 2023-01-03 | 2023-01-31 | TECH3 AD | TECH3 AD | 320 | 320 | C | Budgeted Units |  |  |  | 320
S345920 | Install Rack Protection systems - Lower platform | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S345930 | Install Rack Protection systems - Middle platform | 2022-12-02 | 2022-12-30 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S345940 | Install Rack Protection systems - Upper platform | 2023-01-03 | 2023-01-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Budgeted Units |  |  |  | 160
S346222 | Complete lighting and convenience power | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346222 | Complete lighting and convenience power | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346222 | Complete lighting and convenience power | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346224 | Complete wiring of chiller platform | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346224 | Complete wiring of chiller platform | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S346224 | Complete wiring of chiller platform | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346226 | Complete wiring of N & S Ploe Tip doors and motors | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346226 | Complete wiring of N & S Ploe Tip doors and motors | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346226 | Complete wiring of N & S Ploe Tip doors and motors | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346228 | Complete on-detector 24V-DC distribution system | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346228 | Complete on-detector 24V-DC distribution system | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S346228 | Complete on-detector 24V-DC distribution system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346235 | Complete rack interlock system (36 racks) | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346235 | Complete rack interlock system (36 racks) | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 160 | 160 | C | Budgeted Units |  |  |  | 160
S346235 | Complete rack interlock system (36 racks) | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346232 | Complete global interlock system | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346232 | Complete global interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346232 | Complete global interlock system | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346234 | Complete ODH, crash, sweeps - CAD PASS | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346234 | Complete ODH, crash, sweeps - CAD PASS | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S346234 | Complete ODH, crash, sweeps - CAD PASS | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346236 | Complete FAP and HSSP - Fire Alarm group | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346236 | Complete FAP and HSSP - Fire Alarm group | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S346236 | Complete FAP and HSSP - Fire Alarm group | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346238 | Complete network installation | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346238 | Complete network installation | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346238 | Complete network installation | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346245 | Complete VESDA north/south solenoid - piping (sEPD area) | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346245 | Complete VESDA north/south solenoid - piping (sEPD area) | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 120 | 120 | C | Budgeted Units |  |  |  | 120
S346245 | Complete VESDA north/south solenoid - piping (sEPD area) | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346242 | Complete ECW water leak detection | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346242 | Complete ECW water leak detection | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346242 | Complete ECW water leak detection | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346244 | Complete contactor boxes for interlock system | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346244 | Complete contactor boxes for interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 120 | 120 | C | Budgeted Units |  |  |  | 120
S346244 | Complete contactor boxes for interlock system | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346246 | Complete I/O terminations Rack 3B1 | 2022-11-01 | 2022-12-30 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S346246 | Complete I/O terminations Rack 3B1 | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 240 | 240 | C | Budgeted Units |  |  |  | 240
S346246 | Complete I/O terminations Rack 3B1 | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346248 | Test rack interlock system | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346248 | Test rack interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S346248 | Test rack interlock system | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346250 | Test global interlock system | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S346250 | Test global interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S346250 | Test global interlock system | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S356252 | Control system programming | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 120 | 120 | C | Budgeted Units |  |  |  | 120
S356252 | Control system programming | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S356252 | Control system programming | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S356255 | Control system HMI and usage testing | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 120 | 120 | C | Budgeted Units |  |  |  | 120
S356255 | Control system HMI and usage testing | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S356255 | Control system HMI and usage testing | 2022-11-01 | 2022-12-30 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | PROF2 AD | PROF2 AD | 20 | 10 | C | Budgeted Units |  |  | 13 | 7
POM02-13.02.05.03 Cradle Carriage Assembly/Installation |  | 01-Oct-19 A | 26-Jul-22 A |  |  | 4396 | 0 |  | Budgeted Units | 711 | 1327 | 2358
S347910 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - CA-D Resource(s) | 01-Oct-19 A | 05-Feb-20 A | PROF4 AD | PROF4 AD | 80 | 0 | C | Budgeted Units | 80
S347910 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - CA-D Resource(s) | 01-Oct-19 A | 05-Feb-20 A | TECH4 AD | TECH4 AD | 80 | 0 | C | Budgeted Units | 80
S348010 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s | 01-May-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 192 | 0 | C | Budgeted Units | 170 | 22
S348010 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s | 01-May-20 A | 30-Sep-20 A | TECH4 AD | TECH4 AD | 20 | 0 | C | Budgeted Units | 18 | 2
S348210 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - CA-D Resource(s) | 01-Oct-20 A | 29-Oct-20 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units |  | 40
S348210 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - CA-D Resource(s) | 01-Oct-20 A | 29-Oct-20 A | TECH4 AD | TECH4 AD | 20 | 0 | C | Budgeted Units |  | 20
S348310 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource | 26-Oct-20 A | 29-Oct-20 A | TECH4 AD | TECH4 AD | 8 | 0 | C | Budgeted Units |  | 8
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | 03-May-21 A | 30-Jun-21 A | PROF4 AD | PROF4 AD | 88 | 0 | C | Budgeted Units |  | 88
S348910 | Assemble HCal cradle onto base - Labor - CA-D Resource(s) | 01-Jun-21 A | 30-Jun-21 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units |  | 40
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 01-Mar-22 A | 12-Jul-22 A | PROF4 AD | PROF4 AD | 176 | 0 | C | Budgeted Units |  |  | 176
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 01-Mar-22 A | 26-Jul-22 A | PROF4 AD | PROF4 AD | 136 | 0 | C | Budgeted Units |  |  | 136
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | 03-May-21 A | 30-Jun-21 A | TECH3 AD | TECH3 AD | 72 | 0 | C | Budgeted Units |  | 72
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | 03-May-21 A | 30-Jun-21 A | TECH4 AD | TECH4 AD | 32 | 0 | C | Budgeted Units |  | 32
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 01-Mar-22 A | 12-Jul-22 A | TECH3 AD | TECH3 AD | 72 | 0 | C | Budgeted Units |  |  | 72
S349310 | Install platforms & access - Labor - CA-D Resource(s) | 01-Mar-22 A | 12-Jul-22 A | TECH4 AD | TECH4 AD | 80 | 0 | C | Budgeted Units |  |  | 80
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 01-Mar-22 A | 26-Jul-22 A | TECH4 AD | TECH4 AD | 80 | 0 | C | Budgeted Units |  |  | 80
S349100 | Install magnet mounting feet - Labor - CA-D Resource(s) | 06-Sep-21 A | 30-Sep-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S348310 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource | 26-Oct-20 A | 29-Oct-20 A | PROF4 AD | PROF4 AD | 12 | 0 | C | Budgeted Units |  | 12
S348410 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design&Safety Reviews-AD | 26-Oct-20 A | 29-Oct-20 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S348710 | Assemble base, carriage alignment and carriage roller supports - Labor - CA-D Resource(s) | 03-May-21 A | 30-Jun-21 A | CRAFT3 | CRAFT3 | 160 | 0 | C | Budgeted Units |  | 160
S348910 | Assemble HCal cradle onto base - Labor - CA-D Resource(s) | 01-Jun-21 A | 30-Jun-21 A | CRAFT3 | CRAFT3 | 64 | 0 | C | Budgeted Units |  | 64
S349510 | Install Pole Tips - Labor - CA-D Resource(s) | 01-Mar-22 A | 26-Jul-22 A | CRAFT3 | CRAFT3 | 120 | 0 | C | Budgeted Units |  |  | 120
S347900 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - Physics Resource(s) | 01-Oct-19 A | 05-Feb-20 A | PROF4 PO M | PROF4 PO M | 20 | 0 | C | Budgeted Units | 20
S347900 | Design Cradle Carriage Integration/Installation Tooling/Fixtures - Physics Resource(s) | 01-Oct-19 A | 05-Feb-20 A | TECH3 PO D | TECH3 PO D | 160 | 0 | C | Budgeted Units | 160
S348000 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - Physics Resourc | 01-May-20 A | 30-Sep-20 A | PROF4 PO M | PROF4 PO M | 48 | 0 | C | Budgeted Units | 42 | 6
S348000 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures - Labor - Physics Resourc | 01-May-20 A | 30-Sep-20 A | TECH3 PO D | TECH3 PO D | 160 | 0 | C | Budgeted Units | 141 | 19
S348200 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | 01-Oct-20 A | 29-Oct-20 A | PROF4 PO M | PROF4 PO M | 48 | 0 | C | Budgeted Units |  | 48
S348200 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | 01-Oct-20 A | 29-Oct-20 A | TECH3 PO D | TECH3 PO D | 30 | 0 | C | Budgeted Units |  | 30
S348300 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resou | 26-Oct-20 A | 29-Oct-20 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S348300 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resou | 26-Oct-20 A | 29-Oct-20 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S348400 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design&Safety Reviews-PO | 26-Oct-20 A | 29-Oct-20 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S348400 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design&Safety Reviews-PO | 26-Oct-20 A | 29-Oct-20 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S348700 | Assemble base, carriage alignment and carriage roller supports - Labor - Physics Resource(s) | 03-May-21 A | 30-Jun-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  | 16
S348700 | Assemble base, carriage alignment and carriage roller supports - Labor - Physics Resource(s) | 03-May-21 A | 30-Jun-21 A | TECH3 PO M | TECH3 PO M | 480 | 0 | C | Budgeted Units |  | 480
S348700 | Assemble base, carriage alignment and carriage roller supports - Labor - Physics Resource(s) | 03-May-21 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S348900 | Assemble HCal cradle onto base - Labor - Physics Resource(s) | 01-Jun-21 A | 30-Jun-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  | 16
S348900 | Assemble HCal cradle onto base - Labor - Physics Resource(s) | 01-Jun-21 A | 30-Jun-21 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units |  | 80
S348900 | Assemble HCal cradle onto base - Labor - Physics Resource(s) | 01-Jun-21 A | 30-Jun-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S349300 | Install platforms & access - Labor - Physics Resource(s) | 01-Mar-22 A | 12-Jul-22 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S349300 | Install platforms & access - Labor - Physics Resource(s) | 01-Mar-22 A | 12-Jul-22 A | TECH3 PO M | TECH3 PO M | 240 | 0 | C | Budgeted Units |  |  | 240
S349300 | Install platforms & access - Labor - Physics Resource(s) | 01-Mar-22 A | 12-Jul-22 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 01-Mar-22 A | 26-Jul-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 01-Mar-22 A | 26-Jul-22 A | TECH3 PO M | TECH3 PO M | 64 | 0 | C | Budgeted Units |  |  | 64
S349500 | Install Pole Tips - Labor - Physics Resource(s) | 01-Mar-22 A | 26-Jul-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | PROF4 PO M | PROF4 PO M | 10 | 0 | C | Budgeted Units |  |  | 10
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO M | TECH3 PO M | 160 | 0 | C | Budgeted Units |  |  | 160
S1002239 | Install magnet mounting feet - Labor - Physics Resource(s) | 06-Sep-21 A | 30-Sep-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S349670 | Install Upper Platform Joists and Components for Poletips and Cryoplatforms | 28-Apr-22 A | 12-Jul-22 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
S349680 | Install Mid-Level Platforms and West Extension Structures | 28-Apr-22 A | 18-Jul-22 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
S349690 | Install Upper Platform West Extension Structure | 20-Jun-22 A | 16-Jul-22 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
S349691 | Install Upper Platform Fall Protection | 20-Jun-22 A | 26-Jul-22 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
S349694 | Install Trapped West Lower Racks with Forklift | 01-Apr-22 A | 29-Apr-22 A | TECH3 AD | TECH3 AD | 40 | 0 | C | Budgeted Units |  |  | 40
S349695 | Install Upper Platform Cable Tray | 03-May-22 A | 25-May-22 A | TECH3 AD | TECH3 AD | 80 | 0 | C | Budgeted Units |  |  | 80
S349696 | Install West Side Cable Tray | 18-Apr-22 A | 25-Jul-22 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units |  |  | 80
POM02-13.02.05.04 Outer Hcal Installation |  | 01-Oct-19 A | 2022-12-06 |  |  | 6982 | 672 |  | Budgeted Units | 258 | 2320 | 3201 | 1203
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | 21-Jun-21 A | 29-Sep-21 A | TECH4 AD | TECH4 AD | 600 | 0 | C | Budgeted Units |  | 528 | 72
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 20-Dec-21 A | 28-Feb-22 A | TECH4 AD | TECH4 AD | 480 | 0 | C | Budgeted Units |  |  | 480
S350200 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource(s) | 15-Mar-21 A | 23-Mar-21 A | PROF2 AD | PROF2 AD | 4 | 0 | C | Budgeted Units |  | 4
S350200 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - CA-D Resource(s) | 15-Mar-21 A | 23-Mar-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  | 4
S350300 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - C | 15-Mar-21 A | 23-Mar-21 A | PROF2 AD | PROF2 AD | 4 | 0 | C | Budgeted Units |  | 4
S350300 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - C | 15-Mar-21 A | 23-Mar-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  | 4
S350600 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - CA-D Resource(s) | 29-Jun-21 A | 30-Jun-21 A | PROF2 AD | PROF2 AD | 8 | 0 | C | Budgeted Units |  | 8
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | 21-Jun-21 A | 29-Sep-21 A | PROF2 AD | PROF2 AD | 20 | 0 | C | Budgeted Units |  | 18 | 2
S350800 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - CA-D Resource(s) | 21-Jun-21 A | 29-Sep-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 7 | 1
S351000 | Transport Remainder of Outer Hcal Sectors to AH - Labor - CA-D Resource(s) | 20-Dec-21 A | 28-Feb-22 A | PROF2 AD | PROF2 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 20-Dec-21 A | 28-Feb-22 A | PROF2 AD | PROF2 AD | 20 | 0 | C | Budgeted Units |  |  | 20
S351200 | Install Remainder of Outer HCal Sectors - Labor - CA-D Resource(s) | 20-Dec-21 A | 28-Feb-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | 21-Feb-22 A | 28-Feb-22 A | TECH3 AD | TECH3 AD | 60 | 0 | C | Budgeted Units |  |  | 60
S351410 | Align/Survey Outer Hcal to Centerline - Labor - CA-D Resource(s) | 21-Feb-22 A | 28-Feb-22 A | CRAFT3 | CRAFT3 | 80 | 0 | C | Budgeted Units |  |  | 80
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | 29-Jun-21 A | 29-Jun-21 A | CRAFT3 | CRAFT3 | 256 | 0 | C | Budgeted Units |  | 256
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 21-Jun-21 A | 29-Sep-21 A | CRAFT3 | CRAFT3 | 600 | 0 | C | Budgeted Units |  | 600
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 16-Dec-21 A | 28-Feb-22 A | CRAFT3 | CRAFT3 | 256 | 0 | C | Budgeted Units |  |  | 256
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 16-Dec-21 A | 28-Feb-22 A | CRAFT3 | CRAFT3 | 480 | 0 | C | Budgeted Units |  |  | 480
S349900 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - Labor | 15-Nov-19 A | 30-Jan-20 A | PROF4 PO M | PROF4 PO M | 48 | 0 | C | Budgeted Units | 48
S349900 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - Labor | 15-Nov-19 A | 30-Jan-20 A | TECH3 PO D | TECH3 PO D | 48 | 0 | C | Budgeted Units | 48
S349900 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures - Labor | 15-Nov-19 A | 30-Jan-20 A | TECH3 PO M | TECH3 PO M | 48 | 0 | C | Budgeted Units | 48
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | 16-Sep-20 A | 26-Feb-21 A | PROF4 PO M | PROF4 PO M | 40 | 0 | C | Budgeted Units |  | 40
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | 16-Sep-20 A | 26-Feb-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | 16-Sep-20 A | 26-Feb-21 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  | 16
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | 21-Feb-22 A | 28-Feb-22 A | TECH3 PO D | TECH3 PO D | 4 | 0 | C | Budgeted Units |  |  | 4
S351400 | Align/Survey Outer Hcal to Centerline - Labor - Physics Resource(s) | 21-Feb-22 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | TECH3 PO M | TECH3 PO M | 80 | 11 | C | Budgeted Units |  |  | 80
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | TECH3 PO E | TECH3 PO E | 160 | 11 | C | Budgeted Units |  |  | 160
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | PROF4 PO E | PROF4 PO E | 80 | 11 | C | Budgeted Units |  |  | 80
S351800 | Review Outer HCal for Operational Readiness (ORR) | 01-Apr-22 A | 29-Apr-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S351800 | Review Outer HCal for Operational Readiness (ORR) | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S351800 | Review Outer HCal for Operational Readiness (ORR) | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S351800 | Review Outer HCal for Operational Readiness (ORR) | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S351900 | Address Action Items from Outer Hcal ORR | 01-Apr-22 A | 29-Apr-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S351900 | Address Action Items from Outer Hcal ORR | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S351900 | Address Action Items from Outer Hcal ORR | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S351900 | Address Action Items from Outer Hcal ORR | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S352000 | Commission Outer HCal - Labor | 01-Apr-22 A | 29-Apr-22 A | PROF4 PO M | PROF4 PO M | 32 | 0 | C | Budgeted Units |  |  | 14 | 18
S352000 | Commission Outer HCal - Labor | 01-Apr-22 A | 29-Apr-22 A | SCI3 PO | SCI3 PO | 160 | 0 | C | Budgeted Units |  |  | 72 | 88
S352000 | Commission Outer HCal - Labor | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO D | TECH3 PO D | 32 | 0 | C | Budgeted Units |  |  | 14 | 18
S352000 | Commission Outer HCal - Labor | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO M | TECH3 PO M | 320 | 0 | C | Budgeted Units |  |  | 144 | 176
S352000 | Commission Outer HCal - Labor | 01-Apr-22 A | 29-Apr-22 A | PROF4 PO E | PROF4 PO E | 160 | 0 | C | Budgeted Units |  |  | 72 | 88
S352000 | Commission Outer HCal - Labor | 01-Apr-22 A | 29-Apr-22 A | TECH3 PO E | TECH3 PO E | 320 | 0 | C | Budgeted Units |  |  | 144 | 176
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures FY20 | 01-Oct-19 A | 25-Nov-19 A | PROF4 PO M | PROF4 PO M | 30 | 0 | C | Budgeted Units | 30
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures FY20 | 01-Oct-19 A | 25-Nov-19 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units | 24
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures FY20 | 01-Oct-19 A | 25-Nov-19 A | TECH3 PO D | TECH3 PO D | 60 | 0 | C | Budgeted Units | 60
S350950 | Install Large Support Rings and Cross Braces | 22-Nov-21 A | 29-Dec-21 A | TECH3 PO M | TECH3 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S350950 | Install Large Support Rings and Cross Braces | 22-Nov-21 A | 29-Dec-21 A | PROF4 PO M | PROF4 PO M | 40 | 0 | C | Budgeted Units |  |  | 40
S1002279 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resource(s) | 15-Mar-21 A | 23-Mar-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S1002279 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resource(s) | 15-Mar-21 A | 23-Mar-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S1002279 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics Resource(s) | 15-Mar-21 A | 23-Mar-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S1002359 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - P | 15-Mar-21 A | 23-Mar-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S1002359 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - P | 15-Mar-21 A | 23-Mar-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S1002359 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews - P | 15-Mar-21 A | 23-Mar-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | 29-Jun-21 A | 29-Jun-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | 29-Jun-21 A | 29-Jun-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S1002439 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) - Labor - Physics Resource(s) | 29-Jun-21 A | 29-Jun-21 A | TECH3 PO M | TECH3 PO M | 128 | 0 | C | Budgeted Units |  | 128
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 21-Jun-21 A | 29-Sep-21 A | PROF4 PO M | PROF4 PO M | 64 | 0 | C | Budgeted Units |  | 64
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 21-Jun-21 A | 29-Sep-21 A | TECH3 PO D | TECH3 PO D | 48 | 0 | C | Budgeted Units |  | 48
S1002519 | Install Partial Outer HCal (Prior to SC Magnet Install) - Labor - Physics Resource(s) | 21-Jun-21 A | 29-Sep-21 A | TECH3 PO M | TECH3 PO M | 512 | 0 | C | Budgeted Units |  | 512
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 16-Dec-21 A | 28-Feb-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 16-Dec-21 A | 28-Feb-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S1002599 | Transport Remainder of Outer Hcal Sectors to AH - Labor - Physics Resource(s) | 16-Dec-21 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 128 | 0 | C | Budgeted Units |  |  | 128
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 16-Dec-21 A | 28-Feb-22 A | PROF4 PO M | PROF4 PO M | 64 | 0 | C | Budgeted Units |  |  | 64
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 16-Dec-21 A | 28-Feb-22 A | TECH3 PO D | TECH3 PO D | 64 | 0 | C | Budgeted Units |  |  | 64
S1002679 | Install Remainder of Outer HCal Sectors - Labor - Physics Resource(s) | 16-Dec-21 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 512 | 0 | C | Budgeted Units |  |  | 512
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S351720 | Install OHCal gas distribution panels and route lines | 2022-11-21 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
POM02-13.02.05.05 SC Magnet Installation |  | 15-Apr-20 A | 28-Apr-22 A |  |  | 2240 | 0 |  | Budgeted Units |  | 538 | 1702
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | 01-Nov-21 A | 29-Nov-21 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units |  |  | 40
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 01-Apr-22 A | 14-Apr-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | 04-Oct-21 A | 29-Oct-21 A | PROF4 AD | PROF4 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | 04-Oct-21 A | 29-Oct-21 A | PROF4 AD | PROF4 AD | 32 | 0 | C | Budgeted Units |  |  | 32
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | 01-Nov-21 A | 29-Nov-21 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units |  |  | 40
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 15-Apr-22 A | 28-Apr-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | 01-Nov-21 A | 29-Nov-21 A | TECH3 AD | TECH3 AD | 160 | 0 | C | Budgeted Units |  |  | 160
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 01-Apr-22 A | 14-Apr-22 A | TECH3 AD | TECH3 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 15-Apr-22 A | 28-Apr-22 A | TECH3 AD | TECH3 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | 01-Nov-21 A | 29-Nov-21 A | TECH3 AD | TECH3 AD | 320 | 0 | C | Budgeted Units |  |  | 320
S353710 | Prep SC Magnet for Run (Cryo) - Labor - CA-D Resource(s) | 01-Nov-21 A | 29-Nov-21 A | PROF6 AD | PROF6 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S353910 | Prep SC Magnet for Run (Electric) - Labor - CA-D Resource(s) | 01-Nov-21 A | 29-Nov-21 A | PROF6 AD | PROF6 AD | 16 | 0 | C | Budgeted Units |  |  | 16
S354110 | SC Magnet - Operational Readiness Review (ORR) - CA-D Resource(s) | 01-Apr-22 A | 14-Apr-22 A | PROF6 AD | PROF6 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S354210 | Address Action Items from SC Magnet ORR - CA-D Resource(s) | 15-Apr-22 A | 28-Apr-22 A | PROF6 AD | PROF6 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S352700 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification- CA-D | 22-Mar-21 A | 26-Mar-21 A | TECH4 AD | TECH4 AD | 4 | 0 | C | Budgeted Units |  | 4
S352300 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - CA-D Resource(s) | 15-Apr-20 A | 30-Sep-20 A | PROF4 AD | PROF4 AD | 40 | 0 | C | Budgeted Units |  | 40
S352400 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - CA-D Resource(s) | 17-Mar-21 A | 31-Aug-21 A | PROF4 AD | PROF4 AD | 10 | 0 | C | Budgeted Units |  | 10
S352600 | Prepare SC Magnet Integration/Installation Procedures - CA-D Resource(s) | 08-Feb-21 A | 23-Feb-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S352600 | Prepare SC Magnet Integration/Installation Procedures - CA-D Resource(s) | 08-Feb-21 A | 23-Feb-21 A | TECH4 AD | TECH4 AD | 80 | 0 | C | Budgeted Units |  | 80
S352700 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification- CA-D | 22-Mar-21 A | 26-Mar-21 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  | 4
S353510 | Align/Survey SC Magnet to Cradle - Labor - CA-D Resource(s) | 04-Oct-21 A | 29-Oct-21 A | TECH3 AD | TECH3 AD | 240 | 0 | C | Budgeted Units |  |  | 240
S353110 | Transport SC Magnet from 912 to AH - Labor - CA-D Resource(s) | 04-Oct-21 A | 29-Oct-21 A | CRAFT3 | CRAFT3 | 64 | 0 | C | Budgeted Units |  |  | 64
S353310 | Install SC Magnet on Cradle - Labor - CA-D Resource(s) | 04-Oct-21 A | 29-Oct-21 A | CRAFT3 | CRAFT3 | 64 | 0 | C | Budgeted Units |  |  | 64
S353510 | Align/Survey SC Magnet to Cradle - Labor - CA-D Resource(s) | 04-Oct-21 A | 29-Oct-21 A | CRAFT3 | CRAFT3 | 160 | 0 | C | Budgeted Units |  |  | 160
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 22-Mar-21 A | 26-Mar-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 22-Mar-21 A | 26-Mar-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 22-Mar-21 A | 26-Mar-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | 04-Oct-21 A | 29-Oct-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | 04-Oct-21 A | 29-Oct-21 A | TECH3 PO D | TECH3 PO D | 4 | 0 | C | Budgeted Units |  |  | 4
S353100 | Transport SC Magnet from 912 to AH - Labor - Physics Resource(s) | 04-Oct-21 A | 29-Oct-21 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units |  |  | 32
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | 04-Oct-21 A | 29-Oct-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | 04-Oct-21 A | 29-Oct-21 A | TECH3 PO D | TECH3 PO D | 2 | 0 | C | Budgeted Units |  |  | 2
S353300 | Install SC Magnet on Cradle - Labor - Physics Resource(s) | 04-Oct-21 A | 29-Oct-21 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units |  |  | 32
S353500 | Align/Survey SC Magnet to Cradle - Labor - Physics Resource(s) | 04-Oct-21 A | 29-Oct-21 A | TECH3 PO M | TECH3 PO M | 80 | 0 | C | Budgeted Units |  |  | 80
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | 01-Nov-21 A | 29-Nov-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | 01-Nov-21 A | 29-Nov-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S353700 | Prep SC Magnet for Run (Cryo) - Labor - Physics Resource(s) | 01-Nov-21 A | 29-Nov-21 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | 01-Nov-21 A | 29-Nov-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | 01-Nov-21 A | 29-Nov-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  |  | 16
S353900 | Prep SC Magnet for Run (Electric) - Labor - Physics Resource(s) | 01-Nov-21 A | 29-Nov-21 A | TECH3 PO E | TECH3 PO E | 160 | 0 | C | Budgeted Units |  |  | 160
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 01-Apr-22 A | 14-Apr-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 01-Apr-22 A | 14-Apr-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S354100 | SC Magnet - Operational Readiness Review (ORR) - Physics Resource(s) | 01-Apr-22 A | 14-Apr-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 15-Apr-22 A | 28-Apr-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 15-Apr-22 A | 28-Apr-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S354200 | Address Action Items from SC Magnet ORR - Physics Resource(s) | 15-Apr-22 A | 28-Apr-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1003399 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | 15-Apr-20 A | 30-Sep-20 A | PROF4 PO M | PROF4 PO M | 120 | 0 | C | Budgeted Units |  | 120
S1003399 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | 15-Apr-20 A | 30-Sep-20 A | TECH3 PO M | TECH3 PO M | 24 | 0 | C | Budgeted Units |  | 24
S1003399 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures - Physics Resource(s) | 15-Apr-20 A | 30-Sep-20 A | TECH3 PO D | TECH3 PO D | 120 | 0 | C | Budgeted Units |  | 120
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | 17-Mar-21 A | 31-Aug-21 A | PROF4 PO M | PROF4 PO M | 30 | 0 | C | Budgeted Units |  | 30
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | 17-Mar-21 A | 31-Aug-21 A | TECH3 PO M | TECH3 PO M | 10 | 0 | C | Budgeted Units |  | 10
S1003479 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures - Labor - Physics Resource(s) | 17-Mar-21 A | 31-Aug-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units |  | 10
S1003559 | Prepare SC Magnet Integration/Installation Procedures - Physics Resource(s) | 08-Feb-21 A | 23-Feb-21 A | PROF4 PO M | PROF4 PO M | 20 | 0 | C | Budgeted Units |  | 20
S1003559 | Prepare SC Magnet Integration/Installation Procedures - Physics Resource(s) | 08-Feb-21 A | 23-Feb-21 A | TECH3 PO D | TECH3 PO D | 10 | 0 | C | Budgeted Units |  | 10
S1003639 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics | 15-Dec-20 A | 27-Jan-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S1003639 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics | 15-Dec-20 A | 27-Jan-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S1003639 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification - Physics | 15-Dec-20 A | 27-Jan-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
POM02-13.02.05.06 Inner Hcal Installation |  | 01-Oct-19 A | 2022-12-06 |  |  | 7954 | 960 |  | Budgeted Units | 180 | 740 | 6058 | 976
S356000 | Transport & Install IHCal Barrel - Labor - CA-D | 01-Jun-22 A | 24-Jun-22 A | TECH4 AD | TECH4 AD | 120 | 0 | C | Budgeted Units |  |  | 120
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - & dismantle Labor - CA-D Resource(s) | 01-Jun-22 A | 24-Jun-22 A | TECH4 AD | TECH4 AD | 60 | 0 | C | Budgeted Units |  |  | 60
S355200 | Transport assembled Inner HCal Sectors to AH - Labor - CA-D Resource(s) | 08-Feb-21 A | 24-Feb-21 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  | 8
S356000 | Transport & Install IHCal Barrel - Labor - CA-D | 01-Jun-22 A | 24-Jun-22 A | PROF4 AD | PROF4 AD | 4 | 0 | C | Budgeted Units |  |  | 4
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - & dismantle Labor - CA-D Resource(s) | 01-Jun-22 A | 24-Jun-22 A | TECH3 AD | TECH3 AD | 60 | 0 | C | Budgeted Units |  |  | 60
S356410 | Align/Survey Inner HCal to SC Magnet Centerline - & dismantle Labor - CA-D Resource(s) | 01-Jun-22 A | 24-Jun-22 A | CRAFT3 | CRAFT3 | 80 | 0 | C | Budgeted Units |  |  | 80
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | 08-Feb-21 A | 24-Feb-21 A | CRAFT3 | CRAFT3 | 160 | 0 | C | Budgeted Units |  | 160
S354500 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - Labor | 06-Sep-21 A | 30-Nov-21 A | PROF4 PO M | PROF4 PO M | 120 | 0 | C | Budgeted Units |  |  | 120
S354500 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures - Labor | 06-Sep-21 A | 30-Nov-21 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units |  |  | 40
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | 08-Feb-21 A | 28-Jul-21 A | PROF4 PO M | PROF4 PO M | 80 | 0 | C | Budgeted Units |  | 80
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | 08-Feb-21 A | 28-Jul-21 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units |  | 40
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 15-Jun-21 A | 29-Oct-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 15-Jun-21 A | 29-Oct-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 15-Jun-21 A | 29-Oct-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 15-Nov-21 A | 31-Dec-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 15-Nov-21 A | 31-Dec-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 15-Nov-21 A | 31-Dec-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S355600 | Install Stanchions & south slider beam - Labor | 01-Apr-22 A | 27-May-22 A | PROF4 PO M | PROF4 PO M | 64 | 0 | C | Budgeted Units |  |  | 64
S355600 | Install Stanchions & south slider beam - Labor | 01-Apr-22 A | 27-May-22 A | TECH3 PO D | TECH3 PO D | 64 | 0 | C | Budgeted Units |  |  | 64
S355600 | Install Stanchions & south slider beam - Labor | 01-Apr-22 A | 27-May-22 A | TECH3 PO M | TECH3 PO M | 512 | 0 | C | Budgeted Units |  |  | 512
S356400 | Align/Survey Inner HCal to SC Magnet Centerline & dismantle - Labor - Physics Resource(s) | 01-Jun-22 A | 24-Jun-22 A | TECH3 PO D | TECH3 PO D | 4 | 0 | C | Budgeted Units |  |  | 4
S356400 | Align/Survey Inner HCal to SC Magnet Centerline & dismantle - Labor - Physics Resource(s) | 01-Jun-22 A | 24-Jun-22 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Budgeted Units |  |  |  | 160
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | PROF4 PO E | PROF4 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S356800 | Inner HCal - Operational Readiness Review (ORR) | 01-Jun-22 A | 27-Jun-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S356800 | Inner HCal - Operational Readiness Review (ORR) | 01-Jun-22 A | 27-Jun-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S356800 | Inner HCal - Operational Readiness Review (ORR) | 01-Jun-22 A | 27-Jun-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S356800 | Inner HCal - Operational Readiness Review (ORR) | 01-Jun-22 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S356800 | Inner HCal - Operational Readiness Review (ORR) | 01-Jun-22 A | 27-Jun-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S356900 | Address Action Items from Inner Hcal ORR | 01-Jun-22 A | 27-Jun-22 A | PROF4 PO E | PROF4 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S356900 | Address Action Items from Inner Hcal ORR | 01-Jun-22 A | 27-Jun-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S356900 | Address Action Items from Inner Hcal ORR | 01-Jun-22 A | 27-Jun-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  | 8
S356900 | Address Action Items from Inner Hcal ORR | 01-Jun-22 A | 27-Jun-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S356900 | Address Action Items from Inner Hcal ORR | 01-Jun-22 A | 27-Jun-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S357000 | Commission Inner HCal (labor - if instrumented) - Labor | 01-Jun-22 A | 27-Jun-22 A | SCI3 PO | SCI3 PO | 80 | 0 | C | Budgeted Units |  |  | 64 | 16
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures FY20 | 01-Oct-19 A | 29-Oct-21 A | PROF4 PO M | PROF4 PO M | 60 | 0 | C | Budgeted Units | 60
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures FY20 | 01-Oct-19 A | 29-Oct-21 A | TECH3 PO D | TECH3 PO D | 120 | 0 | C | Budgeted Units | 120
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | 08-Feb-21 A | 24-Feb-21 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  | 16
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | 08-Feb-21 A | 24-Feb-21 A | TECH3 PO D | TECH3 PO D | 16 | 0 | C | Budgeted Units |  | 16
S1003719 | Transport assembled Inner HCal Sectors to AH - Labor - Physics Resource(s) | 08-Feb-21 A | 24-Feb-21 A | TECH3 PO M | TECH3 PO M | 120 | 0 | C | Budgeted Units |  | 120
S1003799 | Transport & Install IHCal Barrel - Labor - Phys | 01-Jun-22 A | 24-Jun-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1003799 | Transport & Install IHCal Barrel - Labor - Phys | 01-Jun-22 A | 24-Jun-22 A | TECH3 PO D | TECH3 PO D | 2 | 0 | C | Budgeted Units |  |  | 2
S1003799 | Transport & Install IHCal Barrel - Labor - Phys | 01-Jun-22 A | 24-Jun-22 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units |  |  | 32
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S356720 | Install IHCal gas distribution panels and route lines | 2022-11-21 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S355310 | Add scintillating tiles first 8 IHCal sectors | 23-Aug-21 A | 29-Oct-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  | 50
S355310 | Add scintillating tiles first 8 IHCal sectors | 23-Aug-21 A | 29-Oct-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  | 250
S355312 | Add electronics first 8 IHCal sectors | 06-Sep-21 A | 31-Dec-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355312 | Add electronics first 8 IHCal sectors | 06-Sep-21 A | 31-Dec-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355316 | Cosmic test first 8 IHCal sectors | 06-Sep-21 A | 31-Dec-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355316 | Cosmic test first 8 IHCal sectors | 06-Sep-21 A | 31-Dec-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355314 | LED test/Light tight test first 8 IHCal sectors | 06-Sep-21 A | 31-Dec-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355314 | LED test/Light tight test first 8 IHCal sectors | 06-Sep-21 A | 31-Dec-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355318 | Move first 8 IHCal sectors to assembly area | 06-Sep-21 A | 29-Oct-21 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S355320 | Add scintillating tiles second 8 IHCal sectors | 11-Oct-21 A | 29-Oct-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355320 | Add scintillating tiles second 8 IHCal sectors | 11-Oct-21 A | 29-Oct-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355322 | Add electronics second 8 IHCal sectors | 11-Oct-21 A | 31-Dec-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355322 | Add electronics second 8 IHCal sectors | 11-Oct-21 A | 31-Dec-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355326 | Cosmic test second 8 IHCal sectors | 13-Dec-21 A | 30-Dec-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355326 | Cosmic test second 8 IHCal sectors | 13-Dec-21 A | 30-Dec-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355324 | LED test/Light tight test second 8 IHCal sectors | 20-Dec-21 A | 31-Dec-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355324 | LED test/Light tight test second 8 IHCal sectors | 20-Dec-21 A | 31-Dec-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355328 | Move second 8 IHCal sectors to assembly area | 11-Oct-21 A | 29-Oct-21 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S355330 | Add scintillating tiles third 8 IHCal sectors | 11-Oct-21 A | 29-Oct-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355330 | Add scintillating tiles third 8 IHCal sectors | 11-Oct-21 A | 29-Oct-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355332 | Add electronics third 8 IHCal sectors | 11-Oct-21 A | 31-Dec-21 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355332 | Add electronics third 8 IHCal sectors | 11-Oct-21 A | 31-Dec-21 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355336 | Cosmic test third 8 IHCal sectors | 20-Dec-21 A | 31-Jan-22 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355336 | Cosmic test third 8 IHCal sectors | 20-Dec-21 A | 31-Jan-22 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355334 | LED test/Light tight test third 8 IHCal sectors | 13-Dec-21 A | 31-Jan-22 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355334 | LED test/Light tight test third 8 IHCal sectors | 13-Dec-21 A | 31-Jan-22 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355338 | Move third 8 IHCal sectors to assembly area | 13-Dec-21 A | 31-Dec-21 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S355340 | Add scintillating tiles fourth 8 IHCal sectors | 23-Nov-21 A | 24-Jan-22 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355340 | Add scintillating tiles fourth 8 IHCal sectors | 23-Nov-21 A | 24-Jan-22 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355342 | Add electronics fourth 8 IHCal sectors | 20-Dec-21 A | 27-Jan-22 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355342 | Add electronics fourth 8 IHCal sectors | 20-Dec-21 A | 27-Jan-22 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355346 | Cosmic test fourth 8 IHCal sectors | 20-Dec-21 A | 31-Jan-22 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355346 | Cosmic test fourth 8 IHCal sectors | 20-Dec-21 A | 31-Jan-22 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355344 | LED test/Light tight test fourth 8 IHCal sectors | 20-Dec-21 A | 31-Jan-22 A | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 50 | 0 | C | Budgeted Units |  |  | 50
S355344 | LED test/Light tight test fourth 8 IHCal sectors | 20-Dec-21 A | 31-Jan-22 A | STUDENT GRAD Other - Unpaid | STUDENT GRAD Other - Unpaid | 250 | 0 | C | Budgeted Units |  |  | 250
S355348 | Move fourth 8 IHCal sectors to assembly area | 06-Dec-21 A | 29-Dec-21 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S355350 | Assemble first 8 IHCal sectors into barrel on fixture | 21-Feb-22 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S355352 | Assemble second 8 IHCal sectors into barrel on fixture | 21-Feb-22 A | 28-Feb-22 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units |  |  | 32
S355356 | Assemble fourth/last 8 IHCal sectors into barrel on fixture | 01-Mar-22 A | 31-Mar-22 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units |  |  | 32
S355354 | Assemble third 8 IHCal sectors into barrel on fixture | 01-Mar-22 A | 31-Mar-22 A | TECH3 PO M | TECH3 PO M | 32 | 0 | C | Budgeted Units |  |  | 32
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
POM02-13.02.05.07 EMCal Installation |  | 11-Mar-20 A | 2023-02-10 |  |  | 5420 | 4034 |  | Budgeted Units |  | 484 | 832 | 4104
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH4 AD | TECH4 AD | 60 | 30 | C | Budgeted Units |  |  |  | 60
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 01-Jul-22 A | 2022-12-09 | PROF4 AD | PROF4 AD | 8 | 4 | C | Budgeted Units |  |  | 8
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH3 AD | TECH3 AD | 60 | 30 | C | Budgeted Units |  |  |  | 60
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | CRAFT3 | CRAFT3 | 320 | 320 | C | Budgeted Units |  |  |  | 320
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | CRAFT3 | CRAFT3 | 80 | 40 | C | Budgeted Units |  |  |  | 80
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 01-Jul-22 A | 2022-12-09 | CRAFT3 | CRAFT3 | 120 | 53 | C | Budgeted Units |  |  | 120
S357400 | Design EMCal Integration/Installation Tooling/Fixtures FY21 | 11-Mar-20 A | 31-Dec-20 A | PROF4 PO M | PROF4 PO M | 26 | 0 | C | Budgeted Units |  | 26
S357400 | Design EMCal Integration/Installation Tooling/Fixtures FY21 | 11-Mar-20 A | 31-Dec-20 A | TECH3 PO M | TECH3 PO M | 21 | 0 | C | Budgeted Units |  | 21
S357400 | Design EMCal Integration/Installation Tooling/Fixtures FY21 | 11-Mar-20 A | 31-Dec-20 A | TECH3 PO D | TECH3 PO D | 53 | 0 | C | Budgeted Units |  | 53
S357500 | Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | 01-Feb-21 A | 29-Oct-21 A | PROF4 PO M | PROF4 PO M | 120 | 0 | C | Budgeted Units |  | 120
S357500 | Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | 01-Feb-21 A | 29-Oct-21 A | TECH3 PO M | TECH3 PO M | 48 | 0 | C | Budgeted Units |  | 48
S357500 | Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures - Labor | 01-Feb-21 A | 29-Oct-21 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units |  | 40
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | 01-Feb-21 A | 29-Oct-21 A | PROF4 PO M | PROF4 PO M | 80 | 0 | C | Budgeted Units |  | 80
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | 01-Feb-21 A | 29-Oct-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S357700 | Prepare EMCal Integration/Installation Tooling/Fixtures Procedures | 01-Feb-21 A | 29-Oct-21 A | TECH3 PO D | TECH3 PO D | 40 | 0 | C | Budgeted Units |  | 40
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 22-Mar-21 A | 26-Mar-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 22-Mar-21 A | 26-Mar-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 22-Mar-21 A | 26-Mar-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 22-Mar-21 A | 26-Mar-21 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  | 8
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 22-Mar-21 A | 26-Mar-21 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 22-Mar-21 A | 26-Mar-21 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  | 8
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | PROF4 PO M | PROF4 PO M | 64 | 32 | C | Budgeted Units |  |  | 64
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | TECH3 PO D | TECH3 PO D | 64 | 32 | C | Budgeted Units |  |  | 64
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | TECH3 PO M | TECH3 PO M | 512 | 256 | C | Budgeted Units |  |  | 512
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH3 PO M | TECH3 PO M | 20 | 10 | C | Budgeted Units |  |  |  | 20
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Budgeted Units |  |  |  | 160
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO M | TECH3 PO M | 64 | 64 | C | Budgeted Units |  |  |  | 64
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | PROF4 PO M | PROF4 PO M | 32 | 32 | C | Budgeted Units |  |  |  | 32
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO D | TECH3 PO D | 32 | 32 | C | Budgeted Units |  |  |  | 32
S359000 | EMCal - Operational Readiness Review (ORR) | 01-Aug-22 A | 31-Aug-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  |  | 8
S359000 | EMCal - Operational Readiness Review (ORR) | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  |  | 8
S359000 | EMCal - Operational Readiness Review (ORR) | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  |  | 8
S359000 | EMCal - Operational Readiness Review (ORR) | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  |  | 8
S359100 | Address Action Items from EMCal ORR | 01-Aug-22 A | 31-Aug-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  |  | 8
S359100 | Address Action Items from EMCal ORR | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO E | TECH3 PO E | 8 | 0 | C | Budgeted Units |  |  |  | 8
S359100 | Address Action Items from EMCal ORR | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  |  | 8
S359100 | Address Action Items from EMCal ORR | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  |  |  | 8
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | SCI3 PO | SCI3 PO | 400 | 200 | C | Budgeted Units |  |  |  | 400
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | PROF4 PO E | PROF4 PO E | 40 | 20 | C | Budgeted Units |  |  |  | 40
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO E | TECH3 PO E | 40 | 20 | C | Budgeted Units |  |  |  | 40
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | PROF4 PO M | PROF4 PO M | 40 | 20 | C | Budgeted Units |  |  |  | 40
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO D | TECH3 PO D | 40 | 20 | C | Budgeted Units |  |  |  | 40
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO M | TECH3 PO M | 40 | 20 | C | Budgeted Units |  |  |  | 40
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 01-Jul-22 A | 2022-12-09 | TECH3 PO M | TECH3 PO M | 64 | 28 | C | Budgeted Units |  |  | 64
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 2022-11-01 | 2022-11-07 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S359402 | Install EMCal cooling panels and route lines | 2022-11-01 | 2022-11-02 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S359402 | Install EMCal cooling panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359402 | Install EMCal cooling panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359402 | Install EMCal cooling panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S359404 | Install EMCal gas distribution panels and route lines | 2022-11-01 | 2022-11-02 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S359404 | Install EMCal gas distribution panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359404 | Install EMCal gas distribution panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359404 | Install EMCal gas distribution panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | SCI3 | SCI3-1 | 160 | 160 | C | Budgeted Units |  |  |  | 160
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | SCI3 | SCI3-1 | 160 | 160 | C | Budgeted Units |  |  |  | 160
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | SCI4 PO | SCI 4 PO | 0 | 0 | C | Budgeted Units
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S359520 | Install TPot Installation fixtures and test | 2022-10-03 | 2022-10-04 | PROF3 PO M | PROF3 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S359520 | Install TPot Installation fixtures and test | 2022-10-03 | 2022-10-04 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359520 | Install TPot Installation fixtures and test | 2022-10-03 | 2022-10-04 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359520 | Install TPot Installation fixtures and test | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S359530 | Install TPot support system | 2022-12-02 | 2022-12-02 | PROF3 PO M | PROF3 PO M | 4 | 4 | C | Budgeted Units |  |  |  | 4
S359530 | Install TPot support system | 2022-12-02 | 2022-12-02 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359530 | Install TPot support system | 2022-12-02 | 2022-12-02 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359530 | Install TPot support system | 2022-12-02 | 2022-12-02 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | PROF3 PO M | PROF3 PO M | 4 | 4 | C | Budgeted Units |  |  |  | 4
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | PROF3 PO M | PROF3 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Budgeted Units |  |  |  | 16
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S359580 | Install TPot cooling panels and route lines | 2022-10-03 | 2022-10-04 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S359580 | Install TPot cooling panels and route lines | 2022-10-03 | 2022-10-04 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359580 | Install TPot cooling panels and route lines | 2022-10-03 | 2022-10-04 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S359580 | Install TPot cooling panels and route lines | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S359590 | Install TPot gas distribution panels and route lines | 2022-10-03 | 2022-10-04 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S359590 | Install TPot gas distribution panels and route lines | 2022-10-03 | 2022-10-04 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359590 | Install TPot gas distribution panels and route lines | 2022-10-03 | 2022-10-04 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S359590 | Install TPot gas distribution panels and route lines | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Budgeted Units |  |  |  | 16
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Budgeted Units |  |  |  | 16
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 2022-11-01 | 2022-11-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Budgeted Units |  |  |  | 320
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 320 | 320 | C | Budgeted Units |  |  |  | 320
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Budgeted Units |  |  |  | 320
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 320 | 320 | C | Budgeted Units |  |  |  | 320
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Budgeted Units |  |  |  | 8
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Budgeted Units |  |  |  | 8
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | TECH3 AD | TECH3 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Budgeted Units |  |  |  | 8
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Budgeted Units |  |  |  | 8
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Budgeted Units |  |  |  | 48
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Budgeted Units |  |  |  | 24
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Budgeted Units |  |  |  | 48
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Budgeted Units |  |  |  | 24
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Budgeted Units |  |  |  | 48
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Budgeted Units |  |  |  | 24
POM02-13.02.05.08 TPC Installation |  | 02-Dec-19 A | 2023-03-06 |  |  | 3374 | 3010 |  | Budgeted Units | 202 | 68 | 104 | 3000
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 2022-12-13 | 2022-12-19 | PROF4 AD | PROF4 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | TECH4 AD | TECH4 AD | 60 | 60 | C | Budgeted Units |  |  |  | 60
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 2022-12-29 | 2023-01-12 | PROF2 AD | PROF2 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | TECH3 AD | TECH3 AD | 60 | 60 | C | Budgeted Units |  |  |  | 60
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | CRAFT3 | CRAFT3 | 240 | 240 | C | Budgeted Units |  |  |  | 240
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | CRAFT3 | CRAFT3 | 80 | 80 | C | Budgeted Units |  |  |  | 80
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | CRAFT3 | CRAFT3 | 36 | 36 | C | Budgeted Units |  |  |  | 36
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 03-Jan-22 A | 2022-10-20 | PROF4 PO M | PROF4 PO M | 60 | 6 | C | Budgeted Units |  |  | 60
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 03-Jan-22 A | 2022-10-20 | TECH3 PO D | TECH3 PO D | 20 | 2 | C | Budgeted Units |  |  | 20
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 10-Feb-21 A | 31-Jan-22 A | PROF4 PO M | PROF4 PO M | 40 | 0 | C | Budgeted Units |  | 40
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 10-Feb-21 A | 31-Jan-22 A | TECH3 PO M | TECH3 PO M | 8 | 0 | C | Budgeted Units |  | 8
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | 10-Feb-21 A | 31-Jan-22 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  | 20
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | PROF4 PO M | PROF4 PO M | 8 | 1 | C | Budgeted Units |  |  | 8
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | TECH3 PO M | TECH3 PO M | 8 | 1 | C | Budgeted Units |  |  | 8
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | TECH3 PO D | TECH3 PO D | 8 | 1 | C | Budgeted Units |  |  | 8
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Budgeted Units |  |  |  | 8
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Budgeted Units |  |  |  | 4
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Budgeted Units |  |  |  | 16
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-01-13 | 2023-01-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Budgeted Units |  |  |  | 120
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Budgeted Units |  |  |  | 60
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Budgeted Units |  |  |  | 24
S360600 | Open SC Magnet Pole Tip Doors | 2022-12-20 | 2022-12-20 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Budgeted Units |  |  |  | 4
S360600 | Open SC Magnet Pole Tip Doors | 2022-12-20 | 2022-12-20 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | 02-Dec-19 A | 30-Nov-21 A | PROF4 PO M | PROF4 PO M | 77 | 0 | C | Budgeted Units | 77
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | 02-Dec-19 A | 30-Nov-21 A | TECH3 PO M | TECH3 PO M | 48 | 0 | C | Budgeted Units | 48
S359605 | Design TPC Integration/Installation Tooling/Fixtures FY21 Split | 02-Dec-19 A | 30-Nov-21 A | TECH3 PO D | TECH3 PO D | 77 | 0 | C | Budgeted Units | 77
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Budgeted Units |  |  |  | 4
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Budgeted Units |  |  |  | 16
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Budgeted Units |  |  |  | 60
S360620 | Install TPC Installation fixtures and test | 2022-12-21 | 2022-12-21 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S360620 | Install TPC Installation fixtures and test | 2022-12-21 | 2022-12-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S360620 | Install TPC Installation fixtures and test | 2022-12-21 | 2022-12-21 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | SCI3 | SCI3-1 | 16 | 16 | C | Budgeted Units |  |  |  | 16
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Budgeted Units |  |  |  | 160
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S361440 | Install TPC cooling panels and route lines | 2022-12-21 | 2022-12-22 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S361440 | Install TPC cooling panels and route lines | 2022-12-21 | 2022-12-22 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S361440 | Install TPC cooling panels and route lines | 2022-12-21 | 2022-12-22 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S361460 | Install TPC gas distribution panels and route lines | 2022-12-21 | 2022-12-22 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S361460 | Install TPC gas distribution panels and route lines | 2022-12-21 | 2022-12-22 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S361460 | Install TPC gas distribution panels and route lines | 2022-12-21 | 2022-12-22 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | SCI3 | SCI3-1 | 12 | 12 | C | Budgeted Units |  |  |  | 12
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | TECH3 PO E | TECH3 PO E | 24 | 24 | C | Budgeted Units |  |  |  | 24
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Budgeted Units |  |  |  | 160
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Budgeted Units |  |  |  | 160
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S361950 | Erect 1008 IR Shield Wall | 2023-02-28 | 2023-03-06 | CRAFT3 | CRAFT3 | 0 | 0 | C | Budgeted Units
S361950 | Erect 1008 IR Shield Wall | 2023-02-28 | 2023-03-06 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S361950 | Erect 1008 IR Shield Wall | 2023-02-28 | 2023-03-06 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
POM02-13.02.05.09 INTT Installation |  | 01-Oct-19 A | 2023-03-10 |  |  | 2662 | 2492 |  | Budgeted Units |  | 90 | 80 | 2492
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 AD | TECH3 AD | 60 | 60 | C | Budgeted Units |  |  |  | 60
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | CRAFT3 | CRAFT3 | 240 | 240 | C | Budgeted Units |  |  |  | 240
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 01-Oct-19 A | 31-Jan-22 A | PROF4 PO M | PROF4 PO M | 30 | 0 | C | Budgeted Units |  | 30
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 01-Oct-19 A | 31-Jan-22 A | TECH3 PO D | TECH3 PO D | 60 | 0 | C | Budgeted Units |  | 60
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | 14-Feb-22 A | 30-Sep-22 A | PROF4 PO M | PROF4 PO M | 60 | 0 | C | Budgeted Units |  |  | 60
S362100 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures - Labor | 14-Feb-22 A | 30-Sep-22 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  |  | 20
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 2022-10-03 | 2022-10-17 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 2022-10-03 | 2022-10-17 | TECH3 PO D | TECH3 PO D | 20 | 20 | C | Budgeted Units |  |  |  | 20
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Budgeted Units |  |  |  | 8
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Budgeted Units |  |  |  | 60
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Budgeted Units |  |  |  | 60
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Budgeted Units |  |  |  | 120
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Budgeted Units |  |  |  | 120
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Budgeted Units |  |  |  | 24
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Budgeted Units |  |  |  | 24
S364000 | Commission INTT - Labor | 2023-03-10 | 2023-03-10 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S362920 | Install INTT Installation fixtures and test | 2023-02-06 | 2023-02-07 | PROF3 PO M | PROF3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S362920 | Install INTT Installation fixtures and test | 2023-02-06 | 2023-02-07 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S362920 | Install INTT Installation fixtures and test | 2023-02-06 | 2023-02-07 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S363120 | Install Beampipe | 2023-02-21 | 2023-02-21 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S363120 | Install Beampipe | 2023-02-21 | 2023-02-21 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363120 | Install Beampipe | 2023-02-21 | 2023-02-21 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363140 | Install Beampipe vacuum system | 2023-02-22 | 2023-02-22 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S363140 | Install Beampipe vacuum system | 2023-02-22 | 2023-02-22 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363140 | Install Beampipe vacuum system | 2023-02-22 | 2023-02-22 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363160 | Pump down beampipe | 2023-02-23 | 2023-02-23 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S363160 | Pump down beampipe | 2023-02-23 | 2023-02-23 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363160 | Pump down beampipe | 2023-02-23 | 2023-02-23 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363180 | Perform Beampipe Bakeout | 2023-02-24 | 2023-03-02 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S363180 | Perform Beampipe Bakeout | 2023-02-24 | 2023-03-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Budgeted Units |  |  |  | 80
S363180 | Perform Beampipe Bakeout | 2023-02-24 | 2023-03-02 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363520 | Install beampipe permanent support | 2023-03-03 | 2023-03-03 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S363520 | Install beampipe permanent support | 2023-03-03 | 2023-03-03 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363520 | Install beampipe permanent support | 2023-03-03 | 2023-03-03 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363540 | Remove beampipe Temporary Support | 2023-03-06 | 2023-03-06 | PROF3 PO M | PROF3 PO M | 0 | 0 | C | Budgeted Units
S363540 | Remove beampipe Temporary Support | 2023-03-06 | 2023-03-06 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363540 | Remove beampipe Temporary Support | 2023-03-06 | 2023-03-06 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363740 | Install INTT cooling panels and route lines | 2023-03-07 | 2023-03-07 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S363740 | Install INTT cooling panels and route lines | 2023-03-07 | 2023-03-07 | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S363740 | Install INTT cooling panels and route lines | 2023-03-07 | 2023-03-07 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363760 | Install INTT gas distribution panels and route lines | 2023-03-07 | 2023-03-07 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S363760 | Install INTT gas distribution panels and route lines | 2023-03-07 | 2023-03-07 | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S363760 | Install INTT gas distribution panels and route lines | 2023-03-07 | 2023-03-07 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
POM02-13.02.05.10 MVTX Installation |  | 01-Oct-19 A | 2023-03-22 |  |  | 3612 | 3382 |  | Budgeted Units |  | 140 | 124 | 3348
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-17 | 2023-03-20 | TECH3 AD | TECH3 AD | 40 | 40 | C | Budgeted Units |  |  |  | 40
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | CRAFT3 | CRAFT3 | 160 | 160 | C | Budgeted Units |  |  |  | 160
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-17 | 2023-03-17 | CRAFT3 | CRAFT3 | 0 | 0 | C | Budgeted Units
S365700 | Install FELIX | 2023-03-10 | 2023-03-13 | PROF3 IO E | PROF3 IO E | 16 | 16 | C | Budgeted Units |  |  |  | 16
S366000 | Install RU | 2023-03-10 | 2023-03-13 | PROF3 IO E | PROF3 IO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | 01-Oct-19 A | 31-Jan-22 A | PROF4 PO M | PROF4 PO M | 30 | 0 | C | Budgeted Units |  | 30
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | 01-Oct-19 A | 31-Jan-22 A | TECH3 PO D | TECH3 PO D | 60 | 0 | C | Budgeted Units |  | 60
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 17-Jan-22 A | 31-Jan-22 A | PROF4 PO M | PROF4 PO M | 60 | 0 | C | Budgeted Units |  |  | 60
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 17-Jan-22 A | 31-Jan-22 A | TECH3 PO D | TECH3 PO D | 20 | 0 | C | Budgeted Units |  |  | 20
S364400 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures - Labor | 17-Jan-22 A | 31-Jan-22 A | TECH3 PO M | TECH3 PO M | 20 | 0 | C | Budgeted Units |  |  | 20
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | PROF4 PO M | PROF4 PO M | 40 | 10 | C | Budgeted Units |  | 40
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | TECH3 PO D | TECH3 PO D | 10 | 3 | C | Budgeted Units |  | 10
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | PROF4 PO M | PROF4 PO M | 8 | 7 | C | Budgeted Units |  |  | 8
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | TECH3 PO D | TECH3 PO D | 8 | 7 | C | Budgeted Units |  |  | 8
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | TECH3 PO M | TECH3 PO M | 8 | 7 | C | Budgeted Units |  |  | 8
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Budgeted Units |  |  |  | 8
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Budgeted Units |  |  |  | 60
S366700 | Align/Survey MVTX to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-03-17 | 2023-03-17 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Budgeted Units |  |  |  | 24
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Budgeted Units |  |  |  | 80
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Budgeted Units |  |  |  | 24
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Budgeted Units |  |  |  | 24
S365900 | Install Optical fibers | 2023-03-10 | 2023-03-13 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S366200 | Install Samtec Cables | 2023-03-10 | 2023-03-10 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S366300 | Install Half-Barrel 1 | 2023-03-13 | 2023-03-14 | PROF3 PO M | PROF3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S366300 | Install Half-Barrel 1 | 2023-03-13 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S366500 | Install Half-Barrel 2 | 2023-03-15 | 2023-03-16 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S366500 | Install Half-Barrel 2 | 2023-03-15 | 2023-03-16 | PROF3 PO M | PROF3 PO M | 80 | 80 | C | Budgeted Units |  |  |  | 80
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | PROF4 PO M | PROF4 PO M | 0 | 0 | C | Budgeted Units
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S367020 | Install MVTX cooling panels and route lines | 2023-03-20 | 2023-03-21 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S367020 | Install MVTX cooling panels and route lines | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Budgeted Units |  |  |  | 120
S367020 | Install MVTX cooling panels and route lines | 2023-03-20 | 2023-03-21 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S367030 | Install MVTX gas distribution panels and route lines | 2023-03-20 | 2023-03-21 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S367030 | Install MVTX gas distribution panels and route lines | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S367030 | Install MVTX gas distribution panels and route lines | 2023-03-20 | 2023-03-21 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 40 | 40 | C | Budgeted Units |  |  |  | 40
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 40 | 40 | C | Budgeted Units |  |  |  | 40
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Budgeted Units |  |  |  | 320
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Budgeted Units |  |  |  | 320
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Budgeted Units |  |  |  | 320
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
POM02-13.02.05.11 Min Bias Installation |  | 13-May-20 A | 2023-03-29 |  |  | 2084 | 1968 |  | Budgeted Units |  | 106 | 37 | 1941
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-16 | 2023-03-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S369450 | Check MBD operation during cabling | 2023-03-23 | 2023-03-23 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S369460 | Install MBD cooling panels and route lines | 2023-03-24 | 2023-03-24 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S369470 | Install MBD gas distribution panels and route lines | 2023-03-24 | 2023-03-24 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 2023-03-23 | 2023-03-29 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S369490 | Check MBD operation with DAQ in counting house | 2023-03-23 | 2023-03-29 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S370105 | Install MBD cooling panels and route lines | 2023-03-14 | 2023-03-14 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S370120 | Install sEPD Installation fixtures and test | 2023-03-15 | 2023-03-15 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S370140 | Install sEPD support system | 2023-03-15 | 2023-03-15 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S370160 | Install sEPD | 2023-03-16 | 2023-03-16 | TECH4 AD | TECH4 AD | 0 | 0 | C | Budgeted Units
S370180 | Align sEPD | 2023-03-17 | 2023-03-17 | TECH3 AD | TECH3 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | TECH3 PO E | TECH3 PO E | 20 | 20 | C | Budgeted Units |  |  |  | 20
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-16 | 2023-03-17 | TECH3 AD | TECH3 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S369450 | Check MBD operation during cabling | 2023-03-23 | 2023-03-23 | TECH3 AD | TECH3 AD | 0 | 0 | C | Budgeted Units
S369460 | Install MBD cooling panels and route lines | 2023-03-24 | 2023-03-24 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S369470 | Install MBD gas distribution panels and route lines | 2023-03-24 | 2023-03-24 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 2023-03-23 | 2023-03-29 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S369490 | Check MBD operation with DAQ in counting house | 2023-03-23 | 2023-03-29 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S370105 | Install MBD cooling panels and route lines | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370120 | Install sEPD Installation fixtures and test | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370140 | Install sEPD support system | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370160 | Install sEPD | 2023-03-16 | 2023-03-16 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370180 | Align sEPD | 2023-03-17 | 2023-03-17 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | TECH3 PO M | TECH3 PO M | 0 | 0 | C | Budgeted Units
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-16 | 2023-03-16 | CRAFT3 | CRAFT3 | 0 | 0 | C | Budgeted Units
S369450 | Check MBD operation during cabling | 2023-03-23 | 2023-03-23 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S369460 | Install MBD cooling panels and route lines | 2023-03-24 | 2023-03-24 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S369470 | Install MBD gas distribution panels and route lines | 2023-03-24 | 2023-03-24 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 2023-03-23 | 2023-03-29 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S369490 | Check MBD operation with DAQ in counting house | 2023-03-23 | 2023-03-29 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370105 | Install MBD cooling panels and route lines | 2023-03-14 | 2023-03-14 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S370120 | Install sEPD Installation fixtures and test | 2023-03-15 | 2023-03-15 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S370140 | Install sEPD support system | 2023-03-15 | 2023-03-15 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S370160 | Install sEPD | 2023-03-16 | 2023-03-16 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S370180 | Align sEPD | 2023-03-17 | 2023-03-17 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | SCI3 PO | SCI3 PO | 0 | 0 | C | Budgeted Units
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Budgeted Units |  |  |  | 40
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | 13-May-20 A | 18-Apr-22 A | PROF4 PO M | PROF4 PO M | 16 | 0 | C | Budgeted Units |  | 16
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | 13-May-20 A | 18-Apr-22 A | TECH3 PO D | TECH3 PO D | 30 | 0 | C | Budgeted Units |  | 30
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | PROF4 PO M | PROF4 PO M | 30 | 15 | C | Budgeted Units |  |  | 22 | 8
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | TECH3 PO D | TECH3 PO D | 10 | 5 | C | Budgeted Units |  |  | 7 | 3
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | TECH3 PO M | TECH3 PO M | 10 | 5 | C | Budgeted Units |  |  | 7 | 3
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | PROF4 PO M | PROF4 PO M | 40 | 10 | C | Budgeted Units |  | 40
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | TECH3 PO D | TECH3 PO D | 20 | 5 | C | Budgeted Units |  | 20
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 2023-03-13 | 2023-03-13 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 2023-03-13 | 2023-03-13 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Budgeted Units |  |  |  | 8
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-03-16 | 2023-03-22 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Budgeted Units |  |  |  | 20
S369300 | Install Min Bias Cables and Services - Labor | 2023-03-23 | 2023-03-23 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S368650 | Install MBD Installation fixtures and test | 2023-03-14 | 2023-03-14 | PROF3 PO M | PROF3 PO M | 10 | 10 | C | Budgeted Units |  |  |  | 10
S368650 | Install MBD Installation fixtures and test | 2023-03-14 | 2023-03-14 | TECH3 PO D | TECH3 PO D | 0 | 0 | C | Budgeted Units
S368650 | Install MBD Installation fixtures and test | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 10 | 10 | C | Budgeted Units |  |  |  | 10
S369300 | Install Min Bias Cables and Services - Labor | 2023-03-23 | 2023-03-23 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-03-16 | 2023-03-22 | TECH3 AD | TECH3 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S369450 | Check MBD operation during cabling | 2023-03-23 | 2023-03-23 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 2023-03-23 | 2023-03-29 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S369490 | Check MBD operation with DAQ in counting house | 2023-03-23 | 2023-03-29 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Budgeted Units |  |  |  | 160
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Budgeted Units |  |  |  | 80
POM02-13.02.05.12 Full System Integration and ORR |  | 01-Aug-22 A | 2023-01-31 |  |  | 1992 | 1592 |  | Budgeted Units |  |  | 400 | 1592
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF5 AD | PROF5 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF5 AD | PROF5 AD | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | PROF5 AD | PROF5 AD | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | PROF5 AD | PROF5 AD | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 AD | PROF4 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 AD | PROF4 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 01-Aug-22 A | 31-Aug-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | PROF6 AD | PROF6 AD | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | PROF6 AD | PROF6 AD | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | SCI3 AD | SCI3 AD | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | SCI3 AD | SCI3 AD | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI3 AD | SCI3 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 01-Aug-22 A | 31-Aug-22 A | TECH4 AD | TECH4 AD | 40 | 0 | C | Budgeted Units |  |  | 40
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 01-Aug-22 A | 31-Aug-22 A | TECH4 AD | TECH4 AD | 48 | 0 | C | Budgeted Units |  |  | 48
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 01-Aug-22 A | 31-Aug-22 A | PROF2 AD | PROF2 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S370000 | Move Full sPHENIX to IR - Labor - CA-D Resource(s) | 01-Aug-22 A | 31-Aug-22 A | PROF4 AD | PROF4 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 01-Aug-22 A | 31-Aug-22 A | PROF2 AD | PROF2 AD | 8 | 0 | C | Budgeted Units |  |  | 8
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF6 AD | PROF6 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF2 AD | PROF2 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 AD | PROF4 AD | 20 | 20 | C | Budgeted Units |  |  |  | 20
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF6 AD | PROF6 AD | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF6 AD | PROF6 AD | 8 | 8 | C | Budgeted Units |  |  |  | 8
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 01-Aug-22 A | 31-Aug-22 A | TECH3 AD | TECH3 AD | 48 | 0 | C | Budgeted Units |  |  | 48
S370210 | Align Full sPHENIX to Nominal Beamline and IP - Labor - CA-D Resource(s) | 01-Aug-22 A | 31-Aug-22 A | CRAFT3 | CRAFT3 | 40 | 0 | C | Budgeted Units |  |  | 40
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | PROF4 PO E | PROF4 PO E | 8 | 8 | C | Budgeted Units |  |  |  | 8
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 PO E | PROF4 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 01-Aug-22 A | 31-Aug-22 A | TECH3 AM | TECH3 AM | 40 | 0 | C | Budgeted Units |  |  | 40
S370200 | Align Full sPHENIX to Nominal Beamline and IP - Labor - Physics Resource(s) | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO M | TECH3 PO M | 16 | 0 | C | Budgeted Units |  |  | 16
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 01-Aug-22 A | 31-Aug-22 A | PROF4 PO M | PROF4 PO M | 8 | 0 | C | Budgeted Units |  |  | 8
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO E | TECH3 PO E | 24 | 0 | C | Budgeted Units |  |  | 24
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO M | TECH3 PO M | 96 | 0 | C | Budgeted Units |  |  | 96
S1003919 | Move Full sPHENIX to IR - Labor - Physics Resource(s) | 01-Aug-22 A | 31-Aug-22 A | TECH3 PO D | TECH3 PO D | 8 | 0 | C | Budgeted Units |  |  | 8
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | PROF4 PO E | PROF4 PO E | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | SCI3 PO | SCI3 PO | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | SCI4 PO | SCI 4 PO | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Budgeted Units |  |  |  | 8
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | SCI4 PO | SCI 4 PO | 24 | 24 | C | Budgeted Units |  |  |  | 24
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | SCI3 PO | SCI3 PO | 24 | 24 | C | Budgeted Units |  |  |  | 24
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | SCI3 PO | SCI3 PO | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | SCI4 PO | SCI 4 PO | 40 | 40 | C | Budgeted Units |  |  |  | 40
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | SCI3 PO | SCI3 PO | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | TECH3 PO E | TECH3 PO E | 24 | 24 | C | Budgeted Units |  |  |  | 24
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Budgeted Units |  |  |  | 24
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | SCI4 PO | SCI 4 PO | 24 | 24 | C | Budgeted Units |  |  |  | 24
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | TECH3 PO E | TECH3 PO E | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | TECH3 PO E | TECH3 PO E | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI3 PO | SCI3 PO | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 2023-01-25 | 2023-01-31 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Budgeted Units |  |  |  | 16
S370595 | Prepare for sPHENIX IRR | 2022-11-01 | 2023-01-31 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S370595 | Prepare for sPHENIX IRR | 2022-11-01 | 2023-01-31 | SCI3 | SCI3-1 | 160 | 160 | C | Budgeted Units |  |  |  | 160
S370595 | Prepare for sPHENIX IRR | 2022-11-01 | 2023-01-31 | PROF3 PO M | PROF3 PO M | 160 | 160 | C | Budgeted Units |  |  |  | 160
S370597 | Prepare for sPHENIX ARR | 2022-11-01 | 2023-01-31 | TECH3 PO E | TECH3 PO E | 0 | 0 | C | Budgeted Units
S370597 | Prepare for sPHENIX ARR | 2022-11-01 | 2023-01-31 | PROF3 PO M | PROF3 PO M | 160 | 160 | C | Budgeted Units |  |  |  | 160
S370597 | Prepare for sPHENIX ARR | 2022-11-01 | 2023-01-31 | SCI3 | SCI3-1 | 160 | 160 | C | Budgeted Units |  |  |  | 160

## FY23
Activity ID | Activity Name | Start | Finish | Resource ID | Resource Name | Budgeted Units | Remaining Units | BNL_Fund Source | Spreadsheet Field | FY21 | FY22 | FY23
POM02-13 POM02 sPHENIX WBS 1.x, 2.x October 2022- with Resources |  | 15-Feb-21 A | 2023-03-29 |  |  | 33956 | 30434 |  | Remaining Units |  |  | 30434
POM02-13.02 Infrastructure/Facility |  | 15-Feb-21 A | 2023-03-29 |  |  | 33956 | 30434 |  | Remaining Units |  |  | 30434
POM02-13.02.01 Infrastructure/Facility Management |  | 2022-10-03 | 2022-10-07 |  |  | 435 | 435 |  | Remaining Units |  |  | 435
POM02-13.02.01.04 Infrastructure Management |  | 2022-10-03 | 2022-10-07 |  |  | 153 | 153 |  | Remaining Units |  |  | 153
S277100 | 2023 Facility Support Systems L3 Project Management | 2022-10-03 | 2022-10-07 | PROF2 AD | PROF2 AD | 113 | 113 | C | Remaining Units |  |  | 113
S276500 | 2023 Infrastructure Project Management | 2022-10-03 | 2022-10-07 | PROF3 PO E | PROF3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
POM02-13.02.01.05 Installation Management |  | 2022-10-03 | 2022-10-05 |  |  | 282 | 282 |  | Remaining Units |  |  | 282
S278300 | 2023 Integration & Installation Project Management | 2022-10-03 | 2022-10-05 | PROF5 PO M | PROF5 PO M | 282 | 282 | C | Remaining Units |  |  | 282
POM02-13.02.02 SC Magnet |  | 08-Mar-21 A | 2023-01-17 |  |  | 2726 | 2258 |  | Remaining Units |  |  | 2258
POM02-13.02.02.01 Safety Reviews, Cooldown, Power Tests |  | 17-Aug-22 A | 2022-10-27 |  |  | 756 | 731 |  | Remaining Units |  |  | 731
POM02-13.02.02.01.01 Safety Reviews |  | 16-Sep-22 A | 2022-10-07 |  |  | 32 | 16 |  | Remaining Units |  |  | 16
S279000 | ASSRC REVIEW and Full Walkthrough | 16-Sep-22 A | 2022-10-07 | PROF6 AD | PROF6 AD | 16 | 8 | C | Remaining Units |  |  | 8
S279000 | ASSRC REVIEW and Full Walkthrough | 16-Sep-22 A | 2022-10-07 | SCI3 AD | SCI3 AD | 16 | 8 | C | Remaining Units |  |  | 8
POM02-13.02.02.01.02 Cooldown & Power Tests |  | 17-Aug-22 A | 2022-10-27 |  |  | 724 | 715 |  | Remaining Units |  |  | 715
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | PROF3 AD | PROF3 AD | 60 | 57 | C | Remaining Units |  |  | 57
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | PROF3 AD | PROF3 AD | 8 | 8 | C | Remaining Units |  |  | 8
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | PROF3 AD | PROF3 AD | 20 | 20 | C | Remaining Units |  |  | 20
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | PROF3 AD | PROF3 AD | 20 | 20 | C | Remaining Units |  |  | 20
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | TECH3 AD | TECH3 AD | 60 | 57 | C | Remaining Units |  |  | 57
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | TECH3 AD | TECH3 AD | 8 | 8 | C | Remaining Units |  |  | 8
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | PROF6 AD | PROF6 AD | 60 | 57 | C | Remaining Units |  |  | 57
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | PROF6 AD | PROF6 AD | 8 | 8 | C | Remaining Units |  |  | 8
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | PROF6 AD | PROF6 AD | 80 | 80 | C | Remaining Units |  |  | 80
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | PROF6 AD | PROF6 AD | 80 | 80 | C | Remaining Units |  |  | 80
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | SCI3 AD | SCI3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | SCI3 AD | SCI3 AD | 80 | 80 | C | Remaining Units |  |  | 80
POM02-13.02.02.04 Magnet Power Supplies/Controls/Quench Protection |  | 01-Jul-22 A | 2022-10-19 |  |  | 650 | 241 |  | Remaining Units |  |  | 241
POM02-13.02.02.04.01 AC/DC Power Distribution |  | 01-Jul-22 A | 2022-10-07 |  |  | 420 | 126 |  | Remaining Units |  |  | 126
POM02-13.02.02.04.01.03 Install PS AC/DC Cabling |  | 01-Jul-22 A | 2022-10-07 |  |  | 420 | 126 |  | Remaining Units |  |  | 126
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | TECH3 AD | TECH3 AD | 160 | 48 | C | Remaining Units |  |  | 48
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | PROF4 AD | PROF4 AD | 40 | 12 | C | Remaining Units |  |  | 12
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | CRAFT3 | CRAFT3 | 220 | 66 | C | Remaining Units |  |  | 66
POM02-13.02.02.04.02 Power Supply |  | 10-Aug-22 A | 2022-10-19 |  |  | 230 | 115 |  | Remaining Units |  |  | 115
POM02-13.02.02.04.02.01 Install Power Supply |  | 10-Aug-22 A | 2022-10-19 |  |  | 230 | 115 |  | Remaining Units |  |  | 115
S305000 | Magnet Power Supply Installation: Power Supply Testing | 23-Sep-22 A | 2022-10-19 | TECH3 AD | TECH3 AD | 80 | 40 | C | Remaining Units |  |  | 40
S305000 | Magnet Power Supply Installation: Power Supply Testing | 23-Sep-22 A | 2022-10-19 | PROF4 AD | PROF4 AD | 80 | 40 | C | Remaining Units |  |  | 40
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 10-Aug-22 A | 2022-10-11 | TECH3 AD | TECH3 AD | 70 | 35 | C | Remaining Units |  |  | 35
POM02-13.02.02.05 Magnet Field Measurements |  | 08-Mar-21 A | 2023-01-17 |  |  | 1320 | 1286 |  | Remaining Units |  |  | 1286
POM02-13.02.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication |  | 01-Sep-22 A | 2023-01-17 |  |  | 112 | 98 |  | Remaining Units |  |  | 98
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | SCI4 PO | SCI 4 PO | 24 | 19 | C | Remaining Units |  |  | 19
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | PROF4 PO E | PROF4 PO E | 24 | 19 | C | Remaining Units |  |  | 19
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | TECH3 PO E | TECH3 PO E | 24 | 19 | C | Remaining Units |  |  | 19
S308619 | Install probes and readout on TPC | 2023-01-03 | 2023-01-17 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
POM02-13.02.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis |  | 08-Mar-21 A | 2022-12-22 |  |  | 1208 | 1189 |  | Remaining Units |  |  | 1189
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units |  |  | 160
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | SCI4 PO | SCI 4 PO | 160 | 160 | C | Remaining Units |  |  | 160
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | SCI4 PO | SCI 4 PO | 160 | 160 | C | Remaining Units |  |  | 160
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units |  |  | 160
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 2022-11-16 | 2022-11-22 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 2022-11-16 | 2022-11-22 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S309110 | Receive report from CERN, incorporate into analysis | 2022-11-23 | 2022-12-22 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units |  |  | 16
S308633 | Construct mapping support (mechanical and electrical) | 08-Mar-21 A | 2022-11-01 | TECH3 PO M | TECH3 PO M | 32 | 13 | C | Remaining Units |  |  | 13
POM02-13.02.03 Carriage and Structural Components |  | 26-Sep-22 A | 2022-11-14 |  |  | 180 | 172 |  | Remaining Units |  |  | 172
POM02-13.02.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports |  | 26-Sep-22 A | 2022-11-14 |  |  | 180 | 172 |  | Remaining Units |  |  | 172
S318140 | Perform TPC Supports Acceptance | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S318140 | Perform TPC Supports Acceptance | 2022-10-31 | 2022-11-14 | PROF3 PO E | PROF3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S318170 | Perform MBD Supports Acceptance | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 10 | 10 | C | Remaining Units |  |  | 10
S318170 | Perform MBD Supports Acceptance | 2022-10-31 | 2022-11-14 | PROF3 PO E | PROF3 PO E | 10 | 10 | C | Remaining Units |  |  | 10
S318190 | Perform Beampipe Supports Acceptance | 26-Sep-22 A | 2022-10-17 | TECH3 PO M | TECH3 PO M | 40 | 36 | C | Remaining Units |  |  | 36
S318190 | Perform Beampipe Supports Acceptance | 26-Sep-22 A | 2022-10-17 | PROF3 PO E | PROF3 PO E | 40 | 36 | C | Remaining Units |  |  | 36
POM02-13.02.04 Infrastructure |  | 15-Feb-21 A | 2023-02-09 |  |  | 3797 | 3155 |  | Remaining Units |  |  | 3155
POM02-13.02.04.01 Infrastructure Detector Support Systems |  | 15-Feb-21 A | 2023-02-09 |  |  | 3234 | 2693 |  | Remaining Units |  |  | 2693
POM02-13.02.04.01.03 Detector Electronics Racks and Rack generic support systems |  | 13-Sep-21 A | 2022-11-10 |  |  | 780 | 546 |  | Remaining Units |  |  | 546
S331470 | Assemble Racks for Lower East Platform | 15-Nov-21 A | 2022-10-31 | TECH3 PO E | TECH3 PO E | 80 | 6 | C | Remaining Units |  |  | 6
S331490 | Assemble Racks for Main Upper Platform | 13-Sep-21 A | 2022-10-31 | TECH3 PO E | TECH3 PO E | 200 | 40 | C | Remaining Units |  |  | 40
S331496 | ADDED RACK ASSEMBLY EFFORT, BASED ON EFFORT TO DATE | 2022-11-01 | 2022-11-10 | TECH3 PO E | TECH3 PO E | 500 | 500 | C | Remaining Units |  |  | 500
POM02-13.02.04.01.04 Detector Gas and Cooling Services Systems |  | 15-Feb-21 A | 2023-02-09 |  |  | 2334 | 2027 |  | Remaining Units |  |  | 2027
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | PROF4 PO M | PROF4 PO M | 96 | 19 | C | Remaining Units |  |  | 19
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | TECH3 PO D | TECH3 PO D | 48 | 10 | C | Remaining Units |  |  | 10
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 22-Jul-22 A | 2022-10-31 | PROF4 PO M | PROF4 PO M | 32 | 19 | C | Remaining Units |  |  | 19
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 22-Jul-22 A | 2022-10-31 | TECH3 PO D | TECH3 PO D | 72 | 43 | C | Remaining Units |  |  | 43
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 05-Sep-22 A | 2022-11-02 | PROF4 PO M | PROF4 PO M | 24 | 14 | C | Remaining Units |  |  | 14
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 05-Sep-22 A | 2022-11-02 | TECH3 PO D | TECH3 PO D | 24 | 14 | C | Remaining Units |  |  | 14
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 03-Sep-22 A | 2023-02-02 | PROF4 PO M | PROF4 PO M | 96 | 58 | C | Remaining Units |  |  | 58
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 03-Sep-22 A | 2023-02-02 | TECH3 PO D | TECH3 PO D | 96 | 58 | C | Remaining Units |  |  | 58
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | PROF4 PO M | PROF4 PO M | 16 | 10 | C | Remaining Units |  |  | 10
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | TECH3 PO D | TECH3 PO D | 16 | 10 | C | Remaining Units |  |  | 10
S332781 | Design, procure, test remaining cooling system items | 2022-11-01 | 2022-11-02 | PROF3 PO E | PROF3 PO E | 100 | 100 | C | Remaining Units |  |  | 100
S332781 | Design, procure, test remaining cooling system items | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S332782 | Cooling System Panel Fabrication - TPC | 2022-11-03 | 2022-11-04 | PROF3 PO E | PROF3 PO E | 8 | 8 | C | Remaining Units |  |  | 8
S332782 | Cooling System Panel Fabrication - TPC | 2022-11-03 | 2022-11-04 | TECH3 PO M | TECH3 PO M | 130 | 130 | C | Remaining Units |  |  | 130
S332783 | Cooling System Panel Fabrication - TPot | 2022-11-07 | 2022-11-08 | PROF3 PO E | PROF3 PO E | 4 | 4 | C | Remaining Units |  |  | 4
S332783 | Cooling System Panel Fabrication - TPot | 2022-11-07 | 2022-11-08 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units |  |  | 60
S332784 | Cooling System Panel Fabrication - EMCal SiPM | 2022-11-09 | 2022-11-10 | TECH3 PO M | TECH3 PO M | 290 | 290 | C | Remaining Units |  |  | 290
S332785 | Cooling System Panel Fabrication - EMCal PreAmp | 2022-11-14 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 290 | 290 | C | Remaining Units |  |  | 290
S332786 | Cooling System Panel Fabrication - INTT ROC | 2022-11-16 | 2022-11-17 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Remaining Units |  |  | 120
S332787 | Cooling System Panel Fabrication - INTT Stave | 2022-11-18 | 2022-11-21 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Remaining Units |  |  | 120
S332788 | Cooling System Panel Fabrication - MVTX | 2022-11-22 | 2022-11-23 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S332789 | Cooling System Platform Manifolding | 2022-11-28 | 2022-11-29 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S332789 | Cooling System Platform Manifolding | 2022-11-28 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 100 | 100 | C | Remaining Units |  |  | 100
S332790 | Gas Distribution Panel Fabrication - TPC Ar-CF4 | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 100 | 100 | C | Remaining Units |  |  | 100
S332791 | Gas Distribution Panel Fabrication - TPC Laser N2 | 2022-10-05 | 2022-10-06 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 2022-10-07 | 2022-10-11 | PROF3 PO E | PROF3 PO E | 4 | 4 | C | Remaining Units |  |  | 4
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 2022-10-07 | 2022-10-11 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S332793 | Gas Distribution Panel Fabrication - EMCal SiPM N2 | 2022-10-12 | 2022-10-13 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S332794 | Gas Distribution Panel Fabrication - INTT Stave N2 | 2022-10-14 | 2022-10-17 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S332795 | Gas Distribution Panel Fabrication - MVTX N2 | 2022-10-18 | 2022-10-19 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S332796 | Gas Distribution Panel Fabrication - MBD dry compressed air | 2022-10-20 | 2022-10-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | TECH3 PO M | TECH3 PO M | 48 | 10 | C | Remaining Units |  |  | 10
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | TECH3 PO M | TECH3 PO M | 8 | 5 | C | Remaining Units |  |  | 5
POM02-13.02.04.01.05 Detector Safety Subsystems |  | 2022-11-01 | 2022-12-01 |  |  | 120 | 120 |  | Remaining Units |  |  | 120
S333720 | Fabricate Detector Safety Systems | 2022-11-01 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units |  |  | 60
S333720 | Fabricate Detector Safety Systems | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 60 | 60 | C | Remaining Units |  |  | 60
POM02-13.02.04.02 Infrastructure Facility Support Systems |  | 03-Sep-22 A | 2023-01-06 |  |  | 563 | 462 |  | Remaining Units |  |  | 462
POM02-13.02.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR |  | 2022-10-03 | 2022-10-04 |  |  | 113 | 113 |  | Remaining Units |  |  | 113
S277700 | 2023 Detector Support Systems L3 Project Management | 2022-10-03 | 2022-10-04 | PROF5 PO M | PROF5 PO M | 113 | 113 | C | Remaining Units |  |  | 113
POM02-13.02.04.02.05 IR/AH Safety Subsystems |  | 03-Sep-22 A | 2023-01-06 |  |  | 450 | 349 |  | Remaining Units |  |  | 349
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | TECH4 AD | TECH4 AD | 24 | 12 | C | Remaining Units |  |  | 12
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | TECH4 AD | TECH4 AD | 48 | 36 | C | Remaining Units |  |  | 36
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | TECH4 AD | TECH4 AD | 88 | 66 | C | Remaining Units |  |  | 66
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | PROF2 AD | PROF2 AD | 48 | 24 | C | Remaining Units |  |  | 24
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | PROF4 AD | PROF4 AD | 4 | 2 | C | Remaining Units |  |  | 2
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | PROF2 AD | PROF2 AD | 96 | 72 | C | Remaining Units |  |  | 72
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | PROF4 AD | PROF4 AD | 2 | 2 | C | Remaining Units |  |  | 2
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | PROF2 AD | PROF2 AD | 16 | 12 | C | Remaining Units |  |  | 12
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | PROF4 AD | PROF4 AD | 4 | 3 | C | Remaining Units |  |  | 3
S342390 | Design IR/AH Safety Systems | 2022-11-01 | 2022-12-30 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S342390 | Design IR/AH Safety Systems | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
POM02-13.02.05 Integration and Installation |  | 29-Apr-21 A | 2023-03-29 |  |  | 26818 | 24414 |  | Remaining Units |  |  | 24414
POM02-13.02.05.02 Infrastructure Installation |  | 09-Sep-21 A | 2023-02-06 |  |  | 7378 | 6303 |  | Remaining Units |  |  | 6303
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | PROF4 AD | PROF4 AD | 40 | 40 | C | Remaining Units |  |  | 40
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 AD | TECH3 AD | 104 | 104 | C | Remaining Units |  |  | 104
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | PROF2 AD | PROF2 AD | 40 | 2 | C | Remaining Units |  |  | 2
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | PROF4 AD | PROF4 AD | 40 | 2 | C | Remaining Units |  |  | 2
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | PROF4 AD | PROF4 AD | 16 | 12 | C | Remaining Units |  |  | 12
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | PROF2 AD | PROF2 AD | 40 | 30 | C | Remaining Units |  |  | 30
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | PROF2 AD | PROF2 AD | 80 | 80 | C | Remaining Units |  |  | 80
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF4 AD | PROF4 AD | 32 | 3 | C | Remaining Units |  |  | 3
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF4 AD | PROF4 AD | 32 | 16 | C | Remaining Units |  |  | 16
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF6 AD | PROF6 AD | 4 | 2 | C | Remaining Units |  |  | 2
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF6 AD | PROF6 AD | 4 | 0 | C | Remaining Units |  |  | 0
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | TECH3 AD | TECH3 AD | 80 | 60 | C | Remaining Units |  |  | 60
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | TECH3 AD | TECH3 AD | 40 | 2 | C | Remaining Units |  |  | 2
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 AD | TECH3 AD | 160 | 80 | C | Remaining Units |  |  | 80
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | CRAFT3 | CRAFT3 | 64 | 3 | C | Remaining Units |  |  | 3
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | CRAFT3 | CRAFT3 | 24 | 18 | C | Remaining Units |  |  | 18
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | CRAFT3 | CRAFT3 | 32 | 29 | C | Remaining Units |  |  | 29
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | CRAFT3 | CRAFT3 | 80 | 40 | C | Remaining Units |  |  | 40
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | CRAFT3 | CRAFT3 | 160 | 16 | C | Remaining Units |  |  | 16
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 30-Aug-22 A | 2022-10-31 | CRAFT3 | CRAFT3 | 80 | 40 | C | Remaining Units |  |  | 40
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | PROF4 PO M | PROF4 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Remaining Units |  |  | 16
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | TECH3 PO E | TECH3 PO E | 80 | 72 | C | Remaining Units |  |  | 72
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | TECH3 PO M | TECH3 PO M | 40 | 36 | C | Remaining Units |  |  | 36
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | PROF4 PO E | PROF4 PO E | 20 | 18 | C | Remaining Units |  |  | 18
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | PROF4 PO M | PROF4 PO M | 20 | 18 | C | Remaining Units |  |  | 18
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | PROF4 PO M | PROF4 PO M | 120 | 120 | C | Remaining Units |  |  | 120
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 720 | 720 | C | Remaining Units |  |  | 720
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | TECH3 PO D | TECH3 PO D | 96 | 96 | C | Remaining Units |  |  | 96
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 PO E | TECH3 PO E | 80 | 40 | C | Remaining Units |  |  | 40
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 PO M | TECH3 PO M | 80 | 40 | C | Remaining Units |  |  | 40
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | PROF4 PO E | PROF4 PO E | 80 | 40 | C | Remaining Units |  |  | 40
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | PROF4 PO M | PROF4 PO M | 120 | 114 | C | Remaining Units |  |  | 114
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO E | TECH3 PO E | 280 | 114 | C | Remaining Units |  |  | 114
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO M | TECH3 PO M | 280 | 114 | C | Remaining Units |  |  | 114
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO D | TECH3 PO D | 48 | 114 | C | Remaining Units |  |  | 114
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | PROF4 PO E | PROF4 PO E | 120 | 114 | C | Remaining Units |  |  | 114
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | TECH3 PO M | TECH3 PO M | 80 | 72 | C | Remaining Units |  |  | 72
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | TECH3 PO D | TECH3 PO D | 16 | 14 | C | Remaining Units |  |  | 14
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | PROF4 PO E | PROF4 PO E | 20 | 18 | C | Remaining Units |  |  | 18
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF4 PO E | PROF4 PO E | 40 | 4 | C | Remaining Units |  |  | 4
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF4 PO E | PROF4 PO E | 40 | 20 | C | Remaining Units |  |  | 20
S346298 | Build North and South work platforms | 17-Aug-22 A | 2023-01-27 | TECH3 PO M | TECH3 PO M | 30 | 21 | C | Remaining Units |  |  | 21
S346220 | Install AC power to Racks - Lower platforms | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Remaining Units |  |  | 120
S346230 | Install AC power to Racks - Middle platforms | 2022-12-02 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Remaining Units |  |  | 120
S346240 | Install AC power to Racks - Upper platforms | 2023-01-03 | 2023-01-31 | TECH3 PO E | TECH3 PO E | 480 | 480 | C | Remaining Units |  |  | 480
S347610 | Off Carriage Water Lines & Flow Control - Sill & Labyrinth area | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S347620 | Off Carriage Water Lines & Flow Control - Chiller Platforms | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S347630 | Off Carriage Water - ECW to 'brass block' | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S347640 | Off Carriage Water - Brass block to chillers | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S347650 | Off Carriage Water - Chiller panels to cooling lines | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S347660 | Off Carriage Water - Bridge lines | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S347670 | Off Carriage Water - Bridges to on-carriage panels | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S347680 | Off Carriage Water - Carriage ECW to on-carriage panels | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S347820 | Install Rack Cooling water - Lower platforms | 2022-11-01 | 2022-12-01 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S347830 | Install Rack Cooling water - Middle platforms | 2022-12-02 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S347840 | Install Rack Cooling water - Upper platforms | 2023-01-03 | 2023-01-31 | TECH3 AD | TECH3 AD | 320 | 320 | C | Remaining Units |  |  | 320
S345920 | Install Rack Protection systems - Lower platform | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S345930 | Install Rack Protection systems - Middle platform | 2022-12-02 | 2022-12-30 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S345940 | Install Rack Protection systems - Upper platform | 2023-01-03 | 2023-01-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units |  |  | 160
S346222 | Complete lighting and convenience power | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S346224 | Complete wiring of chiller platform | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S346226 | Complete wiring of N & S Ploe Tip doors and motors | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S346228 | Complete on-detector 24V-DC distribution system | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S346228 | Complete on-detector 24V-DC distribution system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S346235 | Complete rack interlock system (36 racks) | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 160 | 160 | C | Remaining Units |  |  | 160
S346232 | Complete global interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S346234 | Complete ODH, crash, sweeps - CAD PASS | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S346236 | Complete FAP and HSSP - Fire Alarm group | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S346238 | Complete network installation | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S346245 | Complete VESDA north/south solenoid - piping (sEPD area) | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 120 | 120 | C | Remaining Units |  |  | 120
S346242 | Complete ECW water leak detection | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S346244 | Complete contactor boxes for interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 120 | 120 | C | Remaining Units |  |  | 120
S346246 | Complete I/O terminations Rack 3B1 | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 240 | 240 | C | Remaining Units |  |  | 240
S346248 | Test rack interlock system | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S346248 | Test rack interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S346250 | Test global interlock system | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S346250 | Test global interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S356252 | Control system programming | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 120 | 120 | C | Remaining Units |  |  | 120
S356255 | Control system HMI and usage testing | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 120 | 120 | C | Remaining Units |  |  | 120
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | PROF2 AD | PROF2 AD | 20 | 10 | C | Remaining Units |  |  | 10
POM02-13.02.05.04 Outer Hcal Installation |  | 01-Mar-22 A | 2022-12-06 |  |  | 960 | 672 |  | Remaining Units |  |  | 672
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | TECH3 PO M | TECH3 PO M | 80 | 11 | C | Remaining Units |  |  | 11
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | TECH3 PO E | TECH3 PO E | 160 | 11 | C | Remaining Units |  |  | 11
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | PROF4 PO E | PROF4 PO E | 80 | 11 | C | Remaining Units |  |  | 11
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S351720 | Install OHCal gas distribution panels and route lines | 2022-11-21 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
POM02-13.02.05.06 Inner Hcal Installation |  | 2022-10-03 | 2022-12-06 |  |  | 960 | 960 |  | Remaining Units |  |  | 960
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units |  |  | 160
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | PROF4 PO E | PROF4 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S356720 | Install IHCal gas distribution panels and route lines | 2022-11-21 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
POM02-13.02.05.07 EMCal Installation |  | 01-Jul-22 A | 2023-02-10 |  |  | 4872 | 4034 |  | Remaining Units |  |  | 4034
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH4 AD | TECH4 AD | 60 | 30 | C | Remaining Units |  |  | 30
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 01-Jul-22 A | 2022-12-09 | PROF4 AD | PROF4 AD | 8 | 4 | C | Remaining Units |  |  | 4
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH3 AD | TECH3 AD | 60 | 30 | C | Remaining Units |  |  | 30
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | CRAFT3 | CRAFT3 | 320 | 320 | C | Remaining Units |  |  | 320
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | CRAFT3 | CRAFT3 | 80 | 40 | C | Remaining Units |  |  | 40
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 01-Jul-22 A | 2022-12-09 | CRAFT3 | CRAFT3 | 120 | 53 | C | Remaining Units |  |  | 53
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | PROF4 PO M | PROF4 PO M | 64 | 32 | C | Remaining Units |  |  | 32
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | TECH3 PO D | TECH3 PO D | 64 | 32 | C | Remaining Units |  |  | 32
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | TECH3 PO M | TECH3 PO M | 512 | 256 | C | Remaining Units |  |  | 256
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH3 PO M | TECH3 PO M | 20 | 10 | C | Remaining Units |  |  | 10
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units |  |  | 160
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO M | TECH3 PO M | 64 | 64 | C | Remaining Units |  |  | 64
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | PROF4 PO M | PROF4 PO M | 32 | 32 | C | Remaining Units |  |  | 32
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO D | TECH3 PO D | 32 | 32 | C | Remaining Units |  |  | 32
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | SCI3 PO | SCI3 PO | 400 | 200 | C | Remaining Units |  |  | 200
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | PROF4 PO E | PROF4 PO E | 40 | 20 | C | Remaining Units |  |  | 20
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO E | TECH3 PO E | 40 | 20 | C | Remaining Units |  |  | 20
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | PROF4 PO M | PROF4 PO M | 40 | 20 | C | Remaining Units |  |  | 20
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO D | TECH3 PO D | 40 | 20 | C | Remaining Units |  |  | 20
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO M | TECH3 PO M | 40 | 20 | C | Remaining Units |  |  | 20
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 01-Jul-22 A | 2022-12-09 | TECH3 PO M | TECH3 PO M | 64 | 28 | C | Remaining Units |  |  | 28
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 2022-11-01 | 2022-11-07 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S359402 | Install EMCal cooling panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S359404 | Install EMCal gas distribution panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units |  |  | 160
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units |  |  | 160
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S359520 | Install TPot Installation fixtures and test | 2022-10-03 | 2022-10-04 | PROF3 PO M | PROF3 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S359520 | Install TPot Installation fixtures and test | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S359530 | Install TPot support system | 2022-12-02 | 2022-12-02 | PROF3 PO M | PROF3 PO M | 4 | 4 | C | Remaining Units |  |  | 4
S359530 | Install TPot support system | 2022-12-02 | 2022-12-02 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | PROF3 PO M | PROF3 PO M | 4 | 4 | C | Remaining Units |  |  | 4
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | PROF3 PO M | PROF3 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Remaining Units |  |  | 16
S359580 | Install TPot cooling panels and route lines | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S359590 | Install TPot gas distribution panels and route lines | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Remaining Units |  |  | 16
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Remaining Units |  |  | 16
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 2022-11-01 | 2022-11-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units |  |  | 320
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 320 | 320 | C | Remaining Units |  |  | 320
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units |  |  | 320
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 320 | 320 | C | Remaining Units |  |  | 320
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Remaining Units |  |  | 8
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Remaining Units |  |  | 8
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | TECH3 AD | TECH3 AD | 20 | 20 | C | Remaining Units |  |  | 20
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Remaining Units |  |  | 8
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Remaining Units |  |  | 8
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Remaining Units |  |  | 48
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Remaining Units |  |  | 24
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Remaining Units |  |  | 48
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Remaining Units |  |  | 24
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Remaining Units |  |  | 48
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Remaining Units |  |  | 24
POM02-13.02.05.08 TPC Installation |  | 03-Jan-22 A | 2023-03-06 |  |  | 3104 | 3010 |  | Remaining Units |  |  | 3010
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 2022-12-13 | 2022-12-19 | PROF4 AD | PROF4 AD | 8 | 8 | C | Remaining Units |  |  | 8
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | TECH4 AD | TECH4 AD | 60 | 60 | C | Remaining Units |  |  | 60
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 2022-12-29 | 2023-01-12 | PROF2 AD | PROF2 AD | 8 | 8 | C | Remaining Units |  |  | 8
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | TECH3 AD | TECH3 AD | 60 | 60 | C | Remaining Units |  |  | 60
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | CRAFT3 | CRAFT3 | 240 | 240 | C | Remaining Units |  |  | 240
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | CRAFT3 | CRAFT3 | 80 | 80 | C | Remaining Units |  |  | 80
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | CRAFT3 | CRAFT3 | 36 | 36 | C | Remaining Units |  |  | 36
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 03-Jan-22 A | 2022-10-20 | PROF4 PO M | PROF4 PO M | 60 | 6 | C | Remaining Units |  |  | 6
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 03-Jan-22 A | 2022-10-20 | TECH3 PO D | TECH3 PO D | 20 | 2 | C | Remaining Units |  |  | 2
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | PROF4 PO M | PROF4 PO M | 8 | 1 | C | Remaining Units |  |  | 1
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | TECH3 PO M | TECH3 PO M | 8 | 1 | C | Remaining Units |  |  | 1
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | TECH3 PO D | TECH3 PO D | 8 | 1 | C | Remaining Units |  |  | 1
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Remaining Units |  |  | 8
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Remaining Units |  |  | 4
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Remaining Units |  |  | 16
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-01-13 | 2023-01-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Remaining Units |  |  | 120
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units |  |  | 60
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Remaining Units |  |  | 24
S360600 | Open SC Magnet Pole Tip Doors | 2022-12-20 | 2022-12-20 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Remaining Units |  |  | 4
S360600 | Open SC Magnet Pole Tip Doors | 2022-12-20 | 2022-12-20 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Remaining Units |  |  | 4
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Remaining Units |  |  | 16
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units |  |  | 60
S360620 | Install TPC Installation fixtures and test | 2022-12-21 | 2022-12-21 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S360620 | Install TPC Installation fixtures and test | 2022-12-21 | 2022-12-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | SCI3 | SCI3-1 | 16 | 16 | C | Remaining Units |  |  | 16
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units |  |  | 160
S361440 | Install TPC cooling panels and route lines | 2022-12-21 | 2022-12-22 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S361460 | Install TPC gas distribution panels and route lines | 2022-12-21 | 2022-12-22 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | SCI3 | SCI3-1 | 12 | 12 | C | Remaining Units |  |  | 12
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | TECH3 PO E | TECH3 PO E | 24 | 24 | C | Remaining Units |  |  | 24
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units |  |  | 160
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units |  |  | 160
S361950 | Erect 1008 IR Shield Wall | 2023-02-28 | 2023-03-06 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S361950 | Erect 1008 IR Shield Wall | 2023-02-28 | 2023-03-06 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
POM02-13.02.05.09 INTT Installation |  | 2022-10-03 | 2023-03-09 |  |  | 2492 | 2492 |  | Remaining Units |  |  | 2492
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 AD | TECH3 AD | 60 | 60 | C | Remaining Units |  |  | 60
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | CRAFT3 | CRAFT3 | 240 | 240 | C | Remaining Units |  |  | 240
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 2022-10-03 | 2022-10-17 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 2022-10-03 | 2022-10-17 | TECH3 PO D | TECH3 PO D | 20 | 20 | C | Remaining Units |  |  | 20
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Remaining Units |  |  | 8
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units |  |  | 60
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units |  |  | 60
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Remaining Units |  |  | 120
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Remaining Units |  |  | 120
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Remaining Units |  |  | 24
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Remaining Units |  |  | 24
S362920 | Install INTT Installation fixtures and test | 2023-02-06 | 2023-02-07 | PROF3 PO M | PROF3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S362920 | Install INTT Installation fixtures and test | 2023-02-06 | 2023-02-07 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S363120 | Install Beampipe | 2023-02-21 | 2023-02-21 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S363140 | Install Beampipe vacuum system | 2023-02-22 | 2023-02-22 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S363160 | Pump down beampipe | 2023-02-23 | 2023-02-23 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S363180 | Perform Beampipe Bakeout | 2023-02-24 | 2023-03-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units |  |  | 80
S363520 | Install beampipe permanent support | 2023-03-03 | 2023-03-03 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S363540 | Remove beampipe Temporary Support | 2023-03-06 | 2023-03-06 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S363740 | Install INTT cooling panels and route lines | 2023-03-07 | 2023-03-07 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S363760 | Install INTT gas distribution panels and route lines | 2023-03-07 | 2023-03-07 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
POM02-13.02.05.10 MVTX Installation |  | 29-Apr-21 A | 2023-03-22 |  |  | 3422 | 3382 |  | Remaining Units |  |  | 3382
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-17 | 2023-03-20 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units |  |  | 40
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | CRAFT3 | CRAFT3 | 160 | 160 | C | Remaining Units |  |  | 160
S365700 | Install FELIX | 2023-03-10 | 2023-03-13 | PROF3 IO E | PROF3 IO E | 16 | 16 | C | Remaining Units |  |  | 16
S366000 | Install RU | 2023-03-10 | 2023-03-13 | PROF3 IO E | PROF3 IO E | 40 | 40 | C | Remaining Units |  |  | 40
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | PROF4 PO M | PROF4 PO M | 40 | 10 | C | Remaining Units |  |  | 10
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | TECH3 PO D | TECH3 PO D | 10 | 3 | C | Remaining Units |  |  | 3
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | PROF4 PO M | PROF4 PO M | 8 | 7 | C | Remaining Units |  |  | 7
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | TECH3 PO D | TECH3 PO D | 8 | 7 | C | Remaining Units |  |  | 7
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | TECH3 PO M | TECH3 PO M | 8 | 7 | C | Remaining Units |  |  | 7
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Remaining Units |  |  | 8
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units |  |  | 60
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Remaining Units |  |  | 24
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units |  |  | 80
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Remaining Units |  |  | 24
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Remaining Units |  |  | 24
S365900 | Install Optical fibers | 2023-03-10 | 2023-03-13 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S366200 | Install Samtec Cables | 2023-03-10 | 2023-03-10 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S366300 | Install Half-Barrel 1 | 2023-03-13 | 2023-03-14 | PROF3 PO M | PROF3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S366300 | Install Half-Barrel 1 | 2023-03-13 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S366500 | Install Half-Barrel 2 | 2023-03-15 | 2023-03-16 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S366500 | Install Half-Barrel 2 | 2023-03-15 | 2023-03-16 | PROF3 PO M | PROF3 PO M | 80 | 80 | C | Remaining Units |  |  | 80
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S367020 | Install MVTX cooling panels and route lines | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Remaining Units |  |  | 120
S367030 | Install MVTX gas distribution panels and route lines | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 40 | 40 | C | Remaining Units |  |  | 40
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 40 | 40 | C | Remaining Units |  |  | 40
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units |  |  | 320
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units |  |  | 320
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units |  |  | 320
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
POM02-13.02.05.11 Min Bias Installation |  | 29-Apr-21 A | 2023-03-29 |  |  | 2038 | 1968 |  | Remaining Units |  |  | 1968
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-16 | 2023-03-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S370180 | Align sEPD | 2023-03-17 | 2023-03-17 | TECH3 AD | TECH3 AD | 20 | 20 | C | Remaining Units |  |  | 20
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | TECH3 PO E | TECH3 PO E | 20 | 20 | C | Remaining Units |  |  | 20
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-16 | 2023-03-17 | TECH3 AD | TECH3 AD | 20 | 20 | C | Remaining Units |  |  | 20
S369460 | Install MBD cooling panels and route lines | 2023-03-24 | 2023-03-24 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S369470 | Install MBD gas distribution panels and route lines | 2023-03-24 | 2023-03-24 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S370105 | Install MBD cooling panels and route lines | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S370120 | Install sEPD Installation fixtures and test | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S370140 | Install sEPD support system | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S370160 | Install sEPD | 2023-03-16 | 2023-03-16 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S370180 | Align sEPD | 2023-03-17 | 2023-03-17 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S369450 | Check MBD operation during cabling | 2023-03-23 | 2023-03-23 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 2023-03-23 | 2023-03-29 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S369490 | Check MBD operation with DAQ in counting house | 2023-03-23 | 2023-03-29 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units |  |  | 40
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | PROF4 PO M | PROF4 PO M | 30 | 15 | C | Remaining Units |  |  | 15
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | TECH3 PO D | TECH3 PO D | 10 | 5 | C | Remaining Units |  |  | 5
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | TECH3 PO M | TECH3 PO M | 10 | 5 | C | Remaining Units |  |  | 5
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | PROF4 PO M | PROF4 PO M | 40 | 10 | C | Remaining Units |  |  | 10
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | TECH3 PO D | TECH3 PO D | 20 | 5 | C | Remaining Units |  |  | 5
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 2023-03-13 | 2023-03-13 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 2023-03-13 | 2023-03-13 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units |  |  | 8
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-03-16 | 2023-03-22 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units |  |  | 20
S369300 | Install Min Bias Cables and Services - Labor | 2023-03-23 | 2023-03-23 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S368650 | Install MBD Installation fixtures and test | 2023-03-14 | 2023-03-14 | PROF3 PO M | PROF3 PO M | 10 | 10 | C | Remaining Units |  |  | 10
S368650 | Install MBD Installation fixtures and test | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 10 | 10 | C | Remaining Units |  |  | 10
S369300 | Install Min Bias Cables and Services - Labor | 2023-03-23 | 2023-03-23 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-03-16 | 2023-03-22 | TECH3 AD | TECH3 AD | 20 | 20 | C | Remaining Units |  |  | 20
S369450 | Check MBD operation during cabling | 2023-03-23 | 2023-03-23 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 2023-03-23 | 2023-03-29 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S369490 | Check MBD operation with DAQ in counting house | 2023-03-23 | 2023-03-29 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Remaining Units |  |  | 160
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 40 | 40 | C | Remaining Units |  |  | 40
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 40 | 40 | C | Remaining Units |  |  | 40
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units |  |  | 80
POM02-13.02.05.12 Full System Integration and ORR |  | 2022-10-03 | 2023-01-31 |  |  | 1592 | 1592 |  | Remaining Units |  |  | 1592
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF5 AD | PROF5 AD | 20 | 20 | C | Remaining Units |  |  | 20
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF5 AD | PROF5 AD | 16 | 16 | C | Remaining Units |  |  | 16
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | PROF5 AD | PROF5 AD | 16 | 16 | C | Remaining Units |  |  | 16
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | PROF5 AD | PROF5 AD | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 AD | PROF4 AD | 8 | 8 | C | Remaining Units |  |  | 8
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 AD | PROF4 AD | 8 | 8 | C | Remaining Units |  |  | 8
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | PROF6 AD | PROF6 AD | 16 | 16 | C | Remaining Units |  |  | 16
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | PROF6 AD | PROF6 AD | 16 | 16 | C | Remaining Units |  |  | 16
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | SCI3 AD | SCI3 AD | 16 | 16 | C | Remaining Units |  |  | 16
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | SCI3 AD | SCI3 AD | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI3 AD | SCI3 AD | 8 | 8 | C | Remaining Units |  |  | 8
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF6 AD | PROF6 AD | 20 | 20 | C | Remaining Units |  |  | 20
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF2 AD | PROF2 AD | 20 | 20 | C | Remaining Units |  |  | 20
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 AD | PROF4 AD | 20 | 20 | C | Remaining Units |  |  | 20
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF6 AD | PROF6 AD | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF6 AD | PROF6 AD | 8 | 8 | C | Remaining Units |  |  | 8
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | PROF4 PO E | PROF4 PO E | 8 | 8 | C | Remaining Units |  |  | 8
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 PO E | PROF4 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | PROF4 PO E | PROF4 PO E | 40 | 40 | C | Remaining Units |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | SCI3 PO | SCI3 PO | 40 | 40 | C | Remaining Units |  |  | 40
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | SCI4 PO | SCI 4 PO | 40 | 40 | C | Remaining Units |  |  | 40
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units |  |  | 8
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | SCI4 PO | SCI 4 PO | 24 | 24 | C | Remaining Units |  |  | 24
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | SCI3 PO | SCI3 PO | 24 | 24 | C | Remaining Units |  |  | 24
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Remaining Units |  |  | 40
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | SCI3 PO | SCI3 PO | 40 | 40 | C | Remaining Units |  |  | 40
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | SCI4 PO | SCI 4 PO | 40 | 40 | C | Remaining Units |  |  | 40
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Remaining Units |  |  | 16
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | SCI3 PO | SCI3 PO | 16 | 16 | C | Remaining Units |  |  | 16
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units |  |  | 16
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | TECH3 PO E | TECH3 PO E | 24 | 24 | C | Remaining Units |  |  | 24
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Remaining Units |  |  | 24
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | SCI4 PO | SCI 4 PO | 24 | 24 | C | Remaining Units |  |  | 24
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | TECH3 PO E | TECH3 PO E | 16 | 16 | C | Remaining Units |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Remaining Units |  |  | 16
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | TECH3 PO E | TECH3 PO E | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units |  |  | 16
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI3 PO | SCI3 PO | 16 | 16 | C | Remaining Units |  |  | 16
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 2023-01-25 | 2023-01-31 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units |  |  | 16
S370595 | Prepare for sPHENIX IRR | 2022-11-01 | 2023-01-31 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units |  |  | 160
S370595 | Prepare for sPHENIX IRR | 2022-11-01 | 2023-01-31 | PROF3 PO M | PROF3 PO M | 160 | 160 | C | Remaining Units |  |  | 160
S370597 | Prepare for sPHENIX ARR | 2022-11-01 | 2023-01-31 | PROF3 PO M | PROF3 PO M | 160 | 160 | C | Remaining Units |  |  | 160
S370597 | Prepare for sPHENIX ARR | 2022-11-01 | 2023-01-31 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units |  |  | 160

## Time-Phased
Activity ID | Activity Name | Start | Finish | Resource ID | Resource Name | Budgeted Units | Remaining Units | BNL_Fund Source | Spreadsheet Field | time axis 2022-10-01 to 2023-03-29
POM02-13 POM02 sPHENIX WBS 1.x, 2.x October 2022- with Resources |  | 15-Feb-21 A | 2023-03-29 |  |  | 33956 | 30434 |  | Remaining Units |  |  | 570 | 570 | 472 | 378 | 420 |  |  |  | 310 | 201 | 201 | 201 |  |  | 201 | 176 | 176 | 254 | 253 |  |  | 233 | 233 | 237 | 237 | 150 |  |  | 233 | 768 | 767 | 396 | 387 |  |  | 350 | 318 | 431 | 431 |  |  |  | 368 | 358 | 234 | 234 | 231 |  |  | 367 | 347 | 324 |  |  |  |  | 346 | 346 | 268 | 265 | 243 |  |  | 399 | 351 | 135 | 135 | 225 |  |  | 206 | 304 | 304 | 304 | 297 |  |  | 297 | 308 | 468 | 396 | 306 |  |  |  | 306 | 146 | 150 | 150 |  |  |  | 142 | 142 | 142 | 92 |  |  | 90 | 102 | 102 | 102 | 145 |  |  |  | 145 | 150 | 148 | 148 |  |  | 133 | 133 | 110 | 110 | 86 |  |  | 142 | 142 | 80 | 80 | 78 |  |  | 185 | 179 | 149 | 149 | 149 |  |  | 137 | 137 | 137 | 137 | 137 |  |  |  | 197 | 197 | 197 | 173 |  |  | 173 | 108 | 108 | 78 | 398 |  |  | 398 | 406 | 326 | 402 | 88 |  |  | 144 | 172 | 192 | 148 | 114 |  |  | 1190 | 1212 | 348 | 360 | 160 |  |  | 80 | 80 | 80
POM02-13.02 Infrastructure/Facility |  | 15-Feb-21 A | 2023-03-29 |  |  | 33956 | 30434 |  | Remaining Units |  |  | 570 | 570 | 472 | 378 | 420 |  |  |  | 310 | 201 | 201 | 201 |  |  | 201 | 176 | 176 | 254 | 253 |  |  | 233 | 233 | 237 | 237 | 150 |  |  | 233 | 768 | 767 | 396 | 387 |  |  | 350 | 318 | 431 | 431 |  |  |  | 368 | 358 | 234 | 234 | 231 |  |  | 367 | 347 | 324 |  |  |  |  | 346 | 346 | 268 | 265 | 243 |  |  | 399 | 351 | 135 | 135 | 225 |  |  | 206 | 304 | 304 | 304 | 297 |  |  | 297 | 308 | 468 | 396 | 306 |  |  |  | 306 | 146 | 150 | 150 |  |  |  | 142 | 142 | 142 | 92 |  |  | 90 | 102 | 102 | 102 | 145 |  |  |  | 145 | 150 | 148 | 148 |  |  | 133 | 133 | 110 | 110 | 86 |  |  | 142 | 142 | 80 | 80 | 78 |  |  | 185 | 179 | 149 | 149 | 149 |  |  | 137 | 137 | 137 | 137 | 137 |  |  |  | 197 | 197 | 197 | 173 |  |  | 173 | 108 | 108 | 78 | 398 |  |  | 398 | 406 | 326 | 402 | 88 |  |  | 144 | 172 | 192 | 148 | 114 |  |  | 1190 | 1212 | 348 | 360 | 160 |  |  | 80 | 80 | 80
POM02-13.02.01 Infrastructure/Facility Management |  | 2022-10-03 | 2022-10-07 |  |  | 435 | 435 |  | Remaining Units | 2022-10-03: 125; 2022-10-04: 125; 2022-10-05: 125; 2022-10-06: 31; 2022-10-07: 31
POM02-13.02.01.04 Infrastructure Management |  | 2022-10-03 | 2022-10-07 |  |  | 153 | 153 |  | Remaining Units | 2022-10-03: 31; 2022-10-04: 31; 2022-10-05: 31; 2022-10-06: 31; 2022-10-07: 31
S277100 | 2023 Facility Support Systems L3 Project Management | 2022-10-03 | 2022-10-07 | PROF2 AD | PROF2 AD | 113 | 113 | C | Remaining Units | 2022-10-03: 23; 2022-10-04: 23; 2022-10-05: 23; 2022-10-06: 23; 2022-10-07: 23
S276500 | 2023 Infrastructure Project Management | 2022-10-03 | 2022-10-07 | PROF3 PO E | PROF3 PO E | 40 | 40 | C | Remaining Units | 2022-10-03: 8; 2022-10-04: 8; 2022-10-05: 8; 2022-10-06: 8; 2022-10-07: 8
POM02-13.02.01.05 Installation Management |  | 2022-10-03 | 2022-10-05 |  |  | 282 | 282 |  | Remaining Units | 2022-10-03: 94; 2022-10-04: 94; 2022-10-05: 94
S278300 | 2023 Integration & Installation Project Management | 2022-10-03 | 2022-10-05 | PROF5 PO M | PROF5 PO M | 282 | 282 | C | Remaining Units | 2022-10-03: 94; 2022-10-04: 94; 2022-10-05: 94
POM02-13.02.02 SC Magnet |  | 08-Mar-21 A | 2023-01-17 |  |  | 2726 | 2258 |  | Remaining Units | 2022-10-03: 30; 2022-10-04: 30; 2022-10-05: 30; 2022-10-06: 30; 2022-10-07: 30; 2022-10-11: 71; 2022-10-12: 49; 2022-10-13: 49; 2022-10-14: 49; 2022-10-17: 49; 2022-10-18: 75; 2022-10-19: 75; 2022-10-20: 136; 2022-10-21: 136; 2022-10-24: 136; 2022-10-25: 136; 2022-10-26: 136; 2022-10-27: 136; 2022-10-28: 50; 2022-10-31: 50; 2022-11-01: 58; 2022-11-02: 57; 2022-11-03: 57; 2022-11-04: 57; 2022-11-07: 57; 2022-11-08: 57; 2022-11-09: 57; 2022-11-10: 57; 2022-11-14: 57; 2022-11-15: 57; 2022-11-16: 25; 2022-11-17: 25; 2022-11-18: 25; 2022-11-21: 25; 2022-11-22: 25; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 1; 2022-12-27: 1; 2022-12-28: 1; 2022-12-29: 1; 2022-12-30: 1; 2023-01-03: 4; 2023-01-04: 4; 2023-01-05: 4; 2023-01-06: 4; 2023-01-09: 4; 2023-01-10: 4; 2023-01-11: 4; 2023-01-12: 4; 2023-01-13: 4; 2023-01-17: 4
POM02-13.02.02.01 Safety Reviews, Cooldown, Power Tests |  | 17-Aug-22 A | 2022-10-27 |  |  | 756 | 731 |  | Remaining Units | 2022-10-03: 3; 2022-10-04: 3; 2022-10-05: 3; 2022-10-06: 3; 2022-10-07: 3; 2022-10-11: 34; 2022-10-12: 34; 2022-10-13: 34; 2022-10-14: 34; 2022-10-17: 34; 2022-10-18: 12; 2022-10-19: 12; 2022-10-20: 87; 2022-10-21: 87; 2022-10-24: 87; 2022-10-25: 87; 2022-10-26: 87; 2022-10-27: 87
POM02-13.02.02.01.01 Safety Reviews |  | 16-Sep-22 A | 2022-10-07 |  |  | 32 | 16 |  | Remaining Units | 2022-10-03: 3; 2022-10-04: 3; 2022-10-05: 3; 2022-10-06: 3; 2022-10-07: 3
S279000 | ASSRC REVIEW and Full Walkthrough | 16-Sep-22 A | 2022-10-07 | PROF6 AD | PROF6 AD | 16 | 8 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2
S279000 | ASSRC REVIEW and Full Walkthrough | 16-Sep-22 A | 2022-10-07 | SCI3 AD | SCI3 AD | 16 | 8 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2
POM02-13.02.02.01.02 Cooldown & Power Tests |  | 17-Aug-22 A | 2022-10-27 |  |  | 724 | 715 |  | Remaining Units | 2022-10-11: 34; 2022-10-12: 34; 2022-10-13: 34; 2022-10-14: 34; 2022-10-17: 34; 2022-10-18: 12; 2022-10-19: 12; 2022-10-20: 87; 2022-10-21: 87; 2022-10-24: 87; 2022-10-25: 87; 2022-10-26: 87; 2022-10-27: 87
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | PROF3 AD | PROF3 AD | 60 | 57 | C | Remaining Units | 2022-10-11: 11; 2022-10-12: 11; 2022-10-13: 11; 2022-10-14: 11; 2022-10-17: 11
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | PROF3 AD | PROF3 AD | 8 | 8 | C | Remaining Units | 2022-10-18: 4; 2022-10-19: 4
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | PROF3 AD | PROF3 AD | 20 | 20 | C | Remaining Units | 2022-10-20: 7; 2022-10-21: 7; 2022-10-24: 7
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | PROF3 AD | PROF3 AD | 20 | 20 | C | Remaining Units | 2022-10-25: 7; 2022-10-26: 7; 2022-10-27: 7
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | TECH3 AD | TECH3 AD | 60 | 57 | C | Remaining Units | 2022-10-11: 11; 2022-10-12: 11; 2022-10-13: 11; 2022-10-14: 11; 2022-10-17: 11
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | TECH3 AD | TECH3 AD | 8 | 8 | C | Remaining Units | 2022-10-18: 4; 2022-10-19: 4
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-10-20: 27; 2022-10-21: 27; 2022-10-24: 27
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-10-25: 27; 2022-10-26: 27; 2022-10-27: 27
S279100 | Cooldown | 17-Aug-22 A | 2022-10-17 | PROF6 AD | PROF6 AD | 60 | 57 | C | Remaining Units | 2022-10-11: 11; 2022-10-12: 11; 2022-10-13: 11; 2022-10-14: 11; 2022-10-17: 11
S279200 | 4.5K Static Heat Load test | 2022-10-18 | 2022-10-19 | PROF6 AD | PROF6 AD | 8 | 8 | C | Remaining Units | 2022-10-18: 4; 2022-10-19: 4
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | PROF6 AD | PROF6 AD | 80 | 80 | C | Remaining Units | 2022-10-20: 27; 2022-10-21: 27; 2022-10-24: 27
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | PROF6 AD | PROF6 AD | 80 | 80 | C | Remaining Units | 2022-10-25: 27; 2022-10-26: 27; 2022-10-27: 27
S279300 | 4.5K Low power test | 2022-10-20 | 2022-10-24 | SCI3 AD | SCI3 AD | 80 | 80 | C | Remaining Units | 2022-10-20: 27; 2022-10-21: 27; 2022-10-24: 27
S279400 | 4.5K High Power Test | 2022-10-25 | 2022-10-27 | SCI3 AD | SCI3 AD | 80 | 80 | C | Remaining Units | 2022-10-25: 27; 2022-10-26: 27; 2022-10-27: 27
POM02-13.02.02.04 Magnet Power Supplies/Controls/Quench Protection |  | 01-Jul-22 A | 2022-10-19 |  |  | 650 | 241 |  | Remaining Units | 2022-10-03: 25; 2022-10-04: 25; 2022-10-05: 25; 2022-10-06: 25; 2022-10-07: 25; 2022-10-11: 35; 2022-10-12: 13; 2022-10-13: 13; 2022-10-14: 13; 2022-10-17: 13; 2022-10-18: 13; 2022-10-19: 13
POM02-13.02.02.04.01 AC/DC Power Distribution |  | 01-Jul-22 A | 2022-10-07 |  |  | 420 | 126 |  | Remaining Units | 2022-10-03: 25; 2022-10-04: 25; 2022-10-05: 25; 2022-10-06: 25; 2022-10-07: 25
POM02-13.02.02.04.01.03 Install PS AC/DC Cabling |  | 01-Jul-22 A | 2022-10-07 |  |  | 420 | 126 |  | Remaining Units | 2022-10-03: 25; 2022-10-04: 25; 2022-10-05: 25; 2022-10-06: 25; 2022-10-07: 25
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | TECH3 AD | TECH3 AD | 160 | 48 | C | Remaining Units | 2022-10-03: 10; 2022-10-04: 10; 2022-10-05: 10; 2022-10-06: 10; 2022-10-07: 10
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | PROF4 AD | PROF4 AD | 40 | 12 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2
S303600 | Magnet: Pull & Terminate AC/DC Power Cables and Signal Cables 1008IR | 01-Jul-22 A | 2022-10-07 | CRAFT3 | CRAFT3 | 220 | 66 | C | Remaining Units | 2022-10-03: 13; 2022-10-04: 13; 2022-10-05: 13; 2022-10-06: 13; 2022-10-07: 13
POM02-13.02.02.04.02 Power Supply |  | 10-Aug-22 A | 2022-10-19 |  |  | 230 | 115 |  | Remaining Units | 2022-10-11: 35; 2022-10-12: 13; 2022-10-13: 13; 2022-10-14: 13; 2022-10-17: 13; 2022-10-18: 13; 2022-10-19: 13
POM02-13.02.02.04.02.01 Install Power Supply |  | 10-Aug-22 A | 2022-10-19 |  |  | 230 | 115 |  | Remaining Units | 2022-10-11: 35; 2022-10-12: 13; 2022-10-13: 13; 2022-10-14: 13; 2022-10-17: 13; 2022-10-18: 13; 2022-10-19: 13
S305000 | Magnet Power Supply Installation: Power Supply Testing | 23-Sep-22 A | 2022-10-19 | TECH3 AD | TECH3 AD | 80 | 40 | C | Remaining Units | 2022-10-12: 7; 2022-10-13: 7; 2022-10-14: 7; 2022-10-17: 7; 2022-10-18: 7; 2022-10-19: 7
S305000 | Magnet Power Supply Installation: Power Supply Testing | 23-Sep-22 A | 2022-10-19 | PROF4 AD | PROF4 AD | 80 | 40 | C | Remaining Units | 2022-10-12: 7; 2022-10-13: 7; 2022-10-14: 7; 2022-10-17: 7; 2022-10-18: 7; 2022-10-19: 7
S304700 | Magnet Power Supply Installation: Water Cooled Bus Termination 1008IR L | 10-Aug-22 A | 2022-10-11 | TECH3 AD | TECH3 AD | 70 | 35 | C | Remaining Units | 2022-10-11: 35
POM02-13.02.02.05 Magnet Field Measurements |  | 08-Mar-21 A | 2023-01-17 |  |  | 1320 | 1286 |  | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 50; 2022-10-19: 50; 2022-10-20: 50; 2022-10-21: 50; 2022-10-24: 50; 2022-10-25: 50; 2022-10-26: 50; 2022-10-27: 50; 2022-10-28: 50; 2022-10-31: 50; 2022-11-01: 58; 2022-11-02: 57; 2022-11-03: 57; 2022-11-04: 57; 2022-11-07: 57; 2022-11-08: 57; 2022-11-09: 57; 2022-11-10: 57; 2022-11-14: 57; 2022-11-15: 57; 2022-11-16: 25; 2022-11-17: 25; 2022-11-18: 25; 2022-11-21: 25; 2022-11-22: 25; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 1; 2022-12-27: 1; 2022-12-28: 1; 2022-12-29: 1; 2022-12-30: 1; 2023-01-03: 4; 2023-01-04: 4; 2023-01-05: 4; 2023-01-06: 4; 2023-01-09: 4; 2023-01-10: 4; 2023-01-11: 4; 2023-01-12: 4; 2023-01-13: 4; 2023-01-17: 4
POM02-13.02.02.05.02 Magnet Field Measurements Equipment Purchase and Fabrication |  | 01-Sep-22 A | 2023-01-17 |  |  | 112 | 98 |  | Remaining Units | 2022-10-03: 1; 2022-10-04: 1; 2022-10-05: 1; 2022-10-06: 1; 2022-10-07: 1; 2022-10-11: 1; 2022-10-12: 1; 2022-10-13: 1; 2022-10-14: 1; 2022-10-17: 1; 2022-10-18: 1; 2022-10-19: 1; 2022-10-20: 1; 2022-10-21: 1; 2022-10-24: 1; 2022-10-25: 1; 2022-10-26: 1; 2022-10-27: 1; 2022-10-28: 1; 2022-10-31: 1; 2022-11-01: 1; 2022-11-02: 1; 2022-11-03: 1; 2022-11-04: 1; 2022-11-07: 1; 2022-11-08: 1; 2022-11-09: 1; 2022-11-10: 1; 2022-11-14: 1; 2022-11-15: 1; 2022-11-16: 1; 2022-11-17: 1; 2022-11-18: 1; 2022-11-21: 1; 2022-11-22: 1; 2022-11-23: 1; 2022-11-28: 1; 2022-11-29: 1; 2022-11-30: 1; 2022-12-01: 1; 2022-12-02: 1; 2022-12-05: 1; 2022-12-06: 1; 2022-12-07: 1; 2022-12-08: 1; 2022-12-09: 1; 2022-12-12: 1; 2022-12-13: 1; 2022-12-14: 1; 2022-12-15: 1; 2022-12-16: 1; 2022-12-19: 1; 2022-12-20: 1; 2022-12-21: 1; 2022-12-22: 1; 2022-12-23: 1; 2022-12-27: 1; 2022-12-28: 1; 2022-12-29: 1; 2022-12-30: 1; 2023-01-03: 4; 2023-01-04: 4; 2023-01-05: 4; 2023-01-06: 4; 2023-01-09: 4; 2023-01-10: 4; 2023-01-11: 4; 2023-01-12: 4; 2023-01-13: 4; 2023-01-17: 4
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | SCI4 PO | SCI 4 PO | 24 | 19 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | PROF4 PO E | PROF4 PO E | 24 | 19 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0
S308617 | Calibrate probes | 01-Sep-22 A | 2022-12-30 | TECH3 PO E | TECH3 PO E | 24 | 19 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0
S308619 | Install probes and readout on TPC | 2023-01-03 | 2023-01-17 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units | 2023-01-03: 4; 2023-01-04: 4; 2023-01-05: 4; 2023-01-06: 4; 2023-01-09: 4; 2023-01-10: 4; 2023-01-11: 4; 2023-01-12: 4; 2023-01-13: 4; 2023-01-17: 4
POM02-13.02.02.05.03 Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis |  | 08-Mar-21 A | 2022-12-22 |  |  | 1208 | 1189 |  | Remaining Units | 2022-10-03: 1; 2022-10-04: 1; 2022-10-05: 1; 2022-10-06: 1; 2022-10-07: 1; 2022-10-11: 1; 2022-10-12: 1; 2022-10-13: 1; 2022-10-14: 1; 2022-10-17: 1; 2022-10-18: 49; 2022-10-19: 49; 2022-10-20: 49; 2022-10-21: 49; 2022-10-24: 49; 2022-10-25: 49; 2022-10-26: 49; 2022-10-27: 49; 2022-10-28: 49; 2022-10-31: 49; 2022-11-01: 57; 2022-11-02: 56; 2022-11-03: 56; 2022-11-04: 56; 2022-11-07: 56; 2022-11-08: 56; 2022-11-09: 56; 2022-11-10: 56; 2022-11-14: 56; 2022-11-15: 56; 2022-11-16: 24; 2022-11-17: 24; 2022-11-18: 24; 2022-11-21: 24; 2022-11-22: 24; 2022-11-23: 1; 2022-11-28: 1; 2022-11-29: 1; 2022-11-30: 1; 2022-12-01: 1; 2022-12-02: 1; 2022-12-05: 1; 2022-12-06: 1; 2022-12-07: 1; 2022-12-08: 1; 2022-12-09: 1; 2022-12-12: 1; 2022-12-13: 1; 2022-12-14: 1; 2022-12-15: 1; 2022-12-16: 1; 2022-12-19: 1; 2022-12-20: 1; 2022-12-21: 1; 2022-12-22: 1
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-10-18: 8; 2022-10-19: 8; 2022-10-20: 8; 2022-10-21: 8; 2022-10-24: 8; 2022-10-25: 8; 2022-10-26: 8; 2022-10-27: 8; 2022-10-28: 8; 2022-10-31: 8
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units | 2022-10-18: 16; 2022-10-19: 16; 2022-10-20: 16; 2022-10-21: 16; 2022-10-24: 16; 2022-10-25: 16; 2022-10-26: 16; 2022-10-27: 16; 2022-10-28: 16; 2022-10-31: 16
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units | 2022-10-18: 8; 2022-10-19: 8; 2022-10-20: 8; 2022-10-21: 8; 2022-10-24: 8; 2022-10-25: 8; 2022-10-26: 8; 2022-10-27: 8; 2022-10-28: 8; 2022-10-31: 8
S308900 | Magnet Field Measurements: Install Field Mapping Equipment | 2022-10-18 | 2022-10-31 | SCI4 PO | SCI 4 PO | 160 | 160 | C | Remaining Units | 2022-10-18: 16; 2022-10-19: 16; 2022-10-20: 16; 2022-10-21: 16; 2022-10-24: 16; 2022-10-25: 16; 2022-10-26: 16; 2022-10-27: 16; 2022-10-28: 16; 2022-10-31: 16
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-11-01: 8; 2022-11-02: 8; 2022-11-03: 8; 2022-11-04: 8; 2022-11-07: 8; 2022-11-08: 8; 2022-11-09: 8; 2022-11-10: 8; 2022-11-14: 8; 2022-11-15: 8
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | SCI4 PO | SCI 4 PO | 160 | 160 | C | Remaining Units | 2022-11-01: 16; 2022-11-02: 16; 2022-11-03: 16; 2022-11-04: 16; 2022-11-07: 16; 2022-11-08: 16; 2022-11-09: 16; 2022-11-10: 16; 2022-11-14: 16; 2022-11-15: 16
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units | 2022-11-01: 8; 2022-11-02: 8; 2022-11-03: 8; 2022-11-04: 8; 2022-11-07: 8; 2022-11-08: 8; 2022-11-09: 8; 2022-11-10: 8; 2022-11-14: 8; 2022-11-15: 8
S309000 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units | 2022-11-01: 16; 2022-11-02: 16; 2022-11-03: 16; 2022-11-04: 16; 2022-11-07: 16; 2022-11-08: 16; 2022-11-09: 16; 2022-11-10: 16; 2022-11-14: 16; 2022-11-15: 16
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 2022-11-16 | 2022-11-22 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-11-16: 8; 2022-11-17: 8; 2022-11-18: 8; 2022-11-21: 8; 2022-11-22: 8
S309100 | Magnet Field Measurements: Open poletip door Remove Field Mapping Equipment | 2022-11-16 | 2022-11-22 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units | 2022-11-16: 16; 2022-11-17: 16; 2022-11-18: 16; 2022-11-21: 16; 2022-11-22: 16
S309005 | Magnet Field Measurements: Map Magnetic Field of SC Magnet | 2022-11-01 | 2022-11-15 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units | 2022-11-01: 8; 2022-11-02: 8; 2022-11-03: 8; 2022-11-04: 8; 2022-11-07: 8; 2022-11-08: 8; 2022-11-09: 8; 2022-11-10: 8; 2022-11-14: 8; 2022-11-15: 8
S309110 | Receive report from CERN, incorporate into analysis | 2022-11-23 | 2022-12-22 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units | bar: 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-22
S308633 | Construct mapping support (mechanical and electrical) | 08-Mar-21 A | 2022-11-01 | TECH3 PO M | TECH3 PO M | 32 | 13 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31 to 2022-11-01
POM02-13.02.03 Carriage and Structural Components |  | 26-Sep-22 A | 2022-11-14 |  |  | 180 | 172 |  | Remaining Units | 2022-10-03: 7; 2022-10-04: 7; 2022-10-05: 7; 2022-10-06: 7; 2022-10-07: 7; 2022-10-11: 7; 2022-10-12: 7; 2022-10-13: 7; 2022-10-14: 7; 2022-10-17: 7; 2022-10-31: 10; 2022-11-01: 10; 2022-11-02: 10; 2022-11-03: 10; 2022-11-04: 10; 2022-11-07: 10; 2022-11-08: 10; 2022-11-09: 10; 2022-11-10: 10; 2022-11-14: 10
POM02-13.02.03.02 Inner Detector Rings and Interface to Mechanical Structural Supports |  | 26-Sep-22 A | 2022-11-14 |  |  | 180 | 172 |  | Remaining Units | 2022-10-03: 7; 2022-10-04: 7; 2022-10-05: 7; 2022-10-06: 7; 2022-10-07: 7; 2022-10-11: 7; 2022-10-12: 7; 2022-10-13: 7; 2022-10-14: 7; 2022-10-17: 7; 2022-10-31: 10; 2022-11-01: 10; 2022-11-02: 10; 2022-11-03: 10; 2022-11-04: 10; 2022-11-07: 10; 2022-11-08: 10; 2022-11-09: 10; 2022-11-10: 10; 2022-11-14: 10
S318140 | Perform TPC Supports Acceptance | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-10-31: 4; 2022-11-01: 4; 2022-11-02: 4; 2022-11-03: 4; 2022-11-04: 4; 2022-11-07: 4; 2022-11-08: 4; 2022-11-09: 4; 2022-11-10: 4; 2022-11-14: 4
S318140 | Perform TPC Supports Acceptance | 2022-10-31 | 2022-11-14 | PROF3 PO E | PROF3 PO E | 40 | 40 | C | Remaining Units | 2022-10-31: 4; 2022-11-01: 4; 2022-11-02: 4; 2022-11-03: 4; 2022-11-04: 4; 2022-11-07: 4; 2022-11-08: 4; 2022-11-09: 4; 2022-11-10: 4; 2022-11-14: 4
S318170 | Perform MBD Supports Acceptance | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 10 | 10 | C | Remaining Units | bar: 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14
S318170 | Perform MBD Supports Acceptance | 2022-10-31 | 2022-11-14 | PROF3 PO E | PROF3 PO E | 10 | 10 | C | Remaining Units | bar: 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14
S318190 | Perform Beampipe Supports Acceptance | 26-Sep-22 A | 2022-10-17 | TECH3 PO M | TECH3 PO M | 40 | 36 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4
S318190 | Perform Beampipe Supports Acceptance | 26-Sep-22 A | 2022-10-17 | PROF3 PO E | PROF3 PO E | 40 | 36 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4
POM02-13.02.04 Infrastructure |  | 15-Feb-21 A | 2023-02-09 |  |  | 3797 | 3155 |  | Remaining Units | 2022-10-03: 118; 2022-10-04: 118; 2022-10-05: 31; 2022-10-06: 31; 2022-10-07: 53; 2022-10-11: 53; 2022-10-12: 31; 2022-10-13: 31; 2022-10-14: 31; 2022-10-17: 31; 2022-10-18: 17; 2022-10-19: 17; 2022-10-20: 33; 2022-10-21: 33; 2022-10-24: 13; 2022-10-25: 13; 2022-10-26: 13; 2022-10-27: 13; 2022-10-28: 13; 2022-10-31: 13; 2022-11-01: 182; 2022-11-02: 182; 2022-11-03: 148; 2022-11-04: 148; 2022-11-07: 111; 2022-11-08: 111; 2022-11-09: 224; 2022-11-10: 224; 2022-11-14: 162; 2022-11-15: 162; 2022-11-16: 71; 2022-11-17: 71; 2022-11-18: 71; 2022-11-21: 71; 2022-11-22: 51; 2022-11-23: 51; 2022-11-28: 73; 2022-11-29: 73; 2022-11-30: 11; 2022-12-01: 11; 2022-12-02: 5; 2022-12-05: 5; 2022-12-06: 5; 2022-12-07: 5; 2022-12-08: 5; 2022-12-09: 5; 2022-12-12: 5; 2022-12-13: 5; 2022-12-14: 5; 2022-12-15: 5; 2022-12-16: 5; 2022-12-19: 5; 2022-12-20: 5; 2022-12-21: 5; 2022-12-22: 13; 2022-12-23: 13; 2022-12-27: 13; 2022-12-28: 13; 2022-12-29: 13; 2022-12-30: 13; 2023-01-03: 10; 2023-01-04: 10; 2023-01-05: 10; 2023-01-06: 10; 2023-01-09: 2; 2023-01-10: 2; 2023-01-11: 2; 2023-01-12: 2; 2023-01-13: 2; 2023-01-17: 2; 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2; 2023-01-25: 2; 2023-01-26: 2; 2023-01-27: 2; 2023-01-30: 2; 2023-01-31: 2; 2023-02-01: 2; 2023-02-02: 2; 2023-02-03: 0; 2023-02-06: 0; 2023-02-07: 0; 2023-02-08: 0; 2023-02-09: 0
POM02-13.02.04.01 Infrastructure Detector Support Systems |  | 15-Feb-21 A | 2023-02-09 |  |  | 3234 | 2693 |  | Remaining Units | 2022-10-03: 58; 2022-10-04: 58; 2022-10-05: 28; 2022-10-06: 28; 2022-10-07: 50; 2022-10-11: 50; 2022-10-12: 28; 2022-10-13: 28; 2022-10-14: 28; 2022-10-17: 28; 2022-10-18: 12; 2022-10-19: 12; 2022-10-20: 28; 2022-10-21: 28; 2022-10-24: 8; 2022-10-25: 8; 2022-10-26: 8; 2022-10-27: 8; 2022-10-28: 8; 2022-10-31: 8; 2022-11-01: 173; 2022-11-02: 173; 2022-11-03: 140; 2022-11-04: 140; 2022-11-07: 103; 2022-11-08: 103; 2022-11-09: 216; 2022-11-10: 216; 2022-11-14: 153; 2022-11-15: 153; 2022-11-16: 68; 2022-11-17: 68; 2022-11-18: 68; 2022-11-21: 68; 2022-11-22: 48; 2022-11-23: 48; 2022-11-28: 70; 2022-11-29: 70; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2; 2023-01-03: 2; 2023-01-04: 2; 2023-01-05: 2; 2023-01-06: 2; 2023-01-09: 2; 2023-01-10: 2; 2023-01-11: 2; 2023-01-12: 2; 2023-01-13: 2; 2023-01-17: 2; 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2; 2023-01-25: 2; 2023-01-26: 2; 2023-01-27: 2; 2023-01-30: 2; 2023-01-31: 2; 2023-02-01: 2; 2023-02-02: 2; 2023-02-03: 0; 2023-02-06: 0; 2023-02-07: 0; 2023-02-08: 0; 2023-02-09: 0
POM02-13.02.04.01.03 Detector Electronics Racks and Rack generic support systems |  | 13-Sep-21 A | 2022-11-10 |  |  | 780 | 546 |  | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2; 2022-11-01: 63; 2022-11-02: 63; 2022-11-03: 63; 2022-11-04: 63; 2022-11-07: 63; 2022-11-08: 63; 2022-11-09: 63; 2022-11-10: 63
S331470 | Assemble Racks for Lower East Platform | 15-Nov-21 A | 2022-10-31 | TECH3 PO E | TECH3 PO E | 80 | 6 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0
S331490 | Assemble Racks for Main Upper Platform | 13-Sep-21 A | 2022-10-31 | TECH3 PO E | TECH3 PO E | 200 | 40 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2
S331496 | ADDED RACK ASSEMBLY EFFORT, BASED ON EFFORT TO DATE | 2022-11-01 | 2022-11-10 | TECH3 PO E | TECH3 PO E | 500 | 500 | C | Remaining Units | 2022-11-01: 63; 2022-11-02: 63; 2022-11-03: 63; 2022-11-04: 63; 2022-11-07: 63; 2022-11-08: 63; 2022-11-09: 63; 2022-11-10: 63
POM02-13.02.04.01.04 Detector Gas and Cooling Services Systems |  | 15-Feb-21 A | 2023-02-09 |  |  | 2334 | 2027 |  | Remaining Units | 2022-10-03: 55; 2022-10-04: 55; 2022-10-05: 25; 2022-10-06: 25; 2022-10-07: 47; 2022-10-11: 47; 2022-10-12: 25; 2022-10-13: 25; 2022-10-14: 25; 2022-10-17: 25; 2022-10-18: 9; 2022-10-19: 9; 2022-10-20: 25; 2022-10-21: 25; 2022-10-24: 5; 2022-10-25: 5; 2022-10-26: 5; 2022-10-27: 5; 2022-10-28: 5; 2022-10-31: 5; 2022-11-01: 105; 2022-11-02: 105; 2022-11-03: 71; 2022-11-04: 71; 2022-11-07: 34; 2022-11-08: 34; 2022-11-09: 147; 2022-11-10: 147; 2022-11-14: 147; 2022-11-15: 147; 2022-11-16: 62; 2022-11-17: 62; 2022-11-18: 62; 2022-11-21: 62; 2022-11-22: 42; 2022-11-23: 42; 2022-11-28: 64; 2022-11-29: 64; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2; 2023-01-03: 2; 2023-01-04: 2; 2023-01-05: 2; 2023-01-06: 2; 2023-01-09: 2; 2023-01-10: 2; 2023-01-11: 2; 2023-01-12: 2; 2023-01-13: 2; 2023-01-17: 2; 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2; 2023-01-25: 2; 2023-01-26: 2; 2023-01-27: 2; 2023-01-30: 2; 2023-01-31: 2; 2023-02-01: 2; 2023-02-02: 2; 2023-02-03: 0; 2023-02-06: 0; 2023-02-07: 0; 2023-02-08: 0; 2023-02-09: 0
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | PROF4 PO M | PROF4 PO M | 96 | 19 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | TECH3 PO D | TECH3 PO D | 48 | 10 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 22-Jul-22 A | 2022-10-31 | PROF4 PO M | PROF4 PO M | 32 | 19 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31
S332755 | Prepare Detector Gas Services Systems Components Procurement Packages | 22-Jul-22 A | 2022-10-31 | TECH3 PO D | TECH3 PO D | 72 | 43 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 05-Sep-22 A | 2022-11-02 | PROF4 PO M | PROF4 PO M | 24 | 14 | C | Remaining Units | 2022-11-01: 7; 2022-11-02: 7
S332760 | Evaluate & Process Bids Detector Gas Services Systems Components | 05-Sep-22 A | 2022-11-02 | TECH3 PO D | TECH3 PO D | 24 | 14 | C | Remaining Units | 2022-11-01: 7; 2022-11-02: 7
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 03-Sep-22 A | 2023-02-02 | PROF4 PO M | PROF4 PO M | 96 | 58 | C | Remaining Units | bar: 2022-11-03 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30; 2023-01-03 to 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-02
S332765 | Procure & Deliver Detector Gas Services Systems Components - Labor | 03-Sep-22 A | 2023-02-02 | TECH3 PO D | TECH3 PO D | 96 | 58 | C | Remaining Units | bar: 2022-11-03 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30; 2023-01-03 to 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-02
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | PROF4 PO M | PROF4 PO M | 16 | 10 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0; 2023-01-03: 0; 2023-01-04: 0; 2023-01-05: 0; 2023-01-06: 0; 2023-01-09: 0; 2023-01-10: 0; 2023-01-11: 0; 2023-01-12: 0; 2023-01-13: 0; 2023-01-17: 0; 2023-01-18: 0; 2023-01-19: 0; 2023-01-20: 0; 2023-01-23: 0; 2023-01-24: 0; 2023-01-25: 0; 2023-01-26: 0; 2023-01-27: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 0; 2023-02-02: 0; 2023-02-03: 0; 2023-02-06: 0; 2023-02-07: 0; 2023-02-08: 0; 2023-02-09: 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | TECH3 PO D | TECH3 PO D | 16 | 10 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0; 2023-01-03: 0; 2023-01-04: 0; 2023-01-05: 0; 2023-01-06: 0; 2023-01-09: 0; 2023-01-10: 0; 2023-01-11: 0; 2023-01-12: 0; 2023-01-13: 0; 2023-01-17: 0; 2023-01-18: 0; 2023-01-19: 0; 2023-01-20: 0; 2023-01-23: 0; 2023-01-24: 0; 2023-01-25: 0; 2023-01-26: 0; 2023-01-27: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 0; 2023-02-02: 0; 2023-02-03: 0; 2023-02-06: 0; 2023-02-07: 0; 2023-02-08: 0; 2023-02-09: 0
S332781 | Design, procure, test remaining cooling system items | 2022-11-01 | 2022-11-02 | PROF3 PO E | PROF3 PO E | 100 | 100 | C | Remaining Units | 2022-11-01: 50; 2022-11-02: 50
S332781 | Design, procure, test remaining cooling system items | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-11-01: 40; 2022-11-02: 40
S332782 | Cooling System Panel Fabrication - TPC | 2022-11-03 | 2022-11-04 | PROF3 PO E | PROF3 PO E | 8 | 8 | C | Remaining Units | 2022-11-03: 4; 2022-11-04: 4
S332782 | Cooling System Panel Fabrication - TPC | 2022-11-03 | 2022-11-04 | TECH3 PO M | TECH3 PO M | 130 | 130 | C | Remaining Units | 2022-11-03: 65; 2022-11-04: 65
S332783 | Cooling System Panel Fabrication - TPot | 2022-11-07 | 2022-11-08 | PROF3 PO E | PROF3 PO E | 4 | 4 | C | Remaining Units | 2022-11-07: 2; 2022-11-08: 2
S332783 | Cooling System Panel Fabrication - TPot | 2022-11-07 | 2022-11-08 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units | 2022-11-07: 30; 2022-11-08: 30
S332784 | Cooling System Panel Fabrication - EMCal SiPM | 2022-11-09 | 2022-11-10 | TECH3 PO M | TECH3 PO M | 290 | 290 | C | Remaining Units | 2022-11-09: 145; 2022-11-10: 145
S332785 | Cooling System Panel Fabrication - EMCal PreAmp | 2022-11-14 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 290 | 290 | C | Remaining Units | 2022-11-14: 145; 2022-11-15: 145
S332786 | Cooling System Panel Fabrication - INTT ROC | 2022-11-16 | 2022-11-17 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Remaining Units | 2022-11-16: 60; 2022-11-17: 60
S332787 | Cooling System Panel Fabrication - INTT Stave | 2022-11-18 | 2022-11-21 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Remaining Units | 2022-11-18: 60; 2022-11-21: 60
S332788 | Cooling System Panel Fabrication - MVTX | 2022-11-22 | 2022-11-23 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-11-22: 40; 2022-11-23: 40
S332789 | Cooling System Platform Manifolding | 2022-11-28 | 2022-11-29 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Remaining Units | 2022-11-28: 12; 2022-11-29: 12
S332789 | Cooling System Platform Manifolding | 2022-11-28 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 100 | 100 | C | Remaining Units | 2022-11-28: 50; 2022-11-29: 50
S332790 | Gas Distribution Panel Fabrication - TPC Ar-CF4 | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 100 | 100 | C | Remaining Units | 2022-10-03: 50; 2022-10-04: 50
S332791 | Gas Distribution Panel Fabrication - TPC Laser N2 | 2022-10-05 | 2022-10-06 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-10-05: 20; 2022-10-06: 20
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 2022-10-07 | 2022-10-11 | PROF3 PO E | PROF3 PO E | 4 | 4 | C | Remaining Units | 2022-10-07: 2; 2022-10-11: 2
S332792 | Gas Distribution Panel Fabrication - Tpot Ar-Isobutane | 2022-10-07 | 2022-10-11 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-10-07: 40; 2022-10-11: 40
S332793 | Gas Distribution Panel Fabrication - EMCal SiPM N2 | 2022-10-12 | 2022-10-13 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-10-12: 20; 2022-10-13: 20
S332794 | Gas Distribution Panel Fabrication - INTT Stave N2 | 2022-10-14 | 2022-10-17 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-10-14: 20; 2022-10-17: 20
S332795 | Gas Distribution Panel Fabrication - MVTX N2 | 2022-10-18 | 2022-10-19 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | 2022-10-18: 4; 2022-10-19: 4
S332796 | Gas Distribution Panel Fabrication - MBD dry compressed air | 2022-10-20 | 2022-10-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-10-20: 20; 2022-10-21: 20
S332735 | Create Layout/Schematic Drawings & Design, Specs Control Docs, Assem. & Detail Drawings for Det Gas | 15-Feb-21 A | 2022-10-31 | TECH3 PO M | TECH3 PO M | 48 | 10 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0
S332775 | Perform Components Acceptance Detector Gas Services Systems Components | 12-Sep-22 A | 2023-02-09 | TECH3 PO M | TECH3 PO M | 8 | 5 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0; 2023-01-03: 0; 2023-01-04: 0; 2023-01-05: 0; 2023-01-06: 0; 2023-01-09: 0; 2023-01-10: 0; 2023-01-11: 0; 2023-01-12: 0; 2023-01-13: 0; 2023-01-17: 0; 2023-01-18: 0; 2023-01-19: 0; 2023-01-20: 0; 2023-01-23: 0; 2023-01-24: 0; 2023-01-25: 0; 2023-01-26: 0; 2023-01-27: 0; 2023-01-30: 0; 2023-01-31: 0; 2023-02-01: 0; 2023-02-02: 0; 2023-02-03: 0; 2023-02-06: 0; 2023-02-07: 0; 2023-02-08: 0; 2023-02-09: 0
POM02-13.02.04.01.05 Detector Safety Subsystems |  | 2022-11-01 | 2022-12-01 |  |  | 120 | 120 |  | Remaining Units | 2022-11-01: 6; 2022-11-02: 6; 2022-11-03: 6; 2022-11-04: 6; 2022-11-07: 6; 2022-11-08: 6; 2022-11-09: 6; 2022-11-10: 6; 2022-11-14: 6; 2022-11-15: 6; 2022-11-16: 6; 2022-11-17: 6; 2022-11-18: 6; 2022-11-21: 6; 2022-11-22: 6; 2022-11-23: 6; 2022-11-28: 6; 2022-11-29: 6; 2022-11-30: 6; 2022-12-01: 6
S333720 | Fabricate Detector Safety Systems | 2022-11-01 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3
S333720 | Fabricate Detector Safety Systems | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 60 | 60 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3
POM02-13.02.04.02 Infrastructure Facility Support Systems |  | 03-Sep-22 A | 2023-01-06 |  |  | 563 | 462 |  | Remaining Units | 2022-10-03: 60; 2022-10-04: 60; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4; 2022-10-18: 5; 2022-10-19: 5; 2022-10-20: 5; 2022-10-21: 5; 2022-10-24: 5; 2022-10-25: 5; 2022-10-26: 5; 2022-10-27: 5; 2022-10-28: 5; 2022-10-31: 5; 2022-11-01: 8; 2022-11-02: 8; 2022-11-03: 8; 2022-11-04: 8; 2022-11-07: 8; 2022-11-08: 8; 2022-11-09: 8; 2022-11-10: 8; 2022-11-14: 8; 2022-11-15: 8; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 11; 2022-12-23: 11; 2022-12-27: 11; 2022-12-28: 11; 2022-12-29: 11; 2022-12-30: 11; 2023-01-03: 8; 2023-01-04: 8; 2023-01-05: 8; 2023-01-06: 8
POM02-13.02.04.02.01 Magnet Cryo, Electrical & Control Structural Support in IR |  | 2022-10-03 | 2022-10-04 |  |  | 113 | 113 |  | Remaining Units | 2022-10-03: 57; 2022-10-04: 57
S277700 | 2023 Detector Support Systems L3 Project Management | 2022-10-03 | 2022-10-04 | PROF5 PO M | PROF5 PO M | 113 | 113 | C | Remaining Units | 2022-10-03: 57; 2022-10-04: 57
POM02-13.02.04.02.05 IR/AH Safety Subsystems |  | 03-Sep-22 A | 2023-01-06 |  |  | 450 | 349 |  | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4; 2022-10-18: 5; 2022-10-19: 5; 2022-10-20: 5; 2022-10-21: 5; 2022-10-24: 5; 2022-10-25: 5; 2022-10-26: 5; 2022-10-27: 5; 2022-10-28: 5; 2022-10-31: 5; 2022-11-01: 8; 2022-11-02: 8; 2022-11-03: 8; 2022-11-04: 8; 2022-11-07: 8; 2022-11-08: 8; 2022-11-09: 8; 2022-11-10: 8; 2022-11-14: 8; 2022-11-15: 8; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 11; 2022-12-23: 11; 2022-12-27: 11; 2022-12-28: 11; 2022-12-29: 11; 2022-12-30: 11; 2023-01-03: 8; 2023-01-04: 8; 2023-01-05: 8; 2023-01-06: 8
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | TECH4 AD | TECH4 AD | 24 | 12 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | TECH4 AD | TECH4 AD | 48 | 36 | C | Remaining Units | 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2; 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | TECH4 AD | TECH4 AD | 88 | 66 | C | Remaining Units | 2022-12-22: 7; 2022-12-23: 7; 2022-12-27: 7; 2022-12-28: 7; 2022-12-29: 7; 2022-12-30: 7; 2023-01-03: 7; 2023-01-04: 7; 2023-01-05: 7; 2023-01-06: 7
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | PROF2 AD | PROF2 AD | 48 | 24 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | 03-Sep-22 A | 2022-10-17 | PROF4 AD | PROF4 AD | 4 | 2 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | PROF2 AD | PROF2 AD | 96 | 72 | C | Remaining Units | 2022-10-18: 4; 2022-10-19: 4; 2022-10-20: 4; 2022-10-21: 4; 2022-10-24: 4; 2022-10-25: 4; 2022-10-26: 4; 2022-10-27: 4; 2022-10-28: 4; 2022-10-31: 4; 2022-11-01: 4; 2022-11-02: 4; 2022-11-03: 4; 2022-11-04: 4; 2022-11-07: 4; 2022-11-08: 4; 2022-11-09: 4; 2022-11-10: 4; 2022-11-14: 4; 2022-11-15: 4
S342500 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) - Labor | 18-Sep-22 A | 2022-11-15 | PROF4 AD | PROF4 AD | 2 | 2 | C | Remaining Units | 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | PROF2 AD | PROF2 AD | 16 | 12 | C | Remaining Units | bar: 2022-12-22 to 2022-12-23; 2022-12-27 to 2022-12-30; 2023-01-03 to 2023-01-06
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | 22-Sep-22 A | 2023-01-06 | PROF4 AD | PROF4 AD | 4 | 3 | C | Remaining Units | 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0; 2023-01-03: 0; 2023-01-04: 0; 2023-01-05: 0; 2023-01-06: 0
S342390 | Design IR/AH Safety Systems | 2022-11-01 | 2022-12-30 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30
S342390 | Design IR/AH Safety Systems | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
POM02-13.02.05 Integration and Installation |  | 29-Apr-21 A | 2023-03-29 |  |  | 26818 | 24414 |  | Remaining Units |  |  | 291 | 291 | 279 | 279 | 299 |  |  |  | 179 | 113 | 113 | 113 |  |  | 113 | 84 | 84 | 84 | 84 |  |  | 84 | 84 | 87 | 87 | 87 |  |  | 161 | 519 | 519 | 181 | 172 |  |  | 172 | 140 | 140 | 140 |  |  |  | 140 | 140 | 137 | 137 | 135 |  |  | 271 | 271 | 271 |  |  |  |  | 271 | 271 | 255 | 252 | 236 |  |  | 392 | 344 | 128 | 128 | 218 |  |  | 199 | 297 | 297 | 297 | 291 |  |  | 291 | 301 | 461 | 381 | 291 |  |  |  | 291 | 131 | 135 | 135 |  |  |  | 127 | 127 | 127 | 78 |  |  | 84 | 95 | 95 | 95 | 139 |  |  |  | 139 | 148 | 146 | 146 |  |  | 130 | 130 | 108 | 108 | 84 |  |  | 140 | 140 | 78 | 78 | 78 |  |  | 185 | 179 | 149 | 149 | 149 |  |  | 137 | 137 | 137 | 137 | 137 |  |  |  | 197 | 197 | 197 | 173 |  |  | 173 | 108 | 108 | 78 | 398 |  |  | 398 | 406 | 326 | 402 | 88 |  |  | 144 | 172 | 192 | 148 | 114 |  |  | 1190 | 1212 | 348 | 360 | 160 |  |  | 80 | 80 | 80
POM02-13.02.05.02 Infrastructure Installation |  | 09-Sep-21 A | 2023-02-06 |  |  | 7378 | 6303 |  | Remaining Units | 2022-10-03: 69; 2022-10-04: 69; 2022-10-05: 69; 2022-10-06: 69; 2022-10-07: 69; 2022-10-11: 69; 2022-10-12: 69; 2022-10-13: 69; 2022-10-14: 69; 2022-10-17: 69; 2022-10-18: 44; 2022-10-19: 44; 2022-10-20: 44; 2022-10-21: 44; 2022-10-24: 44; 2022-10-25: 44; 2022-10-26: 44; 2022-10-27: 44; 2022-10-28: 44; 2022-10-31: 121; 2022-11-01: 359; 2022-11-02: 359; 2022-11-03: 99; 2022-11-04: 99; 2022-11-07: 99; 2022-11-08: 99; 2022-11-09: 99; 2022-11-10: 99; 2022-11-14: 99; 2022-11-15: 99; 2022-11-16: 99; 2022-11-17: 99; 2022-11-18: 99; 2022-11-21: 99; 2022-11-22: 99; 2022-11-23: 99; 2022-11-28: 99; 2022-11-29: 99; 2022-11-30: 99; 2022-12-01: 84; 2022-12-02: 61; 2022-12-05: 61; 2022-12-06: 61; 2022-12-07: 61; 2022-12-08: 61; 2022-12-09: 61; 2022-12-12: 61; 2022-12-13: 61; 2022-12-14: 61; 2022-12-15: 61; 2022-12-16: 58; 2022-12-19: 58; 2022-12-20: 58; 2022-12-21: 58; 2022-12-22: 58; 2022-12-23: 58; 2022-12-27: 58; 2022-12-28: 58; 2022-12-29: 58; 2022-12-30: 58; 2023-01-03: 50; 2023-01-04: 50; 2023-01-05: 50; 2023-01-06: 50; 2023-01-09: 56; 2023-01-10: 56; 2023-01-11: 56; 2023-01-12: 56; 2023-01-13: 56; 2023-01-17: 56; 2023-01-18: 56; 2023-01-19: 54; 2023-01-20: 54; 2023-01-23: 58; 2023-01-24: 58; 2023-01-25: 58; 2023-01-26: 58; 2023-01-27: 58; 2023-01-30: 114; 2023-01-31: 114; 2023-02-01: 66; 2023-02-02: 66; 2023-02-03: 66; 2023-02-06: 6
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | PROF4 AD | PROF4 AD | 40 | 40 | C | Remaining Units | 2023-01-30: 8; 2023-01-31: 8; 2023-02-01: 8; 2023-02-02: 8; 2023-02-03: 8
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 AD | TECH3 AD | 104 | 104 | C | Remaining Units | 2023-01-30: 21; 2023-01-31: 21; 2023-02-01: 21; 2023-02-02: 21; 2023-02-03: 21
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | PROF2 AD | PROF2 AD | 40 | 2 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | PROF4 AD | PROF4 AD | 40 | 2 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | PROF4 AD | PROF4 AD | 16 | 12 | C | Remaining Units | bar: 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | PROF2 AD | PROF2 AD | 40 | 30 | C | Remaining Units | 2023-01-09: 2; 2023-01-10: 2; 2023-01-11: 2; 2023-01-12: 2; 2023-01-13: 2; 2023-01-17: 2; 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2; 2023-01-25: 2; 2023-01-26: 2; 2023-01-27: 2; 2023-01-30: 2; 2023-01-31: 2; 2023-02-01: 2; 2023-02-02: 2; 2023-02-03: 2; 2023-02-06: 2
S346310 | Install Beampipe Temp Support - Labor - CA-D Resource(s) | 2023-01-30 | 2023-02-03 | PROF2 AD | PROF2 AD | 80 | 80 | C | Remaining Units | 2023-01-30: 16; 2023-01-31: 16; 2023-02-01: 16; 2023-02-02: 16; 2023-02-03: 16
S346000 | Install Line Electric Power Distribution Off Detector - Labor - CA-D Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF4 AD | PROF4 AD | 32 | 3 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF4 AD | PROF4 AD | 32 | 16 | C | Remaining Units | 2022-10-31: 16
S346100 | Install Line Electric Power Distribution On Detector - Labor - CA-D Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF6 AD | PROF6 AD | 4 | 2 | C | Remaining Units | 2022-10-31: 2
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF6 AD | PROF6 AD | 4 | 0 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | TECH3 AD | TECH3 AD | 80 | 60 | C | Remaining Units | 2023-01-09: 3; 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3; 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3; 2023-01-25: 3; 2023-01-26: 3; 2023-01-27: 3; 2023-01-30: 3; 2023-01-31: 3; 2023-02-01: 3; 2023-02-02: 3; 2023-02-03: 3; 2023-02-06: 3
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | TECH3 AD | TECH3 AD | 40 | 2 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 AD | TECH3 AD | 160 | 80 | C | Remaining Units | 2022-10-03: 8; 2022-10-04: 8; 2022-10-05: 8; 2022-10-06: 8; 2022-10-07: 8; 2022-10-11: 8; 2022-10-12: 8; 2022-10-13: 8; 2022-10-14: 8; 2022-10-17: 8
S345500 | Install IR HVAC - Labor - C-AD Resources | 03-Jan-22 A | 2022-10-28 | CRAFT3 | CRAFT3 | 64 | 3 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0
S345700 | Install Off Detector Safety Subsystems inc Vesda - Labor - C-AD Resources | 01-Apr-22 A | 2023-02-06 | CRAFT3 | CRAFT3 | 24 | 18 | C | Remaining Units | bar: 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | CRAFT3 | CRAFT3 | 32 | 29 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0; 2023-01-03: 0; 2023-01-04: 0; 2023-01-05: 0; 2023-01-06: 0; 2023-01-09: 0; 2023-01-10: 0; 2023-01-11: 0; 2023-01-12: 0; 2023-01-13: 0; 2023-01-17: 0; 2023-01-18: 0
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | CRAFT3 | CRAFT3 | 80 | 40 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | CRAFT3 | CRAFT3 | 160 | 16 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 30-Aug-22 A | 2022-10-31 | CRAFT3 | CRAFT3 | 80 | 40 | C | Remaining Units | 2022-10-31: 40
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | PROF4 PO M | PROF4 PO M | 20 | 20 | C | Remaining Units | 2023-01-30: 4; 2023-01-31: 4; 2023-02-01: 4; 2023-02-02: 4; 2023-02-03: 4
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-01-30: 8; 2023-01-31: 8; 2023-02-01: 8; 2023-02-02: 8; 2023-02-03: 8
S346300 | Install Beampipe Temp Support - Labor - Physics Resource(s) | 2023-01-30 | 2023-02-03 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Remaining Units | 2023-01-30: 3; 2023-01-31: 3; 2023-02-01: 3; 2023-02-02: 3; 2023-02-03: 3
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | TECH3 PO E | TECH3 PO E | 80 | 72 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-15
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | TECH3 PO M | TECH3 PO M | 40 | 36 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-15
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | PROF4 PO E | PROF4 PO E | 20 | 18 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0
S345800 | Install On Detector Safety Subsystems - Labor | 14-Sep-22 A | 2022-12-15 | PROF4 PO M | PROF4 PO M | 20 | 18 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | PROF4 PO M | PROF4 PO M | 120 | 120 | C | Remaining Units | 2022-10-03: 3; 2022-10-04: 3; 2022-10-05: 3; 2022-10-06: 3; 2022-10-07: 3; 2022-10-11: 3; 2022-10-12: 3; 2022-10-13: 3; 2022-10-14: 3; 2022-10-17: 3; 2022-10-18: 3; 2022-10-19: 3; 2022-10-20: 3; 2022-10-21: 3; 2022-10-24: 3; 2022-10-25: 3; 2022-10-26: 3; 2022-10-27: 3; 2022-10-28: 3; 2022-10-31: 3; 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 720 | 720 | C | Remaining Units | 2022-10-03: 18; 2022-10-04: 18; 2022-10-05: 18; 2022-10-06: 18; 2022-10-07: 18; 2022-10-11: 18; 2022-10-12: 18; 2022-10-13: 18; 2022-10-14: 18; 2022-10-17: 18; 2022-10-18: 18; 2022-10-19: 18; 2022-10-20: 18; 2022-10-21: 18; 2022-10-24: 18; 2022-10-25: 18; 2022-10-26: 18; 2022-10-27: 18; 2022-10-28: 18; 2022-10-31: 18; 2022-11-01: 18; 2022-11-02: 18; 2022-11-03: 18; 2022-11-04: 18; 2022-11-07: 18; 2022-11-08: 18; 2022-11-09: 18; 2022-11-10: 18; 2022-11-14: 18; 2022-11-15: 18; 2022-11-16: 18; 2022-11-17: 18; 2022-11-18: 18; 2022-11-21: 18; 2022-11-22: 18; 2022-11-23: 18; 2022-11-28: 18; 2022-11-29: 18; 2022-11-30: 18; 2022-12-01: 18
S347400 | Install Gas and Cooling System Services - Labor | 2022-10-03 | 2022-12-01 | TECH3 PO D | TECH3 PO D | 96 | 96 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2; 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 PO E | TECH3 PO E | 80 | 40 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | TECH3 PO M | TECH3 PO M | 80 | 40 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4
S346700 | Install Non-IR Infrastructure - Labor - Physics Resource(s) | 01-Apr-22 A | 2022-10-17 | PROF4 PO E | PROF4 PO E | 80 | 40 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | PROF4 PO M | PROF4 PO M | 120 | 114 | C | Remaining Units | 2022-10-03: 3; 2022-10-04: 3; 2022-10-05: 3; 2022-10-06: 3; 2022-10-07: 3; 2022-10-11: 3; 2022-10-12: 3; 2022-10-13: 3; 2022-10-14: 3; 2022-10-17: 3; 2022-10-18: 3; 2022-10-19: 3; 2022-10-20: 3; 2022-10-21: 3; 2022-10-24: 3; 2022-10-25: 3; 2022-10-26: 3; 2022-10-27: 3; 2022-10-28: 3; 2022-10-31: 3; 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO E | TECH3 PO E | 280 | 114 | C | Remaining Units | 2022-10-03: 3; 2022-10-04: 3; 2022-10-05: 3; 2022-10-06: 3; 2022-10-07: 3; 2022-10-11: 3; 2022-10-12: 3; 2022-10-13: 3; 2022-10-14: 3; 2022-10-17: 3; 2022-10-18: 3; 2022-10-19: 3; 2022-10-20: 3; 2022-10-21: 3; 2022-10-24: 3; 2022-10-25: 3; 2022-10-26: 3; 2022-10-27: 3; 2022-10-28: 3; 2022-10-31: 3; 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO M | TECH3 PO M | 280 | 114 | C | Remaining Units | 2022-10-03: 3; 2022-10-04: 3; 2022-10-05: 3; 2022-10-06: 3; 2022-10-07: 3; 2022-10-11: 3; 2022-10-12: 3; 2022-10-13: 3; 2022-10-14: 3; 2022-10-17: 3; 2022-10-18: 3; 2022-10-19: 3; 2022-10-20: 3; 2022-10-21: 3; 2022-10-24: 3; 2022-10-25: 3; 2022-10-26: 3; 2022-10-27: 3; 2022-10-28: 3; 2022-10-31: 3; 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | TECH3 PO D | TECH3 PO D | 48 | 114 | C | Remaining Units | 2022-10-03: 3; 2022-10-04: 3; 2022-10-05: 3; 2022-10-06: 3; 2022-10-07: 3; 2022-10-11: 3; 2022-10-12: 3; 2022-10-13: 3; 2022-10-14: 3; 2022-10-17: 3; 2022-10-18: 3; 2022-10-19: 3; 2022-10-20: 3; 2022-10-21: 3; 2022-10-24: 3; 2022-10-25: 3; 2022-10-26: 3; 2022-10-27: 3; 2022-10-28: 3; 2022-10-31: 3; 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3
S347200 | Install Electronics Racks On Carriage - Labor | 01-Apr-22 A | 2022-11-30 | PROF4 PO E | PROF4 PO E | 120 | 114 | C | Remaining Units | 2022-10-03: 3; 2022-10-04: 3; 2022-10-05: 3; 2022-10-06: 3; 2022-10-07: 3; 2022-10-11: 3; 2022-10-12: 3; 2022-10-13: 3; 2022-10-14: 3; 2022-10-17: 3; 2022-10-18: 3; 2022-10-19: 3; 2022-10-20: 3; 2022-10-21: 3; 2022-10-24: 3; 2022-10-25: 3; 2022-10-26: 3; 2022-10-27: 3; 2022-10-28: 3; 2022-10-31: 3; 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | TECH3 PO M | TECH3 PO M | 80 | 72 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30; 2023-01-03 to 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-18
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | TECH3 PO D | TECH3 PO D | 16 | 14 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0; 2023-01-03: 0; 2023-01-04: 0; 2023-01-05: 0; 2023-01-06: 0; 2023-01-09: 0; 2023-01-10: 0; 2023-01-11: 0; 2023-01-12: 0; 2023-01-13: 0; 2023-01-17: 0; 2023-01-18: 0
S347700 | Install IR Electronics Cooling Water On Detector - Labor - Physics Resources | 01-Aug-22 A | 2023-01-18 | PROF4 PO E | PROF4 PO E | 20 | 18 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-27: 0; 2022-12-28: 0; 2022-12-29: 0; 2022-12-30: 0; 2023-01-03: 0; 2023-01-04: 0; 2023-01-05: 0; 2023-01-06: 0; 2023-01-09: 0; 2023-01-10: 0; 2023-01-11: 0; 2023-01-12: 0; 2023-01-13: 0; 2023-01-17: 0; 2023-01-18: 0
S1003679 | Install Line Electric Power Distribution Off Detector - Labor - Physics Resource(s) | 09-Sep-21 A | 2022-10-28 | PROF4 PO E | PROF4 PO E | 40 | 4 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0
S1003759 | Install Line Electric Power Distribution On Detector - Labor - Physics Resource(s) | 30-Aug-22 A | 2022-10-31 | PROF4 PO E | PROF4 PO E | 40 | 20 | C | Remaining Units | 2022-10-31: 20
S346298 | Build North and South work platforms | 17-Aug-22 A | 2023-01-27 | TECH3 PO M | TECH3 PO M | 30 | 21 | C | Remaining Units | 2023-01-23: 4; 2023-01-24: 4; 2023-01-25: 4; 2023-01-26: 4; 2023-01-27: 4
S346220 | Install AC power to Racks - Lower platforms | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Remaining Units | 2022-11-01: 6; 2022-11-02: 6; 2022-11-03: 6; 2022-11-04: 6; 2022-11-07: 6; 2022-11-08: 6; 2022-11-09: 6; 2022-11-10: 6; 2022-11-14: 6; 2022-11-15: 6; 2022-11-16: 6; 2022-11-17: 6; 2022-11-18: 6; 2022-11-21: 6; 2022-11-22: 6; 2022-11-23: 6; 2022-11-28: 6; 2022-11-29: 6; 2022-11-30: 6; 2022-12-01: 6
S346230 | Install AC power to Racks - Middle platforms | 2022-12-02 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Remaining Units | 2022-12-02: 6; 2022-12-05: 6; 2022-12-06: 6; 2022-12-07: 6; 2022-12-08: 6; 2022-12-09: 6; 2022-12-12: 6; 2022-12-13: 6; 2022-12-14: 6; 2022-12-15: 6; 2022-12-16: 6; 2022-12-19: 6; 2022-12-20: 6; 2022-12-21: 6; 2022-12-22: 6; 2022-12-23: 6; 2022-12-27: 6; 2022-12-28: 6; 2022-12-29: 6; 2022-12-30: 6
S346240 | Install AC power to Racks - Upper platforms | 2023-01-03 | 2023-01-31 | TECH3 PO E | TECH3 PO E | 480 | 480 | C | Remaining Units | 2023-01-03: 24; 2023-01-04: 24; 2023-01-05: 24; 2023-01-06: 24; 2023-01-09: 24; 2023-01-10: 24; 2023-01-11: 24; 2023-01-12: 24; 2023-01-13: 24; 2023-01-17: 24; 2023-01-18: 24; 2023-01-19: 24; 2023-01-20: 24; 2023-01-23: 24; 2023-01-24: 24; 2023-01-25: 24; 2023-01-26: 24; 2023-01-27: 24; 2023-01-30: 24; 2023-01-31: 24
S347610 | Off Carriage Water Lines & Flow Control - Sill & Labyrinth area | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 40; 2022-11-02: 40
S347620 | Off Carriage Water Lines & Flow Control - Chiller Platforms | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 40; 2022-11-02: 40
S347630 | Off Carriage Water - ECW to 'brass block' | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | 2022-11-01: 20; 2022-11-02: 20
S347640 | Off Carriage Water - Brass block to chillers | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-11-01: 20; 2022-11-02: 20
S347650 | Off Carriage Water - Chiller panels to cooling lines | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 40; 2022-11-02: 40
S347660 | Off Carriage Water - Bridge lines | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | 2022-11-01: 20; 2022-11-02: 20
S347670 | Off Carriage Water - Bridges to on-carriage panels | 2022-11-01 | 2022-11-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 40; 2022-11-02: 40
S347680 | Off Carriage Water - Carriage ECW to on-carriage panels | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-11-01: 40; 2022-11-02: 40
S347820 | Install Rack Cooling water - Lower platforms | 2022-11-01 | 2022-12-01 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 4; 2022-11-02: 4; 2022-11-03: 4; 2022-11-04: 4; 2022-11-07: 4; 2022-11-08: 4; 2022-11-09: 4; 2022-11-10: 4; 2022-11-14: 4; 2022-11-15: 4; 2022-11-16: 4; 2022-11-17: 4; 2022-11-18: 4; 2022-11-21: 4; 2022-11-22: 4; 2022-11-23: 4; 2022-11-28: 4; 2022-11-29: 4; 2022-11-30: 4; 2022-12-01: 4
S347830 | Install Rack Cooling water - Middle platforms | 2022-12-02 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-12-02: 4; 2022-12-05: 4; 2022-12-06: 4; 2022-12-07: 4; 2022-12-08: 4; 2022-12-09: 4; 2022-12-12: 4; 2022-12-13: 4; 2022-12-14: 4; 2022-12-15: 4; 2022-12-16: 4; 2022-12-19: 4; 2022-12-20: 4; 2022-12-21: 4; 2022-12-22: 4; 2022-12-23: 4; 2022-12-27: 4; 2022-12-28: 4; 2022-12-29: 4; 2022-12-30: 4
S347840 | Install Rack Cooling water - Upper platforms | 2023-01-03 | 2023-01-31 | TECH3 AD | TECH3 AD | 320 | 320 | C | Remaining Units | 2023-01-03: 16; 2023-01-04: 16; 2023-01-05: 16; 2023-01-06: 16; 2023-01-09: 16; 2023-01-10: 16; 2023-01-11: 16; 2023-01-12: 16; 2023-01-13: 16; 2023-01-17: 16; 2023-01-18: 16; 2023-01-19: 16; 2023-01-20: 16; 2023-01-23: 16; 2023-01-24: 16; 2023-01-25: 16; 2023-01-26: 16; 2023-01-27: 16; 2023-01-30: 16; 2023-01-31: 16
S345920 | Install Rack Protection systems - Lower platform | 2022-11-01 | 2022-12-01 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2
S345930 | Install Rack Protection systems - Middle platform | 2022-12-02 | 2022-12-30 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S345940 | Install Rack Protection systems - Upper platform | 2023-01-03 | 2023-01-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units | 2023-01-03: 8; 2023-01-04: 8; 2023-01-05: 8; 2023-01-06: 8; 2023-01-09: 8; 2023-01-10: 8; 2023-01-11: 8; 2023-01-12: 8; 2023-01-13: 8; 2023-01-17: 8; 2023-01-18: 8; 2023-01-19: 8; 2023-01-20: 8; 2023-01-23: 8; 2023-01-24: 8; 2023-01-25: 8; 2023-01-26: 8; 2023-01-27: 8; 2023-01-30: 8; 2023-01-31: 8
S346222 | Complete lighting and convenience power | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S346224 | Complete wiring of chiller platform | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30
S346226 | Complete wiring of N & S Ploe Tip doors and motors | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S346228 | Complete on-detector 24V-DC distribution system | 2022-11-01 | 2022-12-30 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30
S346228 | Complete on-detector 24V-DC distribution system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S346235 | Complete rack interlock system (36 racks) | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 160 | 160 | C | Remaining Units | 2022-11-01: 4; 2022-11-02: 4; 2022-11-03: 4; 2022-11-04: 4; 2022-11-07: 4; 2022-11-08: 4; 2022-11-09: 4; 2022-11-10: 4; 2022-11-14: 4; 2022-11-15: 4; 2022-11-16: 4; 2022-11-17: 4; 2022-11-18: 4; 2022-11-21: 4; 2022-11-22: 4; 2022-11-23: 4; 2022-11-28: 4; 2022-11-29: 4; 2022-11-30: 4; 2022-12-01: 4; 2022-12-02: 4; 2022-12-05: 4; 2022-12-06: 4; 2022-12-07: 4; 2022-12-08: 4; 2022-12-09: 4; 2022-12-12: 4; 2022-12-13: 4; 2022-12-14: 4; 2022-12-15: 4; 2022-12-16: 4; 2022-12-19: 4; 2022-12-20: 4; 2022-12-21: 4; 2022-12-22: 4; 2022-12-23: 4; 2022-12-27: 4; 2022-12-28: 4; 2022-12-29: 4; 2022-12-30: 4
S346232 | Complete global interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S346234 | Complete ODH, crash, sweeps - CAD PASS | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30
S346236 | Complete FAP and HSSP - Fire Alarm group | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30
S346238 | Complete network installation | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S346245 | Complete VESDA north/south solenoid - piping (sEPD area) | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 120 | 120 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3; 2022-12-29: 3; 2022-12-30: 3
S346242 | Complete ECW water leak detection | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S346244 | Complete contactor boxes for interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 120 | 120 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3; 2022-12-29: 3; 2022-12-30: 3
S346246 | Complete I/O terminations Rack 3B1 | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 240 | 240 | C | Remaining Units | 2022-11-01: 6; 2022-11-02: 6; 2022-11-03: 6; 2022-11-04: 6; 2022-11-07: 6; 2022-11-08: 6; 2022-11-09: 6; 2022-11-10: 6; 2022-11-14: 6; 2022-11-15: 6; 2022-11-16: 6; 2022-11-17: 6; 2022-11-18: 6; 2022-11-21: 6; 2022-11-22: 6; 2022-11-23: 6; 2022-11-28: 6; 2022-11-29: 6; 2022-11-30: 6; 2022-12-01: 6; 2022-12-02: 6; 2022-12-05: 6; 2022-12-06: 6; 2022-12-07: 6; 2022-12-08: 6; 2022-12-09: 6; 2022-12-12: 6; 2022-12-13: 6; 2022-12-14: 6; 2022-12-15: 6; 2022-12-16: 6; 2022-12-19: 6; 2022-12-20: 6; 2022-12-21: 6; 2022-12-22: 6; 2022-12-23: 6; 2022-12-27: 6; 2022-12-28: 6; 2022-12-29: 6; 2022-12-30: 6
S346248 | Test rack interlock system | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S346248 | Test rack interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30
S346250 | Test global interlock system | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 80 | 80 | C | Remaining Units | 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2; 2022-12-07: 2; 2022-12-08: 2; 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2
S346250 | Test global interlock system | 2022-11-01 | 2022-12-30 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09; 2022-12-12 to 2022-12-16; 2022-12-19 to 2022-12-23; 2022-12-27 to 2022-12-30
S356252 | Control system programming | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 120 | 120 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3; 2022-12-29: 3; 2022-12-30: 3
S356255 | Control system HMI and usage testing | 2022-11-01 | 2022-12-30 | PROF3 PO E | PROF3 PO E | 120 | 120 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3; 2022-12-29: 3; 2022-12-30: 3
S346710 | Install Non-IR Infrastructure - Labor - CA-D Resource(s) | 01-Apr-22 A | 2022-10-17 | PROF2 AD | PROF2 AD | 20 | 10 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17
POM02-13.02.05.04 Outer Hcal Installation |  | 01-Mar-22 A | 2022-12-06 |  |  | 960 | 672 |  | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-11-21: 68; 2022-11-22: 68; 2022-11-23: 68; 2022-11-28: 68; 2022-11-29: 68; 2022-11-30: 60; 2022-12-01: 60; 2022-12-02: 60; 2022-12-05: 60; 2022-12-06: 60
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | TECH3 PO M | TECH3 PO M | 80 | 11 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | TECH3 PO E | TECH3 PO E | 160 | 11 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28
S351600 | Install Outer HCal Cables and Services - Labor | 01-Mar-22 A | 2022-10-28 | PROF4 PO E | PROF4 PO E | 80 | 11 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-11-21: 4; 2022-11-22: 4; 2022-11-23: 4; 2022-11-28: 4; 2022-11-29: 4; 2022-11-30: 4; 2022-12-01: 4; 2022-12-02: 4; 2022-12-05: 4; 2022-12-06: 4
S351720 | Install OHCal gas distribution panels and route lines | 2022-11-21 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-11-21: 4; 2022-11-22: 4; 2022-11-23: 4; 2022-11-28: 4; 2022-11-29: 4; 2022-11-30: 4; 2022-12-01: 4; 2022-12-02: 4; 2022-12-05: 4; 2022-12-06: 4
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-11-21: 4; 2022-11-22: 4; 2022-11-23: 4; 2022-11-28: 4; 2022-11-29: 4; 2022-11-30: 4; 2022-12-01: 4; 2022-12-02: 4; 2022-12-05: 4; 2022-12-06: 4
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S351710 | Check OHCal operation during cabling | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S351730 | Check OHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S351740 | Check OHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
POM02-13.02.05.06 Inner Hcal Installation |  | 2022-10-03 | 2022-12-06 |  |  | 960 | 960 |  | Remaining Units | 2022-10-03: 16; 2022-10-04: 16; 2022-10-05: 16; 2022-10-06: 16; 2022-10-07: 16; 2022-10-11: 16; 2022-10-12: 16; 2022-10-13: 16; 2022-10-14: 16; 2022-10-17: 16; 2022-10-18: 16; 2022-10-19: 16; 2022-10-20: 16; 2022-10-21: 16; 2022-10-24: 16; 2022-10-25: 16; 2022-10-26: 16; 2022-10-27: 16; 2022-10-28: 16; 2022-10-31: 16; 2022-11-21: 68; 2022-11-22: 68; 2022-11-23: 68; 2022-11-28: 68; 2022-11-29: 68; 2022-11-30: 60; 2022-12-01: 60; 2022-12-02: 60; 2022-12-05: 60; 2022-12-06: 60
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4; 2022-10-18: 4; 2022-10-19: 4; 2022-10-20: 4; 2022-10-21: 4; 2022-10-24: 4; 2022-10-25: 4; 2022-10-26: 4; 2022-10-27: 4; 2022-10-28: 4; 2022-10-31: 4
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units | 2022-10-03: 8; 2022-10-04: 8; 2022-10-05: 8; 2022-10-06: 8; 2022-10-07: 8; 2022-10-11: 8; 2022-10-12: 8; 2022-10-13: 8; 2022-10-14: 8; 2022-10-17: 8; 2022-10-18: 8; 2022-10-19: 8; 2022-10-20: 8; 2022-10-21: 8; 2022-10-24: 8; 2022-10-25: 8; 2022-10-26: 8; 2022-10-27: 8; 2022-10-28: 8; 2022-10-31: 8
S356600 | Install Inner HCal Cables and Services (if instrumented) - Labor | 2022-10-03 | 2022-10-31 | PROF4 PO E | PROF4 PO E | 80 | 80 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4; 2022-10-18: 4; 2022-10-19: 4; 2022-10-20: 4; 2022-10-21: 4; 2022-10-24: 4; 2022-10-25: 4; 2022-10-26: 4; 2022-10-27: 4; 2022-10-28: 4; 2022-10-31: 4
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-11-21: 4; 2022-11-22: 4; 2022-11-23: 4; 2022-11-28: 4; 2022-11-29: 4; 2022-11-30: 4; 2022-12-01: 4; 2022-12-02: 4; 2022-12-05: 4; 2022-12-06: 4
S356720 | Install IHCal gas distribution panels and route lines | 2022-11-21 | 2022-11-29 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-11-21: 4; 2022-11-22: 4; 2022-11-23: 4; 2022-11-28: 4; 2022-11-29: 4; 2022-11-30: 4; 2022-12-01: 4; 2022-12-02: 4; 2022-12-05: 4; 2022-12-06: 4
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-11-21: 4; 2022-11-22: 4; 2022-11-23: 4; 2022-11-28: 4; 2022-11-29: 4; 2022-11-30: 4; 2022-12-01: 4; 2022-12-02: 4; 2022-12-05: 4; 2022-12-06: 4
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S356710 | Check IHCal operation during cabling | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S356730 | Check IHCal operation with slow controls (LV, bias, temp) | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
S356740 | Check IHCal operation with DAQ in counting house | 2022-11-21 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-21: 8; 2022-11-22: 8; 2022-11-23: 8; 2022-11-28: 8; 2022-11-29: 8; 2022-11-30: 8; 2022-12-01: 8; 2022-12-02: 8; 2022-12-05: 8; 2022-12-06: 8
POM02-13.02.05.07 EMCal Installation |  | 01-Jul-22 A | 2023-02-10 |  |  | 4872 | 4034 |  | Remaining Units | 2022-10-03: 67; 2022-10-04: 67; 2022-10-05: 55; 2022-10-06: 55; 2022-10-07: 75; 2022-10-11: 75; 2022-10-12: 9; 2022-10-13: 9; 2022-10-14: 9; 2022-10-17: 9; 2022-10-18: 9; 2022-10-19: 9; 2022-10-20: 9; 2022-10-21: 9; 2022-10-24: 9; 2022-10-25: 9; 2022-10-26: 9; 2022-10-27: 9; 2022-10-28: 9; 2022-10-31: 9; 2022-11-01: 121; 2022-11-02: 121; 2022-11-03: 41; 2022-11-04: 41; 2022-11-07: 41; 2022-11-08: 9; 2022-11-09: 9; 2022-11-10: 9; 2022-11-14: 9; 2022-11-15: 9; 2022-11-16: 9; 2022-11-17: 9; 2022-11-18: 9; 2022-11-21: 9; 2022-11-22: 9; 2022-11-23: 9; 2022-11-28: 9; 2022-11-29: 9; 2022-11-30: 9; 2022-12-01: 25; 2022-12-02: 33; 2022-12-05: 189; 2022-12-06: 141; 2022-12-07: 9; 2022-12-08: 9; 2022-12-09: 9; 2022-12-12: 110; 2022-12-13: 198; 2022-12-14: 198; 2022-12-15: 198; 2022-12-16: 198; 2022-12-19: 198; 2022-12-20: 198; 2022-12-21: 198; 2022-12-22: 198; 2022-12-23: 198; 2022-12-27: 198; 2022-12-28: 38; 2022-12-29: 38; 2022-12-30: 38; 2023-01-03: 38; 2023-01-04: 38; 2023-01-05: 38; 2023-01-06: 12; 2023-01-09: 12; 2023-01-10: 12; 2023-01-11: 12; 2023-01-12: 12; 2023-01-13: 12; 2023-01-17: 12; 2023-01-18: 12; 2023-01-19: 12; 2023-01-20: 12; 2023-01-23: 12; 2023-01-24: 12; 2023-01-25: 12; 2023-01-26: 12; 2023-01-27: 12; 2023-01-30: 12; 2023-01-31: 12; 2023-02-01: 12; 2023-02-02: 12; 2023-02-03: 12; 2023-02-06: 12; 2023-02-07: 12; 2023-02-08: 12; 2023-02-09: 12; 2023-02-10: 12
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH4 AD | TECH4 AD | 60 | 30 | C | Remaining Units | 2022-12-12: 30
S358200 | Transport Assembled EMCal Sectors to AH - Labor - CA-D Resource(s) | 01-Jul-22 A | 2022-12-09 | PROF4 AD | PROF4 AD | 8 | 4 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-11-14: 0; 2022-11-15: 0; 2022-11-16: 0; 2022-11-17: 0; 2022-11-18: 0; 2022-11-21: 0; 2022-11-22: 0; 2022-11-23: 0; 2022-11-28: 0; 2022-11-29: 0; 2022-11-30: 0; 2022-12-01: 0; 2022-12-02: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH3 AD | TECH3 AD | 60 | 30 | C | Remaining Units | 2022-12-12: 30
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | CRAFT3 | CRAFT3 | 320 | 320 | C | Remaining Units | 2022-12-13: 20; 2022-12-14: 20; 2022-12-15: 20; 2022-12-16: 20; 2022-12-19: 20; 2022-12-20: 20; 2022-12-21: 20; 2022-12-22: 20; 2022-12-23: 20; 2022-12-27: 20; 2022-12-28: 20; 2022-12-29: 20; 2022-12-30: 20; 2023-01-03: 20; 2023-01-04: 20; 2023-01-05: 20
S358610 | Align/Survey EMCal to SC Magnet Centerline - Labor - CA-D Resource(s) | 17-Aug-22 A | 2022-12-12 | CRAFT3 | CRAFT3 | 80 | 40 | C | Remaining Units | 2022-12-12: 40
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 01-Jul-22 A | 2022-12-09 | CRAFT3 | CRAFT3 | 120 | 53 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | PROF4 PO M | PROF4 PO M | 64 | 32 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | TECH3 PO D | TECH3 PO D | 64 | 32 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09
S358400 | Install EMCal Sectors - Labor | 01-Aug-22 A | 2022-12-09 | TECH3 PO M | TECH3 PO M | 512 | 256 | C | Remaining Units | 2022-10-03: 6; 2022-10-04: 6; 2022-10-05: 6; 2022-10-06: 6; 2022-10-07: 6; 2022-10-11: 6; 2022-10-12: 6; 2022-10-13: 6; 2022-10-14: 6; 2022-10-17: 6; 2022-10-18: 6; 2022-10-19: 6; 2022-10-20: 6; 2022-10-21: 6; 2022-10-24: 6; 2022-10-25: 6; 2022-10-26: 6; 2022-10-27: 6; 2022-10-28: 6; 2022-10-31: 6; 2022-11-01: 6; 2022-11-02: 6; 2022-11-03: 6; 2022-11-04: 6; 2022-11-07: 6; 2022-11-08: 6; 2022-11-09: 6; 2022-11-10: 6; 2022-11-14: 6; 2022-11-15: 6; 2022-11-16: 6; 2022-11-17: 6; 2022-11-18: 6; 2022-11-21: 6; 2022-11-22: 6; 2022-11-23: 6; 2022-11-28: 6; 2022-11-29: 6; 2022-11-30: 6; 2022-12-01: 6; 2022-12-02: 6; 2022-12-05: 6; 2022-12-06: 6; 2022-12-07: 6; 2022-12-08: 6; 2022-12-09: 6
S358600 | Align/Survey EMCal to SC Magnet Centerline - Labor - Physics Resource(s) | 17-Aug-22 A | 2022-12-12 | TECH3 PO M | TECH3 PO M | 20 | 10 | C | Remaining Units | 2022-12-12: 10
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO E | TECH3 PO E | 160 | 160 | C | Remaining Units | 2022-12-13: 10; 2022-12-14: 10; 2022-12-15: 10; 2022-12-16: 10; 2022-12-19: 10; 2022-12-20: 10; 2022-12-21: 10; 2022-12-22: 10; 2022-12-23: 10; 2022-12-27: 10; 2022-12-28: 10; 2022-12-29: 10; 2022-12-30: 10; 2023-01-03: 10; 2023-01-04: 10; 2023-01-05: 10
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO M | TECH3 PO M | 64 | 64 | C | Remaining Units | 2022-12-13: 4; 2022-12-14: 4; 2022-12-15: 4; 2022-12-16: 4; 2022-12-19: 4; 2022-12-20: 4; 2022-12-21: 4; 2022-12-22: 4; 2022-12-23: 4; 2022-12-27: 4; 2022-12-28: 4; 2022-12-29: 4; 2022-12-30: 4; 2023-01-03: 4; 2023-01-04: 4; 2023-01-05: 4
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | PROF4 PO M | PROF4 PO M | 32 | 32 | C | Remaining Units | 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2; 2023-01-03: 2; 2023-01-04: 2; 2023-01-05: 2
S358800 | Install EMCal Cables and Services - Labor | 2022-12-13 | 2023-01-05 | TECH3 PO D | TECH3 PO D | 32 | 32 | C | Remaining Units | 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2; 2022-12-20: 2; 2022-12-21: 2; 2022-12-22: 2; 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2; 2023-01-03: 2; 2023-01-04: 2; 2023-01-05: 2
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | SCI3 PO | SCI3 PO | 400 | 200 | C | Remaining Units | 2023-01-06: 8; 2023-01-09: 8; 2023-01-10: 8; 2023-01-11: 8; 2023-01-12: 8; 2023-01-13: 8; 2023-01-17: 8; 2023-01-18: 8; 2023-01-19: 8; 2023-01-20: 8; 2023-01-23: 8; 2023-01-24: 8; 2023-01-25: 8; 2023-01-26: 8; 2023-01-27: 8; 2023-01-30: 8; 2023-01-31: 8; 2023-02-01: 8; 2023-02-02: 8; 2023-02-03: 8; 2023-02-06: 8; 2023-02-07: 8; 2023-02-08: 8; 2023-02-09: 8; 2023-02-10: 8
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | PROF4 PO E | PROF4 PO E | 40 | 20 | C | Remaining Units | bar: 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO E | TECH3 PO E | 40 | 20 | C | Remaining Units | bar: 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | PROF4 PO M | PROF4 PO M | 40 | 20 | C | Remaining Units | bar: 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO D | TECH3 PO D | 40 | 20 | C | Remaining Units | bar: 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10
S359200 | Commission EMCal - Labor | 01-Aug-22 A | 2023-02-10 | TECH3 PO M | TECH3 PO M | 40 | 20 | C | Remaining Units | bar: 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-17 to 2023-01-20; 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10
S1003839 | Transport Assembled EMCal Sectors to AH - Labor - Physics Resource(s) | 01-Jul-22 A | 2022-12-09 | TECH3 PO M | TECH3 PO M | 64 | 28 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-09
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 2022-11-01 | 2022-11-07 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units | 2022-11-01: 16; 2022-11-02: 16; 2022-11-03: 16; 2022-11-04: 16; 2022-11-07: 16
S359402 | Install EMCal cooling panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-11-01: 40; 2022-11-02: 40
S359404 | Install EMCal gas distribution panels and route lines | 2022-11-01 | 2022-11-02 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-11-01: 40; 2022-11-02: 40
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units | 2022-12-13: 16; 2022-12-14: 16; 2022-12-15: 16; 2022-12-16: 16; 2022-12-19: 16; 2022-12-20: 16; 2022-12-21: 16; 2022-12-22: 16; 2022-12-23: 16; 2022-12-27: 16
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units | 2022-12-13: 16; 2022-12-14: 16; 2022-12-15: 16; 2022-12-16: 16; 2022-12-19: 16; 2022-12-20: 16; 2022-12-21: 16; 2022-12-22: 16; 2022-12-23: 16; 2022-12-27: 16
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | 2022-12-01: 8
S359520 | Install TPot Installation fixtures and test | 2022-10-03 | 2022-10-04 | PROF3 PO M | PROF3 PO M | 16 | 16 | C | Remaining Units | 2022-10-03: 8; 2022-10-04: 8
S359520 | Install TPot Installation fixtures and test | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2022-10-03: 10; 2022-10-04: 10
S359530 | Install TPot support system | 2022-12-02 | 2022-12-02 | PROF3 PO M | PROF3 PO M | 4 | 4 | C | Remaining Units | 2022-12-02: 4
S359530 | Install TPot support system | 2022-12-02 | 2022-12-02 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2022-12-02: 20
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | PROF3 PO M | PROF3 PO M | 4 | 4 | C | Remaining Units | 2022-10-05: 2; 2022-10-06: 2
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-10-05: 40; 2022-10-06: 40
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2022-12-05: 20
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | PROF3 PO M | PROF3 PO M | 24 | 24 | C | Remaining Units | 2022-10-07: 12; 2022-10-11: 12
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units | 2022-10-07: 40; 2022-10-11: 40
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2022-10-07: 10; 2022-10-11: 10
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Remaining Units | 2022-12-05: 8; 2022-12-06: 8
S359580 | Install TPot cooling panels and route lines | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-10-03: 20; 2022-10-04: 20
S359590 | Install TPot gas distribution panels and route lines | 2022-10-03 | 2022-10-04 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-10-03: 20; 2022-10-04: 20
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Remaining Units | 2022-12-05: 8; 2022-12-06: 8
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | SCI3 | SCI3-1 | 16 | 16 | C | Remaining Units | 2022-12-05: 8; 2022-12-06: 8
S358190 | Check EMCal sectors 24-32 prior to leaving Bldg 510 | 2022-11-01 | 2022-11-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-11-01: 16; 2022-11-02: 16; 2022-11-03: 16; 2022-11-04: 16; 2022-11-07: 16
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units | 2022-12-13: 32; 2022-12-14: 32; 2022-12-15: 32; 2022-12-16: 32; 2022-12-19: 32; 2022-12-20: 32; 2022-12-21: 32; 2022-12-22: 32; 2022-12-23: 32; 2022-12-27: 32
S359406 | Check EMCal operation with slow controls (LV, bias, temp) | 2022-12-13 | 2022-12-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 320 | 320 | C | Remaining Units | 2022-12-13: 32; 2022-12-14: 32; 2022-12-15: 32; 2022-12-16: 32; 2022-12-19: 32; 2022-12-20: 32; 2022-12-21: 32; 2022-12-22: 32; 2022-12-23: 32; 2022-12-27: 32
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units | 2022-12-13: 32; 2022-12-14: 32; 2022-12-15: 32; 2022-12-16: 32; 2022-12-19: 32; 2022-12-20: 32; 2022-12-21: 32; 2022-12-22: 32; 2022-12-23: 32; 2022-12-27: 32
S359408 | Check EMCal operation with DAQ in counting house | 2022-12-13 | 2022-12-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 320 | 320 | C | Remaining Units | 2022-12-13: 32; 2022-12-14: 32; 2022-12-15: 32; 2022-12-16: 32; 2022-12-19: 32; 2022-12-20: 32; 2022-12-21: 32; 2022-12-22: 32; 2022-12-23: 32; 2022-12-27: 32
S359510 | Transport TPot from Stony Brook to 1008 AH | 2022-12-01 | 2022-12-01 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Remaining Units | 2022-12-01: 8
S359540 | Install TPot | 2022-10-05 | 2022-10-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Remaining Units | 2022-10-05: 4; 2022-10-06: 4
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | TECH3 AD | TECH3 AD | 20 | 20 | C | Remaining Units | 2022-12-05: 20
S359550 | Align TPot | 2022-12-05 | 2022-12-05 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Remaining Units | 2022-12-05: 8
S359560 | Install TPot cables - LV, bias, signal, control | 2022-10-07 | 2022-10-11 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 8 | 8 | C | Remaining Units | 2022-10-07: 4; 2022-10-11: 4
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Remaining Units | 2022-12-05: 24; 2022-12-06: 24
S359570 | Check TPot operation during cabling | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Remaining Units | 2022-12-05: 12; 2022-12-06: 12
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Remaining Units | 2022-12-05: 24; 2022-12-06: 24
S359595 | Check TPot operation with slow controls (LV, bias, temp) | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Remaining Units | 2022-12-05: 12; 2022-12-06: 12
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 48 | 48 | C | Remaining Units | 2022-12-05: 24; 2022-12-06: 24
S359597 | Check TPot operation with DAQ in counting house | 2022-12-05 | 2022-12-06 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 24 | 24 | C | Remaining Units | 2022-12-05: 12; 2022-12-06: 12
POM02-13.02.05.08 TPC Installation |  | 03-Jan-22 A | 2023-03-06 |  |  | 3104 | 3010 |  | Remaining Units | 2022-10-03: 1; 2022-10-04: 1; 2022-10-05: 1; 2022-10-06: 1; 2022-10-07: 1; 2022-10-11: 1; 2022-10-12: 1; 2022-10-13: 1; 2022-10-14: 1; 2022-10-17: 1; 2022-10-18: 1; 2022-10-19: 1; 2022-10-20: 1; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-12-13: 10; 2022-12-14: 10; 2022-12-15: 10; 2022-12-16: 10; 2022-12-19: 10; 2022-12-20: 20; 2022-12-21: 180; 2022-12-22: 100; 2022-12-23: 20; 2022-12-27: 20; 2022-12-28: 20; 2022-12-29: 24; 2022-12-30: 24; 2023-01-03: 24; 2023-01-04: 24; 2023-01-05: 24; 2023-01-06: 1; 2023-01-09: 1; 2023-01-10: 1; 2023-01-11: 1; 2023-01-12: 1; 2023-01-13: 44; 2023-01-17: 44; 2023-01-18: 44; 2023-01-19: 44; 2023-01-20: 44; 2023-01-23: 24; 2023-01-24: 24; 2023-01-25: 24; 2023-01-26: 24; 2023-02-06: 127; 2023-02-07: 127; 2023-02-08: 127; 2023-02-09: 127; 2023-02-10: 127; 2023-02-13: 127; 2023-02-14: 127; 2023-02-15: 127; 2023-02-16: 127; 2023-02-17: 127; 2023-02-21: 127; 2023-02-22: 127; 2023-02-23: 127; 2023-02-24: 127; 2023-02-27: 127; 2023-02-28: 62; 2023-03-01: 62; 2023-03-02: 32; 2023-03-03: 32; 2023-03-06: 32
S360410 | Transport Assembled TPC Sections to AH - Labor - CA-D Resource(s) | 2022-12-13 | 2022-12-19 | PROF4 AD | PROF4 AD | 8 | 8 | C | Remaining Units | 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | TECH4 AD | TECH4 AD | 60 | 60 | C | Remaining Units | 2023-01-13: 12; 2023-01-17: 12; 2023-01-18: 12; 2023-01-19: 12; 2023-01-20: 12
S360900 | Install TPC (Mechanical) - Labor - CA-D Resource(s) | 2022-12-29 | 2023-01-12 | PROF2 AD | PROF2 AD | 8 | 8 | C | Remaining Units | bar: 2022-12-29 to 2022-12-30; 2023-01-03 to 2023-01-06; 2023-01-09 to 2023-01-12
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | TECH3 AD | TECH3 AD | 60 | 60 | C | Remaining Units | 2023-01-13: 12; 2023-01-17: 12; 2023-01-18: 12; 2023-01-19: 12; 2023-01-20: 12
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | CRAFT3 | CRAFT3 | 240 | 240 | C | Remaining Units | 2023-02-06: 16; 2023-02-07: 16; 2023-02-08: 16; 2023-02-09: 16; 2023-02-10: 16; 2023-02-13: 16; 2023-02-14: 16; 2023-02-15: 16; 2023-02-16: 16; 2023-02-17: 16; 2023-02-21: 16; 2023-02-22: 16; 2023-02-23: 16; 2023-02-24: 16; 2023-02-27: 16
S361110 | Align/Survey TPC to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-01-13 | 2023-01-20 | CRAFT3 | CRAFT3 | 80 | 80 | C | Remaining Units | 2023-01-13: 16; 2023-01-17: 16; 2023-01-18: 16; 2023-01-19: 16; 2023-01-20: 16
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | CRAFT3 | CRAFT3 | 36 | 36 | C | Remaining Units | 2022-12-29: 7; 2022-12-30: 7; 2023-01-03: 7; 2023-01-04: 7; 2023-01-05: 7
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 03-Jan-22 A | 2022-10-20 | PROF4 PO M | PROF4 PO M | 60 | 6 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0
S359700 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures - Labor | 03-Jan-22 A | 2022-10-20 | TECH3 PO D | TECH3 PO D | 20 | 2 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | PROF4 PO M | PROF4 PO M | 8 | 1 | C | Remaining Units | 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | TECH3 PO M | TECH3 PO M | 8 | 1 | C | Remaining Units | 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 25-Jan-22 A | 2022-11-02 | TECH3 PO D | TECH3 PO D | 8 | 1 | C | Remaining Units | 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | bar: 2022-11-03 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-17
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | bar: 2022-11-03 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-17
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-03 | 2022-11-17 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | bar: 2022-11-03 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-17
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Remaining Units | 2022-12-13: 5; 2022-12-14: 5; 2022-12-15: 5; 2022-12-16: 5; 2022-12-19: 5
S360400 | Transport Assembled TPC Sections to AH - Labor - Physics Resource(s) | 2022-12-13 | 2022-12-19 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Remaining Units | 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2; 2022-12-16: 2; 2022-12-19: 2
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Remaining Units | bar: 2022-12-21 to 2022-12-23; 2022-12-27 to 2022-12-28
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Remaining Units | 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3
S360700 | Install TPC Support - Labor | 2022-12-21 | 2022-12-28 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-12-21: 16; 2022-12-22: 16; 2022-12-23: 16; 2022-12-27: 16; 2022-12-28: 16
S361100 | Align/Survey TPC to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-01-13 | 2023-01-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2023-01-13: 4; 2023-01-17: 4; 2023-01-18: 4; 2023-01-19: 4; 2023-01-20: 4
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Remaining Units | 2023-02-06: 8; 2023-02-07: 8; 2023-02-08: 8; 2023-02-09: 8; 2023-02-10: 8; 2023-02-13: 8; 2023-02-14: 8; 2023-02-15: 8; 2023-02-16: 8; 2023-02-17: 8; 2023-02-21: 8; 2023-02-22: 8; 2023-02-23: 8; 2023-02-24: 8; 2023-02-27: 8
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units | 2023-02-06: 4; 2023-02-07: 4; 2023-02-08: 4; 2023-02-09: 4; 2023-02-10: 4; 2023-02-13: 4; 2023-02-14: 4; 2023-02-15: 4; 2023-02-16: 4; 2023-02-17: 4; 2023-02-21: 4; 2023-02-22: 4; 2023-02-23: 4; 2023-02-24: 4; 2023-02-27: 4
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Remaining Units | 2023-02-06: 2; 2023-02-07: 2; 2023-02-08: 2; 2023-02-09: 2; 2023-02-10: 2; 2023-02-13: 2; 2023-02-14: 2; 2023-02-15: 2; 2023-02-16: 2; 2023-02-17: 2; 2023-02-21: 2; 2023-02-22: 2; 2023-02-23: 2; 2023-02-24: 2; 2023-02-27: 2
S361300 | Install TPC Cables and Services - Labor | 2023-02-06 | 2023-02-27 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Remaining Units | 2023-02-06: 2; 2023-02-07: 2; 2023-02-08: 2; 2023-02-09: 2; 2023-02-10: 2; 2023-02-13: 2; 2023-02-14: 2; 2023-02-15: 2; 2023-02-16: 2; 2023-02-17: 2; 2023-02-21: 2; 2023-02-22: 2; 2023-02-23: 2; 2023-02-24: 2; 2023-02-27: 2
S360600 | Open SC Magnet Pole Tip Doors | 2022-12-20 | 2022-12-20 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Remaining Units | 2022-12-20: 4
S360600 | Open SC Magnet Pole Tip Doors | 2022-12-20 | 2022-12-20 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units | 2022-12-20: 16
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | PROF4 PO M | PROF4 PO M | 4 | 4 | C | Remaining Units | bar: 2022-12-29 to 2022-12-30; 2023-01-03 to 2023-01-05
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | TECH3 PO D | TECH3 PO D | 16 | 16 | C | Remaining Units | 2022-12-29: 3; 2022-12-30: 3; 2023-01-03: 3; 2023-01-04: 3; 2023-01-05: 3
S1003879 | Install TPC (Mechanical) - Labor - Physics Resource(s) | 2022-12-29 | 2023-01-05 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units | 2022-12-29: 12; 2022-12-30: 12; 2023-01-03: 12; 2023-01-04: 12; 2023-01-05: 12
S360620 | Install TPC Installation fixtures and test | 2022-12-21 | 2022-12-21 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Remaining Units | 2022-12-21: 40
S360620 | Install TPC Installation fixtures and test | 2022-12-21 | 2022-12-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-12-21: 40
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | SCI3 | SCI3-1 | 16 | 16 | C | Remaining Units | 2023-01-23: 4; 2023-01-24: 4; 2023-01-25: 4; 2023-01-26: 4
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-01-23: 10; 2023-01-24: 10; 2023-01-25: 10; 2023-01-26: 10
S361111 | Install North and South Line Lasers | 2023-01-23 | 2023-01-26 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units | 2023-01-23: 10; 2023-01-24: 10; 2023-01-25: 10; 2023-01-26: 10
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
S361440 | Install TPC cooling panels and route lines | 2022-12-21 | 2022-12-22 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-12-21: 40; 2022-12-22: 40
S361460 | Install TPC gas distribution panels and route lines | 2022-12-21 | 2022-12-22 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2022-12-21: 40; 2022-12-22: 40
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | SCI3 | SCI3-1 | 12 | 12 | C | Remaining Units | 2023-02-28: 6; 2023-03-01: 6
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Remaining Units | 2023-02-28: 12; 2023-03-01: 12
S361465 | Install TPC Diffuse Lasers | 2023-02-28 | 2023-03-01 | TECH3 PO E | TECH3 PO E | 24 | 24 | C | Remaining Units | 2023-02-28: 12; 2023-03-01: 12
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
S361950 | Erect 1008 IR Shield Wall | 2023-02-28 | 2023-03-06 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2023-02-28: 16; 2023-03-01: 16; 2023-03-02: 16; 2023-03-03: 16; 2023-03-06: 16
S361950 | Erect 1008 IR Shield Wall | 2023-02-28 | 2023-03-06 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units | 2023-02-28: 16; 2023-03-01: 16; 2023-03-02: 16; 2023-03-03: 16; 2023-03-06: 16
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
S361420 | Check TPC operation during cabling | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
S361470 | Check TPC operation with slow controls (LV, bias, temp) | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
S361480 | Check TPC operation with DAQ in counting house | 2023-02-06 | 2023-02-27 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-02-06: 11; 2023-02-07: 11; 2023-02-08: 11; 2023-02-09: 11; 2023-02-10: 11; 2023-02-13: 11; 2023-02-14: 11; 2023-02-15: 11; 2023-02-16: 11; 2023-02-17: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11
POM02-13.02.05.09 INTT Installation |  | 2022-10-03 | 2023-03-09 |  |  | 2492 | 2492 |  | Remaining Units | 2022-10-03: 6; 2022-10-04: 6; 2022-10-05: 6; 2022-10-06: 6; 2022-10-07: 6; 2022-10-11: 6; 2022-10-12: 6; 2022-10-13: 6; 2022-10-14: 6; 2022-10-17: 6; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2; 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2023-02-06: 40; 2023-02-07: 40; 2023-02-08: 10; 2023-02-09: 10; 2023-02-10: 10; 2023-02-13: 10; 2023-02-14: 10; 2023-02-15: 10; 2023-02-16: 10; 2023-02-17: 10; 2023-02-21: 70; 2023-02-22: 70; 2023-02-23: 70; 2023-02-24: 46; 2023-02-27: 46; 2023-02-28: 46; 2023-03-01: 46; 2023-03-02: 46; 2023-03-03: 366; 2023-03-06: 366; 2023-03-07: 406; 2023-03-08: 326; 2023-03-09: 326
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 AD | TECH3 AD | 60 | 60 | C | Remaining Units | 2023-02-21: 8; 2023-02-22: 8; 2023-02-23: 8; 2023-02-24: 8; 2023-02-27: 8; 2023-02-28: 8; 2023-03-01: 8; 2023-03-02: 8
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | CRAFT3 | CRAFT3 | 240 | 240 | C | Remaining Units | 2023-03-03: 48; 2023-03-06: 48; 2023-03-07: 48; 2023-03-08: 48; 2023-03-09: 48
S363410 | Align/Survey INTT to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2023-02-21: 10; 2023-02-22: 10; 2023-02-23: 10; 2023-02-24: 10; 2023-02-27: 10; 2023-02-28: 10; 2023-03-01: 10; 2023-03-02: 10
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 2022-10-03 | 2022-10-17 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Remaining Units | 2022-10-03: 4; 2022-10-04: 4; 2022-10-05: 4; 2022-10-06: 4; 2022-10-07: 4; 2022-10-11: 4; 2022-10-12: 4; 2022-10-13: 4; 2022-10-14: 4; 2022-10-17: 4
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | 2022-10-03 | 2022-10-17 | TECH3 PO D | TECH3 PO D | 20 | 20 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | bar: 2022-10-18 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | bar: 2022-10-18 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-18 | 2022-10-31 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | bar: 2022-10-18 to 2022-10-21; 2022-10-24 to 2022-10-28; 2022-10-31
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-15
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-15
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | 2022-11-01 | 2022-11-15 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | bar: 2022-11-01 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-15
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | 2023-02-06: 4; 2023-02-07: 4
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Remaining Units | 2023-02-06: 12; 2023-02-07: 12
S362800 | Transport Assembled INTT Sections to AH - Labor | 2023-02-06 | 2023-02-07 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Remaining Units | 2023-02-06: 4; 2023-02-07: 4
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | bar: 2023-02-08 to 2023-02-10; 2023-02-13 to 2023-02-17
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | bar: 2023-02-08 to 2023-02-10; 2023-02-13 to 2023-02-17
S363000 | Install INTT Support - Labor | 2023-02-08 | 2023-02-17 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units | 2023-02-08: 8; 2023-02-09: 8; 2023-02-10: 8; 2023-02-13: 8; 2023-02-14: 8; 2023-02-15: 8; 2023-02-16: 8; 2023-02-17: 8
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | bar: 2023-02-21 to 2023-02-24; 2023-02-27 to 2023-03-02
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | bar: 2023-02-21 to 2023-02-24; 2023-02-27 to 2023-03-02
S363200 | Install INTT (mechanical) - Labor | 2023-02-21 | 2023-03-02 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units | 2023-02-21: 8; 2023-02-22: 8; 2023-02-23: 8; 2023-02-24: 8; 2023-02-27: 8; 2023-02-28: 8; 2023-03-01: 8; 2023-03-02: 8
S363400 | Align/Survey INTT to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-02-21 | 2023-03-02 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2023-02-21: 3; 2023-02-22: 3; 2023-02-23: 3; 2023-02-24: 3; 2023-02-27: 3; 2023-02-28: 3; 2023-03-01: 3; 2023-03-02: 3
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO E | TECH3 PO E | 120 | 120 | C | Remaining Units | 2023-03-03: 24; 2023-03-06: 24; 2023-03-07: 24; 2023-03-08: 24; 2023-03-09: 24
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Remaining Units | 2023-03-03: 24; 2023-03-06: 24; 2023-03-07: 24; 2023-03-08: 24; 2023-03-09: 24
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Remaining Units | 2023-03-03: 5; 2023-03-06: 5; 2023-03-07: 5; 2023-03-08: 5; 2023-03-09: 5
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Remaining Units | 2023-03-03: 5; 2023-03-06: 5; 2023-03-07: 5; 2023-03-08: 5; 2023-03-09: 5
S363600 | Install INTT Cables and Services - Labor | 2023-03-03 | 2023-03-09 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Remaining Units | 2023-03-03: 5; 2023-03-06: 5; 2023-03-07: 5; 2023-03-08: 5; 2023-03-09: 5
S362920 | Install INTT Installation fixtures and test | 2023-02-06 | 2023-02-07 | PROF3 PO M | PROF3 PO M | 20 | 20 | C | Remaining Units | 2023-02-06: 10; 2023-02-07: 10
S362920 | Install INTT Installation fixtures and test | 2023-02-06 | 2023-02-07 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2023-02-06: 10; 2023-02-07: 10
S363120 | Install Beampipe | 2023-02-21 | 2023-02-21 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | 2023-02-21: 40
S363140 | Install Beampipe vacuum system | 2023-02-22 | 2023-02-22 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | 2023-02-22: 40
S363160 | Pump down beampipe | 2023-02-23 | 2023-02-23 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | 2023-02-23: 40
S363180 | Perform Beampipe Bakeout | 2023-02-24 | 2023-03-02 | TECH3 AD | TECH3 AD | 80 | 80 | C | Remaining Units | 2023-02-24: 16; 2023-02-27: 16; 2023-02-28: 16; 2023-03-01: 16; 2023-03-02: 16
S363520 | Install beampipe permanent support | 2023-03-03 | 2023-03-03 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | 2023-03-03: 40
S363540 | Remove beampipe Temporary Support | 2023-03-06 | 2023-03-06 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | 2023-03-06: 40
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-03: 8; 2023-03-06: 8; 2023-03-07: 8; 2023-03-08: 8; 2023-03-09: 8
S363740 | Install INTT cooling panels and route lines | 2023-03-07 | 2023-03-07 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-07: 40
S363760 | Install INTT gas distribution panels and route lines | 2023-03-07 | 2023-03-07 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-07: 40
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-03: 8; 2023-03-06: 8; 2023-03-07: 8; 2023-03-08: 8; 2023-03-09: 8
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-03: 32; 2023-03-06: 32; 2023-03-07: 32; 2023-03-08: 32; 2023-03-09: 32
S363720 | Check INTT operation during cabling | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-03: 32; 2023-03-06: 32; 2023-03-07: 32; 2023-03-08: 32; 2023-03-09: 32
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-03: 32; 2023-03-06: 32; 2023-03-07: 32; 2023-03-08: 32; 2023-03-09: 32
S363770 | Check INTT operation with slow controls (LV, bias, temp) | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-03: 32; 2023-03-06: 32; 2023-03-07: 32; 2023-03-08: 32; 2023-03-09: 32
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-03: 8; 2023-03-06: 8; 2023-03-07: 8; 2023-03-08: 8; 2023-03-09: 8
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-03: 32; 2023-03-06: 32; 2023-03-07: 32; 2023-03-08: 32; 2023-03-09: 32
S363780 | Check INTT operation with DAQ in counting house | 2023-03-03 | 2023-03-09 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-03: 32; 2023-03-06: 32; 2023-03-07: 32; 2023-03-08: 32; 2023-03-09: 32
POM02-13.02.05.10 MVTX Installation |  | 29-Apr-21 A | 2023-03-22 |  |  | 3422 | 3382 |  | Remaining Units | 2022-10-03: 1; 2022-10-04: 1; 2022-10-05: 1; 2022-10-06: 1; 2022-10-07: 1; 2022-10-11: 1; 2022-10-12: 1; 2022-10-13: 1; 2022-10-14: 1; 2022-10-17: 1; 2022-10-18: 1; 2022-10-19: 1; 2022-10-20: 1; 2022-10-21: 1; 2022-10-24: 1; 2022-10-25: 1; 2022-10-26: 1; 2022-10-27: 1; 2022-10-28: 1; 2022-10-31: 2; 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-09: 128; 2022-12-12: 8; 2022-12-13: 8; 2022-12-14: 8; 2022-12-15: 8; 2023-03-09: 76; 2023-03-10: 88; 2023-03-13: 128; 2023-03-14: 80; 2023-03-15: 80; 2023-03-16: 80; 2023-03-17: 30; 2023-03-20: 1058; 2023-03-21: 1204; 2023-03-22: 340
S366710 | Align/Survey MVTX to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-17 | 2023-03-20 | TECH3 AD | TECH3 AD | 40 | 40 | C | Remaining Units | 2023-03-17: 30; 2023-03-20: 10
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | CRAFT3 | CRAFT3 | 160 | 160 | C | Remaining Units | 2023-03-20: 107; 2023-03-21: 53
S365700 | Install FELIX | 2023-03-10 | 2023-03-13 | PROF3 IO E | PROF3 IO E | 16 | 16 | C | Remaining Units | 2023-03-10: 8; 2023-03-13: 8
S366000 | Install RU | 2023-03-10 | 2023-03-13 | PROF3 IO E | PROF3 IO E | 40 | 40 | C | Remaining Units | 2023-03-10: 20; 2023-03-13: 20
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | PROF4 PO M | PROF4 PO M | 40 | 10 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-28
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | TECH3 PO D | TECH3 PO D | 10 | 3 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | PROF4 PO M | PROF4 PO M | 8 | 7 | C | Remaining Units | bar: 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | TECH3 PO D | TECH3 PO D | 8 | 7 | C | Remaining Units | bar: 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 26-Jul-22 A | 2022-11-14 | TECH3 PO M | TECH3 PO M | 8 | 7 | C | Remaining Units | bar: 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | bar: 2022-11-15 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-11-30
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | bar: 2022-11-15 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-11-30
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | bar: 2022-11-15 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-11-30
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | TECH3 PO M | TECH3 PO M | 24 | 24 | C | Remaining Units | 2022-12-09: 5; 2022-12-12: 5; 2022-12-13: 5; 2022-12-14: 5; 2022-12-15: 5
S365300 | Transport Assembled MVTX Sections to IR - Labor | 2022-12-09 | 2022-12-15 | TECH3 PO E | TECH3 PO E | 8 | 8 | C | Remaining Units | 2022-12-09: 2; 2022-12-12: 2; 2022-12-13: 2; 2022-12-14: 2; 2022-12-15: 2
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | 2023-03-09: 8
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | 2023-03-09: 8
S365500 | Install MVTX Support - Labor | 2023-03-09 | 2023-03-09 | TECH3 PO M | TECH3 PO M | 60 | 60 | C | Remaining Units | 2023-03-09: 60
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2023-03-20: 53; 2023-03-21: 27
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Remaining Units | 2023-03-20: 16; 2023-03-21: 8
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO E | TECH3 PO E | 80 | 80 | C | Remaining Units | 2023-03-20: 53; 2023-03-21: 27
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | TECH3 PO D | TECH3 PO D | 24 | 24 | C | Remaining Units | 2023-03-20: 16; 2023-03-21: 8
S366900 | Install MVTX Remaining Cables and Services - Labor | 2023-03-20 | 2023-03-21 | PROF4 PO M | PROF4 PO M | 24 | 24 | C | Remaining Units | 2023-03-20: 16; 2023-03-21: 8
S365900 | Install Optical fibers | 2023-03-10 | 2023-03-13 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units | 2023-03-10: 20; 2023-03-13: 20
S366200 | Install Samtec Cables | 2023-03-10 | 2023-03-10 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units | 2023-03-10: 40
S366300 | Install Half-Barrel 1 | 2023-03-13 | 2023-03-14 | PROF3 PO M | PROF3 PO M | 80 | 80 | C | Remaining Units | 2023-03-13: 40; 2023-03-14: 40
S366300 | Install Half-Barrel 1 | 2023-03-13 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2023-03-13: 40; 2023-03-14: 40
S366500 | Install Half-Barrel 2 | 2023-03-15 | 2023-03-16 | TECH3 PO M | TECH3 PO M | 80 | 80 | C | Remaining Units | 2023-03-15: 40; 2023-03-16: 40
S366500 | Install Half-Barrel 2 | 2023-03-15 | 2023-03-16 | PROF3 PO M | PROF3 PO M | 80 | 80 | C | Remaining Units | 2023-03-15: 40; 2023-03-16: 40
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2022-12-09: 40
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-20: 13; 2023-03-21: 20; 2023-03-22: 7
S367020 | Install MVTX cooling panels and route lines | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 120 | 120 | C | Remaining Units | 2023-03-20: 80; 2023-03-21: 40
S367030 | Install MVTX gas distribution panels and route lines | 2023-03-20 | 2023-03-21 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-20: 27; 2023-03-21: 13
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-20: 13; 2023-03-21: 20; 2023-03-22: 7
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-20: 13; 2023-03-21: 20; 2023-03-22: 7
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 40 | 40 | C | Remaining Units | 2022-12-09: 40
S365450 | Install MVTX Installation fixtures and test | 2022-12-09 | 2022-12-09 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 40 | 40 | C | Remaining Units | 2022-12-09: 40
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units | 2023-03-20: 107; 2023-03-21: 160; 2023-03-22: 53
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-20: 53; 2023-03-21: 80; 2023-03-22: 27
S367010 | Check MVTX operation during cabling | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-20: 53; 2023-03-21: 80; 2023-03-22: 27
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units | 2023-03-20: 107; 2023-03-21: 160; 2023-03-22: 53
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-20: 53; 2023-03-21: 80; 2023-03-22: 27
S367040 | Check MVTX operation with slow controls (LV, bias, temp) | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-20: 53; 2023-03-21: 80; 2023-03-22: 27
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 320 | 320 | C | Remaining Units | 2023-03-20: 107; 2023-03-21: 160; 2023-03-22: 53
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | TECH3 Other - Unpaid | TECH3 Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-20: 53; 2023-03-21: 80; 2023-03-22: 27
S367050 | Check MVTX operation with DAQ in counting house | 2023-03-20 | 2023-03-22 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-20: 53; 2023-03-21: 80; 2023-03-22: 27
POM02-13.02.05.11 Min Bias Installation |  | 29-Apr-21 A | 2023-03-29 |  |  | 2038 | 1968 |  | Remaining Units | 2022-10-03: 122; 2022-10-04: 122; 2022-10-05: 122; 2022-10-06: 122; 2022-10-07: 122; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 5; 2022-10-27: 5; 2022-10-28: 5; 2022-10-31: 2; 2022-11-01: 2; 2022-11-02: 2; 2022-11-03: 2; 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2023-03-13: 16; 2023-03-14: 92; 2023-03-15: 112; 2023-03-16: 68; 2023-03-17: 84; 2023-03-20: 132; 2023-03-21: 8; 2023-03-22: 8; 2023-03-23: 360; 2023-03-24: 160; 2023-03-27: 80; 2023-03-28: 80; 2023-03-29: 80
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-16 | 2023-03-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2023-03-16: 8; 2023-03-17: 8; 2023-03-20: 4
S370180 | Align sEPD | 2023-03-17 | 2023-03-17 | TECH3 AD | TECH3 AD | 20 | 20 | C | Remaining Units | 2023-03-17: 20
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | TECH3 PO E | TECH3 PO E | 20 | 20 | C | Remaining Units | 2023-03-20: 20
S369110 | Align/Survey Min Bias to SC Magnet Centerline - Labor - CA-D Resource(s) | 2023-03-16 | 2023-03-17 | TECH3 AD | TECH3 AD | 20 | 20 | C | Remaining Units | 2023-03-16: 12; 2023-03-17: 8
S369460 | Install MBD cooling panels and route lines | 2023-03-24 | 2023-03-24 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-24: 40
S369470 | Install MBD gas distribution panels and route lines | 2023-03-24 | 2023-03-24 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-24: 40
S370105 | Install MBD cooling panels and route lines | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-14: 40
S370120 | Install sEPD Installation fixtures and test | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-15: 40
S370140 | Install sEPD support system | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-15: 40
S370160 | Install sEPD | 2023-03-16 | 2023-03-16 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-16: 40
S370180 | Align sEPD | 2023-03-17 | 2023-03-17 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-17: 40
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2023-03-20: 20
S369450 | Check MBD operation during cabling | 2023-03-23 | 2023-03-23 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-23: 40
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 2023-03-23 | 2023-03-29 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-23: 8; 2023-03-24: 8; 2023-03-27: 8; 2023-03-28: 8; 2023-03-29: 8
S369490 | Check MBD operation with DAQ in counting house | 2023-03-23 | 2023-03-29 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2023-03-23: 8; 2023-03-24: 8; 2023-03-27: 8; 2023-03-28: 8; 2023-03-29: 8
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-10-03: 8; 2022-10-04: 8; 2022-10-05: 8; 2022-10-06: 8; 2022-10-07: 8
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-10-03: 8; 2022-10-04: 8; 2022-10-05: 8; 2022-10-06: 8; 2022-10-07: 8
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 | SCI3-1 | 40 | 40 | C | Remaining Units | 2022-10-03: 8; 2022-10-04: 8; 2022-10-05: 8; 2022-10-06: 8; 2022-10-07: 8
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | PROF4 PO M | PROF4 PO M | 30 | 15 | C | Remaining Units | bar: 2022-10-03 to 2022-10-07; 2022-10-11 to 2022-10-14; 2022-10-17 to 2022-10-21; 2022-10-24 to 2022-10-25
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | TECH3 PO D | TECH3 PO D | 10 | 5 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0
S367800 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures - Labor | 01-Jul-22 A | 2022-10-25 | TECH3 PO M | TECH3 PO M | 10 | 5 | C | Remaining Units | 2022-10-03: 0; 2022-10-04: 0; 2022-10-05: 0; 2022-10-06: 0; 2022-10-07: 0; 2022-10-11: 0; 2022-10-12: 0; 2022-10-13: 0; 2022-10-14: 0; 2022-10-17: 0; 2022-10-18: 0; 2022-10-19: 0; 2022-10-20: 0; 2022-10-21: 0; 2022-10-24: 0; 2022-10-25: 0
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | PROF4 PO M | PROF4 PO M | 40 | 10 | C | Remaining Units | 2022-10-26: 3; 2022-10-27: 3; 2022-10-28: 3
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | 29-Apr-21 A | 2022-10-28 | TECH3 PO D | TECH3 PO D | 20 | 5 | C | Remaining Units | 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | bar: 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | bar: 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | 2022-10-31 | 2022-11-14 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | bar: 2022-10-31 to 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | bar: 2022-11-15 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-11-30
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | bar: 2022-11-15 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-11-30
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | 2022-11-15 | 2022-11-30 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | bar: 2022-11-15 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-11-30
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 2023-03-13 | 2023-03-13 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | 2023-03-13: 8
S368500 | Transport Assembled Min Bias Sections to AH - Labor | 2023-03-13 | 2023-03-13 | TECH3 PO M | TECH3 PO M | 8 | 8 | C | Remaining Units | 2023-03-13: 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | 2023-03-14: 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | 2023-03-14: 8
S368700 | Install Min Bias Support - Labor | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units | 2023-03-14: 16
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | 2023-03-15: 8
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | TECH3 PO D | TECH3 PO D | 8 | 8 | C | Remaining Units | 2023-03-15: 8
S368900 | Install Min Bias (mechanical) - Labor | 2023-03-15 | 2023-03-15 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units | 2023-03-15: 16
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-03-16 | 2023-03-22 | TECH3 PO M | TECH3 PO M | 20 | 20 | C | Remaining Units | 2023-03-16: 4; 2023-03-17: 4; 2023-03-20: 4; 2023-03-21: 4; 2023-03-22: 4
S369300 | Install Min Bias Cables and Services - Labor | 2023-03-23 | 2023-03-23 | TECH3 PO E | TECH3 PO E | 40 | 40 | C | Remaining Units | 2023-03-23: 40
S368650 | Install MBD Installation fixtures and test | 2023-03-14 | 2023-03-14 | PROF3 PO M | PROF3 PO M | 10 | 10 | C | Remaining Units | 2023-03-14: 10
S368650 | Install MBD Installation fixtures and test | 2023-03-14 | 2023-03-14 | TECH3 PO M | TECH3 PO M | 10 | 10 | C | Remaining Units | 2023-03-14: 10
S369300 | Install Min Bias Cables and Services - Labor | 2023-03-23 | 2023-03-23 | TECH3 PO M | TECH3 PO M | 40 | 40 | C | Remaining Units | 2023-03-23: 40
S369100 | Align/Survey Min Bias to SC Magnet Centerline - Labor - Physics Resource(s) | 2023-03-16 | 2023-03-22 | TECH3 AD | TECH3 AD | 20 | 20 | C | Remaining Units | 2023-03-16: 4; 2023-03-17: 4; 2023-03-20: 4; 2023-03-21: 4; 2023-03-22: 4
S369450 | Check MBD operation during cabling | 2023-03-23 | 2023-03-23 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-23: 160
S369480 | Check MBD operation with slow controls (LV, bias, temp) | 2023-03-23 | 2023-03-29 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-23: 32; 2023-03-24: 32; 2023-03-27: 32; 2023-03-28: 32; 2023-03-29: 32
S369490 | Check MBD operation with DAQ in counting house | 2023-03-23 | 2023-03-29 | STUDENT Other - Unpaid | STUDENT Other - Unpaid | 160 | 160 | C | Remaining Units | 2023-03-23: 32; 2023-03-24: 32; 2023-03-27: 32; 2023-03-28: 32; 2023-03-29: 32
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 40 | 40 | C | Remaining Units | 2023-03-20: 40
S370205 | Install sEPD cables - LV, bias, signal, control | 2023-03-20 | 2023-03-20 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 40 | 40 | C | Remaining Units | 2023-03-20: 40
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-10-03: 16; 2022-10-04: 16; 2022-10-05: 16; 2022-10-06: 16; 2022-10-07: 16
S370220 | Check sEPD operation during cabling | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-10-03: 16; 2022-10-04: 16; 2022-10-05: 16; 2022-10-06: 16; 2022-10-07: 16
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-10-03: 16; 2022-10-04: 16; 2022-10-05: 16; 2022-10-06: 16; 2022-10-07: 16
S370240 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-10-03: 16; 2022-10-04: 16; 2022-10-05: 16; 2022-10-06: 16; 2022-10-07: 16
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | SCI3 Other - Unpaid | SCI3 Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-10-03: 16; 2022-10-04: 16; 2022-10-05: 16; 2022-10-06: 16; 2022-10-07: 16
S370260 | Check sEPD operation with slow controls (LV, bias, temp) | 2022-10-03 | 2022-10-07 | POSTDOC Other - Unpaid | POSTDOC Other - Unpaid | 80 | 80 | C | Remaining Units | 2022-10-03: 16; 2022-10-04: 16; 2022-10-05: 16; 2022-10-06: 16; 2022-10-07: 16
POM02-13.02.05.12 Full System Integration and ORR |  | 2022-10-03 | 2023-01-31 |  |  | 1592 | 1592 |  | Remaining Units | 2022-10-03: 8; 2022-10-04: 8; 2022-10-05: 8; 2022-10-06: 8; 2022-10-07: 8; 2022-10-11: 8; 2022-10-12: 8; 2022-10-13: 8; 2022-10-14: 8; 2022-10-17: 8; 2022-10-18: 8; 2022-10-19: 8; 2022-10-20: 8; 2022-10-21: 8; 2022-10-24: 8; 2022-10-25: 8; 2022-10-26: 8; 2022-10-27: 8; 2022-10-28: 8; 2022-10-31: 8; 2022-11-01: 32; 2022-11-02: 32; 2022-11-03: 32; 2022-11-04: 23; 2022-11-07: 23; 2022-11-08: 23; 2022-11-09: 23; 2022-11-10: 23; 2022-11-14: 23; 2022-11-15: 23; 2022-11-16: 23; 2022-11-17: 23; 2022-11-18: 23; 2022-11-21: 23; 2022-11-22: 23; 2022-11-23: 23; 2022-11-28: 23; 2022-11-29: 23; 2022-11-30: 23; 2022-12-01: 23; 2022-12-02: 23; 2022-12-05: 23; 2022-12-06: 23; 2022-12-07: 59; 2022-12-08: 59; 2022-12-09: 20; 2022-12-12: 20; 2022-12-13: 20; 2022-12-14: 20; 2022-12-15: 20; 2022-12-16: 25; 2022-12-19: 25; 2022-12-20: 25; 2022-12-21: 25; 2022-12-22: 25; 2022-12-23: 15; 2022-12-27: 15; 2022-12-28: 15; 2022-12-29: 15; 2022-12-30: 15; 2023-01-03: 15; 2023-01-04: 15; 2023-01-05: 15; 2023-01-06: 15; 2023-01-09: 15; 2023-01-10: 27; 2023-01-11: 27; 2023-01-12: 27; 2023-01-13: 27; 2023-01-17: 27; 2023-01-18: 36; 2023-01-19: 36; 2023-01-20: 36; 2023-01-23: 36; 2023-01-24: 36; 2023-01-25: 14; 2023-01-26: 14; 2023-01-27: 14; 2023-01-30: 14; 2023-01-31: 14
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF5 AD | PROF5 AD | 20 | 20 | C | Remaining Units | bar: 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-06
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF5 AD | PROF5 AD | 16 | 16 | C | Remaining Units | 2022-12-07: 8; 2022-12-08: 8
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | PROF5 AD | PROF5 AD | 16 | 16 | C | Remaining Units | 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | PROF5 AD | PROF5 AD | 16 | 16 | C | Remaining Units | 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2; 2023-01-03: 2; 2023-01-04: 2; 2023-01-05: 2; 2023-01-06: 2; 2023-01-09: 2
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 AD | PROF4 AD | 8 | 8 | C | Remaining Units | 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 AD | PROF4 AD | 8 | 8 | C | Remaining Units | 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | PROF6 AD | PROF6 AD | 16 | 16 | C | Remaining Units | 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | PROF6 AD | PROF6 AD | 16 | 16 | C | Remaining Units | 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2; 2023-01-03: 2; 2023-01-04: 2; 2023-01-05: 2; 2023-01-06: 2; 2023-01-09: 2
S370540 | Magnet Checkout After Power Testing | 2022-12-09 | 2022-12-15 | SCI3 AD | SCI3 AD | 16 | 16 | C | Remaining Units | 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3
S370560 | Preparation for Full Operation - Magnet Re-check Cryo/PSU/QD/ODH Check | 2022-12-23 | 2023-01-09 | SCI3 AD | SCI3 AD | 16 | 16 | C | Remaining Units | 2022-12-23: 2; 2022-12-27: 2; 2022-12-28: 2; 2022-12-29: 2; 2022-12-30: 2; 2023-01-03: 2; 2023-01-04: 2; 2023-01-05: 2; 2023-01-06: 2; 2023-01-09: 2
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI3 AD | SCI3 AD | 8 | 8 | C | Remaining Units | 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF6 AD | PROF6 AD | 20 | 20 | C | Remaining Units | bar: 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-06
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF2 AD | PROF2 AD | 20 | 20 | C | Remaining Units | bar: 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-06
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 AD | PROF4 AD | 20 | 20 | C | Remaining Units | bar: 2022-11-04; 2022-11-07 to 2022-11-10; 2022-11-14 to 2022-11-18; 2022-11-21 to 2022-11-23; 2022-11-28 to 2022-12-02; 2022-12-05 to 2022-12-06
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF6 AD | PROF6 AD | 16 | 16 | C | Remaining Units | 2022-12-07: 8; 2022-12-08: 8
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF6 AD | PROF6 AD | 8 | 8 | C | Remaining Units | 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | PROF4 PO E | PROF4 PO E | 8 | 8 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 PO E | PROF4 PO E | 40 | 40 | C | Remaining Units | 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | PROF4 PO E | PROF4 PO E | 40 | 40 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | SCI3 PO | SCI3 PO | 40 | 40 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2
S370500 | Prepare for Review of Safety System Design by CAD ESRC | 2022-10-03 | 2022-10-31 | SCI4 PO | SCI 4 PO | 40 | 40 | C | Remaining Units | 2022-10-03: 2; 2022-10-04: 2; 2022-10-05: 2; 2022-10-06: 2; 2022-10-07: 2; 2022-10-11: 2; 2022-10-12: 2; 2022-10-13: 2; 2022-10-14: 2; 2022-10-17: 2; 2022-10-18: 2; 2022-10-19: 2; 2022-10-20: 2; 2022-10-21: 2; 2022-10-24: 2; 2022-10-25: 2; 2022-10-26: 2; 2022-10-27: 2; 2022-10-28: 2; 2022-10-31: 2
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | PROF4 PO M | PROF4 PO M | 8 | 8 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | SCI4 PO | SCI 4 PO | 24 | 24 | C | Remaining Units | 2022-11-01: 8; 2022-11-02: 8; 2022-11-03: 8
S370510 | Review of Safety System Design by CAD ESRC | 2022-11-01 | 2022-11-03 | SCI3 PO | SCI3 PO | 24 | 24 | C | Remaining Units | 2022-11-01: 8; 2022-11-02: 8; 2022-11-03: 8
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | PROF4 PO M | PROF4 PO M | 40 | 40 | C | Remaining Units | 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | SCI3 PO | SCI3 PO | 40 | 40 | C | Remaining Units | 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2
S370520 | Prepare Procedures (Blue Sheet, Pink Sheet) | 2022-11-04 | 2022-12-06 | SCI4 PO | SCI 4 PO | 40 | 40 | C | Remaining Units | 2022-11-04: 2; 2022-11-07: 2; 2022-11-08: 2; 2022-11-09: 2; 2022-11-10: 2; 2022-11-14: 2; 2022-11-15: 2; 2022-11-16: 2; 2022-11-17: 2; 2022-11-18: 2; 2022-11-21: 2; 2022-11-22: 2; 2022-11-23: 2; 2022-11-28: 2; 2022-11-29: 2; 2022-11-30: 2; 2022-12-01: 2; 2022-12-02: 2; 2022-12-05: 2; 2022-12-06: 2
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Remaining Units | 2022-12-07: 8; 2022-12-08: 8
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Remaining Units | 2022-12-07: 8; 2022-12-08: 8
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | SCI3 PO | SCI3 PO | 16 | 16 | C | Remaining Units | 2022-12-07: 8; 2022-12-08: 8
S370530 | Review and approve procedures | 2022-12-07 | 2022-12-08 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units | 2022-12-07: 8; 2022-12-08: 8
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | TECH3 PO E | TECH3 PO E | 24 | 24 | C | Remaining Units | 2022-12-16: 5; 2022-12-19: 5; 2022-12-20: 5; 2022-12-21: 5; 2022-12-22: 5
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | PROF4 PO E | PROF4 PO E | 24 | 24 | C | Remaining Units | 2022-12-16: 5; 2022-12-19: 5; 2022-12-20: 5; 2022-12-21: 5; 2022-12-22: 5
S370550 | Preparation for Full Operation - In-Rack Safety System Check | 2022-12-16 | 2022-12-22 | SCI4 PO | SCI 4 PO | 24 | 24 | C | Remaining Units | 2022-12-16: 5; 2022-12-19: 5; 2022-12-20: 5; 2022-12-21: 5; 2022-12-22: 5
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Remaining Units | 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | TECH3 PO E | TECH3 PO E | 16 | 16 | C | Remaining Units | 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units | 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Remaining Units | 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3
S370570 | Preparation for Full Operation - Verify Global Safety System | 2023-01-10 | 2023-01-17 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units | 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 PO M | PROF4 PO M | 16 | 16 | C | Remaining Units | 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | TECH3 PO E | TECH3 PO E | 16 | 16 | C | Remaining Units | 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | TECH3 PO M | TECH3 PO M | 16 | 16 | C | Remaining Units | 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | PROF4 PO E | PROF4 PO E | 16 | 16 | C | Remaining Units | 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units | 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3
S370580 | Preparation for Full Operation - Final Safety Walk Trough | 2023-01-18 | 2023-01-24 | SCI3 PO | SCI3 PO | 16 | 16 | C | Remaining Units | 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3
S370590 | Preparation for Full Operation - Approvals - CAD and Physics | 2023-01-25 | 2023-01-31 | SCI4 PO | SCI 4 PO | 16 | 16 | C | Remaining Units | 2023-01-25: 3; 2023-01-26: 3; 2023-01-27: 3; 2023-01-30: 3; 2023-01-31: 3
S370595 | Prepare for sPHENIX IRR | 2022-11-01 | 2023-01-31 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3; 2022-12-29: 3; 2022-12-30: 3; 2023-01-03: 3; 2023-01-04: 3; 2023-01-05: 3; 2023-01-06: 3; 2023-01-09: 3; 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3; 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3; 2023-01-25: 3; 2023-01-26: 3; 2023-01-27: 3; 2023-01-30: 3; 2023-01-31: 3
S370595 | Prepare for sPHENIX IRR | 2022-11-01 | 2023-01-31 | PROF3 PO M | PROF3 PO M | 160 | 160 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3; 2022-12-29: 3; 2022-12-30: 3; 2023-01-03: 3; 2023-01-04: 3; 2023-01-05: 3; 2023-01-06: 3; 2023-01-09: 3; 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3; 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3; 2023-01-25: 3; 2023-01-26: 3; 2023-01-27: 3; 2023-01-30: 3; 2023-01-31: 3
S370597 | Prepare for sPHENIX ARR | 2022-11-01 | 2023-01-31 | PROF3 PO M | PROF3 PO M | 160 | 160 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3; 2022-12-29: 3; 2022-12-30: 3; 2023-01-03: 3; 2023-01-04: 3; 2023-01-05: 3; 2023-01-06: 3; 2023-01-09: 3; 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3; 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3; 2023-01-25: 3; 2023-01-26: 3; 2023-01-27: 3; 2023-01-30: 3; 2023-01-31: 3
S370597 | Prepare for sPHENIX ARR | 2022-11-01 | 2023-01-31 | SCI3 | SCI3-1 | 160 | 160 | C | Remaining Units | 2022-11-01: 3; 2022-11-02: 3; 2022-11-03: 3; 2022-11-04: 3; 2022-11-07: 3; 2022-11-08: 3; 2022-11-09: 3; 2022-11-10: 3; 2022-11-14: 3; 2022-11-15: 3; 2022-11-16: 3; 2022-11-17: 3; 2022-11-18: 3; 2022-11-21: 3; 2022-11-22: 3; 2022-11-23: 3; 2022-11-28: 3; 2022-11-29: 3; 2022-11-30: 3; 2022-12-01: 3; 2022-12-02: 3; 2022-12-05: 3; 2022-12-06: 3; 2022-12-07: 3; 2022-12-08: 3; 2022-12-09: 3; 2022-12-12: 3; 2022-12-13: 3; 2022-12-14: 3; 2022-12-15: 3; 2022-12-16: 3; 2022-12-19: 3; 2022-12-20: 3; 2022-12-21: 3; 2022-12-22: 3; 2022-12-23: 3; 2022-12-27: 3; 2022-12-28: 3; 2022-12-29: 3; 2022-12-30: 3; 2023-01-03: 3; 2023-01-04: 3; 2023-01-05: 3; 2023-01-06: 3; 2023-01-09: 3; 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 3; 2023-01-13: 3; 2023-01-17: 3; 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3; 2023-01-25: 3; 2023-01-26: 3; 2023-01-27: 3; 2023-01-30: 3; 2023-01-31: 3