## Slide 1
Development of HRPPDs for EIC:
Status update
A. Lyashenko (on behalf of Incom Inc.)

## Slide 2
Task | 2023 |  |  |  |  |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
0. Project Management |  |  |  |  |  |  |  |  |  |  |  | 
Window to Ceramic Sealing (60% complete) |  |  |  |  |  |  |  |  |  |  |  | 
Anode Design and Fabrication (50% complete) |  |  |  |  |  |  |  |  |  |  |  | 
Internal Connections (80% complete) |  |  |  |  |  |  |  |  |  |  |  | 
Internal Components Design and Procurement (80% complete) |  |  |  |  |  |  |  |  |  |  |  | 
Readout Board Design (50% complete) |  |  |  |  |  |  |  |  |  |  |  | 
Tile Performance/Process Optimization (50% complete) |  |  |  |  |  |  |  |  |  |  |  | 
BNL/EIC Tile Test Plans |  |  |  |  |  |  |  |  |  |  |  | 
Fabricate 5 HRPPDs for EIC delivery |  |  |  |  |  |  |  |  |  |  |  | 
Schedule
now

## Slide 3
Task 1: window to ceramic seal
60% complete
Responsible Individuals: A. Lyashenko
Ceramic metallization for reliable indium wetting
Performing 3 sealing trials to verify sealing

## Slide 4
HRPPD9
LTA: Ceramic, 0.229”
MCPs: CJ17936001-004 / CJ17936001-003 (10um, C14)
Spacers: square
Window: 5mm FS
Anode: Resistive
Photocathode: Na-K-Sb
Sealed, but Indium alloy leaked in
No photocathode discoloration after two weeks

## Slide 5
Task 1 Summary
Metallization figured out
Backup options available
Three sealing trials planned; one completed
Two other trials will be completed by end of May

## Slide 6
Task 2: Anode Design and Fabrication
50% complete (see talk by A. Kiselev)
Responsible Individuals: A. Lyashenko, M. Popecki, A. Kiselev
Design of LTCC anode
Fabrication of a test anode (3”x3” form factor)
Fabrication of a full size anode

## Slide 7
Two Test Anodes Fabricated
Electrical integrity verified
Trace capacitance have been measured to be within 10pF

## Slide 8
Task 3: Internal Connections
80% complete
Responsible Individuals: A. Lyashenko
Improving reliability of internal connections
Getting rid of compression springs
Brazing contacts directly onto the anode plate
Test connections in a sealed device

## Slide 9
Brazed Contacts

## Slide 10
Ceramic HRPPD packages
Capacitively Coupled
Directly Coupled

## Slide 11
HRPPD9 (sealing trial)
No Springs
Spot-welded MCP contact electrodes to brazed contacts
Gapped MCPs

## Slide 12
Task 3 Summary
Brazed contacts seem reliable
Will be tested on Techtra anodes in June 2023

## Slide 13
Task 4: Internal Components Design and Procurement
80% complete
Responsible Individuals: A. Lyashenko, D. Mensah, M. Foley
Design of internal stack components for 75% OAR including spacers, shims, getter connections
Ordering components from a third party vendor

## Slide 14
104 mm
100 mm
75% active area fraction
69% active area fraction
HRPPD active area
Present design
Thinner Spacers

## Slide 15
75% OAR components
HRPPD active area

## Slide 16
Task 4 Summary
Internal components ordered; expected delivery mid-May 2023

## Slide 17
Task 5: Readout Board Design and Procurement
50% complete (see talk by A. Kiselev)
Responsible Individuals: A. Kiselev, M. Popecki, A.Lyashenko
Design and Fabrication of PCB board to connect with LTCC anode
Connectivity options

## Slide 18
Task 6: Tile Performance / Process optimization
50% complete
Responsible Individuals: A.Lyashenko
Photocathode optimization
Tilablity
Gapped MCPs

## Slide 19
Photocathode development
Goal: Shift QE max to longer wavelengths
Na2KSb

## Slide 20
Rb-K-Cs-Sb photocathode trials
Na2KSb
Rb-K-Cs-Sb

## Slide 21
Photocathode: Summary
Several Rb-K-Cs-Sb Trials Performed
Underlayer to improve Sb quality
Thermal noise reduction

## Slide 22
Tilability
Tilable capacitively coupled anode (75% OAR)

## Slide 23
Gapped MCPs
Realized in the new HRPPD package

## Slide 24
Summary
HRPPD SBIR grant is ending on May 2
Most tasks are on schedule
Manufacturing of first tiles for EIC will start in August