## Slide 1
Lucas Brouwer (for the modeling working group team)
3/21/2023
MDP modeling working group: current status of R&D and upcoming milestones

## Slide 2
A wide range of modeling is performed across all areas of US-MDP program, our update focuses on the work described in the updated 2020 roadmap
from 2020 US-MDP Updated Roadmaps: https://arxiv.org/abs/2011.09539

## Slide 3: Overarching thrusts: (1) connect interfaces to training, (2) hybrid magnet behavior, (3) advanced simulation of HTS
from 2020 US-MDP Updated Roadmaps: https://arxiv.org/abs/2011.09539
(1) connect interfaces to training
(3) advanced simulation of HTS
(2) hybrid magnet behavior

## Slide 4: Takeaway: great progress on interfaces and HTS, delay in hybrid modeling correlated with slip in planned testing
(1) connect interfaces to training
(3) advanced simulation of HTS
(2) hybrid magnet behavior
Hybrid modeling is likely to be an area of growing effort next year, requires close coordination with other working groups
AIIIb-M6 | Design and optimization of quench protection systems for planned hybrid tests in the Nb3Sn and HTS roadmaps | March, 2023 | Preliminary work
AIIIb-M4 | Benchmarking of new codes with existing hybrid magnet test data | October, 2023 | Preliminary work
Milestone # | Description | Target | Status
AIIIb-M5 | Report correlating interface modeling results with experimental magnet training and summarizing desired interface conditions for stress managed designs | July, 2022 | Publication being prepared
AIIIb-M11 | Training modeling with debonding elements | December, 2022 | Complete
AIIIb-M12 | Advanced material model for Nb3Sn coils | March, 2023 | Complete
AIIIb-M13 | Integration of advanced contact elements in SMCT mechanical models | May, 2023 | In progress
AIIIb-M14 | Extension of novel thin shell mixed finite element formulations for modeling current sharing and quench in HTS cables in 2D | November, 2022 | Almost complete
AIIIb-M15 | Extension of novel thin shell mixed finite element formulations for modeling current sharing and quench in HTS cables in 3D | May, 2023 | In progress
AIIIb-M10 | Creation of a finite element multiphysics toolbox tailored to HTS cable modeling needs shared within the US-MDP community | March, 2024 | Pending