## Milestones
Training Reduction Milestones
Milestone # | Description | Target |  | Updated Target | Requestor | Comments
AI-M1a | Development and test of stress management concept using a 2-layer large-aperture and 4-layer small-aperture cos-theta coils and dipole mirror structure. | 2022-03-01 | In progress | 2022-12-30 | A. Zlobin
AI-M2a | Development, fabrication and test of stress management concept in a 2-layer 120-mm dipole with the field up to 11 T. | 2023-04-01 | In progress | 2023-12-30 | A. Zlobin
AI-M3a | Assembly and test of stress-management concept in a 4-layer 60-mm 17 T dipole with stress management. | 2024-04-01 | Not started | 2024-08-30 | A. Zlobin
Milestones for the Canted-Cosine-Theta (CCT) effort within the Nb3Sn area of the MDP
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
AI-M1b | Improve numerical modeling of magnet mechanics to accurately predict stresses when surface failure/delamination can occur. | 2020-12-01
AI-M2b | Use CCT subscale program to increase understanding and improve training in stress managed magnets. | 2021-07-01
AI-M3b | Design of CCT6 4-layer magnet with target field of 13 T and bore diameter of 120 mm (with feedback from desired diameter from HTS components of MDP). Design of CCT6 will profit from feedback provided by subscale testing and improved modeling methods. | 2022-01-01
AI-M4b | Fabrication and test of CCT6 4-layer CCT magnet. | 2023-06-01
Milestones for the CCT effort within the Bi-2212 area of the MDP
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
AIIa-M1a | Build and test two 2.4 T, 40 cm long BIN5c dipole magnets. | Dec 2020 and March 2021 | Completed |  | T. Shen | BIN5c1 magnet tested. BIN5c2 coils fabricated (but not tested) and are backup for the Alla-M2a.
AIIa-M2a | Hybrid magnet test with a total field generation of 8-10 T at 4.2 K. Assemble and test BIN5c in the background field of the Nb3Sn CCT5 | 2021-12-01 | In progress | 2022-12-01 | T. Shen | Modify description to "Hybrid magnet test with a total field generation of 8-10 T at 4.2 K. Assemble and test BIN5c inside the 90 mm bore Nb3Sn CCT5 magnet."
AIIa-M3a | Build and test two 3.5 T, 80 cm long, Bi-2212 dipole magnet with 17-strand, 7.8 mm wide Rutherford cables. | July 2021 and Jan 2022 | In progress | 2023-Feb and 2025-Oct | T. Shen | Modify description to "Build and test two Bi-CCT1, a 3.5 T, 40 mm bore, 85 cm long CCT Bi-2212 dipole magnets with 17-strand, 7.8 mm wide Rutherford cables made from 0.8 mm strands."
AIIa-M4a | Build and test two 5 T, 80 cm long, Bi-2212 dipole magnet with 27-strand, 12 mm wide Rutherford cables. | July 2022 and Jan 2023 | In progress | 2024-02-01 | T. Shen | Modify description to "Build and test one Bi-CCT2, a 5 T, 40-50 mm bore, 85 cm long Bi-2212 CCT dipole magnet with 12 mm wide Rutherford cables made from 1.0 mm strands." Note that only one magnet is going to be built.
AIIa-M5a | Hybrid magnet test with a total field generation of >14.5 T at 4.2 K. Assemble and test magnets from AI-M3c and M4c inside a background field of the 120 mm, 11 T Nb3Sn magnet from the area I. | 2023-09-01 | Not started | 2026-02-01 | T. Shen | Modify description to "Hybrid magnet test with a total field generation of 11-15 T at 4.2 K. Assemble and test Bi-CCT1 inside the 120 mm bore, >11 T Nb3Sn magnet from the area I."
Milestones for the Stress-Managed Cosine-Theta (SMCT) effort within the Bi-2212 area of the MDP
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
AIIa-M1b | Study strand damages due to cabling, transverse pressure dependence | 2022-04-01 | Not started | n/a | A.Zlobin, E. Barzi | Remove
AIIa-M2b | Fabricate the first 2-layer 17-mm aperture Bi-2212 coil using LBNL cable. Coil test independently and inside a 60-mm aperture 2-layer Nb3Sn dipole coil in mirror configuration. | 2022-07-01 | In progress | 2023-06-30 | A. Zlobin | Modify to: "Design and fabricate the first 2-layer 17-mm small-aperture Bi-2212 coil using LBNL cable. Coil test independently and inside a 60-mm aperture 2-layer Nb3Sn dipole coil in mirror configuration."
AIIa-M3b | Fabricate the 2nd 2-layer 17-mm aperture Bi-2212 coil using optimized Bi-2212 cable, coil structure, materials and technologies. Coil test independently and inside a 60-mm aperture 4-layer Nb3Sn dipole coil in mirror configuration. | 2022-12-01 | Not started | 2024-03-30 | A. Zlobin | Modify to: "Design and fabricate the 2nd 2-layer 17-mm small-aperture Bi-2212 coil using optimized Bi-2212 cable, coil structure, materials and technologies. Coil test independently and inside a 60-mm aperture 4-layer Nb3Sn dipole coil in mirror configuration. "
AIIa-M4b | Fabricate another 2-layer Bi-2212 coil using optimized Bi-2212 cable and coil structure. Bi-2212 coil test independently and inside a 60-mm aperture 4-layer Nb3Sn dipole coil. | 2024-09-01 | Not started | 2024-12-30 | A. Zlobin | Modify to:"Fabricate another 2-layer small-aperture Bi-2212 coil using optimized Bi-2212 cable and coil structure. Bi-2212 coil test independently and inside a 60-mm aperture 4-layer Nb3Sn dipole coil.
Milestones for OPHT facility upgrade and Rutherford-cable-based solenoid development
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
AIIa-M1c | Renegade OPHT facility upgrade. 1 m and 250 mm hot zone. | 2020-12-01
AIIa-M2c | 16 T Rutherford cable based solenoid development | 2020-12-01
AIIa-M3c | 20 T Rutherford cable based solenoid development | 2021-06-01
AIIa-M4c | 25 T Rutherford cable based solenoid development | 2022-06-01
Milestones for the REBCO effort within the HTS area of the MDP
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
Magnet technology development
AIIb-M1 | Test of CORC® subscale common coil in 10 T background field | 2021-06-01 | In progress | 2022-12-01 | Ramesh Gupta | Delays due to covid related and ACT winding coil to the updated design
AIIb-M2 | Demonstrate first COMB (Conductor on Molded Barrel) technology | 2021-09-01 | In progress | 2022-12-22 | V. Kashikhin | Delay due to vendor testing of conductor re-lubrication to determine bending degradation in stainless-steel COMB structure and the way to proceed for the first demonstration model.
AIIb-M3 | CORC® CCT to reach 5 T dipole field | 2021-12-01 | In progress | 2023-12-01 | X. Wang | We are about to make the 3-turn version. Conductor delivery for c3 is making very good progress. Hopefully we can have it by the end of 2022. Then it may take a year to make c3 as a conservative estimate. Can take longer if senior technical staff is not around.
AIIb-M4 | Complete design study of a 8 T REBCO dipole magnet | 2021-12-01 | In progress | 2022-12-22 | X. Wang | We are getting more steam on this front to get it done.
AIIb-M5 | Complete COMB insert test | 2022-05-01 | Not started | 2022-06-23 | V. Kashikhin | This milestone is a successor to AIIb-M2.
AIIb-M6 | Generate 1 T with REBCO insert in a background field of 8 T from Nb3Sn CCT5 | 2022-06-01 | Not started | 6 months after the test facility is upgraded | X. Wang | STAR conductor can become a driver for the REBCO insert. Therefore we may need more results from the STAR technology to push the insert forward. This can take some time, depending on how fast we can learn on the STAR route.
AIIb-M7 | COMB performance demonstration | 2023-03-01 |  | 2024-03-15 | V. Kashikhin | Need to receive "high-performance" REBCO cable to start this task.
AIIb-M8 | REBCO magnet generate a 8 T dipole field stand-alone | 2023-03-01 | Not started | 2025-03-01 | X. Wang | Need the design first (Allb-M4), then order the conductor, make a subscale, followed by the the full-scale version
Conductor characterization
AIIb-M9 | CORC® wire quench study at BNL 10 T common coil magnet | 2020-12-01 | Incorporated in AIIb-M1 | 2022-12-22 | Ramesh Gupta | This task is combined with and incorporated in Task AIIb-M1
AIIb-M10 | Impact of Lorentz load on CORC® wires using ASC 14 T solenoid | 2021-06-01 | Obsolete |  | X. Wang | Let's remove this milestone. Insufficient interest and resource.
Key assumptions: infrastructure availability
AIIb-M11 | Commission Nb3Sn CCT5 test platform | 2021-06-01
AIIb-M12 | 120 mm aperture 10 – 12 T Nb3Sn magnet | 2022-06-01
AIIb-M13 | Hybrid test platform with outsert magnet available at FNAL | 2022-12-01
Milestones for the 20 T hybrid magnet design and comparative analysis effort within the Technology area of the MDP
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
AIIIa-M1 | Review previous work on hybrid magnets, and identify the design and comparison criteria. In addition, perform preliminary designs through analytical models. | 2021-07-01 | Completed
AIIIa-M2 | Perform 2D finite element models to study the different design options, focusing on magnetic, mechanical and quench protection studies | 2021-11-01 |  | 2022-11-22 | P. Ferracin
AIIIa-M3 | Comparison analysis, including considerations about fabrication, cost, integration and testing | 2023-01-01 |  | 2022-01-24 | P. Ferracin
Milestones for the Advanced Modeling effort within the Technology area of the MDP
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
AIIIb-M1 | Identification and/or development of advanced finite element techniques for mechanical interfaces (such as cohesive zone elements) | 2021-05-01 | Complete |  | Giorgio Vallone | both 2D and 3D are completed
AIIIb-M2 | Extension of existing codes to model HTS quench behavior and magnetization as required for hybrid magnet protection studies | 2021-05-01 | Obselete |  | Lucas Brouwer | This milestone is captured by AIIIb-M6
AIIIb-M3 | Integration of advanced contact elements in existing CCT and SMCT mechanical models | 2021-06-01 | Complete |  | Giorgio Vallone | SMCT task is moved to a new milestone (AIIIb-M13)
AIIIb-M4 | Benchmarking of new codes with existing hybrid magnet test data | 2021-09-01 | Not started | 2023-10-01 | Lucas Brouwer | Shift due to delay in planned hybrid testing
AIIIb-M5 | Report correlating interface modeling results with experimental magnet training and summarizing desired interface conditions for stress managed designs | 2021-12-01 | In progress | 2022-07-22 | Giorgio Vallone | Paper being prepared
AIIIb-M6 | Design and optimization of quench protection systems for planned hybrid tests in the Nb3Sn and HTS roadmaps | 2022-05-01 | In progress | 2023-03-01 | Lucas Brouwer | Shift due to delay in planned hybrid testing
AIIIb-M7 | Efficient parallelization of new and existing HTS codes to leverage DOE high-performance computing resources | 2022-12-01 | Obselete |  | Chrisitan Messe | see updated milestones M14-15
AIIIb-M8 | Application of multi-scale, mechanical strain studies to refine strain-based conductor limitations from the strand to magnet level for both Nb3Sn and HTS designs | 2023-12-23 | Obselete |  |  | replace by AIIIb-M12
AIIIb-M9 | Development of new methods for modeling of HTS which leverage advanced numerical techniques such as adaptive meshing and unfitted finite element methods (such as XFEM) | 2023-03-01 | Obselete |  | Chrisitan Messe | see updated milestones M14-15
AIIIb-M10 | Creation of a hierarchical, multiphysics toolbox for HTS cable modeling with increasing levels of complexity and computational requirements (from equivalent circuit models to finite element techniques) | 2023-03-01 |  | 2024-03-01 | Chrisitan Messe | please modify to: "Creation of a finite element multiphysics toolbox tailored to HTS cable modeling needs shared within the US-MDP community"
AIIIb-M11 | Training modeling with debonding elements | N/A | In progress | 2022-12-22 | Giorgio Vallone | new milestone
AIIIb-M12 | Advanced material model for Nb3Sn coils | N/A | In progress | 2023-03-22 | Giorgio Vallone | new milestone
AIIIb-M13 | Integration of advanced contact elements in SMCT mechanical models | N/A | Not started | 2023-05-22 | Giorgio Vallone | new milestone
AIIIb-M14 | Extension of novel thin shell mixed finite element formulations for modeling current sharing and quench in HTS cables in 2D | N/A | In progress | 2022-11-01 | Chrisitan Messe | new milestone
AIIIb-M15 | Extension of novel thin shell mixed finite element formulations for modeling current sharing and quench in HTS cables in 3D | N/A | Not started | 2023-05-01 | Chrisitan Messe | new milestone
Near term milestones for the Magnet Materials section. The focus initially is on novel impregnation resins and on interface treatment
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
AIIIc-M1 | Demonstration of High Viscosity (Thermoplastic) Resin Systems for Superconducting Magnets | 2021-06-01
AIIIc -M2 | Down-selection and Fabrication of CCT based on the above | 2021-11-01
AIIIc -M3 | Evaluation of surface treatments and interface modification | 2021-12-01
AIIIc -M4 | Test of a CCT implementing interface modifications | 2022-07-01
Near term milestones for the Novel Diagnostics section
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
AIIId-M1 | Development of a new generation of self-calibrating acoustic emission diagnostics hardware | 2020-12-01 | Completed |  | M. Marchevsky
AIIId-M2 | Finalizing software algorithms for acoustic data analysis, completing analysis for the CCTs and 15T dipole | 2020-12-01 | Completed |  | M. Marchevsky
AIIId-M3 | Development and test of a linear quench localization sensor on a Bi-2212 subscale and/or ReBCO CCT series | 2021-03-01 | Obsolete / modified |  | M. Marchevsky
AIIId-M3ab | Development and implementation of non-optical distributed sensing for cables and magnets RF TDR-based techniques Ultrasonic waveguide-based techniques | 2022-03-23 | In progress |  | M. Marchevsky / G.S. Lee
AIIId-M4 | Test of a large-scale Hall array and imaging current distribution in HTS tape stacks and coils | 2021-05-01 | Completed
AIIId-M5 | Completing spot heater studies to improve voltage-based diagnostics and address “silent” quenches | 2022-07-21 | Not started | 2022-07-23 | S. Stoynev | No initial agreement on goals (no support); scope changed, agreement reached
AIIId-M5a | Development and comissioning of a dedicated V-I measurement system (multichannel nanovoltmeter) for superconducting magnets | Jan-00 | In progress | 2022-03-23 | S. Stoynev | AIIId-M7
AIIId-M6 | Demonstration of inverse acoustics-based probing of interfaces in a dedicated small-scale coil | 2021-09-01 | Modified
AIIId-M6a | Demonstration of acoustics-based probing of coil interfaces | 2022-09-21 | Not started | 2022-12-23 | M. Marchevsky
AIIId-M7 | Development of multi-element and flexible quench antennas and localization of quenches using flexible quench antenna arrays | 2021-09-30 | Completed |  | S. Stoynev/J. DiMarco
AIIId-M7a | Characterization of different quench antenna designs for use in superconducting devices |  | In progress | 2022-01-23 | S. Stoynev/J. DiMarco | extended studies
AIIId-M7b | Development of a flexible ‘sinusoid-shaped’ quench antenna, which would have loops everywhere parallel to the CCT conductor. |  | Not started | 2022-09-23 | J. DiMarco/R. Teyber | extended goals
AIIId-M8 | Characterization of training-like behavior in different impregnation materials under load using a Transverse Pressure Insert (TPI) measurement system | 2022-12-21 | In progress | n/a | E. Barzi
AIIId-M9 | Development and test of a standalone acoustic quench detection and localization FPGA-based system | 2021-12-01
AIIId-M10 | Development and test of a non-rotating new magnetic probe prototype | 2022-12-21 | Not started | 2022-12-23 | M. Marchevsky / J. DiMarco
AIIId-M11 | Demonstration of a programmable fully-cryogenic FPGA “smart” sensor core with digital readout and analog front-end (SQUID) amplifiers | 2021-12-01 | Modified
AIIId-M11a | Demonstration of a programmable fully-cryogenic FPGA “smart” sensor core with digital readout | 2022-12-21 | In progress | Jan-23 | M. Turqueti
AIIId-M12 | Calibration of FBG fibers in a small cryostat. Installation on an MDP magnet and strain measurement during a quench. Design a proof of principle experiment for quench 3D spatial detection and coil azimuthal strain mapping and install fiber on MDP magnet. Use fibers for energy spectrum analysis and HTS quench detection. | 2022-12-01 | Modified |  | M. Baldini
AIIId-M12a | Calibration of FBG fibers in a small cryostat (2021) Installation of fibers on an MDP magnet and strain measurement during a quench. Modification of magnet test facility top plate to accommodate fiber line (2021) Design a proof of principle experiment for quench detection: Small coil fabrication and tests (March 2023) Energy spectrum analysis (Dec 2023) Coil azimuthal strain mapping: Experiment on coil ten stacks sample made with different epoxy (March 2023) Install distributed fiber on a mirror magnet for coil strain map (Dec 2022) | Dec-22 | In progress | 2022-12-23 | M. Baldini
AIIId-M13 | Develop quality control capabilities to identify defects and performance limiting regions in REBCO cables and accelerator magnets |  | In progress | 2022-11-23 | R. Teyber | Direct feedback to HTS/CORC magnet development
AIIId-M14 | Advance numerical and experimental abilities to monitor and predict current distributions in ReBCO cables for accelerator magnets |  | In progress | 2022-03-24 | R. Teyber | Seek to exploit recent FES research progress in HEP magnets
Near term milestones for the Training Reduction subsection within the Technology area
AIIIe-M1 | Commissioning of QCD | 2021-05-01 | Done |  | S. Stoynev
AIIIe-M2 | First Ultrasound based test | 2021-05-01 | Obsolete |  | S. Stoynev | It should be retired (removed), it is not a viable option anymore
AIIIe-M3 | First high-Cp cable fabrication | 2021-09-01 | Not started | n/a | E. Barzi | Target dates cannot be provided without allocated resources
AIIIe-M4 | First magnet test with QCD | 2021-09-01 | Done |  | S. Stoynev
AIIIe-M5 | Results from High-Cp cable studies | 2021-12-01 | In progress | n/a | E. Barzi | Target dates cannot be provided without allocated resources
AIIIe-M6 | Optimized strand and cable FEM simulations | 2021-12-01 | Not started | n/a | E. Barzi | Target dates cannot be provided without allocated resources
AIIIe-M7 | First CCT test with QCD | 2022-02-01 | In progress | 2023-09-01 | S. Stoynev | It depends on agreements with LBNL (discussions started)
AIIIe-M8 | High-Cp wire and tape optimized versions | 2022-05-01 | Obsolete |  | S. Stoynev | We have split this milestone (in 2022)
AIIIe-M8a | High-Cp wire optimized versions | 2022-05-01 | In progress | 2023-09-30 | X. Xu | Delay due to COVID-related factors
AIIIe-M8b | High-Cp tape optimized versions | 2022-05-01 | In progress | n/a | E. Barzi | Target dates cannot be provided without allocated resources
AIIIe-M9 | Fabrication of first coil with High-Cp conductor | 2022-09-01 | Not started | n/a | X. Xu | Schedule is hard to predict as it involves many efforts from collaborators, e.g., cabling, coil fabrication, etc.
AIIIe-M10 | Design of a dedicated device/technique using vibrational methods | 2022-09-01 | In progress | 2024-09-01 | S. Stoynev | Activities started but at minimum involvement of a junor engineer (we could split the milestone into smaller ones)
AIIIe-M11 | Design of a “cable/stack” testing device and samples | 2023-01-01 | Obsolete |  | S. Stoynev | See the new Milestone
AIIIe-M12 | QCD preparations and test on a large magnet | 2023-02-01 | Obsolete |  | S. Stoynev | It should be retired (removed), it is not a realistic option anymore
AIIIe-M13 | Fabrication of a “cable/stack” testing device | 2023-09-01 | Obsolete |  | S. Stoynev | See the new Milestone
AIIIe-M13a | Design and fabrication of a “cable/stack” testing device |  | Not started | 2025-04-01 | S. Stoynev | I am taking an advice to combine design and fabrication, given that there is nothing immenent happening (no resources/support)
Near term milestones for the development of Bi-2212 wires
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
CPRD-Bi-2212-1 | Develop production-like specifications, quality-control methods, and quality assurance. QC methods may need assistance of University programs. | 2021 | in progress | unknown | L. Cooley | University programs are engaged with BOST. Production specifications deemed to be unreasonable until powder specifications and QC is established. Present lack of quantititative powder information is given highest priority attention.
CPRD-Bi-2212-2 | Achieve consistent longer pieces, stable critical current, and consistent overall production in larger billets | 2023 20 kg billets | not started | unknown | L. Cooley | Powder supplied in 2 kg batches, so 5 batches per 10 kg billet. Powder scale-up will not take place until questions related to powder are resolved.
|  | 2025 50 kg billets | see above
CPRD-Bi-2212-3 | Facilitate innovations and improvements | As needed
Near term milestones for the development of advanced Nb3Sn wires
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
CPRD-Nb3Sn-1 | Transfer of LDRD, ECRA, and University research ideas to development scale proposals at major industries. | 2021(better 2022?), contingent on alloy availability | in progress | 2022 | L. Cooley | LTSW 2022 discussions urged the procurement of conductor from SBIR and similar output to begin virtuous cycle of development. CPRD funds allocated in 2022 for this purpose.
CPRD-Nb3Sn-2 | Scale successful industry development to production level | 2023 half billets | in progress | 2023 | L. Cooley | B-OST revised their proposal to scale Ta-Hf technology to half billets, to be supported 2022.
|  | 2025 full billets |  |  | L. Cooley
CPRD-Nb3Sn-3 | Facilitate combined approaches at development level | 2022 and beyond | in progress |  | L. Cooley | CPRD discussions with vendors requested quotations for single and combined innovations. Funds will be awarded depending on proposal quality.
Near term milestones for the development of REBCO wires and cables
Milestone # | Description | Target | Status * | Updated Target | Requestor | Comments
CPRD-REBCO-1 | Address coated conductor and cable aspects that improve flexibility and bend tolerance in CCT magnets, e.g. by addition of a lubricant with low inter-conductor resistance | 2021 | not completed | n/a | L. Cooley | Contact resistance was found to depend more upon contacting area than lubrication. PbSn-coated conductor was found to greatly increase contacting area.
CPRD-REBCO-2 | Achieve consistent cross-section and longer pieces, in the present thin, narrow configuration, to facilitate longer cables | 2022 | in progress | 2022 | L. Cooley | C3 cable from ACT will have improved characteristics if acceptable conductor is provided.
CPRD-REBCO-3 | Adapt pinning additives to needs at 4 K and high field in isotropic cables, such as by addition of Y2O3 nanodots instead of BaZrO3 nanorods. | 2023 | in progress | Unknown; delayed by Russia-Ukraine conflict and embargo against SuperOx | L. Cooley | ASC group is in discussion with suppliers
*Status
Done
In progress
Not started
Obsolete