## Slide 1: EIC Project Update
Elke Aschenauer and Rolf Ent
Co-Associate Directors for the Experimental Program
ePIC General Meeting
May 11th 2023

## Slide 2: CD-2/3A Planning Dates
DOE OPA Status Review October 19-21, 2021(A)
FPD Status Update at BNL June 28, 29, 30 2022(A)
Technical, Cost, and Schedule Scrutiny Meeting July – Sept 2022 (A)
Project, Detector & Infrastructure Advisory Meeting October 2022(A)
DOE OPA Status Review Jan. 31-Feb 2, 2023(A)
Project Advisory Meeting February 22, 23 2023(A)
Infrastructure Advisory Meeting March 22, 23 2023(A)
1st RRB Meeting April 4,5 2023 (A)
Begin LLP EVMS (practice 3 months data) July 2023
CD-3A Director’s Review (Co-Chaired by M. Reichanadter / S. Cousineau) October 10-12, 2023
DOE CD 3A OPA Review November 2023
DOE CD 3A ESAAB Approval January 2024
Final Design Reviews for all ePIC subsystems April – October 2024
DOE CD 2/3 OPA Review and ICR January 2025 (TBC)
DOE CD 2/3 ESAAB Approval April 2025
RHIC Operations Concludes June 2025
The project Machine and Detector Advisory Committees will perform design assessments in Late Summer.

## Slide 3: What we are doing this Summer
REVIEWS REVIEWS REVIEWS REVIEWS
EIC Project ePIC Engineering Workshop May 10-12, 2023, at BNL/Zoom
EIC Cost Review-June 26-29, 2023
EIC AB Meeting- June 29, 2023, virtual
Preliminary Design Status Review ePIC PID detectors 5&6 or 6&7 of July  3 reviewers confirmed by now
PAC Meeting- TBD- Summer 2023
MAC Meeting- TBD Summer/Fall 2023
DAC Meeting(s)-TBD Late Summer/Fall 2023  detector R&D (2 days) and technical design review of entire ePIC detector (2 days)
September FDRs for LLPs of Detector
90% Design Review Solenoid October 5&6
EIC CD-3A Director’s Review- October 10-12, 2023, at BNL
EIC CD-3A OPA Review- November 14-16, 2023, at BNL
RRB Meetings
December 7-8, 2023, at SURA
April 2024 tentative for Europe/Italy

## Slide 4: Follow up on recent technology choices
The path to integrate the recent technology changes, Barrel Ecal and backward RICH,
by ePIC into the EIC Project baseline
Remember: five-step change control process
  The detector collaboration initiates a possible change in baseline scope
  The collaboration technical board or equivalent ensures the change is consistent
  with the NAS science requirements and initiates the change request
   prepare input for the TCCB
  detailed changes in cost, schedule and risk  implement in P6
  science and technical justification for the change  input from ePIC
  first backward RICH as it is a less complex case
  The detector TCCB collects wide input, discusses, and gives advise
  The Project Technical Director gives approval
  The EIC Management Team needs to approve the formal baseline change control
   process for both detectors needs to be compete by the DAC technical design review

## Slide 5: EIC Project Detector R&D Program
https://wiki.bnl.gov/conferences/index.php/ProjectRandDFY23
Call for FY24 sent to R&D-Contacts May 8th
Dear current and future R&D participants, it is time to discuss the next steps in our path, i.e., the FY24 projects. We are trying to get the R&D program fully in sync with the FY boundaries. Proposals 1. Please submit your proposals and progress reports (where applicable) to us by July 7, 2023. We aspire to have a DAC meeting well in time to prepare for contracts at the beginning of FY24. 2. We expect progress report from all ongoing projects eRD101 to eRD113. What milestones were achieved. How did our understanding improve. What is left to do? 3. eRD102, eRD103, eRD104, eRD106, eRD107, eRD108, eRD109, eRD110, eRD111, eRD112, and eRD113 may submit continuation proposals if and only if technical risk milestones remain. These new proposals should be relatively straightforward to write. Keep them short and concise. List whatever technical risks remain, the milestones, deliverables, and two money matrices showing cost/item and funding/institution to close those remaining risks. Also list the representatives for each institution. List all participating members and institutions on the front page. Please also give, if applicable, an outlook for the years past FY24. Be aware that R&D should not be mixed with PED. If you are not sure, talk to us. The proposals should concentrate on detector R&D tasks that mitigate project detector technical, risk. DAC Review Meeting With the project detector R&D expected to dwindle down at CD-2, we will limit the meeting to a two-day review meeting in the July-August period. The FY24 proposal goals of all continuation projects should be presented as well as a short status report of all FY22/FY23 proposals. More details on this meeting will be announced soon. Best regards, Elke, Rolf, and Thomas

## Slide 6: Services Layout and Management
Gathered service estimates from detector groups
Laid out 2 common paths (red and orange) for service routing
Determined locations of bottlenecks
Calculated service bundle volumes at bottleneck locations
Totals for services passing from one point to the next are shown below
Point 1 to 2 on each side needs more space allocated
1
2
3
4
1
2
3
4
5
We need an update from all detectors by the end of May PLEASE !!!!
The information should be updated here
https://wiki.bnl.gov/EPIC/index.php?title=Project_Information
both for central and ancillary subdetectors
PLEASE also update the readout chain information in the same
excel sheet  still no info from many detectors
 all critical to pass the upcoming reviews

## Slide 7: System Engineering
for more details see talk by Walt Akers
https://indico.bnl.gov/event/19202/contributions/75979/attachments/47422/80408/Akers-20230510.pptx

## Slide 8: System Engineering

## Slide 9: Examples of What is Ongoing
Continue meetings with subgroups to discuss progress and organization – THANK YOU!!!!
Close to all contracts related to EIC project detector R&D with BNL and JLab procurements being awarded, some are still waiting for responses at the Universities and Labs. Some contracts for PED are also ongoing.
Magnet “mid-project” review (~75% design completion) completed April 17th – 19th
Started work on specifications for LLPs (SiPMs & PbWO4)  critical input for LLPs FDR.
Intensive mechanical engineering effort on all subsystems
Detailing installation schedule for the EIC experimental equipment
 see https://www.dropbox.com/s/w9oz0asvtb66hfh/Installation%20Schedule%20for%20the%20EIC%20052023.docx?dl=0
Would welcome if all ePIC DSCs could define their work package structures so integration in project structure can proceed
CERN visit April 24-25:
  Visit with Joachim Mnich CERN Science Director
     very positive feedback on making ePIC recognized experiment (now in the hands of John and Silvia) and cooperation on EIC overall
  Meeting on photo-sensors and RICH detectors with LHC-b and ALICE
  Meeting with ALICE ITS-3 team on collaboration with EIC Si Consortium

## Slide 10: Summary on ITS-3 ALICE –EIC SiC
Overall a very positive and successful meeting  clear goal to cooperate as much as possible in boundary conditions.
Main lessons learned and next steps
ITS3 open to sharing their sensor design with EIC  necessary agreements will need to be put in place in the next month.
ITS3 development made significant progress  received a lot of critical technical information to guide the next steps in R&D for both sensor and system design/integration of the ePIC SVT
but there remains still some risk in the ITS development  ALICE team will need to remain focused on their requirements and timeline challenges
 ITS3 welcomes/seeks partnership in development with EIC designers contributing to ITS3
 Received extremely valuable input to overall schedule and workforce needs for EIC SVT
Example: relation between schedule for ITS3 ER2/ER3 submission and evaluation and the
EIC/LAS development schedule  adjust our schedule to give more time for the sensor
modifications and the schedule and integrate lessons learnt from ITS3
 ITS3 suggests we put in place a backup plan as our workforce is still growing, and the
overall EIC SVT schedule is aggressive
All the inputs are currently folded in an updated plan by the EIC SVT team
Updates will be presented in the respective ePIC meetings (TIC & TWG) by the SVT team

## Slide 13: Preliminary Timeline-Preparation for Director/OPA Reviews
Interim Schedule meeting May 15
Schedule Updates/Installation Workshop complete May 31
Cost Estimate Updates for LLP items complete June 16
LLP Cost Review by June 30
Revisions incorporated by July 14
Management Review by August 4
Incorporate final changes and freeze data August 25
PC prepare docs for Management Review August 30
Revisions to backup documentation finalized by Sept. 6
Page Turn week of (CAMs have numbers) Sept 11
Run reports for posting by Sept 11
Dry Run week of Sept 18
Post documentation including backup by Sept 26
Post Presentations by October 3
Director’s Review starts October 10
CD-3A OPA Review starts November 14

## Slide 14: Collaboration – Project Integration
Integrating Collaborators:
L3: CAM from the project
Fold in users/collaborators as
on L4: CAM + technical contact == DSTC
  bRICH
  DIRC
  dRICH
  ToF
on L5 Work Package leaders
as defined in the DSS - structure
  Photon-Sensors
  Quartz-Bars
  ………..
Level-2
6.10.04 Particle
Identification
Level-3
6.10.04.01 Backward RICH
Level-4
6.10.04.02 Barrel DIRC
Level-4
6.10.04.03 dRICH
Level-4
We need a control account manager (CAM) at each WBS level. WBS levels go down to where it is meaningful to accumulate cost and schedule variance. There can be many Work Packages below.
DIRC-Photon-sensors
Level-5
DIRC-Quartz-bars
Level-5
Rolf & Elke
6.10.04.04 Time-of-Flight
Level-4
6.10.04.04.01
bToF
Level-5
6.10.04.04.02
fToF
Level-5

## Slide 15: Collaboration – Project integration
6.10.04 Particle
Identification
Level-3
6.10.04.01 Backward RICH
Level-4
6.10.04.02 Barrel DIRC
Level-4
6.10.04.03 dRICH
Level-4
Photonsensors
Level-5
DIRC-Quartz-bars
Level-5
6.10.04.04 Time-of-Flight
Level-4
6.10.04.04.01
bToF
Level-5
6.10.04.04.02
fToF
Level-5
Photonsensors
Level-5
Gas system
Level-5
Vessel
Level-5
Mirror
Level-5
Readout
Level-5
Cooling
Level-5
Cooling
Level-6
Readout
Level-6
Sensor
Level-6
Sensor
Level-6
Support
Structure
Level-6
Support
Structure
Level-6
and more
and more
and more
Aerogel
Level-5
Vessel / Boxes
Level-5
Mirror /F-Lens
Level-5
Readout
Level-5
Cooling
Level-5
Support
Structure
Level-5
Readout
Level-5
Photonsensors
Level-5
and more
can be
the same
 one WP
merge
if PS are the same
 one WP
CAM from Project
CAM from Project
+
DSTC from
Work Package lead
from
Work Package lead
from
Work Package lead
from