## Slide 1: EIC Project Update
Elke Aschenauer and Rolf Ent
Co-Associate Directors for the Experimental Program
ePIC General Meeting
June 8th 2023

## Slide 2: Long Lead Procurements Overview
Selection already accounts for design changes and recent technology choices
 Removed fHCal scintillators and WSF that was a critical need for an earlier design variation
 Added scintillating fibers as we need now two large orders.
WBS 6.10.07 1.7 T Solenoid
  Magnet is long-lead as the detector assembly and installation requires the availability of the fully-tested magnet
  limited world-wide vendors and long production time (estimated from recent 12 GeV magnets)
Electromagnetic and Hadronic Calorimeters and SiPMs
  WBS 6.10.04, 05, 06 SiPMs for calorimeters and dRICH
  Need 735000 SiPMs not all the same type
   DSL & DSTL of subdetectors with SiPMs expect an invitation for a meeting to discuss
  specifications
  WBS 6.10.05 PbWO4 – crystals
  WBS 6.10.05 fECAL and Barrel ECal SciFi need in total ~8000 km
  WBS 6.10.06 forward HCal: Steel and Tungsten plates
All these long-lead items are driven by
  limited world-wide vendors  competition by other projects around the world
  production times and capability and/or labor-intensive manufacturing tasks
  SiPMs staggered procurement
Final Design Reviews for LLPs to justify specifications for procurement on the July – August time frame  Requirement for CD-3A

## Slide 3: Reminder of R&D versus PED
Detector R&D:
For the project detector R&D we follow the posted and public EIC detector R&D plan.
Project detector R&D can only address formal project risks (i.e., no science optimizations or work that moves into design).
We aim to complete the project detector R&D milestones that are in P6 – these are based on completion dates from last year’s EIC detector R&D presentations to the DAC.
We kept some consistency with the earlier 2011-2021 generic EIC detector R&D program, so we do have an annual mail for status updates and an annual DAC meeting dedicated to this.
The annual call for EIC detector R&D reports is such that we hear about progress, to see if we need to adjust milestones, and to get DAC feedback on possible R&D continuation.
Recall that detector R&D will dwindle down around CD-2 (i.e., in FY25).
Detector PED:
There is no PED submission process. For PED we directly follow the activities that are included by the CAMs in the formal Project P6 schedule.
Any PED work must be linked to an activity in P6, and if not, it may require a change request.
PED contracts that we have put in place are conform activities that the various L3 Control Account Managers have put in P6, and then we fund them (be it to pay internal labor or for external contracts).

## Slide 4: R&D Milestones in P6
R&D Milestones & Timeline February 26, 2023
Particle ID
eRD101 (mRICH)
Validate production readiness of a Ring-Imaging Cherenkov Detector as matched with photosensors and readout electronics on the electron-side end cap of the EIC detector, including validation by prototypes that the EIC requirements can be met. [March 2025] – note this one ends in FY23 given the choice for pfRICH detector technology
eRD102 (dRICH)
Validate production readiness of a dual Ring-Imaging Cherenkov Detector as matched with photosensors, readout electronics, and integrated cooling on the ion-side end cap of the EIC detector, including validation by prototypes that the EIC requirements can be met. [March 2025]
eRD103 (hpDIRC)
Validate production readiness of a new high-performance DIRC detector by DIRC bar characterization, and vertical-slice prototype cosmic and beam tests including a realistic readout box. [June 2025]
eRD110 (photosensors)
Ensure applicability of SiPM readout for Ring-Imaging Cherenkov detectors. This implies validation of operation in the single photon regime, and studies of irradiation and in-situ annealing to ensure operation in a "radiation damaged and annealed" mode is possible. [September 2022] - complete
Establish production readiness of a LAPPD/HRPPD-based photon-sensor readout for a Ring-Imaging Cherenkov Detector on the electron-side end cap of the EIC detector, including validation by prototype beam tests. [Sept. 2024]
eRD112 (AC-LGAD/ToF)
Validate production readiness of the AC-LGAD detectors in the barrel region, the forward side end cap of the EIC detector, and the far-forward Roman Pot beam line detectors. This includes sensor prototypes, ASIC demonstrator, and full-scale parts tested and finalized. [September 2026]

## Slide 5: R&D Milestones in P6
Calorimetry
eRD105 (SciGlass)
Scintillating glass scaled up and characterized to >15X0. Prototype tested in electron beam. [May 2023]
Beam test results of 5 x 5 prototype documented. R&D to implement final projective geometry of scintillating glass completed. [September 2024]
eRD106 (fwd EMCal)
Validate production readiness of the EM calorimeter in the forward ion direction by optimizing uniformity and efficiency of light collection with SiPM readout, integration of final readout, and common beam test with hadron calorimeter prototype. [June 2025]
eRD107 (fwd HCAL)
Validate production readiness of the hadron calorimeter in the forward ion direction by machining and characterization of tiles, prototype module production, integration of final readout, and common beam test with EM calorimeter prototype. [June 2025]

## Slide 6: R&D P6 Milestones in P6
Tracking
eRD108 (MPGD)
Complete beam test validation of cylindrical mRWELL with prototype [September 2023]
Complete validation of use of light-weight cylindrical Micromegas with 2D readout patterns as derived from the earlier used cylindrical technology [December 2024?]
eRD104 (Service Reduction)
Develop powering scheme based on serial powering to mitigate service space needs of DC-DC scheme. [December 2023]
Evaluate radiation tolerant FPGAs and high-speed fiber optic transmission option with beam test. Complete prototype multiplexing firmware. [December 2024]
eRD111 (Si Tracker)
Report completed on barrel and disc cooling options, allowing cooling choice [December 2023]
R&D completed for stitching of sensors [September 2024]
eRD113 (Si Sensors/ITS3)
End-of-R&D Milestone: EIC vertex sensor quantification finalized [September 2026]
(Note: link in P6 to EIC large area sensor production start [February 2027])

## Slide 7: R&D Milestones in P6
Electronics
eRD109 (ASICs/FEEs)
Develop a streaming readout solution for the EIC calorimeters with SiPMs and the associated PCBs and cabling infrastructure. Decide between options using COTS devices or directly starting from existing ASICs. [September 2025]
Develop a streaming readout solution specific to the Ring-Imaging Cherenkov (RICH) particle identification detectors with SiPMs. This may require a modification of an existing ASIC design. [December 2025]
Develop a streaming readout solution specific to particle identification detectors with LAPPDs and/or MCPMTs. This requires a novel ASIC in 130 nm CMOS technology that meets the requirements set by EIC providing a precise time measurement with a TDC combined with an Analog Digital Converter (ADC) for the amplitude measurement. [December 2026]
Develop a low-mass streaming readout solution specific to the barrel-region AC-LGAD at an EIC Detector, including design of the power delivery and readout service system. This includes a decision between redesign of existing ASICs or use of third-party ASIC solutions [September 2025].
Develop a streaming readout solution specific to the MPGD-based tracking detectors. This requires a modification based on previous ASIC designs to include compatibility with streaming readout, a new CMOS technology, and 64-channels. [March 2026].

## Slide 8: Test Beam Facilities
In the timeframe 2026 to 2028 basically all high energy hadron test beams are shutdown
To possibly mitigate this, we ask all DSLs to please fill in the following excel-sheet
https://brookhavenlab.sharepoint.com/:x:/s/EICPublicSharingDocs/EYRoY3efWvBNhPJRevfekrIBmos8-BG7lEXMqy6qiBKPlQ?e=nyNnIM
In addition, we are collection information about testbeam facilities around the world not listed above,
i.e. JLAB, Sendai, MAMI, BONN
especially also low energy for irradiation tests
 Please sent information to elke@bnl.gov  thanks to everybody who already sent input
 will prepare a wiki-page with all the info under the ePIC wiki

## Slide 11: EIC Project Detector R&D Program
https://wiki.bnl.gov/conferences/index.php/ProjectRandDFY23
Call for FY24 sent to R&D-Contacts May 8th
Dear current and future R&D participants, it is time to discuss the next steps in our path, i.e., the FY24 projects. We are trying to get the R&D program fully in sync with the FY boundaries. Proposals 1. Please submit your proposals and progress reports (where applicable) to us by July 7, 2023. We aspire to have a DAC meeting well in time to prepare for contracts at the beginning of FY24. 2. We expect progress report from all ongoing projects eRD101 to eRD113. What milestones were achieved. How did our understanding improve. What is left to do? 3. eRD102, eRD103, eRD104, eRD106, eRD107, eRD108, eRD109, eRD110, eRD111, eRD112, and eRD113 may submit continuation proposals if and only if technical risk milestones remain. These new proposals should be relatively straightforward to write. Keep them short and concise. List whatever technical risks remain, the milestones, deliverables, and two money matrices showing cost/item and funding/institution to close those remaining risks. Also list the representatives for each institution. List all participating members and institutions on the front page. Please also give, if applicable, an outlook for the years past FY24. Be aware that R&D should not be mixed with PED. If you are not sure, talk to us. The proposals should concentrate on detector R&D tasks that mitigate project detector technical, risk. DAC Review Meeting With the project detector R&D expected to dwindle down at CD-2, we will limit the meeting to a two-day review meeting in the July-August period. The FY24 proposal goals of all continuation projects should be presented as well as a short status report of all FY22/FY23 proposals. More details on this meeting will be announced soon. Best regards, Elke, Rolf, and Thomas

## Slide 12: Collaboration – Project integration
6.10.04 Particle
Identification
Level-3
6.10.04.01 Backward RICH
Level-4
6.10.04.02 Barrel DIRC
Level-4
6.10.04.03 dRICH
Level-4
Photonsensors
Level-5
DIRC-Quartz-bars
Level-5
6.10.04.04 Time-of-Flight
Level-4
6.10.04.04.01
bToF
Level-5
6.10.04.04.02
fToF
Level-5
Photonsensors
Level-5
Gas system
Level-5
Vessel
Level-5
Mirror
Level-5
Readout
Level-5
Cooling
Level-5
Cooling
Level-6
Readout
Level-6
Sensor
Level-6
Sensor
Level-6
Support
Structure
Level-6
Support
Structure
Level-6
and more
and more
and more
Aerogel
Level-5
Vessel / Boxes
Level-5
Mirror /F-Lens
Level-5
Readout
Level-5
Cooling
Level-5
Support
Structure
Level-5
Readout
Level-5
Photonsensors
Level-5
and more
can be
the same
 one WP
merge
if PS are the same
 one WP
CAM from Project
CAM from Project
+
DSTC from
Work Package lead
from
Work Package lead
from
Work Package lead
from