## Slide 1
Closeout Presentation of Detector Advisory Committee
R&D Review
August 28,31, 2023
Participating Members: E. Auffray, , E. Kinney, P. Merkel, S. Miscetti, A. Papanestis, H. Schellman, B. Vachon, A. White, K. Wyllie, C. Yang
Thanks to Elke Aschenauer, Rolf Ent, Thomas Ullrich, and Anna Mendez!
Thanks to EIC Project Team, ePIC Collaboration, and all the presenters!

## Slide 2
Charge to DAC
For the August 2023 DAC meeting dedicated to R&D we welcome your guidance and advice on:
  The status and progress from all ongoing projects eRD101 to eRD113. What milestones
  were achieved. How did our understanding improve. What is left to do?
  If applicable, the plans for remaining EIC project detector R&D for eRD102, eRD103, eRD104, eRD106, eRD107, eRD108, eRD109, eRD110, eRD111, eRD112, and eRD113.
  These may submit continuation proposals if and only if technical risk milestones remain. eRD101 and eRD105 are concluded as the ePIC collaboration has recently made the decision for a technology change for the backward RICH and the barrel ECal.
  The request for EIC project detector R&D for eRD114 and eRD115 that follow these two final detector technology selections for the ePIC detector.
  Further planning for the outyears of the EIC Project detector R&D as documented in the “Assessment of R&D Needs for an EIC Detector” (EIC Detector R&D) document.
  What do you see as priorities?

## Slide 3
eRD104 –Silicon Services Reduction
The community proposes RnD towards a serial-powering scheme to reduce the material contribution from power-cabling. They have studied this, based on their experience of a similar approach in ATLAS, and have started the design of an integrated shunt-LDO circuit together with architectural studies. They have also studied a standalone alternative for the shunt-LDO.
They also propose an electrical-optical conversion on detector to reduce the material contribution from data cabling and have identified options for the electrical and optical parts. Funding/procurements delays hindered the progress so far. They have also studied the readout implementation for ALICE-ITS3.
How is the shunt-LDO prototyping planned and funded? The ‘standalone’ option allows flexibility to use MPW submission on TJ180 (or similar) while the integrated shunt-LDO is a large deviation from the ‘baseline’ ITS3 design. So the standalone shunt-LDO is a more promising route for the R&D.
Two of the options for readout (PolarFire FPGA and Firefly Transceiver) are off-the-shelf and would likely require radiation testing. Is this part of the planned characterisation? If yes, are radiation facilities available, and is funding available?
The switch to serial-powering is a significant change and is a large R&D effort requiring both ASIC and system design. Hardware prototyping is essential to prove its viability and the community should strive to advance with this as quickly as possible. The planned submission of the LAS v1 chip in Q1-2025 requires rapid closure of the R&D in 2024.
There is potential synergy with ALICE-ITS3 on the readout links and this should be investigated thoroughly for the ePIC case. The ALICE system will use radiation-proven parts so requirements on radiation testing would be minimised. Access to these parts would likely require a request to CERN.

## Slide 4
eRD111 –Modules, Mechanics, Cooling and Integration
The community has made good use of the close contacts to the ALICE community, in particular for the successful demonstration of bending dummy-ALPIDE chips to the ITS3 innermost radius and connecting them with FPCs. This has allowed the construction of a prototype tracker layer using dummy components.
Air-cooling studies have advanced with carbon fibre + foam structures. The benchmark of a deltaT of 10C has been achieved with conducting carbon foam, which is encouraging for the prospect of air cooling.
Simulations have been made to evaluate the presence of the air-flow on the beam-pipe bakeout, indicating that further study is required.
The restrictions on the sensor-length variations imposed by the foundry triggered new layout considerations and CAD modelling.
Is there a possibility to access prototype parts from ER1 for integration tests?
Are the R&D concepts from eRD104 included in the integration modelling here? For example, the concept of the 'Data Management Board' borrowed from ALICE and the FPC.
Proceed as fast as possible to prototyping bent structures using active ALPIDE parts or, even better, parts from ER1.
Build strong communication with eRD104 for FPC and readout concept and design.

## Slide 5
eRD113 –Sensor Development and Characterization
Together with the ALICE community, there has been significant progress on the validation of the TJ65 process with MLR1, then ER1. Multiple building blocks were submitted and many from MLR1 have been tested, including some radiation testing.
Designs of other blocks customized for the EIC application were delayed waiting for funding approval and are carried forward to FY24.
First discussions on a collaboration agreement with ALICE were held, paving the way for contact between designers.
EIC institutes became more and more active in testing of structures from TJ65, including calibration with radioactive sources. A telescope was developed for testbeam activities and is available for EIC use.
Is access to ALICE designs now granted and a collaboration agreement in place? This is vital for a EIC outer-barrel design submission targetting Q1-2025.
The detector construction relies on stitching. Has there been a study on what yield is acceptable?
Advance as quickly as possible to finalise the collaboration agreement with ALICE and integrate designers in the team at CERN.
Foster strong ties with eRD104 to ensure the correct consideration in the MAPS design of the systems aspects of both serial-powering and readout links.

## Slide 6
eRD108 –Micro-Pattern Gas Detectors: Micromegas Barrel Tracker
Beam testing of several configurations of small prototypes, with varying resistive layer and readout patterns, was carried out. No results are shown from the beam testing.
A full-scale prototype section with the selected readout patterns is under design.
A new configuration of the MPGD systems for ePIC evolved in mid-2023 with an inner barrel layer consisting of three cylindrical sections.
What were the results of the beam tests at MAMI?
How do these results impact the new inner barrel layer design?
The timeline and milestones indicated for FY24 seem to stretch well into FY25 and impact readiness for CD2/CD3?
The new design indicates a close interaction of the services (power, cooling, readout) between SVT and the MM inner barrel layer. Is there a conceptual design for these services? How will these services impact the tracking coverage?
Continue with full scale prototyping, focusing on critical issues to prepare for CD2/3
Thin gap studies need to proceed on a rapid timescale

## Slide 7
eRD108 –MPGD: Cylindrical 𝜇RWELL Prototype
A prototype was constructed to investigate this technology as a backup for the baseline cylindrical MM approach. Due to interruption of operations for safety issues at the lab no data was taken with the prototype.
Modifications to the drift foil and its support are planned followed by lab testing with cosmics and sources. No further funding is requested for Fy24.
Is further development of this technology for the inner barrel layer still prudent as risk mitigation for the MM technology approach, particularly in view of the effort needed for the endcap detectors (see next item)?
Recommend test beam studies of existing prototype as soon as possible.

## Slide 8
eRD108 –MPGD: Endcap 𝜇RWELL Layers
To provide additional tracking hits in the endcap regions of ePIC two planar MPGD disks at each end were added to the baseline design. An additional benefit would be providing fast hit points for background rejection.
One year is a very short time to accomplish the design and development of new large-area μRWELL chambers particularly given the issue of charge-up and chamber integrity using light-weight materials.
Reliance on students for design tasks poses a risk.
The anticipated one-year needed for the CERN workshop to design, develop, and fabricate large-area μRWELL foils pushes chamber construction and testing well into FY25.
No beam testing of large area μRWELL chambers poses a risk.
What is the proposed strategy and impact of the services for the forward disks?
Explore the possibility of employing professional design engineers.

## Slide 9
eRD108 –MPGD: Outer Barrel 𝜇RWELL Layer
A layer of planar μRWELL chambers, using a hybrid GEM-μRWELL technology, arranged around a circle is proposed for the outer barrel tracking layer in front of the hpDIRC.
These chambers will provide fast timing hits as an aid to pattern recognition and improve the determination of the angles of charged particles entering the hpDIRC.
A full-size prototype is planned to address stability issues albeit with a mock μRWELL foil.
Many technical challenges (foil stretching, low mass materials, HV stability) must be overcome in a short time period to create a reliable final design.
There is a risk posed by using a Ph.D. student to design and fabricate the prototype.
Explore the possibility of employing professional design engineers.

## Slide 10
eRD105 – SciGlass
Large size (40cm) production achieved
Transmittance studied of crystals studied
SiPM photosensors readout successfully implemented
Beam tests using 3x3 and 5x5 arrays were performed, results suggest further readout optimization required to understand performance of SciGlass
Although no longer a baseline detector technology, this is a very interesting material which should be studied further in order to understand intrinsic performance, details of light transmittance and effects of irradiation
Recommend continuing study in the EIC Generic R&D program

## Slide 11
eRD106 – Forward EM Calorimeter
Calorimeter based on molded Tungsten/Scintillating Fibers components
Funding delays only allowed start of FY23 program in August 2023
Progress on mechanical design and support (shear) test
Development of molding facilities at Fudan including supplies for initial prototype production
Optimization of light guide design on-going
Activities to proceed in FY24 using PED funding
Recommend focus on open questions for a final design for CD2/3 review

## Slide 12
eRD107 – Forward Hadron Calorimeter
Changed from previous design to an iron/scintillating tile readout with SIPM's mounted on the tiles (instead of fiber readout)
SIPM design is based on CALICE and shared with CMS upgrade.
Substantial work has been done on fabrication techniques.
The detectors will not be accessible for long periods - so need to be rad tolerant.
Two parts - outer part with 5 cm segmentation and 7 longitudinal sections has , inner part 'insert' not yet fully specified as optimization studies need to be done.
Will be doing beam tests at CERN in 23 and 24. Would be interested in more detail on the 23 test status. 23 test will be with individual tiles and absorbers while 24 will test modules manufactured in two different ways.
Fabrication testing is well underway and there is a strong team to perform the physical design/fabrication studies.
Full optimization of the design - in particular the insert granularity depends on simulation and was not yet complete as of July 23. The presentation at this meeting provided an update that the only remaining issue was the segmentation of the insert readout, which does not affect the mechanical design.
Test beam runs at CERN are critical path for final design decisions. Would like to know status of DAQ systems needed for those tests.
Overall the technology seems to be well demonstrated and the design is well advanced but optimization/fabrication/system tests still need to be performed.
Ensure sufficient funding/staffing/lead time to support CERN beam tests.

## Slide 13
eRD115 – Imaging Calorimeter -1
This is a new FY24 R&D proposal related to the final technology choice for the EM Barrel (bECAL) calorimeter. The new selected option, adopted after FDR of March 2023, replaced the Sci glass option with a new Imaging Calorimeter concept.
This Imaging Calorimeter combines the well-established Pb/Scifi technology (Kloe and Gluex with SiPM readout) with a well performing position detector developed for AstroParticles, ASTROPIX.
The design shows a pre-shower region with 4 (baseline) to 6 (optional) layers of ASTROPIX interleaved with short Pb/Scifi sections (SFIL) followed by a traditional EM section. From simulation, this calorimeter can achieve an energy resolution like Gluex (5%/sqrt(E)) while dramatically improving the position and angular resolution, from O(cm) to better than 0.5 mm as due to the chosen pixel size.
The design with 6 ASTROPIX/SFIL layers matches/surpasses the required bECAL performance for e/pi and p0-g separation in all required energy ranges.
This R&D proposes to assemble, operate, and characterize a small-scale hybrid detector realized with different combinations of ASTROPIX and SFIL sections, followed by a small size Pb/Scifi Gluex prototype (baby BCAL). The baby BCAL is identical in composition and cross-section dimension to Gluex calorimeter but is shorter longitudinally.
Goals of the R&D are to benchmark the combined performance, validate the simulation and test integration by exposing the prototypes (FNAL test beam) to e/pi beams from 5 to 30 GeV.
The proposed R&D plan is detailed and ambitious, but it is important for the evaluation of the final detector performance and for its realization, due to the difficulty to integrate such different technologies in such a short time. The test beam plan is crucial to demonstrate that there are not unwanted problems and can provide a first test bed for integration.

## Slide 14
eRD115 – Imaging Calorimeter -2
We commend the team for the rapid organization of this program and provide our support to the proposed plan.
A long list of tasks/milestones is presented. Three different aspects are considered:
A practical organization for integrating the different mechanical structure configurations, the readout and triggering.
Extract experimental results on energy, position resolution and e/p separation for different configurations of the hybrid detector.
Perform a detailed data-simulation comparison. This work will feed the general simulation to improve fidelity on the e/pi shower profiles and the achievable e/pi separation.
The team demonstrated a lot of expertise on the Pb/Scifi and ASTROPIX sides. There are many upcoming changes on the usable layouts and on the ASTROPIX versions (from 2x2 cc to quad 2x2 cc to other layouts, to ASTROPIX-V4). The R&D program outlined is only one year long and some of the ASTROPIX changes looks coming late in the game. We suggest the proponents not to sacrifice any available beam time for running and understanding the data with respect to speed-up further configurations that can be carried out also without beam.
Characterize the high energy side and test linearity in response for the electrons is very relevant for this detector. The dynamic range of the Gluex apparatus has been changed from few GeV up to 50 GeV (for the electrons) and it is not immediately evident that the selected SiPM pixel size (50 um as used in Gluex) will not suffer non-linearity at the highest energy points.
The test beam can be used for testing the readout section with SiPMs of different pixel size to be sure that linearity is proven before starting the SiPM LLP. Test of different sensors is already foreseen in Milestone N.9 and our request can be accommodated in this framework.
In case of needs, we recommend to prioritize the efforts related to testing the e/pi response with respect to more advanced integration efforts (mechanics, DAQ, triggering) since many of those can be carried out, independently from the FNAL test beam, also with Cosmics Ray data taking at a later on at a parallel stage.

## Slide 15
eRD112 – AC-LGAD -1-
This project is dedicated to advancing the AC-LGAD technology, intended for implementation in multiple crucial subdetectors: the main detector of TOF, as well as in the far-forward and far-backward instrumentation along the beam line adjacent to the main detector. Large efforts are proposed to be made on not only the fabrication of AC-LGADs but also the readout electronics including ASICs. Many institutions involved in the project and made their own progress due to a well-organized R&D proposal.
By FY23, both BNL and commercial vendors have produced prototypes of the sensor, substantially reducing risks. The beam testing at Fermilab on these sensors are ongoing, and achieved some positives. The timing resolution and position resolution of the pixel sensors produced by HPK have reached 20ps and 20um respectively. The development of the first prototype of the low-mass mechanical support structure has been completed. There are plans to continue further testing of sensor prototypes and to develop multiple versions of the mechanical support structure. Additionally, the possibility of introducing another vender, FBK, will be considered."
Compared to FY22, significant progress has been made in this project, especially in the development of the sensor. So far, the results look promising and are in line with the project timeline. Clearly, continuing the research on sensor production options is still crucial, whether at BNL or with commercial venders. The current US-Japan collaboration may benefit on the scheduling in mass production at HPK. These will mitigate risks.
According to simulations based on the latest simulation framework, the material budget requirements for the forward TOF and the spatial resolution requirements for the B0 tracker have both been significantly enhanced. The research team plans to continue the study of a common design to reduce costs and risks. At the same time, attention should also be given to whether the original design can meet the significantly improved performance requirements of these individual detectors. More detail checks are suggested to see if there are other requirement changes.

## Slide 16
eRD112 – AC-LGAD -2-
Since there are several commercial vendors involved, ensuring enough funding contingency is something that needs to be considered due to the fluctuations in the international supply chain prices.
Continue the study on sensor fabrications options in various vendors.
Using the latest simulation frame, further check if there are crucial performance requirements changed in related individual detector to meet the goals of ePIC.
Continue the material budget study based on whole system including sensor, bounding base, supporting structure and other integration materials.

## Slide 17
eRD101 – mRICH
Test data from prototype in Jlab beam has been analysed to determine single photon resolution
Multiple ring discrimination studies initiated from test beam data
Further optimization of Fresnel lens focal length and detector geometry under study
As mRICH is no longer a baseline technology, no funding request for FY24
Reorganized efforts to use mRICH has a tool to characterize aerogel and photosensors
Encourage joining detectors groups using aerogel and photosensors to use of mRICH in testing

## Slide 18
eRD102 – dRICH
Moving towards a relatively design
Testing of subcomponents are underway
Operation of a closed gas C2F6 system is likely to be non-trivial and a comprehensive system design is desirable to understand impact on the rest of the detector
Present aerogel does not fufill the performance requirements; attention should be paid to working with manufacturer to obtain the necessary quality aerogel
Review in July 2023 points out possible need for cooling of SiPMs which needs to be studied both in physics performance terms as well as infrastructure/interface demands
Need full scale prototype to confirm support of detector structures is possible
Need to understand effects of background tracks from outside the collision region that may spoil pattern recognition

## Slide 19
eRD103 – hpDIRC
Goal is to achieve required performance, minimize technical risks and to realize opportunities
Progress over the last year includes transferring prototype DIRC components from GSI to SBU, completing simulation and mechanical design of the cosmic ray telescope (CRT), and advancing facility construction
The CRT will be used to perform three functions. It will enable prompt testing of radiator bars from the disassembly of the BaBar DIRC bar boxes at JLab. Secondly, it will be used to test the readout chain as photosensors and readout electronics become available. Finally, QC of the completed hpDIRC bar boxes during production will be carried out. The CRT needs to be commissioned during FY24.
The bar boxes from SLAC will be transported to JLab in fall 2023, where they will be disassembled. Then the bars will be cleaned, inspected and evaluated for optical quality.
Need to understand what will be planned in the case that not all the Babar bars are of sufficient quality.
The accepted event rates in the CRT for different trigger conditions will be determined during commissioning of the system.
Travel funds are requested for experts from CUA and GSI to support the prototype installation and commissioning.
Setup of the CRT at SBU is well underway. A 3D stage has been purchased and the prototype DIRC from GSI will be installed later this summer/fall. The Geant4 simulation of the entire setup has been completed, including the integration into the full EIC simulation packages.
Existing photosensors for the CRT no longer show sufficient single-photon sensitivity and need to be replaced. Funding is requested for a set of phototubes.
Once the prototype DIRC assembly has been completed, it will be installed in the CRT together with the readout electronics. This will allow to exercise the DAQ system.
Continue to ensure sufficient funding, communication and collaboration with the various DIRC experts in the group as well as experts from the original SLAC bars in order to facilitate a smooth and time efficient installation and commissioning phase.

## Slide 20
eRD110 – Photosensors/HRPPD
Advanced program to purchase and evaluate HRPPD sensors from Incom described.
Additional sensor purchases may be necessary to establish stability and uniformity in addition to manufacturability
Design for use at EIC developed with backplate connector and cooling incorporated
Large effort must be maintained in the near future in order to understand if this is a viable technology for the baseline detector
Need to compare ageing expected for HRPPD vs MCP-PMT under expected operational environmental conditions over typical detector lifetime.

## Slide 21
eRD114 – pfRICH
Choice of pfRICH in backward choice only made recently.
Prototype module using HRPPD being designed
Beam test to confirm performance of prototype planned in FY24 to prove proof of system capability
Significant development and testing of the HRPPD needs to be accomplished before CD2/3, so it would be prudent to fully develop the fallback solution in the design of the pfRICH, including compatibility with the readout electronics.
Support the prototype studies in test beams

## Slide 22
eRD109 – ASICS/Electronics
Combination of multiple development efforts
Delay due to difficulty in setting up contracts hindered FY23 progress
Close attention should be made to ASIC development schedule, especially with regard to chip availability for use in detector component testing/development as well as the availability of expert support
Scope of R&D activities has expanded since last year’s proposal, including well-motivated EICROC and HGCROC modification
Fully explore the cost and timescale of packaging, especially for future productions
High priority projects with large impact to the EIC effort/performance

## Slide 23
Global Recommendations
Again, congratulations to all on enormous progress in short time!
Aggressive effort needed to keep to project timeline
Important to expand manpower as soon as possible to keep on track
Recommend continued direction of effort towards final detector development for CD2/3
Silicon tracker, Imaging barrel calorimeter are critical complex components and should be a high priority; the choice of the HRPPD must be made relatively soon (in some cases already). ASICS development is also of high priority and will need a large, experienced manpower support to remain on timeline after CD2/3.