## Slide 1: Shutdown ‘23
Date August 30th 2023
Paul Sampson

## Slide 2: Agenda
General information
Status
Progress
Schedules
Summary

## Slide 3: General Info:
Unscheduled early start
Short duration
Injector programs running
Procedure issues
Major knowns
Unknowns…

## Slide 4: CAD Status
EBIS running beams for NSRL
LINAC: run ends today, next run Friday
Booster: Running for NSRL
AGS- Shutdown
  A10 HVAC repairs deferred; temporary unit installed.
AtR- Shutdown

## Slide 5: RHIC Status
RHIC LHe offloading ✅
Warm up sector 4/5 and 8/9 Blue ✅
Vacuum bleed up, 4/5, 8/9 Blue ✅
Shielding: Sector 8/9 and 12/1 Bock removed
  Sector 4 pending
  Sector 6 & 8 under discussion
CeC and LEReC equipment secured

## Slide 6: RHIC HVAC
1004B Package unit #4- replacement ordered
1004B Package unit #3- running ½ capacity, awaiting parts (20 weeks and counting)
1004B Package unit #1 (CR)- Awaiting parts (6 weeks estimated)
1002F Laser Trailer- Awaiting parts (4 weeks estimated)
1007 dehumidifier- repairs underway
1008IR 2 of 4 units installed, awaiting parts for install completion

## Slide 7: Systems Status:
Cooling towers:
930, 957 on for NSRL running
AGS RFPA, 1000P, 1004: On for testing
1010 on for sPHENIX 80k circulation
RF systems:
AGS on for testing, PA installation
AtR magnet tests in progress
Other systems off or turning off for shutdown

## Slide 8: Progress:
AGS opened, works in progress
  Skew quad installation and hookup continues
  RF work continues
Booster and NSRL Maintenance bi-weekly
LINAC maintenance between BLIP runs, NSRL needs
Shutdown maintenance and other approved work in RHIC has begun
Major works planning in progress:
  Valve box – Approvals for initial inspection this morning, work in progress
  Sector 8/9 work (Snake installation and diode inspection): Work plans being reviewed, pre-work (sampling, posting etc.) under way
  9MHz common cavity removal: Work plan is progress
  1007 Tower shutdown complete, some pre-work for fan control upgrade this shutdown

## Slide 9: Issues:
Unscheduled shutdown reduced planning time
Review and approvals hampered by outdated OPMs
EWPs necessary for outdated OPMs or references for:
Valve Box entry
RMMPS LOTO
RHIC SNAKE installation
RHIC Diode removal
Many times, the owners had submitted reviews long ago…

## Slide 11: Schedules

## Slide 12: CAD Schedule

## Slide 13: Full schedules and timelines:
Available on the web “This Week”.
Discussed at meetings:
Supervisor’s meeting (weekly).
Shutdown “Time” Meetings
Links:
  This Week
  Shutdown Status
  JRS
  Web Status
  Overview Project

## Slide 16: Summary and comments:
This is an extremely short shutdown, with a very large amount of work
The valve box and other critical job(s) are still emerging
New staff learning curve: Additional time necessary to gain experience
Procedure issues and oversite are adding to the workload
As always, coordination, communication and cooperation are key to success.
Planning for major works for shutdown ‘23!

## Slide 17
Thank you