## Slide 1: WBS 6.10.12 Pre-Ops Detector
E.C. Aschenauer (BNL)
EIC Detector Comprehensive
Design Review
August 29-30, 2023

## Slide 2: WBS 6.10.12 Pre-OPS
Scope:
This WBS covers all activities to commissions the detector first with cosmic and then with beam to be ready for data taking.
Big Picture:
Two commissioning periods
  First detector commissioning in assembly hall with cosmic
  Commissioning with beam
Note:
all subcomponents will be tested before installation not part of Pre-Ops
during collider commissioning without detector, we will have the beam-pipe around the IP with detectors to understand backgrounds and other beam related parameters

## Slide 3: EIC high Level Project Schedule
Recent change replaced CD-4A with project internal milestones - PO_0305_0900:
  Detector Assembled and Ready for Cosmic Data Taking
   this milestone is a predecessor for L2 milestone
  L2_0600-Construction of Components Complete

## Slide 4: High Level Installation Schedule
CD-3
04/2025
Milestone
PO_0305_0900
early CD-4
09/2032
CD-4
09/2034
Detector Assembled and Ready for Cosmic Data Taking
Start of
Operations
&
Science
Construction
Oct 2028
IR-6 ready
for installation
Jan 2029
lower half
barrel Hcal
installed
Solenoid
delivered
Barrel Hcal
& Solenoid
installed
followed by low
power test
April 2029
Endcap HCals
completed
Solenoid
Field mapping
Dec 2029
Barrel Ecal
ready
for installation
June 2030
Barrel Detectors
installed
ECal, DIRC,
ToF, Trackers
Oct 2030
Hadron Endcap
Detectors
installed
Trackers, dRICH
ECal
Jan 2031
Lepton Endcap
Detectors
installed
Trackers, bRICH
ECal
done in beam position
done in IP-6 Assembly Hall
Take Away:
Solenoid and Barrel HCal need to be ready by Jan 2029
all other subdetectors need to be ready between 06/29 to 06/30 depending on their location in the detector
Early start of
Operations
&
Science
Pre-OPS

## Slide 5: KPPs for Detector
PreOps activities aligned with original CD-4A KPPs
KPP | Performance Measure | Threshold KPP | Objective KPP | Ultimate PP
DET-4a | Detector | Detector subsystem component testing complete. | Detector subsystems constructed and tested with cosmic rays. | Same as Objective
KPP | Performance Measure | Threshold KPP | Objective KPP | Ultimate PP
DET-4 | Detector | Detector installed and ready for beam operations. | Inelastic scattering events in e-p and e-A collisions measured in Detector. | Inclusive, semi-inclusive, and exclusive events measured as the basis for 3D maps of subatomic quark-gluon structure.
Detector sits as a whole in the assembly hall and gets tested with cosmic
Detector is moved into the collision hall to take first collision data

## Slide 6: Resource Assumptions
For shift-work, we assume one person each shift is dedicated to project requirements, with further shift-personnel contributed by the EIC user community. We assume a little over 5 weeks of dedicated 24/7 operations for detector commissioning, which amounts to 880 hours of science labor.
For magnet commissioning and detector commissioning with cosmic tests, we assume the magnet commissioning is dominated by technical labor, and the detector commissioning by scientific labor. For the latter, we assumed 1 FTE-year on average per detector technology, bridging a two-year period, with 1/2 of this for technical labor for repairs. The magnet commissioning is assumed to also bridge two year, but with ramped down efforts the second year, with 8 FTE-years integrated.
For the full-system detector cosmic tests, we assumed two people 24/7 for a full integrated time period of 5 weeks, and 10 weeks of intermittent work on repairs by technical staff (two people, for 12 hours each day, including weekends).
A significant load of the commissioning will be covered by the scientific collaboration