## Slide 1: Electronics & DAQ Outlook
ePIC Collaboration Meeting
Argonne National Laboratory
9 January – 13 January 2024
Fernando Barbosa, JLab
Chief Electrical Engineer
L3 CAM WBS 6.10.08

## Slide 2: Outline
Status Overview
P6 Partitioning
Timeline
Construction Timeline Details
Next Steps

## Slide 3: Status Overview
Architecture, Readout Chain, Nomenclature, Partitioning
      Defined and well understood
ASIC & Electronics R&D Initiatives
      ASIC & Discrete, Services Reduction, Timing
        R&D well established through eRD109 FY24 and FY25
        Monthly updates from all developers at E&DAQ WG meetings start on 1 February 2024
    To Do
        ASIC interface specifications need to be well defined for SRO operation and interfacing to RDOs
        RDO functionality and interface specifications to DAM/FELIX need to be finalized.

## Slide 4: Status Overview cont.
DAQ
      GTU
        Clock jitter tests with COTS HW measured @ <5 ps
      FELIX
        Re-design efforts for EIC under discussion.
Services
      Sub-detector technologies, channels and readout are mostly settled; some require additional edits: TOFs, Auxiliary and Astropix, Timepix, FLAT32.
      LV, Bias, HV, cabling: type, quantities – on-going.
      Grounding implementation document needed for CD-2.

## Slide 5: Status Overview cont.
Sub-Detectors
      Standard nomenclature has not been finalized
      Need specifications/requirements for ASICs: Qmin, Qmax, Rates
      Need expression of interest/commitments for development of the electronics and DAQ (Scientists, Engineers, Technicians)
Link to ePIC Detector Information Request.xlsx
https://brookhavenlab.sharepoint.com/sites/EICPublicSharingDocs/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FEICPublicSharingDocs%2FShared%20Documents%2FExperimental%20Program%2FePIC%2FDAQ%26Electronics&p=true&ga=1

## Slide 6: Streaming Readout Chain – P6 Partitions
Name
Design
Function
Attributes
Adapter
Detector Specific
-HV/Bias Distribution
-HV divider
-Interconnect Routing
-Sensor Specific
-Passive
Sensor
Detector Specific
-Multi-Channel Sensor
-MAPS
-AC-LGAD
-MPGD
-MCP-PMT
-SiPM
-LAPPD
Front End Board
(FEB)
Detector Specific
-Amplification
-Shaping
-Digitization
-Zero Suppression
-Bias Control & Monitoring
-ASIC/ADC
-Discrete
-Serial Link
Readout Board
(RDO)
Few Variants
-Communication
-Aggregation
-Formatting
-Data Readout
-Config & Control
-Clock & Timing
-FPGA
-Fiber Link
Data Aggregation Module (DAM)
Common
-Computing Interface
-Aggregation
-Software Trigger
-Config & Control
-Clock & Timing
-Large FPGA
-PCIe
-Ethernet
Computing
Common
-Data Buffering and Sinking
-Calibration Support
-QA/Scalers
-Collider Feedback
-Event ID/Building
-Software Trigger
-Monitoring
-COTS
-Ethernet
Global Timing Unit (GTU)
-Interfaces to Collider, Run Control & DAM
-Config & Control
-Clock & Timing
On Detector
SMT BGA
Sub-Detector P6s
Electronics P6
WBS 6.10.08
DAQ P6
WBS 6.10.09
Soon, I will distribute P6 spreadsheets to all sub-detectors for concurrence.

## Slide 7: Timeline
Construction and Installation includes procurements and deliveries and are initiated at different times of this phase.
Bulk of Construction & Installation phase for Electronics: April 2025 – October 2029.
Installation of some items may be extended to April 2031.
eRD109 until mid FY27
ASIC Production mostly in FY26
Design until 9/2028
4/2025 to 4/2031
Engineering Articles
Construction
R&D

## Slide 8: Construction Timeline Details
SALSA (MPGDs) shown as an example
Similar approach for all others.
Maximize synergies.
FEB PCB
1st Article
Design, Layout, Fab, Assembly, Test
FEB PCB
Production
FEB PCB
Test
Other multiple steps not shown, for clarity.

## Slide 9: Next Steps
eRD109 Completion Milestones:
    Discrete/H2GCROC (Calo): September 2025
    EICROC/FCFD (AC-LGAD): September 2025
    ALCOR (dRICH): January 2026
    SALSA (MPGD): March 2026
    FCFD/EICROCx (LAPPD/MCPMT): Dec 2026
Finalize P6: Spring 2024
Electronics & DAC PDR: May 2024
eRD109 FY25 proposal submission: 1 July 2024
DAC: August 2024
CD-2: April 2025
These are official project milestones.
Signify start of production.
Any discrepancies or updates?
P6 - Harmonize Project and ePIC Collaboration.
Maximize Synergies developing Adapters, FEBs, RDOs.