## Slide 1: Responses to Elke’s email Sept 20
Kondo Gnanvo
On behalf of the eRD108 Consortium / DSC Gaseous Trackers
Meeting with Project and Collaboration leaders - 09/28/2023

## Slide 2: 1. What R&D needs still to be finalized to show that the Standard μRWell (as discussed on slide 5 of Kondo’s TIC presentation, leftmost column) provides an option for an MPGD tracker for ePIC even if the hit resolution is inadequate. We would also like to see a time estimate needed to complete this R&D.
Standard µRWELL with simple 2D strip readout (1 mm pitch / no capacitive-sharing)
  Large area µRWELL modules: Main R&D challenges  Satisfy all the constrains from ePIC
    Small allocated envelop for the Barrel Outer Tracker 2.5 cm volume
    Minimize material thickness (~1% X0) and service and cables requirements
    Time resolution ~ 10 – 20 ns
  Simple 2D strip readout  No capacitive sharing because we are not targeting good spatial resolution
    No need for high performance low channel count readout  its is an overkill because the spatial resolution is dominated by the drift gap
    1-mm strip pitch  ~ 300 µm [1/sqrt (12)] poor nominal resolution but uniform over a broad track angle range

## Slide 3: 1. What R&D needs still to be finalized to show that the Standard μRWell (as discussed on slide 5 of Kondo’s TIC presentation, leftmost column) provides an option for an MPGD tracker for ePIC even if the hit resolution is inadequate. We would also like to see a time estimate needed to complete this R&D.
Time estimate to complete R&D: here R&D means large area µRWELL prototypes for barrel Outer Tracker modules and End Cap disk  Answer is ~2 to 2.5 years and
  ~6 months to finalize the design
  ~12 months for procurement / fabrication and delivery of the detector parts (mostly from CERN)
  ~3 months assembly and characterization in participating institutions
  ~6 months test in beam and analyzing and finalizing
Opinion within eRD108
  Strongly expressed opinion by several members within eRD108 is that this not a good option for ePIC gaseous trackers
  The simulation is in our opinion not ready to provide the input needed to validate such choice for the trackers
  eRD108 will rally behind the decision by the project and collaboration leaders & build the best detector possible for ePIC
  But there is very little enthusiasm for the members to work on “poor performance” detector subsystem for ePIC

## Slide 4: 2. What additional R&D is needed to make a thin-gap μRWell (as discussed on slide 5 of Kondo’s TIC presentation, 2nd column from the left) an option for an MPGD tracker for ePIC. We want also would like to see a time estimate needed to complete the R&D for a full-size thin-gap μRWell prototype. Again, we note that this should assume the availability of heavy noble gases and the gas should be chose to optimize the stability of the detector.
Thin Gap µRWELL with capacitive-sharing 2D strip readout (~1 mm pitch)
  Large area µRWELL modules: Same R&D challenges as for standard µRWELL +
    Better control of 1-mm drift gap uniformity add a little bit to the challenge
    Single amplification even with Xe  limited detector efficiency (< 90%)
    Time resolution < 10 ns
  Capacitive-sharing 2D strip readout  trying to achieve good spatial resolution over a wide track angle range
    1-mm strip pitch  nominal resolution < 100 µm
    Average resolution over angular range ~ 150 µm  targeted performance

## Slide 5: 2. What additional R&D is needed to make a thin-gap μRWell (as discussed on slide 5 of Kondo’s TIC presentation, 2nd column from the left) an option for an MPGD tracker for ePIC. We want also would like to see a time estimate needed to complete the R&D for a full-size thin-gap μRWell prototype. Again, we note that this should assume the availability of heavy noble gases and the gas should be chose to optimize the stability of the detector.
Time estimate to complete R&D: similar timeline for R&D to standard µRWELL  Answer is ~2 to 2.5 years and
  Additional complication  heavy gas cost and availability (during R&D phase) Xe non available
    8k$ small Kr-bottle last 8h during June 2023 small thin gap prototypes beam test at Fermilab
    R&D would be delayed by the heavy gas  then everything depends on how we define completing the R&D effort
Opinion within eRD108
  We have some reservation regarding single amplification thin gap even with heavy gas
  Pushing the gain from the µRWELL device to reach a good level S/N for time and position resolution performance will very likely lead to operating the detectors at their stability limit
  There won’t be any degree of freedom regarding the operating HV of the detectors
  This might not be way to approach a detector subsystem that will be installed in a collider experiment

## Slide 6: In parallel to developing the requested information about remaining R&D, Matt Posik’s simulation studies should be pursued because they will guide how small the μRWell gap needs to be, i.e., maybe can one live with a drift gap of 2mm instead of 1mm.
2-mm “thin gap” µRWELL does not make much sense in the context we are talking to
  It is basically the worse both worlds
  In fact, ideally we would like to go below 1 mm is this is technically feasible