## Blank Master Schedules - Table
PIP-II PROJECT - High Level Master Schedule
[7 empty] | FY19 |  |  |  | FY20 |  |  |  | FY21 |  |  |  | FY22 |  |  |  | FY23 |  |  |  | FY24 |  |  |  | FY25 |  |  |  | FY26 |  |  |  | FY27 |  |  |  | FY28 |  |  |  | FY29 |  |  |  | FY30 |  |  |  | FY31 |  |  |  | FY32 |  |  |  | FY33 |  |  |  | FY34 |  |  |  | FY35
| Activity | Expectations | Tools / Process / Systems | Targets | Ref | Resp | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
CD | ACTIVITY 1
Research & Development
Design
ACTIVITY 1
Construction & Installation
ACTIVITY 1
Commissioning & Pre-Ops
Key
ACTIVITY 2
CD-0(A)
Dec 2019
PREPARED BY Kelly Krug August 16, 2023
APPROVED BY Project Manager, Luisella Lari, August 17, 2023
CD-1 (A)
Jun 2021
CD-3A
Jan 2024
CD-2/3
Apr 2025
Research & Development
Research & Development
Accelerator
Systems
Detector
Conceptual Design
Infrastructure
Accelerator Systems
Detector
Detector
Conventional Construction
Procurement, Fabrication, Installation & Test
Procurement, Fabrication, Installation & Test
Accelerator Systems
Infrastructure
Commissioning & Pre-Ops
Accelerator Systems
Detector
Commissioning & Pre-Ops
Planned
(A) Actual
Data
Date
Completed
Critical
Path
Level 0
Milestones
CD-4
Aproved Completion
Oct 2034
Early CD-4
Completion
Oct 2032
CD-3B
Oct 2024