## Slide 1: Closeout Report
Wolfram Zeuner; Gerrit van Nieuwenhuizen; and Fulvia Pilat
Electron-Ion Collider
Technical Review of the EIC IR Integration and Auxiliary Far-Forward/Far-Backward Detectors
April 27,2022

## Slide 2: Outline
Review Panel
Charge Questions
Committee Report
  Findings
  Comments
  Recommendations
Conclusion

## Slide 3: Review Panel
Wolfram Zeuner – CERN
Gerrit van Nieuwenhuizen – BNL
Fulvia Pilat – ORNL

## Slide 4: Response to Charge Questions
Are the technical performance requirements appropriately defined and complete for this stage of the project?
YES, but significant effort is needed to validate accelerator and detector required performance

## Slide 5: Comments
There has been excellent progress since CD-1 in assessing and addressing the technical performance in the IR and Ancillary Detector scope
Since the maturity level of the Ancillary Detectors and IR integration at CD3 will ~70% a strategy should be developed to maintain design flexibility and to be able to integrate evolving in-kind contributions
A formal change control process needs to be in place well before CD-2

## Slide 6: Comments
The Project should carefully prioritize the 61 technical recommendation received in the IR and MDI technical review
This committee concurs that the focus should be in addressing dynamic aperture considerations, and in particular the effect of:
- effects of crab cavities
- impact of auxiliary accelerator components such correctors, diagnostics, pumps
- tolerances on the alignment of the interaction plane and crab tilt
- effect of the detector solenoid and coupling correction elements
- higher order modes analysis for the beam pipe

## Slide 7: Comments
Make sure that the collaborators providing in-kind contributions have a clear understanding of the overall detector requirements

## Slide 8: Recommendations
Ensure that WBS 6.06 continues to develop comprehensive dynamic aperture evaluations including effect of crab cavities, auxiliary components and imperfections to demonstrate the requirements technical feasibility before CD-2

## Slide 9: Response to Charge Questions
Are the plans for achieving detector performance and construction sufficiently developed and documented for the present phase of the project?
YES, for the scope presented

## Slide 10: Comments
For B0 make sure that the beampipe does not need to be removed for detector maintenance and upgrade
Make sure the cooling of roman pots is not using liquid or gas inside the vacuum envelope

## Slide 11: Recommendations
Fast track the engineering design of B0 and Roman Pots, before CD2

## Slide 12: Response to Charge Questions
Are the current designs for detectors and electronics readout likely to achieve the performance requirements with a low risk of cost increases, schedule delays, and technical problems?
YES, for detectors. Not enough information was presented on electronics readout.

## Slide 13: Comments
No details about readout systems were presented
The project will benefit from a review of the general readout strategy
Some detectors do not seem to be close to a technology choice at this point

## Slide 14: Recommendations
Develop and review the readout strategy
Provide as soon as possible milestones towards technology choices for the detectors

## Slide 15: Response to Charge Questions
Are the sub-detector fabrication and assembly plans consistent with the overall project and detector schedule?
YES

## Slide 16: Comments
No specific information was presented about the sub-detector fabrication and assembly plans. They will have to be reassessed when the overall project and detector schedule is firmed up

## Slide 17: Recommendations
none

## Slide 18: Response to Charge Questions
Are the plans for detector integration in the interaction region appropriately developed for the present phase of the project?
YES

## Slide 19: Comments
The Committee commends the systematic approach to system engineering and integration and the good progress achieved so far
The complexity of the IR and MDI design calls for focused attention on access: systems will need to be installed, maintained and repaired so and access consideration must be integral part of system design. The Project is aware about it and access is part of the design considerations
A project-wide rigorous engineering change process is critical to design development and effective institutional collaboration

## Slide 20: Comments
It is critical that all collaborating institutes are familiar and on-board with the integration strategy and systems
Product Lifetime Management (PLM) for engineering systems and Asset Management (AM) systems for components and spare parts are being adopted and proving effective at existing facilities. We encourage the EIC project to considering the adoption of formal system management early in the lifetime of the facility.

## Slide 21: Recommendations
Continue making system accessibility a priority in system and sub-system design
Make sure that all collaborating institutes are familiar and on-board with the integration strategy and systems
Consider the adoption of formal engineering and system management system such as PLM (Product Lifetime Management) and AM (Asset Management) early in the life of the EIC facility

## Slide 22: Response to Charge Questions
Have ES&H considerations been adequately incorporated into the designs at their present stage?
YES, but a formal plan for quality control and assurance is needed

## Slide 23: Comments
No specific ES&H information was presented at the review
The Committee believes that ES&H deserve focus and attention in the light of the complexity of the project and the many collaborating institutions
An overall project wide plan for Quality Assurance and Control is needed

## Slide 24: Recommendations
For future review, include an ESH&Q slide in every presentation
Develop and review an overall project plan for Quality Assurance and Control
Make sure you work with the Project to plan your Accelerator Readiness Reviews (ARR) well in advance

## Slide 25: Charge Questions
Are the technical performance requirements appropriately defined and complete for this stage of the project? YES, But significant effort is needed to validate accelerator and detector required performance
Are the plans for achieving detector performance and construction sufficiently developed and documented for the present phase of the project? YES, for the scope presented
Are the current designs for detectors and electronics readout likely to achieve the performance requirements with a low risk of cost increases, schedule delays, and technical problems? YES, for detector readout. Not enough information was presented on electronics readout.
Are the sub-detector fabrication and assembly plans consistent with the overall project and detector schedule? YES
Are the plans for detector integration in the interaction region appropriately developed for the present phase of the project? YES
Have ES&H considerations been adequately incorporated into the designs at their present stage? YES, but a formal plan for quality control and assurance is needed