## Slide 1: MPGD ENDCAP Trackers (ECT)
Incremental Design and Safety Review of the EIC Tracking Detectors March 20-21, 2024
Annalisa D’Angelo
GEM - Rwell technology
ECT project coordinator

## Slide 2: Charge Questions Addressed
Are the technical performance requirements appropriately defined and complete for this stage of the project?
Are the plans for achieving detector performance and construction sufficiently developed and documented for the present phase of the project?
Are the current designs and plans for detector, electronics readout, and services sufficiently developed to achieve the performance requirements?
Are plans in place to mitigate risk of cost increases, schedule delays, and technical problems?
Are the fabrication and assembly plans for the various tracking detector systems consistent with the overall project and detector schedule?
Are the plans for detector integration in the EIC detector appropriately developed for the present phase of the project?
Have ES&H and QA considerations been adequately incorporated into the designs at their present stage?

## Slide 3: Outline
Technical performance requirements
  Scope of the MPGD Endcap Trackers Detector
  Detector Geometry: Envelope and Active Regions
  Pseudo-rapidity coverage: effective ranges
  List of Technical Performance Characteristics
  Detector Performances and Production Plans
  (X,Y) readout – 500 m pitch
  Detector technology
  Detector, Electronics Read-out and Services
  MPGD semi-disks endcap configuration
  Electronic FEBs configuration
  Services
  Fabrication and Assembly Plans
  Timeline
  Workforce
  Detector Integration in ePIC
Summary
Charge 1
Charge 2
Charge 3
Charge 5
Charge 6

## Slide 4: Scope of the MPGD Endcap Trackers
Are the technical performance requirements appropriately defined and complete for this stage of the project?
Charge 1
In May 2023, MC simulations showed that the tracking configuration in the endcap regions of the ePIC detector, which will experience the highest backgrounds in the experiment, would not provide enough hit points in the |η| > 2 region for good pattern recognition.
ePIC tracker geometry before June 2023
Previous Configuration

## Slide 5: Scope of the MPGD Endcap Trackers
Charge 1
Adding two MPGD Endcap Tracking (ECT) disks both in the hadronic and in the leptonic regions increased the number of hits in the |η| > 2 region to improve pattern recognition.
Present ePIC tracker geometry
Present Configuration

## Slide 6
Charge 1
Detector Geometry: Envelope and Active Regions
50 cm external radius
45 cm of active area
considering a 5 cm outer ring for gas frames and services location.
Endcaps Envelope Dimensions -
Disks Outer Radius
MPGD Disk | Max Z Pos (cm) | Disk Outer Radius (cm) | Outer Active Reg. radius (cm) | Calculated Beam pipes radii (mm) | Offset (mm) | Disk Inner Radius (cm) | Inner Active Reg. radius (cm)
HD MPGD 2 | 163.5 | 50 | 45 | 55.8 | 22.5 | 8 | 9.5
HD MPGD 1 | 150.5 | 50 | 45 | 53.1 | 19.9 | 8 | 9.5
LD MPGD 1 | -112.5 | 50 | 45 | 37.7 | -3.1 | 4.5 | 6.0
LD MPGD 2 | -122.5 | 50 | 45 | 39.2 | -3.4 | 4.5 | 6.0
Calculated
Radii
Disks Inner Radius
different for the two HD and LD regions
HD: 8 cm inner radius
9.5 cm radius of active area
LD: 4.5 cm inner radius
6 cm radius of active area
considering 1.5 cm gas frame
Beam Pipes Envelope Radii and Offsets
The geometrical envelopes are available at: https://eic.jlab.org/Geometry/Detector/Detector-20240117135224.html

## Slide 7
-3.61
1.993.44
Charge 1
Pseudo-rapidity coverage: effective ranges
Component | Z (cm) | Inner Active Reg. Radius (cm) | min (deg) | max | Outer Active Reg. Radius (cm) | max | min
HD MPGD 2 | 162 | 9.5 | 3.35 | 3.53 | 45 | 15.52 | 1.99
HD MPGD 1 | 148 | 9.5 | 3.67 | 3.44 | 45 | 16.91 | 1.9
LD MPGD 1 | -111 | 6 | 3.09 | 3.61 | 45 | 22.07 | 1.63
LD MPGD 2 | -121 | 6 | 2.83 | 3.69 | 45 | 20.40 | 1.72
Component | Z (cm) | Inner Active Reg. Radius (cm) |  |  | Outer Active Reg. Radius (cm) |  | 
HD MPGD 2 | 162 | 9.5 | 3.35 | 3.53 | 45 | 15.52 | 1.99
HD MPGD 1 | 148 | 9.5 | 3.67 | 3.44 | 45 | 16.91 | 1.9
LD MPGD 1 | -111 | 6 | 3.09 | 3.61 | 45 | 22.07 | 1.63
LD MPGD 2 | -121 | 6 | 2.83 | 3.69 | 45 | 20.40 | 1.72
The range covered by the MPGD Endcap tracking disks is compliant with requirements.
The minimum value is not larger than 2
it is limited by the outer HD disk location/dimensions
The maximum value is not less than 3.44
it is limited by the inner HD disk location/dimensions

## Slide 8: Technical Performance Requirements
Time resolution 10 ns time to provide tracking timing
  Fast rise time ~ 20 50 ns
  Peaking time 50 ns
  Sampling faster than 50 MHz
Low material budget
  1-2 % X0 - it will be the minimum compatible with the chosen technology
Spatial resolution: 150 m or better
  <150 m intrinsic spatial resolution for perpendicular tracks
  Technological optimizations to retain 150 m resolution for inclined/curved tracks
High Efficiency
  Single detector efficiency ~ 96 –97 % 92 –94 % combined efficiency for two disks
Charge 1

## Slide 9: Detector performance and construction plans
(X, Y) readout is preferred vs (R,) – no FEB on the active area
500 pitch better than 150 intrinsic position resolution
Charge 2
PROs | CONs
The strip length does not vary much along the active area | Alignment is critical
All readout FE hybrids may be located outside the active area | Routes to read-out connectors must be accurately studied
(X, Y) read-out geometry
Are the plans for achieving detector performance and construction sufficiently developed and documented for the present phase of the project?

## Slide 10: Detector Technology
Charge 2
GEM - Rwell Technology
All R&D Studies for EIC disks performed within eRD108 and in synergic collaboration with INFN-LNF and JLAB
GEM- Rwell hybrid configuration has been chosen to increase the gain in the 10 000 20 000 range
2D strip read-out using a “COMPASS-like” scheme
500 pitch guarantees a spatial resolution better than 150 (no need of capacitive sharing)
Technological solutions exist to retain 150 position resolution also for inclined/curved tracks (
A gas gap lager than 3 mm is compatible with single detector efficiency larger than 96%
PCB read-out
Rwell
GEM
cathode
3 mm gas gap

## Slide 11
Charge 3
Detector, Electronics Readout, and Services
>1.99
525 mm
1000 mm
525 mm
1000 mm
Are the current designs and plans for detector, electronics readout, and services sufficiently developed to achieve the performance requirements?
The two half disks will have 2 cm of active area overlap
MPDG Endcaps semi-detectors overlap
The split may be mounted to be either horizontal or vertical

## Slide 12
Charge 3
Detector, Electronics Readout, and Services
>1.99
1000 mm
Are the current designs and plans for detector, electronics readout, and services sufficiently developed to achieve the performance requirements?
The two disks are mounted facing each another
The FEBs are connected perpendicularly to the disks and will not overlap the active area
MPGD Endcaps configuration
by Seung Joon Lee
by Seung Joon Lee

## Slide 13: Services
For each endcap disk (4 disks in total):
16 HV cables
4 gas inlets and 4 gas outlets
32 data cables
32 low voltage cables
2 temperature sensors cables
2 humidity sensors cables
2 inlet and 2 outlet cooling hoses (dry-air or liquid)
Space for 32 RDO cards
Charge 3
4 disks
Electronics Readout based on SALSA ASIC developed at Saclay
All the service requirements have been communicated to the Integration group

## Slide 14: Fabrication and Assembly Plans
Are the fabrication and assembly plans for the various tracking detector systems consistent with the overall project and detector schedule?
Design by end of 2024
2025 - 2026 pre-production and Engineering Test Article
2027 - 2029 production & QA
2030 Commissioning & Installation
Charge 5
MPGD Timeline |  |  | DURATION (years)
START DATE | END DATE | DESCRIPTION | 
3/1/24 | 12/31/24 | Detectors Overall Design | <1
1/1/25 | 12/31/26 | Pre - Production | 2
1/1/27 | 31/12/29 | Production & QA | 3
1/1/30 | 6/1/30 | Commissioning & Installation | 0.5

## Slide 15: Involved Institutions & Workforce
INFN Workforce:
Roma Tor Vergata
Coordinator: A. D’Angelo,
Detector Hardware and QA: E. Sidoretti (PhD) A. Fantini, L. Lanza
Simulation & Reconstruction: L. Lanza, A. Fantini, R. Di Salvo
FEB Electronics: R. Ammendola
Genova
FEB Electronics: Paolo Musico, M. Battaglieri (streaming ro)
Catania
Simulation & Reconstruction: Mariagela Bondi’
The work will be performed in close connection with:
the group of Gianni Bencivenni @ INFN LNF and with the JLab detector group (Kondo Gnanvo, Seung Joon Lee)
Interest in the project has been expressed also by:
BNL (A. Kiselev et al.), Florida Tech.(M. Hohlmann et al.), Temple U. (M. Posik, et al.)
Charge 5

## Slide 16
The assigned envelope will include the detectors and the FEB electronics.
The disks will be attached together and to the support frame under design.
Charge 6
Detector Integration in ePIC
>1.99
>1.72

## Slide 17
Geometrical Acceptance and Technical Performances of hybrid GEM-Rwell endcap trackers have been defined.
A detector layout compliant with requirements has been identified.
Readout Electronics is based on SALSA ASIC developed at Saclay.
Production timeline is consistent with the overall ePIC detector schedule.
The two disk couples are rigidly connected and attached to the inner tracker support via multiple points (~ 6 points/disk).
INFN workforce and laboratories are involved in the construction + BNL, Florida Tech and Temple U. have expressed their interest in the project
Summary

## Slide 18
Back-up Slides

## Slide 19: Technical performance requirements
Are the technical performance requirements appropriately defined and complete for this stage of the project?
Rate Capability
  Not critical ~ 1 kHz/cm2 or less
Radiation Hardness
  Not critical for the detectors
  Important for FEBs and RDO electronics boards
Temperature Stability
  Not critical for the detector performances
  Detector calibration should consider gas pressure variations
Electronics power consumption and cooling
  SALSA ASIC consumption ~ 15 mW/channel at 1.2V 60 W/disk
  Air vs liquid cooling is under study at Saclay – see Irakli’s talk
Charge 1
MPGD Endcaps

## Slide 20: Detector performance and construction plans
(X, Y) readout is preferred vs (R,) – no FEB on the active area
500 pitch better than 150 intrinsic position resolution
Charge 2
PROs | CONs
Direct radial and azimuthal information | The linear density of the azimuthal strips increases by a factor 10 on the inner hole
 | The radial readout hybrid FE overlaps the active area or long flex cables should be used.
 | Radial strip length varies by a factor 10.
PROs | CONs
The strip length does not vary much along the active area | Alignment is critical
All readout FE hybrids may be located outside the active area | Routes to read-out connectors must be accurately studied
(R,) vs (X, Y)
Are the plans for achieving detector performance and construction sufficiently developed and documented for the present phase of the project?

## Slide 21: Risks Mitigation
Are plans in place to mitigate risk of cost increases, schedule delays, and technical problems?
Main risk is related to CERN being the unique producer of -Rwell detector layer
Risk Mitigation: accurate planning
  Early procurement
  In-house detector assembly
  Technology transfer to external manufactures
  Person at CERN to supervise the -Rwell /GEM foils production
  Continuous QA tests
Charge 4

## Slide 22
Charge Centroid (CC)reconstruction method
The track position is determined as a weighted average of fired strips
GOOD FOR ORTHOGONAL TRACKS
Bended tracks
the Charge Centroid method gives a very broad spatial distribution on the anode-strip plane.
The spatial resolutionis strongly dependent on the impinging angle of the track =>
A not uniform resolution in the solid angle covered by the apparatus => Large systematical errors.

## Slide 23
      TPC reconstruction
A possible solution :
The electrons created by the ionizing particle drift towards the amplification region
In the μTPC mode from the knowledge of the drift time and the measurement of the arrival time of electrons, the track segment in the gas gap is reconstructed
The fit of the analog signal gives the arrival time of drifting electrons.
By the knowledge of the drift velocity, the 3D trajectory of the ionizing particle in the drift gap is reconstructed.
Integrated charge as a function of the
sampling time
Example of a track reconstruction using the TPC algorithm.
Comparison of the CC and reconstruction algorithms in function of the impinging angle
drift field
Notes: The idea developed for the ATLAS MicroMegas of the New Small Wheels [10, 11], and also implemented on the BESIII cylindrical GEM [12, 13], is to reconstruct a track segment inside the detector conversion gap rather than a single hit exploiting the analog readout of the signals.