## Slide 1: Alternative Tracker
Goal is always to progress towards using ITS3 based sensors
  Only way to meet full performance requirements
Branchpoints – both based on schedule delays
ITS3 (inner barrel) schedule remains compatible with project schedule but LAS (outer barrel & disks) development is delayed
ITS3 (inner barrel) schedule becomes incompatible with project schedule

## Slide 2: Alternative Tracker – Layout
Hadron and Electron Endcap Disks (HE, EE)
Outer Barrel (OB)
Inner Barrel (IB)
Replaced with two MPGD barrel layers derived from the outer MPGD tracker, specifically its innermost (Micromegas) layer
Branchpoint 1 & 2
Replaced by two or three layers based on the existing ITS2 sensor, as used in ALICE and sPHENIX without EIC specific modifications
Branchpoint 2 only
Replaced with (in total up to) seven near-identical MPGD disks on each side, specifically based on existing uRWELL disks
Branchpoint 1 & 2

## Slide 3: Alternative Tracker – Schedule
Will be further refined leading up to CD-2 based on ITS3 development
Branchpoint | Date | Milestones
1 (LAS Delay) | Q2/Q3 2026 | 1 year for MPGD foils + 3 years construction
2 (ITS3 Delay) | Q3/Q4 2027 | Same 3 years construction as current IB
CD-3
04/2025
Apr 2031
early CD-4
09/2032
CD-4
09/2034
Detector Assembled and Ready for Cosmic Data Taking
Start of
Operations
&
Science
Construction
Oct 2028
IR-6 ready
for installation
June 2030
Barrel Detectors
installed
Oct 2030
Hadron Endcap
Detectors
installed
Jan 2031
Electron Endcap Detectors installed
Early start of
Operations
&
Science
Pre-OPS