## Slide 1
RHIC Schedule (Week 15: July 22nd-July 28th)
Monday (7/22)
Day
  Steering test for sPHENIX
  Change crossing angle to +1.5mrad (~14:00)
Day/Evening
  Collisions for sPHENIX and STAR
Tuesday (7/23)
Day/Evening
  Collisions for sPHENIX and STAR
  Delays due to ODH trip/LINAC RF mod 5
Wednesday (7/24)
Day
  APEX (08:00-00:00)
    Setup for test of tagging He3+ breakup in Hjet/initial measurement
Overnight
  Collisions for sPHENIX and STAR
Thursday (7/25)
Day
  Machine Development (11:00-15:00)
    Beta Squeeze ramp development
Day/Evening
  Collisions for sPHENIX and STAR
Friday (7/26)
Day/Evening
  Collisions for sPHENIX and STAR
Saturday-Sunday (7/27-7/28)
Collisions for sPHENIX and STAR

## Slide 2
Isobutane Timeline
Tuesday (7/23)
Safety Walkthrough (11:00)
Wednesday (7/24)
Turn on gas (sPHENIX)
Friday (7/26)
6 hours without beam
  Power supply work in parallel
Sunday-Monday (7/28-7/29)
1-2 stores with low lumi (6 bunches)
RHIC Schedule (Week 15: July 22nd-July 28th)
*Note: Items in purple are pending approval and subject to change. They are also contingent on prior steps being met—thus delays will propagate down the timeline