## Slide 1
RHIC Schedule (Week 17: Aug 5th-Aug 11th)
Tuesday (8/6)
Day
  sPHENIX request: TPC access followed by special store
    Access 3 hours; other RHIC accesses in parallel
    Power supply feed-through clean sector 5/6
    STAR Controlled access
    LEReC cathode, CeC, RF YS2 QEI.
Evening
  Collisions for sPHENIX and STAR
Wednesday (8/7)
Day
  APEX (08:00-23:00, physics at 00:00)
    Test of tagging He3+ breakup in H-jet
    15+1 hours
Overnight
  Collisions for sPHENIX and STAR
Thursday (8/8)
Day
  sPHENIX Access ~8 hours, starts am.
  DX Training, Access
Evening
  Collisions for sPHENIX and STAR
Friday (8/9)
Day/Evenings
  PHENIX special store: 111x111, 1.5e11/bunch, 1.5mrad crossing angle
Collisions for sPHENIX and STAR
Saturday-Sunday (8/10-8/11)
Collisions for sPHENIX and STAR
* Items in purple pertain to TPC commissioning

## Slide 2
Items to discuss:
Requests from the experiments?
Any other plans with TPC progress?
  Any more requests for special stores? Change in crossing angle?
  TBD for Friday
  Are there requests for any more accesses this week?
  CA for STAR, RF and CeC, LEReC behind sPHENIX accesses Today and Thursday
Machine Development?
  With sPHENIX request for +1.5mrad crossing angle should we schedule time to optimize setup? Beta squeeze ramp?
  None Planned
Other requests?
Looking ahead…DX training?
Depends on Thursday
Reminders:
Next week: August 14th Maintenance
RHIC Schedule (Week 17: Aug 5th-Aug 11th)