## Slide 1
EIC Preliminary Design & Safety Review of the EIC Auxiliary
Far-Forward/Far-Backward Detectors
February 12th, 2024

## Slide 2: What to include
For each of the subsystems:
- the lifetime of each detector
-where what calibrations are done where,
-what is delivered when to BNL, number of pieces sizes and from where
-what Q&A is done of the pieces if arriving at BNL who will be doing this work
-describe if the detector comes assembled or needs to be assembled at BNL
-What workforce / labor do you need from BNL which has not been costed in P6
-If users are coming, please think about what support for the users is needed.
-For the detectors what space and what special conditions the space needs, clean room, gases, size and so on.
-Please have a list of collaborating institutions.

## Slide 3: Charge Questions

## Slide 5
B0 detectors
ZDC
Tel Aviv University, Israel
Ben Gurion University of the Negev, Israel
Hebrew University of Jerusalem, Israel
Riken, Japan
Kobe, Japan
Kansas university, USA
PNNL, USA
UCR, USA
RomanPots and OMD
AC-LGAD consortium :
BNL, USA
IJCLab - Orsay, France
OMEGA , France
IRFU/CEA-Saclay, France
Far-forward: participating institutions
also recently joined Uni’s from Taiwan and
South Korea

## Slide 6: Space needed at BNL for AC-LGAD
Roman Pots AC-LGAD modules: 128 ( 3.2x3.2 cm^2 units) or 512 ( ( 1.6x1.6 cm^2 units)
Off-Momentum detectors : 72 ( 3.2x3.2 cm^2 units) or 288 ( 1.6x1.6 cm^2 units)
B0 tracking: 168 (3.2x3.2 cm^2 units) or 672 ( 1.6x1.6 cm^2 units)
Lumi-PS: 164 (3.2cm x 3.2cm units) or 656 (1.6 cm x 1.6cm units) – total for 4 layers
Space needed at BNL for AC-LGAD sensors production, the bump-bonding, assembly, QA and tests

## Slide 7: B0 -logistic
EMCAL- crystals
EMCAL- SiPMs
Tracker- AC-LGADs :
BNL
Tracker-EICROC
France
Inst.C
Cooling
JLAB/BNL
Support Structure
Purchasing
Assembly
Tests/QA
Inst. A
Inst. A
BNL
BNL
Inst.C
Cooling
Inst.C
Cooling
JLAB/BNL
Support Structure
JLAB/BNL
Support Structure
Final Assembly
Arrival to BNL

## Slide 8: Space needed at BNL for B0 final assembly
        Required Resources and Potential Hazards
              Space Requirements
                300 ft 2 for B0 trackers and calorimeter
              Floor Loading
                No
              Crane Capacity
                No ( only after integration with B0-magnet)
              Power Requirements
                No special requirements
              Environmental Cooling/Humidity Control
                No special requirements
              Low Conductivity Water / Process Cooling Water
                Not required.
              Cryogenics
                Not required
              Gases
                None required.
              Air Supply/Exchange
                N/A
              Clean Space
                Standard Lab space
              Amenities
                What work tables/chairs/cabinets/furnishings will be required?
                Standard benches for test equipment and assemble. Electronics + computing racks. Desk and chair working space for 4 people.
              Special Equipment/Tooling
                N/A
              Security
                N/A
              Waste Production
None
            Work will include:
assembling tracker layers on the frame , assembling calorimeter modules on the frame, configuring data acquisition systems, operations testing, cosmic tests, alignments, long term stability tests.
Detector assembly and commissioning is expected to continue for 9-12 months.

## Slide 9: RP/OMD- logistic
RP/OMD: AC-LGADs
BNL
RP/OMD: EICROC
France?
Cooling
BNL
Support/Vacuum :
BNL
Purchasing
Assembly
Tests/QA
RP layers assembly
BNL
RP/OMD
BNL
BNL
BNL
BNL
BNL
Final Assembly,
Tests,
DAQ tests
At BNL:
Space needs at BNL

## Slide 10: Space needed at BNL for B0
        Required Resources and Potential Hazards
              Space Requirements
                300 ft 2 for B0 trackers and calorimeter
              Floor Loading
                No
              Crane Capacity
                No ( yes, only after integration with B0-magnet)
              Power Requirements
                No special requirements
              Environmental Cooling/Humidity Control
                No special requirements
              Low Conductivity Water / Process Cooling Water
                Not required.
              Cryogenics
                Not required
              Gases
                None required.
              Air Supply/Exchange
                N/A
              Clean Space
                Standard Lab space
              Amenities
                What work tables/chairs/cabinets/furnishings will be required?
                Standard benches for test equipment and assemble. Electronics + computing racks. Desk and chair working space for 4 people.
              Special Equipment/Tooling
                N/A
              Security
                N/A
              Waste Production
None
            Work will include:
assembling tracker layers on the frame , assembling calorimeter modules on the frame, configuring data acquisition systems, operations testing, cosmic tests, alignments, long term stability tests.
Detector assembly and commissioning is expected to continue for 9-12 months.

## Slide 11: ZDC -logistic
EMCAL- crystals
Inst 1
EMCAL- SiPMs
Inst1
HCAL- Scint, foils, Fe :
UCR
HCAL - SiPMs:
UCR
Cooling
Inst. C
Support Table
JLAB
Purchasing
Assembly
Tests/QA
Inst. A
Inst. A
at UCR
at UCR
Inst.C
Inst.C
JLAB
JLAB
Final Assembly
Where? When?
Arrival to BNL
Space needs at BNL

## Slide 12: Space needed at BNL for ZDC
        Required Resources and Potential Hazards
              Space Requirements
                ca.500 ft 2
              Floor Loading
                Yes, ca 3300 kg
              Crane Capacity
                Yes , ca 3300 kg
              Power Requirements
                No special requirements
              Environmental Cooling/Humidity Control
                No special requirements
              Low Conductivity Water / Process Cooling Water
                Not required.
              Cryogenics
                Not required
              Gases
                None required.
              Air Supply/Exchange
                N/A
              Clean Space
                Standard Lab space
              Amenities
                What work tables/chairs/cabinets/furnishings will be required?
                Standard benches for test equipment and assemble. Electronics + computing racks. Desk and chair working space for 4 people.
              Special Equipment/Tooling
                N/A
              Security
                N/A
              Waste Production
None
            Work will include:
assembling calorimeter modules on the table, configuring data acquisition systems, operations testing, cosmic tests, alignments, long term stability tests.
            Detector assembly and commissioning is expected to continue for 12–18 months.

## Slide 13
Low-Q2 tagger - tracker :
Lumi - photon calorimeter:
Low-Q2 tagger - calorimeter :
Glasgow, UK
York, UK
JLAB/BNL
W&M, USA
Far-backward: participating institutions
Prague, CZ
Lumi - pair-spectrometer :
York, UK
Houston, USA
Prague, CZ
Kraków, Poland
York, UK
Prague, CZ
Prague, CZ
Low-Q2
tagger1
Low-Q2
tagger2
Lumi system
IP
15
  Weekly meetings to discuss engineering and integration aspects with JLAB/BNL designers, collaborating institutes
Kraków, Poland

## Slide 14: Low-Q2
Timepix4 +Si :
Glasgow, UK
EMCAL :
Inst A
EMCAL - SiPMs:
Inst A
Cooling :
Inst. B
Support Table
JLAB
Purchasing
Assembly
Tests/QA
Tracking layers: Glasgow, UK
Tracking layers:
Glasgow, UK
EMCAL
Inst A
EMCAL
Inst A
Inst. B
Inst.B
JLAB
JLAB
Final Assembly
Where? When?
Arrival to BNL
Space needs at BNL

## Slide 15: Space needed at BNL for Low-Q2
        Required Resources and Potential Hazards
              Space Requirements
                300 ft 2 for trackers and calorimeters
              Floor Loading
                No special needs
              Crane Capacity
                Not required.
              Power Requirements
                No special requirements
              Environmental Cooling/Humidity Control
                No special requirements
              Low Conductivity Water / Process Cooling Water
                Not required.
              Cryogenics
                Not required
              Gases
                None required.
              Air Supply/Exchange
                N/A
              Clean Space
                Standard Lab space
              Amenities
                What work tables/chairs/cabinets/furnishings will be required?
                Standard benches for test equipment and assemble. Electronics + computing racks. Desk and chair working space for 4 people.
              Special Equipment/Tooling
                N/A
              Security
                N/A
              Waste Production
None
Trackers work will include: a) assembling tracker frame hardware and table, b) configuring data acquisition systems, c) performing Timepix4 module installations, d) operations testing, e) cosmic tests, and alignments f) long term stability tests.
Calorimeter work will include: a) assembling hardware on the table b) configuring data acquisition systems, c) operations testing, d) cosmic tests, and alignments e) long term stability tests.
            Detector assembly and commissioning is expected to continue for 9-12 months.

## Slide 16: Lumi Pair Spec (PS)
Calorimeter materials - York
Trackers –
BNL/Houston/TelAviv
Magnets/Vacuum Chamber
BNL
Support Table
JLab
Purchasing
Assembly
Tests/QA
Calorimeters - York
Calorimeters - York
Trackers
BNL (as part of AC-LGad efforts)
Trackers - BNL/Houston/Tel Aviv
BNL/JLab
BNL/JLab
Final Assembly
Calorimeters/trackers – 6 months before pre-ops
Magnets – 12 months before pre-ops
Calorimeter Electronics - York

## Slide 17: Lumi Direct Photon Detector (DPD)
Calorimeter materials – York/Krakow
Support Table
BNL/JLab
Purchasing
Assembly
Tests/QA
Calorimeters – Krakow/York
Calorimeters – Krakow/York
BNL/JLab
BNL/JLab
Final Assembly
6 months before pre-ops
Calorimeter Electronics - Krakow

## Slide 18: Space needed at BNL for Lumi Detectors (PS/DPD)
        Required Resources and Potential Hazards
              Space Requirements
                500 ft 2 for PS trackers and PS/DPD calorimeters
              Floor Loading
                No
              Crane Capacity
                No
              Power Requirements
                No special requirements
              Environmental Cooling/Humidity Control
                No special requirements
              Low Conductivity Water / Process Cooling Water
                Not required.
              Cryogenics
                Not required
              Gases
                None required.
              Air Supply/Exchange
                N/A
              Clean Space
                Standard Lab space
              Amenities
                What work tables/chairs/cabinets/furnishings will be required?
                Standard benches for test equipment and assemble. Electronics + computing racks. Desk and chair working space for 4-6 people.
              Special Equipment/Tooling
                N/A
              Security
                N/A
              Waste Production
None
            Work will include:
assembling tracker layers on the frame , assembling calorimeter modules on the frame, configuring data acquisition systems, operations testing, cosmic tests, alignments, long term stability tests.
Detector assembly and commissioning is expected to continue for 3-6 months.

## Slide 19: Workforce for Lumi Pair Spec
Workforce request/requirements from BNL very limited
  1 FTE tech support for 3-6 months to support assembly/cabling efforts
Workforce contribution from collaborating institutions
  York
    2 FTE for 2 months (PDRA + faculty)
    1 FTE for 3 months student
  Houston
    1 FTE for 1 month (faculty)
    1 FTE for 2 months student
  Tel Aviv
    1 FTE for 2 month (faculty)
Work/office space for users will be needed (outlined in space requirements)

## Slide 20: Workforce for Lumi Direct Photon Detector
Workforce request/requirements from BNL very limited
  1 FTE tech support for 3-6 months to support assembly/cabling efforts
Workforce contribution from collaborating institutions
  Krakow
    2 FTE for 2-3 months (PDRA + faculty)
    1 FTE for 2-3 months student
  York
    Overlap with support for PS in some aspects
      Low luminosity WSciFi variant
Work/office space for users will be needed (outlined in space requirements)

## Slide 21: Lumi Pair Spec Calorimeters – Prototyping QA
Lumi Pair Spec calorimeter prototype construction underway at York
~5-10 prototype modules by end of year
Beam tests for prototype modules planned
  Mainz (A2) – 800/1600 MeV e- and up to 800/1600 MeV real γ
    Planned – Late 2024
    Initial uniformity/performance tests
  JLab Hall D (GlueX) beam tests
    Planned for Q1/Q2 2025 (depending upon JLab/GlueX beam schedule)
    Performance/shower reconstruction testing
Iterate/improve upon design as needed following beam test results

## Slide 22: Lumi Pair Spec Calorimeters – Other Details
Lumi Pair Spec modules (3 x 20 x 3 – 180 total) will be assembled at York
  Shipped to BNL as modules, full detectors assembled there
    Minimum of 6 months before pre-ops period
  Each module is ~1kg in weight
  Pair Spec – 2x3x20 – 120 modules
  DPD – 3x20 – 60 modules (for WSciFi variant)
QA on modules
  Cosmics/beam tests (Mainz/JLab) upon construction
  Subsequent cosmics tests on arrival at BNL
Calibrations – From QA testing
  Procedure being developed
10+ year lifetime for PairSpec in operation
  Can potentially extend by cycling layers periodically (between runs?)

## Slide 23: Quality Assurance
During the engineering design phase:
considering to production of mockups and engineering test articles to insure the proper functionality and quality.
Full-chain integration with DAQ at early stage.
Beam tests, etc.
During the production and testing:
developing a document with a detailed steps of production and test procedures
production yield control, noise level characterization, light yield, and other parameters.
X-ray, source and beam tests
Hardware status will be included into the data-base.

## Slide 24: Environment, safety, and health (ES&H)
We will be using the appropriate ES&H and Radiation Safety measures as dictated by the participating universities and labs(BNL/JLAB). All personnel working within the labs have to have the appropriate training to ensure adherence to these safety protocols.
Flammable materials: fibers
Use of proper storage, extinguishing system, keep away from the open fire or hot temperature.
Electrical/ Cooling/Trip safety:
For operation with HV and Cooling: we will ensure that these are mechanically secure and not a trip hazard, have proper warning signs and follow the lab procedures for electrical safety.
Operation nearby magnets/magnetic fields:
In coordination with accelerator team: flashing signs or lights indicate magnet is on and magnetic fields may be present. Posting signs.
Operation near the beam-pipe and vacuum:
we will require that anyone working near the far-forward/backward detectors to wears ear protection, and will post signage to that effect.

## Slide 25: Timeline
Detailed schedule for each sub-detector component in P6.
Preliminary design review of ANC detectors in Feb 2024, next review is expecting in May 2025.
The installation of far-forward equipment is at later stage ( after accelerator commissioning ). All scattering chambers that house detectors will be installed from the start of pre-ops. The detector packages will be installed later, after achieving a stable operation of the accelerator.
Luminosity detectors has to be at start of pre-ops.
FF/FB PDR
Feb 2024
FF/FB FDR
May 2025
FF/FB review
Apr 2022
CD3A
Nov
2023
CD3B
Oct
2024
CD2/3
Apr
2025
early
CD4
Oct 2032
CD4
Oct
2034
Pre-OPS
Apr. 2031
now
R&D, TDR,
engineering test articles
assembly and tests

## Slide 26: Installation
IR-6 Far-Forward Region
B0 Tracker and Calorimeter timeline needs to be aligned with accelerator schedule
Off-momentum trackers and Roman Pots will install first only what is needed to be able to install the detectors at a later stage, timeline needs to be aligned with accelerator schedule
ZDC timeline needs to be aligned with accelerator schedule
IR-6 Far-Backward Region
Luminosity Monitor timeline needs to be aligned with accelerator schedule
Low Q2 Tagger will install first only what is needed to be able to install the detectors at a later stage, timeline needs to be aligned with accelerator schedule