## Slide 1
Maddie Schoell
2024 Accelerator Safety Workshop
October 8-10, 2024
DOE O 420.2D Implementation
from Fermilab’s perspective
FERMILAB-SLIDES-24-0258-ESH

## Slide 2: Outline
Fermilab’s Implementation Plan
Community Engagement and Sharing

## Slide 3: Fermilab’s Implementation
2D Update
FY23 PEMP Notable
FSO ASE Comments
Test Stand RGDs now accelerators
Update SAD to include unmitigated and mitigated risk discussion
USI Process: include RGD and obtain FSO approval
“Update and externally validate, an updated ASE and SAD to reflect the requirements in DOE O 420.2D, the current configuration, and a consistent authorized operating limit.”
Implement Credited Controls for ODH
Include Risk Matrices in SAD
Updates to ASE:
  explicitly list out all required shielding, rad monitors
  Specify applicability, basis, requirements, and response to violations
Include analysis in ASE, don’t reference another document

## Slide 4: Fermilab’s Implementation
Fermilab completed the updates to the USI Program, RGD Program, and SAD Chapters/ASEs and commissioned an independent Accelerator Readiness Review (ARR) in Aug 2023
  Updates included new consistent templates, expanded risk tables, and additional Credited Controls (i.e., ODH)
  ARR to determine if the SADs and ASEs met 420.2D requirements
The ARR generally concluded that Fermilab had appropriately updated the SADs and ASEs in accordance with DOE O 420.2D
  The ARR had additional recommendations that needed to be addressed
  FSO also had additional comments related to the updated ASE
Following the ARR, the Laboratory Director required completion and independent verification of SAD/ASE updates before resuming main accelerator complex operations

## Slide 5: Fermilab’s Implementation Plan
New formal SAD/ASE Project Team established
  Deputy COO as Project Director, helped with communications between Team and Senior Leadership/FSO
  New MCI analysis methodology developed, each accelerator segment performed new analysis
  Update USI Program
  New phased review approach:
    Sequential IRRs of each segment of the Fermilab Main Accelerator focused only on MCI, SAD and ASE
    After successful IRR, FSO authorized resumption of operation of associated segment
    Full ARR of entire main accelerator after all IRRs complete
    After ARR of main accelerator, continue IRR/ARR process for Test Stand Accelerators
Biggest lift to complete IRRs/ARRs

## Slide 6: Fermilab’s Implementation Plan
Accelerator Facility / Accelerator / Segment | IRR | ARR | Current Status
Common Information, Support Facilities, Fermilab Main Accelerator: Linac & MTA | IRR 1a – 11/29/2023 | ARR 1 – 3/19/2024 | Approved 1/11/2024 Also approved USI Program 1/11/2024
Fermilab Main Accelerator: Booster, 8 GeV, BNB | IRR 1b – 1/9/2024 |  | Approved 3/7/2024
Fermilab Main Accelerator: Main Injector, NuMI | IRR 1b – 1/9/2024 |  | Approved 3/7/2024
Fermilab Main Accelerator: Muon Campus, Switchyard, Meson, Neutrino | IRR 1c – 1/23/2024 |  | Approved 3/28/2024
Test Stand Accelerators: CMTS1, PIP2IT, VTS, STC | IRR 3 – 5/14/2024 | ARR 3 – 6/11/2024 | Approved 6/26/2024
FAST Accelerator | IRR 2 – TBD | ARR 2 – TBD | Undergoing facility modifications, IRR/ARR dependent on work completion

## Slide 7: Community Engagement and Sharing
DOE Assist Visits helped us understand:
  How to interpret the new definition of accelerators
  What this meant for test stands
  What worked well at other Labs and how that might help improve something at our own Lab
Monthly community calls
  Continued discussions on implementation plan
  Guidance on how to address areas still in questions: DT generators, ODH
  Sharing resources, scheduling reviews/obtaining reviewers, sharing program documents
  Sharing and bringing home best practices and lessons learned

## Slide 8: Community Engagement and Sharing
Every Lab is unique  implementation approaches varied
  Xx Labs had some kind of extension approved
  Different methods of finalizing implementation used:
    ARR(s)
    ASO Program Element review
    Via OIAIs / site office approvals (no external reviews)
  Inventory of accelerators managed under ASO shifted, and by different amounts
    One lab reduced their inventory by 1
    One lab increased their inventory by ~100

## Slide 9: Community Engagement and Sharing
Real comradery amongst our community that you don’t see in many other places
Let’s figure this out together
Let’s do this together
We did it together!

## Slide 10: Questions?