## Slide 1: Shutdown ‘24
Date November 15th, 2024
Paul Sampson

## Slide 2: Agenda
General information
Status
Progress
Schedules
Summary

## Slide 3: General Information:
Late start due run extension
Duration uncertain
Injector programs ran to November

## Slide 4: CAD Status
EBIS running setup
LINAC Booster and NSRL Shutdown began November 1st and continues
AGS, AtR and RHIC Shutdown began October 21st and continues

## Slide 5: RHIC HVAC
1004B Package unit #4- replacement for failed coil (warrantee). Work to be completed this month.
1004B Package unit #3- replacement installation
under way.A10 house
L18A package unit replacement underway
1007W Bard until replacement under way
1004A package unit shipping next week
1007 dehumidifier- repairs underway
Alcove units: maintenance, replacement and repair: 1A, 1B, 5A, 5B, 9A, 9B, 11A,11B and 11C

## Slide 6: Systems Status:
Cooling towers:
Mandatory cleanings and shutdown, as needed.
Tower 1010 on for sPHENIX 80k circulation**
Tower 7 off, cleaned awaiting contractor for switching gear recall remediation.
All RF systems secured.
Most magnet systems secured, some testing, NSRL and Booster towers on for EBIS tuning.
**Leak found in heat exchanger, isolated, sPHENIX magnet “floating" until remediation completed

## Slide 7: Progress so far:
LINAC:
Maintenance progressing on schedule.
Upgrades schedule permitting
55 total jobs submitted and scheduled
EBIS:
Tuning with beam down EtB will continue.
Cathode swap to follow.
Trap aperture change to TBD.

## Slide 8: Progress:
EBIS – 19 weeks under way- Setup with beam at present.*
LION – 9 weeks to start in December.
LINAC maintenance continues.
BLIP:
  Target cooling upgrades on track for January 24th completion.
  Lighting repair ongoing.
  Windows replacement in December.
Booster:
  Vacuum (10 weeks) Under way.
  RF PA replacement under way.
  911 chilled water tower: progressing well
AGS : Cable trench remediation Is under way.
RHIC: Y12 valve box repair, locate repair other leaks: Under way
RHIC R&R:
  E-Lens: Briefing meeting held, work to start today.

## Slide 9: Booster and NSRL:
Vacuum work in BtA & Sectors F going well.
Bakeout as early as next week.
RF A3 PA modification is underway.
911 Chilled water tower replacement installation progressing on schedule (Chilled water for BRF).
NSRL tower temperature control valve replacement after EBIS is shutdown.
E4 Skew Quad installation complete.
36 other jobs approved; work is progressing on schedule.

## Slide 15: AGS and AtR
L18A trench remediation is underway.
Tunnel lights are on!
RF work completed.
Snake cold head replacement awaiting delivery.
Main Magnet water drained and refilled (tritium remediation).
Annual Maintenance.
45 jobs total scheduled

## Slide 18: RHIC
Leak detection in the cryogenics system.
Yellow Valve Box 12 leak repairs pending.
e-Lens infrastructure removal started today.
  Break vacuum, grind cryogenics only after assessment.
Cryogenics Tower 7 cleaned and shut down.
  Switchgear remediation (manufacturer’s recall) to be addressed mid December.

## Slide 20: Tower 7

## Slide 21: End of shutdown schedule: Injectors

## Slide 22: AGS and RHIC start Up

## Slide 23: Early scenario?

## Slide 24: Full schedules and timelines:
Available on the web “This Week”.
Discussed at meetings:
Supervisor’s meeting (weekly).
Shutdown “Time” Meetings (bi-weekly).
Links:
  This Week
  Shutdown Status
  JRS
  Web Status
  Overview Project

## Slide 25: Summary and comments:
This shutdown is evolving:
Work plans developed are dynamic and made able to adapt.
Large amount of work and coordination.
High risk jobs need careful scrutiny.
Resources:
Supervisor’s meeting (weekly).
Shutdown “Time” Meetings (bi-weekly).
Links:
  This Week
  Shutdown Status
  JRS
  Web Status
  Overview Project

## Slide 26
Thank you