## Slide 1
Agenda
(https://indico.bnl.gov/conferenceDisplay.py?confId=2490)
Status Reports / Discussion:
  Steel preparation  See next page
  Power Supply Preparation/Dump Resistor
P. Rosas: No work done last week. Tue. morning one Tech worked on the PS (not sure for how long when he wrote) … Plan to work in mid-Nov. to mid-Dec. to finish, if nothing else breaks down.
  Quench Protection / DAQ Preparation
Z. Altinbas: Plan to do the noise measurement (for the PXIe system) that Carl asked for.
  Cryo Preparation
  Valve Box Extension (the end of Oct. ?)
  Mag. Measurements

## Slide 2
sPHENIX HIGH FIELD TEST RETURN STEEL STATUS
IF RIGGERS ARE AVAILABLE NEXT WEEK, WE WILL BE ABLE TO ASSEMBLE THE SIDE WALLS
HOLES IN MIDDLE BRACKETS NEED TO BE OPENED FOR LARGER BOLTS
END WALL SHIMS ARE PRESENTLY BEING DRILLED
LEFT AND RIGHT SIDE BOTTOM SIDE WALLS COMPLETE
10/25/16
Jon told us: We need welders to cut and put up the end walls, which has just become possible (since yesterday).