## Slide 1: Annual NASA Review of the NSRL Performance: Action Items from last year
20 November 2024
Mike Sivertz

## Slide 2: Action Items
1) Staffing needs:
Beamline Scientist (1 position to be posted soon) HIRED
NSRL Operators (1 hired + 2 open posts) 1 HIRED + 0.5 READY TO JOIN
2) Lack of meeting NASA & DOD program requirements in 2022/2023
EBIS Upgrade and Tandem Safety Review NSRL FAILED TO DELIVER BEAM
FOR RUN 22C, AND STRUGGLED WITH EEBIS STARTUP IN 23AB
3) NSRL Extension/Trailer to allow more densely packed schedule
Unloading/Loading, Equipment preparation and Set-up INSTALLED
4) Need for communication of scheduling approach impacting beam delivery
Better communication identifying risks and mitigation strategy IN PROGRESS
5) NSRL Maintenance and upgrade technical, cost, schedule SOME PROGRESS MADE
6) Costed extension (basis of estimate for 24A/B) & new contract development DONE

## Slide 3: Watchlist - Action Items
7) Power Supply Status (Funaro + Rosas)
List of spare parts for NSRL beam line power supplies
Discussion of which PS should be replaced rather than maintained
New EEBIS Collector PS INSTALLATION ON HOLD
8) GCR Sim Cut Off Chamber (Hock) ON HOLD
Software incomplete - Further development on hold pending hardware
Hardware incomplete - Making progress
Scheduled for completion Fall of 2023
9) NSRL Development and Test Station (Curcio, Jao) (JAO OUT ON DISABILITY)
Hardware in place (Jao) DONE
Software under development (Clark) IN PROGRESS
10) New 1024 1x1 cm2 pixel chamber for upstream beam imaging replacing 302
On hold pending additional staff ON HOLD

## Slide 4: Watchlist - Action Items
11) Air Conditioning (Middleton)
Support Rooms – replaced
Animal Rooms – In preparation (See Jameela’s talk later) INSTALLED.
HUMIDITY CONTROLS FOR EACH ROOM BEING ADDED BEFORE 3/2025.
12) Heat sinks for D6 Septum Magnet PS (Marneris, Mahler) IN PROGRESS
Installed summer of 2022, injecting noise into the D6 PS
New Heat Sinks removed.
Replacement Heat Sinks of the original design being made, for future use.
COMPLETION BY 1/1/2025
13) ARC-20 PS controls (Rosas) OPERATIONAL
Testing of feedback systems complete
PS performance improved and stable.
14) Building Maintenance – 957 & 958 (Hock/Middleton) ONGOING