## Slide 1: EIC Project News
E.C. Aschenauer (BNL), R. Ent (JLab)
Co-Associate Directors for the EIC Experimental Program
ePIC Bi-Weekly
February 20th, 2025

## Slide 2: Outline
General EIC Project Update
Subprojects Musings
Detector Path to CD-2 and CD-3 (reviews, reviews, reviews)
International Engagement and In-Kind Contribution Status

## Slide 3: Slide from Sergei Nagaitsev: Can You Spot the Four Design Changes?
1
2
3
4
2023
2025

## Slide 4: EIC Concept 2025 (Electron Injector Change)
Accelerator Status in a glance:
Polarized ion/proton source
Ion injection and initial acceleration systems – Linac (200 MeV), Booster (1.5 GeV), AGS (25 GeV)
Hadron Storage Ring (40-275 GeV) – HSR
Electron Pre-Injector (750 MeV linac) – EPI
Electron Rapid Cycling Synchrotron (0.75 GeV – top energy) – RCS
Electron Storage Ring (5 GeV – 18 GeV) – ESR
Interaction Region(s) – IR
Hadron Injection Cooling System
Ultimate EIC Performance Parameters:
High Luminosity: L= 1033 – 1034cm-2sec-1
Highly Polarized Beams: 70%
Large Center of Mass Energy Range: Ecm = 28 – 140 GeV
Large Ion Species Range: protons – Uranium
Large Detector Forward Acceptance and Low-Background Conditions
Possibility to Implement a Second Interaction Region (IR)

## Slide 5: Slide from Jim Yeck: Priorities for 2025 and 2026
Priorities for 2025 include:
  Execute the CD-3A and CD-3B procurements.
  Prepare plans for addressing the “portfolio” of project dependencies including the Removal and Repurposing (R&R) of RHIC facilities (IP6 prepared for ePIC).
  Define subprojects and prepare a CD-2 quality performance baseline for the entire project (all subprojects).
  Conduct reviews to assess status of CD-2 preparation for each subproject and prepare the collider subproject for DOE approvals in 2026.
RHIC will run through December 2025 and the R&R work will immediately proceed.
Complete the DOE reviews needed to start EIC construction in 2026 with the approval of the collider subproject. Detector should be baseline ready.

## Slide 6: Construction is starting: CD-3A
Actively Cooled Beam Screen Material
Cryo Beam Position Monitor (BPM) Buttons and Silicon Dioxide (SiO2) cables
Interaction Region (IR) Super Conducting (SC) Strand for IR SC Magnets
Electron Storage Ring (ESR) 591 MHz 1-Cell Cryomodule First Article
Design and Fabrication of One 2K Satellite Refrigerator Plant
Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter
Scintillating Fibers for the Detector Barrel and Forward EM Calorimeters
Silicon Photomultipliers for the Detector Forward Hadronic Calorimeter
Steel and Tungsten for the Detector Forward Hadronic Calorimeter
Detector Solenoid Magnet Design and Fabrication and Conductor
Unit Substations for Infrastructure
Accelerator
Detector
Infrastructure
Approved and Authorized – Procurements In Progress

## Slide 7: Construction is starting: CD-3B
Electron Storage Ring (ESR) Dipole Magnets
Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement
ESR Magnetic Measurement Bench
APS Quadrupole Magnet Refurbishment, Testing, and Measurement
ESR APS Quadrupole Magnetic Measurement Stand
* Lead Tungstate Crystals for the Detector Backward Electromagnetic (EM) Calorimeter - Batch 3 and Batch 4
* Scintillating Fibers for the Detector Barrel - Bath 2 and Forward - Batch 2 EM Calorimeters
* Steel for the Detector Forward Hadronic Calorimeter
Detector Solenoid Magnet Power Supply
Detector Electronics Versatile Link Plus Transceiver (VRTX+) and Low Power Giga-bit Transceiver (lpGBT)
Detector Endcap Structures – Flux Return Steel
Accelerator
Detector
* Continuation of CD-3A contracts
Approved and Waiting for Authorization – Preparing procurements

## Slide 8: EIC and Subprojects – Preparation for CD-2 and CD-3
Science Program starts after Subproject 3 is complete. |  |  |  |  |  | 
Subproject 1 - Accelerator – HSR, ESR, INF |  |  |  |  |  | 
 | Subproject 2 - IR Integration, SC Magnets, Detector |  |  |  |  | 
 |  | Subproject 3 - Electron Injector, Infrastructure |  |  |  | 
 |  |  | Subproject 4 - Full EIC Capabilities |  |  | 
Mission Need is met after Subproject 4 is complete.
One integrated project delivery plan for the EIC aligned with annual funding constraints

## Slide 9: Slide from Jim Yeck: EIC Subproject Plans
Project Office Integrated Support, CD-3A, CD-3B, …. (L. Lari) |  |  |  |  |  |  |  |  |  | 
 | NYS Infrastructure Project (C. Folz) |  |  |  |  |  |  |  |  | 
SP |  | Collider – Infrastructure, HSR, ESR, Installation (C. Folz, SPM) |  |  |  |  |  |  |  | 
SP |  |  | Electron Injector – Infras., LINAC, RCS, Install (Q. Wu, POC for April Review) |  |  |  |  |  |  | 
SP |  |  | IR SC Magnets, Crab Cavities, Integration, Install |  |  |  |  |  |  | 
 |  |  | Detector, Integration, Install |  |  |  |  |  |  | 
SP |  |  |  |  |  |  |  | EIC Full Capabilities (K. Wilson, POC) |  | 
Project Office, CD-3A execution underway
NYS Project execution underway
Collider into construction in 2026
IR, ePIC, E-Injector baseline quality in 2026
▲ DOE mini-IPR Jul/Aug 2025 Assesses Tailoring Strategy and Project Execution Plans
▲ DOE IPR in 2026 supports CD approvals

## Slide 10: Science at Early Accelerator Operations and at Mission Need
RCS:
7nC / bunch Add an accumulation ring to reach 28 nC / bunch
5 – 10 GeV polarized e- and add RF to accelerate to 18 GeV electrons
HSR:
100 – 250 GeV polarized p Update PS to reach 275 GeV protons and 110 GeV/u nuclei
100 GeV/u nuclear beams add 41 GeV bypass to get full HSR beam energy capabilities
cooling at injection energy
Proposal for the early science is driven by
  Alignment with expected order in commissioning the collider
  Ramp up of performance that comes with operational experience
  Start of the promised NSAC/NAS science program
  Early access to new physics results and high impact publications, i.e. PRLs …
ESR:
7nC / bunch Add more RF cavities to operate at 18 GeV electrons
5 – 10 GeV polarized e- and 28 nC / bunch
Commissioning – Science
Full EIC Capabilities – Mission Need
Similar as you have seen many times

## Slide 11: Proposal for EIC Science Program in the First Years
Year - 1
Start with Phase 1 EIC
New Capability:
Commission electron polarization in parallel
Run:
10 GeV electrons on 115 GeV/u heavy ion beams (Ru or Cu)
Physics:
Saturation & Structure of Nuclei
(nuclear PDF & nFF)
Year - 2
Phase 1 EIC
+ electron polarization
New Capability:
Commission proton polarization in parallel
Run:
10 GeV polarized electrons on 130 GeV/u Deuterium
Physics:
free vs. bound proton structure
Run:
Last weeks 10 GeV electrons on 130 GeV transversely polarized protons
Physics:
spatial and dynamical structure of QCD
Year - 3
Phase 1 EIC
+ electron polarization
+ proton polarization
New Capability:
Commission running with hadron spin rotators
Run:
10 GeV polarized electrons on 130 GeV transverse polarized protons
Physics:
spatial and dynamical structure of QCD
Run:
Last weeks switch to longitudinal proton polarization
Physics:
Spin structure of the proton
Year - 4
Phase 1 EIC
+ electron polarization
+ proton polarization
+ operation of hadron spin rotators
New Capability:
Commission hadron accelerator to operate with not centered orbits
Run:
10 GeV polarized electrons on 100 GeV Au
Physics:
Saturation & Structure of Nuclei
(nuclear PDF & nFF)
Run:
10 GeV electrons on 250 GeV transverse and longitudinal polarized protons
Physics:
spatial and dynamical structure of QCD
Spin structure of the proton
Year - 5
Phase 1 EIC
+ electron polarization
+ proton polarization
+ operation of hadron spin rotators
+ operation of hadron beams with not centered orbits
Run:
10 GeV polarized electrons on 100 GeV Au
Physics:
Saturation & Structure of Nuclei
(nPDF & nFF)
Run:
10 GeV electrons on 166 GeV transverse and longitudinal polarized He-3
New Capability:
Commission running with polarized He-3
Physics:
flavor dependent spatial and dynamical structure of QCD
flavor dependent spin structure of the nucleon
Time to install additional ESR RF and HSR PS to
reach design Current and max. Energies
Similar as you have seen – with science examples but you get to fill in

## Slide 12: Proposal for EIC Science Program in the First Years
Year - 5
Year - 6
Year - 7
Phase 1 EIC
+ electron polarization
+ proton polarization
+ operation of hadron spin rotators
+ operation of hadron beams with not centered orbits
New Capability:
Commission ESR & HSR at max. energy and beam currents
Run:
18 GeV polarized electrons on 275 GeV/u polarized (longitudinal & transverse) proton beams
Physics:
spatial and dynamical structure of QCD at the lowest x
flavor dependent spin structure of the nucleon at the lowest x
Phase 1 EIC
+ electron polarization
+ proton polarization
+ operation of hadron spin rotators
+ operation of hadron beams with not centered orbits
+ operation of ESR & HSR at max. energy and beam currents
New Capability:
Operate HSR with 41 GeV bypass
Run:
5 GeV polarized electrons on 41 GeV transverse polarized proton beams
Physics:
spatial and dynamical structure of QCD in the valence quark regime
Phase 1 EIC
+ electron polarization
+ proton polarization
+ operation of hadron spin rotators
+ operation of hadron beams with not centered orbits
Run:
10 GeV polarized electrons on 100 GeV Au
Physics:
Saturation & Structure of Nuclei
(nPDF & nFF)
Run:
10 GeV electrons on 166 GeV transverse and longitudinal polarized He-3
Physics:
flavor dependent spatial and dynamical structure of QCD
flavor dependent spin structure of the nucleon
Full EIC Capabilities – Mission Need
High Luminosity: L= 1033 – 1034cm-2sec-1
Highly Polarized Beams: 70%
Large Center of Mass Energy Range: Ecm ~ 30 – 140 GeV
Large Ion Species Range: protons – Uranium
Large Detector Acceptance and Good Background Conditions
Possibility to implement a Second Interaction Region (IR)
Similar as you have seen but added the mission need checkmarks at year-6

## Slide 13: ePIC (Central) Detector
We have been checking the software versus engineering “CAD” (no large differences found).
We have a new beam pipe design that now has all ports, beam position monitors, gate valves included, all the way through B0 (it is overall similar to what we had) – we will add stp files.
We are updating the detector envelopes with as our goal end of February
Some (“known”) changes due to:
  Alignment of engagement rings that shift some detectors.
  Radially shifting hpDIRC/outer GEM-muRwell up to 1,.5 cm.
  About 4” areas at end of detector with more clearance to beam pipe (affects fHCAL insert electronics area, e-direction flux return steel)
  Likely a few cm shift of hpDIRC away from dRICH.

## Slide 14: Detector Reviews planned for 2025: Path to CD-2 Readiness
Preliminary Design Reviews (60% design maturity equivalent, called PDR, PDR2 or PDR3, pending the subsystem)
  PDR2: MPGD Tracking Detectors (6.10.03.02) – Summer 2025 – exact timing linked to progress on first engineering test articles
  PDR2: Silicon Tracking Detectors (6.10.03.01) – Fall 2025 – After early results of ITS3 ER2
  PDR2: Cherenkov-based Particle Identification Detectors (6.10.04; pfRICH, hpDIRC, dRICH) – April 1-2, 2025
  PDR2: AC-LGAD-based Particle Identification Detectors (6.10.04; BTOF, FTOF, common systems) – Fall 2025
  PDR3: Barrel EM Cal (6.10.05.02) – ~August 2025
  PDR2: Backward HCAL (6.10.06.01) – ~September 2025
  PDR: Magnet Cryogenics and infrastructure (6.10.07) – September/October 2025
  PDR3: Electronics/DAQ-computing (6.10.08. 6.10.09.01) – Late August 2025 – this does not include slow controls
  PDR: DAQ-Slow Controls (6.10.09.02) – November/December 2025 – Later to ensure integration DAQ in the collider common platform
  PDR: Integration, Infrastructure and Installation (6.10.10) – September/October – everything outside GST, includes cradle, HCAL, etc.
  PDR: Integration, Infrastructure and Installation (6.10.10) – November/December 2025 – everything inside GST
  PDR3: IR Integration and Auxiliary Detectors (6.10.11) – November/December 2025 – includes 6.10.14 lumi detector
  PDR2: Polarimetry (6.10.014) – September/October 2025
Final Design Reviews (FDR):
  FDR: Backward & Forward EM Calorimetry, Barrel & Forward HCAL (6.10.05.01; 6.10.05.03; 6.10.06.02; 6.10.06.03) – May 2025
Project Reviews:
  OPA CD-3B Review – January 7-9, 2025
  OPA Project Status Review – Summer 2025 (~6 months after CD-3B Review) – expectation: late July/early August
Other Meetings:
  Detector R&D Day hosted by ePIC and EIC Project: ~April 2025?
  DAC Meeting – Comprehensive look to design status and readiness for CD-2: 3 days to split topics. June 11-13 @ BNL.
  5th RRB Meeting: June 5-6, 2025 – Prague, Czech
  EIC International Computing Organization (EICO) is planning to meet on April 2–4, 2025 @BNL
  ePIC Software & Computing review by host labs: ~April/May 2025 for status check?

## Slide 15: 10th DAC Meeting, June 11-13, 2025
Day One – General Status Update, June 11, 2025
(This DAC meeting is in person at BNL on three consecutive days, with a remote closeout about a week later. We will be able to accommodate remote participation for exceptions.)
(Draft) Agenda
(Eastern Daylight Savings Time)
08:30 – 09:00 DAC Executive Session
09:00 – 09:30 EIC Status and Plans – Jim Yeck
09:30 – 10:10 ePIC Collaboration: Status, Plans, Responsibilities, Capabilities – John/Silvia
10:10 – 11:00 ePIC Technical Baseline and Agreements Status – Elke/Rolf
11:00 – 11:30 Break
11:30 – 12:00 ePIC Electronics – Fernando Barbosa
12:00 – 12:30 ePIC DAQ/Computing – David Abbott, Jeff Landgraf
12:30 – 13:00 ePIC Magnet Status – CAM
13:00 – 14:00 Lunch Break
14:00 – 14:40 ePIC Detector Integration, Infrastructure and Installation – Rahul Sharma
14:40 – 15:10 Electron and Hadron Polarimetry – CAM
15:10 – 15:40 Accelerator and Detector Commissioning Plan – Elke
15:40 – 16:00 Break
16:00 – 17:30 DAC Executive Session

## Slide 16: 10th DAC Meeting, June 11-13, 2025
Day Two – Tracking and Particle Identification, June 12, 2025
(Draft) Agenda
(Eastern Daylight Savings Time)
08:30 – 09:00 Follow-up on DAC Questions
09:00 – 09:30 EIC Tracking and Particle Identification Requirements
09:30 – 10:30 ePIC Silicon Vertex Tracker Status – DSC/CAM
10:30 – 11:10 ePIC MPGD Tracker Status – DSC/CAM
11:10 – 11:30 Break
11:30 – 12:00 ePIC proximity-focusing RICH Status – DSC/CAM
12:00 – 12:30 ePIC dual RICH Status – DSC/CAM
12:30 – 13:00 ePIC high-performance DIRC Status – DSC/CAM
13:00 – 14:00 Lunch Break
14:00 – 15:00 ePIC AC-LGAD/TOF Detector Status – DSC/CAM
15:00 – 17:30 DAC Executive Session
CAMs will reach out to the DSCs to discuss the best plan to present

## Slide 17: 10th DAC Meeting, June 11-13, 2025
Day Three – Calorimetry and Ancillary Detectors, June 13, 2025
(Draft) Agenda
(Eastern Daylight Savings Time)
08:30 – 09:00 Follow-up on DAC Questions
09:00 – 09:30 EIC Calorimetry and Ancillary Detectors Requirements
09:30 – 10:30 ePIC Ancillary Detectors – DSC/CAM
10:30 – 11:00 ePIC Backward EM calorimeter (EEEMCAL) status – DSC/CAM
11:00 – 11:30 Break
11:30 – 12:00 ePIC Forward EM calorimeter status – DSC/CAM
11:00 – 12:30 ePIC Barrel EM calorimeter (BIC) status – DSC/CAM
12:30 – 13:10 ePIC Forward Hadron Calorimeter & Insert – DSC/CAM
13:10 – 14:10 Lunch Break
14:10 – 14:40 ePIC Barrel Hadron Calorimeter – DSC/CAM
14:40 – 15:00 ePIC Backward Hadron Calorimeter – DSC/CAM
15:00 – 17:30 DAC Executive Session
Closeout (remote), day roughly a week later, June ??, 2025
09:00 – 10:00 Closeout
CAMs will reach out to the DSCs to discuss the best plan to present
Likely Far-Backward (lumi + low-Q2) and Far-Forward talk

## Slide 18: International Engagement: Resource Review Board (RRB) Meetings
https://www.bnl.gov/eic-rrbmeeting/
1st RRB meeting on April 3-4, 2023 at Stony Brook University.
2nd RRB meeting on December 7 + 8, 2023 at Catholic University of America.
3rd RRB meeting on May 6 + 7, 2024 in Rome hosted by INFN/Italy.
4th RRB meeting on November 12 + 13, 2024 at BNL.
5th RRB meeting will be June 5 + 6, 2025 in Prague/CZ.
Future meetings: 1st week of May & 1st week of November
DOE and the host labs promoting the EIC as a facility “fully international in character.”
Initial RRB Co-Chairs:
Haiyan Gao (BNL) – (Now: Abhay Deshpande)
Diego Bettoni (INFN)

## Slide 19: Outlook to CD-2 – In-Kind Contributions (IKC)
The IKC target for the EIC detector is about 30% of the total scope approx. $100M.
The preparations of ICRADAs – First phase – has completed
The preparations of ICRADAs – Second phase – has started
Agency | Scope | Status
Italy-INFN | Detector (dRICH, Si/ITS3, GEM-muRwell) | Finalizing ICRADA details
UK-STFC | Si-LAS, Low-Q2, Lumi) | Finalizing ICRADA details
France-CEA | MicroMegas, SALSA | Confirmed within CEA, ministry proposal ongoing
France-IN2P3 | EEEmCAL, RPs, ASICs | Confirmed within IJCLab/OMEGA, ministry proposal ongoing
Italy-INFN | Solenoid | Finalizing ICRADA details
France-CEA | Solenoid | Finalizing ICRADA details
Agency | Scope | Status
Korea-MSIT | Barrel EMCal, muRwell-ECT, TOF/ZDC collab. | Draft ICRADA exists, MSIT proposal in final stages
Japan-MEXT | Barrel TOF, streaming DAQ, ZDC | Draft ICRADA exists, MEXT proposal in final stages
Canada-CFI | Barrel EMCal readout, software | Draft ICRADA exists, CFI proposal submitted
Israel | B0 detectors | Plan to submit proposal this April, then start draft ICRADA
India | Forward EMCal, forward TOF, dRICH collab. | Plan to submit proposal this Summer
Taiwan | AC-LGAD sensors, PWO/LYSO | Pending success of Taiwan to produce sensors, prototype tests
Other? |  | 
Status: folding in
Reuse of components enabled by explicit design (e.g., barrel HCal, cradle, DIRC bars, ….)
In-kind contributions to PED
Likely IKC
  UK detector (UKRI/STFC)
  Italy/INFN detector
  Italy/INFN magnet
  CEA/IN2P3 detector
Possible IKC
  Japan detector
  Korea detector
  Canada detector
  Taiwan detector
  NSF/MSRI
we would surpass this $100M goal.
This is coded in P6 in anticipation of further proposal confirmations and the signed formal agreements.

## Slide 21: Reference Schedule
Plans for CD-2 and CD-3 originally aligned with conclusion of RHIC.
Critical Path is Accelerator Systems
RHIC Operations is planned for the end of CY2025
Science operations start in roughly a decade