## Slide 1
LCLS-II SRF commissioning and early operational experience
Sebastian Aderhold, SC Linac Physics Department Head
December 5, 2024

## Slide 2: Outline
Facility Overview
Cryogenic system & Cooldown
SRF commissioning
Operational experience
Outlook & Summary

## Slide 3
LCLS-II
New Injector and
New Superconducting Linac
Existing Bypass Line
New Transport Line
Two New Undulators
And X-Ray Transport
Reconfigure Near Experiment Hall
New Cryoplant
Remove SLAC Linac from Sectors 0-10
LCLS-II design features:
CW VHF gun
CW SRF linac
Support MHz-rate
Two undulator lines
Pulsed magnetic kicker
Long (2km) bypass line
Machine protection and beam loss control

## Slide 4: LCLS FEL complex based on normal and superconducting Accelerators
Superconducting Linac
4 GeV, High
rep-rate, CW RF
Normal Conducting Linac
3.5-17 GeV,
120 Hz Pulsed RF
Soft and Hard X-ray
Variable Gap
Undulators (VGUs)
3 km
Linac gallery and new cryoplant viewed from Sector 0
Future 8 GeV extension
(LCLS-II-HE)

## Slide 5: LCLS-II Key Performance Parameters - KPPs
Performance Measure | Threshold (5 kW beam) | Objective (120 kW beam) | Measurements
Variable gap undulators | 2 (soft and hard x‑ray) | 2 (soft and hard x‑ray) | 
Superconducting linac-based FEL system |  |  | 
Superconducting linac electron beam energy | 3.5 GeV | ≥ 4 GeV | Spectrometer bend (magnet strength, screen)
Electron bunch repetition rate | 93 kHz | 929 kHz | BPM’s, laser rate
Superconducting linac charge per bunch | 0.02 nC | 0.1 nC | Toroid, Faraday cup
Photon beam energy range | 250–3,800 eV | 200–5,000 eV | Absorption edges, spectrometer
High repetition rate capable end stations | ≥ 1 | ≥ 2 | N/A
FEL photon quantity (10-3 BW) per bunch | 5x108 (10x spontaneous) @2,500 eV | > 1011 @ 3,800 eV | Gas energy monitor, GMD, Spectrometer
Normal conducting linac-based system |  |  | 
Normal conducting linac electron beam energy | 13.6 GeV | 15 GeV | Spectrometer bend (magnet strength, screen)
Electron bunch repetition rate | 120 Hz | 120 Hz | BPM’s, laser rate
Normal conducting linac charge per bunch | 0.1 nC | 0.25 nC | Toroid, Faraday cup
Photon beam energy range | 1–15 keV | 1–25k eV | Absorption edges, spectrometer
Low repetition rate capable end stations | ≥ 2 | ≥ 3 | N/A
FEL photon quantity (10-3 BWa) per bunch | 1010 (lasing @ 15 keV) | > 1012 @ 15 keV | Gas energy monitor, GMD, Spectrometer

## Slide 6: Outline
Facility Overview
Cryogenic system & Cooldown
SRF commissioning
Operational experience
Outlook & Summary

## Slide 7
Plan to fully commission and operate LCLS-II with 1 of 2 installed cryoplants

## Slide 8: Cryoplant Commissioning Process
~ 30 Months
10 mths
4 mths
3 mths
7 mths
2.5 mths
3 mths
1.5 mths
UTILITIES
Electricity
Control Network
Water
Air
Nitrogen
Helium
AUXILIARIES
Recovery compressor
Gas Analyzer
Purifier
COMPRESSORS
4K Cold Box
LINAC Ready
LINAC @ 2 K
2 K Pump Down
LINAC @ 4 K
Cool Down
Aug. 15th 2019
Dec. 15th 2019
Mar. 15th 2020
Jan. 15th 2021
Oct. 15th 2021
Jan. 1st 2022
Mar. 30th 2022
May 15th 2022

## Slide 9: Cool Down & Pump Down to 2 K
Cool down of the entire linac was completed in ~5 days!
A rate of 2-3 K/hour was maintained over that duration
Cool down was near-fully automated by the cryogenic controls system
After multiple attempts, stable operation at 2 K was achieved only 11 days later
2-3 K/hr
Cavity Temperatures During Cool Down

## Slide 10: Outline
Facility Overview
Cryogenic system & Cooldown
SRF commissioning
Operational experience
Outlook & Summary

## Slide 11: SRF Commissioning
SRF commissioning was very successful
97% of all cavities fully operational (planned for 94%)
Total commissioned (summed individual cavity) voltage exceeded design by >20% and reached 4.8GV
No significant change in field emission observed with respect to cryomodule acceptance tests at partner labs
Gradient Performance

## Slide 12: Gradient Performance
Gradient performance is in line with CM acceptance test measurements at FNAL and Jlab
No observable change in field emission onsets or magnitude from installation
Multipacting processing resulted in ~3 MV/m gain in stable gradient
Admin limits:
18 MV/m in commissioning
21 MV/m in acceptance test
Comparison with Acceptance Test
Change in FE Onset

## Slide 13: Undulator and FEL commissioning
First lasing with SC-linac beam, SXR line, 8/23/2023; HXR line, 9/6/2023
SXR undulator
HXR undulator
Beam-based alignment with Cu-linac beam;
E-beam transverse and longitudinal optimization;
Beam loss control; Undulator tapering;
GMD, spectrometer, XTCAV measurement.
XTCAV and XTCAVB to support commissioning

## Slide 14: Beam Repetition Rate
Achieved 10 kHz beam rate on 12/9/2022.
Achieved 93 kHz (6/7/2023)
   Project Threshold Milestone
Initial science program operates at 8.25 kHz.
While ramping up the beam rate:
  Diagnostic devices response
  Feedback system response
  Machine protection system
  Beam loss monitor display
  Beam dump and cooling water temperature response
  Verify actual beam rate with Toroid or BPM BSA data
10kHz
93kHz

## Slide 15: Outline
Facility Overview
Cryogenic system & Cooldown
SRF commissioning
Operational experience
Outlook & Summary

## Slide 16: Beam Stability
With the 3rd cathode
Design jitter specs (rms):
charge jitter: 1.5%,
energy jitter: 1e-4,
peak current jitter: 4%,
arrival time jitter: 20 fs.
6/23/2024
65pC, 8kHz, 530eV: operation data in 4 hours

## Slide 17: Cavity availability
After initial commissioning only 3% of cavities non-operational (problems inside the CM that need room temperature warm-up)
No additional cavities with problems inside cryomodule since then
All new problems related to LLRF system, cables/connections or SSAs
Individual Solid State Amplifiers allow to take single cavities with intermittent problems offline for maintenance
Generally enough amplitude overhead to compensate for cavities being repaired while the linac is running or during maintenance periods

## Slide 18: Offline cavities over time
During operation cavities with problems are taken offline to be fixed later.
Repair during maintenance periods or parasitically (if possible)
9 cavities (3%) offline due to long term issues
  power coupler: 2x
  Tuner (stepper/piezo/limit switch): 7x
  Will require linac warm-up
Remaining cavities mostly RF-system related

## Slide 19: Cryogenic system is very robust
Electric heaters on underside of cavity helium vessels to compensate for change in RF heatload
Control loop regulates linac helium pressure by adjusting electric heaters to keep return pressure to cold compressors stable
Even in cases of sudden loss of all RF heat [e.g. shut-off by Personal Protection System (PPS)] feedback keeps cold compressors stable and recovers pressure within minutes

## Slide 20: Software development and automation
Auto Setup GUI
Push-button tool for initial set-up or to address cavities that have become unstable
Building heavily on software framework developed for and since initial linac commissioning
Simplified interface on top of expert screens for ease of operator use
  Automated sequence of steps, some level of error handling and checking if values are within set boundaries
Start of the whole linac (e.g. after maintenance days) CM by CM within 30min - 1h, depending on number of parallel instances
Recent infrastructure improvement cut down to less than 5min, true single button

## Slide 21: Microphonics
Overall microphonics levels are very good
  94% of cavities within specification of +/-10Hz
Only two cavities are currently amplitude limited due to microphonics
Biggest source of excessive microphonics are cooldown valve leaks
More details by R. Porter at SRF2023: MOPMB081

## Slide 22: L3 insulating vacuum
Upstream linac section
L3 string is separated into section upstream and downstream of insulating vacuum break
L3 upstream string exhibits higher than expected static heatload and increased insulating vacuum pressure
  Suspect leak from helium process pipe into insulating vacuum space
  Partially mitigated by doubled pump capacity
 | EXPECTED CM STATIC | OBSERVED CM STATIC (Initial) | OBSERVED CM STATIC (with Additional Pump)
LO-L2 | 9 W / CM  150 W | 9 W / CM  150 W | 9 W / CM  150 W
L3-UPSTREAM | 9 W / CM  90 W | 47 W / CM  470 W | 17 W / CM  170 W
L3-DOWNSTREAM | 9 W / CM  90 W | 16 W / CM  160 W | 16 W / CM  160 W
TOTAL CM STATIC | 330 W | 800 W | 500 W
Added Pumps

## Slide 23: L3 insulating vacuum
Downstream section
L3 downstream string insulating vacuum pressure has oscillating behavior
  Oscillation period is dependent on whether RF is on (~1.5h) or off (~3h)
  Global heater feedback reacts in response to change in static heatload
  Suspect leak in cooldown line of one of the later CMs (~CM33-34)
  Most notable consequence is HOM couplers on some cavities to start (over-) heating
    Decreased cavity amplitudes slightly to accommodate

## Slide 24: New Field Emission in CM01
CM01 has specific cavity amplitude requirements for optimal injector performance and linac beam quality
  Cryomodule with high max amplitudes and without field emission was chosen for this location
  For best emittance preservation cavity 1 runs at low amplitude (6.5MV) and cavity 2 is chosen to be off
Prompted by unexplained high signals on beam loss monitors in injector moved radiation monitors next to CM01 and re-characterized field emission
  Found field emission in cavities 2, 3, 4, 5
No specific events in beamline vacuum that would explain particle migration or gas bursts

## Slide 25: CM01: Path forward
Will keep monitoring field emission levels in CM01 on a regular basis
Started re-characterization campaign for all other CMs (moving one set of sensors every maintenance period)
Assessing impact on injector performance
  Just at the lower edge of required energy for laser heater operation while keeping cavities below 50mR/hr when turning on cavity 2
  Seems feasible as long as FE does not get worse
Looking for mechanisms that would explain pattern with highest radiation in the middle of the CM
Long term solutions (both would need room temperature warm-up and significant work):
  Replace cryomodule with spare
  Perform in-situ plasma processing

## Slide 26: Change in cavity amplitude limits due to Field Emission (FE)
Total amplitude lost over whole linac: 47.4 MV
Total cavities in linac | 296
Cavities re-characterized for FE | 192 (65%)
Cavities with change in FE characteristics | 15 (5%)
Number of affected CMs | 9 (out of 23 re-characterized)
Cavities where the change impacts operational setpoint | 8 (3%)
Chart: Change in cavity amplitude limits
| CM01-2 | CM01-3 | CM01-4 | CM01-5 | CM01-8 | CM08-4 | CM10-5 | CM10-6 | CM20-8 | CM28-6 | CM30-1 | CM30-2 | CM32-8 | CM33-7 | CM35-8
after FE onset | 15.6 | 10.9 | 5 | 12.3 | 16.6 | 16.6 | 12.3 | 16.6 | 16.6 | 16.6 | 10.5 | 12.5 | 16.3 | 8.3 | 6.5
before FE onset | 1 | 5.7 | 11.6 | 4.3 | 0 | 0 | 4.1 | 0 | 0 | 0 | 1.5 | 0.5 | 0.3 | 8.3 | 10.1

## Slide 27: Multipacting processing
Repeated cavity quenches at increasing gradients
  “scrubbing” the inner cavity surface
  Redistribution of adsorbed gases, lowering the secondary electron emission yield
  Typically accompanied by a short x-ray burst
  Persistent effect until next room temperature cycle of the linac
Goal:
  Gain more available amplitude towards 4GeV (and eventually 4.3GeV) operation of the SC linac

## Slide 28: Timeline and process
Completed 8 dedicated shifts over the last two weeks
Working on two cryomodules in parallel, one cavity at a time
47 cavities in 7 cryomodules in L3B were processed
  ~2-3h per cavity
    Initial estimate was 4h
Start at 16.6MV ramping amplitude up to 21.8MV in small steps
  When reaching 21.8MV, or other maximum amplitude below that, run for ~30min
Majority of cavities reached 21.8MV
  Some “hard quenches” at lower gradients

## Slide 29: MP processing gains
209.1MV total gain
  When considering up to 21.8MV max amplitude
96.8MV total gain
  When considering up to 18.7MV max amplitude
  Taking into account operational constraints (RF overhead, stability,…)

## Slide 30: Outline
Facility Overview
Cryogenic system & Cooldown
SRF commissioning
Operational experience
Outlook & Summary

## Slide 31: Ramp-up Plan for 500 kHz FEL Operation – 120 kW Limit
Current beam power limit is 5 kW (safety system limitation)
Ramp – up to full performance is governed by safety system functionality, RP surveys, beam loss minimization.
Process to achieve KPP’s will take 2-3 (+) years and will be integrated into user program.
Repetition Rate and Bunch charge can be traded to maintain a specific beam power.
Chart: 500 kHz FEL Operation (max)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
FEL Rep Rate (kHz) | 0.12 | 1 | 10 | 25 | 25 | 50 | 50 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 375 | 375 | 375 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500
Charge (pC) | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 31.25 | 25 | 25 | 25 | 50 | 50 | 48 | 48 | 48 | 52 | 52 | 52 | 54.25 | 54.25 | 54.25 | 54.25 | 57.6 | 57.6 | 57 | 58.816 | 58.816 | 58.816 | 58.816 | 58.816 | 58.816
2-3 (++) years to objective KPPs
Ramp-up is governed by beam power considerations, management of beam losses.

## Slide 32: Summary
LCLS-II SRF commissioning has been a successfully completed and threshold key performance parameters have been met
Early operations of SRF systems are going well (beam stability, microphonics, cavity availability) with some issues (new field emission in CM01, insulating vacuum in L3 string)
Next year will be spent delivering beam to users in parallel to further beam performance improvement and beam power ramp up
Getting ready of LCLS-II-HE installation